## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01/07/2017 - 30/06/2018
| Project Title: | TF 015041 - INCREASING CLIMATE RESILIENCE AND ENHANCING SUSTAINABLE LAND MANAGEMENT IN THE SOUTHWEST OF THE BUENOS AIRES PROVINCE
| Project Summary: | The Project Development Objective (PDO) is to contribute to reducing climate and man-made vulnerability of the agro-ecosystems in the Southwest of the Buenos Aires Province (SWBA) by increasing the adaptive capacity of key local institutions and actors and piloting and disseminating climate resilient and sustainable land management practices. Participatory planning processes were used to identify and are used to pilot concrete adaptation measures focusing on water, crops and livestock management to promote climate resilience. The Project benefits farmers and families engaged in small and medium-sized agricultural-cattle production on dry lands within the direct and indirect intervention zones; the counties of Puan, Villarino and Patagones; and 9 further SWBA counties, respectively. Additionally, a wide range of current and potential partner organizations working on related aspects within the area and up to national level benefit from and contribute to a comprehensive set of capacity building and institutional strengthening measures. A continued inter-sectoral learning process, through which the Project evolves supported by cross-institutional work, aims at (1) creating an enabling political, social, and economic framework to facilitate adoption, sustainability, scale-up and further development of the piloted adaptation efforts; and (2) bolstering and fine-tuning the adaptation measures identified and chosen for implementation through institutional and community-level participation and capacity building. After a serious delay to get the Project initially effective and operational, since early 2016 the Project has shown steady progress and presents Satisfactory results on the ground. It benefits of a strong ownership both by the direct beneficiaries and the responsible agencies at the national and local level, and the targets of the PDO indicators are achieved or achievable by the original closing date on December 30, 2018. There is certain disconnect between progress against indicators and the level of disbursements, taken (i) 2/3 of the PDO indicators focus on non-material aspects as institutional commitment and inter-institutional collaboration e.g. on running the Information and Early-Warning System (IEWS), and (ii) lack of an intermediate results indicator that would reflect execution of the funds under Component 2 on concrete adaptation pilots that owns the bulk of the Project budget. By the end of June 2018, the disbursement rate reached 71%. On the downside, the Project has proved of high transaction cost as it needs to comply with three sets of differing reporting formats and operational procedures; those of the Government, the World Bank (WB), and the Adaptation Fund (AF). During the reporting period, the three parties agreed upon a Project closing date extension until September 30, 2018 to enable sufficient time for consolidation of physical results on the ground and systematizing and disseminating of the main Project results that have a great potential for replication and scale-up.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ARG/MIE/Rural/2011/1 - P125804 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | The World Bank | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Argentina | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Counties of Patagones, Villarino and Puan - Buenos Aires Province, Argentina | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 14-Dic-2012
IE-AFB Agreement Signature Date: |  | 2013-02-25 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June, 2015 (Inception Workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | April, 2017 (Actual)
| Terminal Evaluation Date: | 6/30/2019 (Original)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Brochure of the Project (Description)/ Brochure on Resilience and Sustainable Land Management for the intervention area/ Multi-proposal poster for teaching at local schools and capacity building for local agents, opinion leaders and farmers, chapter in the publication "Economics of Land Degradation and Improvement – A Global Assessment for Sustainable Development" edited by the Economics of Land Degradation Initiative of the UNCCD, available at http://link.springer.com/book/10.1007/978-3-319-19168-3. Stories in the Adaptation Fund website, available at https://www.adaptation-fund.org/world-bank-adapting-climate-variability-transition-zone-pampa-patagonia-argentina/; https://www.adaptation-fund.org/argentina-gabriel-demarchi/; https://www.adaptation-fund.org/argentina-roberto-miller/; and https://www.adaptation-fund.org/argentina-mateo-perez-anses-justo/. Videos published by the World Bank, available at https://videos.tube/video/2927hNZK3Vo/forestacin-sudoeste-de-la-provincia-de-buenos-aires; https://www.youtube.com/watch?reload=9&v=26fz-EIpNEc; and https://www.youtube.com/watch?v=qWm-xchMNFU; and more than 242 media articles. Further, the Project features at the National Observatory of Land and Desertification http://www.desertificacion.gob.ar/wp-content/uploads/2018/01/Centro-BA.Cdoba.CABA/Centro-BA-Patagones-Ganader%C3%ADa%20sustentable%20en%20el%20Partido%20de%20Patagones-16.pdf. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.argentina.gob.ar/ambiente/tierra/bosques-suelos/manejo-sustentable-suelo/sudoesteba http://projects.worldbank.org/P125804/adaptation-fund-increasing-climate-resilience-enhancing-sustainable-land-management-southwest-buenos-aires-province?lang=en&tab=overview | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | National Director Dolores Duverges - Argentina's Ministry of Environment and Sustainable Development | Dominican Republic
| Email: | dduverges@ambiente.gob.ar | Ecuador
| Date: | June, 2018 | Egypt
| Government DA |  | El Salvador
| Name: | Secretary Diego Moreno - Argentina's Ministry of Environment and Sustainable Development | Equatoral Guinea
| Email: | dmoreno@ambiente.gob.ar | Eritrea
| Date: | June, 2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Environmental Specialist, Task Team Leader Tuuli Bernardini - The World Bank | Fiji
| Email: | tbernardini@worldbank.org | Finland
| Date: | June, 2018 | France
| Executing Agency |  | Gambia
| Name: | Coordinator Joaquin Etorena - Argentina's Ministry of Environment and Sustainable Development | Georgia
| Email: | jetorena@ambiente.gob.ar | Germany
| Date: | June, 2018 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to June 30th, 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of June 30, 2018 | 2807890
Add any comments on AF Grant Funds. (word limit=200) | USD 2,307,890.48 have been documented to the WB. As of June 28, 2018, a new disbursement of USD 442,931.97 was requested.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| COMPONENT 1 - Reducing Institutional and Community-level Vulnerability | 201586.74
| 1.1.1.1 Information and early-warning system for droughts, land degradation and desertification control | 175105.05
| 1.1.1.2 Regional Consultative Observatory of Public Policies on Climate Change and Desertification to mainstream climate change adaptation | 0
| 1.1.1.3 Institutional capacity building program directed at local public officers | 4916.77
| 1.2.1.1 Training program on climate change and different adaptation options for disseminators | 2194.97
| 1.2.1.2 Training program for rural school teachers to mainstream environmental factors, climate change and approaches to climate resilience into the curriculum | 7746.38
| 1.2.1.3 A gender-sensitive program to empower farmers and their families and strengthen their social role for sustainable development | 11623.57
| COMPONENT 2 - Implementing Adaptation Measures in Productive Agroecosystems | 1358595.62
| 2.1.1.1 Water Resources Management: Installation of microsystems for irrigation and rainwater harvesting | 121177.18
| 2.1.1.2 Crop Management: Implementation of crop rotation systems, diversification, time alteration of sowing, and organic agriculture in demonstration sites | 891967.28
| 2.1.1.3 Livestock and Pasture Management: Implementation of adaptation measures such as forage banks, silvopastorile systems, rangeland recovery and sustainable plot management | 295940.96
| 2.1.1.4 Participatory development of Good Agricultural Practices (GAPs) aimed at enhancing management plans for production and adoption of a voluntary code of climate resilient GAP. Based on results of further stakeholder consultations, identification of alternative livelihood options and ways to facilitate their adoption | 49510.2
| COMPONENT 3 - Applying Participatory Approach to Knowledge Management and local capacity - development for adaptation to climate change | 47684.93
| 3.1.1.1 Combined consultation, coordination, training, and knowledge sharing at the local level in the three counties of direct Project intervention to develop and validate intervention proposals and work plans | 20161.33
| 3.1.1.2 Capacity building for indicator development and measurement plans, systems of continuous improvement, training for local application groups, and mutual knowledge sharing in terms of the proposed activities between and beyond the counties | 23401.28
| 3.1.1.3 Participatory development of progress information through development of periodic reports to make information available to all stakeholders | 3144.01
| 3.1.1.4 Training and knowledge management with stakeholders through joint demonstrative field visits | 978.31
| COMPONENT 4 - Development a Sustainability Strategy | 30854.35
| 4.1.1.1 A representative Working Committee for the Project’s intervention area comprised by the regional Observatory with institutional capacity to maintain the IEWS and committed to provide information to the national and provincial | 6358.71
| 4.1.1.2 A compilation and publication of standard-formatted set of evaluation and tracking tools (specific reports on key issues) | 1344.15
| 4.1.1.3 A compilation and review of domestic and international sources of finance to secure continuity of the key Project activities | 3245.2
| 4.1.1.4 Knowledge sharing on progress evaluation with involved stakeholders and publication and dissemination of lessons learned | 3669.3
| 4.1.1.5 Implementation of a program for dissemination and exchange of experiences from the local to the international | 16236.99
| Project (executing) Unit (PIU) | 67270.3
| TOTAL | 1705991.94
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| COMPONENT 1 | 342057.77
| 1.1.1.1 Information and early-warning system for droughts, land degradation and desertification control | 323663.69 | 2019-09-01
| 1.1.1.2 Regional Consultative Observatory of Public Policies on Climate Change and Desertification to mainstream climate change adaptation | 0 | 2019-09-01
| 1.1.1.3 Institutional capacity building program directed at local public officers | 0 | 2019-09-01
| 1.2.1.1 Training program on climate change and different adaptation options for disseminators | 12570.21 | 2019-09-01
| 1.2.1.2 Training program for rural school teachers to mainstream environmental factors, climate change and approaches to climate resilience into the curriculum | 4803.28 | 2019-09-01
| 1.2.1.3 A gender-sensitive program to empower farmers and their families and strengthen their social role for sustainable development | 1020.59 | 2019-09-01
| COMPONENT 2 | 468730.25
| 2.1.1.1 Water Resources Management: Installation of microsystems for irrigation and rainwater harvesting | 86396.49 | 2019-09-01
| 2.1.1.2 Crop Management: Implementation of crop rotation systems, diversification, time alteration of sowing, and organic agriculture in demonstration sites | 142968.7 | 2019-09-01
| 2.1.1.3 Livestock and Pasture Management: Implementation of adaptation measures such as forage banks, silvopastorile systems, rangeland recovery and sustainable plot management | 239365.06 | 2019-09-01
| 2.1.1.4 Participatory development of Good Agricultural Practices (GAPs) aimed at enhancing management plans for production and adoption of a voluntary code of climate resilient GAP. Based on results of further stakeholder consultations, identification of alternative livelihood options and ways to facilitate their adoption | 0 | 2019-09-01
| COMPONENT 3 | 174792.63
| 3.1.1.1 Combined consultation, coordination, training, and knowledge sharing at the local level in the three counties of direct Project intervention to develop and validate intervention proposals and work plans | 112000 | 2019-09-01
| 3.1.1.2 Capacity building for indicator development and measurement plans, systems of continuous improvement, training for local application groups, and mutual knowledge sharing in terms of the proposed activities between and beyond the counties | 0 | 2019-09-01
| 3.1.1.3 Participatory development of progress information through development of periodic reports to make information available to all stakeholders | 37572.24 | 2019-09-01
| 3.1.1.4 Training and knowledge management with stakeholders through joint demonstrative field visits | 25220.39 | 2019-09-01
| COMPONENT 4 | 105368.14
| 4.1.1.1 A representative Working Committee for the Project’s intervention area comprised by the regional Observatory with institutional capacity to maintain the IEWS and committed to provide information to the national and provincial | 16999.74 | 2019-09-01
| 4.1.1.2 A compilation and publication of standard-formatted set of evaluation and tracking tools (specific reports on key issues) | 20726 | 2019-09-01
| 4.1.1.3 A compilation and review of domestic and international sources of finance to secure continuity of the key Project activities | 0 | 2019-09-01
| 4.1.1.4 Knowledge sharing on progress evaluation with involved stakeholders and publication and dissemination of lessons learned | 40000 | 2019-09-01
| 4.1.1.5 Implementation of a program for dissemination and exchange of experiences from the local to the international | 27642.4 | 2019-09-01
| PIU | 77659.61
| PIU | 77659.61 | 2019-09-01
| TOTAL | 1168608.4
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | USD 319,774 by the Ministry of Environment and Sustainable Development (MAyDS)
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Actual co-financing until June 30, 2018 includes in-kind, non-grant instruments and other types of co-financing for more than USD 1.4 million as follows: i) INTA staff time, transportation, use of laboratory and meteorological equipment, use of facilities, and conduction of studies and training; ii) UNS and CERZOS staff time, transportation, use of equipment and facilities, conduction of studies and use of the Naposta experimental field; iii) SMN staff time, use of meteorological equipment and servers, and conduction of studies; iv) municipal governments of Patagones, Villarino and Puan staff time, meeting and workshop arrangements, and running of plant nurseries; v) Spegazzini Agriculture School staff time and field work; vi) farmers' time and expenses, use of fields and agroforestry products; vii) Ministry of Social Development staff time and transportation; viii) Vialidad Nacional staff time and transportation; ix) OPDS staff time, transportation, training and meetings.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
| Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 30
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
| Contract Type | Agency / Contracted party | Contract Value/Amount (USD) (*) | Signature Date | Payment to Date | Remaining Balance
| Consultants' services | Paula Ramos | 4786.97 | 2017-09-29 | 4432.38 | 354.59
| Consultants' services | Pablo Sívori 2017 | 7237.88 | 2017-09-29 | 5625.66 | 1612.22
| Consultants' services | Ezequiel Gaspes 2018 | 29054.16 | 2018-01-01 | 7498.73 | 21555.43
| Consultants' services | Juan Corvalán 2018 | 27177.27 | 2018-01-01 | 9718.63 | 17458.64
| Consultants' services | Ricardo Rotsztein 2018 | 27177.27 | 2018-01-01 | 9084.8 | 18092.47
| Consultants' services | Anastasia Luciano 2018 | 3125.04 | 2018-01-01 | 2856.96 | 268.08
| Consultants' services | Pablo Sívori 2018 | 29054.16 | 2018-01-01 | 0 | 29054.16
| Consultants' services | Martin Testani 2018 | 25299.73 | 2018-01-01 | 7119.77 | 18179.96
| Consultants' services | Andres Buono 2018 | 23443.43 | 2018-01-01 | 6597.41 | 16846.02
| Consultants' services | Paula Ramos 2018 | 21565.9 | 2018-01-01 | 7209.04 | 14356.86
| Non-consulting services and works | Crearte Publicación de Avisos (20, 24 y 25 de septiembre) | 31509.68 | 2017-09-19 | 31194.58 | 315.1
| Non-consulting services and works | Berardi Publicación octubre 2017 | 20615.19 | 2017-10-20 | 20441.97 | 173.22
| Goods | Cientist | 3648.03 | 2017-08-30 | 3369.01 | 279.02
| Goods | Instrumentalia | 42920.25 | 2017-08-07 | 42608.73 | 311.52
| Goods | Instrumentos del Sur | 5631.9 | 2017-08-07 | 4489 | 1142.9
| Goods | Wekume Agro Servicios SRL | 3523.52 | 2017-12-04 | 3007.88 | 515.64
| Goods | Wekume Agro Servicios SRL | 4905.56 | 2017-12-04 | 4187.68 | 717.88
| Goods | El Fortín | 7260 | 2017-12-08 | 6722.22 | 537.78
| Goods | El Fortín | 37949.72 | 2017-11-03 | 35941.8 | 2007.92
| Goods | Bertotto Boglione | 11652.9 | 2017-11-14 | 10199.86 | 1453.04
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 30479 | 2017-08-08 | 22365.43 | 8113.57 | This contract covers 5 bids/lots.
| Goods | Abelardo Cuffia | 51121.88 | 2018-01-22 | 46485.78 | 4636.1
| Goods | Metalbert SRL | 23235.86 | 2018-02-19 | 17722.7 | 5513.16 | This contract covers 2 bids/lots.
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL | 25265.08 | 2018-02-19 | 24585.57 | 679.51
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL | 58913.17 | 2018-02-27 | 19060.84 | 39852.33 | This contract covers 4 bids/lots.
| Goods | Corvial S.A | 12158.18 | 2018-02-14 | 2284.26 | 9873.92
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL | 28473.85 | 2018-02-19 | 25828.36 | 2645.49
| Goods | Top West S.A | 77165.08 | 2017-12-05 | 66870.21 | 10294.87
| Goods | IVECAM | 57481.92 | 2017-12-06 | 49733.14 | 7748.78
| Goods | La Emancipación Coop. | 299693.14 | 2018-04-06 | 227129.25 | 72563.89 | This contract covers 2 bids/lots.
| Goods | Runco S.A. | 21989.28 | 2017-12-18 | 21604.31 | 384.97 | This contract covers 2 bids/lots.
| Goods | COMMIT IT | 23228.8 | 2017-12-19 | 20727 | 2501.8 | This contract covers 3 bids/lots.
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 87362.71 | 2017-07-27 | 85147.54 | 2215.17 | This contract covers 7 bids/lots.
| Goods | Eule Graphics | 10071.67 | 2017-11-20 | 6551 | 3520.67 | This contract covers 2 bids/lots.
| Goods | Riegos Pigue SRL | 137848.5 | 2017-08-07 | 99624.24 | 38224.26 | This contract covers 5 bids/lots.
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL | 4435.32 | 2017-07-29 | 4055 | 380.32
| Goods | Seedmech Latinoamérica | 163542 | 2018-02-24 | 114763.53 | 48778.47
| Goods | Mercobras | 76535.93 | 2018-02-14 | 20090.68 | 56445.25
| Goods | Semillas Argentinas | 33743.35 | 2018-03-27 | 32475.5 | 1267.85 | This contract covers 2 bids/lots.
| Goods | Wekume Agro Servicios SRL Agro Servicios SRL | 20833.29 | 2018-03-26 | 16069.06 | 4764.23 | This contract covers 2 bids/lots.
| Goods | La Emancipación Coop. | 6403.44 | 2018-04-19 | 0 | 6403.44
| Goods | Tekniplant | 3061.72 | 2017-07-19 | 2826.21 | 235.51
| Goods | Ferrimac S.A | 36571.12 | 2017-07-19 | 28866.57 | 7704.55
31 | (*) Exchange rate: US Dolar, seller, Banco Nación Divisas, at date of contract signature | [5 empty] | 31 signed contracts, out of which 11 contracts cover more than 1 bid/lot as commented above; a total of 56 bids/lots.
BIDS
List all bids for each contract signed with date of open call and winning bid
| CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD)(*) | Winning Bid Amount (USD)(*) | Selection Justification for the Winner
| Shopping PIRCMGS-75-CP-B Acquisition of Minor Tools Lot 2, 28/11/2017 | Wekume Agro Servicios SRL | 3523.52 | 3523.52 | Lowest price fulfilling technical requirements
|  | Agro Luro | 3799.4
|  | El Galpón | 3872
| Shopping PIRCMGS-75-CP-B Acquisition of Minor Tools Lot 5, 28/11/2017 | Wekume Agro Servicios SRL | 4905.56 | 4905.56 | Lowest price fulfilling technical requirements
|  | El Galpón | 7261.42
|  | Agro Luro | 5211.81
| Shopping PIRCMGS-75-CP-B Acquisition of Minor Tools Lot 10, 28/11/2017 | El Fortín | 7260 | 7260 | Lowest price fulfilling technical requirements
|  | Agro Luro | 12134.57
|  | Wekume Agro Servicios SRL | 11135.09
|  | El Galpon | 14174.28
| Shopping PIRCMGS-94-CP-B Australian tanks, polyethylene tanks and drinking fountains Lot 1, 31/10/2017 | El Fortín | 37949.72 | 37949.72 | Lowest price fulfilling technical requirements
|  | Agua Piscinas | 82672.06
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 52861.45
| Shopping PIRCMGS-94-CP-B Australian tanks, polyethylene tanks and drinking fountains Lot 2, 31/10/2017 | Bertotto Boglione | 11652.9 | 11652.9 | Lowest price fulfilling technical requirements
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 23828.21
5 |  | El Fortín | 14905.3
| Shopping AR PIU MIN AMBIENTE 32771 GO RFQ System for mapping soil conductivity Lot 1, 27/12/2017 | Abelardo Cuffia | 51121.88 | 51121.88 | Only bidder, fulfilled technical requirements
| Shopping AR PIU MIN AMBIENTE 37365 GO RFQ Weeders and augers Lot 1, 28/12/2017 | Metalbert SRL | 2769.82 | 2769.82 | Lowest price fulfilling technical requirements
|  | María José Ibarrola | 3728.04
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 46090.09
|  | Agro Luro SRL | 4973.26
|  | Corvial S.A | 5721.92
| Shopping AR PIU MIN AMBIENTE 37365 GO RFQ Weeders and augers Lot 2, 28/12/2017 | Metalbert SRL | 20466.04 | 20466.04 | Lowest price fulfilling technical requirements
|  | María José Ibarrola | 18601.81 | Did not meet technical evaluation
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 25409.09
|  | Agro Luro SRL | 35631.81
|  | Corvial S.A | 25882.35
| Shopping AR PIU MIN AMBIENTE 37365 GO RFQ Weeders and augers Lot 3, 28/12/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 25265.08 | 25265.08 | Lowest price fulfilling technical requirements
|  | Corvial S.A | 24472.36 | Did not meet technical evaluation
|  | Agro Luro SRL | 23795.9 | Did not meet technical evaluation
|  | María José Ibarrola | 19647.72 | Did not meet technical evaluation
| Shopping AR PIU MIN AMBIENTE 37372 GO RFQ Seed Machines Lot 1, 28/12/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 4077.27 | 4077.27 | Lowest price fulfilling technical requirements
10 |  | Ferrimac S.A | 4875
| Shopping AR PIU MIN AMBIENTE 37372 GO RFQ Seed Machines Lot 2, 28/12/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 27418.18 | 27418.18 | Lowest price fulfilling technical requirements
|  | Ferrimac S.A | 30727
| Shopping AR PIU MIN AMBIENTE 37372 GO RFQ Seed Machines Lot 3, 28/12/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 13945.45 | 13945.45 | Lowest price fulfilling technical requirements
|  | Ferrimac S.A | 17727.27
| Shopping AR PIU MIN AMBIENTE 37372 GO RFQ Seed Machines Lot 4, 28/12/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 13472.27 | 13472.27 | Lowest price fulfilling technical requirements
|  | Ferrimac S.A | 15363.63
| Shopping AR PIU MIN AMBIENTE 37375 GO RFQ Dredge and Roller Grinder Lot 1, 27/12/2017 | Corvial S.A | 12158.18 | 12158.18 | Lowest price fulfilling technical requirements
|  | María José Ibarrola | 11883.96 | Did not meet technical evaluation
|  | Agro Luro SRL | 36258.26
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 16857.95
| Shopping AR PIU MIN AMBIENTE 37375 GO RFQ Dredge and Roller Grinder Lot 2, 27/12/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 28473.85 | 28473.85 | Lowest price fulfilling technical requirements
|  | Corvial S.A | 35589.38
15 |  | María José Ibarrola | 25073.9 | Did not meet technical evaluation
| AR PIRCMGS 129 LPN Pickup Trucks Lot 1, 26/10/2017 | Top West S.A | 77165.08 | 77165.08 | Lowest price fulfilling technical requirements
|  | Igarreta SACI | 84107.34
| AR PIU MIN AMBIENTE 26175 LPN Rural Machinery Lot 1, 26/10/2017 | IVECAM | 57481.92 | 57481.92 | Only bidder, fulfilled technical requirements
| AR PIU MIN AMBIENTE 35012 LPN Tractors Lot 1, 22/01/2018 | La Emancipación Coop. | 64887.89 | 64887.89 | Lowest price fulfilling technical requirements
|  | Agropecuaria Agromax | 125720
|  | Navarro S.A | 119614
|  | Corvial S.A | 89922.07
|  | Motortrac SRL | 93987.27
|  | Cosechar S.A | 136128
| AR PIU MIN AMBIENTE 35012 LPN Tractors Lot 2, 22/01/2018 | La Emancipación Coop. | 234805.25 | 234805.25 | Lowest price fulfilling technical requirements
|  | Agropecuaria Agromax | 344400
|  | Navarro S.A | 431909
|  | TVL S.A | 299064.93
|  | Corvial S.A | 281608
|  | Motortrac SRL | 322565.29
|  | Cosechar S.A | 392384
20 | AR PIRCMGS 136 LPN Computer equipment Lot 10, 24/10/2017 | Runco S.A. | 4031.58 | 4031.58 | Only bidder, fulfilled technical requirements
| AR PIRCMGS 136 LPN Computer equipment Lot 11, 24/10/2017 | Runco S.A. | 17957.7 | 17957.7 | Only bidder, fulfilled technical requirements
| AR PIRCMGS 136 LPN Computer equipment Lot 13, 24/10/2017 | COMMIT IT | 4154.8 | 4154.8 | Only bidder, fulfilled technical requirements
| AR PIRCMGS 136 LPN Computer equipment Lot 14, 24/10/2017 | COMMIT IT | 15470 | 15470 | Only bidder, fulfilled technical requirements
| AR PIRCMGS 136 LPN Computer equipment Lot 17, 24/10/2017 | COMMIT IT | 3604 | 3604 | Only bidder, fulfilled technical requirements
| Shopping AR PIRCMGS 116 CP Institutional Visibility Material Lot 2, 01/11/2017 | Eule Graphics | 2566.42 | 2566.42 | Lowest price fulfilling technical requirements
|  | Talleres Trama | 2710.8
25 |  | Arsa Gráfica | 3934.13
| Shopping AR PIRCMGS 116 CP Institutional Visibility Material Lot 4, 01/11/2017 | Eule Graphics | 7505.25 | 7505.25 | Only bidder fulfilling technical requirements
| AR PIRCMGS 81 LPN Meteorological Stations Lot 1, 06/11/2017 | Seedmech Latinoamérica | 163542 | 163542 | Lowest price fulfilling technical requirements
|  | Dastec | 507534.95
|  | Tracnova | 139330.8 | Did not meet technical evaluation
|  | American Consulting | 244539.88
| AR PIRCMGS 81 LPN Meteorological Stations Lot 2, 06/11/2017 | Mercobras | 76535.93 | 76535.93 | Lowest price fulfilling technical requirements
|  | American Consulting | 214103.37
|  | Dastec | 672054.95
|  | Tracnova | 64619.4 | Did not meet technical evaluation
| Shopping AR PIU MIN AMBIENTE 32774 CP Seeds Lot 1, 21/03/2018 | Semillas Argentinas | 27341.6 | 27341.6 | Lowest price fulfilling technical requirements
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 59890.98
|  | La Emancipación Coop. | 44157.25
|  | Peman Semillas | 41527.2
|  | Itaí Minuchín | 100956
| Shopping AR PIU MIN AMBIENTE 32774 CP Seeds Lot 2, 21/03/2018 | Wekume Agro Servicios SRL Agro Servicios SRL | 4270.82 | 4270.82 | Lowest price fulfilling technical requirements
|  | Semillas Argentinas | 4482
|  | Peman Semillas | 4991.25
30 |  | Itaí Minuchín | 17286.5
| Shopping AR PIU MIN AMBIENTE 32774 CP Seeds Lot 4, 21/03/2018 | Semillas Argentinas | 6401.75 | 6401.75 | Lowest price fulfilling technical requirements
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 5686 | Did not meet technical evaluation
|  | Peman Semillas | 4525.4 | Did not meet technical evaluation
|  | Itaí Minuchín | 7525
| Shopping AR PIU MIN AMBIENTE 32774 CP Seeds Lot 5, 21/03/2018 | Wekume Agro Servicios SRL Agro Servicios SRL | 16562.47 | 16562.47 | Lowest price fulfilling technical requirements
|  | Peman Semillas | 12687.74 | Did not meet technical evaluation
|  | Itaí Minuchín | 30430.4
| Shopping AR PIU MIN AMBIENTE 32774 CP Seeds Lot 7, 21/03/2018 | La Emancipación Coop. | 6403.44 | 6403.44 | Lowest price fulfilling technical requirements
|  | Wekume Agro Servicios SRL Agro Servicios SRL | 10714.91
|  | Semillas Argentinas | 6155.25 | Did not meet technical evaluation
|  | Peman Semillas | 6724.575
|  | Itaí Minuchín | 12642.5
| Shopping PIRCMGS-71-CP-B Laboratory Supplies Lot 13 31/05/2017 | Cientist | 3648.03 | 3648.03 | Lowest price fulfilling technical requirements |  |  | 325000 | 16.3
|  | Instrumentos del Sur | 9969 | [5 empty] | 19938.6503
|  | Instrumentalia | 19938
35 | Shopping PIRCMGS-71-CP-B Laboratory Supplies Lot 14 31/05/2017 | Instrumentalia | 42920.25 | 42920.25 | Only bidder, fulfilled technical requirements
| Shopping PIRCMGS-71-CP-B Laboratory Supplies Lot 18 31/05/2017 | Instrumentos del Sur | 5631.9 | 5631.9 | Only bidder, fulfilled technical requirements
| Shopping PIRCMGS-97-CP-B Elements and machinery for bee production Lot 11 05/06/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 7890.92 | 7890.92 | Lowest price fulfilling technical requirements at the end
|  | Distribuidora Apícola Vailoratti S.A | 3137.11 | Did not meet technical evaluation
|  | Inderco S.A | 7372.99 |  | Originally selected supplier rejected the award
| Shopping PIRCMGS-97-CP-B Elements and machinery for bee production Lote 1 05/06/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 2969.26 | 2969.26 | Lowest price fulfilling technical requirements
|  | Inderco S.A | 4925.04 | Supplier rejected the award
| Shopping PIRCMGS-97-CP-B Elements and machinery for bee production Lot 13 05/06/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 2969.26 | 2969.26 | Lowest price fulfilling technical requirements
|  | Implementos Marinari | 975.46 | Did not meet technical evaluation
|  | Inderco S.A | 3725.13
| Shopping PIRCMGS-97-CP-B Elements and machinery for bee production Lot 14 05/06/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 10168.71 | 10168.71 | Lowest price fulfilling technical requirements at the end
|  | Implementos Marinari | 6012.26 | Did not meet technical evaluation
40 |  | Inderco S.A | 6202.23 |  | Supplier rejected the award
| Shopping PIRCMGS-97-CP-B Elements and machinery for bee production Lot 16 05/06/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 6480.85 | 6480.85 | Lowest price fulfilling technical requirements at the end
|  | Distribuidora Apícola Vailoratti S.A | 6554.78
|  | Inderco S.A | 3541.42 |  | Supplier rejected the award
|  | Implementos Marinari | 2331.28 | Did not meet technical evaluation
| Shopping AR PIRCMGS 95 CP Plants Lot 1 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 4591.27 | 4591.27 | Lowest price fulfilling technical requirements
|  | Vivero Spinelli | 3673.02 | Did not meet technical evaluation
| Shopping AR PIRCMGS 95 CP Plants Lot 2 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 4591.27 | 4591.27 | Lowest price fulfilling technical requirements
|  | Vivero Spinelli | 3673.02 | Did not meet technical evaluation
| Shopping AR PIRCMGS 95 CP Plants Lot 3 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 4591.27 | 4591.27 | Lowest price fulfilling technical requirements
|  | Vivero Spinelli | 3673.02 | Did not meet technical evaluation
| Shopping AR PIRCMGS 95 CP Plants Lot 7 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 28905.55 | 28905.55 | Lowest price fulfilling technical requirements
45 |  | Vivero Spinelli | 9709.87 | Did not meet technical evaluation
| Shopping AR PIRCMGS 95 CP Plants Lot 9 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 32490.74 | 32490.74 | Only bidder, fulfilled technical requirements
| Shopping AR PIRCMGS 95 CP Plants Lot 16 30/05/2017 | Ferrimac S.A | 36571.12 | 36571.12 | Lowest price fulfilling technical requirements
|  | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 67367.87
|  | Sur Forestal | 87775.41
|  | Vivero Spinelli | 51327.9
| Shopping AR PIRCMGS 95 CP Plants Lot 17 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 8888.27 | 8888.27 | Only bidder, fulfilled technical requirements
| Shopping AR PIRCMGS 95 CP Plants Lot 19 30/05/2017 | Tekniplant | 3061.72 | 3061.72 | Lowest price fulfilling technical requirements
|  | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 313.7 | Did not meet technical evaluation
|  | Vivero Spinelli | 167.3 | Did not meet technical evaluation
50 | Shopping AR PIRCMGS 95 CP Plants Lot 20 30/05/2017 | Wekume Agro Servicios SRL Agro Servicios SRL SRL | 3304.34 | 3304.34 | Only bidder, fulfilled technical requirements
| Shopping AR PIRCMGS 93 CP Irrigation systems Lot 1 02/06/2017 | Riegos Pigue SRL | 3159.31 | 3159.31 | Lowest price fulfilling technical requirements
|  | Agro Luro | 4430.76
| Shopping AR PIRCMGS 93 CP Irrigation systems Lot 2 02/06/2017 | Riegos Pigue SRL | 2684.86 | 2684.86 | Lowest price fulfilling technical requirements
|  | Agro Luro | 3138.46
| Shopping AR PIRCMGS 93 CP Irrigation systems Lot 3 02/06/2017 | Riegos Pigue SRL | 34126.77 | 34126.77 | Lowest price fulfilling technical requirements
|  | Agro Luro | 37230.76
| Shopping AR PIRCMGS 93 CP Irrigation systems Lot 4 02/06/2017 | Riegos Pigue SRL | 40065.39 | 40065.39 | Lowest price fulfilling technical requirements
|  | Toledo Carlos y Mellinger Maximiliano S.H | 41042.4
55 | Shopping AR PIRCMGS 93 CP Irrigation systems Lot 5 02/06/2017 | Riegos Pigue SRL | 57812.17 | 57812.17 | Only bidder, fulfilled technical requirements
| Shopping AR PIRCMGS 96 CP Geomembrana caños de PVC Lot 1 05/06/2017 | Wekume Agro Servicios SRL Agro Servicios SRL | 4435.32 | 4435.32 | Lowest price fulfilling technical requirements
|  | Riegos Pigue SRL | 6215.81
|  | Agro Luro SRL | 10493.82
|  | Hydro 4 SRL | 8451.85
|  | Ferrimac S.A | 13444.44
|  | Megacer SRL | 10329.62
56 | (*) Exchange rate: US Dolar, seller, Banco Nación Divisas, at date of contract signature

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Stakeholder Risk: The number of involved stakeholders (national and provincial government agencies and municipal authorities, farmers and communities, scientific institutions, and NGOs) may make swift decisionmaking difficult and slow down project implementation. Incentives/direct benefits at community level might prove insufficient to convince people to adopt behavioral changes and new ways of cooperation in order to achieve longer-term objectives especially outside the key intervention zones. | This risk was rated as High at the PPP and is now lowered to Moderate as the generally successful implementation of the Project activities has already peaked its most critical phase. Beneficiaries and participants are overall committed, yet achieving longer-term objectives of course remains to be seen. | Considering that this Project fundamentally constructs on participatory planning procedures, the number of involved stakeholders has meant a great challenge for timely execution. Due to the participatory approach followed in the management of Project activities, quite close to Community-Driven Development strategies, actions must be discussed, planned and carried out with stakeholders that don't usually count with prior training on M&E procedures, environmental and social safeguards or procurement regulations; neither introducing considerations on climate resilience in their productive activities. To deal with these challenges, the PIU implemented a system that pre-formatted the planning procedures, based on a site-specific template for planning the investments, including safeguards check-lists, indicators, planning schedules, and procurement guidelines. Besides of facilitating the dialogue with the beneficiaries and local counterparts, this system facilitates the progress assessment, exchange of experiences, continued evaluation and early implementation of corrective measures, as needed. It is worth mentioning that this procedure has also provided an important set of lessons learned that have been summarized by the PIU and shared with the stakeholders through workshops on Project Planning. The participatory process has contributed to local capacity development, which by itself is expected to constitute a lasting Project result (see Monitoring Arrangements in the Project Proposal/Assessment Documents). Nonetheless, it has implied a great effort in local capacity building through small workshops and missions to the field, sometimes challenging the intended execution schedules.
Capacity: Financial Management and Procurement may prove challenging for the PIU and certain administrative processes may delay Project execution. | This risk was initially rated Low and was upgraded to Moderate after the first year of Project implementation. It is now upgraded to High considering new contracting restrictions at the national level due to the June 2018 currency crisis and the following extremely tight macroeconomic situation, including the Government commitment to a zero deficit for 2019, related with the biggest loan package ever from the International Monetary Fund (IMF). | This risk has been addressed through enhanced inter and intra-institutional articulation. During the current reporting period, all the PIU staff has contributed to fiduciary management and the PIU has counted with fiduciary support from other areas of the MAyDS. New restrictions to contracting at the national level urge the PIU to develop strategies to surpass this situation, in consultation with and support by the World Bank.
Governance: Policy/political priorities across administrative levels (national, provincial, and municipal) could differ and/or change during Project implementation. Similarly, due to lack of synchronicity between political cycles and dynamics of ecosystem recovery, political counterparts may not prioritize Project-related cooperation. | This risk was originally rated Moderate and was increased to High in the last PPRT as the country had entered a new electoral period. The risk remains High due to the currency crisis that initiated in June 2018 and impacts the overall country and political situation. | Humid environmental conditions prevailed during three (3) consecutive years since the Project started. A removal of a tax on wheat production was approved by the Government in 2016, which affected political commitment to the overall long-term Project objectives. To counter this trend, activities for awareness-raising have been and are currently undertaken by the PIU jointly with the participating local governments, as well as giving a new focus to local policies aimed at rangeland-recovery and cattle-ranching support. During the reporting period, the PIU/MAyDS has been able to maintain a positive articulation with OPDS, the provincial Environmental Agency, which has participated in various field events and all the WB missions. The highest municipal authorities of the three (3) involved counties have continued active participation in Project activities, including implementation of plans on planting tree windbreaks on national, provincial and local routes and emergency forage production.
Design: Changing climate conditions could affect the success of adaptation measures to be piloted during Project implementation; climate change may take a different form than anticipated (more or less severe and different in specific aspects such as impact on rainfall totals, regularity, intensity, etc., or to occur slowlier than anticipated). The chosen adaptive practices may prove less effective than anticipated in reducing impacts of climate variability and change to farmers; farmers might not wish to adopt the chosen adaptive practices due to lack of inputs, financing, or TA. | This risk was originally assessed as Moderate, upgraded to High in the last PPRT and now remains the same. | The climate variability factor dominated by the El Niño Southern Oscillation caused a humid cycle during the period 2015-2017, causing the perception of risk and vulnerability that made key beneficiaries and stakeholders receptive to the Project proposals to weaken. This meant that the identified risk materialized. During spring and summer 2017-2018, an arid period took place with scarce rainfall, and some farmers restarted to worry about the issue, but not to the extent reached with the climate extremes that took place 8 to 10 years ago. A strategy to take advantage of the more humid conditions implied supporting local public policies such as forage emergency plans through the provision of seeds and other supplies to make cattle-rising (a more sustainable productive option for the Project area than the mainstream wheat production) more appealing to local farmers. The focus on participative Project planning has fortunately proved to be an adequate mean to mitigate the design risks. Stakeholders in the field have decided and planned the Project activities jointly with the PIU, so the actions implemented are based on strong stakeholder-ownership. Considering that the Project is being implemented on a typically change-reluctant territory, participatory planning has been fundamental to ensure acceptance and continuity of the proposed measures. This approach has implied a need for major investments in participatory planning workshops, mechanisms, field visits, etc. that all require time and sometimes delay expected implementation period of the field activities. Since December 2016, the IEWS has developed 7 Meteorological and Agricultural Outlook Reports on a quarterly basis, in which information on the six (6) previous months and a forecast for the next three (3) months is detailed and delivered to principally local stakeholders. This contributes to the critical awareness-rising amongst local farmers and stakeholders and prevention of the related risks.
Social and Environmental: Moderate capacity for environmental and social management could negatively affect achievement of the PDO. The PIU has no earlier experience on environmental and social management under the Bank safeguards. However, other divisions in the SAyDS have been implementing safeguard policies. | This risk was rated Low and continues the same. | The PIU staff was trained with WB specialists on environmental and social management under the Bank safeguards as the Project implementation got started. This led to the development of a checklist to be completed by local partners of each Specific Intervention Site (SIS) and controlled by specialized staff of the PIU/MAyDS when consolidating the guidelines for management of the SISs. Additionally, the PIU has received support from other WB related Projects executed by the Ministry of Agroindustry to take advantage of their experience on implementing WB social and environmental safeguard policies. The Project's mid-term review mission and overall the field visits are used to review and discuss safeguards implementation.
Delivery, Monitoring and Sustainability: In case the overall Project results proved insufficient to create expected behavioral changes across different stakeholder groups, or the planned communication and dissemination efforts would not succeed, the Project may fail to promote expected replications and scale-up operations. | This risk was rated Moderate and continues the same. | The Project design has established participatory planning processes that have sometimes delayed expected execution time on-the-ground yet have proved to guarantee strong stakeholder commitment and engagement in longer run. A monitoring process through indicators and local consultive workshops was developed and implemented with participation of technicians, local authorities and farmers involved in the SISs and other pilot activities. During the first three (3) years of the Project implementation, different Sustainable Land Management (SLM) practices and technologies started implementation in the pilot SISs. As the initial results in the ground conditions are starting to become visible, the final year of Project implementation will focus on systematizing the practices and developing case studies for dissemination and expected replication and scale-up of the technologies and practices by farmers, all aimed at facilitating behavioral changes in favor of SLM. On the other hand, promoting inter-institutional agreements (IEWS and a pilot program of green employment with a road-side afforestation plan) have been strategies oriented to guarantee sustainability of Project guidelines which may, at medium and long term, help in replicate and scale-up experiences and best practices.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The climate variability factor dominated by the El Niño Southern Oscillation (ENSO) caused a humid cycle in the Project area during the period 2015-2017 and weakened key beneficiaries' and stakeholders' perception of risk and vulnerability that originally made them receptive to the Project proposal. | 50% | The PIU focused Project work on coordinating with broader county-level policies linked to recovery of local ecosystems, such as the plans on emergency forage production and municipal urban and road-side afforestation, as well as provincial regulation on native forests. Said plans aim to widen the scale of the adaptation activities promoted by the Project, such as dune-fixation and wind-erosion control through afforestation. In line with this, awareness-raising and technical capacity building events have been undertaken jointly by the Project and local governments. Additionally, when designing Terms of Reference for studies on related issues, the Project emphasizes cost-benefit analysis as well as the concept of opportunity-costs of inaction in view of the forecasted climate variability and change, both being concepts that draw farmers' attention.
Policies - Changes in the National Government at the end of 2015 resulted in the elimination of export taxes on wheat, making wheat production more attractive to farmers than it was at the time of the Project preparation. Productive alternatives to traditional wheat production promoted by the Project to prevent further soil erosion and increasing vulnerability to climate variability may lose attraction to farmers. | 60% | As mentioned above, the PIU focused Project work on articulating with major existing county-level policies as the plans on emergency forage production to direct them more to ecosystem recovery, as well as on new policies like afforestation of road sides to widen the scale of the measures that increase climate resilience. Direct investments have been made to foster the plans on emergency forage production and to support development of nurseries for native tree species. Also, investments have been focused on practices that show visible results in short term, like those developed to recover soil structure and productivity, to motivate farmers to continue forage production. To accompany this work, the PIU/MAyDS collaborates with the local governments on related awareness-raising through Project's participation in the main community fairs in the Project area hosting stands and organizing capacity-building events.
Continued and worsening budget cuts within the key local counterparts, such as the Universities and the National Institute for Agricultural Technology (INTA), are causing unexpected needs that affect the local counterparts' structural ability to deliver agreed upon Project activities, including lack of vehicles, fuel for machines, and salaries for technicians and other personnel. | 85% | The PIU is giving maximum efforts and uses its potential for institutional networking to cope with the increasing budget challenges. Inter-institutional collaboration increases importance as resources grow scarcer, and the PIU emphasizes mutually beneficial collaboration to minimize costs and maximize benefits e.g. related with training events.
Institutional changes in the Provincial Agency for Sustainable DevelopmentEnvironmental Agency (OPDS) and Ministry of Agroindustry may impose limitations to future replication and scale-up in particuar as their overall involvement in Project activities has remained limited. | 70% | The PIU has developed direct and strong relationships with the participating local governments to contribute to overcome the referred lack of buy-in by the key provincial institutions. Since OPDS has not counted with any local office in the field or specialized staff in the region during the Project implementation period, the PIU has opted with strong direct links with the local governments. Additionally, high-level meetings between representatives of the MAyDS and OPDS have taken place to strengthen the involvement of the provincial authorities in strategic Project activities. At the national level, a new WB operation on integrated climate risk management with the Ministry of Agroindustry has provided new momentum to exchange and disseminate Project's experience and lessons learnt.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Diverse risk mitigation measures have been employed during the reporting period as described above. E.g., strong involvement by the local authorities has been fostered to continue the momentum gained through their participation in the Climate Change Adaptation Training Program held in Montevideo in May 2016, after which they have continued motivated in strong involvement in several Project activities after their signature of an Agreement for the creation of the Network for Iberoamerican Sustainable Development and Resilient Local Governments. Moreover, first results of strategic policy instruments as the plans on forage production and afforestation in road sides are emerging and have consolidated local authorities' interest and involvement. Additionally, certain investments in the SISs, like the farm equipment paratill and provision of seeds have kept farmers and other local stakeholders interested and engaged. Investment-related results have been complemented with a stronger presence of the PIU and MAyDS in the Project intervention area and strategic focus on disseminating Project results. Meetings with the WB Task Team have also continued frequent during the current reporting period to monitor progress, anticipate issues and find solutions to implementation bottlenecks, including fiduciary aspects. Further, innovative agreements involving additional federal organizations, such as the Ministry of Social Development, National Roads Agency and National Meteorological Service have been consolidated to increase sustainability of Project initiatives and ownership by the local governments. Advancing with concrete action e.g. on the IEWS and afforestation before formalizing the necessary interinstitutional framework has proved to be a fruitful strategy to generate major involvement of key stakeholders.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | PIU capacity and the overall Project governance structure/institutional arrangements and capacity |  | The Project governance structure/institutional arrangements are functional and the capacity sufficient to achieve the expected results |  | After a serious delay to get the Project initially effective and operational, since early 2016 the Project has shown steady progress and presents Satisfactory results on the ground. It benefits of a strong ownership both by the direct beneficiaries and the responsible agencies at the national and local level, and the targets of the Project Development Objective (PDO) indicators are achievable by the original closing date. There has been certain disconnect between progress against indicators and the level of disbursements, taken (i) 2/3 of the PDO indicators focus on non-material aspects as institutional commitment and inter-institutional collaboration e.g. on running the Information and Early-Warning System (IEWS), and (ii) lack of an intermediate results indicator that would reflect execution of the funds under Component 2 on concrete adaptation pilots that owns the bulk of the Project budget. The Project’s mid-term review (MTR) in April 2017 confirmed the continued relevance of the PDO and the five embedded outcomes at the national, provincial and local level. In May 2018, the PDO rating was increased to “Satisfactory” as the PDO indicators reflect strong results and the PDO is deemed achievable even without extension of the Project closing date (please see below on the status of the main results). The implementation progress has been considered “Satisfactory” since the MTR due to Project investments’ advance in the 11 Specific Intervention Sites (SIS); strong institutional commitment with the key Project activities; steady advance with disbursements since 2017; and completion of the heaviest bulk of the procurement work. In early 2018, internal reorganization within the Ministry of Environment and Sustainable Development (MAyDS) moved the Project under the authority of the Secretary of Environmental Policy, Climate Change and Sustainable Development, causing a momentary halt in administrative aspects and a slow-down in disbursements. By mid-April most of the issues were resolved through dedicated efforts by the Project Implementation Unit (PIU) that benefits of highly motivated and proactive personnel. It continues with solid working relation with the targeted municipal actors and coordinates efficiently with other related national and provincial institutions and programs. In early May 2018, disbursements reached 71% and the Government of Argentina (GoA) confirmed it will request a closing date extension to be able to take full advantage of the grant and further strengthen the Project results. The need for more time to be able to demonstrate solid proof of improved soil quality and rooting of Sustainable Land Management practices at the necessary scale won’t be resolved by a minor project extension. However, the extension will facilitate a major increase in the quality and actual impact of the Project results when core members of the PIU can focus on dissemination and expanding the thus far scope of active dialogue on replication and scale-up options beyond the direct implementation area. | S
| Execution of the Project activities according to the operational framework presented to the AF and the Annual Operating Plan |  | The overall implementation pace and results of the key indicators are on track |  | The overall Project execution rate improved since June 2017 and is deemed Satisfactory for the reporting period, during which the main investments took place and all the SISs moved strongly forward. Progress in the main aspects of the Project Development Objective (PDO) are reflected through the three (3) PDO indicators e.g. regarding agreements formalized with participating institutions and establishing public policies/plans aimed at ensuring continuity beyond the Project closure: PDO Indicator 1: Eight (8) institutions reflect institution-specific adaptation needs in their budget/resource allocations to increase their capacity to address climate-related challenges: (i) Municipality of Villarino has created a Municipal Environmental Agency and a Municipal Nature Reserve (protected area); is co-implementing a pilot program of green employment with a road-side afforestation plan aimed at reducing wind erosion (“Green Employment Pilot”), and has established a Municipal Plan on Sustainable Forage Production that aims at fixing soil and reducing wind erosion through increased topsoil coverage (“Forage Plan”); (ii) Municipality of Puan has allocated resources to strengthen the Municipal Tree Nursery and established a Municipal Nature Reserve (protected area); and has established a Forage Plan; (iii) Municipality of Patagones has established a Forage Plan; (iv) National Ministry of Social Development is co-implementing the Green Employment Pilot; (v) National Roads Agency is co-implementing the Green Employment Pilot; (vi) National Institute on Agricultural Technology (INTA: Ascasubi Experimental Station) signed the Information and Early-Warning System (IEWS) Agreement in February 2018 and is implementing several related projects with own funding; (vii) National Meteorological Service (SMN) provides maintenance of meteorological stations, server space and data processing for the development of a Drought Index in the Project area and signed the IEWS Agreement in April 2018; and (viii) Center of Renewable Natural Resources in the Semiarid Zone (CERZOS) – National Center of Scientific and Technical Research (CONICET) signed the IEWS Agreement in May 2018. PDO Indicator 2: 41 climate-smart land use practices/technologies have been identified through participatory processes and 12 of them are being implemented in 11 Specific Intervention Sites (SISs). The indicator bases on a proxy index with hypothetical values from 0 to 24, assuming a total of 12 SISs as planned during the project preparation. In said index, each SIS where the status of the agroecosystem improves adds 2 points; a SIS where it is maintained adds 1 point; and a SIS where the agroecosystem deteriorates adds 0 point. The targeted result at the end of the Project implementation is 10. Collection of the respective baseline information and development of a monitoring system on the SISs was completed in August 2017 by The Nature Conservancy (TNC) to determine the initial soil conservation status and the key variables to monitor the evolvement of soil quality in the Semi-arid, Irrigation and Arid Geographical Intervention Area (GIA). A control study on the baseline results of the selected variables in the 3 GIAs will be conducted in each SIS by the end of 2018. Consequently, until said control study, reporting on the index value bases on visual observations. The current indicator value of 13 is conservative by reflecting that out of the total of 11 SISs, 2 have improved and 9 maintained the quality of the agroecosystem to withstand conditions imposed by climate variability. The improved conditions are observed in 2 SISs in the Municipality of Patagones: (i) “San Jose Dryland” due to the use of paratill, a machine that lifts and bends subsoil to remove hardpans. It gently lifts the soil, allowing it to fracture along its natural planes of weakness and then settle back again. The soil loosening improves water infiltration and drainage, encourages root development, and allows for deeper fertilizer placement. The gentle lifting action leaves topsoil and subsoil layers intact, minimizes clods, and leaves valuable residue on the surface. The paratill financed by the project is the first in the project area; and (ii) “Patagones Rangelands/Monte Biome” due to soil fertilization through incorporation of perennial legumes. Out of the 9 SISs maintained to withstand conditions resulting from climate variability, 2 are located in irrigated areas in Patagones and Villarino and could already be calculated as having improved, taken the Project-financed infrastructure improvements have increased water availability from 2 to 6-7 days per week and water use efficiency from 30-50% to 80-90%. 4 other SISs considered to have maintained their conditions are in nonirrigated areas; 2 in Patagones and 1 in Puan and 1 in Villarino. PDO Indicator 3: A prototype Information and Early Warning System on climate change and desertification (IEWS) has been developed jointly with local research and extension institutions and the National Meteorological Service (SMN) to generate and disseminate relevant (Project-related) information on threats and hazards to farmers and other stakeholders on a timely basis. Seven (7) quarterly reports (in Dec 2016; Feb; June; Sep and; Dec 2017; March; and June 2018) that include agro-meteorological information, productive forecasts and risk assessment on fires and wind-erosion, as well as land management and crop and animal management recommendations have been compiled and disseminated through rural radios, local institutions, particularly Municipalities and INTA, relevant public offices and websites, as well as social media, e.g. WhatsApp groups. The institutional arrangements, i.e. the institutional legal agreement and operational manual have been developed and signed by INTA, SMN and CERZOS-CONICET to sustain the IEWS operation beyond the Project closure. Further on the intermediate results achieved until June 30, 2018 to justify the overall Satisfactory project rating, please see the section on Project Indicators. | S
| Progress on Project activities that pave the way for sustainability, replication and scale-up of key Project activities |  | Progress achieved in implementing Component 4: Developing a Sustainability Strategy meets expectations at the current implementation stage |  | The activities conducted under Component 4 focused on Developing a Sustainability Strategy for the main Project activities include thus far six (6) inter-institutional work fronts on policies/plans that aim to develop/replicate/scale-up results that transcend the Project implementation period: i) The IEWS that has been improving the presentation and dissemination of the Agro-meteorological and Productive Forecasts and Risk Assessment Reports, consolidating the institutional set-up (legal agreement and operational manual) by the four (4) institutions that constitute it, and are developing a Drought Index (first experience also for the National Meteorological Service) and a related database/information platform. ii) Villarino Reforestation Plan that counts with innovative collaboration with the National Ministry of Social Development, Roads Agency and Ministry of Environment and Sustainable Development. A Forestry Cooperative has been created as a pilot on promoting green jobs. The Reforestation Plan scales-up the original pilot established through the Project, aimed at strengthening the local tree nursery in the short term and reducing wind erosion in the long term. This example is expected to be replicated in other regions in Argentina; iii) Municipal forage production plans to support recovery of degraded soil and natural pastures through use of perennial and nitrogen fixing species has been established and is under implementation in all three counties (Patagones Villarino and Puan) with specific regulations with climate variability criteria included; iv) A cooperative of honey producers has been created and is working to improve and enlarge honey production in Patagones; v) A preliminary dialogue within the Governmental Committee on Climate Change (GCCC), including elaboration of national adaptation plans, particularly on agroindustry, as well as sector plans and funding proposals for the Nationally Determined Contributions (NDCs). vi) Application for international funding, whereby activities have been developed jointly in partnership with different local and international institutions aimed at improving local, provincial and national level technical and institutional capacity to sustain, replicate and scale-up the Project outcomes. Two (2) project proposals have been developed and are in the pipeline for approval, including Buenos Aires Province and Sustainable Land Management based on project experience and a GEF Project “Mainstreaming Biodiversity Conservation and Sustainable Land Management (SLM) into Development Planning: Making Environmental Land Use Planning (ELUP) Operational in Argentina”. The Project has also developed abundant communication materials such as leaflets, pamphlets, posters, etc. However, production of guidance material on critical pieces of policy framework, piloted adaptation practices, and potential sources of financing to support continued efforts to promote climate resiliency at different administrative levels and disseminate Project results remains work in progress. The positive exception is a document that systematizes the municipal plans for emergency forage production that is currently under review. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joaquin Etorena
| Email: | jetorena@ambiente.gob.ar
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The execution rate has been deemed Satisfactory since the Project MTR and it further improved during the current reporting period. The PDO rating was increased to “Satisfactory” in May 2018 as the PDO indicators reflect strong results and the PDO is deemed achievable, yet a 9-month extension of the Project closing date in WB terms has been agreed upon by the Government, WB and AF from December 2018 to September 2019 to allow better systemization and dissemination of the main Project results. The initial participatory planning phase was time consuming to complete the consultative processes and joint planning procedures for implementing the pilot activities on 11 Specific Intervention Sites (SISs), but the participatory approach has then yielded its worth as the key stakeholders and counterparts have strong ownership of the Project and are committed to maximizing its results. The PIU/MAyDS maintains excellent working relations with several key institutions at local and national level. These include the National Meteorological Service and the three (3) extension/research institutions, National Institute for Agricultural Technology (INTA), Southern National University (UNS), and Center of Renewable Natural Resources in the Semiarid Zone (CERZOS) that form institutional basis and workforce for the Information and Early-Warning System (IEWS) that serves as a model for similar work in other areas of the country. Further, innovative collaboration with the National Road Agency and Ministry of Social Development with the local government of Villarino to plant tree barriers along national roads to prevent wind erosion through creation of green employment has been further consolidated. Towards the end of the current reporting period, the Project focus started to shift towards Component 4 on the Sustainability Strategy that promises great opportunities to consolidate and scale-up Project results.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Increase the development impact of the Project through improved results |  | To bring added value to the EA, providing managerial and technical assistance on aspects that could lead to improved results at the project level. ACHIEVE THE EXPECTED RESULTS OR TIMELY ADJUST EXPECTATIONS TO WHAT IS AMBITIOUS, BUT STILL ACHIEVABLE. |  | As a development agency, the World Bank has an invested interest in assisting the Executing Agency (EA) in achieving the PDO on a sustainable basis and with a maximum development impact. For this purpose, the WB provides operational/managerial and technical assistance to strengthen the results at the Project level and in the sector(s) supported by the Project. During the current reporting period, the WB supported the PIU/MAyDS particularly in disseminating Project results e.g. through (i) facilitating the PIU lead’s travel to COP 23 in Bonn in November 2017 to present the Project in a Side Event organized by the Adaptation Fund (AF), titled “Fostering Environmental and Social Principles in Adaptation Projects” in celebration of the 10th anniversary of the AF; (ii) promoting exchange and synergy with related WB operations in Argentina and Paraguay in the agricultural sector, particularly a new IBRD loan of USD 150M for Integrated Management of Agricultural Risk (P162316); (iii) financing preparation of video clips on the main work fronts of the Project; (iv) participating in a consultancy that systematized comparison of implementation of two AF projects in Argentina, one with a National Implementing Entity (NIE) and this Project with a Multilateral IE (MIE), including a workshop titled "Reflections on the Projects financed by the Adaptation Fund in Argentina"; and (v) organizing a Brown Back Lunch (BBL) on the Project results and potential for continued inter-institutional collaboration in June 2018, convening more than 20 related institutions from local to international level and the WB Southern Cone Country Director and Program Leader. During the reporting period, the WB carried out only one official implementation support mission in December 2017, including participation in a workshop where the PIU/MAyDS and beneficiaries and their supporting institutions at the local level exchanged on the Project monitoring and results across the SISs. Importantly, the WB provided the PIU continuous support through weekly interaction to resolve doubts, monitor progress and support the PIU in addressing implementation issues particularly related with the Government’s administrative reforms that have caused a wealth of concerns and challenged smooth implementation progress. | S
| Increase the development impact of the Project through eficient execution and risk management |  | To address implementation issues efficiently and timely, and resolve problems quickly. ENSURE A SMOOTH EXECUTION OF RESOURCES AND MANAGE THE RISKS SO THEY DO NOT HAMPER THE PROJECT EXECUTION, NEITHER DAMAGE THE BANK NOR THE EA's REPUTATION |  | During the reporting period, the WB task team maintained continued contact with the PIU receiving updates on advances and challenges often accompanied with consultation on the best way forward in situations that arose e.g. with different procurement processes and in administrative terms at different levels. The tightening fiscal situation in the country impacted all participating institutions, and the WB supported the PIU/MAyDS in resolving budget issues and in maintaining the necessary PIU staff. In terms of portfolio-wide challenges, the WB elevated exchange and agreements to a higher level between MAyDS and WB authorities. Overall, the WB provided close and efficient support in terms of fiduciary issues and institutional support. Regarding environmental and social risk management, the WB guided the PIU/MAyDS in updating the situation of presence of any Indigenous Peoples community within the Project’s direct intervention area in consultation with the responsible provincial authority. The conclusion remained pending by the end of the reporting period, yet it is not probable any new community would be present compared with the initial screening with negative results conducted during the Project preparation. Regarding environmental risk management, the Specific Intervention Site “Patagones Rangelands/Monte Biome” has been studied in detail to discard any potential for negative impact on conservation of native forests beyond the SIS. Said analysis also remained work in progress by the end of the reporting period. On the downside, it has taken the WB task team much longer than expected to process and close the Project restructuring agreed upon during the Project’s mid-term review. A partial and minor restructuring to adjust funds allocation between disbursement categories was approved in January 2018, but the exchange on the other restructuring needs with the AF Secretariat got extended until May 2018 and the restructuring that includes a Project closing dat extension until September 2019 moved beyond the reporting period. | MS
| Increase the development impact of the Project through increased institutional development of the Executing Agency |  | To increase EA's capacity for Project management under international standards. |  | The WB task team has consolidated a strong and frank partnerships with the PIU/MAyDS staff and relevant stakeholders, using efficient means of communication to dialogue and deal with implementation issues on a continuous basis to expedite decision-making. In line with that, the Bank and the EA have developed a working environment in which problems and their causes are identified and addressed promptly. The WB provides technical support to the EA to strengthen its capacity to manage and deliver Project activities following agreed technical specifications and quality standards and to address technical issues that arise during implementation. During the reporting period, the WB support has provided the PIU/MAyDS particularly with stronger capacity to manage procurement processes for the benefit of the Project. | S
| Ensure compliance with the Project Legal Agreements |  | To achieve the Project development objectives in conformity with the project’s Legal Agreements. |  | The WB monitors and provides advice as necessary to the EA on implementing the Project with due diligence to achieve its development objectives in conformity with the Project’s Legal Agreement (e.g. compliance with technical and financial reporting requirements, implementation of environmental and social safeguards, efficient use of procurement rules and conduction of both interim and independent financial audit). The respective rating is lowered to MS during the reporting period due to the delays suffered by closing the restructuring-related update of the Project’s Operational Manual and the restructuring overall. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Tuuli Bernardini
| Email: | tbernardini@worldbank.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The progress on key milestones has been rated MS-S basically because the managerial and technical support provided by the IE has resulted in better Project execution and partial achievement of the result, in most cases in line with the targets expected for Project year 2. The general trend toward the achievement of planned outcomes is possitive, although they might fall short due the initial delays to start Project execution. The main risks identified have been, to a certain degree, mitigated so they have not impacted severely the Project execution, which improvement is also reflected in the increase of the disbursement of the grant proceeds. No major breaches to the legal agreements have occurred so far. When it comes to the risks that have affected progress, thel limited cooperation between the Provincial and National environmental agencies might have prevented a faster achievement of the results, and what is more, might hamper sustainability of results. However, a series of shorcomings have been identified in the implementation of some planned activities (such as the public policies observatory and the trainings for teachers), and some aspects of the original project design have shown not being that relevant now (e.g. some of the results targets have proven over ambitious, and some progress indicators resulted too complex), so after the mid-term evaluarion some adjustments might be proposed and implemented in order to bring the project intervention strategies efficiently back on track towards the broader expected impacts.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…) |  |  |  |  | Comments
Type of Indicator | Indicator | Baseline | Progress since inception (30/06/2018) | Target for Project End (31/12/2018)
Outcome | Outcome indicator 1 Targeted institutions that reflect institution-specific adaptation needs in their budget allocations to increase their capacity to address climate-related challenges (Number, Custom) | 0 | 8 | 10 | This indicator aligns to the PDO outcome (ii) on increased adaptive capacity of key local institutions. The main part of the funding that has allowed the above results came from Component 2. Component 1 that includes the IEWS has also contributed significantly to these results. Overall, taken the high level of these results that demonstrate changes at institutional level, all Project expenditure can be claimed to have contributed to reaching them. Please see the description of the eight reported institutions under the Rating section. The work remaining to achieve the targeted result of 10 institutions is also well on the way, taken the National Southern University (UNS), the fourth institution that contributes to the IEWS was expected to sign the IEWS Agreement within short; the signature took place in October after the current reporting period. The tenth expected inclusion in these institutional results is CORFO, the Development Corporation of the Colorado River in Bonaerense Valley that runs a mayor irrigation system on which some of the vegetable producers/SISs depend. With support by the Project, CORFO is working to establish a new program to support financing of water efficiency measures by its members.
Outcome | Outcome indicator 2 Productive agroecosystems in the pilot sites maintained or improved to withstand conditions resulting from climate variability and change (Number, Custom) | 0 | 16 | 10 | The indicator aligns to the PDO outcome (i) on contribution to reduction of climate and man-made vulnerability of the agroecosystems in the Southwest of the Buenos Aires Province. The main funding that has allowed the above results came from Component 2, yet expenditures under Component 3 on implementing the participatory approach and knowledge management and capacity building activities have naturally contributed to the same. As the Project advances to its final stretch, contributions by Component 4 on Development of a Sustainability Strategy increase in importance. Please see the description of the reported index value of 13 bases on visual observations under the Rating section. A control study on the baseline results of the selected variables in the 3 Geographical Intervention Areas (GIAs) will be conducted in each SIS by the end of 2018.
Outcome | Outcome indicator 3 Relevant threat and hazard information generated and disseminated to farmers and other stakeholders on a timely basis (Yes/No, Custom) | NO | YES | YES | The indicator aligns to all the PDO outcomes at some level as farmers that adopt improved agricultural technology contribute to all of them. Directly, it aligns to the PDO outcomes (iii) on increased adaptive capacity of key local actors and (iv) on piloted climate resilient and sustainable land management practices. The funding that has allowed the development of the IEWS come from Sub-Component 1.1. This simple Yes/No indicator reflects successful results of first-of-its-kind and rather complex interinstitutional collaboration between four (4) institutions both at national and local level convened and coordinated by the PIU/MAyDS as described in further detail under the Rating section. Said collaboration remains work in constant progress and strengthening and has started to serve as an example for potential replication/scale-up in other regions.
Intermediate Outcome | Intermediate outcome indicator, sub-component 1.1: Targeted clients satisfied with agricultural services (percentage) (Percentage, Core) | 0% | 0% | 50% | As reported in the last PPRT, at the mid-term review (MTR) the PIU suggested and the Bank agreed that, in this context, "agricultural services" refers to the provision of the quarterly IEWS reports. Further, it was agreed that "percentage of targeted clients" refers to the percentage of the 408 farmers who participate in the 11 SISs and the municipal sustainable forage production and reforestation plans established with project support. The reception of the reports has been positive by local producers, agricultural technical advisers, and technicians from local and national institutions. An initial survey to determine the degree of satisfaction among the IEWS users was piloted finally in August-September 2018 amongst involved producers and key actors, whereby 80% of respondents said having considered recommendations included in IEWS reports. Of the participating farmers, 80% (326) are estimated to be male, and 20% (82) female. The satisfaction target was set at 50% (163 and 41, respectively).
| MALE (number) (Number, Core Supplement) | 0 | 0 | 163
| FEMALE (number) (Number, Core Supplement) | 0 | 0 | 41
WB Intermediate | Additional WB core indicator: Targeted clients- MALE (number) (Number, Core Supplement) | 0 | 162 | 352 | 162 male producers receive the IEWS reports by email. Based on the usage metrics of the INTA web site, the IEWS received 336 individual visits, but the same cannot be divided between male and female users.
Outcome | Targeted clients- FEMALE (number) (Number, Core Supplement) | 0 | 49 | 88 | 49 female producers receive the IEWS reports by email.
Output | Output indicator 1.1.1: Targeted local public employees trained (Percentage, Custom) | 0% | 66.66% | 60% | The result reflects 8 trained public employees. The % is measured of the total of the relevant public employees in the Municipalities of Puan, Villarino and Patagones where the project works directly, as defined by MAyDS following the organic municipal structures in place since December 2015. The applicable total of 12 employees corresponds to the 3 Mayors and 3 Secretaries of Production, the Head of the Municipal Tree Nursery in Puan and in Villarino, the Production Assistant and Director of Environment in Villarino, and Director and Assistant of Production in Patagones. In June 2018, 9 of them are men and 3 women. No gender target has been set for this indicator, but the result is monitored by gender. The current gender result is that 8% of the trained officials are female.
| MALE (percentage of the total males+females) (Percentage, Custom Breakdown) | 0% | 87.5% | NS | 7 of the 8 trained public employees are male.
| FEMALE (percentage of the total males+females) (Percentage, Custom Breakdown) | 0% | 12.5% | NS | 1 of the 8 trained public employees is female.
Output | Output indicator 1.1.2: IEWS developed/operational through inter-institutional cooperation (Yes/No, Custom) | N | Y | Y | A prototype Information and Early Warning System on climate change and desertification (IEWS) has been developed jointly with national and local research and extension institutions (INTA / UNS / CERZOS / SMN) to generate and disseminate relevant Project-related information on threats and hazards to producers and other stakeholders on a timely basis. During the reporting period, the IEWS generated and disseminated four new quarterly reports in Sep 2017; Dec 2017; March 2018; and June 2018, including agro-meteorological information, agriculture production forecasts and risk related information on fires and wind erosion. The presentation of the reports has remained subject to improvement report by report, as well as their dissemination channels that include rural radios, local institutions, relevant public offices and websites, and social media (e.g. WhatsApp groups). Further, the institutional arrangements were consolidated to sustain the IEWS beyond the Project closure as the legal IEWS Agreement was signed by 3 of the 4 responsible institutions. Related collaboration arrangements have also been broadened to include further agencies, e.g. CONAE, the national space agency.
Output | Output indicator 1.1.3: Active participation of at least the key institutions of the Observatory (Yes/No, Custom) | N | N | Y | The project MTR concluded that the respective output on a "Regional Consultative Observatory of Public Policies on Climate Change and Desertification" (Observatory) will be dropped from the project design to rationalize the execution efforts by focusing them on the most strategic and promising work fronts. Based on the results of a consultancy that delivered proposed rules of procedure and a 5-year action plan both for the IEWS and the Observatory, the latter was not considered worth the effort: its agenda and key players would resemble closely those of the Development Plan of the Southwest of Buenos Aires Province and its Regional Council, established by the provincial law 13,647 in 2007; an initiative that hasn't prospered on the ground. On the other hand, the IEWS draws overall a keen interest and it also covers similar functions that initially planned for the Observatory. Consequently, the project concentrates available human and other resources in further developing and strengthening the IEWS instead of trying to establish a similar network structure that is not sufficiently demanded on the ground.
Intermediate Outcome | Intermediate outcome indicator, sub-component 1.2: Consulted people who report on modification(s) in their Project-related practices (Percentage, Custom) | 0% | 0% | 60% | At the MTR, the indicator was discussed in detail and it was concluded and reported to the AF that it is not meaningful for the Project and should thus be revised or dropped. Per the Bank Project Appraisal Document (PAD), the population targeted by this indicator refers to the 80,000 inhabitants of the directly targeted Municipalities of Puan, Villarino and Patagones. However, most of the inhabitants live in urban areas, while the Project mainly targets rural farmers working on vulnerable agroecosystems. The 408 farmers that work directly on the Project pilots under Component 2 don’t compose a statistically representative fraction of the total population.
| MALE (percentage of total: male+female) (Percentage, Custom Breakdown) | 0% | 0% | NS
| FEMALE (percentage of total: male+female) (Percentage, Custom Breakdown) | 0% | 0% | NS
Output | Output indicator 1.2.1: Client days of training provided (number) (Number, Core) | 0 | 78 | 64 | The result reflects the cumulative training days delivered on various Project-related topics by the PIU or in close collaboration/with financial support by the Project e.g. on participatory project planning, incorporation of climate considerations in productive activities and early-warning systems.
| FEMALE (number) (Number, Core Breakdown) | 0 | 252 | NS | Per PAD, the indicator does not have a specific gender target, but training was to be monitored by gender. Full information on the number and gender of the accumulated participants is not available. The total of female participants since July 2016 is 252.
Output | Output indicator 1.2.2: Teacher training institutes within SWBA that cooperate with the Project and offer related training (Number, Custom) | 0 | 4 | 10 | The four educative institutions that collaborate with the Project are the UNS, Agrarian School N°1 Carlos Spegazzini, Agrarian School of Patagones, and Agricultural School of Hilario Ascasubi. Further, the General Directorate of Schools, District of Southwest of the Ministry of Education of the Province of Buenos Aires facilitates the Project’s provision of educative material to schools within the targeted Municipalities. The Project has produced useful and popular pedagogical material used across schools and other public institutions in the area, including elaboration and dissemination of a visual poster on climate change and SLM in favor of greater climate resilience. The Project has also organized/supported events like a yearly drawing competition in local schools on Project-related topics. During the reporting period in 2017, the topic of the competition was “My Footprint on the Ground 2017. Tree Our Refuge” (Mi Huella en el Suelo 2017. El Árbol Nuestro Refugio), and the Project produced related T-shirts and cloth bags. Despite these popular activities, as the indicator requires that the reported training institutes would offer related training, the final target of 10 institutes (still more specific “teacher training institutions within the SWBA”), is not going to be achieved. During the MTR and as reported to the AF, the PIU/MAyDS suggested and the Bank agreed to revise/remove this indicator to focus Project implementation on more strategic work fronts. Collaboration with local schools has in every case continued through specific awareness-raising events.
Output | Output indicator 1.2.3: Cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom) | 0 | 11 | 28 | The 3 new activities carried out during the reporting period refer to the Project participation in Expo Villa Iris in Puan and National Garlic Festival and “My Footprint on the Ground” competition in Villarino.
| FEMALES participating in cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom Breakdown) | 0 | 104 | NS | The cumulative number of participating women corresponds to the seven (7) events where the Project participated between July 2016 and June 2018; sex-aggregation of the people that visited the Project booth during the earlier public events with loads of people was not conducted/registered.
| MALES participating in cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom Breakdown) | 0 | 175 | NS | The cumulative number of participating men corresponds to the seven (7) events where the Project participated between July 2016 and June 2018; sex-aggregation of the people that visited the Project booth during the earlier public events with loads of people was not conducted/registered.
Intermediate Outcome | Intermediate outcome indicator, component 2: Clients who have adopted an improved agr. technology promoted by the project (Number, Core) | 0 | 1632 | 1400 | 408 producers participate in the implementation of the SISs and the municipal sustainable forage production and reforestation plans. Each producer represents an average family of 4 persons. "Improved agricultural technology adoption" is understood in terms of the "adoption" involving a process that comprises four stages: 1) Commitment: verified through the application letter of each ISI. 2) Implementation: verified in the field by means of physical investments, associated with the Project activities. 3) Management and evaluation: verified through interviews with producers and field visit. 4) Adoption: verified through interviews with producers and field visit. Within the scope of the Project implementation period, it needs to be noted that that monitoring the number of people who reach the referred stages will only be feasible in terms of the two first stages of the process. There will be a chance to see a trend toward potential adoption of the promoted technologies through verification related with the implementation and management stages, yet the remaining implementation period will be too short to verify reaching of the final adoption stage.
| FEMALE (Number, Core Breakdown) | 0 | 408 | 280 | 408 producers participate in the implementation of the SISs and the municipal sustainable forage production and reforestation plans. 39 of them are women, yet each producer family is considered to represent one woman.
Output | Output indicator 2.1.1: Adaptation/sustainable land management (SLM) technologies identified/verified through local participatory consultations under the Project framework that are demonstrated within the GIAs (Number, Custom) | 0 | 41 IDENTIFIED | 12
|  |  | 13 IMPLEMENTED | 9 | The list of the implemented technologies: 1) Loosening of topsoil and deepening of soil profile by using paratill; 2) planting of perennial pastures to strengthen cattle raising; 3) inclusion of annual legumes in cattle raising management; 4) drip irrigation; 5) planning and implementation of crop rotation; 6) biologic pest management by means of strip cropping; 7) soil mapping; 8) land management zoning and mapping; 9) intercropping of legumes and perennial pastures for fodder; 10) consociated intercropping; 11) production of substrates through composting; 12) breeding of native plants; and 13) simulation and evaluation of effects of drought.
Intermediate Outcome | Intermediate outcome indicator, component 3: Related articles/programs in the local media and political initiatives in the three municipal Councils of the directly targeted counties (Number, Custom) | 0 | 250 | 82
| Related articles/programs in the local media in the three municipal Councils of the directly targeted counties (Number, Custom Breakdown) | 0 | 242 | 72
| Related political initiatives in the three municipal Councils of the directly targeted counties (Number, Custom Breakdown) | 0 | 8 | 10 | The 8 political initiatives by the 3 targeted Municipalities (Puan, Villarino and Patagones) refer to the establishment and functioning of: 2 protected areas (Puan and Villarino); an Environmental Agency (Villarino); a strengthened Municipal Tree Nursery (Puan); a pilot program of green employment with a road-side afforestation plan aimed at reducing wind erosion (Villarino); and 3 Municipal Plans on Sustainable Forage Production.
Output | Output indicator 3.1: Workshops and other Knowledge Management events meet their targets in terms of participation of different stakeholder groups (Yes/No, Custom) | N | Y | Y | The PIU/MAyDS reports that the workshops and other knowledge management events thus far have met their targets in terms of participation of different stakeholder groups (local governments and technical institutions, national and provincial ministries/entities, producers, and local media). Beyond 2 workshops organized in September 2015 on the project objectives and indicators and formulation of the SIS proposals, the PIU organized an end of the year annual workshop to evaluate the project advance in December 2016 and 2017. The latter focused on monitoring the advances in the SISs and the municipal plans, as well as exchange of experience and thus far lessons learnt, including with the IEWS. The PIU/MAyDS has invested a plenty of work into communication and KM activities and the project has gained visibility in local media, but systematic monitoring and reporting on this indicator has not taken place.
Output | Output indicator 3.2: Targeted beneficiaries who have participated in related training and carry out their own means of M&E and continued improvement related to the measures they have adopted through participation in the P (Percentage, Custom) | 0% | 0% | 70% | This indicator has not been measured as the referred M&E processes have resulted to be more institutional than individual in nature. The producers have still received training on project indicators and monitoring, and the project is promoting their use amongst the beneficiary producers as the project implementation advances.
| FEMALE (Percentage, Custom Breakdown) | 0% | 0% | 70%
Intermediate Outcome | Intermediate outcome indicator 4.1: Assumed institutional commitments for the continuity and sustainability of the Project results per sector and activity (Number, Custom) | 0 | 12 | 1 per sector | The result reflects the following 12 institutional commitments: SMN, INTA and CERZOS-CONICET have consolidated their participation in the IEWS (3); a municipal ordinance on a Municipal Plan on Sustainable Forage Production signed and operational in the Municipalities of Puan, Villarino and Patagones (3); the national Ministry of Health and Social Development, National Roads Agency and Municipality of Villarino participating in the pilot program on green employment on road side forestation (3); a Municipal Nature Reserve (protected area) established in the Municipalities of Puan and Villarino (2); and a Municipal Environmental Agency created and functioning in the Municipality of Villarino (1).
Output | Output indicator 4.1.1: Guidance material produced on critical pieces of policy framework, piloted adaptation practices, and potential sources of financing to support continued efforts to promote climate resiliency at differ (Yes/No, Custom) | N | Y | Y | Beyond abundant communication materials (leaflets, posters, videos etc.), the Project has developed a document that systematizes the three Municipal Plans on Sustainable Forage Production. Otherwise, the bulk of work on guidance material on key pieces of the policy framework, piloted adaptation practices and potential sources of financing to support continued efforts to promote climate resiliency take place in 2019.
NS = Not specified

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected the progress? | During the current reporting period, on-the-ground implementation continued facing diverse challenges: 1) Several procurement processes faced difficulties in securing sufficient number of qualified offers and thus compliance with the applicable World Bank policies and guidelines. These challenges have been addressed successfully through a pro-active and close communication between the PIU and Bank Procurement Specialists, the lesson learnt being that frequent and transparent contact on issues faced between the PIU and the IA and the PIU expressing of doubts as they arise pays off in terms of efficient and fruitful results for the Project; 2) Due to the challenged macroeconomic situation in Argentina, the Government sanctioned various reforms to strongly reduce public expenditure, including centralizing PIU functions across the existing institutional structures within line Ministries and other public entities. The PIU/MAyDS needed to invest considerable time and attention to secure continuity of the PIU whose dissolvement at the final stage of the Project implementation has been considered too risky. The lesson learnt has been on the importance of engaged and tactful addressing of similar challenges within and across involved institutions: the PIU lead did not conform in waiting decisions from above, yet took proactive action to make sure the Project situation is known and understood by decisive parties and in time for beneficial results; 3) Related with the above, practically all of the participating institutions at national, provincial and local level have faced serious budget cuts that have limited their resources and ability to mobilize to the Project area. These challenges have been addressed by careful tailoring of different activities to maximize benefits of inter-institutional collaboration and synergies to minimize costs and maximize results e.g. of each field visit. The lesson learnt is on the priceless importance of close collaboration where results weight more than formalities or institution-specific boundaries; and 4) Concretizing collaboration with OPDS, the Provincial Agency for Sustainable Development has continued with slow progress without clearly identified reason at least by the Bank. The lesson learnt is that similar bottlenecks would require more time and dedication to sit down with the parties, analyze the situation and identify solutions to proceed.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Project implementation in terms of results on-the-ground, disbursements, key indicator results, and dissemination advanced in satisfactory terms during the reporting period as presented under the sections on Rating and Project Indicators. On the contrary, the Project has faced continued administrative/operational delays at all levels from the national Government level, internally within the Bank and in terms of reaching agreements between the Bank and the Adaptation Fund. The Project restructuring based on the conclusions of the mid-term review in April 2017 is a prime and unfortunate example of these delays. The restructuring focused strongly on a need to revise several of the Project indicators as typical for Bank operations, yet revising indicators proved to be in direct conflict with revised operational rules by the AF Board in March 2017, which explicitly disapproved any change in indicators after the submissions of the first annual PPRT. The respective exchange covering legal aspects between the Bank and the AF took until May 2018 to get resolved. Meanwhile, the project assumed a practical approach and attitude focusing on advancing activities on-the-ground in the interest of concrete results for the beneficiary and participating actors than honing up the indicators for their measuring. Overall, the lesson learnt is that complying with three different sets of differing administrative and operational requirements (i.e. those of the national Government and across different institutions, the IA/World Bank and the AF) has been overwhelming for a small grant operation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes have been made to the Project design beyond the several, yet not substantive adjustments presented in the last PPRT and the Project’s Report of the Mid-Term Evaluation / Review and subsequently agreed upon by the AF.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations have remained transversal, yet in practice somewhat limited to the Project activities. Key institutions in the Project area present overall a good representation of women at the decision-making level. In case of the typical profile of the beneficiary farmers, however, the Project works mainly with elder male and often lone small-scale farmers whose families live in the villages nearby. The Project has focused on addressing this profile by generating motivation for change and fostering family-related activities through participation in fairs, etc. In terms of employment by women, the Project has continued successful support to the inter-institutional initiative to create green jobs in the Municipality of Villarino among marginal sectors of the local population through subsidized salaries. The members of the Cooperative Foresta that has been created in this context are mostly unemployed women and are also headed by a woman. The group has advanced remarkably in terms of consolidating, strengthening and diversifying its activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ARG/MIE/Rural/2011/1 - P125804 (BIRF TF15041)
Implementing Entity | WORLD BANK
Type of implementing entity | MIE
Country | Argentina
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 1400 | 350 | 1050 | Total | 1632 | 408 | 1224 | Total
|  | % of female beneficiaries | 9.6% | 9.6% | 9.6% | % of female beneficiaries | 20% |  |  | % of female beneficiaries | 9.6% | 9.6% | 9.6% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 440 | Drought | 4: Effective | Total | 173 | Drought | 3: Moderately effective | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted | 23.22% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 7 | 14.28% | Public |  | 7 | 14.28% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Agriculture | 2: Low capacity | Public | Local | Agriculture | 3: Medium capacity | Public | Local | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 4: Effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local | Public policy | 1 | Agriculture | Local | Public policy | 0 | Agriculture | Local | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.