## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | April 2016 - March 2017 (Year 2)
| Project Title: | Belize Marine Conservation and Climate Adaptation Project (MCCAP)
| Project Summary: | The Belize Marine Conservation and Climate Adaptation Project (MCCAP) is a five year project implemented by the World Bank and funded by the Adaptation Fund grant in the amount of US$ 5.53 million and US$ 1.78 million in-kind contribution by the Government of Belize. The objective of MCCAP is to implement priority ecosystem-based marine conservation and climate adaptation measures to strengthen the climate resilience of the Belize Barrier Reef System. Specifically, the Project will support: (1) improvement of the coral reef protection regime including an expansion and enforcement of the MPAs and replenishment (no-take) zones in strategic locations to build climate resilience; (2) promote sustainable alternative livelihoods and income diversification for affected users of the reef, and (3) build local capacity and raising awareness regarding the importance of the overall health of the reef ecosystem to its climate resilience and, consequently the community welfare as well as the growth prospect of the country's economy. The proposed adaptation, conservation, and restoration activities of the Belize Barrier Reef System have socio-economic significance, providing and opportunity for maintaining and potentially increasing the income level and marine resources available dor an estimated 203,000 people living in the coastal areas of Belize. The Project will build capacity for local communities, which are directly affected by the climate impacts, to act as champions of the marine managed areas and of the resources upon which they depend.
|  | The main components are: (1) Improving the Protection Regime of marine and coastal ecosystem (AF resources: USD 2 million; in-kind contribution by the Government of Belize and NGOs USD 0.415 million). (2) Promotion of viable and sustainable alternative livelihoods for afftected users of the reef (AF resources: USD 2.45 million; in-kind contributions from GOB and NGOs USD 0.368 million). (3) Raising awareness, building local capacity, and disseminating information (AF resources: USD 0.56 million). | [9 empty] | ,
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | BLZ/MIE/Coastal/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Bank | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Belize | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Marine Protected Areas - Corozal Bay Wildlife Sanctuary (CBWS), Turneffe Atoll Marine Reserve (TAMR), and South Water Caye Marine Reserve (SWCMR). Fishing communities - Consejo, Corozal Town, Copper Bank, Chunox, Sarteneja, Belize City, Dangriga, Hopkins, Sittee River, Riversdale, Seine Bight, Placencia | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-08-18
IE-AFB Agreement Signature Date: |  | 2014-08-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 3/17/2015 (Inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-09-25
| Terminal Evaluation Date: | 2020-03-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Reports
1. Annual Operational Plan and Procurement Plan (2016/2017)
2. MCCAP Annual Report (2016)
3. Quarterly and Annual Progress Reports
Technical Documents
4. Review and Revision of the Belize Coastal Zone Act and Regulations: Final Inception Report. (2016)
5. Coastal and Marine Data Centre Progress Report, August 2016.
6. Belize National Queen Conch Assement Report 2017.
7. Assessment of the Spiny Lobster (Panulirus agrus) population in the General Use Zone within the SouthWater Caye Marine Reserve (Close fishing season). 2017
8. Repopulate Reefs within Replenishment Zones of Turneffe Atoll Marine Reserve and South Water Caye Marine Reserve with Temperature Resilient Coral Varieties: Inception Report v 1.2 (2016)
9. Repopulate Reefs within Replenishment Zones of Turneffe Atoll Marine Reserve and South Water Caye Marine Reserve with Temperature Resilient Coral Varieties: Bi-Annual Progress Report 1, 3 January 2017
10. Consultancy for the Realignment of Boundaries and the Creation of New Zones for the Targeted Marine Protected Areas under MCCAP: Inception Report 2016
11. Consultancy for the Realignment of Boundaries and the Creation of New Zones for the Targeted Marine Protected Areas under MCCAP: Report No. 2 Boundary Realignment (2016)
12. A Consultancy to Review and Revise the Draft Forests (Protection of Mangroves) Regulations: Inception Report. 2016
13. Corozal Institute for Technical and Vocational Education and Training. MCCAP Training Project in Cosmetology (2016)
14. Corozal Institute for Technical and Vocational Education and Training. MCCAP Training Project in Food Preparation (2016)
15. Orange Walk Technical and Vocational Education and Training. MCCAP Training Project in Computer Service and Repairs (2016)
16. Orange Walk Institute for Technical and Vocational Education and Training. MCCAP Training Project in Electrical installation (2016)
17. Marine Ecology and Climate Change Special Course: Student Journal 2016
18. Delivery of Training of Youths from the Marine Conservation and Climate Adaptation Project targeted communities by Ecology Project International: Final Technical Report. 2017
19. Marine Ecology and Climate Change Special Course: Education Handbook and Curriculum 2017
20. Training of the Trainers on Climate Change Training, July 4-6, 2016: Workshop Report
21. Climate Change and Marine Protected Areas Knowledge, Attitudes and Behavioural Practices Survey: a KAP survey among fisher folks and households in twelve coastal fishing communities in Belize: Final Survey Report. 2016
22. Corozal Institute for Technical and Vocational Education and Training. MCCAP Training Project in Entrepreneurship and Technology (2016)
23. Corozal Institute for Technical and Vocational Education and Training. MCCAP Training Project in Customer Sevice/ Communications (2016)
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.fisheries.gov.bz/mccap/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  | MCCAP | Dominica
| Name: | Sandra Grant | Dominican Republic
| Email: | pc.mccap@fisheries.gov.bz | Ecuador
| Date: | 2015-03-03 | Egypt
| Government DA | Fisheries Department | El Salvador
| Name: | Beverly Wade | Equatoral Guinea
| Email: | administrator@fisheries.gov.bz | Eritrea
| Date: |  | Estonia
| Government DA | Coastal Zone Management Authority and Institute (CZMAI) | Ethiopia
| Name: | Chantalle Clarke-Samuels | Fiji
| Email: | ceo@coastalzonebelize.org | Finland
| Date: |  | France
| Government DA | Forest Department | Gambia
| Name: | Wilber Sabido | Georgia
| Email: | cfo@forest.gov.bz | Germany
| Date: |  | Ghana
| NIE | PACT | Greece
| Name: | Dennisia Francisco | Grenada
| Email: | ed@pactbelize.org | Guatemala
| Date: |  | Guinea
| MIE | World Bank
| Name: | Enos Esikuri (Team Leader) and Sylvia Michele Diez (Co-TTL)
| Email: | eesikuri@worldbank.org / sdiez@worldbank.org
Date:
| Executing Agency | Ministry of Agriculture, Fisheries, Forestry, the Environment and Sustainable Development (MAFFESD) | Guinea Bissau
| Name: | Jose Alpuche | Guyana
| Email: | ceo@agriculture.gov.bz | Haiti
| Date: | 2015-11-06 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to March 2, 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of March 1, 2017 | US $ 1,058,761.75
Add any comments on AF Grant Funds. (word limit=200) | The Designated account at the Central Bank of Belize is account number 311091. In December 2016 the project account was moved from the Belize Bank to Scotiabank due to limited access to international wire transfers. The Project Account number at Scotiabank is 91595-9142068. Total expenditure for the period from 1 April 2016 to 31 March 2017 is US$ 566,274.12. Project expenditure for the interim period March 3, 2016 - March 2, 2017 (reported on the accrual basis of accounting) amounts to US $ 566,274.12
The cummulative expenditure for the project from inception is US $ 1,058,761.75 (Total expenditure and commitment is an estimated US $ 2, 089,500). Total withdrawal of funds from the World Bank is US $ 1,080,511.34.
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD)
Component 1 - USD 410,479.12
| 1.1 Spatially map and analyse target MPAs for realignment or expansion | 0
| 1.2 Verify spatial mapping via ground-truthing | 3119.05
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback | 6300
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning | 452.5
| 1.5 Consultation feedback and baseline data compiled and incorporated into zoning map | 0
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustment | 0
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries | 0
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones | 110824.4
| 1.9 Biological monitoring of strategic and control sites | 25807.82
| 1.10 Management effectiveness assessments using tracking tools | 0
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up | 76508
| 1.12 Establishment of coral nurseries | 0
| 1.13 Out-planting in selected reefs | 0
| 1.14 Rolling out of the over-arching PA legislation | 0
| 1.15 Initial support to the PA administration structure | 0
| 1.16 Revision of mangrove regulations | 6260.25
| 1.17 Revision of the CZM Act | 14858.75
| 1.18 Implementation of an Integrated Coastal Zone Management Plan | 166348.35
Component 2 - USD 32,001.85
| 2.1 Communtiy needs assessment workshops | 6913
| 2.2 Participatory sub-project planning workshop | 1761.97
| 2.3 Development of business plans | 0
| 2.4 Marketing support for business venture | 0
| 2.5 Training in business development | 0
| 2.6 Training in marketable skills | 23326.88
| 2.7 Sub-grants for initial capital investment to support the startup of business venture | 0
Component 3 - USD 44,080.60
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings | -652.035
| 3.2 Development of BCC strategy and action plan | 0
| 3.3 Implementation of BCC strategy and action plan | 0
| 3.4 Updates of project activities (via quarterly electronic and print newsletters) | 1825.29
| 3.5 Web-based platform | 1405.7
| 3.6 Best practice forum | 0
| 3.7 Learning events, leadership development, training | 41501.65
| 3.8 Strategic planning for the network | 0
Project execution cost (PIU/NIE) - USD 79,712.54
| Coordination and management | 54695.05
| Overheads and administration | 15584.24
| Monitoring and Evalution | 6080.7
| Fudiciary management | 3352.55
| SUB-TOTAL | 566274.115
Contracts awarded, payment to be made
| SUB-TOTAL | 0
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1: Improving the protection regime of marine and coastal ecosystems
| 1.1 Spatially map and analyse target MPAs for realignment or expansion | 0 | Completed
| 1.2 Verify spatial mapping via ground-truthing | 2000 | 2017-06-01
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback | 1000 | 2017-06-02
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning | 6000 | 2017-09-01
| 1.5 Consultations feedback and baseline data complied and incorporated into zoning map | 4000 | 2018-12-01
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustments | 20000 | 2018-02-01
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries | 142000 | 2017-12-01
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones | 118000 | 2018-03-01
| 1.9 Biological and water quality monitoring of strategic and control sites within selected MPAs | 50000 | 2017-03-01
| 1.10 Management effectiveness assessments using tracking tools | 37000 | 2017-10-01
1.11 Ground-truthing to identify reefs suitable for nurseries set-up
| 1.12 Establishment of coral nurseries | 100000 | 2018-03-01
| 1.13 Out-planting in selected reefs | 0
| 1.14 Rolling out of the over-arching PA legislation | 0
| 1.15 Initial support to the PA administration structure | 0
| 1.16 Revision of mangrove regulations | 7000 | 2017-06-01
| 1.17 Revision of the CZM Act | 165000 | 2018-03-01
| 1.18 Implementation of an integrated Coastal Zone Management Plan | 126000 | 2018-03-01
Component 2: Promotion of viable and sustainable alternative livelihoods for affected users of the reef
| 2.1 Community needs assessment | 5000 | 2018-03-01
| 2.2 Participatory sub-project planning workshop | 5000 | 2018-03-01
| 2.3 Development of business plans | 0
| 2.4 Marketing support for business venture | 0
| 2.5 Training in business development | 0
| 2.6 Training in marketable skills | 40000 | 2018-03-01
| 2.7 Sub-grants for initial capital investment to support the startup of business venture | 1200000 | 2018-03-01
Component 3: Raising awareness, building local capacity and dissemination of information
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings | 0 | Completed
| 3.2 Development of a BCC Strategy and Action Plan | 40000 | 2017-12-01
| 3.3 Implementation of a BCC strategy and action plan | 82000 | 2018-03-01
| 3.4 Updates of project activities | 6500 | 2018-03-01
| 3.5 Website platform | 2000 | 2018-03-01
| 3.6 Best practice forum | 0
| 3.7 Learning events, leadership development, training | 88000 | 2018-03-01
| 3.8 Strategic planning for the network | 55000 | 2018-03-01
Project execution cost (PIU/NIE)
| Coordination and management | 93000 | 2018-03-01
| Overheads and administration | 27000 | 2018-03-01
| Monitoring and Evalution | 34000 | 2018-03-01
| Fudiciary management | 35000 | 2018-03-01
| TOTAL | 2490500
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is not applicable to this programme
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 6
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Services | Andrea Tillett (shared cost) | 25800 | August 10,2014 | 15050 | 10750
Service | Dr. Sandra Grant | 72600 | March 10,2015 | 68738 | 3862
Service | Saleem Chan | 30300 | September 9,2015 - February 28,2016 | 15849.42 | 0
Service | Belize Environmental Technologies | 51395 | August 31,2015 | 51395
Goods | Caribbean Motors | 46800 | June 5,2015 | 39,800 paid (7,000 duty & tax exemption) | 0
Goods | Belize Estate Company Ltd. | 80693.2 | January 22,2016 | 80693.2 | 0
Goods | William Quan & Company | 116955.5 | February 8,2016 | 11695.54 | 0
Goods | Fultec Systems | 33034.16 | March 1,2016 | 33034.16 | 0
Goods | William Quan & Company | 35223.75 | March 16,2016 | 35223.75 | 0
Services | Ellis Requena | 9608.3 | 2016-03-23 | 8006.9 | 1601.4
Services | Gilbert Andrews | 13200 | April 14,2016 | 10450 | 2750
Services | Ian Gillett | 11395 | May 30,2016 | 6325 | 5070
Services | Fragments of Hope | 340592 | June 9,2016 | 74242.4 | 266349.6
Goods | Sigertronic Systems | 15412.5 | July 4,2016 | 15412.5 | 0
Services | Elisa Montalvo | 20000 | July 5,2016 | 6000 | 14000
Goods | Belize Formulators Ltd | 46885.66 | September1,2016 | 46885.66
Services | Agrer, Grupo | 163380 | September 13,2016 | 19425 | 143955
Goods | 10 Outboard Engines | 127953 | September 29,2016 | 58767.25 | 69185.75
Non- Consulting Services | Linda Mckesey | 3400 | October 15,2016 | 1025 | 2375
Services | Institute for Technical and Vocational Education and Training - Orange Walk | 30270 | October 20,2016 | 13621.5 | 16648.5
Services | Institute for Technical and Vocational Education and Training - Corozal | 21437.5 | October 24,2016 | 9646.87 | 11790.63
Services | Nidia Chacon | 30300 | October 24,2016 | 8274.23 | 22025.77
Services | Ecology Project International | 42400 | October 27,2016 | 37651.2 | 4748.8
| TOTAL | 1369035.57
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Project Coordinator; IC method; D.O.C. December 15,2014 | Vincent Gillett |  |  | Applicant was selected after shortlist and interviews
Ryan Zuniga
| Sandra Grant |  | 36300
Mauro Gongora
Herbert Haylock
Armid Thompson
Colin Gillett
Senior Technical Officer, IC method; D.O.C May 28,2015 | Eric Wade |  |  | Applicant was selected after shortlist and interviews; (Mr. Chan resigned on February 2,2016)
Abraham Alamilla
David Perez
Ramon Carcamo
Ruth Gutierrez
Keisha Rodriguez
Siobhan Lozado
| Seleem Chan |  | 30300
Ryan Zuniga
Antione Devonshire
Developing & Implementing Knowledge,Attitude,Behaviour Practice Survey (KAP Survey); CQS method; D.O.C June 15th 2015 | Compass Communication & Research |  |  | Highest Ranked Firm based on Expression of Interests submitted, who subsequently submitted a combined technical financial proposal for which the contract was negotiated on.
Saunders Consultancy
| Belize Environmental Technologies | 51395 | 51395
Supply & Delivery of 1 only 4x4 Pickup Truck, Shopping Method; D.O.C -May 4,2015 | Bravo Motors | 44168 |  | Lowest evaluated bidder; bidder met all specification requested; Other bidders were non- responsive
| United Motors | 44644.12
| Caribbean Motors | 46800 | 46800
| Belize Diesel & Equipment | 48802.85
| Belize Estate & Co. Ltd | 52071.3
Supply & Delivery of 2 only 4x4 Pickup Truck; Shopping Method; D.O.C - November 4,2015 | Belize Estate & Co. Ltd | 80693.2 | 80693 | Lowest price responsive bidder
| Bravo Motors | 81775
| Belize Diesel & Equipment | 89771.57
Supply & Delivery of Vessels; NCB method; D.O.C - December 11,2015 | William Quan & Company | 116956 | 116956 | 2 suppliers bought bid document, however only William Quan submitted Bid which was subsequently evaluated and passed evaluation.
Consultanting service to re-populate coral reefs in Turneffe Atoll Marine Reserve and South Water Caye Marine Reserve; Single source selection (FIRM) method; D.O.C - Not yet signed | Fragments of Hope | 340592 | 340592 | Single source procurement has been approved by the World Bank (3 September 2015) and is consistent with the World Bank's procurement policy and national policy.
Supply & Delivery of 7 desktop computers, 7 laptops, 1 rugged laptop;Shopping;D.O.C - 23 Nov. 2015 | GS-Com | 28648.12 |  | Lowest Evaluated Bidder
| Fultec Systems | 33034.16 | 33034.16
| 501 Enterprise | 34788.69
Supply & Delivery of 3 Boat Trailers; Shopping mehod;D.O.C - 12 Feb. 2015 | William Quan | 35223.75 | 35223.75 | 3 Suppliers were invited to bid, however only 2 summited bids. William Quan was lowest evaluated bidder that met all specifications..
| Duke Marine | 25900
Boat Captain ;IC method; D.O.C - 27 Oct.2015 | Jerome Gill |  |  | Recommended consultant after evaluation
| Ellis Requena |  | 9608.3
Andre Staine
Environmental lab Technician;IC method; D.O.C - 27 Oct. 2015 | Luis Gongora |  |  | Recommended consultant after evaluation
Raphael Martinez
| Gilbert Andrews |  | 13200
Tyrell Reyes
Realignment of Boundaries and Creation of New Zones for the Targeted Marine Protected Areas under MCCAP; IC method ;D.O.C - 27 October 2015 | Andrew Link |  |  | Recommended consultant after evaluation
| Ian Gillett |  | 11395
Jaime Alvarez
Eugene Ariola
Supply & delivery of enforcement Equipment-12 handheld GPS with marine mount; Shopping Method; D.O.C - 10th May 2016 | GS COM | 11677.5 |  | Lowest evaluated bidder
| Sigertronics System | 15412.5 | 15412.5
| Fultec Systems | 18342.89
Review and Revise the Forest (Protection of Mangroves) Regulations; IC method ;D.O.C. - 6 March 2016 | Magali Marin Young |  |  | Recommended consultant after evaluation
Mark Usher
Winston MaCalla
| Elisa Montalvo |  | 20000
Ismael Fabro
Supply Equipment for WQM program; Shopping method;D.O.C. - 26 July 2016 | Scientific Supplies & Technology USA | 42531.85 |  | Lowest evaluated bidder; bidder met all specification requested
| Belize Formulators | 46885.66 | 46885.66
| Belize Environmentally Sustainable Solutions &Technology | 81635.09
Procurement Officer for MCCAP; D.O.C 10 August 2014 | Andrea Tillett |  | 25800 | WB NO objection to shared cost with KBA project provided on 11 July 2016. MCCAp will pay salary from July 2016 to August 2017
Revision of Coastal Zone Management ACT and Regulations;CQS method; 27 Oct. 2015 | Belize Environment Technologies (BET), |  |  | Highest Ranked Firm based on Expression of Interests submitted, who subsequently submitted a combined technical financial proposal for which the contract was negotiated on.
Environmental Solutions Ltd
Sofia Galvo Advogadas
Amec Foster Wheeler
Coferpeche
| Agrer |  | 163380
Pramod Ganapathiraju
Supply & Installation of 10 Outboard Engines; NCB method;D.O.C - 29 July 2016 | Marelco | 127952.5 | 127952.5 | Lowest evaluated bidder;
| William Quan | 181940
Patrols in CBWS (Accommodations); shopping; D.O.C - 14 March 2016 | Mr. Eleazar Chan | 1500 |  | Lowest evaluated Bidder; Vendor provided better suited accommodations.
| Mrs. Linda Mckesey | 3400 | 3400
skills training to facilitate the communities transition to alternative livelihoods; direct contracting | Institute for Technical and Vocational Education and Training - Orange Walk |  | 30270 | WB No Objection to t contract was received on 19 Oct 2016
skills training to facilitate the communities transition to alternative livelihoods; direct contracting | Institute for Technical and Vocational Education and Training - Corozal |  | 21437.5 | WB No Objection to contract on 14 Oct 2016
Senior Technical Officer;IC method; D.O.C.- 1 March 2016 | Safiria Vasquez |  |  | Applicant was selected after shortlist and interviews;
Renison Enriguez
Shalini Cawich
Ryan Zuniga
Kalen Eck
| Nidia Chacon |  | 30300
Conduct training event for youth on marine conservation and climate adaptation; direct contracting | Ecology Project International |  | 42400 | WB No Objection to Contract received on 25 October 2016

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Project Stakeholder Risks
1.1 Some stakeholders (local communities, land owners, and/or NGOs) may not support the proposed activities (e.g., the proposed expansion of MPAs). | Low | Consultations with local communities, Co-managers, and regulator agencies continued under the implementation phase. Project Implementing Agency Group (PIAG)/Project Implementing Unit (PIU) staff and Fisheries Department staff visited all 12 communities to build awareness of the project and start the discussion on potential livelihood activities. MCCAP consults and collaborate with organizations at multiple levels:
Regional level: (1) The Caribbean Community Climate Change Centre (CCCCC) - on climate change related issues, mainly training (MCCAP staff and line Ministries), climate change clubs in Secondary schools. (2) Caribbean Regional Fisheries Mechanism (CRFM) - fisheries and enforcement related issues. (3) Caribbean Network of Fisherfolk Organizations (CNFO) - issues related to fishermen
National Level: (1) Government Organizations - Fisheries, Coastal Zone Management Authority & Institute, Agriculture, Tourism, National Climate Change Office, Environment, Forest. (2) Non-government Organizations - Belize Federation of Fishers, Belize Fishermen Cooperative Association, Sarteneja Allience for Conservation and Development, The Nature Conservancy, Southern Environemental Association, Turneffe Atoll Sustainability Association, Wildlife Conservation Society, Fragments of Hope, Belize Audubon Society, OCEANA, Belize Red Cross, Pan American Development Foundation, National Protected Area System Secretariat.
Community level: (1) Target communities - Consejo, Corozal Town, Copper Bank, Chunox, Sarteneja, Belize City, Dangriga, Hopkins, Sittee River, Riversdale, Seine Bight, and Placencia. (2) Community Groups - Copper Bank Fishermen Association (FA), Chunox FA, Sarteneja FA, Sarteneja Homestay Group, Sarteneja Tilapia Growers and Development Association, Sarteneja United FA, Belize City Central FA, Wabufu FA, Hopkins FA, Placencia Producers Group.
Projects: (1) Belize Enterprise for Sustainable Technology (BEST)/Japan Social Development Fund grant), Conservation of Marine Resources in Central America (MARFund/German kfw project) and Management and Protection of key Biodiversity Areas in Belize Project (KBA/GEF)
The results of the KAP survey will provide information on knowledge of community and fishers on the Project and climate change. Based on these results the PIAG will organize an appropriately scaled awareness raising campaign to increase the understanding of sub-project activities and the inclusion of sound environmental and social safeguards including climate proofing sub-projects.
2. Operating Environment Risks
2.1 Future Governments may not support the goals, targets and commitments of the Project | Low | Continuous updating on Project activities and expected results is communicated to new members/employee of regulator organizations, co-managers, fishers, etc. Since the General Election November 4, the PIAG spent time updating new members of the TAC and PSC. MCCAP information documents are sent to interested parties, background justifications documents are prepared and distributed (as requested), one-on-one meetings are held to update committee members. Continuous information sharing and networking is required to ensure support for the Project.
2.2 The Government does not meet certain policy and regulatory commitments (e.g., restrictions on ability to de-reserve, additionality commitment, etc.) in accordance to mutually agreed targets (UE, UNDP-GEF, WB-GEF) as in the past projects (e.g., GEF project) | Low | The Government's commitment has been confirmed at the Ministerial level through on-going efforts to improve regulatory and institutional framework of MPAs and coastal zones.
3. Executing Entity Risks (including FM & OR Risks)
3.1 The Executing Entity selected for the Adaptation Fund Project is not equipped with enough capacity to manage the financial transactions and to implement the climate adaptation measures in the future. | Medium - Low | Training PACT and MCCAP staff - Project Coordinator (MCCAP) and Procurement Officer (PACT) trained at the World Bank Caribbean Project Implementation Workshop in Dominican Republic, June 8-11, 2015 in Safeguards and Procument procedures
World Bank supervision and mentoring - The World Bank provides the much needed technical and financial capacity building required for the initial stage of project implementation. Specifically to staff at MCCAP and PACT in the areas of project management, procurement, financial management, disbursement, etc., and the process of preparing technical and procurement documents. Main support comes from the Team Leader Mr. Enos Esikuri - visited Belize/the Project twice last year (March and September 2015) including numerous phone calls to provide technical guidance. (2) Sylvia Michele Diez - technical support almost daily, including follow up on the review process of approving technical and financial documents at the WB. (3) Yingwei Wu - procurement Specialist, reviewed MCCAP procurement plan twice in Belize and provided guidance on the drafting of procurment plans and the utility of it. (4) David I - Financial Specialist, reviewed MCCAP budget/finances once in Belize and provided PACT with the support needed to effectively execute the financial aspects of the project.
Before the Project effectiveness, the World Bank provided retroactive financing of USD 140,000 to enhance the capacity of the PIAG with technical and administrative staff.
PACT was recently accredited by the Adaptation Fund as the National Implementing Entity (NIE) for Belize and is therefore equipped with the requisite personnel and experience to oversee the execution of the project.
3.2 The governance structure, operational guidelines and other institutional policies of the PACT are altered over time and do not conform to the adequate standards | Low | PACT is a statutory Body established by the Protected Areas Conservation Trust Act, No. 15 of 1995 and governed by a Board of Directors. Its jurisdiction is expressly set out in the Act, therefore, makes switching, sharing or evasion of responsibility more difficult.
3.3 Fraud and corruption occur after the proposed Project is completed | Low | MCCAP established internal control system set out in the Operations Manual for MCCAP - revised May 2015, to systematically review expenditures to ensure they are in-line with work plans and the objectives of the project.
MAFFESD does the following: (1) Implementing Entity (Forest, Fisheries, CZMAI) submits budget and workplan to PIAG. (2) Implementing Entity forward request for purchase of goods and services to PIAG. (3) Project Coordinator (PC) ensures that request is consistent with project budget and workplan. (4) PC forwards purchase order request signed appropriately with proper support documents to PACT.
PACT does the following: (1) Ensures expenditures are in compliance with budget and supporting documentation is adequate. (2) Prepares purchase order/payment with authorized signatures. (3) Process payment based on invoices from vendors and attached source documents. (4) Reports irregularities to the PSC for immediate action.
Implementing Entity conducts activity/action and provide technical reports to support expenditure
The Technical Advisory Committee (TAC) and Project Steering Committee (PSC) meets every two months and three months respectively to review technical and financial activities
4. Project Risks
4.1 Program of climate change adaptation measures is too ambitious | Low | The activity build upon or scale up on-going efforts in the country and are complemented by the programmes under the Bank's Country Partnership Strategy
4.2 Downstream conservtion and climate adaptation activities will create social and environmental concerns | Medium - Low | The operational manual of the Project mandates that all activities supported by the Project comply with safeguard policies of the World Bank
4.3 Other donor's programme overlaps with the proposed activities | Low | Donor coordination is done by the PIAG, MAFFESD, and PACT
4.4 Alternative livelhoods activities may not be implemented or may be poorly implemented | Medium - Low | The first year was spent understanding the targetted communities within the context of the Process Framework, IPP and EMF. Additional information was captured in the Knowledge, Attitude and Practice (KAP) survey to understand their knowledge of and importance of the Marine conservation, climate change, and the impact of MPA restriction. Previous attempts have been unsuccessful at changing attitudes and behaviour towards fishing, but we hope by targetting older fishers to adopt a new livelihood activities, diverting youths from fishing to other livelihood options, and encouraging women to engage in economic activities the Project will be able to restore livelihoods and change economic portfolio of households.
In Belize, the success rate of programs with one of the core objectives being to encourage targeted beneficiaries to engage in alternative economic activities has been abysmal. This low success rate results in most programs failing to achieve their objectives. The Alternative Livelihood Forum (January 2016) stimulated an open problem solving discussion on improving the success rate of the adaptation of sustainable alternative livelihoods by targeted beneficiaries. With participants from NGOs, Government organizations, financial institutions, the forum identified opportunities, barrier/challenges and recommendations to improve to sustainable diversify the economic activities of programme beneficiaries.
A review of past and current projects that offered sustainable livelihoods options, such as Belize Rural Development Project, Toledo Institute for Development and Environment, BEST, etc. The lessons learnt were particularly noted and will be applied as required.
In view of the above, the PIAG formed synergies with the Agriculture Department and Ministry of Tourism to apply best practice livelihood activities that has been tried and proven by these departments and to get community by-in for these processes. The PIAG will look at the overall enabling environment for successful livelihood sub-projects and not only support the economic activity, but also provide training, capacity building, market studies, etc., as required. The PIAG will also provide the network needed with the relevant government departments to ensure the livelihood activity is sustainable. Part of the sub-project concept note assessment is to determine the type of help communities/groups need to develop and executed successful livelihood project, and provide the assistance needed within the scope of the Project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Belize's vulnerability to natural hazards, capacity and resource limitations could constrain sustainability of the project achievements. Even if the Project succeeds in removing the local stressors, it may not be enough for the reef’s survival in the face of climate change | Medium-low | The Bank continues to assess the resource issue and mitigate it with efforts to support the Government seeking additional resources for continued activities.
The PIAG is not able to manage the procurement process in a timely way. | Low | PACT has staff trained to administer and monitor the procurement process to properly spend donor grant funds. Procurement process reviews by the WB are conducted periodically.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
A number of risk mitigation measures were employed during the current reportng period (as stated above). Thus far the Project has been able to reduce the risks and kept project activities going by working closely with line ministries and other government departments. In many cases, line ministries do the work required or assist the Project with Administrative work/use of vehicles etc. This arrangement has reduced potential risks for the Project.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Inception Phase |  | Project Launch and Inception Workshop completed |  | Completed | S
| Establishment and Activation of Governance Structure |  | Project Implemention Unit, Project Steering Committee and Technical Advisory Committees established and functional |  | Activities on-going. Conducted 4 TAC and 4 PSC meetings during the year | S
| Project implementation |  | Operating documents finalized |  | No major revision required | S
|  |  | Full staff complement to implement project activities; office established |  | The PIAG office now has its full staff complement: Project Coordinator – employed March 2015; Administrative Officer – employed April 2016; and Senior Technical Officer – October 2016. Approval was given for the Procurement Officer fees to be co-payed by the Key Biodiversity Project and MCCAP. The Project Coordinator and Procurement Officer participated in the World Bank annual Caribbean Fiduciary and safeguard workshop in Santo Domingo, Dominican Republic, May 23-25, 2016. The Procurement Officer participated in the World Bank Procurement Workshop to review the new procurement framework for investment project financing in Grenada on November 8-10, 2016. The Fisheries Administrator participated in the High Level Segment of the COP13 of the Convention of Biological Diversity to address the issue of mainstreaming biodiversity within the fisheries sector, in Cancun, Mexico, December 2-3, 2016.
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sandra Grant
| Email: | pc.mccap@fisheries.gov.bz
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| 1.1 Spatially map and analyse target MPAs for realignment or expansion |  | Stakeholder consultations completed |  | First meetings in a series of consultations with reserve managers, fishers and key stakeholders were successfully held to discuss MPA expansion and Replenishment Zone. The meetings were conducted in the northern communities (Corozal, Sarteneja, Copper Bank, and Chunox), Belize City, and southern communities (Dangriga, Hopkins, Placencia, Seine Bight) to discuss MPA expansion and replenishment zones for CBWS, TAMR, and SWCMR. Over 190 fishers, NGO community, Co-managers participated in the first consultation. | S
Second round of consultation completed with Regulatory agencies, Co-managers, and NGOs. The consultations allowed the Fisheries Department to incorporate all major stakeholder view in the maps. GIS expert contracted to document and verify GPS points of the expansion and replenishment zones. Second consultation conducted with NGO’s, co-managers etc., April 19, 2016 to review the recommendations from the fishermen consultations.
| 1.2 Verify spatial mapping via ground-truthing |  | Ground-truthing completed |  | GIS consultant contracted on May 30, 2016. Inception report approved by the PIAG, TAC, and the PSC. Completed ground truthing in South Water Caye Marine Reserve, Turneffe Atoll Marine Reserve and Corozal Bay Wildlife Sanctuary to aid in verification of the image data (maps and remote sensing data) to real features on the ground. The ground truthing team included the Fisheries Department, the consultant, Lands and Survey Department, and co-managers. | S
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback |  | Activity on-going |  | A task force was formed to provide technical guidance to the process, they met on November 15, 2016 to review and comment on the revised maps. The Task Force include the Fisheries Department, Forest Department, Sarteneja Alliance for Conservation and Development, Turneffe Atoll Sustainability Association, University of Belize, Lands and Survey Department, and the Consultant. Seventeen stakeholders attended the meeting from the Departments mentioned above. Draft maps were presented to Co-managers' Board or Steeing Committee for further review and comments. | S
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning |  | No action required in year 2 |  |  | N/A
| 1.5 Consultation feedback and baseline data compiled and incorporated into zoning map |  | No action required in year 2 |  |  | N/A
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustment |  | No action required in year 2 |  |  | N/A
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries |  | No action required in year 2 |  |  | N/A
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones |  | Enforcement fleet improved |  | Repaired one enforcement vessel | S
|  |  | Patrols increased |  | Increased patrols in TAMR, CBWS, SWCMR by providing monthly allocation of fuel and accommodation and transportation for enforcement officers. MCCAP provides fuel to patrol South Water Caye Marine Reserve by the Reserve Staff in the northern area and the Conservation Compliance Unit - Punta Gorda in the southern area of SWCMR. All enforcement activities in SWCMR is currently being reviewed to mainstream and formalized all enforcement activities by the Fisheries Department. SWCMR will benefit from a fully equipped patrol vessel and SMART system to document all enforcement activities incuding infractions. The Reserve will also include the Coast Guard in all enforcement operations. | S
Established joint patrol for the Corozal Bay Wildlife Sanctuary between Sarteneja Alliance for Conservation and development, Fisheries Department, Forest Department, Coast Guard, and Customs Department. MCCAP rents a house by the coast to house personnel from the various agencies. Two joint patrol meetings were held to discuss agencies roles and responsibilities and reporting procedures.
The first joint patrol meeting with Turneffe Atoll Sustainability Association, Fisheries Department, Coast Guard and MCCAP was held June 28, 2016. The meeting established agencies roles and responsibilities and reporting procedures. To date TASA constructed 2 field stations at Maugre Caye and Calabash Caye. These stations will be used by the Fisheries Department staff to launch enforcement activities with TASA staff and Coast Guard.
The Fisheries Department was impacted greatly by the Hurricane Earl that made landfall on August 4 as a category 1 hurricane near Belize City. The pier and vessel landing facilities were destroyed; which will impact enforcement activities. There was urgent need for the use of trailers purchased under MCCAP to be mobilized to assist in the launching of vessels.
Patrols in the targeted three MPAs ongoing.
|  |  | Capacity building |  | Conducted a 5 days training with 21 participants from Coast Guard, Fisheries Department Marine Reserve and Conservation Compliance Unit, and Co-managers (Belize Audubon Society, Turneffe Atoll Sustainability Association, Southern Environmental Association) in fisheries enforcement, prosecution, small craft handling, engine maintenance, and Spatial Monitoring and Reporting Tool (SMART) a new enforcement software. A Draft Comprehensive Enforcement Training Manual was developed as a training guide for Enforcement Officers. The Manual will be finalized and circulated to the various partner/agencies. | S
MCCAP sponsored one-on-one training with organizations to ensure officers working with co-managers receive further enforcement support. The trainers from the 5-day training visit co-managers and accompany them on enforcement activities and provide additional support where needed. Officers are given additional assignments to be completed and submitted.
Engine maintenance training conducted in collaboration with Marelco Ltd., only certified distributor of Yamaha outboard engines in Belize, on November 10, 2016. The objectives of the meeting were to review maintenance requirements for Yamaha outboard engines and to assess the status of the Fisheries Department outboard engine fleet and to develop a maintenance schedule. Over 35 officers participated in the meeting, including Fisheries Department, co-managers, and Coastal Zone Management Authority and Institute
|  |  | Enforcement equipment provided |  | Enforcement equipment purchases made to date are 2 vessels, 8 outboard engines, 10 GPS, and 2 trailers. | S
| 1.9 Biological monitoring of strategic and control sites |  | Biological monitoring within Marine Reserves initiated |  | (A) Assessment of the Spiny Lobster (Panulirus agrus) population in the General Use Zone within the South Water Caye Marine Reserve during the closed season (See Technical Report). | S
A total of 71 of 75 wooden lobster traps were retrieved during 4 trips to South Water Caye Marine Reserve. The sample population consisted of a total of 450 lobsters. The lobster captured and recorded were all juveniles with majority in the post molting state and about 1% in the pre molting state. Most lobsters reached a maturity level of stage 1 with a small percentage at stage 2 and 3. The assessment ended prematurely with the loss of all traps due to the passing of category 1 hurricane Earl. It is recommended that the traps should be rebuild and a post hurricane assessment done to determine recovery levels within South Water Caye Marine Reserve. Pre assessment report is being prepared by the Fisheries Department.
(B) Conch Assessment - The Fisheries Department conducted its once every 2-year national underwater survey to assess the Queen conch (Strombus gigas) population to determine the potential yield that function as the basis for the allocation of a conch quota. The objectives of the National Queen conch survey were to: (1) assess the distribution and abundance of Conch in the eight fishing areas (Managed Access areas, 2016) including marine reserves; (2) collect morphometric data on conch from each area (e.g. shell length and lip thickness for adult conch); determine the Maximum Sustainable Yield (MSY) of Queen Conch for Belize; and determine the Total Allowable Catch for the 2016/2017 conch fishing season and its allocation to the Cooperative societies.
The conch assessment began with a training workshop to explain the methodology (sampling theory and morphometric) intended to be used to conduct the national conch survey 2016; and to determine the sample size for each new fishing area assigned by the Managed Access programme. Twenty-five Fisheries Officers (Biologists) participated in the workshop. As part of the training a mock survey was carried out near St. George’s Caye.
During the period September 15-30, eleven teams of 4 persons (Fisheries Officers/Biologists and students from the University of Belize) conducted underwater visual survey of specific conch habitats. Team members dived 100m X 4m belt transects and gathered all the conch that were found at survey sites. The shell length and thickness were measured and recorded. The study estimated the density of legal adult conch for each transect, total abundance of legal adult conch, and potential yield based on the Surplus Production Model where Fox Model was applied to estimate Maximum Sustainable Yield (MSY). A total of 7,020 conchs were measured during the 2016 study. Mean density was estimated at 263 conch/ha with the highest densities in Turneffe Atoll. Queen conch abundance was estimated at over 9,000,000 legal size individual conch available to the fishery for the 2016/17 conch fishing season (See Technical Report).
| 1.10 Management effectiveness assessments using tracking tools |  | Initial activities started |  | TOR Management effectiveness assessment for Turneffe Atoll Marine Reserve approved by TAC, PSC and the World Bank. Procurement process on-going. | S
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up |  | Consultations, training, establish reseach protocols, identify stakeholders |  | Contract with Fragments of Hope (FoH) signed 9 June 2016. Inception report approved by TAC, PSC, WB. Literature review and initial stakeholder consultation completed, and bi-annual report submitted. | HS
Meeting/Consultations: (A) Updates on project activities given at National Coral Reef Monitoring Network meeting in September. (B) Three community consultation held for South Water Caye Marine Reserve stakeholders: (1) Dangriga (Mars Place) – 11 October, 2016 with 21 participants (33% females) from different stakeholder groups (Fishermen Association, Hoteliers, etc.) of which 18 wanted to participate in the restoration course. (2) South Water Caye (Blue Marlin Lodge) – 13 October, 2016 with 15 participants (27% female). (3) Hopkins (Hopkins Primary School) – 20 October, 2016 with over 31 participants (19% female) mainly from the Stann Creek Tour Guide Association of which 16 wanted to participate in the restoration course. (C) Planned community consults for Turneffe stakeholders at Calabash Caye Dec 9, 2016. (D) A meeting was held in Belmopan December 22, 2016 with Dr. Leandra Cho-Rickett (ERI marine director) and their staff biologist. In this meeting it was agreed UB will assist FoH with a minimum of monthly monitoring of the established nursery tables, and more ERI staff will participate in the next scheduled Reef Replenishment training. (E) The Consultant met with team member Claire Paris (University of Miami) to discuss coral larvae dispersal map.
Mapping of South Water Caye Marine Reserve - 12-16 October three FoH members (Dale Godfrey, Mariko Wallen & Lisa Carne) mapped acroporids, nursery and outplant locations in SWCMR.
In November, FOH: received vials for coral sampling (genetics); Purchased equipment for project activities, namely temperature loggers, ID tags for nurseries, etc.; Ordered and received training manuals for 3-day reef replenishment training course (tentatively planned for mid-late Jan 2017).
Acroporid samples were collected from both reserves for coral host and symbiont genetics in November and December 2016 (note this activity is on-going, the first set of samples were sent to Dr. Baums’ laboratory January 2017).
The first training - Coral Replenishment Methods in Belize - 25-27 January 2017, in Placencia Village with field activities conducted at the Laughing Bird Caye national Park. The training focused on background, history, biology and ecology of coral replenishment work in Belize. Field work included harvestin nursery-grown corals from the nursery, transportation of corals, preparing outplanting sites, outplanting corals. The twelve participants represented the Fisheries Department, Turneffe Atoll Sustainability Association, Stann Creek Tour Guide Association, University of Belize, and Southern Environmental Association.
Further consultations are being planned for Chunox Village (Feb 16) and Belize City (Feb 25) for fishers operating on the Turneffe Atoll.
| 1.12 Establishment of coral nurseries |  | Establishment of suitable coral nurseries in South Water Caye Marine Reserve and Turneffe Atoll Marine Resere |  | In September, materials for four table nurseries were purchased; they are assembled and ready to be installed. On 29 November 2016, FOH installed one complete and one partial table nursery at South Water Caye Marine Reserve with A. cervciorinis (2 genotypes, 6 ropes) with a total number of 64 starter fragments (Acropora cervicornis). Two completed and one partial nursery were installed at Turneffe Atoll Marine Reserve in December 2016 with a total number of 279 starter fragments (three acropora taxa). | HS
| 1.13 Out-planting in selected reefs |  | No action required in year 2 |  |  | N/A
| 1.14 Rolling out of the over-arching PA legislation |  | No action required in year 2 |  |  | N/A
| 1.15 Initial support to the PA administration structure |  | No action required in year 2 |  |  | N/A
| 1.16 Revision of mangrove regulations |  | Mangrove regulations drafted |  | Revision of the mangrove regulations - The objective of the Consultancy is to finalize the Draft Forests (Protection of Mangroves) Regulations 2014 (sic) to enable improved management of mangroves in an effort to ensure sustainable coastal development. This Consultancy is primarily a Legislative Drafting exercise. Contract signed; inception report approved by TAC, PSC, and WB. | S
Consultant conducted initial consultations with key stakeholders (Deputy Solicitor General, representative from UNESCO, Forest Department, etc.)
Consultant conducted literature review of any existing technical studies, reports, policy documents and other background documents relevant to the consultancy, including a detailed review of the draft regulations.
Task force formed, comprising Forest Department, Fisheries Department, World Wildlife Fund, Attorney General’s Ministry, Lands and Survey Department, Department of the Environment, Independent participant, Fragments of Hope, Coastal Zone Management Authority and Institute. Two meetings of the Task Force were organized to provide valuable inputs to the revision of the Regulations. Based on the information provided the Consultant will finalize the drafting notes for submission to the Forest Department.
Consultant completed drafting notes for the revised Mangrove Regulations. The document was sent by the Forest Department to the Solicitor General's Office where they will finalize the Regulations.
| 1.17 Revision of the CZM Act |  | CZM Act drafted |  | Revision of Coastal Zone Management Act and Regulations – The overall objective of the consultancy is to conduct a review of the Coastal Zone Management Act (CZM) of 1998 to strengthen the legal, policy and institutional framework within which the new ICZM Plan (2016) will be implemented as well as to address key gaps, challenges and opportunities for improvements to the process for integrated management of the coastal zone. | S
The consultancy is therefore designed to: (1) conduct a review of the existing CZM Act of 1998 and Regulations and; (2) conduct an institutional review of the Coastal Zone Management Authority and Institute (CZMAI) of Belize to help strengthen the legal, policy and institutional framework within which the new ICZM Plan (2016) will be implemented as well as to address key gaps, challenges and opportunities for improvements to the process for integrated management of the coastal zone.
Agrer was contracted to undertake this activity. The first preliminary meeting was held on November 1, 2016 with members of the Agrer team, Coastal Zone Management Authority and Institute (CZMAI), and the PIAG. During that week the consultants were able to meet with members of the Coastal Advisory Committee and the CZMAI board.
Inception report approved by CZMAI, TAC and PSC.
| 1.18 Implementation of an Integrated Coastal Zone Management Plan |  | Water Quality personnel and lab equipment in place |  | Developed a Water Quality Monitoring (WQM) protocol which will be discussed with other relevant agencies. Purchased a vehicle, 30 ft vessel with engines and trailer, and computer and laptop to assist in WQM. Hired a Boat Captain/Water quality Assistant and a Laboratory Technician. Started in-house training for the lab Technician and Boat Captain in field water quality data collection. Purchased 3 Sondes and accessory field equipment to take water samples. Training of Boat Captain and Lab Technician in field data collection with Sarteneja Alliance for Conservation and Development in the Corozal Bay Wildlife Sancturay. The CZMAI Officers spend 3 days with SACD staff to calibrate their new Sonde equipments and practice collecting samples for WQM. | S
On Friday 21st October 2016, the CZMAI Water Quality Monitoring Unit deployed the three YSI EXO II Sondes in the Belize River. The sonde was placed within a customized stainless steel cage and embedded into the river bed using stainless steel legs attached to the cage. After deployment and installation, the CZMAI Coastal Planning and Monitoring Unit visited each sonde on a weekly basis for the first month to ensure that Sondes were still in place and functioning properly. Following this time period, the Sondes will only be serviced once a month for data download, calibration and cleaning. On November 18th 2016, they performed the first servicing of the sonde, and downloaded data and exchanged batteries.
To date efforts have been focused on acquiring all the necessary equipment, labware, and reagents for lab analysis of water samples (99% of equipment received). To this end, CZMAI WQM unit will begin to transition into the testing phase by finalizing protocols, setting up lab space, calibrating equipment, and preparing lab space. WQM Unit began mock testing during the first week in December.
|  |  | Inventory of development sites for Ambergris Caye, Central and Caye Caulker |  | The purpose of the inventory is to establish a spatial and temporal baseline for human use of coastal and marine resources in tandem with the implementation of the Belize Integrated Coastal Zone Management (ICZM) Plan. The inventory will serve as an important tool for monitoring and assessing compliance with the ICZM Plan. | S
Tools acquired to assist in compilation and analysis to track health of the coastal systems – 2 GPS, annual subscription for ArcView software, aerial survey data, computers/laptops.
The CZMAI Data Centre applied four steps in developing the spatial baseline: (1) aerial imagery/survey to establish a spatial & temporal baseline for human use of the coastal and marine resources, (2) digitization, (3) ground truth to validate the development sites captured with the aerial survey, and (4) data processing.
Ground truthing for Caye Caulker planning region was carried out from June 27th – July 1st, 2016. Ground truthing for Ambergris Caye was carried out from July 25th – July 29th, 2016. Data processing and final maps were completed for 35% of Caye Caulker and San Pedro.
To complete mapping of Belize's coastal areas, the Coastal Zone Management Authority and Institute is collaborating with the Land Information Centre (to complete Caye Caulker), Belize Association of Planners (for the Central region and Turneffe), San Pedro Town Council (to complete Ambergris Caye), University of Central Florida (for the Central Region), and Physical Planning.
| 2.1 Communtiy needs assessment workshops |  | Needs assessment workshops/meeting |  | Meetings were held on December 6-9, 2016 with 23 community leaders in the southern communities (Dangriga, Hopkins, Sittee River, Riversdale, Seine Bight and Placencia to further discuss the MCCAP project in relation to alternative livelihoods funding opportunities and conduct community needs assessment for skills training through fishers community leaders. | S
| 2.2 Participatory sub-project planning workshops |  | Community mobilization for the development of alternative livelihoods |  | An initial meeting was held with the Department of Rural Development on October 26, 2016. The aim of the meeting was to create synergy with MCCAP and the Department of Rural Development as it relates to component 2. We were informed that the Department of Rural Development can facilitate through their Ministry the drilling of wells for component 2, if MCCAP so desired. The group discussed one concept note submitted by the Belize Red Cross and Consejo Village regarding a new water system for the village. A stakeholder donor agency meeting with MCCAP, Red Cross, Rural Development and Petro Caribe Funds was held on November 30, 2016 to identify funds to assist the Consejo Water Project. | S
|  |  | Dialogue and networking |  | MCCAP continues to network and collaborate with a number of organizations to holistically tackle the issue of alternative livelihoods, while reducing duplication of activities amongst agencies: | S
Consejo water project - Meeting with the Department of Rural Development, 26 October 2016, with MCCAP, Rural Development and the Belize Red Cross to discuss synergies, particularly the water issue in Consejo Village. A follow-up meeting was held 30 November, 2016 with technicians and donors to review the Potable Water Supply Study for Consejo Village prepared by Tunich-Nah Consultants and Engineering (2016) and discuss a plan of action on the way forward with providing potable water to Consejo Village. Attendance at the meeting included the Belize Red Cross, Rural Development, Consejo Village Councillor and ALBA Petro Caribe, Belize Energy.
MCCAP, Belize Audubon Society and Sarteneja Alliance for Conservation and Development met on November 11, 2016 to discuss the outcome of the socio-economic needs assessment for northern communities – Copper Bank, Chunox, and Sarteneja. This document provides valuable information that compliments the MCCAP Knowledge, Attitude and Practice Survey 2016. This document provides guidance on types of alternative activities that should be considered in these northern communities.
MCCAP is a member of the National Fisheries Livelihood Steering Committee. This committee has overall responsibility for the coordination and guidance of ongoing and proposed fisher alternative livelihoods and livelihood diversification projects in Belize to ensure improved streamlining and efficiency of resources. Members of the committee includes The Nature Conservancy, Belize Federation of Fishers, BELTRAIDE, Sustainable Tourism Program II, National Fishermen Cooperative, Northern Fishermen Cooperative, UNDP-GEF Small Grants Programme, Belize Enterprise for Sustainable Technology, and the Fisheries Department. The first meeting was held on the October 21, 2016 and the second on November 25, 2016.
The first meeting of the Seaweed partners was held on December 13, 2016 to discuss and share work done on criteria and standards to sustainably culture and harvest seaweed in Belize and to consider a certification programme for seaweed farms. Participants included the Belize Agriculture Health Authority, Belize Bureau of Standards, BELTRAIDE, Fisheries Department, Industry Consultant, Placencia Cooperative/Coral Cay, Southern Environmental Association, The Nature Conservancy, and Turneffe Seaweed Growers. MCCAP considers seaweed farming an alternative economic activity to fishing and welcomes the collaboration and exchange of technical information, which will be useful in assessing potential sub-projects.
MCCAP was invited to participate at a collaborative meeting with JICA to discuss their project formulation process on alternative fisheries livelihoods. Three potential projects were discussed. The meeting included the Belize Federation of Fishers, Wabafu Fishermen Association (Dangriga), and the Fisheries Department.
The Seaweed Growers Association submitted a sub-project concept note to MCCAP for funding. The fishers took the initiative to invite Turneffe Atoll Sustainability Association, the Fisheries Department, MCCAP and BELTRIDE to introduce agencies to the seaweed project and to identify how each partner organizations can collaborate with the Association.
| 2.3 Development of business plans |  | Business plans developed |  | None requested | N/A
| 2.4 Marketing support for business venture |  | Marketing support given |  | None requested | N/A
| 2.5 Training in business development |  | Support training for business skills |  | Thirty students at the Corozal Institute for Technical and Vocational Education campus will be trained in developing business plans to start their own business. | S
| 2.6 Training in marketable skills |  | Skills training to transition to alternative livelihoods |  | The Belize Institute for Technical and Vocational Education (ITVET) was approved for direct contracting to deliver technical and vocational training for community members. TORs Delivery of skills training at ITVET Orange walk and Corozal was approved by the TAC, PSC and World Bank. | S
Meetings were held with both ITVET Corozal and Orange Walk campuses to discuss guidelines and method of payment for the deliverables outlined in their contracts. Date for classes to begin was identified, as well as requirements from ITVET for all 4 courses that will be offered. ITVET submitted curriculums for Food Preparation, Cosmetology, Electrical Installation, and Computer Reapirs and Servicing and work plans to the PIAG.
Community consultation was conducted in each of the northern communities of Consejo, Sarteneja, Chunox and Copper Bank. The objective of the meeting was to inform the communities the results of the community needs assessment conducted in their villages through their various contact persons within their respective communities. The PIAG informed that there will be four courses from the needs assessment list that will be delivered through ITVET Corozal and ITVET Orange Walk starting on January 14th 2017. Attendees were invited to sign up for the course that they were interested to train through MCCAP project. The PIAG also informed that they will return to the communities, December 1-3, 2016 to conduct interviews with the objective of recruiting the most suitable candidates for the courses being offered. Names of selected candidates was sent to both ITVETs to prepare for selected candidates. Spaces for trainees is 16 food preparation, 14 cosmetology, 15 electrical and 15 computer repairs (approximately 58% female trainees).
On January 14, 2017 sixty registered trainees started their six months training (Cosmetology and Food Preparation) and eight months training (Electrical installation and Computer repairs and service). At the end of the course trainees will sit the Belize National Vocational Qualifications Certification examination and the electrical trainees will sit the Wireman license exam. The Project hopes that by the end of the training, participants will transition to full employment in their respective field.
| 2.7 Sub-grants for initial capital investment to support the startup of business venture |  | Sub-project mechanism for community-based business ventures |  | MCCAP alternative livelihood approach was discussed and approved by the TAC and PSC. Livelihood activities will focus on three main sectors: tourism, agriculture, and fishing. | MS
An agreed Indefinite Delivery Contract (IDC) process was developed for the MCCAP project. TOR IDC for MCCAP sub-project development expert services and Technical Expert services were approved by the TAC, PSC, and World Bank. Both TORs have been advertised. The PIAG along with PACT and Economic Development reviewed 9 Expression of Interest under the IDC to develop concept notes and full proposals including business plans etc. 6 of the 9 Expression of Interest were shortlisted.
|  |  | Sub-project requests received |  | A number of community groups submitted concept note/project profiles for acceptance/rejection by the TAC and PSC. (1) Tourism sub-project profile; (2) Agriculture sub-project profile; (3) Agriculture and Natural Resources Institute school farm; (4) Chunox St. Viator Vocational High School farm; (5) Fishing sub-project profile; (6) BFF Fish Processing Plant; (7) TNC Seaweed farming; (8) Belize Central Fishermen Association deepslope fishing sub-project; (9) Water system for Consejo Village; (10) Stann Creek Fishermen Association traditional boat building project; (11) Seaweed production by the Sarteneja Fishermen Association and Turneff Seaweed Growers. Of the 11 concepts submitted only one was rejected and two needs further inputs. The TAC and PSC agreed that the quality of the sub-project request was unacceptable and agreed that the PIAG should hire a Consultant to assist communities. | MS
Special request for research and development was made by the Fisheries Department, titled Climate Change Adaptation in Southern Belize: Diversification to deep slope Fisheries. The request will be reviewed by the PIAG.
|  |  | Addressing gender and vulnerable groups |  | Ensuring there is equity in mobilizing communities for the development of alternative livelihoods, all affected users and vulnerable communities and groups (women, elderly, indigenous people, level of education and to some extent ethnicity) have been identified (MCCAP Knowledge, Attitude and Behavioural Practice survey 2016) and given an opportunity to participate. MCCAP is taking a multiple faceted/cross-component approach to ensure vulnerable groups/communities have the opportunity to become involved in and benefit from alternative livelihoods assistance being provided. Thus far we have been/will be able to provide the following: | S
· Skills training for women (58%), individuals with primary education levels (23%), and youths that recently completed secondary school (35%). For students in high school we hope to support two school farms that teaches alternative livelihoods in agriculture, livestock, and aquaculture, and encourages graduating students to develop small-businesses in the future.
· Mobilization of fishermen associations, MCCAP encourages wives and daughters of fishers to participate in meetings to assist fishermen to develop project requests.
· Diversifying household livelihood portfolio by maximizing income earning potential of adults in the household. Generally, the MCCAP project considers the fishing household (mother and/or father, children) as the unit to explore alternative livelihoods.
· Fishers near retirement are encouraged to consider alternative livelihood activities.
· Communities that are vulnerable (more that 25% of community fall below the established poverty threshold in Belize) such as Consejo, Copper Bank, Hopkins, and Chunox, are treated differently, as more people are encouraged to participate in alternative livelihood activities and incentives (e.g., waiver fees) given.
In Belize, traditionally women are not directly involved in fishing (<1%). They are mainly involved in fish processing at Processing Plants (e.g. Fishermen Cooperatives), cleaning lobster and conch. Many of our women are domestic workers and care-givers in the fishing households. Recently, there has been a rise in the number of women cleaning fish at the fish markets. MCCAP is guided by the flagship action under Critical Success Factor 1 of the Belize Growth and Sustainable Development Strategy 2016-2019 and the FAO small-scale fisheries guidelines on the issue of gender. The Project Coordinator is exploring gender equity and equality based on the outcome of a small survey (N=50) on gender equality in Caribbean fisheries to gather information that will provide baseline data on the situation of women in fisheries in Belize. In the mean-time MCCAP encourages the participation of women in all activities. Meeting sign-in sheets have changed to track the participation of women at all MCCAP events.
|  |  | Fund sub-projects |  | None approved by the PSC | N/A
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings |  | KAP survey |  | Completed | HS
| 3.2 Development of BCC strategy and action plan |  | Develop and implement communication plan |  | TOR consultancy to develop a communication, education and public awareness strategy and action plan approved by TAC, PSC and World Bank. Received six Expression of Interests of which four firms were asked to submit technical and financial proposal by October 17. Only two firms submitted Technical and Financial proposals, of which WebZWin was selected. The firm should start working early January 2017. | S
|  |  | Climate Change training and awareness |  | First training session on “training of the trainers’ workshop on integrating climate change adaptation into planning processes with specific focus on the fisheries sector in Belize completed July 4-6, 2016. Twenty-six participants (35% females) included Fisheries Department, Forest Department, Department of the Environment, Coastal Zone Management Authority and Institute, Belize Red Cross, National Climate Change Office, Caribbean Community Climate Change Centre, Sarteneja Alliance for Conservation and Development, Turneffe Atoll Sustainability Association attended the training. The second training event is being organized. | S
| 3.3 Implementation of BCC strategy and action plan |  | No action required in year 2 |  |  | N/A
| 3.4 Updates of project activities (via quarterly electronic and print newsletters) |  | Reports completed in a timely fashion |  | Quarterly and yearly reports completed. To improve the image of the Project a branding exercise was undertaken and completed. | HS
| 3.5 Web-based platform |  | Development and maintenance of web-site |  | The Fisheries Department website is up and running, www.fisheries.gov.bz/. A menu bar for MCCAP has been added http://www.fisheries.gov.bz/mccap/. | S
| 3.6 Best practice forum |  | No action required in year 2 |  |  | N/A
| 3.7 Learning events, leadership development, training |  | Conduct Training events |  | Conducted training events for two schools adopted by MCCAP, namely Chunox St. Viator Vocational High School and Agriculture and Natural Resources Institute. | HS
Direct contracting for Ecology Project International Belize was approved by the World Bank. TOR Delivery of Training to Youths from the Marine Conservation and Climate Adaptation Project targeted communities by Ecology Project International was approved by the TAC, PSC and World Bank.
These schools will participate in the first training event on marine conservation and climate change for youths facilitated by Ecology Project International Belize, an organization that involves young people in hands-on science and conservation projects in Belize. They bridge cultural gaps, protect threatened species and habitat, and educate the next generation of conservation leaders, one student at a time. Training dates November 29 – December 3 (group 1) and December 3 – 7, 2016 (group 2). In total 33 students, 6 teachers, 2 parents participated in the training (39% female).
In order to ensure high quality delivery of the course, the preparation involved the following:
· A thorough review of EPI existing marine ecology curriculum to include climate change awareness and adaptation training activities;
· A thorough revision and update of EPI student journal to include climate change activities;
· Conduct an orientation visit to participating school by EPI, MCCAP, and PACT to discuss the training material with parents, students and teachers;
· Conduct a rigorous recruitment, including medical screening of students and chaperones from both ANRI and St. Viator High School to select the most suited participants for the training;
· Organize logistics and secure materials for the course;
· A follow up visits to schools by EPI Instructors to meet with recruited participants, chaperones, teachers and parents and for detailed discussions about the preparations, expectations and logistics of the course;
· Engage instructors and EPI staff in a thorough review and re-confirmation of risk management protocols.
· Students were trained in lion-fish data collection protocols, including focused survey, size estimation, behavior observation and dissection protocol. Students participated in beach cleanup, the activity sparked discussion on waste disposal, pollution and its impact on the ecosystem. They also explored the reef and mangrove ecosystems. They were able to relate all topics to climate change, showing their awareness of the threats it represents for communities like Dangriga and Chunox. Students also explored becoming climate change advocates in their schools and communities.
These schools will be supported to organize environmental/climate change club in school that will drive the climate change agenda in the schools. Participating organizations are MCCAP, Caribbean Community Climate Change Centre, Ecology Project International, Turneffe Atoll Sustainability Association, and PACT.
| 3.8 Strategic planning for the network |  | Develop strategic plan |  | The first strategy identified was a National Fisheries Policy, Strategy and Action Plan for Belize to support the Belize Fisheries Department. The first meeting with 13 senior managers of the Fisheries Department was held 6-7 October 2016. The aim was to conceptualize and apply an approach for the alignment of the proposed Fisheries Department Programmatic Work Plans with the strategic priorities of the Growth and Sustainable Development Strategy (GSDS), building on the prioritization framework defined in the GSDS, and with due consideration for the particularities of the Fisheries Departments legal mandate and operational circumstances. This was a first step in thinking about the national strategy and action plan. | S
The TOR for the consultancy to develop a national fisheries policy, strategy and action plan was recommended for approval by the TAC and PSC.
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sandra Grant
| Email: | pc.mccap@fisheries.gov.bz; linegrant@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Activities undertaken by MCCAP is satisfactory to date. The PIAG scored Component 1 as Satisfactory. To date all major activities have started and continues into the new year. The success of this component is revealed in 70% of funds committed (equipment, coral restoration, legislation, expansion of MPAs and replenishment zones). Most equipment were purchased, and in the coming years we expect to have databases of information which will be analyzed and used to inform fisheries management decision making. Hurricane Earl impacted enforcement activities; however, we are working on reorganizing and continuing enforcement efforts in the 3 MPAs. The PIAG scored Component 2 as Marginally Satisfactory. This has been a challenging component since the start of the Project. October 2016 we replaced the Senior Technical Officer and hope to focus our efforts on pushing component 2 forward in years 2-5. The Indefinite Delivery Contract, approved by the World Bank, will assist communities to develop sub-project proposals in a timely manner. We have a number of project requests that needs to be developed into full proposal. The PIAG hoped to start skills training after approved sub-projects; however, in the interest of time we had to fast-forward this activity. The PIAG scored Component 3 as Satisfactory. This component is moving forward with the selection of a firm to conduct the communication strategy and action plan. Once the message has been identified and the appropriate media, the PIAG will move forward to full implementation. The PIAG scored Component 4 as Satisfactory. Full staffing for the PIAG is in place and the office is fully equipped.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1 Spatially map and analyse target MPAs for realignment or expansion |  | Stakeholder consultations completed |  | A GIS expert was hired on May 30, 2016 to verify the GPS points of the expansion and replenishment ones. A second round of consultations included broader stakeholders including regulatory agencies, Co-managers, and NGOs on April 19, 2016. | S
| 1.2 Verify spatial mapping via ground-truthing |  | Ground-truthing completed |  | Following the approval of the Inception report by PIAG, TAC, and the PSC, groundtruthing was completed in South Water Caye Marine Reserve, Turneffe Atoll Marine Reserve and Corozal Bay Wildlife Sanctuary to aid in verification of the image data (maps and remote sensing data) to real features on the ground. The ground truthing team included the Fisheries Department, the consultant, Lands and Survey Department, and co-managers. | S
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback |  | Activity on-going |  | A Task force with a comprehensive group of stakeholders was formed to provide technical advice. The task force met on November 15, 2017. It is currently being reviewed by Co-managers' Board or Steeing Committee for further review and comments. | S
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning |  | No action required in year 2 |  | - | N/A
| 1.5 Consultation feedback and baseline data compiled and incorporated into zoning map |  | No action required in year 2 |  | - | N/A
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustment |  | No action required in year 2 |  | - | N/A
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries |  | No action required in year 2 |  | - | N/A
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones |  | Enforcement fleet improved, capacity building strenghened and enforcement equipment provided. |  | Enforcement and monitoring activities are progressing well with patrols in the three targeted MPAs. A first joint patrol meeting with Turneffe Atoll Sustainability Association, Fisheries Department, Coast Guard and MCCAP was held on June 28, 2016, which established the agencies roles and responsibilities. Capacity building was strengthened through enforcement trainings, and the development of a Comprehensive Enforcement Training Manual. Hurricane Earl impacted enforcement activities; however, the project is working on rebuilding and continuing the enforcement activities in the 3 MPAs. | S
| 1.9 Biological monitoring of strategic and control sites |  | Biological monitoring within Marine Reserves initiated |  | A comprehensive assessment of the Spiny Lobster and the conch population were undertaken. | S
| 1.10 Management effectiveness assessments using tracking tools |  | Initial activities started |  | World Bank gave its technical no objection to TOR Management effectiveness assessment for Turneffe Atoll Marine Reserve on January 30, 2017 and procurement process is on-going. | S
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up |  | Initial activities started |  | Contract with Fragments of Hope (FoH) has been progressing well. Several consultations have taken place, equipment for activity was purchased and a first training on coral replenishment conducted. Further consultations are being planned. | HS
| 1.12 Establishment of coral nurseries |  | At least 1 coral nursery established |  | Four table nurseries have been installed at South Water Caye Marine Reserve and Turneffe Atoll Marine Reserve. | HS
| 1.13 Out-planting in selected reefs |  | No action required in year 2 |  | - | N/A
| 1.14 Rolling out of the over-arching PA legislation |  | No action required in year 2 |  | - | N/A
| 1.15 Initial support to the PA administration structure |  | No action required in year 2 |  | - | N/A
| 1.16 Revision of mangrove regulations |  | Mangrove regulations drafted |  | Revision of the mangrove regulations - The objective of the Consultancy is to finalize the Draft Forests (Protection of Mangroves) Regulations 2014 (sic) to enable improved management of mangroves in an effort to ensure sustainable coastal development. This Consultancy is primarily a Legislative Drafting exercise. Contract signed; inception report approved by TAC, PSC, and WB. Initial consultation were conducted with key stakeholders, literature review completed, and task force formed to provide inputs to the revision of the Regulations. | S
| 1.17 Revision of the CZM Act |  | CZM Act drafted |  | Hiring to undertake this activity was completed, and a first meeting was held on November 1, 2016. An inception report was delivered. | S
| 1.18 Implementation of an Integrated Coastal Zone Management Plan |  | Water Quality personnel and lab equipment in place |  | Water quality personnel and lab equipment in place. The Sondes were deployed and installed in October, 2016; and in November, 2016 the first servicing was conducted. WQM Unit began mock testing in December. All the necessary equipment was received for lab analysis of water samples. | S
|  |  | Inventory of development sites for Ambergris Caye, Central and Caye Caulker |  | Ground truthing for Caye Caulker planning region was carried out from June 27th – July 1st, 2016. Ground truthing for Ambergris Caye was carried out from July 25th – July 29th, 2016. Data processing and final maps were completed for 35% of Caye Caulker and San Pedro. The purpose of the inventory is to establish a spatial and temporal baseline for human use of coastal and marine resources in tandem with the implementation of the Belize Integrated Coastal Zone Management (ICZM) Plan. | S
| 2.1 Communtiy needs assessment workshops |  | Needs assessment workshops/meeting |  | In addtion to the series of community needs assessment workshops that took place with the 12 targeted communities, meetings with 23 community leaders (Dangriga, Hopkins, Sittee River, Riversdale, Seine Bight and Placencia) were held on December 6-9, to further discuss the MCCAP project and conduct community needs assessment sign-up sheet. | S
| 2.2 Participatory sub-project planning workshops |  | Community mobilization for the development of alternative livelihoods |  | MCCAP held discussions with the Department of Rural Development who has expressed interest in collaborating on the new water system for the Consejo village. A stakeholder meeting was held in November, 2016 to identify additional funds to assist the Consejo Water Project. | S
|  |  | Dialogue and networking |  | Several meeting were held with organizations to tackle the issue of alternative livelihoods, while reducing duplication of activities amongst agencies. More specifically, 1) ongoing discussion on the Consejo water project with Belize Red Cross, Rural Development, Consejo Village Councillor and ALBA Petro Caribe, and Belize Energy; 2) meeting with Belize Audubon Society and Sarteneja Alliance for Conservation and Development to discuss socio-economic needs assessment for northern communities; and 3) meeting with Seaweed partners to consider a certification programme for seaweed farms. There has also been collaboration with JICA to discuss their project formulation process on alternative fisheries livelihoods. | S
| 2.3 Development of business plans |  | Business plans developed |  | - | N/A
| 2.4 Marketing support for business venture |  | Marketing support given |  | - | N/A
| 2.5 Training in business development |  | Support training for business skills |  | The Corozal Institute for Technical and Vocational Education campus will train 30 students to develop business plans to start their own business. | S
| 2.6 Training in marketable skills |  | Skills training to transition to alternative livelihoods |  | On October 19, 2016, the Bank gave no objection to Belize Institute for Technical and Vocational Education (ITVET) contract to deliver skills training to transition to alternative livelihoods. Meetings were held to discuss specifics about the training and ITVET submitted curriculums for Food Preparation, Cosmetology, Electrical and Computer Servicing. On January 14, 2017 sixty registered trainees started their six months training (Cosmetology and Food Preparation) and eight months training (Electrical installation and Computer repairs and service). | S
| 2.7 Sub-grants for initial capital investment to support the startup of business venture |  | Sub-project mechanism for community-based business ventures |  | The Bank has assisted MCCAP to develop an Indefinite Delivery Contract (IDC) process. TOR IDC for MCCAP sub-project development expert services and Technical Expert services were approved by the TAC, PSC, and World Bank. Both TORs have been advertised. The PIAG along with PACT and Economic Development reviewed 9 Expression of Interest under the IDC to develop concept notes and full proposals including business plans etc. | MS
|  |  | Sub-project requests received |  | Eleven community groups submitted concept note/project profiles for acceptance/rejection by the TAC and PSC. Due to the low level of capacity to develop high quality proposals, it was decided to hire a consultant to support the communties in the proposal development. | MS
|  |  | Addressing the vulnerable groups |  | MCCAP has taken a multiple faceted/cross-component approach to ensure vulnerable groups/communities have the opportunity to become involved in and benefit from alternative livelihoods assistance being provided. These groups were identified as part of the MCCAP Knowledge, Attitude and Behavioural Practice survey 2016. | S
|  |  | Fund sub-projects |  | None approved by PSC | N/A
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings |  | KAP survey |  | completed | HS
| 3.2 Development of BCC strategy and action plan |  | Develop and implement communication plan |  | Consultancy to develop a communication, education and public awareness strategy and action plan was approved by TAC, PSC and World Bank, and received six Expression of Interests. The firm WebZWin was selected and will start the work in January, 2017. | S
|  |  | Climate Change training and awareness |  | MCCAP completed the first training on “training of the trainers’ workshop on integrating climate change adaptation into planning process. It was attended by 26 participants from several organizations. The second training is in the process of being organized. | S
| 3.3 Implementation of BCC strategy and action plan |  | No action required in year 2 |  | - | N/A
| 3.4 Updates of project activities (via quarterly electronic and print newsletters) |  | Reports completed in a timely fashion |  | The project has produced quarterly and the yearly report in a timely manner. To improve the image of the Project, a branding exercise has been completed. The new logo shows “the interconnectedness of the social and ecological systems and their ability to adapt and change”. | HS
| 3.5 Web-based platform |  | Development and maintenance of web-site |  | The Fisheries Department website with a menu bar for MCCAP http://www.fisheries.gov.bz/mccap/. | HS
| 3.6 Best practice forum |  | No action required in year 2 |  | - | N/A
| 3.7 Learning events, leadership development, training |  | Conduct Training events |  | Direct contracting for Ecology Project International Belize was approved by the World Bank. TOR Delivery of Training to Youths from the Marine Conservation and Climate Adaptation Project targeted communities by Ecology Project International was approved by the TAC, PSC and World Bank. Ecology Project International conducted training events for two schools adopted by MCCAP, namely Chunox St. Viator Vocational High School and Agriculture and Natural Resources Institute. | HS
| 3.8 Strategic planning for the network |  | Develop strategic plan |  | The first strategy identified was a National Fisheries Policy, Strategy and Action Plan for Belize to support the Belize Fisheries Department. And the first meeting with 13 senior managers of the Fisheries Department was held 6-7 October 2016. The Bank provide the technical no-objection to the TOR on February 7, 2017. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Enos Esikuri/Sylvia Michele Diez
| Email: | eesikuri@worldbank.org/sdiez@worldbank.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The Project Implementing Unit (PIU) continues to be proactive in the management and implementation of the Project. There is effective oversight in place for the project activities in particular with regard to the technical dimensions. For Component 1: All major activities have started, and continue to progress well. About 70% of funds are committed, and most equipment were purchased. For Component 2: This component presented some initial delays, but with the hiring of the Senior Technical Officer, activities are expected to advance. The Bank approved an Indefinite Delivery Contract which will assist communities to develop sub-project proposals in a timely manner. To advance the implementation of this component, the PIU started the skills trainings even before the approval of the subprojects. For Component 3: This component is moving forward with the selection of a firm to conduct the communication strategy and action plan. Trainings were delivered and the first strategic plan identified (National Fisheries Policy, Strategy and Action Plan for Belize). For Component 4: All the PIU staff are in place, now with the new hiring (October, 2016) of a Senior Technical Officer, joining the Project Coordinator and Administrative Officer. The Project Coordinator and Procurement Officer participated in the World Bank annual Caribbean Fiduciary and safeguard workshop in Santo Domingo, Dominican Republic, May 23-25, 2016, and the World Bank Procurement Workshop in Grenada, November 8-10, 2016, to review the new procurement framework for investment project financing. The fiduciary agency for the project, Protected Areas Conservation Trust (PACT), experienced difficulties submitting accurate and timely financial information on the project’s implementation progress. The Bank continues to provide support in order to improve PACT’s financial management capacity.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective Indicator | Marine Protected Areas (MPA) coverage increased to 20.2% and areas declared as marine Replenishment Zones (RZ) increased to at least 3.1% of the Belize's territorial sea as identified in the NPASP, by the third year of the project. (Component 1) | MPAs share 13% of marine ecosystem habitats as identified by NPASP | 21.74% | 20.2%
|  | Marine RZs share approximately 2% of marine ecosystem habitats as identified in the NPASP | 3.15% | 3%
| Coastal zone managed effectively through implementation of Coastal Zone Management Plan, measured by coastline under protection and no net loss of mangroves (Component 1) | ICZM Plan available for implementation in Dec 2012 allowing for the 386 km of Belize’s coastline under better management. | 386 km | 386 km
|  | National mangrove status in 2012 is 74,480 hectares | 74,480 hectares | 74,480 hectares
| Project beneficiaries who have adopted alternative livelihoods and reduced dependency on traditional fishing for household income (at least 2,500 people), of which 30% are women (Component 2) | 0% fishers | 0% fishers | 45% fishers
|  | 0% women | 0% women | 30% women
| Awareness raising campaigns and dissemination of project information and project supported investments reach 100% and change attitude of 75% of intended beneficiaries (Component 3) | The value of marine conservation and impacts of climate change are not understood well among local people | 0% people with enhanced understanding; | 100% people with enhanced understanding;
|  |  | 0% people with changed attitude | 75% people with changed attitude
Project Outcome Indicators | The target MPAs are effectively managed as recorded by the Management Effectiveness Tracking Tool; | Management effectiveness score as recorded by Management Effectiveness Tracking Tool (Note: 1 to 4 – lowest to highest score)
|  | SWCMR - 2009 score of 2.65 of 4; | SWCMR - 2.65 of 4; | SWCMR – score of 3.5 of 4;
|  | CBWS - 2009 score 2.16 of 4; | CBWS - 2.17 of 4; | CBWS - score of 3.5 of 4;
|  | TAMR - nil | TAMR - nil | TAMR - score of 3.5 of 4
| Infractions of rules and regulations in the target MPAs and RZs reduced by 75% | % reduction in infractions of MPA/RZ rules and regulations based on arrests made at the MPAs in 2011-2012 |  | 75%
|  | Turneffe Atoll SPAG MRs - 13 arrest (2011) | Turneffe Atoll - 39 arrests (2014)
|  | SWCMR: 26 arrests (2011) | SWCMR - 17 arrests (2014)
|  | Turneffe Atoll SPAG MRs - 2 arrest (2012) | CBWS - 0 arrests (2014)
SWCMR - 23 arrests (up to September 2012)
| At least 3 restored coral sites, with resilient varieties grown in coral nurseries, within TAMR and SWCMR by the end of the project (with each site measuring 300 m2) | 0 coral sites restored | 0 | 6
| 75% of coastal developments adhering to the development guidelines set by the ICZM Plan | Baseline data being collected from the coastal mapping inventory | 0% | 75%
| Mangrove clearance infractions reduced by 100% (that is, infractions of the revised mangrove regulations) | TBD | 0% | 100%
| Alternative livelihoods subprojects elaborated and financed with 30% of beneficiaries being women | 0 business plans financed; | 0 business plans financed | 20 business plans financed;
|  | 0% of female beneficiaries | 0% of female beneficiaries | 30% of female beneficiaries
| Persons participating in training based on training needs assessment (at least 30% of trainees are women) | 0 number of persons; | 82 persons | 2000 persons;
|  | 0% of female trainees | 58% of female trainees | 30% of females trainees
| Behavioural change communication (BCC) campaigns conducted at all the target fishing communities (Chunox, Copper Bank, Sarteneja, Corozal Town, Belize City, Dangriga, Hopkins, Placencia, Sittee River, Riversdale, Placencia and Seine Bight) and reach 100% of fishers | 0 targetted community | 2 targetted community | 12 targetted communities
|  | 0 fishers | 0 fishers | TBD
| Strategic planning workshops with fishers association and three fisher cooperatives | 4 Fishermen Organizations have strategic plans | 3 planning workshops | 24 planning workshops
|  |  | 0 strategic plans | 8 strategic plans

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Collaboration/consultation requires significant time and investment with key partners (government agencies, NGOs, donor organizations, and community members). The first six months of Project implementation, the PIAG spent considerable time and effort to meet with relevant stakeholders to discuss synergies and reduce duplication of activities.
Balancing Project requirements/expectations with local realities. Community wants assistance on their terms, the project had to spend a lot of time explaining the process and activities to be funded as set out in the Project documents.
Staff of line Ministries directly involved in MCCAP activities are actively involved in implementation. Project activities increase time and counterpart funding which some Departments do not have. Hence, some expectations from the Project had to be reduced, while not affecting quality outcomes or the objectives.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | No. The implementation of activities started even before effectiveness utilizing retroactive financing, and it is progressing well. To expedite some of the processes, such as the identification of Firms/Individual Consultants, the PIAG established a Consultant database and asked firms/individual to register. Once an Advert/TOR is published the same information is emailed directly to firms/individuals. This has significantly improved the selection process.
Contract requiring review/comments/approval from TAC and PSC before payment needs to be properly managed in terms of time allocation for the review/comments/approval. Delays in reviews/comments/approval will delay the execution process. The PIAG established a 5 working days time period for comments/no-objection.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The capacity to manage sub-project activities at the community level is limited, and will impact the success of sub-projects. Results from other alternative livelihood projects have not been sustainable. The PIAG reviewed the lessons learnt and successes of other projects, then convened a sustainable livelihoods forum to discuss some of the challenges. The PIAG hopes to use the outcome to make changes to project outputs/project design as required.
Sub-project implementation has been a challenge. To deal with limited capacity at the community level it was decided to contract two firm to provide sub-project proposal development and address all environmental and climate change issues that will be incorporated in the proposals before presentation to the PSC for approval. This will expedite proposal development and approval; hence, faster project implementation.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The Project Coordinator recently completed a survey on women (as Policy Actors, community members in northern MCCAP targeted areas, processors in fish plants) perspectives on gender equality in the fisheries sector in Belize. The three groups felt that gender issues are integrated in Belize legislations and policies. In regards to gender in fisheries, respondents agreed that there is equal acces to technical services, participation in fisherfolk organizations and decision-making, and formal access to credit. While the survey results showd that there is, to some extent, gender equality; in practice more needs to be done on how women are treated and the opportunities available to them. Hence, MCCAP continues to encourage and/or target the participation of women in all activities and recognize their contribution to the fisheries sector.
MCCAP is taking a multi-faceted/cross-component approach to ensure vulnerable groups have the opportunity to become involved in and benefit from alternative livelihoods assistance being provided. Thus far, the project has been able to provide the following: • Of all the participants that received skills training, 58% are women , 23% are individuals with primary education levels, and 35% are youths that recently completed secondary school. For students in high school, the project will support two school farms that teaches alternative livelihoods in agriculture, livestock, and aquaculture, and encourages graduating students to develop their small-businesses in the future. • Diversifying household livelihood portfolio by maximizing income earning potential of adults in the household. Generally, the MCCAP project considers the fishing household (mother and/or father, children) as the unit to explore alternative livelihoods. • The project encourages wives and daughters of fishers to participate in meetings to assist fishermen to develop project requests. The project encourages the participation of women in all activities, which is captured in sign-in sheets which track the participation of women in all MCCAP activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker (2)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | BLZ/MIE/Coastal/2011/1
Implementing Entity | PACT and the World Bank
Type of implementing entity | NIE
Country | Belize
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 66792 | 2500 | 8825 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 48% | 30% | 30% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Coastal management |  | 50% |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 2500 | 30% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Coastal management | water areas | 4: Effective |  | Coastal management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 74480 | ha protected | 2: Partially effective | Mangroves | 74480 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 248810 | ha protected | 3: Moderately effective | Protected areas/National parks | 386612 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 386 | km protected | 2: Partially effective | Coasts | 386 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 2500 | 26% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Agricultural-related | 600 | 5% | From 1% to 5% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Tourism-related | 500 | 5% | From 1% to 5% | Tourism-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Fishing | 500 | 10% | From 1% to 5% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Livestock production | 400 | 5% | From 1% to 5% | Livestock production
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Financial capital | Coastal management | Supporting livelihoods | 6 | Financial capital | Coastal management | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related |  | 0 | 66792 | Agricultural-related |  | 4176.74
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Tourism-related |  | 0 | 66792 | Tourism-related |  | 6873.27
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Fishing |  | 0 | 66792 | Fishing |  | 8000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Livestock production |  | 0 | 66792 | Livestock production |  | 4176.74
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Coastal management | National | Public policy | 5 | Coastal management | National | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 2: Partially not enforced (Most elements not implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.