## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | August 18, 2019 to August 18, 2020
| Project Title: | Enhancing resilience to climate change of the small-scale agriculture in the O'Higgins Region of Chile
| Project Summary: | Increase the resilience capacity of rural agricultural communities in the coastal and inland secano of the O'Higgins Region with respect to current climate variability and future climate changes. The project lasts four years and the amount allocated is USD 9,960,000. We will work with a number close to 2,000 small farmers and their families, to create resilience capacities in these communities vulnerable to climate variation, with respect to livestock, cultivation, water and soil management, for this we will have machinery and implements that will be available to farmers for the improvement of agricultural practices. In addition, a number greater than 500 farmers will be subsidized with the implementation of rainwater harvesters, storage tanks and a small greenhouse for vegetables, which will allow them to have better water supply and have additional income. The project in turn will improve the agroclimatic information of the sector which will be available to small farmers, which will improve their agricultural management in the face of climate variations. A component of training focused on professionals from the sector, the Ministry of Agriculture and rural communities is also considered.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | CHL/NIE/Agri/2013/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Agencia de Cooperación Internacional para el Desarrollo (AGCID) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity (Government Cooperation Agency) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Chile | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Chile is a tri-continental country, with a territory that extends along the southwestern part of South America and includes Easter Island, in Oceania, as well as part of Antarctica to the south. Continental Chile, is located between 17 ° 30 'and 56 ° 30' Latitude South, while the Chilean Antarctic Territory covers the area between 53 ° and 90 ° west longitude and the South Pole. It is bordered by the Pacific Ocean along 8,000 kilometers of coastline. Its administrative capital is Santiago and the country is subdivided into 16 administrative regions. The total registered population is around 17.5 million people. Due to its geographical condition and variability of climatic regions, Chile is considered a country vulnerable to climate change: low-altitude coastal zones, arid and semi-arid zones, forested areas and areas exposed to deforestation and fragile ecosystems in coastal and Andean regions. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | November 13, 2015
IE-AFB Agreement Signature Date: |  | November 13, 2015 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | August 18, 2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | August 18, 2019
| Original Completion Date: | August 18, 2021
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | First year report prepared by the Project Management Unit (UGP) Mid-term Evaluation Report. (sent to the AF on March 16, 2020) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.cambioclimatico-ohiggins.cl | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Joaquin Arriagada Mujica (Director del Proyecto) | Dominican Republic
| Email: | joaquin.arriagada@minagri.gob.cl | Ecuador
| Date: | March 10th 2018 | Egypt
| Name: | Jorge Carrasco Jimenez (Coordinador Técnico INIA) | Dominican Republic
| Email: | jcarrasc@inia.cl | Ecuador
| Date: | February 6th 2018 | Egypt
| Name: | Miguel Letelier (Coordinador General INIA) | Dominican Republic
| Email: | miguel.letelier@inia.cl | Ecuador
| Date: | June 24th 2019 | Egypt
| Name: | Guido Carreño Reyes (Coordinador entidad Implementadora - AGCID) | Dominican Republic
| Email: | guido.carreno@minagri.gob.cl | Ecuador
| Date: | june 22th 2020 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Carolina Urmeneta (Designated Authority) | Equatoral Guinea
| Email: | curmeneta@mma.gob.cl | Eritrea
| Date: | January 1st 2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Maria Soledad Lucero Directora (S) - AGCID | Fiji
| Email: | mlucero@agci.gob.cl | Finland
| Date: | July 20th 2020 | France
| Name: | Iván Mertens Galle (Coordinador Sectorial - AGCID) | Fiji
| Email: | imertens@agci.gob.cl | Finland
| Date: | September 25th 2013 | France
| Name: | Marco Ibarra Orellana (Adaptation Fund Liaison - AGCID) | Fiji
| Email: | mibarra@agci.gob.cl | Finland
| Date: | September 23th 2020 | France
| Executing Agency |  | Gambia
| Name: | José Ignacio Pinochet (Subsecretario de Agricultura) | Georgia
| Email: | contacto@minagri.gob.cl | Germany
| Date: | November 27th 2019 | Ghana
| Executing Agency |  | Greece
| Name: | Javier Naranjo Solano (Subsecretario de Medio Ambiente) | Grenada
| Email: |  | Guatemala
| Date: | February 10th 2020 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [18/08/2019] |  |  |  | Financial information PPR 2: cumulative from project start to [18/08/2019] |  |  |  |  | Financial information PPR 3: cumulative from project start to [18/08/2020] |  |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] | 1809899 |  |  | Estimated cumulative total disbursement as of [enter Date] | 5643209 |  |  |  | Estimated cumulative total disbursement as of [enter Date] | 5643209 |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The start of the project had the difficulties of administrative processes and consolidation of professional teams. However, these drawbacks have already been overcome and the project is currently in full execution. Below we will comment on the main situations presented to date: In the summer of 2017 the country suffered one of the largest fires in its history and burned to the order of 600,000 hectares, many of which were located in the geographical area of ​​the project . This meant that the government and its institutions focused on the emergency and on the subsequent assistance processes for the victims, leaving pending in this case the start-up of the project. There were delays in the administrative processes, specifically in the agreement between the Ministry of Agriculture and the Institute of Agricultural Research (INIA), because in Chile the system of control of all documentation and agreements that involve financing is very strict. Lastly, in Chile there was a change of government in March 2018, which meant several months of inaction, while the new authorities and particularly in our case, the Project Director was internalized of the details. |  |  | Add any comments on AF Grant Funds. (word limit=200) | During the second year of project execution, we can comment that the program for delivering rainwater harvesters, water accumulation tanks, greenhouses and technified irrigation has worked well. There is an important level of satisfaction on the part of the beneficiaries. Another aspect that has been important and is up to date, is the corresponding to the training program. It has been met smoothly and the level of attendance has been important. An important aspect to highlight corresponds to the formation of a "Participatory Agroclimatic Table", which was not in the original design of the project and was implemented based on an experience of Honduras, presented at a seminar conducted by component 2 of the project . In this table farmers participate together with the technicians and together analyze the weather conditions and aspects related to the drought, to plan their agricultural season. Due to the success achieved in the Marchigue commune, other municipalities have requested the creation of new agroclimatic tables for their farmers, a situation that was included in the Annual Operational Program (POA 2019-2020). In terms of supporting farmers in soil work with machinery and equipment acquired by the project, due to acquisition difficulties (delays in the purchase processes), this program began starting from year 3, which means a delay One year from planned. Finally, a visit from the FACC with 14 representatives of countries that are implementing projects, together with the secretary of the Fund Mr Mikko Ollikainen, who in May were internalized the Chilean project, with field visits, dialogues with beneficiary farmers and meetings techniques with the project team. The experience was valued by the representatives of the countries, of which some have requested additional information to implement similar cases in their regions. |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | Due to unpredicted events, the third year of the Project encountered some delays and postponement of activities. In October 2019 there was a social outbreak in Chile, causing inconvenients to follow regular coexistance patterns as we do on a daily baisis. In addition, the Corona Virus pandemic spread massively in Chile since March 15, 2020, also brought some delays and postponements regarding some face-to-face activities such as agro-climatic tables or trainings. The expenses incurred by the project as of the date of this report are USD 5,008,000 As of 08/18/2020, the disbursement made to the executing entity is USD 5,643,209. Disbursement 3, corresponding to USD 2,464,643, was transferred to the executing agency on November 18 (the delay in the transfer is due to the fact that MINAGRI had to send a report requested in the agreement signed between both institutions) The amount not executed as of 08/18/2020 is USD 3,332,700 and is made up of the balance of disbursement 2 plus the amount of disbursement 3. According to the financial projection prepared by the executing agency, it is expected to disburse the total amount of the project, for this the Ministry of Agriculture will request a 6-month extension of the project, that is, the closure of the project is planned for February 2022. |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | N/A |  |  | INVESTMENT INCOME | N/A |  |  |  | INVESTMENT INCOME | N/A |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | AMOUNT APPROVED** | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | AMOUNT APPROVED** | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 89044.19 |  |  | 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 411494 |  | 260928 |  | 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 572779.4 |  | 416415.52
| 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 29149.14 |  |  | 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 168008 |  | 96871 |  | 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 260107.14 |  | 176723.85
| 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 57782.98 |  |  | 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 1087580 |  | 978426 |  | 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 1358677.49 |  | 1107521.14
| 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 30924.91 |  |  | 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 213455 |  | 119185 |  | 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 323936.12 |  | 223625.65
| 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 29404.45 |  |  | 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 204107 |  | 112727 |  | 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 321585.4 |  | 223559.3
| 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 29361.95 |  |  | 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 201051 |  | 111491 |  | 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 306943.08 |  | 210870.38
| 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 117269.01 |  |  | 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 535704 |  | 346567 |  | 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 966470.7 |  | 540968.51
| 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 8.79 |  |  | 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 34364 |  | 23590 |  | 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 35431.58 |  | 35431.58
| 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 9811.98 |  |  | 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 57234 |  | 27188 |  | 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 56917.43 |  | 56917.43
| 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 26123.35 |  |  | 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 36141 |  | 35403 |  | 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 44098.91 |  | 44098.91
| Execution costs (EC) | 131726.81 |  |  | Execution costs (EC) | 438348 |  | 302706 |  | Execution costs (EC) | 502916.71 |  | 493409.76
| Implementing entity cost (AGCID) | 85031.22 |  |  | Implementing entity cost (AGCID) | 207673.48 |  | 207673.48 |  | Implementing entity cost (AGCID) | 258135.94 |  | 258135.94
| TOTAL | 635638.78 |  |  | TOTAL | 3595159.48 |  | 2622755.48 |  | TOTAL | 5007999.9 |  | 3787677.97 |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 176555 | 2019-08-18 |  | 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 152299.9111 | 2020-08-18 |  |  | 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 130592.4 | 2021-08-18
| 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 131895 | 2019-08-18 |  | 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 40834.6065 | 2020-08-18 |  |  | 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 73014.65 | 2021-08-18
| 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 1619723 | 2019-08-18 |  | 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 884068.4145 | 2020-08-18 |  |  | 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 554451.35 | 2021-08-18
| 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 162467 | 2019-08-18 |  | 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 53280.3602 | 2020-08-18 |  |  | 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 115344.25 | 2021-08-18
| 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 183241 | 2019-08-18 |  | 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 82949.4894 | 2020-08-18 |  |  | 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 135674.24 | 2021-08-18
| 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 157627 | 2019-08-18 |  | 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 55705.619 | 2020-08-18 |  |  | 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 114769.28 | 2021-08-18
| 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 946081 | 2019-08-18 |  | 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 519752.665 | 2020-08-18 |  |  | 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 1743927.9 | 2021-08-18
| 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 59319 | 2019-08-18 |  | 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 31353.249 | 2020-08-18 |  |  | 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 5631.1 | 2021-08-18
| 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 53681 | 2019-08-18 |  | 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 37822.9853 | 2020-08-18 |  |  | 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 13979.51 | 2021-08-18
| 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 76637 | 2019-08-18 |  | 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 71431.4616 | 2020-08-18 |  |  | 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 167172.72 | 2021-08-18
| Execution costs (EC) | 127400 | 2019-08-18 |  | Execution costs (EC) | 136542.0243 | 2020-08-18 |  |  | Execution costs (EC) | 160001.54 | 2021-08-18
| Implementing entity cost (AGCID) | 135601 | 2019-08-18 |  | Implementing entity cost (AGCID) | 8810.04 | 2020-08-18 |  |  | Implementing entity cost (AGCID) | 118141 | 2021-08-18
| TOTAL | 3830227 |  |  | Total unspent to date | 2074850.8259 |  |  |  | Total unspent to date | 3332699.94
[5 empty] | 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 207296 | 2020-08-18 |  |  | 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 129159.3 | 2021-08-18
[5 empty] | 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 442733 | 2020-08-18 |  |  | 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 131771.13 | 2021-08-18
[5 empty] | 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 135024 | 2020-08-18 |  |  | 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 108677.68 | 2021-08-18
[5 empty] | 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 30110 | 2020-08-18 |  |  | 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 117382.96 | 2021-08-18
[5 empty] | 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 30110 | 2020-08-18 |  |  | 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 108913.96 | 2021-08-18
[5 empty] | 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 30110 | 2020-08-18 |  |  | 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 47110.54 | 2021-08-18
[5 empty] | 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 1294548 | 2020-08-18 |  |  | 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 176861.51 | 2021-08-18
[5 empty] | 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 30110 | 2020-08-18 |  |  | 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 35431.58 | 2021-08-18
[5 empty] | 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 54804 | 2020-08-18 |  |  | 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 56917.43 | 2021-08-18
[5 empty] | 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 50964 | 2020-08-18 |  |  | 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 38498.05 | 2021-08-18
[5 empty] | Execution costs (EC) | 158798 | 2020-08-18 |  |  | Execution costs (EC) | 302072.08 | 2021-08-18
[5 empty] | Implementing entity cost (AGCID) | 140601 | 2020-08-18 |  |  | Implementing entity cost (AGCID) | 123723 | 2021-08-18
[5 empty] | TOTAL new spent | 2605208 |  |  |  | TOTAL new spent | 1376519.22
[5 empty] | TOTAL | 4680058.8259 |  |  |  | TOTAL | 4709219.16 |  |  |  | TOTAL | 0 |  |  | TOTAL | 0
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | There is no co-finance committed |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0 |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on Q16: Jessica Farias Ibarra: total At November 2019
Note on V16: Jessica Farias Ibarra: Jessica Farias Ibarra: Estimated cumulative total At ago/2020
Note on Y16: Jessica Farias Ibarra: total At 18/08/2020
Note on F45: Jessica Farias Ibarra: se esta solicitando este monto para el segundo año en relación al POA 2019

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Climate change manifests differently or with greater intensity than projected by the analyzes and studies | High: Chile has had a mega drought for the past 10 years, and during last winter season, the millimeters of a normal year were accumulated, but that has not managed to end the mega drought that dragged on for a decade. | Managements have been carried out in the soils of the benefited farmers, such as scarification, which allows a greater accumulation of water in the soil profile.
Beneficiaries resist changes in practices | Medium: Although progress has been made in educating farmers to make changes in agriculture practices, delays due to non-project factors maintain risk. | Some measures such as the use of the scarifying plow that allows the soil, accumulate more water, is a job that farmers are beginning to carry out and is showing that they achieve better yielding crops. In addition, the agroclimatic tables that could be carried out prior to the Pandemic, seek to deliver knowledge that allows farmers to make better decisions for their crops.
Government or institutions do not assign sufficient priority to the program | Very low: The National Government, through the Ministry of Agriculture and the Regional Government of O'Higgins, have presented high priority to support farmers who have suffered from a mega drought, allocating economic and human resources to achieve mitigation effects. | The communes of the project are in Agricultural Emergency due to the mega drought that affects them. This allows freeing up resources for small farmers to feed livestock or finance minor irrigation works.
Lack of incentives or economic capacity of the beneficiaries to invest in restoration or improvement can lead to inefficient results in land use and other expected results. | Medium: even though this year was a normal year in rainfall, the drag of almost a decade of drought, has diminished the economic capacity of small farmers as their yields have fallen. | The government has made economic contributions and food delivery so that small farmers continue to work their land and maintain their crops and animals.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change of Government and / or authorities: New authorities must assume the direction of a project that they do not know and that requires several months of learning for a normal and efficient management | Low: In March 2018, a new government was elected in the country and will remain unchanged for the remainder of the project. Except for specific situations of cabinet change that could affect the direction of the project. | No changes are projected in the near future
The CLP / US $ exchange rate falls below $ 550 | Low: The exchange rate has remained on average above $ 600 | AGCID has constantly informed the Advisory Committee about the exchange rate projections, with which the finance team projects the budgets for the remaining time, which is essential for the calculations and work to be carried out.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
AGCID has been permanently advising and instructing the technical team of the project, on situations that could complicate some project goals. This is done through the Advisory Committee and the General Coordinator during his fieldwork, that is developed every week. AGCID as the implementing Institution, warns and looks for solutions.
Note on C18: Jessica Farías Ibarra: Riesgo identificado
Note on D18: Jessica Farías Ibarra: Estado actual

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Currently all laws are being enforced. There has been no need to take additional actions | No actions taken | N/A | N/A | N/A | N/A | N/A
2 - Access and equity |  |  | Access assured to the most vulnerable | The project included a list with the names of the beneficiaries | There is an annual management report (AMR) and Annual Beneficiary Survey. | 0 survey / 0 AMR | 1 survey /1 AMR | Some changes were made in the lists of beneficiaries due to voluntary resignations of some farmers participating in the project. | N/A
3 – Marginalized and vulnerable Groups |  |  | Beneficiaries must represent the most vulnerable households on the region. | NIE Coordinator does a permanent monitoring of the beneficiaries | Annual Management Report, Annual Beneficiary Survey. | 0 survey / 0 AMR | 1 survey /1 AMR | During the third year, the vulnerable families of the sector that participate in the project, according to the annual survey and especially women, had improvements in their quality of life. | N/A
4 – Human rights |  |  | Chile is a democratic country, and there is no reason to fear of human rights violation | There is a national regulation on sexual harassment and abuse in the workplace. And a reglament about these topics on the Ministry of Agriculture. | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Favour women as beneficiaries | During year 3, 50% of the users surveyed were women. The percentage of participation in the activities was lower than in year 2, due to the situations that occurred in Chile in October 2019 (social outbreak) and the pandemic since March 2020. | there is an annual management report (AMR) and Annual Beneficiary Survey | 0 survey / 0 AMR | 1 survey /1 AMR | During the third year, the policy of keeping a greater number of female farmers over male farmes in the final list of beneficiaries was continued, reaching 57%. | N/A
6 – Core labour rights |  |  | No risks were identified | Chile has a Labour Code, which prootects all fundamental labor rights. | all people engaged by the project have a contract of employment that includes social and health security. | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | No risks were identified, because the intervened zone has no indigenous population. | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | N/A, there is no need to resettle population. | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | No risks were identified, because the project does not intervene natural habitats | N/A | N/A | N/A | N/A | N/A | N/A
10 – Conservation of biological diversity |  |  | No risks were identified | The practices carried out by farmers during year 3 are considered good agricultural practices and help reduce the risk of biological diversity. Free handling of agrochemicals is carried out. | Training of the agricultural technicians, and workshops with farmers. | 0 Technicians Trainning / 0 farmers workshop | Due to the pandemic, the programmed number of trainings could not be carried out, but knowledge was provided at each visit of the technician to the farmer. | N/A | N/A
11 – Climate change |  |  | Originally, a hazard had not been identified. But the considerable decrease in rainfall in the region puts the water supply for animals and even the human population at risk, damaging food production in the area. | For several years and continuously, the government has decreed an agricultural emergency zone, which allows the delivery of fodder for small farmers and the delivery of water in tanker trucks. | N/A | N/A | Intense work was carried out in year 3 with the improvement of soils and the work of scarification, so that the soils can retain more moisture in their profiles. | N/A | In year 4, greenhouse materials and efficient water use will be improved
12 – Pollution prevention and resource efficiency |  |  | No risks were identified, positive impacts | There are no negative impacts on this issue, since the project executes environmentally friendly techniques. | N/A | N/A | N/A | N/A | N/A
13 – Public health |  |  | No risks were identified, positive impact | A great positive impact has been generated on the beneficiary farmers, since they have their own garden with fresh vegetables and free of agrochemicals, which improves their diet. | Annual Beneficiary Survey | 0 survey | 1 encuesta | Positive | Organic production free of chemicals will be prioritized.
14 – Physical and cultural heritage |  |  | No risks were identified, positive impact | Positive impact, because by using greenhouses the project recovers abandoned practices such us vegetable production for self-consumption. | Annual Beneficiary Survey | 0 survey | 1 survey | Positive | In the annual survey, it is shown that in the families of the farmers, positive cultural changes have been generated.
15 – Lands and soil conservation |  |  | No risks were identified, positive impact | Positive impact thanks to the practices carried out with the project machinery such as zero tillage and guano application. | Reserach of field composition and soil fertility | 1 amr | 1 survey | Positive | The annual report 3 compiled the data of improvements of soils and hectares worked.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, through Agromet (Network of meteorological stations). This network continues to be reinforced, and 50 temperature and rainfall measurement points will be established.
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, climate change has generated a mega drought that has affected the region. While it is true that the normal one-year rainfall fell this year, the considerable decrease in rainfall over the last decade has generated a water crisis.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | It has been suggested to increase the number of beneficiaries through the work carried out by agricultural machinery, which has made it possible to support more small farmers. In addition, how to improve access to water resources has been evaluated, knowing its variation. This was detected during the mid-term evaluation.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | AGCID, as the implementing entity, has a permanent follow-up to the Ministry of Agriculture, which executes the project, and to the technical body INIA. AGCID, through the general coordinator of the project, reviews the quarterly and quarterly reports of the agencies, raising the observations and suggestions necessary for their correct implementation. Weekly field trips are made to the Demonstration Units and project beneficiaries, in order to supervise the activities that are reported. There is also an Advisory Committee made up of the Ministry of the Environment, Agriculture and AGCID on which the AOP project (Annual Operational Plan) is monitored. This means reviewing the schedule, budget execution, and ESP and gender safeguards.
Have the implementation arrangements been effective during the reporting period? |  | In general, there has been efficiency. The Midterm Proposal suggested that the National Director of the Project should not be a political position, but the figure of an Executive Director who is 100% dedicated to the project will be created.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Executing Entity has appointed a new general coordinator of the project, who lives in the region, which enables the corresponding alerts to be raised to carry out the improvements with more precision.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | AGCID and the project's MANAGEMENT UNIT have worked together to make the measures effective.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Originally, the main competencies were in the PROJECT MANAGEMENT UNIT, working as a team with the General Coordinator of the Project. But currently, the technical team that is in the field has joined the work, holding meetings once a week to improve decisions that will directly benefit the benefited farmers.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | The ESPM has been updated in order to take into account the main consequences of Climate Change
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Agroclimatic Tables. They are participatory groups of farmers and technicians, in which changing climatic conditions are evaluated to decide the type and time of sowing crops. In addition, pest control, organic farming techniques and other issues related to the availability of water resources are analyzed. | Yes | Access and equity / Marginalized and vulnerable groups / Gender equality and empowerment of women | As in the previous year, surveys were conducted to see the level of user satisfaction. | Yes | Yes, we have identified, among the participants, the number of women and most vulnerable people
USP 2: Farmers' WhatsApp groups: this in order to share experiences, climate data and technical advice. | Yes | Access and equity / Marginalized and vulnerable groups / Gender equality and empowerment of women | N/A | Yes | Yes, we have identified, among the participants, the number of women and most vulnerable people
USP 3: Training of young people regarding climate change, generating awareness in children and young people in the schools of the project area. | Yes | Access and equity / Marginalized and vulnerable groups | Due to the social outbreak and the pandemic, it has not been possible to assess | Due to the social outbreak and the pandemic, it has not been possible to assess | N/A
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal?
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)?
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In addition to hiring a Sociologist with knowledge on gender issues, AGCID approved to hire a professional for the implementation of the Gender Plan, approving the terms of reference during year 3. Unfortunately, with the arrival of the Pandemic in March, no He was able to specify the hiring of the professional to date, due to the fact that activities to prevent contagion were suspended, as were most of the activities carried out in the field. But it is reported that it is considered to resume this hiring during the first quarter of year 4.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, as a result of the hiring of the professional in year 2, improvements have been implemented in the activities of year 3 in relation to the gender policy.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | AGCID participated throughout the process of hiring the expert professional to implement the gender policy, in addition to working as a team
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes, the changes made by the AGCID were accepted and they were made according to the suggestions made by the professional
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The professionals in the field were not aware of gender issues, which was considerably improved with the hiring of the sociologist. Unfortunately, the Pandemic delayed the hiring of the gender expert, who would deepen the knowledge of the entire team to implement the gender policy.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
no complaints were received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Result 1.1.- Implementation of a capacity building and training systems to increment the resilience capacity of farm communities vulnerable to climate variation and climate change with respect to cattle, crop, water and soil management |  | Outcome 2 | At least 255 officials from 13 institutions (5 services of the Ministry of Agriculture and 8 municipalities) trained to minimize exposure to the risks of climate variability. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 5,343 (direct beneficiaries, at least 1,673 women) farmers trained. |  | 264 officials have been trained to date. 1203 trained farmers have been reported to date, which in the absence of the Pandemic, would have been a much higher number. Regarding the hectares, work has been reported for 2903 improved hectares, benefiting 485 users, of which 330 are men and 155 women; and reporting an increase of USD 265 in households. It should be considered that the value of the work of machinery is not incorporated, since it is in measurement. Out of the direct beneficiaries, 3304 have been trained to date. | S
| Result 1.2.- Improve the decision supporting agroclimatic information management for actual climate and future climate changes for local MINAGRI professionals and farmer communities |  | Outcome 2 | At least 5767 of the incumbents (100% of the agricultural population, the direct beneficiaries, at least 1562 vulnerable women) with a lower risk of extreme weather events (EWS 0-> 3). • 558 farmers (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per owner. Household income increased by at least USD 1,000 / year. • At least 255 officials from 13 institutions (5 services Ministry of Agriculture and 8 municipalities) trained to minimize exposure to the risks of climate variability. |  | Due to the scenario of the global Pandemic, there was less progress than expected in some points of this item, but support networks have been generated thanks to the work carried out in the agroclimatic tables. Regarding the 558 farmers, 323 are still pending in the installation of their storage tanks, due to the scenario described above, since as a preventive measure, activities on the ground have been suspended since March, and then gradually resume. An increase of USD 265 was demonstrated, but this figure was not less than indicated, since they could not be counted every month, in addition to not considering the profit from the machinery works. Regarding the training of officials, 175 attended this year, which added to the previous report, adds 264 officials trained. | MS
| Result 2.1.- Implementation of measures and technologies for increasing water resources availability for rural communities in the coastal and inner dry lands of the O´Higgins region |  | Outcome 3 | • At least 5767 beneficiaries (100% of the agricultural population, direct beneficiaries, at least 1562 vulnerable women) with a lower risk from extreme weather events (EWS 0-> 3). 13 institutions (5 services of the Ministry of Agriculture and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability. |  | Despite all the force majeure problems that have been generated, such as the social outbreak of October 2019 and the Corona Virus Pandemic, progress is being made on the right path. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Guido Carreño Reyes
| Email: | guido.carreno@minagri.gob.cl
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Year 3 was scheduled to be the year in which the project was consolidated, as well as in which various tools would be delivered to small farmers, which would allow them to be better trained to face climate change with better decisions, but two events that occurred In the country and in the world, the implementation of the project delayed: the social outbreak of October 2019 and the Corona Virus Pandemic in March 2020. Despite this, there were important achievements, such as the work with the machinery, which It came to solve serious problems that small farmers had of access to machinery to improve their soils, where in addition to the work done by the scarifying plow, it allowed a greater retention of water in the soil profile. In addition, the work carried out in the agroclimatic work tables prior to the Pandemic, allowed the creation of WhatsApp groups where farmers from the communes share their experiences in order to continue improving. On the other hand, they will be able to have data from stations close to their properties, in order to make better decisions based on them. AGCID, as an institution, has always been working towards the fulfillment of the different objectives, delivering work ideas to improve, and suggestions to those in charge of executing, so that the benefits of this important project reach small farmers in their fullness, and enable them to improve their resilience against climate change.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Result 1.1.- Implementation of a capacity building and training systems to increment the resilience capacity of farm communities vulnerable to climate variation and climate change with respect to cattle, crop, water and soil management |  | Outcome 2 | At least 255 officials from 13 institutions (5 services of the Ministry of Agriculture and 8 municipalities) trained to minimize exposure to the risks of climate variability. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. About 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 5,343 (direct beneficiaries, at least 1,673 women) farmers trained. |  | 264 officials have been trained to date. 1203 trained farmers have been reported to date, which in the absence of the Pandemic, would have been a much higher number. Regarding the hectares, work has been reported for 2903 improved hectares, benefiting 485 users, of which 330 are men and 155 women; and reporting an increase of USD 265 in households. It should be considered that the value of the work of machinery is not incorporated, since it is in measurement. Out of the direct beneficiaries, 3304 have been trained to date. | S
| Result 1.2.- Improve the decision supporting agroclimatic information management for actual climate and future climate changes for local MINAGRI professionals and farmer communities |  | Outcome 2 | At least 5767 of the incumbents (100% of the agricultural population, the direct beneficiaries, at least 1562 vulnerable women) with a lower risk of extreme weather events (EWS 0-> 3). • 558 farmers (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per owner. Household income increased by at least USD 1,000 / year. • At least 255 officials from 13 institutions (5 services of the Ministry of Agriculture and 8 municipalities) trained to minimize exposure to the risks of climate variability |  | Due to the world pandemic scenario, progress was made to a lesser degree than expected for some points of this item, but support networks have been generated thanks to the work carried out in the agroclimatic tables. Regarding the 558 farmers, 323 are still pending in the installation of their storage tanks, due to the scenario described above, since, by way of prevention, activities on the ground have been suspended since March, and then gradually resume. An increase of USD 265 was shown, but this figure does not count every month, in addition to not being considered the profit of the machinery works. Regarding the training of officials, 175 people were trained this year, which added to the previous report, adds 264 people trained. | MS
| Result 2.1.- Implementation of measures and technologies for increasing water resources availability for rural communities in the coastal and inner dry lands of the O´Higgins region |  | Outcome 3 | At least 5767 beneficiaries (100% of the agricultural population, direct beneficiaries, at least 1562 vulnerable women) with a lower risk of extreme weather events (EWS 0-> 3). 13 institutions (5 services of the Ministry of Agriculture and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability. |  | Despite the force majeure problems that have been generated (such as the social outbreak of October 2019 and the Corona Virus Pandemic), progress is being made on the right path. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joaquin Arriagada Mujica (Project Director)
| Email: | joaquin.arriagada@minagri.gob.cl
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
This has undoubtedly been a difficult year for the country and by the way for the project, the social outbreak of October 2019 and the pandemic have made it difficult for us to carry out on the ground, but despite the above we have made good progress in several important points such as the improvement of soils, we have also implemented a weather alert system that has worked very well, also the challenge of social distancing has forced us to be creative in the way of communicating between the team and also with the beneficiaries, on the other On the other hand, the mid-term evaluation has shown us a path of reforms in the organization that will allow us to better face the final part of the project, leaving us in good standing to comply with the environmental indicators and commitments. As a result of the aforementioned, compliance with what is proposed in the annual work plan has been low, which proposes us the challenge of accelerating the step in this fourth year to regularize the pending actions, on the other hand it will be essential to request the client a termination six months to comply with the indicators.The perspective that we have in the team towards the end of the project is very optimistic, we have managed to integrate in a very good way all the relevant actors of the ecosystem in which the project is developed and we have integrated great people and professionals to the team that will give us a better power to give a great closure to this project.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on H8: Jessica Farías Ibarra: • Por lo menos 5767 los titulares de (100% de la población agricultor, los beneficiarios directos, por lo menos 1562 mujeres vulnerables) con un menor riesgo ante fenómenos meteorológicos extremos (EWS 0-> 3). • 558 agricultores (beneficiarios directos, al menos 318 mujeres) con un menor riesgo de fenómenos meteorológicos extremos. 20.000 litros de agua por año disponibles por titular. Ingresos de los hogares aumentó en al menos USD 1.000 / año. • Al menos 255 funcionarios de 13 instituciones (5 servicios Ministerio de Agricultura y 8 municipios) capacitados para minimizar la exposición a los riesgos de la variabilidad climática.
Note on H24: Jessica Farías Ibarra: • Por lo menos 5767 los titulares de (100% de la población agricultor, los beneficiarios directos, por lo menos 1562 mujeres vulnerables) con un menor riesgo ante fenómenos meteorológicos extremos (EWS 0-> 3). • 558 agricultores (beneficiarios directos, al menos 318 mujeres) con un menor riesgo de fenómenos meteorológicos extremos. 20.000 litros de agua por año disponibles por titular. Ingresos de los hogares aumentó en al menos USD 1.000 / año. • Al menos 255 funcionarios de 13 instituciones (5 servicios Ministerio de Agricultura y 8 municipios) capacitados para minimizar la exposición a los riesgos de la variabilidad climática.
Note on H25: Jessica Farías Ibarra: La información adecuada se genera y se difunde a través de los medios adecuados. Junto con el entrenamiento, mejora la toma de decisiones. • Por lo menos 5767 beneficiarios (100% de la población agricultor, beneficiarios directos, al menos 1562 mujeres vulnerables) con un menor riesgo ante fenómenos meteorológicos extremos (EWS 0-> 3). 13 instituciones (5 Ministerio de Agricultura de servicios y 8 municipios) con mayor capacidad para minimizar la exposición a los riesgos de variabilidad climática. .

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Number and type of institutions with the best capacity to minimize exposure to the risks of climate variability. Number of people with lower risk of extreme weather events | Degradation of agricultural land and livestock, for improper practices. The younger generation migrates from family farms to cities in search of better economic and working conditions and better quality of life | It works in coordination with 13 institutions, 5 from the Ministry of Agriculture and the 8 Municipalities in the area: Navidad, Litueche, La Estrella, Marchigüe, Pichilemu, Paredones, Pumanque and Lolol. Everyone has participation in the different committees of the project, making decisions together. The Seremi of Agriculture is the one who leads in the region the work that is carried out through the National Directorate. In year 3, an agreement was signed with SERNAGEOMIN (National Geology and Mining Service), in order to complement the work carried out by the Agricultural Research Institute (INIA). Results: out of the 13 institutions, 175 officials have been trained in various topics related to the project, out of 266. Of the 558 direct beneficiaries of rainwater harvesters, there was no progress due to the reasons of force majeure stated above: Social Outbreak and Pandemic . Regarding direct training, 1203 out of 2208 beneficiaries were trained. Finally, improvements were reported in 2903 hectares, benefiting 485 farmers, of which 155 are women. | Land degradation is reduced through the application of soil conservation techniques and appropriate soil, water and plant cover management practices. • 13 institutions with greater capacity to minimize exposure to the risks of climate variability. • At least 255 officials from 13 institutions trained to minimize exposure to the risks of climate variability. • 558 owners (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per holder. Household income increased by at least USD 1,000 / year. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 4988 owners (100% of the farming population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • At least 5343 (direct beneficiaries, at least 1673 women) trained farmers.
Output 1 | 13 institutions (5 Ministry of Agriculture Services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability | Arable land in the O'Higgins region will be reduced by 44% and 68% respectively (scenario A2). The most vulnerable group of farmers (under 20 ha) includes 4988 farmers (1562 women) and their families | In the context of the project design, a reduction in arable area was considered due to decreased rainfall. During year 3, work was carried out with the machinery such as the use of the scarifier plow, which made it possible to improve the soils by breaking the compacted ground, and thus, achieve a better accumulation of water in the profile. The occupation of the Zero Tillage team also began to take place, which allows a decrease in soil erosion. In addition, tests and measurements were carried out regarding the development of new species for rainfed, in order to find species more resistant to drought. The Demonstration Units have adapted the aforementioned, so that farmers know the studies that are being carried out. Finally, different tasks have been carried out that have achieved an improvement in 2903 hectares of land at the closing date of year 3. | Greater capacities for soil management, livestock, water and crops. Community access to ground handling machines • 13 institutions (5 services Ministry of Agriculture and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability. • At least 255 officials from 13 institutions (5 Ministry of Agriculture services and 8 municipalities) trained to minimize exposure to the risks of climate variability. • 558 owners (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per holder. Household income increased by at least USD 1,000 / year. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 5343 (direct beneficiaries, at least 1673 women) trained farmers.
Result 1.1 | Number of officials trained to respond and mitigate impacts of climate events Staff capacity of selected institutions to respond and mitigate impacts of increased climate events | Low level of access to technical and financial assistance. Low level of connection with the agro-industrial value chain and low participation in organizations | The work in the Demonstration Units of the project that had a communal technician and a bi-communal agronomist, in addition to the advice of INIA on experts in: rainfed crops, irrigation and water management, sheep management and animal production, rainfed pastures, agricultural machinery, soils and soil science, have allowed this knowledge to be passed on to benefited farmers, either to those who currently own the greenhouses, and to whom machinery work has been carried out, all in order to reduce the effects of climate change. | • At least 255 officials from 13 institutions (5 Ministry of Agriculture services and 8 municipalities) trained to minimize exposure to the risks of climate variability. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 4988 holders of (100% of the farming population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • At least 5343 (direct beneficiaries, at least 1673 women) trained farmers.
Result 1.2 | Number of people affected by climate variability | Limited productive capacity Small farmers face water shortages from November to April. They receive water in cisterns of the municipalities, but in insufficient quantity for the maintenance of agricultural activity | Due to the Corona Virus pademic, the construction of the rainwater harvesters could not be increased, going to year 4, with 235 and 323 pending for year 4. Despite this, the work of year 3 showed an increase in income average of USD 265 dollars for greenhouse, however this amount is lower than expected since it was not possible to measure the whole year, missing the winter months as reported. In addition, the work done by the machinery should generate another additional income, which is in full measurement and would be reported in year 4, reaching the goal of generating an increase of $ 1,000. | • At least 4988 holders of (100% of the farming population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • 558 owners (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per holder. Household income increased by at least USD 1,000 / year. • At least 255 officials from 13 institutions (5 Ministry of Agriculture services and 8 municipalities) trained to minimize exposure to the risks of climate variability.
Output 2 | Percentage of population covered by adequate risk reduction systems | Small farmers lack agro-climatic information and capacities for agricultural decision-making in changing and extreme environments | The social outbreak in October and the Coronavirus Pandemic delayed the implementation of the agroclimatic observatory. In any case, progress was made in the purchase of the 50 thermometers and rain gauges, as well as in the list of the properties of the users where they will be installed, in order to have more precise data that allow better decisions on the part of farmers. In addition, weather alerts have been constantly broadcast alerting farmers to weather events. This information reaches the population of influence of the project, through the media and social networks, a population estimated at 50,000 people. Finally, the formation of agroclimatic tables in the 8 communes and the creation of communal WhatsApp groups have allowed experiences and knowledge to be shared among farmers. | The appropriate information that is disseminated through the appropriate means is generated. Together with training, it improves decision making. • At least 4988 farmers (100% of the farming population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • 13 institutions (5 Ministry of Agriculture services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability.
Result 2.1 | Percentage of population covered by adequate risk reduction systems | Small farmers lack agro-climatic information and capacities for agricultural decision-making in changing and extreme environments | The social outbreak in October and the Coronavirus Pandemic delayed the implementation of the agroclimatic observatory. In any case, progress was made in the purchase of the 50 thermometers and rain gauges, as well as in the list of the properties of the users where they will be installed, in order to have more precise data that allow better decisions on the part of farmers. In addition, weather alerts have been constantly broadcast alerting farmers to weather events. This information reaches the population of influence of the project, through the media and social networks, a population estimated at 50,000 people. Finally, the formation of agroclimatic tables in the 8 communes and the creation of communal WhatsApp groups have allowed experiences and knowledge to be shared among farmers. | The appropriate information that is disseminated through the appropriate means is generated. Together with training, it improves decision making. • At least 4988 farmers (100% of the farming population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • 13 institutions (5 Ministry of Agriculture services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | There is a strong commitment from the institutions that are part, and the knowledge acquired in the project will be incorporated for future initiatives in Chile regarding climate change. A negative aspect has been the unexpected, such as the Corona virus Pandemic, which is why several execution activities had to be postponed.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delays in implementation have been generated for reasons of force majeure: the first was the social outbreak that occurred in Chile in October 2019, and the second was the corona virus pandemic. This has generated delays in the execution of some initiatives, and in offering alternatives for year 4 such as trainings and online "fieldwork" to meet the indicators.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | As noted in the previous report, the conformation of the agroclimatic tables has generated a positive impact, since they allow the exchange of knowledge among farmers. In turn, the pandemic has led the project to adapt to online meetings.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Although some issues have been difficult to implement, as some farmers present challenges when communicating their needs, it is also added that their management of technology is below the level of a standard user. As the project progresses, a positive change has been generated on the subject supported by the field teams and the Ministry of Agriculture as a result of AGCID's suggestions.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | As part of gender considerations, the project has been generating, since 2019, selection criteria that prioritize the inclusion of women as direct beneficiaries of the rainwater collection and harvesting systems among other benefits, thus fulfilling its own purposes in this area and promoting gender balance in the group of male and female farmers that comprise it. Indeed, of the definitive list of 558 beneficiaries that was completed during this period, 58% correspond to women. Likewise, although in year 3 there were no installations of rainwater collection and harvesting systems, to date 121 women have one, which has allowed these beneficiary women to have permanent access to vegetables, mostly free of agrochemicals for self-consumption and in some cases, having vegetables for sale, being a contribution to their family economies. On the other hand, the participation of women in project activities such as training and technical home visits has continued to be encouraged, although these visits were affected in the last part of the year by the global pandemic. Additionally, thanks to the agreement signed with Fundación Prodemu, part of its beneficiary women have attended some of the training opportunities that the project has offered. This is extremely important since it has allowed the extension of knowledge through learning by observation and learning by doing, as well as the exchange of experiences among a greater number of female farmers. In turn, during this period a diagnosis on gender was completed, a fundamental document that had the purpose of contributing with information that would facilitate the construction of the Gender Action Plan for the last year of the project. This consisted, on the one hand, of a brief contextualization with statistics from official instruments at the regional level and, on the other, of the adaptation of the Harvard analytical framework, where from four categories (context, activity profile, access profile and control and influencing factors), data from the surveys for years 1 and 2 were presented, disaggregated by gender and information from some semi-structured interviews carried out with beneficiaries in 2019. The project has also been generating the corresponding modifications so that its own information gathering instruments are sensitive to gender issues, allowing the identification of gaps between men and women. Consequently, the surveys applied during the period included questions regarding roles, domestic and productive burdens, property and household decision making, among others. Although these antecedents provide relevant information and are necessary for decision-making, it is required for the current period to be complemented by the aforementioned Action Plan, which could not begin to be executed due to the country situation, but is already in progress. process. This must be linked with the execution of the project, addressing the current gender limitations and opportunities to maximize the benefits of the project, guaranteeing that women and men can have equal access to services, technologies and activities, among other emerging aspects that may appear. Some of the lessons learned are related to the prioritization of women as beneficiaries, since this has been an important element in reducing, in part, gender gaps and fostering greater autonomy through the generation of new income, savings, access to training, exchanges, knowledge and practices. An example of this is that the women who received greenhouses in years 1 and 2 had an average income of CLP $ 223,954 and a median income of CLP $ 167,000, income that although were lower compared to year 1, they still contribute an income economic -be it in savings or sale- that did not exist before. In addition to this, it has been confirmed that greenhouses are spaces essentially led by women, who dedicate an average of 10 hours of weekly work to it. In this sense, the leadership of the space is related to the type of productive activity and the provision for the preparation of food that is part of an entrenched gender role, but also because in many cases it constitutes a space of care and self-care that generates well-being personal, satisfaction and shared meanings. In this same aspect, the report on management and increase of income from the greenhouse concept revealed that the work carried out by the farmers in the greenhouses with the support of the project, has resulted in a process with great potentialities, opportunities and challenges in terms productive, environmental, social and economic, contributing, at least partially, to the SDG 2 regarding ending hunger, achieving food security and improving nutrition and promoting sustainable agriculture. For this reason, it is essential that the process carried out in the greenhouses continues to be strengthened as it is important at the level of the family productive unit, favoring the revitalization of small-scale rural territories, food sovereignty and security, well-being and collective satisfaction and individual and due to its great agroecological potential, weaving peasant knowledge and technical knowledge, which assist the path towards adaptation to climate change of these small and small farmers. Another of the lessons learned was the relevance of information gathering instruments that are gender sensitive, since in this way different areas of interest for the project are identified and monitored, which are reflected in the production of the gender statistics themselves. To summarize, as lessons learned we can identify that: 1. The installation of rainwater collection and harvesting systems for a greater number of farmers has led to the participation of more women in the management of greenhouses and has encouraged the learning of new practices and techniques that contribute to adaptation to change. climate through the formation of social capital, access to technologies and inputs, learning and the implementation of a synergy of knowledge, favoring the reduction of gender gaps regarding access to it, income generation, access to traceable food and in general, free of agrochemicals, the property infrastructure and the possibility of accessing the use of an extra source of water resource: rain. 2. During the lapse, women have reinforced practices that favor the environment, such as handling without agrochemicals. Indeed, 80.7% of the female population did not use this type of product on their properties. 3. It can be inferred that women have been more inclined to adopt the drip irrigation technology promoted by the project, where 89.9% of the female population stated that they had used this system. 4. 89.1% of the female population applied organic amendments in their greenhouses, as did 80.9% of the male population. Although this practice is not totally attributable to the project, since the use of organic amendments is long-standing, it is inferred that this has had an influence on its use through the reinforcement of training and technical advice, which is a positive fact since organic amendments have significant benefits when used correctly. 5. The information collected through the instruments reveals that the women beneficiaries are important agents of change and have certain fundamental characteristics so that the project can have greater results and impacts. As a fact they have a high associativity and 21.6% of them occupy managerial positions in social, territorial and / or functional organizations, almost 90% actively participate in training, they have generated more productions in greenhouses, they implement -in greater proportion that men - measures to face the effects of climate change, show greater awareness and concern regarding it, identifying themselves as responsible, making dependency visible and valuing the close relationship between human beings and nature. All these aspects make them key actors in the process of adaptation to climate change. 6. Regarding roles, there are significant gender gaps regarding the time spent on domestic work between men (1 hour per day on average) and women (6 hours per day on average), being one more expression of the gender division of work , which provides and naturalizes the roles and responsibilities around productive and reproductive work. This situation could constitute a barrier that limits the insertion in the labor market and the free time of some women, diminishing their personal and economic autonomy, for which the work, satisfaction and income produced by greenhouses are essential to contribute to somehow at this point. 7. Related to the above, it was found that 100% of the men declared that they made decisions related to the property, while 85.7% of the female population also indicated that they decided on it. In the case of women, this is a figure that increased by 9% compared to the previous year, so that more women indicated that they were involved in decisions in the field, which is perceived positively, since decisions related to productive work it is an area associated, mainly with men.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Among the lessons learned, it should be mentioned that farmers have a cultural factor, where they tend to work very individually, so this aspect should be considered in the future in new initiatives. In addition, it is important to note that the political factor must be considered, since this project had a change of government when its execution had already begun, so in new projects, it is suggested that the National Director is not a political position.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | High. There is a high potential in own food production with the accumulation of rainwater, which considerably improves access to organic vegetables. In addition, the works carried out on soils such as scarification, allow greater accumulation of water in the soil profile and with this, better resistance to the considerable decrease in rainfall.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | Some of the lessons learned are 1.- Financial support in project preparation is essential when dealing with such technical issues as Climate Change, due to the lack of specialists in the different countries. 2.- The support allows us to have experts with experience in the subject, who, in addition to their knowledge, provide practical experience from other successful projects, which reduces the risk factors for the project. 3.- It allows to have an "external" view capable of objectifying real problems, separating the urgent from the important, which sometimes confuses local experts because they are too close to the problem in question. 4.- A negative element is not having a "record" of certified and qualified consultants with successful experiences, to which users can go, without the need to venture an expert hiring.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | The possibility of having Manuals, Guides and Procedures are a valuable support for the identification of the true needs, as well as in the correct evaluation of them, avoiding waste of time and unwanted deviations in the subject in question. They allow to be more successful in identifying the purpose of each need to be identified, which may be gender, environmental or social.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The creation of greenhouses and the production of vegetables using the rainwater harvest as a water resource, has been very positive, especially in the female gender. In addition, the work carried out by the machinery has allowed these small farmers, who were always postponed by the businessmen of the sector due to their small surface, to considerably improve their productions. Also, the success of the agroclimatic tables has led farmers to share their experiences and make decisions based on what they learn.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Farmers have realized the negative impact generated by climate change, which has allowed them to share knowledge among themselves in order to adapt to this new reality. This project could be implemented in other regions of the country and the world, which added to the use of renewable energies, will generate a high positive impact on resilience to climate change.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | There are two major positive impacts: greater access to water thanks to the harvest of rainwater, generating its own vegetable production; and access to machinery that allows small producers to prepare the soils at the right times.
What measures are/have been put in place to ensure sustainability of the project/program results? | Raising awareness in small farmers to face the effects of climate change will generate measures to face this great challenge. The traditional way of doing agriculture will change considerably and we will have to be much more efficient in the use of water.
What measures are being/could have been put in place to improve project/program results? | Achieving greater work in community, sharing experiences of success and failure, will allow better results.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project sociologist has used the creation of surveys that allow to know the situation of each one of the beneficiaries.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Yes. This information has been disseminated through the technical team of the project and the media with which it is working as local media, as well as social networks.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | 1) https://www.youtube.com/watch?v=1ZOBirzcOt0&t=4s 2) https://www.youtube.com/watch?v=Q_1gJ3HD0e8 3) https://www.youtube.com/watch?v=vM75sESf0Yg&t=5s
If learning objectives have been established, have they been met? Please describe. | Yes, learning objectives have been established in the trainings that were carried out prior to the Pandemic. In them, the farmers were trained in all the important topics and at the end a satisfaction survey was applied to them regarding what was taught. They were taught about topics such as the use of the electric fence and the use of the scarifier plow.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The greatest difficulties were generated due to the fact that there are other actors in the region, but during year 3 we have managed to work together with them, focusing on the same objective, which is to provide knowledge and tools to small farmers so that they can better cope climate change.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, it has contributed since nowadays small farmers are aware of what climate change is and how they should work to maintain themselves as farmers.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | Scarifying farmers who have never done it before, in order to improve their uptake of water in the soil profile, is a tremendous innovation, as is harvesting rainwater from rooftops. In addition, holding agro-climatic tables in order to share experiences and knowledge of successes and failures, could also be considered a great innovation since before the project it was not carried out.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | Gobierno Regional de O´Higgins (O'Higgins Regional Government) has allocated resources for small producers in the area, due to the agricultural emergencies they have faced.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | CHL/NIE/Agri/2013/1
Implementing Entity | Ministry of agriculture (MINAGRI)
Type of implementing entity | NIE
Country | Chile
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 10331 | 2208 | 8123 | Total | 2539 | 355 | 2184 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 31% | 31% | 31% | % of female beneficiaries | 48% | 47% | 48% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 255 | Multi-sector | 3: Medium capacity | Total | 255 | Multi-sector | 3: Medium capacity | Total | 255 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 40% |  |  | % of female targeted | 40% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  | Public |  | 255 | 40% | Public |  | 89 | 36%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 3: Medium capacity | Public | Regional | Multi-sector | 3: Medium capacity | Public | Regional | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100% |  | Multi-sector |  | 25% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 10331 | 31% | 1: Aware of neither |  | 10331 | 31% | 4: Mostly aware |  | 2539 | 48% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness