## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | November 2017-October 2018
| Project Title: | REDUCING THE VULNERABILITY BY FOCUSING ON CRITICAL SECTORS (AGRICULTURE, WATER RESOURCES, AND COASTLINES) IN ORDER TO REDUCE THE NEGATIVE IMPACTS OF CLIMATE CHANGE AND IMPROVE THE RESILIENCE OF THESE SECTORS
| Project Summary: | Support the development of Costa Ricas’s adaptation capacity in line with the Plan Nacional de Acción de la Estrategia Nacional de Cambio Climático (National Action Plan of the National Strategy on Climate Change)
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Fundecooperacion para el Desarrollo Sostenible | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Costa Rica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communities. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-11-01
IE-AFB Agreement Signature Date: |  | 2014-12-10 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-10-07 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-04-07
| Terminal Evaluation Date: | 2020-10-07
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | #FondodeAdaptaciónCostaRica for Facebook's news. "Coffee Producers in Costa Rica Use Science to Tackle Climate Change" http://www.ipsnews.net/2016/10/coffee-producers-in-costa-rica-use-science-to-tackle-climate-change/ “Si no tomamos en consideración la mitad de la población cómo esperamos tener un desarrollo mayor” https://larutadelclima.org/2016/11/18/si-no-tomamos-en-consideracion-la-mitad-de-la-poblacion-como-esperamos-tener-un-desarrollo-mayor/ "Primer informe del Piloto de Adaptación en Zonas Cafetaleras" https://www.youtube.com/watch?v=e2pfGbkuemY&feature=youtu.be "Nuevos seguros “verdes” premiarán a agricultores que se adapten al cambio climático" https://ojoalclima.com/nuevos-seguros-verdes-premiaran-a-agricultores-que-se-adapten-al-cambio-climatico/ "Sistema de Fertirriego de Purines del Sr Ronald Rodríguez beneficiario del proyecto de adaptación que implementa la Cámara Nacional de Productores de Leche" https://www.facebook.com/ganaderiabajaencarbono/videos/686533231536884/ "Costa Rica es un laboratorio. Nuestros Entes Ejecutores del Adaptation Fund son ejemplo para el mundo en #accionesclimáticas" https://www.facebook.com/dccCostaRica/videos/1632324030132590/ "Acciones a través del Programa País del Fondo de Adaptación" http://www.ambientico.una.ac.cr/pdfs/art/ambientico/A6.pdf "Acciones climáticas" https://www.facebook.com/dccCostaRica/videos/1199098133455184/ "41-fincas-lecheras-modelo-inician-proceso-de-adaptacion-al-cambio-climatico" http://presidencia.go.cr/comunicados/2016/06/41-fincas-lecheras-modelo-inician-proceso-de-adaptacion-al-cambio-climatico/ "Caficultores de Costa Rica enfrentan cambio climático con ciencia" https://www.elpais.cr/2016/10/02/caficultores-de-costa-rica-enfrentan-cambio-climatico-con-ciencia/ "Reservorios de agua de lluvia en Hojancha destacan en la cumbre de cambio climático, en Marruecos" http://www.vozdeguanacaste.com/es/articulos/2016/11/17/reservorios-de-agua-de-lluvia-en-hojancha-destacan-en-la-cumbre-de-cambio "En agosto la UNAFOR iniciará la implementación del proyecto ”Fortalecimiento del sector campesino frente al Cambio Climático en Hojancha, Nicoya y Nandayure" http://www.periodicomensaje.com/ambientales/1826-en-agosto-la-unafor-iniciara-la-implementacion-del-proyecto-fortalecimiento-del-sector-campesino-frente-al-cambio-climatico-en-hojancha-nicoya-y-nandayure "Proyecto comunal permite a cantones solucionar problemas de acceso al agua y sequía" https://www.larepublica.net/noticia/proyecto-comunal-permite-a-cantones-solucionar-problemas-de-acceso-al-agua-y-sequia "El Fondo de Adaptación en Costa Rica" http://larutadelclima.org/2016/04/11/fondo-de-adaptacion-en-costa-rica "NOGAL-juego para conocer de Adaptación al Cambio Climático" "Manual de Buenas Prácticas Bríbris y Cabecar" http://es.calameo.com/read/0047140859c1a66ce6402 "El Fondo de Adaptación en Costa Rica y ACEPESA" https://larutadelclima.org/2016/05/17/el-fondo-de-adaptacion-en-costa-rica-y-acepesa/ Juntos por el Mar- Almanaque, video y audio. “El cambio climático ya tiene un impacto en el Parque Nacional Marino Ballena” http://www.vocesnuestras.org/2017-09-07/articulo/cambio-climatico-ya-tiene-impacto-parque-nacional-marino-ballena "Hacia una cultura de adaptación" https://gwpcam.wordpress.com/2017/02/10/hacia-una-cultura-de-adaptacion/ “25 fincas de Puriscal cambiaron sus técnicas de trabajo para ser más eficientes y enfrentar el cambio climático” https://www.ameliarueda.com/nota/25-fincas-de-puriscal-transformaron-operaciones-para-ser-mas-eficientes Talleres con Entes Implementadores Nacionales: https://www.facebook.com/dccCostaRica/videos/1632324030132590/ Projects videos: ALIARSE: https://www.youtube.com/watch?v=sdoY-kjT1S8 COOPEPURISCAL: https://www.youtube.com/watch?v=ubfhwvWn__Q | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.fundecooperacion.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Carolina Reyes | Dominican Republic
| Email: | creyes@fundecooperacion.org | Ecuador
| Date: | 2017-10-10 | Egypt
| Government DA |  | El Salvador
| Name: | Andrea Meza | Equatoral Guinea
| Email: | cambioclimatico@minae.go.cr | Eritrea
| Date: | 2017-10-10 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Carolina Reyes | Fiji
| Email: | creyes@fundecooperacion.org | Finland
| Date: | 2017-10-10 | France
PCU coordinator
Marianella Feoli Peña
mfeoli@fundecooperacion.org
2017-10-10
| Executing Agency |  | Gambia
| Name: | Ministerio de Agricultura y Ganadería | Georgia
| Email: | nmoras@mag.go.cr | Germany
| Date: | 2017-10-10 | Ghana
| Executing Agency |  | Greece
| Name: | MARVIVA | Grenada
| Email: | andres.santana@marviva.net | Guatemala
| Date: | 2017-10-10 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Asociación de Organizaciones del Corredor Biológico Talamanca Caribe | Guyana
| Email: | corrbiol@racsa.co.cr | Haiti
| Date: | 2017-10-10 | Honduras
Executing Agency
| Name: | Coopepuriscal.
| Email: | coopepuris@racsa.co.cr
| Date: | 2017-10-10
Executing Agency
| Name: | Café Forestal
| Email: | cafeforestal@coocafe.com
| Date: | 2017-10-10
Executing Agency
| Name: | INDER
| Email: | scamareno@inder.go.cr
| Date: | 2017-10-10
Executing Agency
| Name: | CNPL
| Email: | csalazar@proleche.com
| Date: | 2017-10-10
Executing Agency
| Name: | UNAFOR
| Email: | eloymg91@gmail.com
| Date: | 2017-10-10
Executing Agency
| Name: | CAC-Jicaral
| Email: | soniaduron@gmail.com
| Date: | 2017-10-10
Executing Agency
| Name: | INTA
| Email: | arosales@inta.go.cr
| Date: | 2017-10-10
Executing Agency
| Name: | ALIARSE
| Email: | grettel.calderon@aliarse.org
| Date: | 2017-10-10
Executing Agency
| Name: | CATIE-INS
| Email: | mariela.morales@catie.ac.cr
| Date: | 2017-10-10
Executing Agency
| Name: | ACEPESA
| Email: | mmarin@acepesa.com
| Date: | 2017-10-10
Executing Agency
| Name: | CEDARENA
| Email: | vreyes@cedarena.org
| Date: | 2017-10-10
Executing Agency
| Name: | IMN
| Email: | archacon@imn.ac.cr
| Date: | 2017-10-10
Executing Agency
| Name: | SETENA
| Email: | nchavarria@setena.go.cr
| Date: | 2017-10-10
Executing Agency
| Name: | ICICOR
| Email: | Jorge.Solano@icicor.com
| Date: | 2017-10-10
Executing Agency
| Name: | CORCOVADO
| Email: | alejandra@corcovadofoundation.org
| Date: | 2017-10-10
Executing Agency
| Name: | KETO
| Email: | cmolina@fundacionketo.org
| Date: | 2017-10-10
Executing Agency
| Name: | CREMA
| Email: | inaranjo@cremacr.org
| Date: | 2017-10-10
Executing Agency
| Name: | CATIE-APROCO
| Email: | rmuschler@yahoo.com
| Date: | 2017-10-10
Executing Agency
| Name: | FUNDECOR
| Email: | pzuniga@fundecor.org
| Date: | 2017-10-10
Executing Agency
| Name: | MAG-BIOLES
| Email: | gflores@mag.go.cr
| Date: | 2017-10-10
Executing Agency
| Name: | CIEDES
| Email: | rafael.oreamuno@gmail.com
| Date: | 2017-10-10
Executing Agency
| Name: | CFIA
| Email: | vnaranjo@cfia.cr
| Date: | 2017-10-10
Executing Agency
| Name: | PRODUS
| Email: | luis.zamoragonzalez@ucr.ac.cr
| Date: | 2017-10-10
Executing Agency
| Name: | SIREFOR
| Email: | gmadrigal@addax.cr
| Date: | 2017-10-10
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to Oct, 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 10/10/2017 | 2713520
Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is deducted.
INVESTMENT INCOME | 71871
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | 2016 | 2017 |  | Total | Total 2018
| 1.1 | 417461.7628 |  |  | 444317 | 570882.0332 | 1015199.0332 | 1432660.796 | 417461.7628
| 1.2. | 91546.73 |  |  | 20000 | 20000 | 40000 | 131546.73 | 91546.73
| 2.1 | 56520.02 |  |  | 50672.97 | 9284.79 | 59957.76 | 116477.78 | 56520.02
| 2.2 | 229004.96 |  |  | 288339 | 21736.32 | 310075.32 | 539080.28 | 229004.96
| 2.3 | 73068.4 |  |  | 115606 | 104489.67 | 220095.67 | 293164.07 | 73068.4
| 3.1 | 100904.43 |  |  | 9834 | 102707.47 | 112541.47 | 213445.9 | 100904.43
| 3.2 | 64703.18 |  |  | 119731.63 | 149086.65 | 268818.28 | 333521.46 | 64703.18
| 3.3 | 13314.63 |  |  | 11811 | 143131.7 | 154942.7 | 168257.33 | 13314.63
| EE Fee | 20000 |  |  | 180014.4984 | 75351 | 255365.4984 | 214603.8412 | -40761.6572
| NIE FEE | 157037.3446 |  |  | 123355.041 | 153169 | 276524.041 | 433561.3855 | 157037.3446
| TOTAL | 1223561.4574 | #REF!
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | Aprobado Año 1 | Reportado Año 1 | Aprobado Año 2 | Reportado Año 2 | Aprobado Año 3 | Reportado Año 3 | Aprobado Año 4 | Total Aprobado | Total Reportado | Projected Cost
| 1.1 | 522339.204 | October 2019 | 345000 | 444317 | 575000 | 570882.0332 | 575000 | 417461.7628 | 460000 | 1955000 | 1432660.796 | 522339.204
| 1.2. | 468453.27 | October 2019 | 50000 | 20000 | 180000 | 20000 | 220000 | 91546.73 | 150000 | 600000 | 131546.73 | 468453.27
| 2.1 | 237403.4389 | October 2019 | 141552.4982 | 50672.97 | 212328.7207 | 9284.79 | 0 | 56520.02 | 0 | 353881.2189 | 116477.78 | 237403.4389
| 2.2 | 900000 | October 2019 | 306563.8709 | 288339 | 527605.8757 | 21736.32 | 527606.4514 | 229004.96 | 492085.1612 | 1853861.3592 | 539080.28 | 1314781.0792
| 2.3 | 469450.3552 | October 2019 | 132704.6329 | 115606 | 237100.4048 | 104489.67 | 223830.547 | 73068.4 | 168978.8405 | 762614.4252 | 293164.07 | 469450.3552
| 3.1 | 292474.1 | October 2019 | 81600 | 9834 | 201280 | 102707.47 | 146880 | 100904.43 | 76160 | 505920 | 213445.9 | 292474.1
| 3.2 | 425358.54 | October 2019 | 122400 | 119731.63 | 301920 | 149086.65 | 220320 | 64703.18 | 114240 | 758880 | 333521.46 | 425358.54
| 3.3 | 333942.67 | October 2019 | 81000 | 11811 | 199800 | 143131.7 | 145800 | 13314.63 | 75600 | 502200 | 168257.33 | 333942.67
| EE Fee | 127583.5016 | October 2019 | 214056 | 180014.4984 | 144631 | 75351 | 179631 | -40761.6572 | 144631 | 682949 | 214603.8412 | 468345.1588
| NIE FEE | 193166.6145 | October 2019 | 176682 | 123355.041 | 146682 | 153169 | 146682 | 157037.3446 | 156682 | 626728 | 433561.3855 | 193166.6145
| TOTAL | 3970171.6942
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 3317341
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 3317341
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | It is expected a total of $5.500.000 of co-financing by the Terminal Evaluation. The co-financing of the project is in-kind and part in cash..

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Extreme weather events or geophysical events diminish programme benefits or cause major disturbances resulting in delays due to needed emergency and recovery processes. | Low | Year 1 The implementation has considered the improvement of community preparation and response by developing and consolidating early warning protocols and systems. Year 2 Differente extreme weather events happened at the end of 2016 and during 2017, Hurrican Otto and Tropical Storm Nate, afected several of the areas where the programme is being implemented. Year 3 Although no other extreme weather events happened during the 3 year, the affectations received from Hurrican Otto and the Tropical Storm Nate created a delay in the implementation of actions thou the recovering process was implemented days after and took several months.
Programme beneficiaries resistant to change or weak cooperation at the proposed sites | Low | The development of the project considers the involved of the consultation of different stakeholders such as organizations, public and private institutions, that are implementing projects related to climate change. The processes facilitate an active participation of the beneficiaries in order to reinforce the beneficiaries’ ownership of the project, supporting proactive and community-led initiatives.
Project beneficiaries are unable to properly manage the technologies or measures being promoted, and/or the technologies or measures do not improve operational efficiency | Low | Knowledge transfer and awareness building through capacity building activities are contemplated throughout the programme. Promotes a capacity development approach which is based on participatory assessments. These assessments will contribute to building the beneficiaries’ ownership and enable the analysis of autonomous adaptation approaches.
Stakeholders are not able to perceive reductions in vulnerability over the time-scale determined by programme duration. | Low | Maintain proactive outreach communications strategy throughout the programme. Also, the programme is strengthening local capacity to monitor project indicators through the support of the Executing Entities.
Insufficient collaboration/coordination between participating partners and stakeholders | Low | Establishment of agreements with detailed roles and responsibilities, work plans and team building activities throughout the programme implementation. Up to now has been important the participation of NGO’s, public organization, academia and other organizations and has been possible to create alliances among organizations. Up to today, the projects selected include letters of commitment among the EE and partners/stakeholders. Also we had made meetings with each organization to confirm their participation. Also, the NIE has signed contribution agreements and MOU's with stakeholders and partners; with the interest of formalize their participation with the adaptation Fund Programme in Costa Rica. For example, an agreement was sighed with Fundación CRUSA for over $800.000 for the implementation of actions at the local level and an MOU with the Agriculture Ministry for the technical support of the projects. Year 3 A very important colaboration between different organizations initiated during this year, as a result of a possible drought that will affect the country during most of the next year. The participation of the Ministry of Agricuture and the sector in general, along with Fundecooperación have been working in creating conciou in the importance of adapt to climate change.
Delays in programme implementation | Low | Programme activities have been designed and paced to ensure a reasonable chance of completion over five years. The Programme Management Board will provide required oversight for management of programme inputs. Year 3 The implementation of the Programme Adapta2+ have some delay, however the indicators are in general on track, because the EIN have been working in the ones that are more difficult to achieve in less than 2 years. The outputs that have some problems are the ones were the Executed Entity have not been indentified yet-
Limited human resources in Government ministries to support activities. | Low | Promotion of early and consistent engagement of senior government decision makers on programme progress and monitoring. Fundecooperación, as NIE, has signed cooperation agreements with the government ministries (that are related to the components) in order to received technical assistance in the field.
Mismanagement of Resources. | Low | Each of the project Executing Entities reports each semester at the financial and technical level. Year 1 A project financial evaluation each semester is made by the NIE to each of the project. Disbursements are to be done depending on the results of the evaluation of the EE and if there are not improvements to be done by the EE. Both the internal and external audits review and verify the sound management of resources of the project by Fundecooperación.
Fluctuations in exchange rate | Low | Financial Coordinator monitor exchange rate (USD to Colones) in order to communicate any implication to the PC. It is important to mention the exchange rate has during the last months have been beneficial to the project.
Delays in disbursements affects project progress | Low | In order to avoid delays has been important to anticipate as much as possible and to promote constant coordination among National Implementing Entity, Executing Entities and the Adaptation Fund. However, delays can happen and some of the delays respond to the importance of responding 100% to the requirements at the financial and administrative level.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Bank scams accounts of the projects | Medium | Awareness building to EE on the risks of banking scams and strentghening financial procedures at the EE. Explanatory comments of why this was identified as risk: Two Executing Entities suffered of bank scams. Specifically, ACEPESA and CAC-JICARAL, both entities reported us what happened and did the procedures required by the Investigation Agency of Costa Rica to recover the money. Both entities assumed due responsibility and replenished the money that was stolen with their own funds in order to continue with the planned activities of the project, while the money is recovered by the Investigation Agency. Also, this situation/risk was informed to all the other Executing Entities, in order to avoid more scams.The Executing Entities, once they receive the disbursment from the NIE, the organization must invest the money in order to avoid be easily scam by having the money in the current account. For example, funds committed in the short term must be invested in liquid money market or similar, looking for the alternative that offers the best profitability conditions with low risk. These liquidity options must ensure adequate compliance with the project's operational commitments. All interest income in case generated, will be used for the project as instructed by AFB.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Programme Implementation Oversight Reunions |  | Framework functioning effectively |  | YEAR 1 Meetings with several authorities at the national level, this reunions serve as the main mechanism for the provision of technical and strategic advice. The reunions comprised members from different stakeholders with technical interest and knowledge; including relevant government Ministries representatives, Departments and Agencies, the Private Sector Organization, academia, and NGO partners. There were two (2) meetings held in 2016. Also, NIE has implemented regular meetings with executing partners to support the implementation process. The meetings provide a platform for knowledge sharing and allows collaboration among organizations to interact with and support each other. This meetings serves as a way for systematically identifying and helping to proactively resolve operational bottlenecks. YEAR 2 At the beginning of the year a monitoring meeting along with several allies of the programme was implemented, in order to confirm support, to improve any action that it is supported by the Adaptation Fund and to seek for possible sinergies among the programe and other initiatives. Also, different meetings were implemented with the Executing Entities in order to: follow up the execution of the activities, to support the Entities to compliance with different aspects that are being requested at the national level (such as the new labor law) and to support, at the national level, the creation of the National Adaptation Plan (NAP). This is particularly important because the Programme here in Costa Rica has given important inputs to the NAP. YEAR 3 As an important result, a Midterm Evaluation Event was held in april this year, in order to report to all of our stakeholders the results of the Programme. A document that indicates the multidimentional approach of the Adapta2+ Programme and it's relationship with Costa Rica's Intended Nationally-Determined Contributions, SUstainable Development Goals, National Adaptation Plan, and the National Development Plan was made in order to promote the impact and the importance of the programme at local, national and international level. This event, reconfirmed the work made during the past years and the importance of the work that is now in implementation. Also is imporantant to mention that this year was an election year, so it was necessary to have extra meetings along with the new authorithies, to confirm the importance of the Programme and the support of the goverment to the initiative. | S
| Promotion and Awareness |  | Implementation Communication actions |  | YEAR 1 The Programme was featured in the different media and magazine publications at the local level (Ambientico and magazine Agropecuaria/MAG). Also the programme also participated in/supported awareness initiatives such as "Juntos por el Mar", Congreso Nacional Forrajero 2016, and Congreso PCCMCA, were the adaptation subject has been included. Some of the results: *Appearances in national TV and newspapers promoting the Adaptation Fund in Costa Rica. *More than 16 workshops had been held in different communities. *Participation at the COP 22 in order to present many of the results achieved by the programme at the local level. YEAR 2. An important aspect for promotion and awareness of the Programme in Costa Rica, was to differentiate the name of the programme here in Costa Rica from the donor's name. Is important to clarify, that usually here in Costa Rica, the people is used to call the projects as the donor's name; so it was important to make a difference and as a way of positioning the programme results and the organization that is financing the initiative. For this reason, the name Adapta2+ was created. Also, Adapta2+ was featured in the different media at the local level (newspapers, radio and social media), participated in/supported awareness initiatives such as the Congreso Nacional Lechero 2017 (were the National Adaptation Project was presented), the Climate Finance Readiness Seminar 2017 and the "National Adaptation Plan Workshops" /that were implemented by the Designated Authority). Some of the results: *Appearances in national TV and newspapers promoting the Adaptation Fund Seminar in Costa Rica. Specificadly, the project of Coopepuriscal was promoted. *Other appearances in national newspapers promoting projects: 1. Final results of the project implemented by ALIARSE. 2. Improvements and objectives of the project implemented by Keto 3. Results obtained by UNAFOR, executing entity that is implementing a project in Guanacaste. 4. Progress Status of the Insurance for the Agricultural Sector *Promotion of the Programme Adapta2+ at the COP22, promoting the the results of the first year of implementation. *2 project videos: ALIARSE and Coopepuriscal *More than 6 workshops had been held in different communities. | S
Year 3 As is was mentioned before, and important Mid-term Event was held in order to inform the different actors of Adapta2+ the results obtained durng the past years of impleementation and it's support on the country commitments. The result was beyond expected, and the results were presented in diferent websites and social media; the main reason, the results obtained supports the work of Costa Rica and has been possible due the work of many institutions. A new website was implemented, were the information of each project can be found, also our Ethic Code, Environmental and Social Policy and the differents results of Fundecooperacion initiatives. (www.fundecooperacion.org) The Programme participated in/supported awareness initiatives such as the Congreso Nacional Lechero 2018 (were the National Adaptation Project was presented), the Forrage Congress 2018, Expo Pyme 2018, "Understanding Risk Forum 2018: Disrupt, comunicate, influence”, II National Congress: Livestock adapted to Climate Change (II Jornada Nacional de Actualización: “Ganadería Adaptada al Cambio Climático”), IV National Congress of Risk Management and Adaptation to Climate Change (“IV Congreso Nacional de Gestión de Riegos y Adaptación al Cambio Climático”), the "First National Congress for the Regulation of Public services: quality as a human right" (Congreso Nacional de Regulación de los Servicios Públicos: la calidad como un derecho ciudadano) and the NAP Regional Expo. Some of the results: *Appearances in national TV and newspapers promoting the Programme Results at the midterm of implementation. 1. 11 Project Videos created: (Executing Entities: Keto, ACEPESA, ABANGARES, JICARAL, UNAFOR, CBTC, INDER, MAG-BIOLES) 2. An Insurance for the Agricultural Sector is already in place and promoted by different financial entities as a warranty for loans in the sector. 3. 2 financial products in place for the livestock sector and the Agriculture sector, in order to promote adaptation measures. 4. A new project implemented in order to prepare the livestock sector to the drought of 2019. 5. More than 10 workshops had been held in different communities. 6. One of the projects was the winner of the category "Female Leadership" at the NAP EXPO 2018.
| Monitoring and field visits |  | Monitoring visits facilitation |  | YEAR 1 Each of the Executing Entity must report the financial and technical improvements each semester. Executing Entities reports were reviewed and feedback was provided with recommendations for improvement. Field visits were undertaken by NIE along with partners (more than 15 field visits), to meet with beneficiaries in target communities and also to confirm the implementation of the actions. Monitoring visits allows to gain a better understanding of the actions, verify expenditures made and confirm that work and results are as planned. YEAR 2 Is important to mention that also each project must report twice a year, and the reports included documents that allows the NIE to confirm the results. However, as NIE, is important to visit, along with partners, the sites of the projects. For this reason, more than 9 field visits were undertaken during the year. Also, in some cases videos were made to promote the results of the projects at the local level: the videos of the projects implemented by ALIARSE and COOPEPURISCAL are now available. YEAR 3 *Videos have been prepare, of at least 13 of the initiatives implemented. *Also 6 audit evaluations were held during the year for those projects that are almost in the final stage of implementation. *More thatn 10 field visits held during ht year. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Carolina Reyes
| Email: | creyes@fundecooperacion.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The implementation of the programme at this stage has been good; until now there are many results achieved at the local level. It is expected to achieved even more results by the fourth year.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component1 |  | Increasing the adaptation capacity to climate change in the agricultural sector Some expected results at the second year: -At least 16 agricultural and livestock units has identified technological options -At least 16 plans for adaptation at farm level |  | YEAR 1 To date the programme has started almost 11 initiatives that respond to agricultural adaptation needs in each of the communities selected. Up to date the programme has achieved the implementation of adaptation measures in 84 farm units. Each unit with its plans farm plans created. YEAR 2 During the second year, 11 initiatives continue their implementation and a new project started its implementation. This new project also responds to agricultural adaptation needs in each of the communities selected. Up to date the programme has achieved the implementation of adaptation measures in 160 farms units. Each unit with its farm plans created. YEAR 3 By the third year of implementation, a new initiative was supported, specificadly in food security. Also, a very important initiative finished it's implementation in a very succesfull way, agriculture and livestock insurance is now a reality in the country. Another important result was the increase of farms units that are implementing adaptation measures, the number is now up to 483. | HS
| Component 2 |  | Improving water resources management in order to increase resilience in coastal communities that are more vulnerable to climate change. Some expected results at the second year: -10 Operadores have implemented a Water Safety Plan or Watershed Management Plans -At least 3 ASADAS have undertaken a vulnerability assessment -10 hectares of aquifer recharge areas reforested |  | YEAR 1 To date the programme has started almost 10 initiatives-projects that respond to water resources and coastal areas adaptation needs in each of the communities selected. Up to date: -4 ASADAS have implemented a Water Safety Plan -4 ASADAS have undertaken a vulnerability assessment -25 hectares of aquifer recharge areas reforested YEAR 2 The second year two more initiatives-projects started, those initiatives respond to water resources adaptation needs. However, the implementation of those 2 projects started in september 2017. Up to date: -9 ASADAS have implemented a Water Safety Plans or Strategies to implement improvements . -4 ASADAS have undertaken a vulnerability assessment. -33.94 hectares of aquifer recharge areas reforested YEAR 3 This third year of implemention, a new initiative was supported wth the intention of invigorate the economy of the coastal-rural areas that usually suffer less development and are the areas were the climate change has affected the most in the last years. With this in mind, the second part of the project will be implemented in 2019 with the support of other donors. -9 ASADAS have implemented a Water Safety Plans or Strategies to implement improvements . -4 ASADAS have undertaken a vulnerability assessment. -127 hectares of aquifer recharge areas reforested- -A water resource protection fee already in place | S
| Component 3 |  | 1. Implementation of different projects at the local level that respond to the adaptation needs of each community. 2. Improving the capacity of communities, producers, institutions, and stakeholders regarding adaptation to Climate Change. |  | YEAR 1 All the projects include, as a cross-cutting theme, the improvement of capacities at the local level. At the same time, specific projects that allow the creation of knowledge tools and the improvement of national frameworks has been supported by the programme. YEAR 2 2 new projects started in order to improve the capacity of national organizations and communities to adapt to climate change. This 2 projects along with the ones that already started, have an important impact on the Adapta2+ indicators. Adapta2+has created several knowledge materials such as: *Manual of Bribri and Cabécar Ancestral Practices *A training guide on adaptation to climate change. *Nogal: A video-game on climate change for kids. *Study Cases YEAR 3 2 ew projects started in order to improve the capacity of national organizations and communities to adapt to climate change. Some other projects finished in a very succesful way and with great results; a new land management policy that includes criteria for adapting to climate change is already delivered to the ministty of enviroment for its approval | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Marianella Feoli as PCU coordinator
| Email: | gerencia@fundecooperacion.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | YEAR 1 The rating of S is because, even though the budger implementation has been slow, we have achieved several important results at the local level. The main reasons for the delay has been that the executing entities, specially the ones in charge of the component 2, had to overcomen some issues in order to start implementation. Component 1 has been the component with more implementation at the local level creating specifics examples of adaptation. However, is important to mention that the second component, in specific coastal zones, had better implementation during this year. The work along with many partners ia a priority in order to ensure the sustainability of the projects and the implementation of the different actions at the local level. Is important a continuos dialogue with the stakeholders and other initiatives. The interaction of different initiatives with the projects that had been implemented had already results that increase the impact. The progress and achievement of concrete results certainly demonstrates the good management and implementation until now; we are expecting even better results during the upcoming periods. YEAR 2 The rating of S is because, even thou an improvement was made in the implementation of actions that responds to the second component, the initiatives started until september 2017. Fundecooperación continuous working with partners from different sectors to ensure the sustainability of the projects, a continuous dialogue with the stakeholders and other initiatives to increase impact and to seek for more opportunities to support adaptation measures and to leveraging existing resources to improve impact and value of the actions. Although we consider we can improve, concrete results were achieved during the year and that certainly demonstrates the good implementation of the Adapta2+. Also, we consider that a better result will be achieved during the upcoming periods and the initiatices that alredy started will have more results at the local level. YEAR 3 The rating of S is because, even thou we have been working in the results of the second component, the work is still in a early stage. The mid-term evaluation result, confirms the good job we have been doing, and also the improvements we need to make in order to achieve the resuls expected. The main problem is that some results still doesnt have an executing entity that can implement at the local level the projects that are needed. For this reason, projects that can nvigorate the economy of the coastal-rural areas are needed in order to stretengh the communities and the organizations.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator: indicators towards Objectives
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1.1.1. | ZAE maps for selected crops of the Central Region | Last ZAE maps of the country were made in 1980 | 2 | 13
1.1.1. | technological showcases implemented and applying technology options for the adaptation to climate change in Naranjo, Puriscal, Dota and Pacayas. | 0 technological showcases implemented | 0 | 4
1.1.1. | Online platform with updated information on adaptation technologies and zoning scenarios | 0 | 0 | 1
1.1.1. | beneficiaries (50% women and 50% men) | 0 | 762 | 1000
1.1.2 | Agricultural and livestock units has identified technological options | 0 units has identified technological options | 483 | 90
1.1.2 | Plans for adaptation at farm level | 0 Plans for adaptation at farm level | 483 | 90
1.1.3 | beneficiaries (50% women and 50% men) | 0 | 1909 | 1000
1.1.3 | Discrete agricultural adaptation practices are demonstrated on-farm. Adaptation practices include: enhanced water management techniques, enhanced soil management practices, planting techniques, post-harvest processing and diversified livestock practices. | 0 | 483 | 90
1.1.3 | Number of farms implementing actions | 0 | 483 | 90
1.1.3 | ha on indigenous territories implementing technical options and methods that enhance their resilience to the effects of climate change | 0 | 352 | 1000
1.2.1 | -At least 10 initiatives per year have access to credit schemes for the implementation of adaptation activities | 0 | 16 | 10
| -At least 5 microfinancing institutions include credit products available to local small producers for adaptation to climate change | 0 | 1 | 5
2.1.1 | At least 50 ASADAS and 2 municipalities have implemented adaptation actions to improve the access to water of their communities | 0 | 7 | 52
2.1.1 | At least 12 ASADAS have undertaken a vulnerability assessment | 0 | 4 | 12
2.1.1 | At least 3 committees formed by various social actors | 0 | 4 | 3
2.1.1 | At least 25,000 water users beneficiated | 0 | 2098 | 25000
2.1.2 | At least 5 measures implemented for integrated watershed protection | 0 | 94 | 5
2.1.2 | 5000 hectares of the watershed improved directly or indirectly by the implementation of management practices | 0 | 0 | 5000
2.2.1 | At least 50 hectares of aquifer recharge areas reforested | 0 | 108 | 50
2.2.1 | Protection of aquifers | 0 | 12 | 1
2.2.2 | At least 25,000 inhabitants in 50 communities have their water supply and associated infrastructure, improved to manage climate-induced impacts on water supply | 0 | 767 | 25000
2.2.2 | 50 communities have their water supply and associated infrastructure improved | 0 | 4 | 50
2.2.3 | -At least 10 initiatives per year | 0 | 3 | 10
| -At least 2 credit products available for adaptation to climate change of local water management associations (ASADAS) and national water systems | 0 | 0 | 2
2.3.1 | At least 500 citizens in coastal zones are prepared and trained to deal with the impacts of climate change | 0 | 1446 | 500
2.3.1 | At least 10 coastal communities have implemented at least one adaptation measure | 0 | 34 | 10
2.3.1 | 8 km of coastline and beaches in protected areas, redesigned and reforested | 0 | 24 | 8
2.3.1 | At least 1 Community Coastal Reforestation Program | 0 | 2 | 1
2.3.3 | 25 ha of mangrove reforested in Gandoca (including areas within the National Wildfire Refuge Gandoca Manzanillo) | 0 | 25 | 25
2.3.3 | At least one coastal community implement a mangrove nursery effective to combat coastal erosion | 0 | 2 | 1
3.1.1 | At least one Early Warning System and Emergency Protocol implemented | 0 | 1 | 1
3.1.1 | One management system and incident management for Forest Fires | 0 | 0 | 1
3.1.2 | At least 5 communities trained, involving traditional leaders, women and youth groups | 0 | 9 | 5
3.2 | At least 3,000 beneficiaries trained | 0 | 690 | 3000
3.2 | At least than 50 stakeholders participating in awareness raising events | 0 | 143 | 50
3.2 | At least 1000 policymakers and technical officers exhibit improved levels of understanding of climate risk assessment and planning processes for climate change adaptation. | 0 | 478 | 1000
3.2 | -At least 10 knowledge materials (experience notes, case studies, photo stories, videos, etc.) are generated per year starting from year 2 of the programme | 0 | 30 | 10
3.2 | -A completed and operationally tested “Handbook on Coastal Adaptation”, "Technical Guide for Adaptation to Climate Change for the artisanal fishing sector" and "Handbook on Water Supply Systems Adaptation" is developed by the end of the project | 0 | 8 | 1
3.2 | Internalization of environmental costs of the water suppliers to facilitate their adaptation to climate change in vulnerable areas | 0 | 1 | 1
3.2 | -1 online training course | 0 | 1 | 1
3.3 | 70% of programme beneficiaries make use of improved climate risk information | 0 | 0 | 2100
3.3 | At least 10 properly installed and functioning new meteorological stations and information platforms | 0 | 6 | 10
Note on F40: Estacion13: ICICOR- SARAPIQUI RESILIENTE ACEPESA

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Year 1: - It is important to promote understanding among the NIE, EE, partners and the community groups in order to implement the project in the most successful way. - The support of allies among the projects are needed in order to increase the impact. However, a follow up from the NIE during the whole process is also needed to obtain results. The programme approach is to build partnerships with key national and local organizations in order to facilitate progress, obtain outputs, implement activities and shared objectives. -The constant coordination among the EE and the NIE is needed. The effective coordination allows transparency and good governance of the implementation process. Year 2: -It is important that during the implementation phase, external aspects affect sometimes the execution of activities Example: natural disasters. For this cases, it is important to consider to consider always additional time for the project and also technical support to the EE and communities. -Searching for initiatives that respond to some of the indicators of the project requires the support of additional possible EE and possible partners. Year 3: -The implementation has been delayed due that searching for Executing Entities that could respond in a good way to indicators that are need has been difficult. -Other indicators have been successfully achieved.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | YEAR 1 Many of the Executing Entities were not ready for complying with the different standards needed for the implementation of the project. This slowed the progress in some of the components. Also, a significant time and effort had to be spent addressing the requirements for the Environmental and Social Policy with each of the projects selected. The coastal sub-component has experience delays due to different challenges with the sector. Measures taken include the promotion of specific adaptive actions from the NIE with specific EE that will be choose considering their experience working with the sector. YEAR 2 The impact of natural disasters had delayed some of the actions. For this reason, re-planning the actions at the local level has been important, in order to respond to the needs and to ensure a good adaptation. YEAR 3 Although there is a delay in the budget implementation, several of the indicators have been achieved or should be achieved by 2020. Some other indicators are pending, this because an Executing Entity haven't been identified yet, as NIE we are supporting national authorities in order to identify the way to implement the pending issues. Specifically, the coastal areas are now with less support by the Programme.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Year 1. In order to implement actions on the ground the NIE had to: (i)facilitate access to information and data bases through the creation of alliances with the organizations that owns the information needed (ii) approved the engagement of technical staff that were already in the Executing Entities as part of the consultants in each of project (iii) to search for support at the technical level with some of the adaptation actions promoted specifically the ones that involves water. Additionally, there were special workshops with each EE to speed up the implementation. Year 2. Some changes had to be made in the following indicators: 1-At least 50 ASADAS and 2 municipalities have implemented a Water Safety Plan/ Watershed Management Plans. The WSP and WMP are methodologies barely known in the country. However, the interventions to be made, are going to be along with the advise of prestigious universities of the country. However, the creation of WSP are not the urgent actions that need to be taking care as a priority; direct interventions as a result of different analysis are the priority. For this reason, it would more reasonable an indicator such as: -At least 50 ASADAS and 2 municipalities have implemented adaptation actions to improve the access to water of their communities. Year 3: -No changes.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | YEAR 1 It is important to mention that the gender consideration on the programme is more focus from a family perspective; as a result, both men and women have been actively involved in programme activities. However, the programme has made efforts on mainstreaming gender into project implementation. The NIE has assisted Executing Entities to gain a better understanding of the importance of addressing gender issues. And to continue this efforts, Fundecooperación asked for the AF technical grant support in order to implement activities such as workshops, stakeholder sensitization sessions and development of the communications strategy etc. in order to comply with the AF Gender Policy. The composition of the PSC is an excellent example of gender equality as both men and women occupy decision-making positions. YEAR 2 During the second year, NIE conducted the implementation of the Gender Policy through an analysis of the gender conditions in different activities of the project along with partners. This has allowed the project to understand the aspects that the EE and us, as NIE, should be following during the implementation period.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | *Many of the adaptation should lead also to economic and social development in order to be implemented by the beneficiaries. *Is important to support the introduction of adaptation and resilience language in public policies in order to impact the country in general. *Adaptation sometimes is confuse with mitigation; so this is difficult as EIN to identify EE that have several experience in the topic
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | *Many of the activities promoted are promoted at the national level by the authorities, for this reason it is possible to promote this actions. *Other donors are now implementing similar actions in other geographic areas.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | *Some of the technologies implemented could be expensive or there are not many supplier which make difficult the implementation in several areas of the country
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | *The existence of a insurance for the agriculture sector have been a key result for the implementation of measures by other farmers, due the access to financial options. *Many ASADAS are now having a new rate to support adaptation measures.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | *The communities and beneficiaries are preparing and adapting to climate change. Some of them realized that, with the past extreme events that happened in the country, this helped to wake up in the need of doing changes. The target communities respond to the 2 types of extreme events, for this reason is easily to replicate the experiences to other communities.
What measures are/have been put in place to ensure sustainability of the project/program results? | *Transformation of Public policies to include the topic of adaptation to climate change as an important aspect to consider in order to implement future actions, such as: -Implementation of a Pilot Adaptation Project in Livestock and coffee to validate the initiatives to promote at national level.. -Adaptation in National Territorial Order. -Creation of a water resource protection rate . -Working with local governments in the inclusion of Climate risks in the analysis of territorial user permissions.
What measures are being/could have been put in place to improve project/program results? | *At national level, the access to climate information from the National Meteorological Institute has been difficult. By today, the main projects that needed this kind of information had to make negotiations in order to have access to the information, this took time and delayed the implementation of actions *It was necessary the creation of alliances in order to replicate and to have more impact at the local level.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | *Case Studies *Videos *Application to awards *Social Media
If learning objectives have been established, have they been met? Please describe. | *Learning tools have been generated and implemented locally with students, producers, technicians and decision makers. The training of trainers has been promoted as one of the most effective means to promote replicability and sustainability of the actions. It has also been important that component 3 has allowed the promotion of local and national impact actions by raising awareness of the importance of including the adaptation issue in the country's actions.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | * Climate information is difficult to access, due to the policies of the country's meteorological institute. These policies have complicated the implementation of some projects that require it in order to generate results. Finally, negotiations between the institutions involved have allowed the implementation of the projects, however it took time and delayed the results.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The learning objectives have contributed to generate a greater impact by allowing the creation of knowledge at the local level and replication of this impact at other levels. At the end, the implementation of the programme, and the learning objectives, were conceptualized in a bottom-up and top-down approach; for this reason, the 3 component "Creation of Capacities" have been able to promote initiatives such as: strengthening national organizations in the inclusion of the adaptation issue in their actions, generation of financial mechanisms for the replication of adaptation actions, creation of necessary tools and knowledge documents

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Fundecooperacion para el Desarrollo Sostenible
Type of implementing entity | NIE
Country | Costa Rica
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 4054842 | 3292 | 4051550 | Total | 4114984 | 3892 | 4111092 | Total
|  | % of female beneficiaries | 0 | 0% | 0% | % of female beneficiaries | 85.99% | 36% | 49.99% | % of female beneficiaries | 79.39% | 29.57% | 49.82% | % of female beneficiaries
|  | % of Youth beneficiaries | 0 | 0% | 0.003269% | % of Youth beneficiaries | 0.23 | 23% | 0% | % of Youth beneficiaries | 12.65% | 12.64% | 0.006% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 |  |  |  | 1 | Water management | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Water management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 1 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 |  |  | Total | 88 | Agriculture | 3: Medium capacity | Total | 211 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 13% |  |  | % of female targeted | 21.33% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
0%
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% |  |  | 204 | 20% | 3: Partially aware |  | 377 | 41% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Agriculture | Local | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
[6 empty] | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
[6 empty] | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
[6 empty] | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[6 empty] | 1 | National |  | Water management | 1 | National |  | Water management
[10 empty] | 1 | National |  | Agriculture
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 27 | ha rehabilitated | 3: Moderately effective | Mangroves | 25 | ha rehabilitated | 4: Effective | Mangroves | 25 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | km protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 12 | km protected | 3: Moderately effective | Catchment area/Watershed/Aquifer | 12 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha protected | 3: Moderately effective | Catchment area/Watershed/Aquifer | 108 | ha protected | 3: Moderately effective | Catchment area/Watershed/Aquifer | 127 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 95 |  | 3: Moderately effective | Cultivated land/Agricultural land | 343 |  | 3: Moderately effective | Cultivated land/Agricultural land | 379 |  | 3: Moderately effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Public policy | 1 | Water management | National | Public policy | 1 | Water management | National | Public policy
|  | No. of Policies introduced or adjusted | Sector | Scale | Type | 1 | Urban development | National | Public policy | 1 | Urban development | National | Public policy
|  | 0 | Urban development | National | Urban policy | 1 | Agriculture | National | Environmental policy | 1 | Agriculture | National | Environmental policy
|  | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on F98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: unit is left blank because it refers to the #of farms

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.