## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 2019 - December 2020
| Project Title: | REDUCING THE VULNERABILITY BY FOCUSING ON CRITICAL SECTORS (AGRICULTURE, WATER RESOURCES, AND COASTLINES) IN ORDER TO REDUCE THE NEGATIVE IMPACTS OF CLIMATE CHANGE AND IMPROVE THE RESILIENCE OF THESE SECTORS
| Project Summary: | Support the development of Costa Ricas’s adaptation capacity in line with the Plan Nacional de Acción de la Estrategia Nacional de Cambio Climático (National Action Plan of the National Strategy on Climate Change)
|  |  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Fundecooperación para el Desarrollo Sostenible |  | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Costa Rica |  | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communities. |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[9 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [7 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-11-01
IE-AFB Agreement Signature Date: |  | 2014-12-10 | [7 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-10-07 | [7 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2018-04-07
| Original Completion Date: | 2020-10-07
Revised Completion Date after approval of |  | 2021-04-07
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
| Planned actions, including a detailed time schedule |  | 1
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each |  | Cyprus
|  | *Inception Report-October 2015 *MTR-30-Nov-2018 |  | Czech Republic
List the Website address (URL) of project |  |  |  | Democratic People's Republic of Korea
|  | https://fundecooperacion.org/es/conozca-los-proyectos/ |  | Democratic Republic of the Congo
Denmark
| Project contacts: |  |  | Djibouti
National/Regional Project Manager/Coordinator |  |  |  | Dominica
| Name: | Carolina Reyes |  | Dominican Republic
| Email: | creyes@fundecooperacion.org |  | Ecuador
| Date: | 2019-10-10 |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Andrea Meza |  | Equatoral Guinea
| Email: | ameza@minae.go.cr |  | Eritrea
| Date: | 2019-10-10 |  | Estonia
| Implementing Entity |  |  | Ethiopia
| Name: | Carolina Reyes |  | Fiji
| Email: | creyes@fundecooperacion.org |  | Finland
| Date: | 2019-10-10 |  | France
| Executing Agency |  |  | Gambia
| Name: | Ministerio de Agricultura y Ganadería |  | Georgia
| Email: | fvargas@mag.go.cr |  | Germany
| Date: | 2019-10-10 |  | Ghana
| Executing Agency |  |  | Lithuania
| Name: | INTA |  | Luxembourg
| Email: | lramirez@inta.go.cr |  | Madagascar
| Date: | 2019-10-10 |  | Malawi
| Executing Agency |  |  | Malaysia
| Name: | ALIARSE |  | Maldives
| Email: | grettel.calderon@aliarse.org |  | Mali
| Date: | 2019-10-10 |  | Malta
| Executing Agency |  |  | Micronesia, Federated States of
| Name: | ACEPESA |  | Monaco
| Email: | mmarin@acepesa.com |  | Mongolia
| Date: | 2019-10-10 |  | Montenegro
| Executing Agency |  |  | Morocco
| Name: | ARESEP |  | Mozambique
| Email: | ezamora@aresep.go.cr |  | Myanmar
| Date: | 2019-10-10 |  | Namibia
| Executing Agency |  |  | Nauru
| Name: | IMN |  | Nepal
| Email: | archacon@imn.ac.cr |  | Netherlands
| Date: | 2019-10-10 |  | New Zealand
| Executing Agency |  |  | Serbia
| Name: | Ministerio Agricultura y Ganadería -BIOLES |  | Seychelles
| Email: | jsegura@mag.go.cr |  | Sierra Leone
| Date: | 2019-10-10 |  | Singapore
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to October 2016 |  |  |  | Financial information PPR 2: cumulative from project start to October 2017 |  |  |  | Financial information PPR 3: cumulative from project start to October 2018 |  |  |  | Financial information PPR 4: cumulative from project start to October 2019 |  |  |  | Financial information PPR 5: cumulative from project start to December 2020
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 10/10/2016 | 1363681.1393 |  |  | Estimated cumulative total disbursement as of 10/10/2017 | 2713520 |  |  | Estimated cumulative total disbursement as of 10-10-2018 | 3937081 |  |  | Estimated cumulative total disbursement as of 10-10-2019 | 5634802.9581 |  |  | Estimated cumulative total disbursement as of 10-12-2020 | 6579262
Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is reduce. |  |  | Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is deducted. |  |  | Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is deducted. |  |  | Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is deducted. |  |  | Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is deducted.
INVESTMENT INCOME | 18139.58 |  |  | INVESTMENT INCOME | 52702 |  |  | INVESTMENT INCOME | 71871 |  |  | INVESTMENT INCOME | 85709 |  |  | INVESTMENT INCOME | 59096.13
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 | 444317 |  |  | 1.1 | 570882.0332 |  |  | 1.1 | 417461.7628 |  |  | 1.1 | 13408.6398 |  |  | 1.1 | 240715.9742
| 1.2. | 20000 |  |  | 1.2. | 20000 |  |  | 1.2. | 91546.73 |  |  | 1.2. | 403015.27 |  |  | 1.2. | 0
| 2.1 | 50672.97 |  |  | 2.1 | 9284.79 |  |  | 2.1 | 56520.02 |  |  | 2.1 | 51857.25 |  |  | 2.1 | 0
| 2.2 | 288339 |  |  | 2.2 | 21736.32 |  |  | 2.2 | 229004.96 |  |  | 2.2 | 615338.03 |  |  | 2.2 | 376539.69
| 2.3 | 115606 |  |  | 2.3 | 104489.67 |  |  | 2.3 | 73068.4 |  |  | 2.3 | 81520.92 |  |  | 2.3 | 180793.41
| 3.1 | 9834 |  |  | 3.1 | 102707.47 |  |  | 3.1 | 100904.43 |  |  | 3.1 | 83698 |  |  | 3.1 | 71315.1
| 3.2 | 119731.63 |  |  | 3.2 | 149086.65 |  |  | 3.2 | 64703.18 |  |  | 3.2 | 197102.1 |  |  | 3.2 | 1376.44
| 3.3 | 11811 |  |  | 3.3 | 143131.7 |  |  | 3.3 | 13314.63 |  |  | 3.3 | 63831.2483 |  |  | 3.3 | 30771.6917
| EE Fee | 180014.4984 |  |  | EE Fee | 75351 |  |  | EE Fee | 20000 |  |  | EE Fee | 10000 |  |  | EE Fee | 14634.5016
| NIE FEE | 123355.041 |  |  | NIE FEE | 153169 |  |  | NIE FEE | 157037.3446 |  |  | NIE FEE | 177950.27 |  |  | NIE FEE | 28312.3445
| TOTAL | 1363681.1393 |  |  | TOTAL | 1349838.6332 |  |  | TOTAL | 1223561.4574 |  |  | TOTAL | 1697721.7282 |  |  | TOTAL | 944459.1519
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 | 1368237.6422 | October 2017 |  | 1.1 | 1273038.609 | October 2018 |  | 1.1 | 522339.204 | October 2019 |  | 1.1 | 508930.5642 | October 2020 |  | 1.1 | 742362.59 | October 2021
| 1.2. | 44800 | June 2017 |  | 1.2. | 274800 | October 2018 |  | 1.2. | 468453.27 | October 2019 |  | 1.2. | 65438 | October 2020 |  | 1.2. | 165438 | October 2021
| 2.1 | 7862 | June 2017 |  | 2.1 | 89456.7382 | October 2018 |  | 2.1 | 237403.4389 | October 2019 |  | 2.1 | 185546.1889 | October 2020 |  | 2.1 | 69770.97 | October 2021
| 2.2 | 433175.4776 | June 2017 |  | 2.2 | 957270.4799 | October 2018 |  | 2.2 | 900000 | October 2019 |  | 2.2 | 699443.0492 | October 2020 |  | 2.2 | 741779 | October 2021
| 2.3 | 117765.503 | June 2017 |  | 2.3 | 254205.0129 | October 2018 |  | 2.3 | 469450.3552 | October 2019 |  | 2.3 | 387929.4352 | October 2020 |  | 2.3 | 131418.6 | October 2021
| 3.1 | 91005 | June 2017 |  | 3.1 | 206943.53 | October 2018 |  | 3.1 | 292474.1 | October 2019 |  | 3.1 | 202469.52 | October 2020 |  | 3.1 | 148189 | October 2021
| 3.2 | 488290.7987 | October 2017 |  | 3.2 | 562192.5187 | October 2018 |  | 3.2 | 425358.54 | October 2019 |  | 3.2 | 228256.44 | October 2020 |  | 3.2 | 398870 | October 2021
| 3.3 | 208604.426 | October 2017 |  | 3.3 | 280461.726 | October 2018 |  | 3.3 | 333942.67 | October 2019 |  | 3.3 | 270111.4217 | October 2020 |  | 3.3 | 311001.73 | October 2021
| EE Fee | 144631 | October 2017 |  | EE Fee | 282952.5016 | October 2018 |  | EE Fee | 127583.5016 | October 2019 |  | EE Fee | 397583.5016 | October 2020 |  | EE Fee | 567580 | October 2021
| NIE FEE | 146682 | October 2017 |  | NIE FEE | 193521.959 | October 2018 |  | NIE FEE | 193166.6145 | October 2019 |  | NIE FEE | 15216.3445 | October 2020 |  | NIE FEE | 113586.02 | October 2021
| TOTAL | 3051053.8475 |  |  | TOTAL | 4374843.0754 |  |  | TOTAL | 3970171.6942 |  |  | TOTAL | 2960924.4652 |  |  | TOTAL | 3389995.91
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | 3317341 |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | 5530095.2059 |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | 5530095.2059
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 3317341 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 3317341 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 3317341
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | It is expected a total of $5.500.000 of co-financing by the Terminal Evaluation. The co-financing of the project is in-kind and part in cash.. |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | It is expected a total of $5.500.000 of co-financing by the Terminal Evaluation. The co-financing of the project is in-kind and part in cash.. |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | It is expected a total of $5.500.000 of co-financing by the Terminal Evaluation. The co-financing of the project is in-kind and part in cash..

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Extreme weather events or geophysical events diminish programme benefits or cause major disturbances resulting in delays due to needed emergency and recovery processes. | Low | No other extreme weather events happened during the 5 year, the affectations received from Hurrican Otto and the Tropical Storm Nate created a delay in the implementation of actions thou the recovering process was implemented days after and took several months.
Programme beneficiaries resistant to change or weak cooperation at the proposed sites | Low | The development of the project considers the involved of the consultation of different stakeholders such as organizations, public and private institutions, that are implementing projects related to climate change. The processes facilitate an active participation of the beneficiaries in order to reinforce the beneficiaries’ ownership of the project, supporting proactive and community-led initiatives.
Project beneficiaries are unable to properly manage the technologies or measures being promoted, and/or the technologies or measures do not improve operational efficiency | Low | Knowledge transfer and awareness building through capacity building activities are contemplated throughout the programme. Promotes a capacity development approach which is based on participatory assessments. These assessments will contribute to building the beneficiaries’ ownership and enable the analysis of autonomous adaptation approaches.
Stakeholders are not able to perceive reductions in vulnerability over the time-scale determined by programme duration. | Low | Maintain proactive outreach communications strategy throughout the programme. Also, the programme is strengthening local capacity to monitor project indicators through the support of the Executing Entities.
Insufficient collaboration/coordination between participating partners and stakeholders | Low | Establishment of agreements with detailed roles and responsibilities, work plans and team building activities throughout the programme implementation. Up to now has been important the participation of NGO’s, public organization, academia and other organizations and has been possible to create alliances among organizations. Up to today, the projects selected include letters of commitment among the EE and partners/stakeholders. Also we had made meetings with each organization to confirm their participation. Also, the NIE has signed contribution agreements and MOU's with stakeholders and partners; with the interest of formalize their participation with the adaptation Fund Programme in Costa Rica. For example, an agreement was sighed with Fundación CRUSA for over $800.000 for the implementation of actions at the local level and an MOU with the Agriculture Ministry for the technical support of the projects. Year 3 A very important collaboration between different organizations initiated during this year, as a result of a possible drought that will affect the country during most of the next year. The participation of the Ministry of Agriculture and the sector in general, along with Fundecooperación have been working in creating conscious in the importance of adapting to climate change.
Delays in programme implementation | Low | Programme activities have been designed and paced to ensure a reasonable chance of completion over five years. The Programme Management Board will provide required oversight for management of programme inputs. Although the results are on track, a delay in the implementation has been an issue to attend by the EIN. A request for extension was approved by the adaptation fund, for 18 months, however, COVID 19 has impacted the implementation during 2020 and it is expected that this delay will continue during 2021.
Limited human resources in Government ministries to support activities. | Low | Promotion of early and consistent engagement of senior government decision makers on programme progress and monitoring. Fundecooperación, as NIE, has signed cooperation agreements with the government ministries (that are related to the components) in order to received technical assistance in the field.
Mismanagement of Resources. | Low | Each of the project Executing Entities reports each semester at the financial and technical level. Year 1 A project financial evaluation each semester is made by the NIE to each of the project. Disbursements are to be done depending on the results of the evaluation of the EE and if there are not improvements to be done by the EE. Both the internal and external audits review and verify the sound management of resources of the project by Fundecooperación.
Fluctuations in exchange rate | Low | Financial Coordinator monitor exchange rate (USD to Colones) in order to communicate any implication to the PC. It is important to mention the exchange rate has during the last months have been beneficial to the project.
Delays in disbursements affects project progress | Low | In order to avoid delays has been important to anticipate as much as possible and to promote constant coordination among National Implementing Entity, Executing Entities and the Adaptation Fund. However, delays can happen and some of the delays respond to the importance of responding 100% to the requirements at the financial and administrative level.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Bank scams accounts of the projects | Medium | No changes this period. It was mentioned in a previous report: Awareness building to EE on the risks of banking scams and strengthening financial procedures at the EE. Explanatory comments of why this was identified as risk: Two Executing Entities suffered of bank scams. Specifically, ACEPESA and CAC-JICARAL, both entities reported us what happened and did the procedures required by the Investigation Agency of Costa Rica to recover the money. Both entities assumed due responsibility and replenished the money that was stolen with their own funds in order to continue with the planned activities of the project, while the money is recovered by the Investigation Agency. Also, this situation/risk was informed to all the other Executing Entities, in order to avoid more scams. The Executing Entities, once they receive the disbursement from the NIE, the organization must invest the money in order to avoid be easily scam by having the money in the current account. For example, funds committed in the short term must be invested in liquid money market or similar, looking for the alternative that offers the best profitability conditions with low risk. These liquidity options must ensure adequate compliance with the project's operational commitments. All interest income in case generated, will be used for the project as instructed by AFB.
Impact of COVID-19 | high | COVID 19 has impacted the implementation during 2020 and it is expected that this delay will continue during 2021. Adaptative management measures applied: *Some initiatives that were suppose to en during 2020 were extended in order to complete the activities *Implementation of virtual activities. *Field visits were suspended until the goverments allowed it, however EE send videos and photos to confirm implementation.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | *For the agricultural initiatives related to fertilization or waste management practices a risk of water contamination exists. *There is a risk that the properties (land) where the initiatives will be developed may present legal issues. *For the initiatives related to construction a risk of noncompliance with the necessary permits requested by the municipality, CFIA, SETENA and others (according to the dimensions of the construction) exists. | Request executing organizations respective permits or legal justification of its omission for all proposed infrastructure. Request executing organizations cadastral plans, land use permits and other legal documents that demonstrate the legality of the properties and implemented activities. Request the respective applicable permits or the legal justification of its waiver for all proposed infrastructure. | *Executing entities completed the permits and legal justification of its omission for all proposed infrastructure. | All Executing Entities presented the legal requirements to implement the projects | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
2 - Access and equity |  |  | *All initiatives are oriented at areas vulnerable to the climate change, including beneficiaries with vulnerable socioeconomic conditions; however there exists a risk that some of the initiatives, as for instance capacity building, would not be oriented towards all existing vulnerable groups. Similarly, all groups are not necessarily willing to receive capacity building. *There exists a risk to maximize existing inequities. For example there exist socioeconomic vulnerable groups that due to their location are more vulnerable to climate change and have not been identified as beneficiaries within the initiative. Similarly, identified beneficiaries are not necessarily the most vulnerable ones. | *Request that the activities that will be executed to build capacity must be published in local media. In the process, priority must be targeted to women and most vulnerable local populations and/or groups. *Include contractual clauses to executing agencies, requiring equitable access to basic benefits and specifying that none of the initiatives is going to inhibit or interfere in the access to basic benefits. Include contractual clauses to executing agencies that no initiative is going to maximize existing inequity. Request previous evidence of the condition of vulnerability of the identified beneficiaries. Ensure continuous monitoring of the selected priority region at the country level in order to ensure that the most vulnerable beneficiaries are selected on a continuous basis. | *Contractual clauses included. *Activities posted and promoted | Projects implemented in vulnerable areas pre-evaluated and approved | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
3 – Marginalized and vulnerable Groups |  |  | *No initiatives are identified with orientation or execution that could generate a negative impact on marginalized and/or vulnerable groups. On the contrary the initiatives are oriented to generate benefits for the groups most vulnerable to climate change and socioeconomic conditions. However, there is the risk represented that during the development of the initiative, marginalized and/or vulnerable groups that could be affected during the development of the initiative are not identified yet. For example, indigenous groups that could be affected by the development of agricultural activities. | *Request executing agencies the identification of vulnerable or marginalized groups that could be directly or indirectly impacted during the development of the initiative, or even after its implementation. In the case they do exist, request mitigation plans to eliminate or solve the adverse impacts. Include clauses that the development of the initiatives will not generate adverse impacts on marginalized groups. | *Identification of vulnerable beneficiaries along with Executing Entities. | Projects implemented in vulnerable areas pre-evaluated and approved | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
4 – Human rights |  |  | *No initiatives are identified whose orientation or execution is misaligned with the established international human rights. On the contrary the objective is to promote basic human rights such as drinking water, sanitation and education. However, there does exist the possibility that for the implementation of some initiatives human rights may be disrespected, for example civil rights, quality of life, social justice, children rights, discrimination, etc. | Include contractual clauses to executing agencies so that the development of the initiatives will be in compliance with human rights and that during their development no deviation or disrespect of human rights will be tolerated. | *Contractual clauses included. | Contracts signed between EIN and EE. Follow up implemented every 6 months | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
5 – Gender equality and women’s empowerment |  |  | *The initiatives are oriented to promote a fair and equal development between men and women. Some initiatives are also oriented to promote the active involvement of women groups in order to achieve enhanced empowerment. However, during the execution of the initiatives a risk exists of not promoting gender equity. | Include contractual clauses to executing agencies that for all initiatives, a crosscutting component of gender equity has to exist and be maintained. | *Contractual clauses included. | Contracts signed between EIN and EE. Follow up implemented every 6 months | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
6 – Core labor rights |  |  | *The risk has been identified that the people working for the beneficiaries or the executing organization of the initiatives could be outside the national or international legislation (for example minimum salary, vacations, insurance, etc.) | Request executing agencies a legal declaration that shows compliance with labor rights identified by the International Organization for Work. Request confirmation from the CCSS (Social Security System) that the executing agency is in due compliance. | *Confirmation from the CCSS that the executing entity is un compliance | *Documentation sent to EIN. | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
7 – Indigenous peoples |  |  | *No initiatives are identified whose orientation or execution disrespects the rights and responsibilities of indigenous groups. However, there does exist a risk that during the development of these initiatives, the rights of indigenous groups could be disrespected in a direct or collateral way, for example because of territorial or cultural issues. | Request identification of indigenous groups that could be directly or indirectly impacted during and after the development of the initiatives and in case they exist, request concrete mitigation plans to eliminate or solve the adverse impacts. Include contractual clauses to executing agencies that the development of the initiatives will not generate adverse direct or indirect impacts on indigenous groups. | *Notes from the indigenous groups that could be directly or indirectly impacted that confirms their participation approval. | *Approval from the indigenous groups along with the proposal | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
8 – Involuntary resettlement |  |  | *No initiative has been identified with orientation or execution requiring involuntary resettlement. However there exists a risk that this may occur, for example if it is necessary to modify the design to an aqueduct for an ASADA. | Include a contractual clause for the necessity to communicate to the implementing agency and formulate a remedial plan in case the involuntary resettlement of part of the population is necessary to develop the initiative. | *Contractual clauses included. | Contracts signed between EIN and EE. Follow up implemented every 6 months | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
9 – Protection of natural habitats |  |  | *There is a risk that some agricultural activities are developed nearby protected areas or surrounding areas. | Request cadastral plans or land use permits to verify the existence or proximity to protected areas. | *Cadastral plans approval. | All beneficiaries have land use permits | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
10 – Conservation of biological diversity |  |  | *The activities are focusing on Ecosystems based Adaptation as proposed, including recovery of biodiversity and agro ecological practices at the farm level. However, a minor risk of unjustified reduction of biodiversity during the development of agricultural activities does exist. *A risk of introduction of non indigenous species and possible invaders have been identified in the reforestation processes. | Request executing agencies to identify and prevent risks of biodiversity loss and to avoid introduction of alien species. Request the technical study for the proposed reforestation processes | *Reforestation process implemented along with national authorities. | Projects that included reforestation efforts are implemented along with authorities that already know the areas and species to use. | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
11 – Climate change |  |  | *No initiative has been identified with an orientation or execution that could generate unjustified greenhouse gases. On the contrary there are initiatives, as the implementation of biodigesters, low carbon technologies and improved pasture that will lead to greenhouse gases reduction. There are transport processes for the initiatives but these are considered unavoidable. In Costa Rica there are established maximum emission parameters controlled by RTV. (National evaluation) | Request RTV for the involved vehicles for the development of the initiative. | *vehicles included in the projects have RTV | No penalties have been received regarding RTV issues. | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
12 – Pollution prevention and resource efficiency |  |  | *No initiative has been identified as a big consumer of energy, however there exists the risk that during the implementation of some initiatives, the use of energy or fuel would not be efficient. No initiatives have been identified as big consumers of natural resources and therefore would require measures for their efficient use. On the contrary, some initiatives are oriented towards the better use of available resources, however, in some initiatives there may exist the risk that the resources may not be used in an efficient way, for example in constructions or transportation. There is a risk that the generated waste in some initiatives, mainly in remote rural areas, will not be adequately disposed of. However, no initiative has been identified that generates solid waste that requires any treatment. | Request an identification of environmental aspects and impacts for each initiative and measures to control and mitigate the energy efficiency risks. Request an identification of environmental aspects and impacts for each initiative and measures to control or mitigate those environmental aspects. Request a waste management plan for those initiative that require one. | *Each project made a identification od possible energy efficiency risks and environmental aspects. *Waste management plans in case needed | *Waste management plans for some beneficiaries have been implemented. | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
13 – Public health |  |  | *The risk has been identified that some of the agricultural initiatives could generate health or odor problems, mainly those related to waste management | Request a technical study for the activities of waste management including occupational health measures. | *Waste management plans in case needed | *Waste management plans for some beneficiaries have been implemented along with the Ministry of Agriculture. | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
14 – Physical and cultural heritage |  |  | *Since some of the activities involve indigenous population, there is a risk during the development of some of the initiates that there will be alteration or damage to sites or cultural resources with natural or scenic value. | Request compliance with Law of Cultural Heritage and Patrimony regarding identification and protection of cultural and archeological, nearby the location where the initiatives. Request the identification of preventive measures if necessary in order to avoid direct or indirect damage. Include contractual clauses that if during the development of the initiative damages to cultural, archeological or sites accepted as natural or scenic are identified, they must be communicated to the implementing entity and if necessary, actions must be suspended until finding and implementing a valid solution. | *Plans of intervention are approved by the indigenous population *Notes from the indigenous groups that could be directly or indirectly impacted that confirms their participation approval. | *Indigenous approved the interventions. *Approval from the indigenous groups along with the proposal | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
15 – Lands and soil conservation |  |  | *No initiatives have been identified with orientation or execution that could degrade soil or productive land. On the contrary some of the initiatives are oriented towards the conservation and use of soil however there exists a risk that during the application of good practices technical errors might incur that generate degradation of land and soil. | Request compliance with Law of Soil Use and Conservation and monitoring with technical endorsement, to verify that there is no risk of degradation of land and soil. | *Plans of intervention are proposed and approved by national authorities. | *MAG was part of the creation of the plans of intervention. | All the safeguards were implemented during the first year of implementation and were followed up every 6 years Also a analysis of the ESP was made by each EE. | No residual impacts identified | No residual impacts identified
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | NO
Have unanticipated ESP risks been identified during the reporting period? |  | NO
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In general, Fundecooperación established a ESP Guideline for the analysis of the possible impact of the projects. This Guideline were completed along with the EE during different workshop sessions. The implementation of all the safeguards are follow up every 6 months.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | *EE made a proper analysis with different stakeholders in order to warranty all the safeguards were in place.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | In general, Fundecooperación established a ESP Guideline for the analysis of the possible impact of the projects. This Guideline were completed along with the EE during different workshop sessions. The implementation of all the safeguards are follow up every 6 months.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
CEDARENA | Yes | *No ESP risks identified | Yes | Yes | Yes
CBTC | Yes | *Conservation of biological diversity. | Yes | Yes | Yes | *Reforestation along with national authorities, experts in the topic. *An analysis was made in the area by the national authority. | *Reforestation implemented with the approval of authorities.
ALIARSE | Yes | *Core labor rights | Yes | Yes | Yes | *Warranty compliance with the law | *Contracts
COOPEPURISCAL R,L | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Organizations legally constituted | *Organizations involve comply with legal requirements.
ACEPESA | Yes | *No ESP risks identified | Yes | Yes | Yes
INTA/FITTACORI | Yes | *No ESP risks identified | Yes | Yes | Yes
CREMA | Yes | *Compliance with the law | Yes | Yes | Yes | *Legal compliance by the organizations involved | *Legal papers approved
MAG/FITTACORI | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
CLADA CATIE | Yes | *No ESP risks identified | Yes | Yes | Yes
Centro Agrícola Cantonal de Puntarenas, sede Jicaral | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
UNAFOR | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
MARVIVA | Yes | *No ESP risks identified | Yes | Yes | Yes
KETO | Yes | *Compliance with the law *Core labor rights *Conservation of biological diversity. | Yes | Yes | Yes | *Request of approvals from the authority for implementation of actions *Verify the insurance require from the touristic sector. *The actions are implemented along with the National Park in order to avoid any risk. | *Approvals requested and received. *Insurance verified.
IMN/FUNDEVI | Yes | *No ESP risks identified | Yes | Yes | Yes
FUNDACION CORCOVADO LON WILLING RAMSEY JR | Yes | *No ESP risks identified | Yes | Yes | Yes
COOCAFE R.L | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
CNPL | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
INDER/FUNDEVI | Yes | *Physical and cultural heritage *Indigenous People | Yes | Yes | Yes | *Notification letters of project approval *Plan of implementation | *Letters of approval *Plans for implementation ready
CFIA | Yes | *No ESP risks identified | Yes | Yes | Yes
SETENA/CORCOVADO | Yes | *No ESP risks identified | Yes | Yes | Yes
INS | Yes | *No ESP risks identified | Yes | Yes | Yes
FEDERACIÓN DE CAMARA DE GANADEROS DE GUANACASTE | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
CATIE | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
ICICOR | Yes | *No ESP risks identified | Yes | Yes | Yes
PRODUS | Yes | *No ESP risks identified | Yes | Yes | Yes
UNA | Yes | *No ESP risks identified | Yes | Yes | Yes
UCR-CIEDES | Yes | *Gender Equity *Conservation of biological diversity. *Soil conservation risk | Yes | Yes | Yes | *Participation of women and men as beneficiaries and as part of the team of the EE. * Soil Management Plan created, that includes best agriculture practices. | *# Participants *Soil Management Plan
FUNDECOR | Yes | *No ESP risks identified | Yes | Yes | Yes
SIREFOR- SINAC | Yes | *No ESP risks identified | Yes | Yes | Yes
MAG-PC | Yes | *Compliance with the law *Core labor rights | Yes | Yes | Yes | *Plan of implementation *Analysis of legal requirements of beneficiaries | *Plans for implementation ready *Analysis of beneficiaries
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Gender-responsive indicators | Output | Percentage of beneficiaries (men and women) | 0 | 47% | Satisfactory
Gender-responsive indicators | Output | Percentage of beneficiaries trained (technicians) by gender on technical options and methods resilient to the effects of Climate Change | 0 | 21.3% | Satisfactory
Gender-responsive indicators | Output | Percentage of beneficiaries from the refundable funds (gender-disaggregated) | 0 | 10% | Poor
Gender-responsive indicators | Output | Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses (gender-disaggregated) | 0 | 41% | Satisfactory
Gender-responsive indicators | Output | Percentage of beneficiaries trained on adaptation measures (gender-disaggregated) | 0 | 47% | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | *A Gender Policy and Plan has been approved *Along with the plan and policy, workshops were made EIN staff. *Regarding the indicator "% of beneficiaries from the refunable funds (gender disaggregated)", even though the women could be involved in the activity, usually the agricultural activities are led by men, many of the applications that we receive from women are more in the commercial sector. Also in some cases the women prefers their partner to ask for the credit instead of them; with this in mind we have launched "Más mujeres, mas natura" as a credit option direct for women.
Have the implementation arrangements at the IE been effective during the reporting period? |  | *Yes, this has made possible for the EIN staff to be more conscious and gender responsive.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | *Identification of possible risks for gender equity in the project. *Include women's in decision making processes *Include gender equity as a main aspect to consider for including possible beneficiaries.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Programme Implementation Oversight Reunions |  | Outcome 8 | Framework functioning effectively |  | During 2020 we had a relevant slow down on execution of activities, also our role had a strong focus on follow up of challenges and opportunities of continuing implementation with the EE during the pandemic and the identification of possible new EE that would be in charge of new projects to support some of the pending indicators. | MS
| Promotion and Awareness |  | Outcome 3 | Implementation Communication actions |  | Some of the results: *4 Virtual Field visits. *7 webinars implemented during the year *Appearances in national TV and newspapers promoting the Adaptation Fund in Costa Rica. *Project videos: 10 more videos, for a total of 20 videos. *2 project events: MEBA, CNPL project and ALIARSE project event. Also an evento along wih the Ministry of Agriculture and Livestock of the impact of ADAPTA2+. *Climate information available for farmers decision making: --Conferences: 4 --Videos: 30 --Webinars: 2 --Facebook lives: 4 --Interviews in radio: 9 --Virtual workshops: 1 --Social media publications: 1.663 --Facebook page: https://www.facebook.com/piactca | HS
| Monitoring and field visits |  | Outcome 8 | Monitoring visits facilitation |  | Each of the Executing Entity must report the financial and technical improvements each semester. A visit for each of the projects have been difficult this year, because of COVID sanitary limitations, most of the monitoring visits were implemented virtually, however it is expected to improve during 2021. | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Carolina Reyes Rivero
| Email: | creyes@fundecooperacion.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
2020 had an important set back on project implementation, a lot of EE had to stop implementation, change activities and/or adjust implementation timelines with each of the initiatives. In general terms, the implementation of the programme at this stage has been satisfactory; however the delay because of COVID-19 had an impact in the implementation expected for 2020, and therefore we consider 2020 as S. Eventhough there was an extension of time approved prior to COVID-19, the effect of this situation will most probably require additional time. We have seen that in order to accelerate implementation, the direct execution services (DES) have been required, 2021 has several challenges but we expect to be able to recover pace on implementation.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1 |  | Outcome 3 | Increasing the adaptation capacity to climate change in the agricultural sector Some expected results: -At least 16 agricultural and livestock units has identified technological options -At least 16 plans for adaptation at farm level |  | By the 5 year of implementation a total of 21 initiatives has been supported. It is important to mention that some very important initiatives had finished it's implementation in a very successfully way, agriculture and livestock insurance and the Agriculture Zonification Maps are now a reality in the country. Another important result is that now up to 650 farms units are implementing adaptation measures. Additionally, it is important to mention that Agricultura y Ganadería PRO-CLIMA (the two credit schemes created by the programme) has placed more than $700.000 for the implementation of adaptation measures at local level, allowing a relevant multiplying effect within farmers. Additionally, the project made strong efforts in improving climate finance mechanisms and tools. | HS
| Component 2 |  | Outcome 3 | Improving water resources management in order to increase resilience in coastal communities that are more vulnerable to climate change. Some expected results: -10 Operadores have implemented a Water Safety Plan or Watershed Management Plans -At least 3 ASADAS have undertaken a vulnerability assessment -10 hectares of aquifer recharge areas reforested |  | The main results by the end of 2020: -84 have implemented adaptation actions to improve the access to water of their communities -100 ASADAS strenghtened. -127 hectares of aquifer recharge areas reforested -Planted more than 1300 coral colonies -Restored 25 acres of mangroves forest -A water resource protection fee already in place. This fee could be requested for the implementation of projects at local level. | HS
| Component 3 |  | Outcome 7 | 1. Implementation of different projects at the local level that respond to the adaptation needs of each community. 2. Improving the capacity of communities, producers, institutions, and stakeholders regarding adaptation to Climate Change. |  | More than 80 communities supported More than 100 organizations had improved theirs capacity regarding to climate change. Adapta2+has created several knowledge materials such as: *Manual of Bribri and Cabécar Ancestral Practices *A training guide on adaptation to climate change. *Nogal: A video-game on climate change for kids. *Study Cases *Meba practices manuals. *webinars *videos *Virtual Field visits. *Climate infomation webinars for small farmers- | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Marianella Feoli as PCU coordinator
| Email: | gerencia@fundecooperacion.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The rating of S is because, some work in the third component is still pending. Until today, the program has achieved very good results, confirming the good job we have been doing. Fundecooperacion started some interesting projects with new executing entities that will allow us to achieve even more interesting results. However, it is important to mention that the implementation has been delayed because of COVID-19 sanitary limitations, we expect to recover the pace during 2021 although with a little of uncertainty
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | 1 |  | Outcome 6 | 90 Discrete agricultural adaptation practices are demonstrated on-farm. Adaptation practices include: enhanced water management techniques, enhanced soil management practices, planting techniques, post-harvest processing and diversified livestock practices. |  | 650 farms implementing Adaptation practices | HS
| 2 |  | Outcome 4 | Some expected results: -10 Operadores have implemented a Water Safety Plan or Watershed Management Plans -At least 3 ASADAS have undertaken a vulnerability assessment -10 hectares of aquifer recharge areas reforested |  | 100 ASADAS implementing adaptation measures. One water resource protection fee implemented. | HS
| 3 |  | Outcome 8 | 1. Implementation of different projects at the local level that respond to the adaptation needs of each community. 2. Improving the capacity of communities, producers, institutions, and stakeholders regarding adaptation to Climate Change. |  | Many workshops and activities were cancel or posponed due COVID 19 other were shifted to virtually. 6 properly installed and functioning new meteorological stations and information platforms Materials published and available for beneficiaries and communities. Early Warning System in process. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Jorge Segura.
| Email: | jsegura@mag.go.cr
| Name: | Grettel Calderón
| Email: | grettel.calderon@aliarse.org
| Name: | Ana Rita Chacón
| Email: | archacon@imn.ac.cr
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Critical risk: delay in implementation due COVID-19 an restrictions until today. Eventhou it is expected that 2021 is better than 2020, because Costa Rica has passed the second wave of COVID-19 and vaccins already started arriving however there is a a little of uncertainty on implementation. The 18 months extention approved prior to COVID-19 is already envisaged that will no be enough for project implementation.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator: indicators towards Objectives
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1.1.1. | ZAE maps for selected crops of the Central Region | Last ZAE maps of the country were made in 1980 | 13 | 13
1.1.1. | technological showcases implemented and applying technology options for the adaptation to climate change in Naranjo, Puriscal, Dota and Pacayas. | 0 technological showcases implemented | 8 | 4
1.1.1. | Online platform with updated information on adaptation technologies and zoning scenarios | 0 | 1 | 1
1.1.1. | beneficiaries (50% women and 50% men) | 0 | 1296 | 1000
1.1.2 | Agricultural and livestock units has identified technological options | 0 units has identified technological options | 543 | 90
1.1.2 | Plans for adaptation at farm level | 0 Plans for adaptation at farm level | 541 | 90
1.1.3 | beneficiaries (50% women and 50% men) | 0 | 3879 | 1000
1.1.3 | Discrete agricultural adaptation practices are demonstrated on-farm. Adaptation practices include: enhanced water management techniques, enhanced soil management practices, planting techniques, post-harvest processing and diversified livestock practices. | 0 | 533 | 90
1.1.3 | Number of farms implementing actions | 0 | 551 | 90
1.1.3 | ha on indigenous territories implementing technical options and methods that enhance their resilience to the effects of climate change | 0 | 704 | 1000
1.2.1 | -At least 50 initiatives have access to credit schemes for the implementation of adaptation activities | 0 | 34 | 10
| -At least 5 microfinancing institutions include credit products available to local small producers for adaptation to climate change | 0 | 2 | 5
2.1.1 | At least 50 ASADAS and 2 municipalities have implemented adaptation actions to improve the access to water of their communities | 0 | 84 | 52
2.1.1 | At least 12 ASADAS have undertaken a vulnerability assessment | 0 | 16 | 12
2.1.1 | At least 3 committees formed by various social actors | 0 | 4 | 3
2.1.1 | At least 25,000 water users beneficiated | 0 | 12603 | 25000
2.1.2 | At least 5 measures implemented for integrated watershed protection | 0 | 94 | 5
2.1.2 | 5000 hectares of the watershed improved directly or indirectly by the implementation of management practices | 0 | 5000 | 5000
2.2.1 | At least 50 hectares of aquifer recharge areas reforested- | 0 | 108 | 50
2.2.1 | Protection of aquifers | 0 | 12 | 1
2.2.2 | At least 25,000 inhabitants in 50 communities have their water supply and associated infrastructure, improved to manage climate-induced impacts on water supply | 0 | 12603 | 25000
2.2.2 | 50 communities have their water supply and associated infrastructure improved | 0 | 39 | 50
2.2.3 | -At least 10 initiatives | 0 | 14 | 10
| -At least 2 credit products available for implementation of adaptation measures to climate change (of local water management associations (ASADAS) and national water systems) | 0 | 2 | 2
2.3.1 | At least 500 citizens in coastal zones are prepared and trained to deal with the impacts of climate change | 0 | 1446 | 500
2.3.1 | At least 10 coastal communities have implemented at least one adaptation measure | 0 | 34 | 10
2.3.1 | 8 km of coastline and beaches in protected areas, redesigned and reforested | 0 | 24 | 8
2.3.1 | At least 1 Community Coastal Reforestation Program | 0 | 2 | 1
2.3.3 | 25 ha of mangrove reforested in Gandoca (including areas within the National Wildfire Refuge Gandoca Manzanillo) | 0 | 25 | 25
2.3.3 | At least one coastal community implement a mangrove nursery effective to combat coastal erosion | 0 | 2 | 1
3.1.1 | At least one Early Warning System and Emergency Protocol implemented | 0 | 1 | 1
3.1.1 | One management system and incident management for Forest Fires | 0 | 0 | 1
3.1.2 | At least 5 communities trained, involving traditional leaders, women and youth groups | 0 | 9 | 5
3.2 | At least 3,000 beneficiaries trained | 0 | 3000 | 3000
3.2 | At least than 50 stakeholders participating in awareness raising events | 0 | 219 | 50
3.2 | At least 1000 policymakers and technical officers exhibit improved levels of understanding of climate risk assessment and planning processes for climate change adaptation. | 0 | 498 | 1000
3.2 | -At least 10 knowledge materials (experience notes, case studies, photo stories, videos, etc.) are generated per year starting from year 2 of the programme | 0 | 46 | 10
3.2 | -A completed and operationally tested “Handbook on Coastal Adaptation”, "Technical Guide for Adaptation to Climate Change for the artisanal fishing sector" and "Handbook on Water Supply Systems Adaptation" is developed by the end of the project | 0 | 8 | 1
3.2 | Internalization of environmental costs of the water suppliers to facilitate their adaptation to climate change in vulnerable areas | 0 | 1 | 1
3.2 | -1 online training course | 0 | 1 | 1
3.3 | 70% of programme beneficiaries make use of improved climate risk information | 0 | 2000 | 2100
3.3 | At least 10 properly installed and functioning new meteorological stations and information platforms | 0 | 11 | 10
Note on F18: Estacion13: Total
Note on F30: Estacion13: Total
Note on D31: Estacion13: ASADAS can only access to credit from only one Bank in the country. We propose to create 2 credit products for financing adaptation measures in general.
Note on F31: Estacion13: Already created 2 credit products: Ganadería Pro-Clima y Agricultura Pro-Clima
Note on F40: Estacion13: ICICOR- SARAPIQUI RESILIENTE ACEPESA
Note on F45: Estacion13: TPRH PIEVC KETO ALIARSE 1 TU-MODELO modulos 1-3
Note on D48: Estacion13: We would like to consider to change this indicator to as follow: More than 4000 have access and make use of improved climate risk information. The main reason is because we are making efforts to have a national impact regarding this indicator... the result is even broader

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | *2020 had an important set back on project implementation, a lot of EE had to stop implementation, change activities and/or adjust implementation timelines. *In general terms, the implementation of the programme at this stage has been satisfactory; however the delay because of COVID-19 had an impact in the implementation expected for 2020. *The support of allies among the projects are needed in order to increase the impact. This is even more important, in a virtual modality.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | *The first year, many of the Executing Entities were not ready for complying with the different standards needed for the implementation of the project. *The impact of natural disasters had delayed some of the actions. *During 2020 we had a relevant slow down on execution of activities, because of COVID-19. Eventhou it is expected that 2021 is better than 2020, because Costa Rica has passed the second wave of COVID-19 and vaccins already started arriving however there is a a little of uncertainty on implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | *Our role had a strong focus on follow up of challenges and opportunities of continuing implementation with the EE during the pandemic and the identification of possible new EE that would be in charge of new projects to support some of the pending indicators. *We have seen that in order to accelerate implementation, the direct execution services (DES) have been required, 2021 has several challenges but we expect to be able to recover pace on implementation.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No changes
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | No changes
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Fundecooperacion para el Desarrollo Sostenible
Type of implementing entity | NIE
Country | Costa Rica
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 43807 | 3292 | 40515 | Total | 60305 | 3892 | 56413 | Total | 160538 | 9025 | 151513 | Total
|  | % of female beneficiaries | 0 | 0% | 0% | % of female beneficiaries | 85.99% | 36% | 49.99% | % of female beneficiaries | 76.57% | 29.57% | 47% | % of female beneficiaries | 68.13% | 30.23% | 37.9% | % of female beneficiaries
|  | % of Youth beneficiaries | 0 | 0% | 0.003269% | % of Youth beneficiaries | 0.23 | 23% | 0% | % of Youth beneficiaries | 12.65% | 12.64% | 0.006% | % of Youth beneficiaries | 50.7% | 27.28% | 23.42% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Water management | 1: No capacity | Total | 227 | Drought | 2: Partially effective | Total | 227 | Coastal flooding | 2: Partially effective | Total | 227 | Coastal flooding | 2: Partially effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 42.73% |  |  | % of female targeted | 42.73% |  |  | % of female targeted | 42.73% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Water management | Local | 1: No plans conducted or updated | 1 | Water management | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Water management | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Water management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage |  | 1 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 2: Low capacity | Total | 88 | Agriculture | 3: Medium capacity | Total | 211 | Agriculture | 3: Medium capacity | Total | 252 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 13% |  |  | % of female targeted | 21.33% |  |  | % of female targeted | 23.41% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 88 | 13% | Public |  | 211 | 21.3% | Public |  | 252 | 23.41% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 100% |  | Agriculture |  | 100% |  | Agriculture |  | 100% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 204 | 20% | 3: Partially aware |  | 377 | 41% | 3: Partially aware |  | 377 | 41% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 1: Non responsive (Lacks all elements ) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 1 | National |  | Water management | 1 | National |  | Water management | 1 | National |  | Water management
[10 empty] | 1 | National |  | Agriculture | 1 | National |  | Agriculture
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 23993 | ha protected | 4: Effective | Mangroves | 25 | ha rehabilitated | 4: Effective | Mangroves | 25 | ha rehabilitated | 2: Partially effective | Mangroves | 62 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 100 | km protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 12 | km protected | 3: Moderately effective | Forests | 55 | ha protected | 4: Effective | Forests | 55 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 108 | ha protected | 3: Moderately effective | Catchment area/Watershed/Aquifer | 127 | ha protected | 3: Moderately effective | Catchment area/Watershed/Aquifer | 276 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 343 | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land | 379 | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land | 565 | ha rehabilitated | 3: Moderately effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Public policy | 1 | Water management | National | Public policy | 1 | Water management | National | Public policy | 1 | Water management | National | Public policy
|  | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Urban development | National | Urban policy | 1 | Urban development | National | Public policy | 1 | Urban development | National | Public policy | 1 | Urban development | National | Public policy
|  | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Other | National | Other policy | 1 | Agriculture | National | Environmental policy | 1 | Agriculture | National | Environmental policy | 1 | Agriculture | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital |  |  |  | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital |  |  |  | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital |  |  |  | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital |  |  |  | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital |  |  |  | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital |  |  |  | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies |  |  |  | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance |  |  |  | Performance at mid-term |  |  |  | Target performance |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness