## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | January 2019 - December 2019
| Project Title: | Reduction of vulnerability to coastal flooding through ecosystem-based adaptation in the south of Artemisa and Mayabeque provinces.
| Project Summary: | The proposed project seeks to reduce the vulnerability of communities in coastal areas of Artemisa and Mayabeque provinces in southern Cuba from climate change (CC) related phenomena including coastal erosion, flooding and saltwater intrusion. This will be achieved through Ecosystem Based Adaptation (EBA), taking advantage of the proven potential of mangrove forests and associated coastal wetlands to limit the effects of wave erosion and coastal flooding, which are among the most damaging results of climate-change related SLR and storms. The project’s objective will be achieved through investments in three complementary components. Component 1 will focus on concrete investments in ecosystem recovery, leading to improved coastline resilience to the impacts of wave action, and improvements to coastal morphology which will reduce seawater incursion. Component 2 will focus on integrated and participatory management of coastal ecosystems, through mainstreaming EBA into integrated coastal zone planning and productive sector activities, promoting buy-in, participation and governance in local communities and developing knowledge management systems at community level. Component 3 will focus on establishing a favourable enabling environment at regional level for the effectiveness and sustainability of adaptation investments, through the provision of consolidated information on costs and benefits of EBA to decision makers and planners and the strengthening of institutions supporting EBA actions, within the framework of updated and actively implemented action plans.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 84007 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cuba | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Coastal areas of Artemisa and Mayabeque provinces in southern Cuba | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-05-19
IE-AFB Agreement Signature Date: |  | 2014-06-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | September 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | January 2018
| Terminal Evaluation Date: | July 2020
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - Inception workshow report, Quarterly Reports from UNPD. - 1st issue of Living Mangrove Forest bulletin. 2nd issue of Living Mangrove Forest bulletin. - http://www.cu.undp.org/content/cuba/es/home/presscenter/articles/2015/04/14/crece-el-proyecto-manglar-vivo.html. - http://www.radiohc.cu/noticias/ciencias/138840-avanza-en-cuba-proyecto-internacional-manglar-vivo. - http://www.radiomayabeque.icrt.cu/es/167-valor-agregado-en-espanol/5768-proyecto-manglar-vivo. - http://www.guerrillero.cu/pinar-del-rio/2802-inauguran-expo-manglar-vivo.html | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.ama.cu/manglar/manglar.html | Democratic Republic of the Congo
|  | https://www.facebook.com/manglarvivo/?ref=ts&fref=ts | Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Luis David Almeida Famada | Dominican Republic
| Email: | almeidafamada@ama.cu; almeidafamada@gmail.com | Ecuador
| Date: | March 20th, 2020 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Gricel Acosta Acosta | Fiji
| Email: | gricel.acosta@undp.org | Finland
| Date: | March 20th, 2020 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 December 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2019 | 5199932
Add any comments on AF Grant Funds. (word limit=200) | At the end of 2019, the project shows a 93% of financial execution. For 2020, the plan is $392,068. An amount of $ 199,200 corresponds to pending contracts signed in 2019, for the adquisition of imported goods. The remaining funds, $ 192,868, are programmed for the adquisition of goods and services within the country. The project must conclude its financial execution at the end of September 2020, according to the approved extension.
INVESTMENT INCOME | Not applicable
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (1 january 2019 - 31 December 2019) | ITEM / ACTIVITY / ACTION/OUTCOME | OUTPUT | AMOUNT
| 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 385258
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 197773
|  | 1.3. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 64665
|  | 1.4. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 295821
| Subtotal Outome 1 |  | 943517
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 70603
|  | 2.2. Buy-in, participation and governance in local communities | 35250
|  | 2.3. Knowledge management systems at community level | 108255
| Subtotal Outome 2 |  | 214108
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 12756
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 20231
| Subtotal Outome 3 |  | 32987
| Project Management |  | 36586
| TOTAL EXPENDITURE |  | 1227198
| REMAINING BALANCE OF CONTRACTS |  | 199200
PLANNED EXPENDITURE SCHEDULE | ITEM / ACTIVITY / ACTION/ OUTCOME | OUTPUT | PROJECTED COST | Est. Completion Date
List outputs planned and corresponding projected cost for the upcoming reporting period (Jan 2020 - Sept 2020) | 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 0
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 86900 | 2020-09-30
|  | 1.3. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 30000 | 2020-09-30
|  | 1.4. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 186600 | 2020-09-30
| Subtotal Outome 1 |  | 303500
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 0
|  | 2.2. Buy-in, participation and governance in local communities | 0
|  | 2.3. Knowledge management systems at community level | 0
| Subtotal Outome 2 |  | 0
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 0
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 0
| Subtotal Outome 3 |  | 0
| Project Management |  | 88568 | 2020-09-30
| TOTAL |  | 392068 | 2020-09-30
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | At the end of 2018, the national co-financing committed in ProDoc, 5,052,000 CUP (Cuban Pesos), had already been over-fulfilled: 17,927,211 CUP - 350 %.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | A specific procedure was established by the Project Management Unit for the monitoring of the national co-financing in CUP. The National Forestry Development Fund (FONADEF), through the State Forestry Service (SEF), is the main source of co-financing. A digital record is regularly updated with all the certifications that SEF issues for the rehabilitation actions in the Project areas. By the end of 2019, this acumulative record shows that FONADEF has issued certifications in an amount of 17,927,211 CUP: Artemisa Province 2,900,700 CUP and Mayabeque Province 2,500,600 CUP in 2019. The rest of the national co-financing comes mainly from the salaries to technical and administrative personnel involved in the Project implementation, paid by Cuban government

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
1 | Extreme climatic events (storms, droughts) and fires, affecting plant survival rates. | Environmental | Impact: Low (2) Probability: High (4) | Medium | In this period the national territory was affected by the Hurricane Irma, it caused great damage to the economy (especially the tourism sector) and natural heritage. This event hit the northern coast of Mayabeque, but did not directly affect the coastal forests in the project's intervention area. As part of the actions developed to deal with extreme weather events, the provincial and municipal disaster reduction plans were updated base on results of new studies by the Environment Agency's Risk Vulnerability and Risk group, with new IPCC reports and real data from recent events. An analysis of the behavior of forest fires was made, highlighting a reduction of fires in the project areas. This is the result of the effectiveness of the surveillance and early warning system, and highlights the relevance of project's interventions in regards training communities to fight fires.
2 | Climate change related changes in tree phenology affecting seed collection and nursery activities. | Environmental | Impact: Low (1) Probability: Medium (3) | Low | Although no phenological affectations were detected during the reporting period, as part of the adaptation measures planned to reduce the risks of climate change in the coastal wetland areas, the following actions/ products were undertaken: - Publication and implementation of a manual for the management of native species in nurseries in the face of a changing climate, created by the institute of ecology and systematic specialist. - Monitoring restoration / rehabilitation actions to periodically evaluate the success of establishing red mangrove forests. In this reporting period, 18 monitoring trips were made by the research institutes and the implementation office.
3 | Variations in commitment to EBA among policy makers. | Institutional | Impact: Low (2) Probability: Medium (3) | Low | The development plan and climate change action plans of the provinces Artemisa and Mayabeque have incorporated ecosystem-based adaptation actions. In 2017, the council of ministers approved the State Plan for Climate Change, known as "Tarea Vida". This plan includes among the prioritized areas the southern coast of the provinces Artemisa and Mayabeque. The successful experience using EbA approaches from the project is being replicated in all country. Being a state mandate, it forces decision makers in the territories to account for what they do every six months to adapt to climate change. In this sense, the Ministry of Agriculture has chosen to use the project methodologies to apply them in all the forestry enterprise in the country.
4 | Slow equipment procurement processes in local Governments. | Institutional | Impact: High (4) Probability: High (4) | Medium | There is evidence of progress in budget execution, with respect to the previous period. The procurement processes have improved in efficiency and speed. The following measures have been applied: - A strategic planning exercise was carried out in 2017 (Mid Term Review year) to rework the delivery of the project until completion in September 2020. - The process of requesting and bidding on media to be imported is done early, to reduce the time of acquisition and delivery at the final destination.
5 | Limited availability of inputs and equipment on national market. | Institutional | Impact: Medium (3) Probability: Medium (3) | Medium | There are 2 international procurements of equipment still pending still which may be at risk of being delayed due to the current global health situation.
6 | Short term economic and livelihood considerations outweigh medium term benefits of EBA actions in priorities of community members. | Institutional | Impact: Low (2) Probability: Low (1) | Low | The benefits of EbA actions are not manifested in the short term. Therefore, the impacts of the implemented actions are monitored and evaluated, with the purpose of quickly disseminating the results. In addition, these are complemented by alternative economic options for local communities. For example: the use of IAS for the manufacture of charcoal has increased the income of the forest workers of the EAF Costa Sur and Mayabeque. Taking into account the potential of each province, two new projects have been proposed to diversify the sources of income of local communities: production of honey in the mangrove and the use of mineral-medicinal sludge. In addition, in a survey process carried out in the communities, a perception of the decrease in the intensity of the waves was evident as a result of the actions of the project.
7 | Short term political considerations outweigh medium term benefits of EBA actions in priorities of members of local institutions | Institutional | Impact: Low (1) Probability: Low (1) | Low | In order to ensure the sustainability of the EBA measures, the following actions were undertaken: - The plan to face climate change (Tarea Vida) ensures the continuity of the Project, preventing all ministries from taking actions that attempt against adaptation to climate change. - The project is evaluating possible sources of national financing for the creation of economic incentives and their inclusion in local development strategies. Also, livelihood alternatives are identified so that the new productive forms promoted by the country do not affect the goods and services provided by the coastal forests. - Working groups for economic evaluation are trained and propose economic development alternatives for each province - The project continues to support the preparation of decision-makers at the provincial and municipal levels, so that they increase their empowerment of the benefits of actions with an EbA approach in coastal wetlands.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
| Delays in the importing process of materials and goods has delayed the financial execution of the project. | Operational | Impact: Medium (3) Probability: High (4) | High | The following measures have been implemented: 1. The project team and the Environment Agency support and maintain a permanent exchange with the new importing company (EMIDICT). 2. UNDP CO in coordination with CITMA (Economics and Planning Department, International Relations Office, Environment Agency, Project Unit), MINCEX and the importing company has carried out four financial analysis meetings of this project. These meetings were focused on the analysis and monitoring of all national import and purchasing processes. In those meetings measures have been adopted to ensure the implementation of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project team has considered that all the measures applied have avoided a negative impact on the project implementation. Only low financial execution is identified as a critical risk; however, the measures applied have contributed to solve this issue in the time left of the project.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Key Milestones I. Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. |  | Increased the: a. Restored mangrove ecosystem area (Artemisa: Majana - Surgidero de Batabano). b. Red mangrove area along the coast (Mayabeque Batabano - Punta Mora). |  | Vulnerability to coastal flooding was reduced, based on preliminary surveys carried out with 690 residents of 11 coastal settlements (6895 hab) intervened with the project. The statistical analyses of the results are currently being carried out. | HS
The functional landscape maps were updated and prepared, referring to the project area. It was used to confirm that the restoration actions corresponded to the functional potential of the landscapes. This is valuable knowledge for Government decision-makers.
The health of mangroves increased, strengthening the quality of ecosystem services such as the capacity for coastal protection, protection of marine species, reduction of the influence of the salt wedge. This result is verified with the update of the mangrove health maps, together with field monitoring carried out in the past 5 years.
Restoration actions completed, with success in establishing and increasing the resilience of the first strip of Mayabeque mangrove forests in the years 1 (85 ha), 2 (418.5 ha), 3 (499 ha), 4 ( 311.7 ha) and 5 (213.7 ha), for a total of 1527.9 ha. The success of the intervention methods was verified. These include direct planting with and without wood staking planting niches, maintenance and creation of ditches and canals and management of natural regeneration. Red mangrove plants reach heights greater than 2 meters and a positive rooting system. This is a new method which will be now applied by the Agro Forestal Companies and the Government of Mayabeque.
The Gulf of Batabanó protected area carried out conservation work and Invasive alien species (IAS) elimination and forest resilience monitoring, with a positive response in its maintenance and coastal protection capacity.
Restoration actions completed, with success in establishing and increasing the resilience of the first strip of mangrove forests of Artemisa in the years 1 (139 ha), 2 (413.5 ha), 3 (577.7 ha), 4 (652.8 ha) and 5 (91.3 ha), for a total of 1874.3 ha. The success of the intervention methods was verified, based on monitoring in plots. These methods include direct planting with and without wood staking, planting niches, maintenance and creation of ditches and canals and management of natural regeneration. Red mangrove plants reach heights greater than 1.50 meters and a positive rooting system. This result constitutes a tool for new methods of work in the mangrove, for the Agro Forestry Companies and the Government of Artemisa.
The intervention method of planting propagules in stakes with protection by stabbing was successful in establishing the red mangrove plants. The success of its establishment in Guanimar, Cajio and Mayabeque beach is evident. In the established areas, the recruitment of new red mangrove individuals and forest resilience evidence is evident. The monitoring showed that the plants are vigorous, reduce the swell, measure more than 3 meters high and with more than 90% success of survival.
Red mangrove planted through the nesting method at sea were established in coastal areas of Guanimar, Artemisa. The nest method constitutes an innovative successful intervention for the establishment of red mangroves in coastal areas. The success of this recent method was verified by monitoring, the red mangrove plants are more than 1 meter high and with 90% success of survival.
Replenishment with enrichment propagules on existing islands was successful, in Cajio. Mangrove coverage was increased in the Artemisa area, with the aim of increasing tree density and achieving greater unification of the islands in less time.
To increase knowledge generation, six Geography theses were studied and incorporated, which contributed to the land cover modeling studies (for 2050) in southern Artemisa and Mayabeque, determining the structures of the landscapes in the areas of intervention, determination of priority areas for ecological restoration and precipitation behavior in intervention municipalities. This information has a high impact to increase the Geographic Information System, an essential tool in the management of the coastal zone by provincial and municipal governments.
Updated list of native species and their associated vegetation formation, this result is of great impact for restoration techniques to increase the resilience of bordering forests and their forest management. New records of the flora (for example, Maxonia apiifolia, Albizia cubensis, Haematoxylum campechanum) for the wetland were identified. Some native species were used for the nursering and enrichment of border forests.
Forestry companies implemented the following activities in the protected area, for the hydrological improvement of the wetland: maintenance, group and individual enrichment, cleaning and conditioning of sites, cleaning and maintenance of ditches and fire trails. Achieved for the first time for companies involved in the project and improvement of the resilience and recovery of mangroves and border forests, experience incorporated in other areas of mangrove recovery in the Cuban archipelago.
| II. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. |  | Increased the: c. Enriched border forest area. d. Control and eradication of IAS. |  | In the five years of the project, forest restoration actions were carried out that include the elimination of exotic species and enrichment with native species in the years 1 (100 ha), 2 (1097.5 ha), 3 (1529.5 ha), 4 (831 ha) and 5 (810 ha), for a total of 4368 hectares of swamp forest. Among the activities and tasks are enrichment with native species, in group and individual, clean and conditioning of sites, clean and maintenance of ditches and trails against fire. In addition, two demonstration sites were implemented, one in Cajío and one in El Embarcadero, with typical species of swamp forests. | HS
The swamp forests of the Artemisa and Mayabeque provinces were enriched with more than 50,000 individuals from 26 native tree species, some of them almost missing from the swamp blocks, such as: palo campeche, majagua, ocuje, arabo, white oak, spiny júcaro. The use of technified nurseries was of great impact on forest management and increased quality of plants planted in bordering vessels. Planting areas with more than 90% of suvival are certified.
Invasive alien species (IAS) were eliminated in 10 ha of swamp forests, increasing their resilience. Estas especies degradan el humedal y limitan los servicios ecosistemicos como la . This activity had important impacts, both in forest improvement, and in the use of forest products, such as charcoal, wood, pallet and foliage production. It was a major economic impact on both forest companies and the protected area.
Implementation of new ecotechnology with impact on the quality of forest nursery plants for the restoration of border forests. The result was the publication of the book "Ecotechnologies for ecological restoration: seed treatments and mycorrhizae".
Printed and disseminated the management plan for Invasive alien species (IAS), for swamps forests. With great impact on IAS control work in other coastal sites of the province specifically agro-forestry companies. It constitutes an impact on knowledge management for the implementation of the state plan for confronting climate change in Cuba.
Inventories of terrestrial flora and fauna of them were updated: 795 of vegetable taxa, 93 species of birds, 31 species of butterflies, 24 of dragonflies and 13 species of freshwater fish. This information is of great impact for knowledge management in biodiversity matters in project areas, management of conservation and management programs of the protected area and economic valuation of wetland services.
| III. Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. |  | Increased the number of: a. Provincial and municipal development plans that effectively incorporate the EBA. b. Provincial and municipal governments with knowledge management systems incorporating EBA implemented. |  | After 5 years of working with local development groups within governments, it was possible to incorporate concrete elements of ecosystem-based adaptation (EBA) in the development plans of the Artemisa and Mayabeque provinces and the 6 municipal plans corresponding to Artemisa , Rent, Güira de Melena, Batabanó, Melena del Sur and Guiñes. Among the main tasks embodied in these plans are the replacement of irrigation technologies and others to improve water management and rehabilitation continuity actions carried out in the 5 years of the project. | HS
Ecosystem-based adaptation actions were also included in other management instruments such as the Provincial Environmental Strategy, Strategic Plan for the agricultural and forestry sector of the Republic of Cuba until 2030.
Within the economic and development plans of the two provinces until 2025, a budget of 20,000,000 pesos was approved only for the recovery of coastal forests. This budget includes not only the project areas but other areas north of the province, among which is the Mariel development area.
An information system that contains all the information generated and collected by the project is implemented in both provinces and municipalities. This information has been used for different purposes: Preparation of territorial development plans, preparation of climate change adaptation plans, preparation of annual reports on compliance with the implementation of the Tarea Vida and location of investments. This information will also be online in virtual platforms (http://repositorio.geotech.cu/jspui/).
The experiences of the project in adaptation to climate change is one of the main sources for the implementation of the Tarea Vida at national level at all levels. For example, to implement it in the education system, the project supported with the preparation and printing of the material “Tarea Vida: by and from Cuba, Preserving Humanity”, aimed at guiding the introduction of Environmental Education in the curricula of the University careers in Cuba.
The knowledge generated by the project has been used for the formulation of other projects throughout the country. Such is the case of the projects "Adaptation to climate change in the coastal zone of Cuba with an ecosystem-based approach" financed by the Green Climate Fund and "Building coastal resilience in Cuba through natural solutions for adaptation to climate change" support by the European Union.
The creation of 5 training classrooms, one of them in conjunction with the international project “Environmental Basis for Local Food Sustainability (BASAL)”, has served to disseminate knowledge to more than 1000 people about the importance of wetlands and coastal adaptation based on ecosystems, as well as adaptation of agriculture measures. In addition, they have been training on the use and mapping of polygons. Fundamental forest rangers, journalists, teachers, students, children, municipal and provincial government groups, hydraulic utilization and producers of the Ministry of Agriculture and Food have benefited from these classrooms.
The results monitoring system through field work and remote sensing techniques has provided governments with reliable information on the rehabilitation process as well as the characteristics and values of their coastal wetlands. In addition, it has been a fundamental tool for decision making for the extension of the hydrological and engineering work of the southern dike.
Synergies between universities and local governments resulted in 11 universities theses (6 from the Faculty of Geography of the University of Havana, 4 from the Agrarian University of Havana and 1 of the CUJAE School of Chemistry) providing information on the landscape approach in the mangrove ecosystem rehabilitation processes, health status analysis and plant cover in the project areas, economic valuation of assets and mangrove services and chemical analysis of the medicinal properties of the soil in some areas of the project.
For the first time in Cuba, South-South cooperation in the restoration of mangroves and wetland forests has been concretized in bilateral exchanges of experiences and lessons learned and signatures of agreements between the Environment Agency in Cuba and government organizations (Ministry of Environment) and non-governmental organizations (Pana mangrove and City of Knowledge) of Panama.
The dissemination of the results and experiences of the project in different events such as the last XII Environment Convention 2019, has caused impacts in the environmental scientific field. For the first time, the experiences in Adaptation to Climate Change with focus (EBA) were presented within the framework of the Climate Change congress. For the first time there were Panamanian guests from different areas including communities, education and science.
For the first time in Cuba, literature was produced on the different methods and ways of applying ecosystem-based adaptation in the coastal zone and its economic feasibility. Among the most prominent materials are: "Ecotechnologies for ecological restoration: Seed treatments and mycorrhizae", a manual on seeds for the restoration of border forests with the wetland; a nursery manual; a rehabilitation manual of mangrove ecosystems; an economic valuation manual for ecosystem goods and services; a meliponiculture manual; a glossary of project terms; a strategy and National Program for fire management and management in the forests of the Republic of Cuba.
For young people, educational materials that can be used in the circles of interest and the work of natural science subjects stand out. Eg Children's story of "Jutia and Manati" Educational kit of Mangrove, Swamp Forests, Climate Change and Swamp Grassland, the numbers 18 of "Manglar" and 19 "Algae" of the series "Let's know the sea" of the National Aquarium of Cuba.
| IV. Local communities increase the knowledge and develop skills to participate in EBA activities. |  | Increased the number of: c. Community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues. d. Local schools with curricula incorporating adaptation to climate change. e. Awareness materials on climate change adaptation issues produced by local media. |  | The knowledge of the members of the communities regarding climate change and the importance of mangroves to diminish its effects has increased considerably from 2014 to date. This could be evidenced by a process of surveys taken at the beginning of the project and at the end of 2019 taken by the Faculty of Communication of the University of Havana to the main communities that are currently most affected by floods and sea level rise. There is also an increase in the perception of the improvement of the health of the mangrove forests and the work of the project in this and the abundance of audiovisual materials of national scope was recognized where they show the results of these areas in terms of adaptation and restoration of mangrove swamp. | HS
Incorporated part of the population directly with rehabilitation, protection and monitoring of coastal forests, through the action of 5 groups of volunteers (of 4 committed) in the settlements of Surgidero de Batabanó, Cajío, Playa Majana, Playa Guanímar and Playa Mayabeque with a total of 74 members of them 24 women and 50 men. The project has provided basic equipment for carrying out these tasks, as well as training materials on the importance of these ecosystems.
Through a process of documentation of the historical heritage of the areas of intervention of the project it has been possible to convey the importance of the conservation of the natural and cultural heritage built in those areas. This process involved the local government of 6 municipalities through tours of historic sites, museums and schools.
The project was able to incorporate into the secondary, pre-university and university curricula, the fundamental elements of ecosystem-based adaptation in a coastal and developing country such as Cuba. Proof of this is the appearance of this content in the textbook of 5th and 10th grade and the transfer of the scientific results obtained, to the project for the Improvement of Environmental Education for Sustainable Development in the National Education System (SNE) in Cuba . It included the advice to 58 professionals of the Ministry of Education (MINED) and Ministry of Higher Education (MES) belonging to the SNE in Cuba, of the General Education, Professional Technical, Pedagogical and university education. The chairs represented were biology, geography, microbiology, biochemistry and agriculture. In addition, advice was given to representatives at the country level based on the development of the research and the improvement of the SNE in 8 universities throughout the country.
The direct work with 35 schools (16 primary schools, 15 secondary schools and 4 municipal university centers), contributed to increase the level of awareness of the inhabitants of the communities of the project intervention area. Conducted 14 educommunicative workshops in the linked schools, meetings with Student Scientific Societies of vocational pre-university institutes in the municipalities Guines and Artemisa. As well as, the work with 19 circles of interest corresponding to the Ranger Corps, Provincial Library of Artemis, Protected Area Wildlife Refuge Gulf of Batabanó and the different territorial schools. In these activities, products prepared by children are used as an alternative for communication and socialization of the actions carried out. The Faculty of Communication of the University of Havana conducted surveys of the inhabitants of Batabanó, Cajio and Guanimar where the knowledge acquired by the communities is evidenced.
The awareness of adults on the issues addressed by the project was another challenge that was met at the end of the project. The training of key people within the communities of these municipalities, such as specialists from territorial CITMA, voluntary groups, forest brigades, professors of the Municipal University Centers (CUM), representatives of local media and leaders of productive enterprice (eg farms, agroforestry enterprise, fisheries cooperatives), was essential to reach the level of awareness evidenced in the two processes of applied surveys.
One of the biggest successes of the project has been the visibility acquired in the press media with 47 appearances in local, national and international television programs and 40 in local and regional radio programs. In addition, during the project 17 audiovisuals were developed, which continue to be streamed in national TV. Given connectivity issues in Cuba, these videos are not yet uploaded in Youtube, but the project team is working in this.
On the initiative of the project, the "National Day for the conservation of mangroves in Cuba" was established from September 12 to 29. Cultural activities, training and rehabilitation of mangrove forests were carried out with the inhabitants of coastal municipalities in 9 provinces of the country. It was agreed that the delegations of CITMA and the Centers for Environmental Studies and / or Services of all these territories maintain this day once the project was completed.
| V. Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. |  | Increased the: a. Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; b. Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. |  | The gradual and successful training of the local decision-makers (local governments) has been the fundamental to the sustainability of the project, once donor financing is finished. Surveys conducted by the Latin American Faculty of Social Sciences (FLACSO) and the Office of Implementation (OIN) support this statement and support the fact that these key people have received the materials generated by the project and use the knowledge acquired to make decisions. | HS
In the five years of the project, three non-professional brigades were trained and strengthened, unique in the country. These brigades, composed of residents of the member settlements of the forest brigades, belong to the companies and the protected area of the Gulf of Batabanó. This action has a great impact on the ability to cope with forest fires in wetland areas and has been used in other forest fires inside and outside the provinces. Thanks to this, it has been possible to reduce the cases of forest fires in the intervention areas, protecting the actions and work of restoration of the wetlands.
As part of the tools to help in making decisions, the evaluation of the Guanímar and Cajío peloids (medicinal mud) was carried out and it was confirmed that they maintain the properties for their use. This result is essential to assess the potential of health tourism as an economic alternative to the provinces of Artemisa and Mayabeque. In addition, the quality of the actions in the wetland is verified to maintain the properties of these peloids. The Batabanó government was interested in extending this study in its territory, claiming that having positive results could be a short-term investment option.
The use of meliponiculture is introduced for the first time with the training of 25 residents of the intervention area in the management of Melipona sp. (land Bee) as an economic alternative for existing communities in the project intervention area. The linkages between governments and the APICUBA company are consolidated. In addition, the results of beekeeping in project areas and their impact on EbA methods are updated, as it increases the pollination service in the rehabilitation process. It was possible to print a Manual of the handling of this bee as a tool for consulting meliponic growers.
In the five years of the project, all certifications were carried out by the Forest Service, in the different types of project and work in both the mangroves and in the border forests. The contribution from FONADEF is 13.6 million CUP. In this way the cost of rehabilitation actions for the state budget for the 5 years of the project is 22,000 CUP per hectare.
In the years of project implementation, the capacity and effectiveness of the naval and land routes with equipment was strengthened. This is of great impact on the protection of forests and the rest of the wetland, achieving the protection and care of the restoration work implemented in the project, reducing the amount of annual contraventions. (eg 110 in 2014, 93 in 2015, 58 in 2016, 28 in 2017 and 7 in 2019.
The ranger corps under the training of the project contributed to the sensitization of the communities, by conducting more than one thousand educational talks over the 5 years.
| VI. Consolidated information on the costs and benefits of EBA available for decision makers and planners. |  | Increased the: c. Studies and methodologies carried out to estimate the cost - benefit ratio of the ABE approach, available to planners and decision makers, is increased. |  | A total of 7 studies related to the economic valuation of ecosystem goods and services, four thesis, two scientific articles and a manual were completed. These studies are the first reference in Cuba and in the region of economic feasibility studies and Cost Benefit Analysis of the application of the Ecosystem Based Adaptation (EBA) approach. As a result of these studies it can be affirmed that in the project area for every dollar invested there is a benefit of USD 9 or higher according to the scenario analyzed, which proved to be a more than viable and profitable project.
Strengthened economic valuation groups of the two provinces, with the implementation and training in the new methodology of economic valuation of ecosystem goods and services for wetlands. This allows the specialists and decision makers of the government of the territories, to update the economic valuation of the ecosystems prioritized in the country confrontation plan for climate change (Tarea Vida).
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Luis David Almeida Famada
| Email: | almeidafamada@ama.cu; almeidafamada@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
In the fifth year of the project, all the results committed in the logical framework and suggestions of international consultants and mid-term evaluation have been fulfilled. In addition, we have achieved unencumbered results such as: • The generalization of project methods in other coastal municipalities of our archipelago such as Regla (Havana), Caimanera (Guantánamo) and Cienfuegos. • The recognition of the results within the framework of the Mangrove Day implemented since 2018 by the project and appropriate in all the provinces of the country. • The implementation of meliponiculture in the coastal communities associated with the project. This included training, hive making, breeding and publication of practical manuals and a catalog of honey species. • Consolidation of work between the project and the Panamanglar network with results in training and transfer of coastal wetland restoration methodology and participation in events. • The incorporation into the national commission of reforestation of the Ministry of Agriculture of the theme of restoration and rehabilitation of Cuban mangroves and priority attention to forestry companies involved in the project once the project is finished financing. • The approval in the plan of the economy of the provinces of a budget destined only to the work of improvement of the health of the mangrove ecosystems. • Work synergies were carried out with other institutions in the country, international projects such as OP15 and Conectando Paisaje, with the objective of developing a network of collaboration and extension activities as an instrument for the implementation of an integral polygon of the Tarea Vida. Component 1. Progress in increasing the resilience of ecosystems, through rehabilitation and restoration, has had a positive trend, by the end of 2019 with a 106% over-compliance with the commitment. Overachievement is appreciated not only in the number of areas benefited, but also in the quality of management and in the increase of native species in nurseries. During the monitoring by the institutions (Ecology and Systematics, Marine Sciences, Agroforestry Research and various faculties of the University of Havana), areas were identified where the rehabilitation actions have had an indirect beneficial impact, in some places presenting indicators of success higher than in areas where interventions have been carried out directly. The companies obtained benefits from forest productions resulting from the elimination of invasive alien species, these products have high added values ​​such as charcoal, wood and production of essential oils. This positive result has been possible, thanks to the work carried out by forestry companies, the protected area and international and national financing, which greatly increases the working conditions, income and dignification of forest workers. Component 2. Everything proposed in this output has been fulfilled. Governments incorporated the EbA approach in most of the territorial management tools. An information system, about adaptation, wetlands and climate change, organized in all governments was updated and implemented, even achieving its use in decision making. As part of the knowledge management system there were several informative and scientific publications on different topics related to the EBA. It was possible to produce several audiovisual materials that had a national and international reach, which resulted in a very high recognition of the actions that the project has carried out in the coastal area. The project's visibility was raised in social media, constantly updating the followers of the actions related to restoration and work with the communities and schools. It was incorporated into the system of the National Education System based on EbA, as part of the impacts of the project on school and professional preparation for the entire country. Component 3. An articulation was achieved between all the factors that have an impact on the control and management of the coastal zone to achieve the sustainability of the project. All committed indicators were met. A total of 976 prevention talks were given and 1510 people from the communities were trained. 1682 maritime and land patrols were carried out, increasing the confrontation and reducing the number of contraventions. All technical projects were certified in the areas of intervention in both provinces, increasing the capacity of municipal forest services specialists and the fulfillment and over-compliance of project financing. In the 5 years of the project, three non-professional fire brigades were formed, two of the forest enterprise and one of the protected area. This had an impact on the reduction and confrontation of forest fires. The methodology for the economic evaluation of ecosystem goods and services of the mangrove and the swamp forest was completed and implemented in 4 municipalities in the province of Mayabeque and Artemisa. The Cost-benefit analysis of the restoration / rehabilitation of the mangrove area of ​​the intervention area was concluded, evidencing the viability of this type of investment.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Key Milestones I. Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. II. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. |  | Increased the: a. Restored mangrove ecosystem area (Artemisa: Majana - Surgidero de Batabano). b. Red mangrove area along the coast (Mayabeque Batabano - Punta Mora). c. Enriched border forest area. d. Control and eradication of IAS. |  | These two key milestones comply with Component 1 of the project: “Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems”. This component is rated satisfactory since its four expected output indicators were achieved. The main results are: - The hectares of coastal wetlands compromised were rehabilitated. The quality of the work performed has been certified. - There is an improvement in the health indicators of the mangrove ecosystem. This enhances its protection service, which helps reduce vulnerability to coastal flooding. | S
| Key Milestones III. Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. IV. Local communities increase the knowledge and develop skills to participate in EBA activities. |  | Increased the number of: a. Provincial and municipal development plans that effectively incorporate the EBA. b. Provincial and municipal governments with knowledge management systems incorporating EBA implemented. c. Community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues. d. Local schools with curricula incorporating adaptation to climate change. e. Awareness materials on climate change adaptation issues produced by local media. |  | These two key milestones comply with Component 2 of the project: “Integrated and participatory management of coastal ecosystems to increase resilience to climate change”. This component is rated satisfactory since its outputs were achieved. The main results are: - The management of coastal ecosystems enhanced. - The EBA approach incorporated into the local development instruments. - The Knowledge Management System working on. - The EBA topics incorporated in school curricula. - Prepared and published a wide variety of printed and audiovisual products. | S
| Key Milestones V. Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. VI. Consolidated information on the costs and benefits of EBA available for decision makers and planners. |  | Increased the: a. Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; b. Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. c. Studies and methodologies carried out to estimate the cost - benefit ratio of the ABE approach, available to planners and decision makers, is increased. |  | These two key milestones comply with Component 3 of the project: “Establishment of a favourable enabling environment at regional level for the effectiveness and sustainability of adaptation investments”. This component is rated satisfactory since its outputs were achieved. The main results are: -The target institutions were strengthened in EBA issues. -The studies to estimate the cost-benefit of the EBA were conducted. -The economic evaluation methodology of ecosystem goods and service was developed. -Information on the costs and benefits of EBA is available for decision makers and planners. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gricel Acosta Acosta
| Email: | gricel.acosta@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. It is considered that the general objective of the project - “To increase the resilience of populations living in the coastal zone of the provinces to Mayabeque Artemisa and the effects of climate change” - has been achieved; because the 2 objective indicators were met. There is evidence that the rehabilitation actions carried out by the Project (in more than 7,000 ha) improved the health indicators of coastal wetlands in the intervention area (about 84 km of coastline), contributing to enhancing the protection service that these ecosystems provide to the coastal zone. In that way, the project has contributed to reducing the vulnerability of coastal communities to floods, generating direct and indirect benefits for more than 200,000 people. The project has validated that the ABE approach is a cost-effective strategy to adapt to climate change that can be applied to other regions of the country. In fact, the rehabilitation methodology, the lessons learned and the economic and financial calculation bases developed by Manglar Vivo are used in the design and implementation of new initiatives. Based on the above and taking in to account that the project implementation period was extended for one year, the overall evaluation proposed is Satisfactory. The arguments that support our evaluation by components are: Component 1. The quality of the rehabilitation actions of coastal wetlands (mangroves and swamp forests) executed by the project has been certified by the State Forest Service. The results of the monitoring system confirm a recovery of the health indicators of these ecosystems, also their capacity to offer protection service to the coastal zone. It is evident that applying the EbA approach has contributed to reducing the impacts of flooding on the southern coast of the provinces of Artemisa and Mayabeque. However, to ensure the long-term sustainability of this result, it is recommended to develop a maintenance program (for the next five years) that has the necessary financial support and commitment from the government and forestry companies. We considered that this component has a satisfactory performance. Component 2. The results achieved by the project contribute to enhance the integrated and participatory management of coastal ecosystems. The Project has achieved the incorporation of the EBA approach into the main management and planning instruments of territorial development; also in the strategies of the productive sectors. The implementation of the Knowledge Management System is an outstanding result; as is the incorporation of EBA and Mangroves related curriculum in the national education system. In addition, the project allowed for local communities to increase their knowledge and develop skills to participate in EBA activities. We considered that this component has a satisfactory performance. Component 3. The project has contributed to strengthening institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. An outstanding result was the culmination (for the first time in Cuba) of the studies to estimate the cost-benefit of the EBA approach in mangroves rehabilitation in the intervention areas. These studies have evidenced the viability of this type of investment as adaptation strategy in this kind of coastal zone. Also, the project developed a methodology for the economic evaluation of ecosystem goods and services for the coastal wetland, which can be applied in other regions of the country. Consolidated information on the costs and benefits of EBA is available for decision makers and planners. We considered that this component has a satisfactory performance. At the end of December, the project showed an accumulated financial execution amounting to 5,199,932.05 USD (total budget: 5,592,000 USD), which represents 92.9% of execution. The 2020 plan amounts to USD 203,366 (at the end of February $73,773 USD has been executed), which represents 36.3% of execution. The pending financing is fully committed (Final evaluation, workshops, printing of books and brochures, monitoring visits to intervention areas, fuel, etc.). Taking this scenario into account, a total execution of the financing is expected by September 30, 2020. 2. Detail critical risks that have affected progress. No critical risks were identified that would affect the implementation of the project in this period. 3. Outline response to MTR undertaken this reporting period. The Project Management Unit has managed to comply with the 19 measures of the plan approved by the National Steering Committee to comply with the recommendations of the MTR. This is considered to have contributed to the achievement of the project results.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: favor de validar edición en rojo

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience of populations living in the coastal zone ofthe provinces to Mayabeque Artemisa and the effects of climate change. | I. Areas with high rates of health and the conditions of the mangroves (soil and salinity of the water, the density of the canopy, the existence of local regimes of protection). | Coastal ecosystems that cover 7 318 ha are degraded, have excessive levels of salinity due to seawater intrusion and the obstruction of channels and have a limited protection regime. | Rehabilitation actions have been developed in 7770.2 ha (in mangrove forests - 3402.2 ha and cienaga forests - 4368 ha), which represents 106% with respect to the goal at the end of the project. The monitoring system of the health status of mangrove forests and swamp forests has been maintained by combining field work with remote sensing techniques. | 7 318 Ha (total area where reforestation of mangrove, restoration of the mangrove ecosystems, and the enrichment of the forested areas inland was carried out) Note: the rates of coastal mangroves and wetlands must be nominated in the methodological documents to be developed at the start of the project.
| II. Numbers of people (men and women) with reduced vulnerability due to proximity of functioning mangrove forest and wetland ecosystems. | 17,524 People in 47 communities are directly affected by coastal flooding. | Vulnerability of 17,524 inhabitants of the communities directly benefited from the work of the project was reduced. The increase in the health of ecosystems together with their ability to reduce waves is a fact verified by research institutions. This capacity will continue to increase as the actions consolidate and the first strip of red mangrove reaches the desired structure. In addition, the perception of the vulnerability of these inhabitants has decreased in recent years and they associate this with the project, according to the results of the recent surveys. | 21,502 People (of which at least 45% are women) experience reduction of vulnerability due to coastal flooding.
|  | 270,705 People are indirectly affected by the impacts of the phenomena associated with the CC on economic activities. | Vulnerability of the 270 705 inhabitants of the communities indirectly benefited from the work of the project was reduced. The increase in the health of ecosystems and the decrease in the perception of vulnerability are facts that indirectly benefit the entire population of the municipalities. In addition to this, the strengthening of knowledge (material and knowledge) of the institutions of the territory has increased their resilience to natural phenomena such as hurricanes and fires. This is evidenced by the fact that the human and technological capital depending on the project has provided support quickly and efficiently in other areas of the country with similar problems. | 270,705 People (at least 45% are women) experience a reduction in vulnerability to CC-related phenomena on economic activities.
| 1.1 Area (ha) of red mangrove is established along shore between Batabanó and Punta Mora. | 533 ha | Rehabilitation actions have been conducted in 1527,9 ha of red mangrove forest (includes restoration of ditches and canals, management of natural regeneration and sowing of propagules). This figure accounts for 118% of final target of the project. | 1290,6 ha of which 85% survived* (1097 ha) *Survival can only be measured 3 years after planting
| 1.2 Cumulative area of mangrove ecosystem restored between Majana and Surgidero de Batabanó. | 144 ha | Rehabilitation actions have been conducted in 1874,3 ha of the mangrove ecosystem (includes restoration of ditches and channels, management of natural regeneration and sowing of propagules). This figure accounts for 109% of final target of the project. | 1711,9 ha of which 85% survived* (1455,1 ha) *Survival can only be measured 3 years after planting
| 1.3 Cumulative area of landward edge woodlands restored and enriched. | 939 ha | 4,368 ha of landward edge woodlands were enriched by planting native species and encouraging natural regeneration. This figure accounts for 101% of the final target of the project. | 4315,5 ha of which 85% survived* (3668,2 ha) *Survival can only be measured 3 years after planting
| 1.4 Numbers of IAS management plans developed. | 0 | The Invasive Exotic Species Management Plan (EEI) by the Institute of Ecology and Systematics (IES) and the Agroforestry Research Institute (INAF) was completed, published and disseminated. In addition, over the 5 years several of the methods proposed here have been used to eliminate more than 100 effective hectares of Terminalia cattapa and Casuarina equisetifolia. This elimination is on par with the use of wood for the production of coal and wood. | 1, covering 7,318 ha
Outcome Indicator | 2.1 Numbers of provincial and municipal development plans that make specific provision for EBA. | 2 provincial and 6 municipal governments are preparing development plans that do not include EBA. | The EbA approach has been included in 3 management instruments. This approach has been included in the local development strategies in 6 municipalities, in the environmental strategy of the 2 provinces, and 8 plans to combat the climate change (in the 2 provinces and the 6 municipalities). It is controlled by the government through semiannual meetings. In the provincial plan of the economy a budget of more than 15 million pesos was included for actions to rehabilitate the protection forests on the coast. | 2 provincial plans and 6 municipal plans
Outcome Indicator | 2.2 Numbers of provincial and municipal governments with EBA-related knowledge management systems in place. | 0 | Both provincial governments use the information generated by the project for climate change adaptation planning. The KM system is also used for planning and execution of supervision trips to the coastal zone, and in the incorporation of EbA actions in the local development strategies and the forestry sector economy plans. An information system that contains all the information generated and collected by the project is implemented in both provinces and municipalities. This information has been used for different purposes: Preparation of development plans, preparation of climate change adaptation plans (Tarea Vida), preparation of annual reports on the Tarea Vida and to identify the location of interventions. | 2 provincial and 6 municipal governments
Outcome Indicator | 2.3 Numbers of community members (men and women) belonging to local voluntary groups addressing environmental and adaptation issues. | 0 | 5 working volunteer groups: one in Guanímar (with 18 members, 10 are women and 8 are men), one in Surgidero de Batabano (with 16 members, including 9 women), one in Cajio (with 10 members, including 2 women), one in Playa Mayabeque (with 25 members, of them 3 women), and another at Majana beach (with 5 members and 5 ships. These groups support: the inspections and controls carried out on the project, the transfer of the trunks to make the palisades, the dissemination of the work of the project in the area. | 1 group with at least 15 members (of which at least 45% are women) in four municipalities
Outcome Indicator | 2.4 Numbers of local schools with study programmes incorporating adaptation issues. | 0 | 35 schools in the two provinces include CC and EBA, of which: 16 primary schools, 15 secondary schools and 4 municipal university centers. Incorporando actividades como trabajos practicos y capacitaciones teorico prácticas en los diferentes circulos de interes ambientalistas. A nivel nacional en libros de 5to y 10mo grado cuentan información sobre el proyecto y conceptos sobre AbE y CC. | 16 primary schools 15 secondary schools 3 municipal universities 1 teacher training institute
Outcome Indicator | 2.5 Numbers of dissemination and awareness raising materials on adaptation issues, produced by local media | 0 | 17 audiovisuals were produced and broadcasted on several occasions by national and local television stations, related to the objectives and advances of the project, the mangroves and the importance of their protection. | 17 videos 3 local television spots 5 local radio spots 2 articles
47 reports were broadcasted by local (26), national (17) and international (4) television stations about the project, its actions, progress and perspectives as well as the importance of mangroves and other coastal wetlands.
39 reports and interviews were disseminated on national (7) and local (32) radio.
18 articles were published in national (4), local (9), web (4) media, and international (1). Many with accceso via internet.
Outcome Indicator | 3.1 Frequency of training and technical support visits carried out by provincial and municipal governments to coastal communities in support of EBA | 0 | 1899 training and technical support actions were carried out with the coastal communities. These activities were conducted by the government, the forest ranger and research institutes. | 3 training and technical assistant activities undertaken per year by technical authorities to coastal areas.
Outcome Indicator | 3.2 Frequency of inspection visits to coastal areas by provincial and municipal governments in support of EBA | 0 | Lead by the goverment, 182 comprehensive inspections were carried out in the intervention areas of the project; 6 in the first year, 3 in the second year, 5 in the third year, 156 in the four year, 12 in the fifth year. In these inspections were participating representatives of all the regulatory institutions of each municipality: the CAP and CAM, SEF, CGB, TGF, PNR, and implementation office. | 3 inspection activities undertakern per year by provincial municipal goverment and other regulatorities authorities
1682 maritime and land inspection and control journeys along the coast (10 during the first year, 70 during the second and 118 during the third year, 987 in the four year, and 357 in the final year) were carried out for the monitoring and protection of natural resources within the Project intervention area. The ranger corps and research institutes participate.
Outcome Indicator | 3.3 Number of studies and methodologies carried out to estimate the cost - benefit from the implementation of the approach ABE, available for planners and policy makers. | 0 | Twelve services of the mangrove ecosystem, 5 of Provision and 7 of Regulation and Support studies were evaluated (agriculture, livestock, beekeeping, fishing, drinking water, air quality and gas regulation, hydrological regime, disaster damage reduction, control of pollution / waste regulation, erosion regulation, nutrient cycle, biodiversity). Four theses, a methodology in economic evaluation of ecosystems services for the goverment application and two scientific contribution (in preparation) on the cost benefit were carried out with the application of the ecosystem-based adaptation approach in the mangrove with 3 scenarios and discount rates of 14 and 4% and their current net values (NPV) for those rates. The benefits per hectare of mangroves and the benefits per annual hectares were also estimated. Additionally, the tourism service was evaluated as a potential resource. | 3
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Qué queremos decir aquí? Que 21,502 personas se benefician de la reducción de vulnerabilidad a la inundación?

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During the five years of the project we have reached important lessons learned, valid for EbA projects in coastal areas and wetlands. The economic valuation of the goods and services of the wetland, as a tool in management and decision-making, based on own methodologies, has been an important guideline for verifying the effectiveness of forestry work. Having trained and trained forest brigades in the hydrological restoration of mangroves, the use of native species and the elimination of IAS, constitutes the guarantee of all restoration or rehabilitation actions in wetland areas affected by anthropic nations The integrated monitoring system, Water-land-sea, with the call and involvement of all experts from national institutions, provides new evidence of the operation and response of natural systems in the coastal area, with the possibility of updating the intervention methods for recovery, and amplify actions with a positive response of wetland resilience. To constitute a group of excellence with all the experts in the matter of coastal wetlands, constitutes a guarantee of the excellence of the results and the capacity of its generalization to other areas of the country with similar problems The creation of alliances and work agreements with other international projects has been fundamental for the monitoring and control of impacts on the wetland, such as: pollution load, agricultural and livestock activities and water management. Project like BASAL and OP15, constituted important counterparts in the success of the actions in the southern zone of the Artemisa and Mayabeque provinces. The lessons learned with the forestry sector for intervention in wetlands, their training, updating of work in technical projects and improvement of working conditions, was an important tool in the conformation of new projects, in addition to marking a milestone in the Ministry of Agriculture for the priority attention of mangroves
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | FONADEF's investment exceeds 10 million pesos (CUP), for all technical projects implemented in the 5 years of the 9573,400.94 project, doubling the amount committed as co-financing of the country. As a lesson, the completion of the brigades and improvement of the work on the technical projects to intervene in the wetlands increases the effectiveness of the tasks. This experience is generalized in other agroforestry companies, with brigades responsible for forest heritage in wetland areas, with a new conception of thinking about coastal management. In addition, they constituted compelling evidence for the implementation of the living task in the rest of the coastal municipalities with intervention in the mangroves or other coastal ecosystems.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In this period, no changes have been made in the project design nor in the outputs in the logical framework.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The work of the volunteer groups, key in the monitoring and early warning of the mangrove response and its associated biological diversity, was maintained. It was a successful experience involving the volunteer groups in the appropriation of the national mangrove day Cubans and leadership in working with the circles of interest and schools in the territory The exchange with other cultural projects with children and adolescents between Havana, Artemisa and Mayabeque was a very successful experience, for the recognition of the values and services of the wetlands for which they will be responsible, as it was with the project + adolescents. The completion of 5 groups of volunteers was achieved, in 5 locations: Surgidero de Batabanó, Cajío, Majana beach, Guanimar and Mayabeque beach. For a total of 74 volunteers (24 women and 50 men).
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | *The restoration of mangrove areas and coastal forests with innovative techniques that not only increase the coverage and diversity of these forests, but also increase their health or resilience to extreme events related to climate change. *The application of methods that generate an increase in microbial activity in the soil, such as water restoration, increases the carbon sequestration capacity of these wetland ecosystems, giving added value as a contribution to climate change mitigation. *Institutional strengthening has served to increase its capacity to respond to weather events such as hurricanes and fires. This has been verified in the years of execution of the Project. *Is necessary indicators of impact and tasks must be included to ensure the sustainability of the project in the long term.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The measures implemented by the project have a great potential for replication inside and outside the intervention area, because the mangrove has shown a great adaptive capacity and responded positively to the restoration interventions carried out. We recommended to review and update (from the technical and economic point of view) before to execute the rehabilitation actions that will be carried out by the forestry company, because it is a key factor to raise the interest of this productive group. In addition, must be considered that the social resilience is not limited to increasing the protection function that ecosystems offer to face the impacts of climate change, it also incorporates attention in the aspects related to the adaptation and improvement of the livelihoods of local inhabitants.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | *We have learned that, in the design of future adaptation projects to climate change for the coastal zone, the hydrographic basin approach must be taken into account. In other words, it is necessary to consider the management effects upstream and downstream of the intervention area. In addition, indicators of impact and tasks must be included to ensure the sustainability of the project in the long term. *The correct application of the principles of ecological restoration in the mangrove ecosystem, taking into account a diagnosis and the preparation of the ecosystem health map. *Constitution of a multidisciplinary team to plan and develop the adaptation actions required by the coastal zone. *Incorporation of adaptation actions in the local development plans. *The improvement of the working conditions of forestry workers who are also inhabitants of local settlements.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | *The project has developed and validated a methodology for the restoration of coastal wetlands, this methodology is available to be applied in other areas of the country. Groups of experts in coastal ecosystems have been set up in the research centers directly linked to the project. The forestry brigades are able to carry out the rehabilitation actions with the required quality. So, the technical conditions to scale the results of the project are created. *The work with the ranger corps has been a successful and replicable element since, in addition to guaranteeing the safety of the project's actions, they carry out prevention and education work for communities that often exceed those carried out by local governments.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The active participation of leaders and coastal communities in activities is a key link to achieve the goals of the project. The training of community leaders on topics such as: climate change, life task, local development and ecosystem services guarantee the sustainability of the project's results. In addition, the involvement of the schools guarantees the environmental education of the young generations in transcendental aspects such as the EBA, and the services provided by the coastal wetlands.
What measures are/have been put in place to ensure sustainability of the project/program results? | Incorporation of adaptation actions in the development plans at the municipal and provincial levels; this ensures the sustainability of the achievements. Incorporation of restoration / rehabilitation actions in technical projects and improvement of control indicators.
What measures are being/could have been put in place to improve project/program results? | Implement a project aimed at increasing the social resilience of communities and their living conditions and recovery time from the damages that could be caused by hurricanes in the future.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project has made an adequate use of the available information and knowledge. Among the documents and information used are: Annual reports of the Mayabeque and South Coast Companies, the Red List of the Flora of Cuba (2016), the protocols for the control protocols of EEI, the annual reports of the Forest Ranger, the inspections reports, and census data (ONEI). The project updated Forest Management using the SIFOMAP system of the Ministry of Agriculture MINAG
If learning objectives have been established, have they been met? Please describe. | The project's learning objectives focus on issues related to the importance of mangroves to adapt to climate change, the importance of swamp forests, protection of coastal wetlands, promotion of native bee breeding and cost-benefit calculation. of the application of ecosystem-based adaptation instead of other forms of "gray" adaptation. The learnings generated by the project have been included in the development plans of the coastal municipalities, this allows their technical and financial planning. The results of the project are shown in government meetings, this allows decision making as adaptive management. In addition, they are being applied in the development loaves of the rest of the coastal municipalities of both provinces.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Although all the necessary information has been able to be collected, there were difficulties in accessing data from the plans of the government's economy and income of some items in the territory.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes. The accumulated experience by the project team has motivated to carry out the redesign of the Communication Strategy; also to establish a mechanisms to measure the impact of the communication strategy and ownership sense of the involved people. Aditionaly, it is proposed to start a designing process of the Knowledge Management System generated by the project.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 84007
Implementing Entity | United Nations Development Program
Type of implementing entity | MIE
Country | Cuba
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 288224 | 17519 | 270705 | Total | 281505 | 10800 | 270705 | Total | 288224 | 17519 | 270705
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 49% | 48% | 50% | % of female beneficiaries | 41% | 38% | 50% | % of female beneficiaries | 49% | 48% | 50%
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 15% | 14% | % of Youth beneficiaries | 15% | 13% | 14% | % of Youth beneficiaries | 15% | 15% | 14%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Coastal flooding | 2: Partially effective | Total |  | Coastal flooding | 4: Effective | Total |  | Coastal flooding | 3: Moderately effective | Total |  | Coastal flooding | 4: Effective
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Multi-sector | National | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Multi-sector | Regional | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local
|  |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 88 | Coastal management | 4: High capacity | Total | 132 | Coastal management | 4: High capacity | Total | 132 | Coastal management | 4: High capacity
|  | % of female targeted | 0 |  |  | % of female targeted | 25% |  |  | % of female targeted | 40% |  |  | % of female targeted | 40%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | land | 4: Effective |  | Coastal management | land |  |  |  |  | 4: Effective |  | Coastal management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 677 | ha rehabilitated | 1: Ineffective | Mangroves | 3002 | ha rehabilitated | 4: Effective | Mangroves | 2047 | ha rehabilitated | 4: Effective | Mangroves | 3402 | ha rehabilitated
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 939 | ha rehabilitated | 1: Ineffective | Forests | 4315 | ha rehabilitated | 4: Effective | Forests | 2727 | ha rehabilitated | 4: Effective | Forests | 4368 | ha rehabilitated
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 |  |  |  | 84 | Natural capital | Coastal management | Mangrove reforestation | 60 | Natural capital | Coastal management | Mangrove reforestation | 84 | Natural capital | Coastal management | Mangrove reforestation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 5: All (Fully integrated) |  |  |  | 4: Most |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 |  |  |  | 8 | 4: Enforced (Most elements implemented) |  | 4: Effective | 8 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective | 8 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness. 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions. 2.2. Number (men and women and other vulnerable groups). 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses. 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None. 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements). 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved. 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement. 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention. 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.