## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | August 2015 - December 2016
| Project Title: | Reduction of vulnerability to coastal flooding through ecosystem-based adaptation in the south of Artemisa and Mayabeque provinces.
| Project Summary: | The proposed project seeks to reduce the vulnerability of communities in coastal areas of Artemisa and Mayabeque provinces in southern Cuba from climate change (CC) related phenomena including coastal erosion, flooding and saltwater intrusion. This will be achieved through Ecosystem Based Adaptation (EBA), taking advantage of the proven potential of mangrove forests and associated coastal wetlands to limit the effects of wave erosion and coastal flooding, which are among the most damaging results of climate-change related SLR and storms. The project’s objective will be achieved through investments in three complementary components. Component 1 will focus on concrete investments in ecosystem recovery, leading to improved coastline resilience to the impacts of wave action, and improvements to coastal morphology which will reduce seawater incursion. Component 2 will focus on integrated and participatory management of coastal ecosystems, through mainstreaming EBA into integrated coastal zone planning and productive sector activities, promoting buy-in, participation and governance in local communities and developing knowledge management systems at community level. Component 3 will focus on establishing a favourable enabling environment at regional level for the effectiveness and sustainability of adaptation investments, through the provision of consolidated information on costs and benefits of EBA to decision makers and planners and the strengthening of institutions supporting EBA actions, within the framework of updated and actively implemented action plans.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 84007 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cuba | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Coastal areas of Artemisa and Mayabeque provinces in southern Cuba | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-05-19
IE-AFB Agreement Signature Date: |  | 2014-06-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | September 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | March 2017
| Terminal Evaluation Date: | September 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Cuba inception report, Quarterly Reports from UNPD 1st issue of Living Mangrove Forest bulletin | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.ama.cu/manglar/manglar.html | Democratic Republic of the Congo
|  | https://www.facebook.com/manglarvivo/?ref=ts&fref=ts | Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Sheila Chang Fente | Dominican Republic
| Email: | sheila@ama.cu | Ecuador
| Date: | December 31th, 2016 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Gricel Acosta Acosta | Fiji
| Email: | gricel.acosta@undp.org | Finland
| Date: | December 31th, 2016 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 December 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2016 | 1453452
Add any comments on AF Grant Funds. (word limit=200) | By the end of December 2016, the financial execution rate is 74% in relation to the total cash availability ($1,960,600). As of December 2016 the avaliable cash is $ 507,148 and there is an amount of $622,058 committed, corresponding to signed contracts for goods internationally procured. As explained in previous Project Performance Report (First Report), the vast majority of acquisitions for international cooperation projects in Cuba need to be internationally procured, due to the low availability of products and services nationally. This is a long and complex process that has to comply with a wide range of national regulations. Additionally, during the period of this Second Report, regulations on projects’s acquisitions have been updated by the Cuban Ministry responsible for international cooperation (MINCEX). In particular, the Project procurement plan was delivered, for the first time, to “EMIDICT”, import enterprise belonging to the Ministry of Science, Technology and Environment (CITMA). It took to EMIDICT more time than initially foreseen, to assimilate required national regulations for international cooperation projects and all procurement processes. It represented a determining factor which had not allowed to expedite processes. As emergent alternative measure, in order to help in this special situation, UNDP/Cuba Country Office was requested by the Government to help with the international procurement of goods for the Project. From May 2016 UNDP was in charge of the majority of planned procurement processes for 2016. Working closely with Project Team and EMIDICT, from July to December 2016, 17 contracts have been signed by UNDP/Cuba for a total amount of $554,115. As of December 2016, $127,252 have been disbursed, and the rest is expected to be disbursed no later than March 2017. Regarding the “remaining balance of signed contracts”, the 90% of the amount reported in the First Report was disbursed. The remaining 10% is under revision with the providers. As of December 2016 an additional amount of $585,465 is being reported for this concept and it corresponds to contracts signed in this second report period. By the end of 2016, the documentation related to 2017 procurement plan (for an amount of $800,000), has been delivered to EMIDICT to initiate procurement processes early in 2017.
INVESTMENT INCOME | Not applicable
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (1 Aug 2015 - 31 Dec 2016) | ITEM / ACTIVITY / ACTION/OUTCOME | OUTPUT | AMOUNT
| 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 180054
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 231469
|  | 1.3. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 146901
|  | 1.4. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 66772
| Subtotal Outome 1 |  | 625196
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 64858
|  | 2.2. Buy-in, participation and governance in local communities | 97061
|  | 2.3. Knowledge management systems at community level | 72425
| Subtotal Outome 2 |  | 234344
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 30322
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 163238
| Subtotal Outome 3 |  | 193560
| Project Management |  | 41523
| TOTAL EXPENDITURE |  | 1094623
| REMAINING BALANCE OF CONTRACTS | (Please refer to Procurement Sheet) | 622058.1656
| GRAND TOTAL |  | 1716681.1656
PLANNED EXPENDITURE SCHEDULE | ITEM / ACTIVITY / ACTION/ OUTCOME | OUTPUT | PROJECTED COST | Est. Completion Date
List outputs planned and corresponding projected cost for the upcoming reporting period (Jan 2017 - Dec 2017) | 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 285054 | 2017-12-31
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 385662 | 2017-12-31
|  | 1.3. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 432720 | 2017-12-31
|  | 1.4. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 627444 | 2017-12-31
| Subtotal Outome 1 |  | 1730880 | 2017-12-31
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 43000 | 2017-12-31
|  | 2.2. Buy-in, participation and governance in local communities | 39200 | 2017-12-31
|  | 2.3. Knowledge management systems at community level | 21000 | 2017-12-31
| Subtotal Outome 2 |  | 103200 | 2017-12-31
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 36630 | 2017-12-31
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 29970 | 2017-12-31
| Subtotal Outome 3 |  | 66600 | 2017-12-31
| Project Management |  | 64000 | 2017-12-31
| TOTAL |  | 1964680 | 2017-12-31
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
179
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Item | Contract Type | Agency / Contracted party | Contract Value/Amount (EUR) * | Contract Value/Amount (USD) | Signature Date (mm/dd/yy) | Payment to Date 12/31/2016 (USD) | Remaining Balance to Date (USD)
1 | Provisions for Expeditions | CIMEX |  | 25220 | 2015-02-09 | 25220 | 0
2 | Vehicles insurance | UEB NEGOCIOS ESPECIALES |  | 15453.22 | 2015-04-27 | 15453.22 | 0
3 | Logistic Contract Services (Annual Workshop) | AVC VENTAS INTRNACIONALES |  | 5710 | 2015-08-01 | 5710 | 0
4 | Tractors and traillers (Purchase abroad) | GAMMA EXPORT SRL | 183631.26 | 207886.94 | 2015-10-26 | 207886.94 | 0
5 | Printing promotionals | ATRIO |  | 6483 | 2015-11-13 | 6483 | 0
6 | Vehicle (2 small trucks) (Purchase abroad) | WOMY EQUIPMENT SUPPLY | 68191.34 | 76457.13 | 2015-11-15 | 76457.13 | 0
7 | Agriculture tools; Office materials and furnitures (Purchase abroad) | BM GLOBAL | 23167.49 | 25126.92 | 2015-11-15 | 25126.92 | 0
8 | Working clothes (Purchase abroad) | LUSAKA | 49134.69 | 51994.32 | 2015-11-23 | 41595.51 | 10398.81
9 | Printing promotionals | ATRIO |  | 3310.1 | 2015-12-03 | 3310.1 | 0
10 | Computer Equipment (Purchase abroad) | GRUPO KAPAN INTERNATIONAL |  | 25061.66 | 2015-12-10 | 25061.66 | 0
11 | Office remodeling | EMPRESA GALERIAS DE ARTE GENESIS |  | 13557.28 | 2015-12-23 | 13557.28 | 0
12 | Fuel to support project activities | FINANCIERA CIMEX, S.A. |  | 12022 | 2015-12-24 | 12022 | 0
13 | Audit services (audit period Jan-Dec 2015) | KPMG ACCOUNTANTS B.V. |  | 7618.38 | 2016-03-07 | 7618.38 | 0
14 | Office materials (Purchase aborad) | INTEL LABORATORY INVESTMENT S.A |  | 3064.86 | 2016-07-15 | 3064.86 | 0
15 | Clima equipment (Purchase abroad) | IBERCUB |  | 4463.62 | 2016-08-08 | 0 | 4463.62
16 | Spare parts for Suzuki motorcycles | MAREGINA INVESTMENT INC |  | 9452 | 2016-09-08 | 0 | 9452
17 | Printing promotionals (Purchase aborad) | ALINA INTERNATIONAL S.A |  | 13369 | 2016-08-10 | 0 | 13369
18 | Mobile Audio Equipment (Purchase aborad) | INTEL LABORATORY INVESTMENT S.A |  | 6748.74 | 2016-08-10 | 6748.74 | 0
19 | Printing promotionals (Purchase aborad) | GRUPO URANO, S.A |  | 5776 | 2016-08-18 | 0 | 5776
20 | Firefighting equipment and supplies (Purchase abroad) | COMERCIAL FIGUEROA S.R.L |  | 44582.56 | 2016-08-29 | 35162.1 | 9420.46
21 | Tires (Purchase abroad) | COLVAZCA |  | 8038.0275 | 2016-09-08 | 0 | 8038.0275
22 | Vehicle (1 microbus and 1 jeep) (Purchase aborad) | WOMY EQUIPMENT SUPPLY | 76102.25 | 85030.4469 | 2016-09-14 | 64630.36 | 20400.0869
23 | Bicycles (Purchase aborad) | SUPLAY INC. |  | 31800.08 | 2016-09-27 | 0 | 31800.08
24 | Working clothes (Purchase abroad) | UNIVEX CARIBBEAN INC |  | 26687.65 | 2016-09-27 | 0 | 26687.65
25 | Spare parts for vehicles (Purchase abroad) | TOYOTA GIBRALTAR STOCKOLDINGS LTD | 1,264,464 YEN | 12071.25 | 2016-09-14 | 11215.8 | 855.45
26 | Motorcycles (Purchase aborad) | MAREGINA INVESTMENT INC |  | 18968.84 | 2016-09-15 | 0 | 18968.84
27 | Supplies for forest nurseries (Purchase aborad) | GRUPO URANO, S.A |  | 20101 | 2016-09-21 | 0 | 20101
28 | Motor for sea craft (Purchase aborad) | BM GLOBAL |  | 14041.64 | 2016-10-31 | 0 | 14041.64
29 | Vehicle (2 trucks) (Purchase aborad) | BRYTESIDE TECH INC |  | 143000 | 2016-12-16 | 0 | 143000
30 | Vehicles (3 small trucks) (Purchase aborad) | WOMY EQUIPMENT SUPPLY | 106374.42 | 118854.1006 | 2016-12-16 | 0 | 118854.1006
31 | Sea craft and auxiliary boats (Purchase aborad) | CEPRONA |  | 5761.89 | 2016-12-15 | 0 | 5761.89
32 | Tractors and traillers (Purchase abroad) | GAMMA EXPORT SRL | 111048.44 | 124076.469 | 2016-11-16 | 0 | 124076.469
33 | Computer Equipment (Purchase abroad) | DARLOCK BUSINESS SA | 79028 | 88299.4413 | 2014-11-25 | 88299 | 0.44134 | **
34 | Forest equipment (Purchase abroad) | LUSAKA | 59328.7 | 66289.0503 | 2015-03-30 | 52445.26 | 13843.7903 | **
35 | Firefighting equipment and supplies (Purchase abroad) | LUSAKA | 28793.94 | 32044 | 2015-03-30 | 32043.75 | 0.25 | **
36 | Working clothes (Purchase abroad) | LUSAKA | 39296.34 | 43355 | 2015-03-30 | 32655 | 10700 | **
37 | Furniture (Purchase abroad) | BM GLOBAL | 12676.36 | 14189 | 2015-05-20 | 14188.92 | 0.08 | **
38 | Forest tools (Purchase abroad) | BM GLOBAL | 4751.61 | 5267 | 2015-05-20 | 5266.9 | 0.1 | **
39 | Office supplies (Purchase abroad) | BM GLOBAL | 12402.59 | 13882 | 2015-05-20 | 13882.49 | -0.49 | **
40 | Provisions (Purchase abroad) | BM GLOBAL | 7684.72 | 8602 | 2015-05-20 | 8601.67 | 0.33 | **
41 | Vehicle (2 small tracks; 1 microbus, 1 truck (Purchase abroad) | WOMY EQUIPMENT SUPPLY | 179822.04 | 199877 | 2015-05-27 | 199877.18 | -0.18 | **
42 | Motorcycles (Purchase abroad) | MAREGINA | 22000 | 24237 | 2015-07-09 | 24237 | 0 | **
43 | Appliances (Purchase abroad) | COMERCIAL FIGUEROA S.R.L | 4304 | 4808.9385 | 2015-07-09 | 4808.9385 | 0 | **
44 | Filming set (Purchase abroad) | LUSAKA |  | 60243.61 | 2015-07-25 | 48194.89 | 12048.72 | **
622058.1656
* Contract/Bid in EURO. The Value Amount in USD has been estimated. Procurement contracts are signed in EUR because Cuba can't transfer in USD due to the current US financial regulations related to Cuba.
** Contracts reported with remaining balances in the last PPR.
BIDS
List all bids for each contact signed with date of open call and winning bid
| CONTRACT & Procurement Method | Submitted Bids | Bid Amount (EUR) * | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
1 | Provisions for Expeditions | CIMEX |  | 25220 | 25220 | Only one offer. This is the only one national supplier authorized to offer/sell the referred goods to international cooperation projects.
2 | Vehicles insurance | UEB NEGOCIOS ESPECIALES |  | 8824.4 | 8824 | Only one offer. This is the only one national supplier authorized to offer/sell the referred service.
3 | Logistic Contract Services (Inception Workshop) | CUBANACAN - HOTEL COMODORO |  | 5710 | 5710 | Best responsive offer. The UNDP country office corporative service Agreement with Cubanacan Travel Agency was used.
|  | CUBANACAN H10 PANORAMA |  | 10182
|  | CUBANACAN-H MELIA HABANA |  | 14062
4 | Tractors and traillers (Purchase abroad) | GAMMA EXPORT SRL | 183631.26 | 207886.94 | 207887 | The purchase of equipment S.A.M.E. was requested, due to its previous good performance in the conditions of the work area. In the other hand, the standardization of this technology facilitate its maintenance due to the existence of spare parts in the country.
5 | Printing promotionals | ATRIO |  | 6483 | 6483 | Only one offer. This is the only one national supplier authorized to offer/sell the referred service to international cooperation projects.
6 | Vehicle (2 small trucks) (Purchase abroad) | WOMY EQUIPMENT SUPPLY | 68191.34 | 76457.13 | 76457.13 | Addendum to an ongoing contract (Refer to Item 6)
7 | Agriculture tools; Office materials and furnitures (Purchase abroad) | BM GLOBAL | 23167.49 | 25126.92 | 25126.92 | Addendum to an ongoing contract (Refer to Item 7)
8 | Working clothes (Purchase abroad) | LUSAKA | 49134.69 | 51994.32 | 51994.32 | Addendum to an ongoing contract (Refer to Item 8)
9 | Printing promotionals | ATRIO |  | 3310.1 | 3310.1 | Only one offer. This is the only one national supplier authorized to offer/sell the referred service to international cooperation projects.
10 | Computer Equipment (Purchase abroad) | KAPAN INT. |  | 25061.66 | 25061.66 | The second best bidder in the process of Item 34 is contracted to purchase the goods not delivered by the winner of the process.
11 | Office remodeling | EMPRESA GALERIAS DE ARTE GENESIS |  | 13557.28 | 13557.28 | Only one offer. This is the only one national supplier authorized to offer/sell the referred service to international cooperation projects.
12 | Fuel to support project activities | FINANCIERA CIMEX, S.A. |  | 12022 | 12022 | Only one offer. This is the only one national supplier authorized to offer/sell the referred service.
13 | Audit services (audit period Jan-Dec 2015) | KPMG ACCOUNTANTS B.V. |  | 7618.38 | 7618.38 | Direct Contract signed UNDP Cuba, for the 2015 audit excersice of selected NIM Projects. Approved under the recommendations of the Advisory Committee on Procurement.
14 | Office materials (Purchase aborad) | INTEL LABORATORY INVESTMENT S.A |  | 3064.86 | 3064.86 | An UNDP Long Term Agreement (LTA) was used
15 | Clima equipment (Purchase abroad) | IBERCUB |  | 4463.62 | 4463.62 | Only one offer. Six suppliers was invited and was received only one offer, due to the small quantity of goods requested.
16 | Spare parts for Suzuki Motorcycles | MAREGINA INVESTMENT INC |  | 9452 | 9452 | Only one offer. This is the only one national supplier authorized to offer/sell the referred good.
17 | Printing promotionals (Purchase aborad) | JP IMPRESORES |  | 15673 | 13728.45 | Best responsive offer.
|  | ALINA INTERNATIONAL S.A |  | 13728.45
|  | GRUPO URANO |  | 16796.39
18 | Mobile Audio Equipment (Purchase aborad) | KAPAN |  | 37426.29 | 6749 | Best responsive offer.
|  | SANTA MONICA |  | 10601.85
|  | INTEL LABORATORY INVESTMENT S.A |  | 10281.71
|  | INTEL LABORATORY INVESTMENT S.A |  | 6748.74
19 | Printing promotionals (Purchase aborad) | JP IMPRESORES |  | 5953 | 5776 | Best responsive offer.
|  | ALINA INTERNATIONAL S.A |  | 11360
|  | GRUPO URANO, S.A |  | 5776
20 | Firefighting equipment and supplies (Purchase abroad) | CONSORCIO VERACRUZ |  | 55545 | 44582.25 | Best responsive offer.
|  | COMERCIAL FIGUEROA |  | 44582.25
|  | AVANTECH |  | 44830
|  | GIRASOL OVER SEAS |  | 61119
|  | UNIVEX |  | 50836.5
21 | Tires (Purchase abroad) | COMAL |  | 18905.1 | 8038 | Best responsive offer.
|  | COLVAZCA |  | 8038
|  | SUPPLY INC |  | 25837.26
|  | CONSORCIO VERACRUZ |  | 13463.58
22 | Vehicles (jeep) (Purchase aborad) | WOMY EQUIPMENT SUPPLY | 44250.59 | 51393.55 | 51393.55 | Best responsive offer (both offers are consolidated into a sigle contract. It represented savings in transportation for $ 1,348.00 )
|  | BRYTSIDE |  | 64231.4
| Vehicles (small bus) (Purchase aborad) | WOMY EQUIPMENT SUPPLY | 29089.66 | 34566.77 | 34566.77
|  | BRYTSIDE |  | 43945
|  | ALINA INTERNATIONAL |  | 58100
23 | Bicycles (Purchase aborad) | SUPLAY INC. |  | 20829 | 20829 | Best responsive offer. The final value was increase due to the request of an additional item.
|  | COMAL |  | 25249
|  | GRUPO URANO | 25430 | 28224
|  | COMERCIAL FIGUEROA |  | 32326
|  | CONSORCIO VERACRUZ |  | 31848
|  | VINEMA |  | 32306
24 | Working clothes (Purchase abroad) | UNIVEX |  | 26687.65 | 26687.65 | Best responsive offer.
|  | AVANTECH |  | 50827.7
|  | QUATTRO EFFE S.R.L |  | 30850
25 | Spare parts for vehicles (Purchase abroad) | TOYOTA GIBRALTAR STOCKOLDINGS LTD | 1,264,464 YEN | 12071.25 | 12071.25 | An UNDP Long Term Agreement (LTA) was used
26 | Motorcycles (Purchase aborad) | CARIBE-MAR |  | 34802.62 | 18968.84 | Best responsive offer
|  | CONSORCIO VERACRUZ |  | 22624.02
|  | MAREGINA INVESTMENT INC |  | 18968.84
27 | Supplies for forest nurseries (Purchase aborad) | COLVAZCA |  | 25127 | 20101 | Best responsive offer.
|  | GRUPO URANO, S.A |  | 20101
28 | Motor for sea craft (Purchase aborad) | BM GLOBAL |  | 14042 | 14042 | Only one offer. After 2 bidding processes, no offers were received. Taking into account the technical complexity of the motor, the manufacturer of the sea craft recommended to contact the provider BM Global. The offer provided by BM Global was satisfactorily evaluated by the specialists.
29 | Vehicle (2 trucks) (Purchase aborad) | ALINA INTERNATIONAL |  | 152470 | 143000 | Best responsive offer.
|  | WOMY EQUIPMENT SUPPLY | 135994.94 | 150937.78
|  | BRYTSIDE |  | 143000
30 | Vehicles (3 small trucks) (Purchase aborad) | WOMY EQUIPMENT SUPPLY | 106374.42 | 118062.62 | 118062.62 | Best responsive offer.
|  | BRYTSIDE |  | 137710
31 | Sea craft and auxiliary boats (Purchase aborad) | CEPRONA |  | 5761.89 |  | Only one offer. This is the only one national supplier authorized to offer/sell the referred good.
32 | Tractors and traillers (Purchase abroad) | GAMMA EXPORT SRL | 111048.44 | 124076.469 | 124076.469 | Standardization (Refer to Item 4)
Note 1: The UNDP country office corporative service Agreement with Cubanacan Travel Agency was used. Whithin this framework a minimum of 3 quotations was requested for each case. An analysis was made and the best responsive (meeting technical requirements and most economic) quotation was selected.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
1 | Extreme climatic events (storms, droughts) and fires, affecting plant survival rates. | Environmental | Impact: Low (2) Probability: High (4) | Medium | Although extreme climatic events were not reported during this period, a proactive measures were applied to reduce the risks. For example: 1.1-The following actions were included in the annual disaster reduction plans of forestry enterprises, being periodically assessed. -There was desing a package of management alternatives for the restoration, taken into account the seasonal. -The Contingency plan have established criteria to reorder project activities depending on the priorities established for recovery of damaged areas. -There were established a propagation areas / nurseries that provide back-up propagules that can be used as soon as possible to restore damaged areas. 1.2- Fire protection plans are reviewed and updated annually. Also it has planned preparation to face the start of the fire protection campaign and take appropriate measures. - There was defined with the main actors a firefighting Protection Plan that includes specialized technical measures (cleaning of channels and construction of trails) and actions for prevention and awaressnes to the population and communities. - There was implemented an effective fire detection and control system by the Forest Guard Corps and the local Government. 1.3-The implementation of a GIS-based monitoring system that allows performing a constant surveillance of weather conditions and mangrove state.
2 | Climate change related changes in tree phenology affecting seed collection and nursery activities. | Environmental | Impact: Low (1) Probability: Medium (3) | Low | Some action were conducted, as part of the adaptation measures plan to reduced the risk, these are: 2.1-A package of management alternatives for seasonal restoration has been prepared. 2.2-The implementation of a monitoring system allows periodically monitoring weather conditions and mangrove state. 2.3-Nurseries are being created to maintain a reserve, taking into account seed collection activities based on previous experiences.
3 | Variations in commitment to EBA among policy makers. | Institutional | Impact: Low (2) Probability: Medium (3) | Medium | In order to ensure the government's understanding of EBA benefits, the project developed activities such as: 3.1-Development of a direct dialogue with the provincial, municipal and local governments. 3.2-Promoting awareness of EBA benefits among policy makers (including training for decision-makers on these issues). 3.3-Development of economic valuation studies for decision making.
4 | Slow equipment procurement processes in local Governments. | Institutional | Impact: High (4) Probability: High (4) | High | In order to support the procurement process, the following measures were taken: 4.1-The government and UNDP have been working closely, in order to leverage the capacities that have been created by the government and other international projects in the territory. 4.2-From the beginning, project activities that do not depend on imported resources are prioritized to make progress. 4.3-Mobilize national co-financing from local governments and economic sectors on those tasks that do not depend on resources acquired abroad Project activities have been included in the work plans of the governments, using the available resources at local level according to the priorities in the project goals. These activities have been monitored in different spaces. 4.4-Early development, approval and execution of procurement plans.
5 | Limited availability of inputs and equipment on national market. | Institutional | Impact: Medium (3) Probability: Medium (3) | Medium | In order to minimize this risk, the following steps were taken to accelerate the acquisition processes: 5.1-Identified and implemented alternative measures, with the support of UNDP and MINCEX, to facilitate the import of material resources required by the project. 5.2-A periodic monitoring of the execution state has been established by MINCEX, UNDP and CITMA with a view to achieving the required effectiveness in these processes. 5.3-Conciliate the project annual budget with the national measures established in the national economic planning process. 5.4-Increase the management capacity to identify new and potential providers that facilitate the acquisition of material resources in the country.
6 | Short term economic and livelihood considerations outweigh medium term benefits of EBA actions in priorities of community members. | Institutional | Impact: Low (2) Probability: Low (1) | Low | In order to mitigate the impact of this risk, the following measures were adopted to raising awareness of economic benefits of EBA actions among community members. 6.1- The possible economic incentives linked to the Project were identified jointly with the local residents and with the productive sectors. 6.2- Groups of people in the municipalities have been trained in topics related to economic valuation.
7 | Short term political considerations outweigh medium term benefits of EBA actions in priorities of members of local institutions | Institutional | Impact: Low (1) Probability: Low (1) | Low | With the purpose of positioning the benefits of the EBA the following actions were developed: 7.1-A strong awareness-raising work has been developed, identifying the possible sources of sectorial national revenues for the creation of incentives and their possible inclusion in local development strategies; but the development of local initiatives is an emerging process in the country and its stabilization requires time. 7.2-Groups of people in the municipalities are being train on economic valuation topics. 7.3-The Project has been raising awareness about the benefits of EBA actions in mangrove forests within decision-makers at the provincial and municipal levels.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
8 | N/A
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Environmental Risk - Proactive measures were applied to reduce environmental risks. The negative impact has been low and it did not affect the Project performance in the reported period, but a high probability of occurrence of these events in the intervention area still remains, given the geographical location of Cuba in the Caribbean region, one of the most active for the occurrence of hurricanes and tropical storms, the significant increase in intense drought events and the occurrence of fires in the area. - Climate Change relation to plant species phenology is a long term process, being necessary to monitor and follow up its behavior, because it involves a high degree of uncertainties. Institutional Risk - Measures applied to mitigate the risks related with the level of commitment shown by local governments have been effective during this period. - With prior coordination, project activities have been included in the work plans of the governments, using the available resources at local level. According to the priorities in the Project goals, these activities have been monitored in different spaces. - A strong awareness-raising work has been developed, identifying the possible sources of sectorial national revenues for the creation of incentives and their possible inclusion in local development strategies. The development of local initiatives is an emerging process in the country and its stabilization requires time. - As for the limited capacities for acquisitions, the transition to the new importing company implied the establishment of legal aspects that included the contracting process, which requires time to adjust to the new conditions. A periodic monitoring of the execution state has been established by MINCEX, UNDP and CITMA with a view to achieving the required effectiveness in these processes. Procedures will be defined to speed up the acquisitions and negotiate the delivery, in order to achieve the expected execution levels. - Besides, in spite of the adopted measures, offers in the national market remain limited, because of the lack of supplies and limited offer capacities. - The possible mobility of the Project human resources did not affect its performance in the reported period, but its probability of occurrence continues to be high, since it depends on external forces and conditions. Though the necessary measures to decrease this risk are being taken. Social Risk - Possible economic incentives were identified jointly with the local residents linked to the Project and with the productive sectors. Groups of people in the municipalities have been trained in topics about economic valuation. - The negative impact has been low and the probability of occurrence stays low, thus it did not affect Project performance in the reported period.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. |  | Carry out expeditions in different seasons to assess the restoration works and monitor the intervention areas. |  | 2 field trips were carried out in mangrove swamp areas of Mayabeque and Artemisa provinces, to assess the restoration works on the coastline front, involving the participation of forestry workers, technicians and specialists from SEF, IES, INAF. | S
2 field expeditions were carried out to evaluate the success in the growth/survival of propagules and other indicators, such as soil and salinity, by means of permanent lots in Melena, including the participation of forestry workers, technicians and specialists from SEF, IES and INAF.
|  |  | Develop training activities and advisory to technicians, forestry enterprise workers and specialists on management and monitoring of ecological restoration in Artemisa and Mayabeque. |  | 2 lectures on mangrove swamp restoration were delivered by an international expert to the technicians, forestry enterprise workers and specialists from several institutions and advising on ecotechnologies and on the development of corresponding reports, procedures and manuals.
1 exchange of experiences was developed with an international expert on restoration in the working areas and a report was prepared, including technical recommendations and immediate actions for gradual implementation by the working group.
1 field trip to the recovered mangrove swamp areas in Guantanamo Bay was conducted to exchange experiences on mangrove swamp restoration in other regions of the country, with the participation of specialists from the restoration technical group and the forestry brigades in the territory.
2 training courses on the use of GIS software (SAGA and Quantum GIS) were provided to technicians from the forestry enterprises and specialists from several institutions, for their application in the restoration and monitoring of coastal ecosystems (mangrove swamp, reefs, beaches) through the analysis of geospatial information and the use of remote sensing.
|  |  | Presented and approved the technical projects for the activities that will be carried out in the areas according to the foreseen objectives for every year of the project. |  | 13 technical projects to carry out restoration activities during the second year were approved by the State Forestry Service, 8 in Artemisa province (4 in Güira, 427.7 ha, and 4 in Alquizar, 194.0 ha) and 5 in Mayabeque province (3 in Batabano, 150 ha; 1 in Melena, 130.5 ha; and 1 in Güines, 35.1 ha).
10 Technical projects are in preparation for restoration activities during the third year, 7 in Mayabeque province (2 in Batabano, 241.3 ha; 3 in Melena, 198.9 ha; 2 in Güines, 58.1 ha), and 3 in Artemisa province (1 in Artemisa, 46 ha, and 2 in Güira, 531 ha).
|  |  | Begin the recovery of 316.0 ha of red mangrove and maintain 85.0 ha from the first year along shore between Batabano and Punta Mora, combining natural regeneration and direct planting. |  | 316.0 ha of red mangrove (Rhizophora mangle) were improved, combining works for promoting natural regeneration with direct planting in the land-sea direction, along the coast of Güines, Melena and Batabano municipalities in Mayabeque province.
3.6 km of protection barriers were built in eroded areas with materials from the zone along the coastline.
3.1 km of gutters and channels were recovered by means of manual dredging (1.5 km in Melena, and 1.6 km in Batabano) benefitting 57 ha in Melena and 64 ha in Batabano.
Maintenance and cleaning works were carried out in 9.8 km of channels and gutters, which had begun during the first year in Melena, Batabano and Güines to facilitate freshwater and seawater exchange, benefitting 136.0 ha.
Maintenance works were carried out in 9.7 km, which had begun during the first year of the project as a specialized measure for the protection against fires and to facilitate the hydrological flow in the area.
Maintenance and replacement of 10% of the propagules that had been affected or lost were carried out in 27 ha of the first year (7.0 ha in Batabano; 10.0 ha in Melena; 10.0 ha in Güines).
|  |  | Begin the recovery of 618,7 ha of mangrove swamp ecosystem and maintain 143.8 ha from the first year between Majana and Surgidero de Batabano. |  | 618.7 ha of red mangrove were improved by means of works to promote natural regeneration, and by direct planting in selected sites of the coastal zone, in Cajio, Güira de Melena Municipality, in Artemisa province.
Maintenance works were carried out in 10.0 km of narrow paths that had begun during the first year of the project in Güira, as a specialized measure for the protection against fires and to facilitate the hydrological flow in the area.
9 furrow drains (6 in Güira and 3 in Alquizar) and 0.7 km of natural gutters were cleaned up, thus facilitating water exchange in the South Dike.
Maintenance works were carried out in 2 furrow drains and 0.8 km of natural gutters that had been cleaned up during the first year in Güira.
Maintenance and replacement of 10% of affected or lost propagules were carried out in 13.9 ha improved during the first year.
|  |  | Implement a monitoring system to assess and follow up ecological restoration actions in the intervention areas. |  | A periodic monitoring system was implemented at different space and temporal scales to follow up the developed and expected changes in the intervention areas, on the basis of working protocols and through geospatial information analysis using remote sensing.
A GIS system was established with information to determine the changes occurred in the intervention areas and the processes that moderate them, for restoration purposes.
| Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. |  | Diagnose the state of swamp woodlands with management and monitoring proposals by site. |  | 2 field trips were carried out, 1 in Mayabeque province and 1 in Artemisa province, to evaluate the state of swamp woodlands by site, including the participation of forestry workers, technicians and specialists from SEF, IES and INAF. | MS
2 field trips were carried out, 1 in Mayabeque and 1 in Artemisa, to set up monitoring lots, according to the proposed protocol for these ecosystems that allows evaluating structural, flora and physical parameters, including the participation of forestry workers, technicians and specialists from SEF, IES and INAF.
A diagnosis of the state of swamp woodlands was conducted for sites with management proposals and adaptation measures, starting from the historical information gathered in the herbarium and from field trips.
A flora inventory and a list of native species were completed by site, including recommendations for their management and conservation with a view to forest enrichment.
20 IAS were identified by site, with proposals for their management and control.
|  |  | Present and approve the technical projects for the activities that will be carried out in the areas according to the foreseen objectives for every year of the project. |  | 10 technical projects to carry out the restoration activities of the second year were approved by the State forestry service, 5 in Mayabeque (2 in Batabano, 212.2 ha; 2 in Melena, 120 ha; 1 in Güines, 75 ha) and 5 in Artemisa (3 in Alquizar, 728.9 ha; 2 in Güira, 162.2 ha)
10 technical projects are in preparation for the third-year restoration activities, 5 in Mayabeque (2 in Batabano, 212.7 ha; 2 in Melena, 120 ha; 1 in Güines, 75 ha), and 5 in Artemisa (3 in Alquizar, 728.9 ha; 2 in Güira, 182.2 ha).
|  |  | Begin the enrichment and restoration of 1301.3 ha of woodlands along the landward limit and maintain 99.9 ha from the first year between Majana and Punta Mora. |  | 407.2 ha of swamp woodlands in Mayabeque and 911.1 ha of forest in Artemisa were benefitted with works for promoting natural regeneration, by means of site preparation and enrichment of native tree species for direct planting or nurseries.
Maintenance works of narrow paths were carried out in 3.2 ha for protection against fires.
Under control and eradication 4 exotic species in 13 ha of the effective intervention area. Under control and eradication 3 exotic species (Terminalia catappa, Mimosa pigra, Acacia farnesiana) in 7 ha of Melena, Mayabeque, and 1 species (Casuarina equisetifolia) in 6 ha of Güira, Artemisa.
10 000 seedlings for woodland enrichment with native species were produced at the nursery in Güines Municipality.
A micro-nursery of 1.5 ha was set up in Cajio, Güira Municipality, and 32 000 seedlings were produced for woodland enrichment with 4 native species.
Maintenance works were carried out in 99.9 ha from the first year between Majana and Punta Mora.
| Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. |  | Implement an information system as a tool for coastal zone planning and development plans. |  | Information on CC effects, threats to coastal ecosystems and actions in the Project area is compiled in databases by means of Geographic Information System (SIG), for its use by different government structures and to contribute to the integrated planning of coastal ecosystems, ensuring that it is compatible with EBA. | MS
|  |  | Analyze and assess Project actions and their gradual integration into local strategies and development plans. |  | Communication products are being prepared about EBA strategic importance for local development.
Development strategies of involved territories are being reviewed, to assess CC coping approaches and include EBA in municipal and provincial local development strategies, as well as in the Territorial Development Indexes.
There were identified EBA and CC topics that should be incorporated into local development plans and strategies by municipal and provincial governments.
The “Workshop for awareness-raising and articulation of actors in relation to the incorporation of EBA approaches into local development strategies” was developed with the participation of specialists and municipal coordinators from Artemisa and Mayabeque.
|  |  | Training representatives of provincial and municipal governments on taking EBA into consideration and Promote the participation of productive sectors to encourage and maintain Project actions. |  | Government representatives were trained in the two provinces and 6 municipalities, as well as officials of political organizations, like PCC and UJC, and delegates of 4 districts, by means of exchanges and debates of materials (pamphlets and videotapes) about CC and adaptation problems in these territories.
The second edition of the Diploma course on “Local Development and politically responsible persons” was carried out for government representatives of Parliament and the Administration Council in 3 municipalities (Melena, Güines and Artemisa), incorporating into the learning module on "strategic ecosystems" EBA topics to present local development projects with that dimension.
Nine (9) exchanges were carried out with the productive sector and government entities that operate in the area, 4 of them with the agricultural sector in Artemisa, 2 with the fishery sector in both provinces to promote that activities conducted and development plans do not undermine Project actions.
| Local communities increase the knowledge and develop skills to participate in EBA activities |  | Establish and strengthen local volunteer groups. |  | Promotion activities were carried out for the conformation of volunteer groups in the 6 municipalities of both provinces. | S
2 groups of volunteers were created and trained: one in Surgidero de Batabano (with 16 members, 9 of them are women) and one in Cajio (with 10 members, 2 of them are women).
|  |  | Build capacities among key community members by stimulating them and providing technical advisory. |  | 17 coastal communities are involved, 9 started in the first year and 8 of recent incorporation: 3 in Mayabeque province (2 in Güines, 1 in Melena) and 5 in Artemisa province (1 in Güira, 2 in Alquizar, 2 in Artemisa), conducting activities to increase awareness levels, and the commitment of local communities, to guarantee the effectiveness and sustainability or restoration works.
Baselines and indicators have been created to measure knowledge increase of community people on coastal zone state and the importance of applying EBA measures.
A participatory diagnosis of environmental communication was carried out in the 6 intervention municipalities, to implement an info-communicational management system that supports Project objectives and guarantees the exchange of information, experience and knowledge among people and entities that participate in the implementation and/or benefit from the actions carried out.
2 neighborhood debates were held in 2 districts of Batabano municipality, in Mayabeque province, including the participation of 46 members of the communities.
1 training was carried out for members of Batabano coastal community on CC and the importance of mangrove forests, participating 29 people.
3 training classrooms are open and in operation: 2 in Artemisa province and 1 in Mayabeque province, carrying out different actions that include exchanges with community authorities and actors (Governments, schools and inhabitants aware of the Project objectives and actions).
|  |  | Incorporate new schools in the territories to work on EBA and CC issues in a cross-cutting manner in the syllabus and extracurricular activities. |  | 26 schools are incorporating adaptation topics, 10 started in the first year and 16 primary and secondary schools have been incorporated: 6 in Mayabeque province (2 in Batabano, 2 in Melena del Sur and 2 in Güines municipality), and 10 schools in Artemisa province (5 in Artemisa, 2 in Alquizar, 3 in Güira municipality), as well as 3 municipal universities.
11 schools have developed “Interest Circles” (gatherings to stimulate vocational interest in students) on mangrove forests, including plan of activities and methodological work: 5 in Artemisa, and 6 in Mayabeque.
62 professors have been trained in 6 schools of Artemisa province, and 10 professors in 1 school of Mayabeque province, through the methodological preparation in adaptation and EBA topics for developing the syllabus.
A pilot experience of an educational-communicational workshop was carried out in Surgidero de Batabano and in Cajio, for its generalization in other schools.
The first edition of “Living Mangrove Forest” Contest (“Manglar Vivo”, in Spanish) was held with more than 180 participants, 168 of them students; prizewinning works were exhibited in Surgidero de Batabano community.
|  |  | Training local and provincial mass media in EBA topics. |  | A training workshop was developed for mass media professionals, with the participation of 16 persons from Artemisa and 25 from Mayabeque.
|  |  | Produce and disseminate audiovisual materials to promote the Project at national and local levels. |  | The documentary film “Change of Time” that describes the Project purpose and expected benefits was published in 3 languages and shown on TV with national and international reach.
A 24-minute documentary film dedicated to the socio-environmental problematic of the Project intervention area was produced and presented for its discussion in Batabano municipality, and in high-rating TV programs with national and international reach (round table, morning show, “On Time” (“A Tiempo”) programs, local broadcasting stations).
2 juvenile national TV programs called “Route 5” (“Ruta 5”) were developed, with 25-minute duration, dedicated to disseminate the Project purpose and expected benefits.
2 local TV programs were produced in Mayabeque, and 11 local radio programs were broadcasted, 6 in Mayabeque and 5 in Artemisa, all dedicated to the topics addressed by the Project.
1 article on Project actions in the territories was published in the printed press with national reach.
Materials have been designed and are being produced as part of the communication campaign: posters, stickers, radio spots, circulars, information spots, educational kits, calendars, adhesive labels for dissemination and raising awareness in the local population.
2 brochures, out of 5, have been prepared and are being reviewed, as part of the educational kit: one on CC and the other on mangrove forest ecosystem; a brochure on marsh forest is in preparation.
1 video clip was produced and published on TV with national and international reach and in the social networks, as part of the communication campaign.
|  |  | Systematize experiences and lessons learned. |  | 2 products for the socialization of best practices were prepared and published:
1st issue of Living Mangrove Forest bulletin. 1 DVD gathering the experience from educational-communicational workshops with 6th-grade students of BacLy school in Batabano Municipality.
1 DVD was published, including the lectures imparted by the international consultant on mangrove forest restoration.
The GIS system was set up and a procedure was defined for monitoring the on-site activities that are carried out in selected places and the key ecosystems functions (intervention areas, hydrological and geomorphological conditions, coastal erosion rate, seawater intrusion and coastal flood events).
| Consolidated Information on the costs and benefits of EBA available for decision makers and planners. |  | Training specialists in economic valuation methods. |  | 4 training actions on economic valuation of ecosystem goods and services were conducted for specialists from different organizations and government representatives, 2 at provincial and 2 at municipal levels, with participatory methods. | MS
|  |  | Gather the necessary information to calculate the cost/benefit ratio in the intervention area. |  | Maps were prepared and necessary information was gathered for the economic valuation study: value of human settlements, population, fixed assets, land use, forest patrimony, flora and fauna, volume of agricultural production, volume of livestock farming and fishery production, indicators of the population's standard of living in the area of greater influence for the Project within the 6 municipalities, to evaluate the current state of local coastal zone. This analysis highlights the economic losses that will occur should the flood scenarios forecasted for 2050 and 2100 be accurate.
| Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. |  | Implement the methodological guide to integrate EBA into inspections that are being prepared in coordination with local actors. |  | A methodological guide with EBA approach was prepared and is being implemented for inspection visits by provincial and municipal governments to the coastal areas. | S
|  |  | Training activities and review of application of the regulatory framework relating to coastal zone protection in the intervention area. |  | 3 training actions for the prevention and fighting of forest fires were conducted: 2 in Artemisa, for members of the professional brigade (16 men) and the specialized brigade of the Forestry Unit in Cajio (10 men), and 1 for the specialized brigade of Batabano, in Mayabeque.
113 prevention actions were carried out, including talks and conferences in outlying communities or inside the Project intervention area, in coordination with the local organizations of the People’s Power, as part of the population's preparation to cope with the critical period of forest fire occurrence and the protection of natural resources.
Regulations were revised at local and provincial levels, and a legislative compendium regarding the protection and sustainable management of coastal ecosystems was finished.
3 training activities were carried out by territorial authorities in coastal areas of Artemisa and 3 in Mayabeque, with regard to the regulatory framework, protection and sustainable management of coastal ecosystems.
|  |  | Carry out at least three integral inspections to Project areas involving the participation of inspectors from CITMA, CGB, fishery and SEF. |  | 83 maritime journeys along the coast and 180 on land were carried out in function of the surveillance and protection of natural resources, inside the Project intervention area.
3 integral inspections to the Project intervention areas were carried out, with the participation of regulatory authorities: 1 in Mayabeque, involving the Coastguards, PNR, CGB, SEF, and 2 in Artemisa: 1 in Guanimar Beach, Alquizar Municipality, and another in Majana Beach, Artemisa Municipality, where provincial CITMA representatives, the Head of Alquizar Forestry Unit and CGB participated.
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sheila Chang
| Email: | sheila@ama.cu
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Component 1. During this period 1145 ha of mangrove along the coast (total area) have been benefited by direct seeding and / or work to favor natural regeneration. Enrichment of 1401.2 ha (total area) of inland forest has been initiated by sowing native species and eliminating or controlling 4 alien invasive species. The establishment of a monitoring system at different spatial and temporal scales, using remote sensing, allows following the restoration work and the mangrove health indicators in the intervention areas. The delay in the arrival of specialized equipment and transportation necessary for the recovery work in these ecosystems has delayed activities in the intervention areas especially in the swamp forests, for which it will be necessary to optimize work planning according to seasonal periods, Accessibility to available areas and resources. Component 2. We have been able to involve more people training and training in 17 communities, 26 schools, 2 groups of volunteers, and 4 training rooms in topics related to CC, ABE, protection and integrated coastal management. A strong diffusion campaign, with different communicative supports, has facilitated training and sensitization of project stakeholders, seeking solutions to mangrove problems and raising the understanding of protecting these ecosystems. Promoted activities to articulate actors around the incorporation of ABE approaches in local development strategies and generated information in databases through GIS on the effects of CC and threats to coastal ecosystems for 2 provincial and 6 municipal governments. Strong work identifying possible economic incentives and their inclusion in local development strategies has been carried out, however, it is a process that begins to take place in the country and its stabilization requires time. These project activities are having a major impact on local governments, but it is necessary to achieve greater ownership and commitment in the territories, through the planning and monitoring of their activities, according to the new governance structures in Artemisa and Mayabeque. Component 3. Completion of information for the baseline of economic valuation studies of the entire coastal strip, and 4 training 2 in provincial governments and 2 in municipal governments for specialists from different institutions. The lifting of the information for the economic evaluations of the EBA costs has taken more time than planned, and it will be necessary to continue the training at the local level to consolidate the working groups. Three training courses were carried out for the prevention and combat of forest fires and three for the protection and sustainable management of coastal ecosystems. The guide developed for the inspections, are in validation as a working instrument for the provincial and municipal governments. The 3 integral inspections carried out, the maritime and terrestrial routes have been favorable to the process of restoration of the ecosystem and the sustainability of the AbE with the alliance of the Ranger Corps, Border Guards, State Forestry Service and the Departments of Fisheries.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems. |  | Increased: - The red mangrove area along the coast (between Batabano-Punta Mora). - The restored mangrove ecosystem area (Majana-Surgidero de Batabano), and - Enriched border forest area. Started the control and eradication of IAS. |  | During the period it was possible: - to establish 418.5 ha of red mangrove between Batabano-Punta Mora; - to improve the habitat of 726.5 ha of mangrove ecosystem, with the accomplishment of works to favor hydrological conditions; and - to benefit and enrich 1401.2 ha of bordering forest, with native species. It was also possible to propose and implement actions for the management and control of identified IAS. Despite these results, it is recognized that important technical tasks could not been realized in the period, due to the significant delay in the arrival of the means of transport and the specialized equipment required by the project to carry out the restoration work in these ecosystems. The greatest afectation was reported in the swamp woodlands. | MS
| Component 2. Integrated and participatory management of coastal ecosystems to increase resilience to climate change. |  | Increased: - The number of provincial and municipal development plans that effectively incorporate the EBA; - The number of provincial and municipal governments with knowledge management systems implemented incorporating EBA; - The number of community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues; - The number of local schools with curricula incorporating adaptation to climate change; and - The number of awareness materials on climate change adaptation issues produced by local media. |  | There were planned and implemented a wide of activities to continue increasing the government’s awareness level on the importance of coastal ecosystems and the need to effectively incorporate the EBA approach into the development plans of the provinces and municipalities, as an adaptation strategy to climate change. Despite of this, it is recognized that the expected progress in the design and implementation of knowledge management systems (required by governments) with this aspects incorporated has not been achieved. The progress in this task is considered essential for the achievement of the final goals of this component. A wide publicity campaign was also developed through different means of communication (27 actions), aimed at highlighting the need to protect coastal ecosystems. There were prepared and disseminated various materials to raise awareness of target audiences: electronic bulletin, a package of audiovisual products on the mangrove ecosystem, a DVD on restoration of mangrove forests and documentaries, TV and radio programs. | MS
| Component 3. Establishment of a favourable enabling environment at regional level for the effectiveness and sustainability of adaptation investments. |  | Increased the frequency of: - Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; - Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. Also, the number of studies and methodologies carried out to estimate the cost - benefit ratio of the ABE approach, available to planners and decision makers, is increased. |  | A methodological guide with EBA approach was provided to the governments and coastal communities in order to increases its technical knowledge. There was also made available a legislative compendium related to the protection and sustainable management of coastal ecosystems. These tools are already used by the authorities during the inspection visits to the coastal areas. There is progress in training in economic valuation of ecosystem goods and services in selected areas and key services, and also in the preparation of maps with the necessary information to carry out economic valuation studies. However, at this stage, studies and methodologies to estimate the cost-benefit of the EBA approach have not been completed and made available to planners and decision-makers. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gricel Acosta Acosta
| Email: | gricel.acosta@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its second year of implementation, the project shows progress in meeting its main milestones. This trend brings it closer to meeting the project's targets and final goal. This has been possible due to the strengthening of coordination and commitment between the project team and the actors involved, in particular: the governments of the Artemisa and Mayabeque provinces and forestry companies. There is a positive progress trend at the objective level, due to the restoration and rehabilitation work has already benefited 2546 ha of coastal plant formations (1145 ha of mangrove and 1401.2 ha of bordering forests). In addition, there were developed awareness-raising activities involving provincial and municipal governments and a growing number of communities directly affected by coastal flooding. At component level the following is highlighted: Component 1. The results show a positive trend towards the reduction of the impacts of coastal flooding becauses is already improvemented 1145 ha (by direct seeding and / or reinforcement of natural regeneration) of mangrove. However, although it have been working on the enrichment of bordering and swamp forests, the expected progress for this period has not been achieved due to the delay in the beginning of some technical activities (eg: nursery creation, access and preparation of areas, etc.). The main cause was not having been able to count on the specialized media to access and work in those areas. It is recommended to include in the 2017 plan actions aimed at recovering this delay so as not to compromise the expected final result. Component 2. There is progress towards achieving integrated and participatory management of coastal ecosystems to increase resilience to climate change, due to the intense awareness-raising and communication campaign has contributed to the increased level of involvement and commitment of local actors with the restoration and conservation of mangroves, in particular the governments and the population. This will contributes to ensuring the sustainability of the results achieved in Component 1. Despite of, there is considered it has not yet been possible to provide to the local authorities an integrated management systems that incorporate these knowledge; this step is considered essential for the achievement the targets of this component. It is recommended that in the projection of work of the third year of implementation, actions aimed at achieving compliance with this indicator are increased. Component 3. While it is recognized that data collection for EBA cost-effectiveness assessments is a novel process in the country and requires time and trained staff at the local level, we appreciate that progress is being made toward the establishment of a favorable environment that ensures the effectiveness and sustainability of adaptation investments. In this sense, a map with the information required to carry out economic valuation studies was elaborated; as well as a methodological guide with an EBA approach. This guide is already used by the government in the execution of the inspections on coastal areas. The number of people trained in economic valuation of ecosystem goods and services has also increased. However, the studies and methodologies to estimate the cost-benefit of the EBA approach have not yet been made available to planners and decision-makers, reflecting some delay in the reached of this indicator. It is recommended special attention be paid to the progress of this aspect in the planning of the third year of implementation. Critical risk: The process of change from the national importing company to the company EMIDICT (belongs to CITMA) has had a negative impact on the implementation of the project; specially in Component 1, due to the arrival of the equipment has been delayed. The impact has not been greater thanks to the adaptive capacity shown by the project team and the support provided by forest companies and the government. The MINCEX, CITMA and PUND continue to implement coordinated actions to support and accelerate the procurement process.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience of populations living in the coastal zone ofthe provinces to Mayabeque Artemis and the effects of climate change. | I. Areas with high rates of health and the conditions of the mangroves (soil and salinity of the water, the density of the canopy, the existence of local regimes of protection). | Coastal ecosystems that cover 7 318 ha are degraded, have excessive levels of salinity due to seawater intrusion and the obstruction of channels and have a limited protection regime. | The project has been working on the implementation of a monitoring system at different spatial and temporal scales to assess and monitor mangrove forest health indices and restoration work, according to established protocols, as well as data collection (soil and salinity of the water,tides, meteorological data, the density of the canopy, hydrological data) at different seasonal periods. The work will be carried out within a detailed framework of spatial and operational planning which has been developed by the IES and the forestry enterprises, including Geographic Information System (GIS) databases and maps based on detailed satellite imagery. The project has established 1145 ha (total area) of mangrove along the coast doing works to promote mangrove forest ecosystem restoration, and the enrichment of 1401.2 ha (total area) of inland forest through work for promoting natural regeneration and planting native species. In connection with the final goal of the project this indicator is at 34.7%. | 7 318 Ha (total area where will be carried out reforestation of mangrove, the restoration of the mangrove ecosystems, and the enrichment of the forested areas inland) Note: the rates of coastal mangroves and wetlands must be nominated in the methodological documents to be developed at the start of the project.
| II. Numbers of people (men and women) with reduced vulnerability due to proximity of functioning mangrove forest and wetland ecosystems. | 17 524 People in 47 communities are directly affected by coastal flooding. | Awareness raising activities about the project have been conducted with the local government and inhabitants of local communities. These included coastal flooding, mitigation measures, mangrove forest restoration, and opportunities that the Project can bring to the communities to implement national policies on climate change adaptation. Training activities on response and adaptation to CC impacts have been conducted, focusing on 17 coastal communities (34 %) with 20014 inhabitants 57 %), of which at least 45% are women. 2 provincial and 6 municipal groups were trained (88 people), with at least 15 members from Artemisa and Mayabeque municipalities, and they review CC adaptation topics in the development strategies, to include EBA approaches. In 2016, the results of the National Population and Housing Census conducted in 2012 has been available for the Project team. In this Census, Districts were the smaller unit of information. This information was used to update the data regarding population, both baseline and final target. However, there were no found significant changes, so data reported in the first PPR are maintained. | 21 502 People (of which at least 45% are women) directly affected by the reduction of coastal flooding.
|  | 270,705 People are indirectly affected by the impacts of the phenomena associated with the CC on economic activities. | Awareness raising activities about the project have been conducted with the provincial governments, decision makers of selected productive sectors, and regulatory authorities. These included coastal flooding, mitigation measures, mangrove restoration and opportunities that the project can bring to the communities to implement national policies about CC adaptation. 2 provincial groups were trained, with at least 15 members from Artemisa and Mayabeque municipalities, and they review CC adaptation topics in the development strategies, to include EBA approaches. Note: During the period, access to the results of the National Census conducted in 2012 was achieved. This involves updating the population figures concerning the baseline and targets in relation to those initially included. | 270,705 People (at least 45% are women) benefit indirectly by the reduction of the impact of the phenomena associated with the CC on economic activitie.
| 1.1 Area (ha) of red mangrove is established along shore between Batabanó and Punta Mora. | 533ha | 418.5 ha have been planted with red mangrove propagules that are growing, thus encouraging natural regeneration along the coast. 32.4% of implementation in relation to the ultimate goal of the Project has been achieved. | 1290,6 ha of which 85% survived* (1097 ha) *Survival can only be measured 3 years after planting
| 1.2 Cumulative area of mangrove ecosystem restored between Majana and Surgidero de Batabanó. | 144ha | 726.5 ha of mangrove ecosystem has improved its conditions through planting native tree species and the restoration of hydrological conditions. 42.4% of implementation has been achieved in relation to the ultimate goal of the Project. | 1711,9 ha of which 85% survived* (1455,1 ha) *Survival can only be measured 3 years after planting
| 1.3 Cumulative area of landward edge woodlands restored and enriched. | 939 ha | 1401.2 ha of landward edge woodlands were enriched by planting native species and encouraging natural regeneration. 32.4% of implementation has been achieved in relation to the ultimate goal of the project. | 4315,5 ha of which 85% survived* (3668,2 ha) *Survival can only be measured 3 years after planting
| 1.4 Numbers of IAS management plans developed. | 0 | 20 invasive alien species (IAS) were identified by site, with proposals for control and management. 4 exotic species are under control in eradication process in 13 ha of the effective intervention area. | 1, covering 7,318ha
Outcome Indicator | 2.1 Numbers of provincial and municipal development plans that make specific provision for EBA. | 2 provincial and 6 municipal governments are preparing development plans that do not include EBA. | Development strategies were reviewed in 2 provincial and 6 municipal governments to assess whether they include EBA approaches in CC adaptation measures, as well as the Territorial Development Indices. | 2 provincial plans and 6 municipal plans
Government representatives and officials of political organizations were trained in 2 provinces and 6 municipalities, through exchanges and discussion of materials (brochures and videos) on CC-related impacts and adaptation in these territories.
9 exchange meetings were carried out with the productive sector and government agencies operating in the area to encourage them to ensure that the activities they undertake and their development plans do not undermine the Project's actions.
The learning module on "strategic ecosystems" was taught as part of the second edition of the Diploma Course on Local Development, for government representatives of the Assembly and the Administration Council in 3 municipalities (Melena, Güines and Artemisa).
Outcome Indicator | 2.2 Numbers of provincial and municipal governments with EBA-related knowledge management systems in place. | 0 | Outreach products on best practices were prepared: electronic bulletin “Living Mangrove Forest” (“Manglar Vivo”), pilot experiences of educational –communicational workshops with students from elementary schools in Batabano and Güira de Melena municipalities, packages of audiovisual products on the mangrove forest ecosystem in Cuba, and production of documentary films on chronicles or life-time stories. | 2 provincial and 6 municipal governments
A DVD was produced to disseminate knowledge to various target audiences about mangrove forest restoration, monitoring and recommendations for Cuba.
A monitoring system was established to follow up on the activities carried out on field sites at different spatial and temporal scales in the intervention areas, based on work protocols and using remote sensing.
Information was gathered and alphanumeric and spatial databases were developed for their use in integrated planning of coastal ecosystems, ensuring that it is compatible with EBA.
Outcome Indicator | 2.3 Numbers of community members (men and women) belonging to local voluntary groupsaddressing environmental and adaptation issues. | 0 | 2 groups of volunteers were created and trained: one in Surgidero de Batabano (with 16 members, including 9 women) and one in Cajio (with 10 members, including 2 women). | 1 group with at least 15 members (of which at least 45% are women) in four municipalities
A participatory diagnosis was conducted in 3 municipalities, to create a baseline and define indicators to measure knowledge progress in the communities on the state of the coastal area and the importance of implementing EBA measures, through the application of an info-communications management system that supports the Project objectives and ensure the exchange of information, experiences and knowledge between people and entities involved in the implementation and/or benefitting from the actions taken.
19 settlements and 9 People’s Councils promote the formation of voluntary groups and community leaders conduct training, outreach and awareness raising actions gathering materials produced by local media on environmental and adaptation issues.
Outcome Indicator | 2.4 Numbers of local schools with study programmes incorporating adaptation issues. | 0 | 34 schools in the two provinces are providing methodological guidance to teachers on how to include CC and EBA issues in the syllabus for 2015-2016 course, of which: 5 are mixed centers, 18 primary schools, 4 secondary schools, 1 pre-university school of basic science, and 6 municipal university centers. | 16 primary schools 15 secondary schools 3 municipal universities 1 teacher training institute
62 professors were trained in 6 schools of Artemisa province, and 10 professors in 1 school of Mayabeque province, through the methodological training on CC adaptation and EBA issues for the syllabus.
A plan of activities and methodological work was developed in 11 primary schools with “Interest Circles” (gatherings to encourage the vocational interests of students) on mangrove forests (5 in Artemisa and 6 in Mayabeque).
An environmental education workshop was conducted in Batabano primary school, as a pilot for generalization to other schools, to generate best practices and develop skills to promote coastal protection.
Outcome Indicator | 2.5 Numbers of dissemination and awareness raising materials on adaptation issues, produced by local media | 0 | The documentary film “Change of Time” that describes the Project purpose and expected benefits was published in 3 national TV programs with national and international reach. | 17 audiovisual 3 local television . 5 local radio 2 articles
A video clip entitled “Living Mangrove Forest” was released on social networks and national TV programs.
More than 200 copies of a DVD with audiovisual materials on mangrove forests and their protection, produced by Mundo Latino Studio, were disseminated and promoted in over 10 events, schools and government entities in the territories of both provinces.
TV programs and other mass media release devoted to the issues addressed by the Project were produced:
2 juvenile national TV programs called “Route 5” (“Ruta 5”), with 25-minute duration.
2 local TV programs in Mayabeque, and 11 local radio programs (6 in Mayabeque and Artemisa 5) 1 articles in the national printed press about the Project actions. 2 programs in provincial TV (1 in every provincial station) 2 programs in municipal TV (1 in every local radio station) 2 radio programs in provincial stations (1 in every provincial station) 2 articles in the printed press (1 in each provincial newspaper).
A communication campaign was developed to promote Project purposes: radio spot, printing of materials for the Project promotional campaign (posters, stickers, totem, paper bracelets, banner, screens, and billboards).
A promotion strategy was developed on social networks, (Facebook) with more than 200 visits.
Outcome Indicator | 3.1 Frequency of training and technical support visits carried out by provincial and municipal governments to coastal communities in support of EBA | 0 | 3 training actions on forest fires prevention and fighting, and protection of natural resources were conducted, 2 in Artemisa for professional brigades (16 men) and specialized brigade of Cajio Forestry Unit (10 men), and 1 in Mayabeque for the specialized brigade in Batabano (10 men). | 3 training and technical assistant activities undertaken per year by technical authorities to coastal areas.
3 training activities were carried out by technical authorities in coastal areas of Artemisa and 3 in those of Mayabeque regarding the regulatory framework, protection and sustainable management of coastal ecosystems.
113 prevention actions were developed, including talks and lectures in outlying communities or within the Project intervention area, in coordination with the local organizations of People’s Power, as part of the preparation of the population to face the critical period of forest fires occurrence and for the protection of natural resources.
Outcome Indicator | 3.2 Frequency of inspection visits to coastal areas by provincial and municipal governments in support of EBA | 0 | A guide with revised local and provincial regulations regarding the protection and sustainable management of coastal ecosystems was prepared and is implementation process, for the visits to coastal areas by provincial and municipal governments in support of EBA regulations. | 3 inspection activities undertakern per year by provincial municipal goverment and other regulatorities authorities
83 maritime journeys along the coast and 180 on land were carried out for the monitoring and protection of natural resources within the Project intervention area.
3 integrated inspection visits were conducted to the Project intervention areas, 2 in Artemisa (Alquizar and Guira Municipalities) and 1 in Mayabeque (Batabano, Melena, Güines) using land and naval means with the participation of regulatory authorities (PNR, CGB, SEF, CITMA and Coastguards).
Outcome Indicator | 3.3 Number of studies and methodologies carried out to estimate the cost - benefit from the implementation of the approach ABE, available for planners and policy makers. | 0 | 4 training actions were conducted for specialists from different agencies, 2 in provincial governments and 2 in municipal governments, with participatory approaches in economic valuation of ecosystem goods and services. | 3
Information was gathered on the value of fixed asset, forest heritage, flora and fauna, volume of agricultural, fishery and livestock raising production, for the assessment of the current state the coastal zone in the 6 municipalities.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Among the actions implemented that have a positive impact on the progress of the project are: 1. Production and dissemination of short appealing and didactic documentaries, filmed at the Project intervention areas with the involvement of key actors, contribute to awareness-raising on the need to protect mangrove swamp ecosystem, while constituting products whose dissemination in similar areas of the country extend the Project benefits. These are materials that show the importance of the preservation, sustainable management and restoration of mangrove swamp ecosystem, jointly with the socio-environmental issues, involving the participation of key actors (communities, local governments, specialists in the field, scientific researchers). They are filmed in the Project intervention areas, as part of the famous Cuban television series “The Secret Nature of Cuba”, produced by “Mundo Latino” National Series Studio that specializes in documentaries devoted to disseminate knowledge on environmental topics. The documentaries “Change of Time” and “In search for the lost forest” show the Project development and implementation. They will be reproduced to be used in the training and awareness-raising of actors in other coastal areas of the country, where mangrove swamp ecosystem also plays a leading role in climate change adaptation. This constitutes an effective way to extend the Project benefits without needing considerable investments. 2. Promotion of communication strategies, such as communication campaigns, strengthens the role of the communicator network in the territories. Didactic, professional, appealing and scientifically sound documentaries have served as support materials to communication campaigns, and facilitated the debate and reflection in a conscious search for solutions to the problems affecting mangrove swamp ecosystem, involving the communities and key actors. 3. Timely agreement between the scientific and the forestry sector generates more outstanding results than those obtained if these actors work separately. The joint and participatory work of personnel in scientific institutions and universities, together with the technicians and workers of forestry companies in these communities and local government specialists, generates more outstanding results than those obtained if these actors work separately. The knowledge, wisdom and experience contributed by each person constitutes an effective training for the other actors involved in the restoration and effective application of EBA for the communities, thus strengthening the work at local level. 4. The catalysis of partnerships between the executors of Project components and the environmental sector turn out to be favorable to the restoration process of mangrove swamp ecosystem. Project actions, in their three components, have catalyzed promising partnerships among key actors (CGB, GEF, SEF) and the environmental sector, which turn out to be favorable to the ecosystem restoration process and the sustainability of the EBA. 5. The introduction of scientific results during the recovery of mangrove swamp ecosystem favors its natural regeneration. The incorporation of new approaches into the technical projects of forestry companies and in the forestry activity, including methods and activities to achieve the recovery of the structure, function and EBA services in mangrove swamps and in other related ecosystems, in order to favor natural regeneration, as well as the design of an information system to monitor the progress of these projects and their implementation, constitute a demonstration of EBA possibilities in other parts of the country that are equally at risk of suffering CC-related impacts. 6. The initial characterization of the population framework in the areas comprised in the Project allows evaluating and reporting on the impact of adaptation measures in the territories. The characterization of the Population Framework in the Project intervention areas, keeping in mind the directly and indirectly benefitted population, as well as the target population, constitutes an effective baseline that allows evaluating and reporting on the impact of adaptation measures in the territory, by means of monitoring the indicators that define the Population Framework in each area of interest (municipalities, provinces).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Some Project activities, such as the work in areas to restore and in the communities, are out of step for the delay in the arrival of specialized transportation resources and equipment, lack of precaution, too ambitious work plans, and communication and coordination problems in the territories. To reduce delays, work schedules have been readjusted as resources have arrived, according to the priorities in the goals and milestones. The forestry companies and government institutions have contributed the available resources, in spite of the limitations existing in the country, to guarantee some activities. The execution process is monitored by MINCEX, UNDP and CITMA to speed up the processes of acquisition and delivery of resources in these territories. In prior coordination with the governments, activities have been included in their work plans using the available resources at that level, following up on their execution in different spaces. Communication channels among all the stakeholders are improved, and the leading role of the heads of components is reinforced, through a communication plan and sessions devoted to awareness-raising, staff training, as well as the follow-up and integration of the work team. Capacity building is necessary in the territories to training staff in developing the activities to consolidate information on costs/benefits, despite having been identified as a priority for the country. The process for collecting information is complex and time-consuming in the territories; therefore, training the personnel has been a priority, as well as the follow-up by national institutions and working towards the integration and stability of the work team.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As was informed in previus report, during the inception workshop some changes related to project logical framework were agreed upon: At the objective level, Indicator I was reformulated to "Areas with increased rates of health and the conditions of the mangroves (soil and salinity of the water, the density of the canopy, the existence of local protection schemes)" In component 1, annual goals of establishment/restoration of mangrove and landward edge woodlands were rearranged while maintaining the total project goals. These changes were undertaken due to two main reasons; one was the long period that went by since technical project approval and availability of funds, leaving calendar year goals obsolete. The other reason responded to seasonality of the planting of mangrove. Because project started at the end of the rainy period, goals had to be rearranged. Output 1.4 was reformulated to "Restoration and enrichment of forests inland that limits the wetland with the lands for cultivation." In component 3 a new indicator was added: "Number of studies and methodologies carried out to estimate the cost - benefit from the implementation of the EBA approach, available for plan and policy makers" with an end of the project target: "3 Studies carried out and available for decision-makers". During the period, access to the results of the National Census conducted in 2012 was achieved. This involves updating the population figures concerning the baseline and targets in relation to those initially included. All these changes were duly reflected in the inception workshop report.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | 1. In this second year of the Project, a detailed analysis of the gender composition was made, starting from the updated the characterization of the Population (in the intervention area) using official information from the ONEI and of the last population census. It will be the baseline for the population dynamics analysis under this approach and to study its modifications for the following years in each province and municipality involved. 2. Breakdown by sex of all social participation indicators managed by the Project. 3. Communication products have applied an inclusive approach, considering not only gender issues, but also territorial, capacity and generation differences. The participation of women is strengthened. 4. All the training has been done following the gender approach; women participation in ecosystem restoration works is promoted. 5. Gender gaps were identified in the info-communication diagnosis.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 84007
Implementing Entity | United Nations Development Program
Type of implementing entity | MIE
Country | Cuba
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 292207 | 21502 | 270705 | Total | 292207 | 21502 | 270705 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 45% | 45% | 45% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 88 | Coastal management | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0 |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 88 | 45% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | land | 4: Effective |  | Coastal management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 1616 | ha rehabilitated | 1: Ineffective | Mangroves | 7318 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 13 | 0% | 2: Limited improvement |  | 13 | 45% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Coastal management | Community-based adaptation | 5 | Adaptation strategies | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on E21: Tomas Escobar: Although the 2012 Census was used there were no significant changes, so data reported in the first PPR are maintained.
Note on I21: Tomas Escobar: Although the 2012 Census was used there were no significant changes, so data reported in the first PPR are maintained.
Note on I54: 8 groups of 10 people each one.
Note on H57: 8 groups of 10 people each one.
Note on E89: 000: It was a mistake. Rectificated data 1616 ha.It is the sum of the indicators of Component 1 (533 ha of coastal belt between Batabanó and Punta Mora + 144 ha of coastal mangrove between Majana and Surgidero de Batabanó + 939 ha of land).
Note on D103: 000: It was a mistake. Rectificated data: 13 communities.
Note on H103: 000: It was a mistake. Rectificated data: 13 communities.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.