## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | From April/1/2017 to December/31/2017
| Project Title: | Climate change resilient production landscapes and socio-economic networks advanced in Guatemala
| Project Summary: | The project aims to increase the resilience of production landscapes and socio-economic systems to climate change in 19 sub watersheds in the Nahualate River watershed, with jurisdiction in 12 municipalities in the departments of Sololá and Suchitepéquez that are threatened by the impacts of climate change and climatic variability; in particular this includes hydro meteorological events that are increasing in frequency and intensity. Towards the above objective, the project implements of set of interrelated actions ranging from the enhancement of institutional capabilities to support for building more resilient local economies and increasing the adaptive capacity of communities through adaptation measures in water resources management, as well as agricultural, agro-silvopastoral and land use practices.
|  |  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | GTM/MIE/Rural/2010/1 |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme - UNDP |  | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Guatemala |  | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Upper and middle watershed of the Nahualate River, in 19 sub watersheds selected based on their vulnerability: Alto Nahualate, Ugualxucube, Tzojomá, Paximbal, Igualcox, Masá, Ixtacapa, Yatzá, Panán, Mixpiyá, Nicá, Mocá, Paquiacamiyá, Tarro, Bravo, San Francisco, Chunajá, Siguacán, and Coralito. The 19 sub watersheds are located within the jurisdiction of 12 municipalities: Nahualá, Santa Catarina Ixtahuacán, Santa Lucía Utatlán, Santa María Visitación, Santa Clara La Laguna, San Juan La Laguna, and Santiago Atitlán, Department of Sololá; Santo Tomás La Unión, San Pablo Jocopilas, San Antonio Suchitepéquez, Chicacao, and Santa Bárbara, Department of Suchitepéquez. |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[9 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [7 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | September/14/2013
IE-AFB Agreement Signature Date: |  | December/19/2014 | [7 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | July/02/2015 | [7 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | April/2018
| Terminal Evaluation Date: | April/2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. |  | Cyprus
Documents:
|  | 1. Inception workshop report. | https://goo.gl/DEU7D6
|  | 2. Social communication material. | https://goo.gl/3PF5ra
|  | 3. Technical manual on climate change adaptation measures: Conservation and management of soil and water. | https://goo.gl/XMypUd
|  | 4. Manual for small-scale civil engineering and bioengineering works. | https://goo.gl/zwUVKY
|  | 5. Information, awareness, and participation strategy. | https://goo.gl/fUi1ZA
|  | 6. Letters of understanding with government agencies: National Forestry Institute (INAB), National Institute of Seismology, Volcanology, Meteorology, and Hydrology (INSIVUMEH); Institute of Agricultural Sciences and Technology (ICTA); and the Agronomy Department of the Universidad de San Carlos de Guatemala (USAC). | https://goo.gl/R5ouNz
|  | 7. Institutional Strategic Plans (PEI) 2016-2020 - Suchitepéquez | https://goo.gl/XzdJ58
|  | 8. Institutional Strategic Plans (PEI) 2016-2020 - Sololá | https://goo.gl/Uri2Qm
|  | 9. Municipal Development Plans (PDM) 2017-2032 - Suchitepéquez | https://goo.gl/Num1Xv
|  | 10. Municipal Development Plans (PDM) 2017-2032 - Sololá | https://goo.gl/bHEqPS
|  | 11. Report: Income and Expenditure by Household Beneficiaries of the Project | https://goo.gl/PKeDyV
|  | 12. Manual of Local Community Projects | https://goo.gl/L9xApg
|  | 13. Manual of Technical Guidelines for the Planning, Organization, Direction and Control of Compensation Mechanisms for Ecosystem and Environmental Services Associated with Forests. | https://goo.gl/B3XFnz
|  | 14. Microfinance as a financial mechanism for adaptation to climate change. | https://goo.gl/brfpfQ
|  | 15. Feasibility study of the potential of credit risk coverage mechanisms in Guatemala. | https://goo.gl/871YRq
|  | 16. Evaluation and design for implementation of financial mechanisms. | https://goo.gl/bmS3Go
|  | 17. Study: Traditional agricultural and forestry practices and implementation proposal for adaptation to climate change in the Nahualate river basin | https://goo.gl/HmhX6H
|  | 18. Identification and implementation of traditional practices for adaptation. | https://goo.gl/BfiiRP
|  | 19. Environmental Report of the State of Guatemala 2016 | https://goo.gl/UcB4ET
|  | 20. Final communication report of radio communication campaign (first phase) | https://goo.gl/mrCSUu
|  | 21. Closing Reports on Small Grants Projects (Local Organizations) | https://goo.gl/kxbpzy
|  | 22. Final Monitoring Reports of Small Grants Projects | https://goo.gl/urCd9b
Articles:
|  | 1. Support for the political transition of local governments in Sololá to continue advancing in the implementation of the PNDRI in the Upper Basin of the Nahualate River | https://goo.gl/kkWXvr
|  | 2. Actions for adaptation to climate change in the Sub-basins of the Nahualate River begin | https://goo.gl/UqTuvb
|  | 3. Climate change resilient production landscapes and socio-economic networks advanced in Guatemala (UNDP web portal) | https://goo.gl/4azBZE
|  | 4. Strengthening productive landscapes and communities resilient to climate change (Project launch). | https://goo.gl/VchGaW
|  | 5. The role of microfinance in adapting to climate change | https://goo.gl/XDDxK5
|  | 6. Local organizations sign subsidy agreements within the framework of small donations | https://goo.gl/a5tK8x
|  | 7. Launch of the diploma in municipal public management and transparency | https://goo.gl/bAKngW
|  | 8. First meeting of the local system of rural extensionism (SLER) within the framework of the Project | https://goo.gl/dTXdd7
|  | 9. First training in soil and water conservation; and best productive practices in the Nahualate river basin | https://goo.gl/4Sse8y
|  | 10. Rural promoters train in better production practices and conservation of soils and water | https://goo.gl/oJG3HM
|  | 11. Meeting of the interinstitutional support committee of the PPRCC project in the department of Sololá | https://goo.gl/YpXful
|  | 12. Forum: "Financial mechanisms of risk coverage related to adaptation to climate change for the agricultural sector" | https://goo.gl/ORV9pk
|  | 13. Capacity Analysis and Climatic Vulnerability Analysis (ACVC) and methodology CRISTAL | https://goo.gl/gmKCzM
|  | 14. Official delivery of institutional strategic plans is made in 12 municipalities of Sololá and Suchitepéquez | https://goo.gl/JMsVv3
|  | 15. Fire shooting in the protected area Rey Tepepul municipal regional park, Santiago Atitlán, Sololá | https://goo.gl/HmhX6H
|  | 16. Course: Bioclimatology, geobotany and biological indicators taught by professionals from the University of Jaén and the University of Santiago de Compostela, Spain | https://goo.gl/sPUlM0
|  | 17. MARN and UNDP authorities conduct field visits to monitor and implement local community projects | https://goo.gl/5txw3k
|  | 18. Launching of reforestation activities in the middle and upper part of the Nahualate River basin | https://goo.gl/w4RNPe
|  | 19. Presentation of the Environmental Report of the State of Guatemala 2016 | https://goo.gl/qt9Ckm
|  | 20. Training course: Training of facilitators on issues of adaptation and mitigation to climate change, biodiversity and vulnerability, to train primary level teachers | https://goo.gl/w1ZwR5
|  | 21. Training course: Development of short-term forecasts, using new methodologies and technologies | https://goo.gl/m8gJUS
|  | 22. Institutional strengthening for decision makers in the generation of climate change scenarios with the research and weather forecast software WRF | https://goo.gl/amfDZx
|  | 23. Workshop on risk management in protected areas with focus on climate variability, occupational health and safety | https://goo.gl/rufhJ8
|  | 24. Training of facilitators on issues of adaptation and mitigation to climate change, biodiversity and vulnerability, to train primary level teachers | https://goo.gl/BYriHi
|  | 25. Field visit to follow the progress of construction or remodeling of collection centers for eco-productive chains of: cocoa, honey, vegetables (pea) and mashan leaf | https://goo.gl/YEZhQn
|  | 26. Delivery of a truck to Cooperativa Nahualá, for the strengthening of the productive eco-chain of the mashan leaf | https://goo.gl/c2CV6Z
Multimedia
|  | 1. Our family's livelihood (video) | https://youtu.be/jY6o2Sx7t4g
|  | 2. In favor of the forest (video) | https://youtu.be/-epWWyz1g0I
|  | 3. It's never too late to change (video) | https://youtu.be/4_r9Ozg_0hI
|  | 4. Honey: an alternative to community development (video) | https://youtu.be/RPuhXOuTsHo
|  | 5. Cocoa is my business (video) | https://youtu.be/JQqzUdCdyAw | Czech Republic
|  | 6. Local strengthening, climate change resiliency (video) | https://www.youtube.com/watch?v=5D68CO7lRCI
|  | 7. Communities Resilient to Climate Change, Strengthening Community Development and Food Security (video) | https://www.youtube.com/watch?v=zNegKrZKyBU&feature=youtu.be
|  | 8. Organic agriculture and family vegetable plots in order to strengthen food security (video) | https://www.youtube.com/watch?v=2ZuKFh8_Asi
|  | 9. Forest Management, secure future (video) | https://www.youtube.com/watch?v=ZqKNqvOtm2I
|  | 10. Community Resiliency, protecting the soil, water and crops (video) | https://www.youtube.com/watch?v=Ac0OzjpvcRo
|  | 11. Conserving the soil, sustainable production (video) | https://www.youtube.com/watch?v=c9wEB_fySiQ
|  | 12. Ecosystem management for sustainable development (video) | https://www.youtube.com/watch?v=MmwRMbBWBUY
|  | 13. Improving productive landscapes, Cacao (video) | https://www.youtube.com/watch?v=k4F46dBCCnM
|  | 14. Water, main element of life and conservation of natural resources (video) | https://www.youtube.com/watch?v=INXKY4Q8-Qc&t=7s
|  | 15. Promoting the conservation of natural forests (video) | https://www.youtube.com/watch?v=LD0fVqkLQts
|  | 16. Project Productive Landscapes Resilient to Climate Change (video) | https://www.youtube.com/watch?v=gXVmwTF6Fx4 https://www.youtube.com/watch?v=xbS7V2bA0D0
|  | 17. Radial awareness campaign (spot and information capsules) | https://goo.gl/LLEJfy
List the Website address (URL) of project. |  |  |  | Democratic People's Republic of Korea
|  | http://marn.gob.gt/s/pprcc |  | Democratic Republic of the Congo
Denmark
| Project contacts: |  |  | Djibouti
National Project Manager/Coordinator |  |  |  | Dominica
| Name: | Johnny Ayendi Toledo González |  | Dominican Republic
| Email: | proyecto.pprcc@gmail.com
|  | jatoledo@marn.gob.gt |  | Ecuador
| Date: | July/02/2015 |  | Egypt
| Government DA |  |  | El Salvador
| Name: | Alfonzo Alonzo Vargas |  | Equatoral Guinea
| Email: | ministro@marn.gob.gt
|  | vesquivel@marn.gob.gt |  | Eritrea
| Date: | January/16/2018 |  | Estonia
| Implementing Entity |  |  | Ethiopia
| Name: | Flor María Bolaños |  | Fiji
| Email: | flor.bolanos@undp.org |  | Finland
| Date: | July/02/2015 |  | France
| Executing Agency |  |  | Gambia
| Name: | Otto José Fernandez Gamarra |  | Georgia
| Email: | ojfernandez@marn.gob.gt |  | Germany
| Date: | January/14/2017 |  | Ghana
| Executing Agency |  |  | Greece
| Name: |  |  | Grenada
| Email: |  |  | Guatemala
| Date: |  |  | Guinea
| Executing Agency |  |  | Guinea Bissau
| Name: |  |  | Guyana
| Email: |  |  | Haiti
| Date: |  |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31/12/2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of December 31, 2017 | 3877730.24
Add any comments on AF Grant Funds. (word limit=200) | The Project has achieved an efficient financial execution in accordance with the implementation schedule, which indicates that it has overcome the risks identified in the PRODOC; its implementation percentage is faster than expected. In the month of execution 30/48, the project has executed USD 3,877,730.24 (77.55%). In addition, it has committed USD 693,920.83 for the first semester of 2018, through contracts signed with local consultants, payments to projects of small donations in execution and expenses of the project management unit, which means that the Project plans to achieve a Percentage of execution of around 91.43% at June 2018, which requires financial resources to cover the commitments acquired and maintain good execution performance.
INVESTMENT INCOME | USD 13,848.52 (2017); USD 23,151.75 (from project start to date including 2017)
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period April 1, 2017 - December 31, 2017 | ITEM / ACTIVITY / ACTION | AMOUNT
1. Institutional and policy capacity strengthened for mainstreaming climate change risks into national, departmental, municipal planning, public investment, budgeting and decision-making.
| 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities | 6983.3
| 1.2 The management strategy for the Nahualate River watershed and eleven municipalities in the Departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning. | 17319.17
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels | 3803.18
| Outcome 1 subtotal | 28105.65
2. Development and implementation of climate change resilient ecosystem management and production practices that reduce the vulnerability of communities.
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program | 74116.26
| 2.2 Ancestral and traditional productions systems and hydrometeorological risk practices implemented by community-based organizations | 7174.13
| 2.3 Investments toward climate-resilient productions practices developed by community-based organizations in target municipalities | 454494
| Outcome 2 subtotal | 535784.39
3. Increased capacity of community based associations to reduce risks associated with climate-induced socioeconomic and ecosystem losses in the target municipalities
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthen in Sololá and Suchitepéquez | 906790.22
| 3.2 Institutional and social networks strengthened to build more climate resilient social environments | 113224.83
| 3.3 Technical assistance to determine the feasibility of existing microfinance mechanisms to provide financing for climate resilient activities and provide recommendations for design and implementation | 190079.65
| Outcome 3 subtotal | 1210094.7
4. Documentation, dissemination and uptake of lessons learned
| 4.1 Establishment of an information system, based on existing sub-national and national centres of expertise, to support more robust science-based decision-making | 20787.41
| 4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences | 22371.99 | Unintentionally, the expenses for result 4.3 were register under result 3.1. The mistake has been corrected.
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices | 19950.97 | Unintentionally, the expenses for result 4.3 were register under result 3.1. The mistake has been corrected.
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes | 0
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level | 0
| Outcome 4 subtotal | 63110.37
| 5. Project Administration | 60745.58
| TOTAL | 1897840.69
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period January 01, 2018 - December 31, 2018 | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
1. Institutional and policy capacity strengthened for mainstreaming climate change risks into national, departmental, municipal planning, public investment, budgeting and decision-making.
| 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities | 35863.23 | 2018-12-01
| 1.2 The management strategy for the Nahualate River watershed and eleven municipalities in the Departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning. | 41253.89 | 2018-12-01
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels | 1948.23 | 2018-12-01
| Outcome 1 subtotal | 79065.35
2. Development and implementation of climate change resilient ecosystem management and production practices that reduce the vulnerability of communities.
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program | 267564.87 | 2018-06-30
| 2.2 Ancestral and traditional productions systems and hydrometeorological risk practices implemented by community-based organizations | 86400 | 2018-12-01
| 2.3 Investments toward climate-resilient productions practices developed by community-based organizations in target municipalities | 409936.2 | 2018-12-01
| Outcome 2 subtotal | 763901.07
3. Increased capacity of community based associations to reduce risks associated with climate-induced socioeconomic and ecosystemic losses in the target municipalities
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthen in Sololá and Suchitepéquez | 8174.09 | 2018-12-01
| 3.2 Institutional and social networks strengthened to build more climate resilient social environments | 28315.38 | 2018-12-01
| 3.3 Technical assistance to determine the feasibility of existing microfinance mechanisms to provide financing for climate resilient activities and provide recommendations for design and implementation | 10899.18 | 2018-12-01
| Outcome 3 subtotal | 47388.65
4. Documentation, dissemination and uptake of lessons learned
| 4.1 Establishment of an information system, based on existing sub-national and national centers of expertise, to support more robust science-based decision-making | 5000 | 2018-12-01
| 4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences | 35308.51 | 2018-12-01
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices | 24784.75 | 2018-12-01
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes | 6811.99 | 2018-12-01
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level | 0 | N/A
| Outcome 4 subtotal | 71905.25
| 5. Project Administration | 160009.44 | 2018-12-01
| TOTAL | 1122269.76
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 100%
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The project is consistent with the Funding Proposal and Project Document presented to the AF in not presenting a figure for cofinancing mobilization. The MTR, however did signal that in practice in kind co financing could be identified particularly in the small grants component. An amount however could not be verified as in the grant budgets there was not a space made available for this component. A recommendation for future similar projects would be to ensure that co finance contributions be taken into account (in kind or in cash) and considered within the small grant budget.

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
National elections and a change in administration lessen support for the project. | Low | Changes in public administration due to national elections or personnel changes have not significantly affected the progress of the Project. To keep the level of risk low, the following actions were taken: (i) A direct and constant dialogue has been maintained with the municipal authorities and the coordinators of the technical units to facilitate the processes. This coordination has allowed the activities to date to be carried out without problems or rejection by the population and have facilitated the streamlining of processes. (ii) Participation in the meetings of the Departmental Development Councils (CODEDE) and the Municipal Development Councils (COMUDE) of the 12 target municipalities continued. The participation in these Councils contributes to socialize the results achieved jointly with the local partners, and maintains the validity of the Project in the political agenda.
Local authorities and communities in the target municipalities will not fully engage with the proposed Project activities, in particular those related to social networks | Low | Local authorities and communities are involved in Project activities. To keep the level of risk low, the following actions were taken: The participation of local authorities in project activities was facilitated through the development of 12 Municipal Development Plans (MDP) for the period 2017-2032, instruments that incorporate the variable of adaptation to climate change and that will serve as support for decision-making by local authorities on local investment and land use. Together with the Institutional Strategic Plans 2016-2020, they are the two instruments that have allowed coordinating with the municipal authorities the construction of nurseries, including the municipal nursery, to dispose of native forest plants in reforestation of areas devoid of forest. The reforestation campaign in the upper part of the Nahualate River basin was initiated by the Minister of Environment and Natural Resources. The Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Education (MINEDUC), both at home and in public schools, promote family gardens and school gardens, through coordination with community groups organized in centers of Learning for Rural Development (CADER).
Resource use groups and other producers do not understand the need to respond to and plan for climate change risks. | Low | The groups of producers have understood the need to respond and plan the risks of climate change quite well. To keep the level of risk low, the following actions were taken: (i) The hiring of local technical teams and the incorporation of local organizations as partners has facilitated the implementation of small grants projects and with them the results achieved by the Project. 7,737 women and men were trained in soil and water conservation practices, resilience and adaptation to climate change, organizational strengthening, governance, accounting, good agricultural practices (GAP), good management practices (GMP). These actions were complemented by the radio campaign that seeks to raise awareness and promote the issue of adaptation to climate change in the population of the Nahualate River basin. Both processes were carried out in three local languages ​​(Quiché, Kakchiquel, Tz'utujil) and in Spanish, assessing the transfer of knowledge through the spoken word to the beneficiaries, ancestral practice used by the Quiché, Kakchiquel, Tz'utujil peoples. (ii) During this period, an improvement was promoted in the economy of 2,491 member households, one hundred eight (108) community organizations (cooperatives, community producers and watershed management boards), through adaptation measures that focus on agricultural and forestry production. which has resulted in 749.82 hectares of agricultural land having good practices for adapting to climate change. This last result has been achieved through two strategies: (i) implementation of community projects; and (ii) The strengthening of the Ministry of Agriculture, Livestock and Food (MAGA) to support community groups organized in Learning Centers for Rural Development (CADER), using demonstration plots to teach conservation practices.
Partners and stakeholders fail to cooperate and/or project data may not be shared between stakeholders | Low | The communication with the institutions partners of the Project is currently effective. The risk remains at a low level. The dissemination of information is mainly done through the Interinstitutional Support Committee. In Sololá Department, the Committee is established within the Commission of Rural Development of the Council of Departmental Development to guarantee the partition of the Departmental Governor, maximum political authority of the department. In Suchitepéquez, the committee is lodged within the Environment Committee of the Departmental Development Council, although this has not guaranteed the participation of the Departmental Governor as the department's highest political authority. Both Committees take place every two months and is the space in which the partners plan, coordinate and the results of the projects are evaluated. The participation in these Councils contributes to socialize the results achieved jointly with the local partners, and maintains the validity of the Project in the political agenda.
Vulnerable groups with low levels of technical, management and financial capacities are unable to make efficient use of existing micro-finance facilities for climate resilient activities | Low | The risk remains low, for which vulnerable groups with low levels of technical, administrative and financial capabilities are supported, so that they initially know about the existing microfinance mechanisms in Guatemala, including current legislation, and then implement that scheme they consider more viable as a community group. During the current period, the creation of two microfinance schemes was promoted, aimed at local groups, with the aim of providing microcredits. Each scheme includes within the obligations of the beneficiary, the set of measures for climate change. We work with two local organizations, ALANEL consisting only of women, and AGEMA made up of men and women. As reported in the previous PPRs, one study allowed the identification of four microfinance mechanisms in Guatemala, which, when set up, can support the implementation of measures to adapt to climate change; These microfinance mechanisms were socialized in a forum with experts and the public interested in the Project area. In addition, through another study, financial mechanisms were established to cover risks related to adaptation to climate change (agricultural sector), evaluating the availability of these mechanisms in Guatemala and their relationship with the Climate Change Law. The Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN), held a space for debate, socialization and dissemination of these mechanisms.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
With the actions implemented by the project, the risks identified in the PRODOC remained at a low level, which did not require additional mitigation measures. One of the risks previously reported has been removed given that it has been overcome due the mitigation measures undertaken and reported in previous reposrt: Interdependence and sequential and simultaneous nature of some activities slows project implementation.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: Johnny Ayendi Toledo González | 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities |  | (i) Nine (9) meteorological stations installed and operating within the Nahualate River basin, as a strengthening to the national meteorological network. (ii) Two (2) bulletins with climate information disseminated with the Project's partners. (iii) One (1) interinstitutional team (INSIVUMEH, MARN, MAGA), in functions to generate climate scenarios and disseminate their uses. (iv) A workshop (1) to socialize the uses of the climatic scenarios professional to the members of the interinstitutional team (INSIVUMEH, MARN, MAGA). |  | (i) INSIVUMEH (National Institute of Seismology, Volcanology and Hydrology) completed the review of its initial field report that guided to the best location of the 9 stations that the Project would install. The INSIVUMEH report determines on the basis of parameters of territoriality, representativeness of livelihood and climatic zones and active meteorological stations, that to densify the meteorological network in the Nahualate River basin, only three (3) new meteorological stations are needed, and they must be located in the upper part of the Nahualate river basin. These stations will be purchased during the first half of 2018. The report was based on the excercise reported in the previous PPR: Prior to making the purchase of the weather stations, the strengthening of the () was continued. The Project supported INSIVUMEH through the installation and start-up of a high capacity data storage server, with the purpose that the database, built in the previous period, works properly. In addition, the Project supported the validation and updating of the information of 29 weather stations, which were incorporated for the first time into the meteorological network, which belong to local entities (Institute of Climate Change and National Coffee Association), entities with which Now, INSIVUMEH has a long-term mutual cooperation agreement. These meteorological stations are located in the southern region of the country, covering the lower and middle part of the Nahualate River basin (target area of ​​the Project). | MS
(ii) Currently, INSIVUMEH issues monthly bulletins containing updated climate information; The Project has strengthened the design of the newsletter, the content and the scope of the users of the information.
(iii) Inter-institutional teams (INSIVUMEH, Ministry of Agriculture, Livestock and Food (MAGA), Ministry of Environment and Natural Resources (MARN and the University of San Carlos de Guatemala) have strengthening their capacities in: (a) Forecasting in the short term, using new methodologies and technologies, (b) Institutional strengthening of decision makers in the generation of climate change scenarios with WRF software, with technical training to create reduced climate projections and promote their use in the revisions of national, departmental and municipal planning.
https://goo.gl/m8gJUS
https://goo.gl/amfDZx
(iv) The workshop to socialize the uses of the climatic scenarios to professionals members of the interinstitutional team (INSIVUMEH, MARN, MAGA) has been planned for February 2018, when it is contemplated to have the official climatic scenarios at the level of each municipality of the country. The results will also be shared to national authorities and techniques of partner institutions.
| 1.2 The management strategy for the Nahualate River watershed and 11 municipalities in the departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning. |  | (i) 12 Municipal Development Plans prepared. (ii) Elaboration of the basin management strategy with 50% progress. |  | (i) Twelve (12) Municipal Development Plans were prepared and approved by the municipal authorities of the twelve municipalities. These plans incorporate adaptation measures to climate change within the guidelines and strategies for the administration of the territory for the period 2017-2032. | S
https://goo.gl/bHEqPS
https://goo.gl/Num1Xv
The strategic planning of the 2018-2050 basin will be completed during 2018. During this period, the Rural Development Commission realize technical and documentary contributions.
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels. |  | (i) Structure of the financial mechanism endorsed by a municipality. (ii) Two (2) workshops on socialization of the financial mechanism with local actors. |  | (i) The municipality of San Lucas Tolimán endorsed the structure of the proposed financial mechanism. The mechanism is public-private, includes actors of the municipal government and three (3) communities. The process is accompanied by the National Forestry Institute (INAB) as a partner in the Project. The mechanism seeks that communities that supply water to the urban area of ​​the municipality receives compensation from the Municipality for the conservation of natural forests. For this purpose, it is proposed that initially the Municipality receives income from the forestry incentive mechanism. In addition, another private-private financial mechanism was proposed, which includes actors from the sub-basin of the Ixtacapa River, involving nine (9) communities located in the upper part of the sub-basin and private owners (mainly producers of sugar cane, rubber, coffee and shrimp farms) located in the lower part of the sub-basin. | S
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program |  | 200 hectares of natural forest under conservation by means of a protected area or forestry incentive. |  | 58.55 hectares of natural forest under conservation via forest incentive, approved by the National Forestry Institute (INAB); 24.2 hectares corresponding to the current period and 34.35 hectares previously reported. 312.90 hectares of natural forest have been submitted to the National Council of Protected Areas (CONAP), to be declared protected areas, under the category of Municipal Regional Park. CONAP´s approval is pending. During the current period, technical and legal observations requested by CONAP were attended as part of the administrative approval process of the three proposed Municipal Regional Parks. During the current period, the effectiveness of protection and conservation management was improved in the 5,886 hectares of existing protected areas, with integrated actions for fire management, through the construction of 57.5 linear kilometers of breach firewalls built in Municipal Regional Park (protected areas) and natural forests. Four brigades of forest firefighters were formed (40 community persons trained as forest firefighters), who operate with the required equipment, and who have been incorporated into the National System for the Prevention and Control of Forest Fires (SIPECIF) | MS
| 2.2 Ancestral and traditional production systems and hydrometeorological risk practices implemented by community-based organizations |  | (i) Implementation of 10 ancestral practices identified in the Nahualate River basin through a participatory evaluation of local community organizations. (ii) 40 hectares implemented with ancestral or traditional practices promoted under the mechanism of small grants projects, benefiting 250 households. |  | (i) 10 ancestral practices, related to the increase of the resilience of productive landscapes in the Nahualate River basin, were further implemented. The traditional or ancestral practices promoted were: organic agriculture, organic cover, minimum tillage, milpa system, orchards with planks and ridges against the slope, incorporation of organic fertilizer, mass selection to separate the corn seed, trench abonera, selection of Creole corn seeds and contour sowing. (ii) Traditional or ancestral practices promoted under the small grants project mechanism are now being practiced on 80.37 hectares, benefiting 250 households and approximately 1,125 people. | HS
https://goo.gl/BfiiRP
| 2.3 Investments toward climate-resilient production practices developed by community-based organizations in target municipalities |  | 15 different types of adaptation measures (including engineering, forestry and agricultural measures) are implemented by community organizations. |  | 15 different adaptation measures (including engineering, forestry and agricultural measures) were implemented by community organizations, using the small grants project mechanism. The adaptation measures were oriented towards production practices, seeking with the investment of the Project the resilience of the communities to climate. The results are the following: 1) 5,769 hectares under forest management and conservation. 2) 291,600 plants produced in twelve forest nurseries. 3) 397.16 hectares with soil conservation practices, including demonstration plots. 4) 98 water springs protected with reforestation and forest protection. 5) 148.51 hectares subject to agroforestry system management. 6) 1,304 domestic animals given to form livestock systems. 7) 5,586 hectares with integral fire management actions; 57.5 linear kilometers of firebreaks built in the Municipal Regional Park (protected areas) and natural forests. 8) 101.23 hectares with reforestation actions. 9) 82.23 hectares under organic agriculture; 9 structures, with minimal infrastructure for the production of 81,300 kilograms of organic fertilizer. 10) 10 traditional or ancestral practices recovered, 83.37 hectares cultivated. 250 households benefited. 11) 1,290 hives in operation, as part of the apicultural system. 12) 38.75 hectares of agricultural landscapes diversification. 13) 2,024 storage structures (silos) delivered. 14) 44.75 kilometers of reforestation of river banks. 15) 90 collection systems for rainwater storage, delivered or built. 16) 17 community seed banks implemented. 17) 150 gray water catchment systems. 18) 328 family gardens, specific work with women. Currently the Project continues to promote several of these adaptation measures through 14 new small grant projects, which have as main objective the formation of community networks of producers. | HS
https://goo.gl/ynP2eK
https://goo.gl/kxbpzy
https://goo.gl/urCd9b
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthened in Sololá and Suchitepéquez. |  | Baseline study of income and expenses per household. 25% of advance in the infrastructure of 8 storage centers intended to improve the conservation, storage and management of products from climate resilient production systems. |  | The Project led a base line study of economic income and expenditure per household, of the direct project beneficiaries: 2,491 household. The average monthly income determined per household is USD 201.33, which represents an annual income of USD 2,415.96. The average monthly expenditure determined per household is USD USD 194.14, which represents an annual expenditure of USD 2,329.72. The baseline study was conducted with a 95 % confidence level. The baseline study established that the average monthly income determined per household is lower than following index: - National minimum wage (USD 214.50/monthly); - Sustainable community level wage stablished by FAO (USD 219.62/ monthly); - minimum agricultural wage (USD 394.17/ monthly); - Lower than the Guatemalan index basket (USD 555.72/monthly). The baseline study establishes that the average monthly income is slightly larger than the independent national wage (USD 176.47/monthly). The baseline study use data from the National Statistics Institute of Guatemala (INE) and the Food and Agriculture Organization of the United Nations (FAO), related to year 2016. | HS
https://goo.gl/PKeDyV
The technical, legal and environmental studies were completed to carry out the construction or remodeling of 8 collection centers, destined to improve the conservation, storage and management of the products coming from the productive chains: honey, cocoa, vegetables (pea) and leaf of mashan The construction of the infrastructure is 40% complete on average.
https://goo.gl/YEZhQn
| 3.2 Institutional and social networks strengthened to build more climate-resilient social environments. |  | One (1) chain formed, reinforced and in operation. |  | 4 production chains, led by community groups, have been promoted and strengthened by the project: honey, cocoa, vegetables (pea) and mashan leaf. Each network has been strengthened through its legal establishment, which allows the negotiation and sale of agricultural products. The project has promoted the establishment of one cooperative and three commercial companies. Each group of leaders has been trained in management, taxes, legal aspects and accounting. Administrative and financial manuals have been prepared to strengthen the management of the groups. The participation of the leaders in fairs and congresses where they have promoted their products was facilitated. In addition, the start of negotiations with potential customers identified for each agricultural chain is supported. Currently, 8 storage centers are under construction. | HS
https://goo.gl/YEZhQn
| 3.3 Technical assistance to determine the feasibility of existing microfinancing mechanisms to provide financing for climate-resilient activities and provide recommendations for design and implementation. |  | The implementation of at least one microfinance mechanism to support processes of adaptation to climate change will be promoted, with a level of support agreed by the Interinstitutional Support Committee. |  | The project supported two microfinance mechanisms that involve the establishment of two revolving funds, with the objective to provide microcredits to two women groups that work on productive iniciatives that involve adaptation to climate change measures. | S
| 4.1 Establishment of an information system, based on existing sub-national and national centers of expertise, to support more robust science-based decision-making. |  | Consolidation of the information exchange and inter-institutional communication system for adaptation to climate change that will operate in a coordinated manner between INSIVUMEH-MARN-MAGA and other institutions (CONAP, INAB, ICTA, FAUSAC). |  | During the current period, the website for the exchange of climatic information hosted by the National Institute of Seismology, Volcanology, Meteorology and Vulcanology (INSIVUMEH) was prepared, where the general public will be able to download climatic information on each meteorological station in the country and can get information on climatic scenarios by municipality, information that is prepared jointly by INSIVUMEH, MAGA and MARN. In the web site, INSIVUMEH publishes climate forecasts and early warning; also issues bi-monthly bulletins containing updated climate information; The Project has also strengthened the design of the newsletter, the content and the scope of the users of the information. | S
http://www.insivumeh.gob.gt/
| 4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences. |  | Implementation of the awareness and promotion program on climate change, through a radio campaign. |  | The radio campaign that implements the awareness and promotion program on climate change was completed, in the period of March to October 2017; Its purpose was to raise awareness and promote the issue of climate change for the target population of the Project area. The campaign was broadcast on three radio stations and in four languages ​​(Quiché, Kakchiquel, Tz'utujil and Spanich). The estimated potential audience for the 12 municipalities of the Project's jurisdiction is 240,000 women (51%) and 234,000 men (49%), including rural and urban population. Given the coverage of the three radio stations, the messages reach an even larger population outside the project area. The Interinstitutional Support Committee requested that during the first semester of 2018 the campaign be repeated, with the purpose of reinforcing the knowledge in the population on the topic of climate change. At the end of the second stage of the radio campaign, the impact data of the program will be measured. | HS
https://goo.gl/mrCSUu
https://goo.gl/LLEJfy
https://goo.gl/fUi1ZA
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices. |  | 5 Documents with lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices. |  | The project has produced and gathered knowledge through the different processes that are under implementation. During 2018, the project will invest time to produce at least 5 documents that will include best practices and lesson learns, in resilient production, traditional practices, production chains, among others. During the reporting period ten videos were made on the implementation of 18 small grants projects with local partner organizations; a video was also made about the area of intervention, scope and local partners of the Project. | MS
https://goo.gl/ynP2eK
https://www.youtube.com/watch?v=gXVmwTF6Fx4
[5 empty] | https://www.youtube.com/watch?v=xbS7V2bA0D0 | MS
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes |  | Formulation of 1 technical standard to incorporate climate change into the planning and programming processes. (INAB). |  | Zero (0) technical standard formulated. The development of a technical standard manual was planned with the National Institute of Seismology, Volcanology, Meteorology and Vulcanology (INSIVUMEH), which was not carried out during this period. The development of the standard´s manual was reprogrammed for the first semester of the year 2018. | MU
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level |  | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Johnny Ayendi Toledo González
| Email: | proyecto.pprcc@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
At the end of the 30/48 month of the life of the Project, the performance rating is satisfactory. Technically, the Project exceeded two of its three impact goals. In the social sphere, 108 community organizations (goal: 50) incorporated measures to adapt to climate change to reduce their vulnerability. Regarding the environment, in 749.82 hectares (goal: 500ha) good agricultural practices were implemented as adaptation measures to climate change, including the recovery of ancestral practices. 7,737 women and men were trained in soil and water conservation practices, resilience and adaptation to climate change, organizational strengthening, governance, accounting, good agricultural practices (GAP), good management practices (GMP). These actions were complemented by the radio campaign that seeks to raise awareness and promote the issue of adaptation to climate change in the population of the Nahualate River basin. Both processes were carried out in three local languages (Quiché, Kakchiquel, Tz'utujil) and in Spanish. 4 productive chains were further promoted, consolidating its legal registration, which facilitates market entry, negotiation and sale of agricultural products (cooperatives or commercial companies); for this, the structure of management groups that promote and negotiate the products with potential clients identified through market studies was supported. The infrastructure supported by the project, will contribute to the economy of the community groups, by facilitating the storage and conservation of agricultural products storage, and with that, the opportunity to acces other markets. Planning and coordination continues at three levels: With two departmental committees for inter-institutional coordination (Sololá, Suchitepéquez); with the municipalities; and with local partners. This inter-institutional coordination facilitated, among others, the following results: • National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH): climate information is now storage according to the World Meteorological Organization (WMO) standards and regulations. The project strengthened INSIVUMEH by acquire a server to support the database. Now, the information can be disseminated by the website, including climate scenarios by municipality, weather forecasts and information on early warning. • National Institute of Forestry (INAB): The project facilitated two regulations under the PROBOSQUE law, both of them are under implementation: (1) forest incentives and (2) ecosystem services payment schemes. • Municipalities: the project facilitated the development of twelve Municipal Development Plans 2017-2032. This planning tools include climate change adaptation measures with clear implementation guidelines. • National Council of Protected Areas (CONAP): 5,886 hectares of protected areas have been strengthened through the construction of 57.5 kilometers of firebreaks and the training of 40 forest firefighters, incorporated into the National Forest Fire Prevention and Control System (SIPECIF). By December 2017, the Project executed 77.55% of the project grant, proving efficiency in its delivery by overarching its financial targets. The project has plane to have by June 2018 a financial commitment of 91.43%. The project has plan to achieve the project indicator by July 2018: storage centers, financial mechanisms, small grants, productive chains. By December 2018, the project will reach the results. .
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities |  | (i) Nine (9) meteorological stations installed and operating within the Nahualate River basin, as a strengthening to the national meteorological network. (ii) Two (2) bulletins with climate information disseminated with the Project's partners. (iii) One (1) interinstitutional team (INSIVUMEH, MARN, MAGA), in functions to generate climate scenarios and disseminate their uses. (iv) A workshop (1) to socialize the uses of the climatic scenarios professional to the members of the interinstitutional team (INSIVUMEH, MARN, MAGA). |  | The meteorological stations have not been acquired. The project has focus its work on making sure that the partnerships between the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) and private sector with meteorological stations at the Nahualate River, become official. Due to the signed cooperation agreement, INSIVUMEH has identify the need to install only 3 of the 9 planed meteorological station. It is expected to install the stations by June 2018. The project has evidence of significant progress on sthrenthening government agancies on generating climate data. Example of this is the monthly climate bulleting generated by INSIVUMEH; government official that participate on technical workshops related to new methodologies, technologies, climate scenarios, use of software, etc. | MS
| 1.2 The management strategy for the Nahualate River watershed and 11 municipalities in the departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning. |  | (i) 12 Municipal Development Plans prepared. (ii) Elaboration of the basin management strategy with 50% progress. |  | The project has facilitating that 12 Municipalities of the upper basing of the Nahualate River, align its planning tools on the National Planning System new methodology. The Municipal Development Plans and Strategic Plans will allow municipalities to link their planning, with the annual budget planning and delivery. The planning tools provide municipalities to identify adaptation measures needs and to invest on infrastructure projects that reduce vulnerability and enhance resilience. This will be documented on the lesson learns and best practices products to be developed on 2018. | S
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels. |  | (i) Structure of the financial mechanism endorsed by a municipality. (ii) Two (2) workshops on socialization of the financial mechanism with local actors. |  | Two financial mechanisms have been identifying, promoted and will be implemented on 2018: (1) public-private financial mechanism, between San Lucas Tolimán Municipality, the National Forestry Institute (INAB), and 3 communities regarding ecosystem services. The mechanism objective is that communities that supply water to the urban area of the municipality receive compensation from the municipality for the conservation of natural forests. (2) private-private financial mechanism, driven by 9 communities and private sector (sugar, rubber, coffee and shrimp’s large producers). The mechanisms promote the implementation of a trust fund, to finance development projects for the 9 communities located in the upper part of the sub-basin, and to contribute to the conservation of 950 hectares of natural forest that protects the water sources of the Ixtacapa River. | S
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program |  | 200 hectares of natural forest under conservation by means of a protected area or forestry incentive. |  | Additional 24.2 Ha (total 58.55 ha) of natural forest are protected under the national forest incentive program. 312.90 ha are proposed to be protected as Municipal Regional Park. The project has facilitated the process that involves a Municipal Regional Park approval by the National Council of Protected Areas (CONAP). Currently the documentation is under revision by CONAP. During the current period, the effectiveness of protection and conservation management was improved in the 5,886 hectares of existing protected areas, with integrated actions for fire management, through the construction of 57.5 linear kilometers of breach firewalls built in Municipal Regional Park (protected areas) and natural forests. Four brigades of forest firefighters were formed (40 community persons trained as forest firefighters), who operate with the required equipment, and who have been incorporated into the National System for the Prevention and Control of Forest Fires (SIPECIF) | S
| 2.2 Ancestral and traditional production systems and hydrometeorological risk practices implemented by community-based organizations |  | (i) Implementation of 10 ancestral practices identified in the Nahualate River basin through a participatory evaluation of local community organizations. (ii) 40 hectares implemented with ancestral or traditional practices promoted under the mechanism of small grants projects, benefiting 250 households. |  | 10 traditional production system practices are being promoted by the projects implemented by local communities and partners, such as organic agriculture, organic cover, minimum tillage, “milpa” system, orchards with planks and ridges against the slope, incorporation of organic fertilizer, mass selection to separate the corn seed, compost system, selection of Creole corn seeds and contour sowing. The project has doubled the expected goal, by implemented the traditional production system in 83.37 hectares. | HS
| 2.3 Investments toward climate-resilient production practices developed by community-based organizations in target municipalities |  | 15 different types of adaptation measures (including engineering, forestry and agricultural measures) are implemented by community organizations. |  | The project has invested in 18 different climate-resilient production practices, which have been developed and lead by community based organizations, through a small grant mechanism. The 18 small grants are currently on its final stage. Currently, 14 new small grants that promote climate-resilient production practices are in progress. The results surpass the expectation regarding community organizations strengthening, production efficiency, market development, food security, women empowerment. Evidence of the results is included in this report. | HS
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthened in Sololá and Suchitepéquez. |  | Baseline study of income and expenses per household. 25% of advance in the infrastructure of 8 storage centers intended to improve the conservation, storage and management of products from climate resilient production systems. |  | Important baseline data was collected and analyzed by the Project by conducting a study of economic income and expenditure per household, of the direct project beneficiaries: 2,491 household. The average monthly income determined per household is USD 201.33, which represents an annual income of USD 2,415.96. The average monthly expenditure determined per household is USD USD 194.14, which represents an annual expenditure of USD 2,329.72. The baseline study was conducted with a 95 % confidence level. The baseline study stablished that the average monthly income determined per household is lower than following index: - National minimum wage (USD 214.50/monthly); - Sustainable community level wage stablished by FAO (USD 219.62/ monthly); - minimum agricultural wage (USD 394.17/ monthly); - Lower than the Guatemalan index basket (USD 555.72/monthly). The baseline study stablishes that the average monthly income is slightly larger than the independent national wage (USD 176.47/monthly). The baseline study used data from the National Statistics Institute of Guatemala (INE) and the Food and Agriculture Organization of the United Nations (FAO), related to year 2016. The project promoted 8 storage centers for honey, cocoa, vegetables (pea) and “mashan” leaf production. The building process will be finish in 2018. The survey will be repeated by the end of the project to verify advances. | HS
| 3.2 Institutional and social networks strengthened to build more climate-resilient social environments. |  | One (1) chain formed, reinforced and in operation. |  | The project has promoted 4 production chains: honey, cocoa, vegetables (pea) and mashan leaf. The production chain associated network has been stablished (in some cases), strengthened and consolidated. The establishment of legal entities such as cooperatives or commercial companies will allow the producer to have better opportunities of business, markets and payments. | HS
| 3.3 Technical assistance to determine the feasibility of existing microfinancing mechanisms to provide financing for climate-resilient activities and provide recommendations for design and implementation. |  | The implementation of at least one microfinance mechanism to support processes of adaptation to climate change will be promoted, with a level of support agreed by the Interinstitutional Support Committee. |  | The project has provided technical assistance to establish a financial mechanism that includes the establishment of two revolving funds, with the objective to provide microcredits to two women groups that work on productive initiatives that involve adaptation to climate change measures. | S
| 4.1 Establishment of an information system, based on existing sub-national and national centers of expertise, to support more robust science-based decision-making. |  | Consolidation of the information exchange and inter-institutional communication system for adaptation to climate change that will operate in a coordinated manner between INSIVUMEH-MARN-MAGA and other institutions (CONAP, INAB, ICTA, FAUSAC). |  | The project accomplished the establishment of the “climate” online communication system, that allows information exchange, reliable data, access to climate information produced by meteorological station, municipality climate scenarios, weather forecast, early warning information. The system is managed by INSIVUMEH but is oversee by a technical team from different government organizations (INSIVUME, Ministry of Agriculture, Livestock and Food (MAGA) and Ministry of Environment and Natural Resources (MARN). | S
| 4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences. |  | Implementation of the awareness and promotion program on climate change, through a radio campaign. |  | The project implemented a successful radio campaign on awareness and promotion of climate change. The campaign was broadcast on three local radio stations, in four languages (Quiché, Kakchiquel, Tz'utujil and Spanish). The estimated audience is 240,000 women (51%) and 234,000 men (49%), including rural and urban population. Given the coverage of the three radio stations, the messages reach an even larger population outside the project area. On 2018 the campaign will be lounge on more time, with the purpose of reinforcing the massages. At the end of the second stage of the radio campaign, the project will measure the scope of the campaign. | HS
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices. |  | 5 Documents with lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices. |  | The project has produced and gathered knowledge through the different processes that are under implementation. During 2018, the project will invest time to produce at least 5 knowledge sharing documents that will include best practices and lesson learns, driven from the resilient production system process, traditional practices, production chains, etc. Ten videos were made on the implementation of 18 small grants projects with local partner organizations. | MS
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes |  | Formulation of 1 technical standard to incorporate climate change into the planning and programming processes. (INAB). |  | Zero (0) technical standard formulated. The project will facilitate the development of a technical standard manual, with the National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH), on the first semester of 2018, and coordination has been initiated. | MU
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level |  | N/A
[5 empty] | Overall Rating | S
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Flor de Maria Bolaños
| Email: | flor.bolanos@udnp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project is rated as Satisfactory due to the significant advances and by reaching some of the target for end of the project. It is important to highlight the consistency between the delivery rate and results accomplishment. The present report includes information from March 2017 to December of the same year. One more time, the evidence based information that highlight the project results is a clear justification for the Project Management Unit, the Ministry of Environment and UNDP to present this progress report to request the fourth disbursement to the Adaptation Fund. The reason for this request is to comply with the financial commitments acquired by the project, current and planned in the 2018 Annual Work Plan. One of the most significant goals that the project has achieve is to include adaptation measures in the official planning municipal tools. 12 Municipalities of the upper basing of the Nahualate River, have align its planning tools to the National Planning System new methodology. The Municipal Development Plans and Strategic Plans will allow municipalities to link their planning, with the annual budget planning and delivery. The planning tools provide municipalities to identify adaptation measures needs and to invest on infrastructure projects that reduce vulnerability and enhance resilience. The project has built a strong community based network that allow the communication and coordination among different local levels. The inter-institutional committee are consolidated in Suchitepequez and Solola, fostering coordination between representatives of central government institutions present in the territory, municipal authorities and civil society (women's groups, producers, local associations and others). The project kept catalyzing on the ground, government programs and activities. Example of this are the two financial mechanisms that have been identifying, that will be implemented on 2018: (1) public-private financial mechanism, between San Lucas Tolimán Municipality, the National Forestry Institute (INAB), and 3 communities regarding ecosystem services. The mechanism objective is that communities that supply water to the urban area of the municipality receive compensation from the municipality for the conservation of natural forests. (2) private-private financial mechanism, driven by 9 communities and private sector (sugar, rubber, coffee and shrimp’s large producers). The mechanisms promote the implementation of a trust fund, to finance development projects for the 9 communities located in the upper part of the sub-basin, and to contribute to the conservation of 950 hectares of natural forest that protects the water sources of the Ixtacapa River. The project has accomplished to surpass the number of organizations that incorporate climate change adaptation measures for reducing vulnerability. The target was 50 organizations and as of today, the project is working with 108 organizations. The project has promoted the establishment of legal entities such as cooperatives or commercial companies, that will allow the producers to have better opportunities of business, markets and payments. A survey carried out by the project, has identify that 2,491 households that are beneficiaries of the project have improved their income. This data includes evidence based information that allowed the project report a significant improving on household economy. The social communication strategy, based on a successful radio campaign on awareness and promotion of climate change is on its second phase. The campaign is broadcast on three local radio stations, in four languages (Quiché, Kakchiquel, Tz'utujil and Spanish). The estimated audience is 240,000 women (51%) and 234,000 men (49%), including rural and urban population. Given the coverage of the three radio stations, the messages reach an even larger population outside the project area. At the end of the second stage of the radio campaign, the project will measure the scope of the campaign. The project has produced and gather knowledge through the different process that are under implementation. During 2018, the project will invest time to produce at least 5 knowledge sharing documents that will include best practices and lesson learns, driven from the resilient production system process, traditional practices, production chains, etc. At the national central level, the project accomplished the establishment of the “climate” online communication system, that allows information exchange, reliable data, access to climate information produced by meteorological station, municipality climate scenarios, weather forecast, early warning information. The system is managed by INSIVUMEH but is oversee by a technical team from different government organizations (INSIVUME, Ministry of Agriculture, Livestock and Food (MAGA) and Ministry of Environment and Natural Resources (MARN). The project has made significant advances and it’s on its way to accomplish the project results.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective: to increase climate resilience in production landscapes and socio-economic systems in target municipalities, threatened by climate change and climatic variability impacts, in particular hydrometeorological events that are increasing in frequency and intensity | O.1. Number organizations (including cooperatives, community producers and watershed management committees) that incorporate climate change adaptation measures for reducing vulnerability. | In project target area there are community organizations only on an ad hoc and informal basis, formed in order to address specific activities (e.g. receive government assistance, maintenance work or community reforestation), but not continuously or systematically, and lacking legal foundation. Other examples are producer groups, including for honey, organic coffee and cocoa, banana (more common in Suchitepequez). Their knowledge and understanding of climate risks and adaptation measures are low. In the inception phase of the project a detailed analysis of the organizational level of communities and non-profit organizations was performed. This analysis identified seven non-governmental organizations (NGOs) and 3 cooperatives, that are called local organizations. These 10 organizations have legal registration, and have administrative capacities conditions to receive and manage small grants. These NGOs therefore serve to channel and manage small grants funds to a number of community-based producer organizations, which have no capacity for administrative and financial management and do not have legal registration. In addition, the project will support the establishment of legal watershed management committees (which currently do not exist), and also help producer and community organizations to be formalized and registered as part of the sustainability measures. In the project area there is a network of agricultural extension called CADER (Learning Centers for Rural Development),a Rural Extension System of the Ministry of Agriculture, Livestock and Food (MAGA). The CADER is a group of farmer families who practice non-formal teaching and learning processes, using collaborative and learning by doing approach. The CADER is directed voluntarily by a person of the community, which is known as a promoter, the only requirement is to have the courage to work for their benefit and that of the other members. The CADER system is supported by the Project on training issues within the framework of agreements with the Ministry of Agriculture, Livestock and Food (MAGA). | One hundred eight (108) organizations (cooperatives, community producers and watershed management boards) have incorporated climate change adaptation measures to reduce their vulnerability. 68 organizations in the current period and 40 organizations previously reported. This result has been achieved through two strategies: (i) implementation of community projects; and (ii) strengthening the Ministry of Agriculture, Livestock and Food (MAGA) to support community groups organized in Rural Development Learning Centers (CADER), using demonstration plots to teach conservation practices. Watch videos of small grant projects and press releases: | At project end, at least 50 organizations (including cooperatives, community producers and watershed management committees) have incorporated climate change adaptation measures for reducing vulnerability.
https://goo.gl/ynP2eK
https://goo.gl/kxbpzy
https://goo.gl/urCd9b
https://goo.gl/jd4Rva
https://goo.gl/CbVnFD
https://goo.gl/O5Ceyj
| O.2. Number of funding mechanisms developed to support national processes of adaptation (payments for environmental services, certifications, budget planning at local and central government level) established to support climate change adaptation processes. | Government authorities have been considering means of funding for climate change adaptation. Although climate change is being identified as a priority, specific funding mechanisms are non existent or insufficient to address adaptation needs to current and projected climate change. | Zero (0) financial mechanisms established to date. Six workshops were held to socialized the proposal of two (2) financial mechanisms. The proposed mechanisms are the following: (i) Public-private, this mechanism includes actors of the municipal government (Municipality of San Lucas Tolimán) and three (3) communities. The proposal is based on the Technical Guide to implement compensation mechanisms for ecosystem services and its manual approved by the National Forestry Institute (INAB) as a partner in the Project. The mechanism seeks that communities that supply water to the urban area of ​​the municipality receive compensation from the municipality for the conservation of natural forests. For this purpose, it is proposed that initially the municipality receive income from the forestry incentive mechanism. (ii) private-private, this mechanism includes actors from the Ixtacapa sub-basin, involving nine (9) communities located in the upper part of the sub-basin and private owners (mainly producers of sugarcane, rubber, coffee and shrimp farms) of farms located in the lower part of the sub-basin. The proposal includes the creation of a fund (trust) to generate and raise financial resources to finance development projects for the 9 communities located in the upper part of the sub-basin, and also to contribute to the conservation of 950 hectares of natural forest that protects the water sources of the Ixtacapa River. The creation of seed capital has been proposed to be shared between contributions from private owners and donations. As reported in the previous PPR, the investigation of the financial mechanisms implemented in Guatemala, both for payments for environmental services, certifications, central and local government budget planning, technical and legal designs, lessons learned during implementation and the role of The actors involved, has served as a reference to develop the proposals of the two mechanisms. It is expected to finish its implementation in December 2018. | At project end, the project will have supported the implementation of at least one financial mechanism (payment for environmental services, certifications, budget planning central and local government) with a level of support agreed by the inter-institutional support committee.
| O.3. Number of Ha area under climate-adaptive agricultural practices | 0 Ha currently. In the project area there is approx. 8200 Ha area under annual cultivars and in an overused status. Current agricultural production is at subsistence level and practiced in small lots with intensive cultivation cycles of 2-3 crops per year. In these areas there are some initial and ad hoc measures pointing towards soil and water conservation (some terrace forms, contour planting, intends of irrigation), but without using effective and integrated adaptation techniques, and lacking systematic and landscape level applications. | 749.82 agricultural hectares with good practices of adaptation to climate change. 502.82 hectares reported in the current period and 247 hectares reported in the previous period. | At project end, at least 500 Ha area under climate-adaptive agricultural practices.
https://goo.gl/ynP2eK
https://goo.gl/kxbpzy
https://goo.gl/urCd9b
Outcome 1: Local and national capacities and tools enable decision makers and communities to reduce vulnerabilities and strengthen adaptive responses. | 1.1. Availability of downscaled climate scenarios and early warning information | Currently, national capacities to manage and analyze information from weather events and risks are reduced and limited to application of regional models, and currently there is no downscaled climate projection, neither early warning information available for users in the target region. Only INSIVUMEH has trained experts on downscaling and will be supporting the project in preparing downscaled projections and in training process. | (i) As reported in the previous PPR, the capacity of the meteorological network and the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) were strengthened as follows: (a) A new database was prepared in accordance with the standards of the World Meteorological Organization (WMO); (b) The purchase of a high capacity data storage server; (c) Historical information was entered from 29 meteorological stations of local agencies (Institute of Climate Change and National Coffee Association), with which INSIVUMEH now has a mutual cooperation agreement to keep the meteorological information of these twenty-nine (29) updated stations. These meteorological stations are located in the southern region of the country, covering the lower and middle part of the Nahualate River basin (target area of ​​the Project). Given these results, a new review of the initial field report issued by the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) was carried out so that the Project will consider the location of the nine (9) stations initially considered. The INSIVUMEH report determines on the basis of parameters of territoriality, representativeness of life zones and active meteorological stations, to densify the meteorological network in the Nahualate River basin, only three (3) new meteorological stations are needed to be located in the upper part of the Nahualate river basin. These stations will be acquired during the first half of 2018. | At the end of the second year, the national meteorological network will be strengthened with nine new stations, installed and operating within the river basin Nahualate. At the end of the second year, an interagency team (INSIVUMEH, MARN, MAGA, among others) will be able to create downscaled climate projections and promote its use in the reviews of national, departmental and municipal planning. At the end of the third year, early warning information generated will be available and disseminated to users in the region (including through quarterly newsletters).
(ii) During the current period, inter-institutional teams (INSIVUMEH, Ministry of Agriculture, Livestock and Food (MAGA), Ministry of Environment and Natural Resources (MARN) and the University of San Carlos de Guatemala) have been strengthened their capacities in: (a) Development of short-term forecasts, using new methodologies and technologies. (b) Institutional strengthening of decision makers in the generation of climate change scenarios with the WRF software. These trainings are in addition to the one reported in the previous PPR, on bioclimatology, geobotany and biological indicators. With these trainings technical personnel are available to create reduced climate projections and promote its use in national, departmental and municipal planning reviews. By February 2018, it is expected to have official climate scenarios at the level of each municipality, which will be share with different government institutions.
https://goo.gl/m8gJUS
https://goo.gl/amfDZx
https://goo.gl/sPUlM0
(iii) During the current period, the website for the exchange of climatic information to be administered by the National Institute of Seismology, Volcanology, Meteorology and Vulcanology (INSIVUMEH) was prepared, where general public will be able to download climatic information on each meteorological station in the country and information on climatic scenarios by municipality that are jointly prepared by INSIVUMEH, MAGA and MARN. In the web site, INSIVUMEH publishes climate forecasts and early warning; also issues bi-monthly bulletins containing updated climate information; The Project has also strengthened the design of the newsletter, the content and the scope of the users of the information.
| 1.2. Number of strategies and development plans adopted and implemented, incorporating information on climate change risks and adaptation measures. | Guatemala has established a Territorial Planning System (SINPET) that allows the integration of sectoral policies and strengthens development processes. In this context, the country has developed plans, which have not yet incorporated risks of climate change and adaptation measures. | (i) As reported in the previous PPR, twelve (12) Institutional Strategic Plans that incorporate adaptation measures to climate change within the municipal government's planning for the 2016-2020 period were approved. | For the third year, the management strategy for the Nahualate Watershed, 12 municipal development plans and 12 municipal institutional strategic plans mainstream climate change risks and opportunities, and incorporate adaptation measures.
https://goo.gl/XzdJ58
https://goo.gl/Uri2Qm
https://goo.gl/JMsVv3
(ii) In the current period, twelve (12) Municipal Development Plans were prepared and approved by the municipal authorities of the twelve municipalities. These plans incorporate adaptation measures to climate change within the guidelines and strategies for the administration of the territory for the period 2017-2032.
https://goo.gl/Num1Xv
https://goo.gl/bHEqPS
(iii) As reported in the previous PPR, the study on the biophysical characterization of the Nahualate river basin and 19 sub-basins was completed. This study, together with the Municipal Development Plans, provides information on physical details, climatology, climate scenarios, and socioeconomic aspects, important for the strategic planning of the 2018-2050 basin, which will be carried out during 2018.
| 1.3. Number and type of financing mechanisms identified and assessed by MARN and relevant stakeholders. | There are no public-private partnerships to support adaptation processes, or mechanisms for national or local funding. | As reported in the previous PPR, the financial mechanisms implemented in Guatemala for payments for environmental services, certifications, central and local government budget planning were identified and evaluated, with the purpose of knowing technical and legal designs, lessons learned during the implementation and the role of the actors involved. With this, the goal of the indicator was completed by the end of the project. | At project's second year, financial mechanisms existing in Guatemala (payments for environmental services, certifications, central and local government budget planning) will be identified and assessed for suitability for target region, including mapping and evaluation of institutional capacities.
https://goo.gl/bmS3Go
Outcome 2: Production landscape resilience increased through application of traditional and ancestral practices and other production activities, as well as targeted investments. | 2.1. Number of ha of natural forest subject to conservation through the protected area or forest incentives mechanisms | In the project area 5,885 hectares of forest areas have been declared as protected areas under the management of municipalities. However, capacities of local municipalities and communities is very limited for effective management of these areas to prevent deforestation, and especially considering capacities of fire prevention and control, risk of it being increasing with changing climatic conditions. Currently there are no areas under conservation management using forestry incentives. Nevertheless, within the Nahualate River watershed, there are areas with natural forests where protected area status can be potentially expanded and conservation management enhanced under the existing forestry incentives programs in Guatemala (PINPEP - Forestry Incentive Programme for Small-holders of Forestry and Agricultural Use, administered by the National Forest Institute). There is a need also to support the conservation of areas that are strategic for water recharge and protection of water sources that supply urban populations. | (i) Effectiveness of protection and conservation management was improved in the 5,886 hectares of existing protected areas, with integrated actions for fire management, through the construction of 57.5 linear kilometers of breach firewalls built in Municipal Regional Park (protected areas) and natural forests. Four brigades of forest firefighters were formed (40 community persons trained as forest firefighters), who operate with the required equipment, and who have been incorporated into the National System for the Prevention and Control of Forest Fires (SIPECIF). | By the end of the project effectiveness of protection and conservation management is enhanced in the existing 5,885 hectares of protected areas. By the end of the project at least 200 hectares of additional natural forest areas are subject to conservation through protected area or forestry incentive mechanism.
https://goo.gl/HmhX6H
(ii) 58.55 hectares of natural forest under conservation through the form of forest incentive, approved by the National Forestry Institute (INAB); As reported in the previous PPR, 312.90 hectares with natural forest have been authorized by the municipal government for conservation as protected area. The three (3) protected areas under the category of Municipal Regional Parks have to be approved and register by the National Council of Protected Areas (CONAP), the approval process is expected to end during the 2018.
| 2.2 Number of ancestral and traditional practices recovered for increased resilience of productions landscapes adopted by the communities in the target area of the project | In the project area recovery of ancestral practices are only focused on the use of biological diversity (CONAP), however not related to production practices. | During the present period, 10 traditional or ancestral practices related to increase resilience of productive landscapes in the Nahualate River basin, were promoted through the cultivation of 80.37 hectares, benefiting 250 households and approximately 1,125 people. | By the end of the Project, at least two traditional or ancestral practices in target area and related to increasing the production landscapes resilience are recovered and implemented
https://goo.gl/BfiiRP
https://goo.gl/HmhX6H
| 2.3 Number and type of adaptation measures implemented by CBOs and NGOs (based on catalogue established by the project). | Communities are applying some initial and ad hoc measures contributing towards adaptation, mainly related to soil and water conservation (some terrace forms, contour planting, intends of irrigation), but without using effective and integrated adaptation techniques, and lacking systematic and landscape level applications. | 18 different adaptation measures (including engineering, forestry and agricultural measures) were implemented by community organizations, using the small grants project mechanism. The adaptation measures were oriented towards production practices, seeking with the investment of the Project the resilience of the communities to climate. The results are the following: 1) 5,769 hectares under forest management and conservation. 2) 291,600 plants produced in twelve forest nurseries. 3) 397.16 hectares with soil conservation practices, including demonstration plots. 4) 98 water springs protected with reforestation and forest protection. 5) 148.51 hectares subject to agroforestry system management. 6) 1,304 domestic animals given to form livestock systems. 7) 5,586 hectares with integral fire management actions; 57.5 linear kilometers of firebreaks built in the Municipal Regional Park (protected areas) and natural forests. 8) 101.23 hectares with reforestation actions. 9) 82.23 hectares under organic agriculture; 9 structures, with minimal infrastructure for the production of 81,300 kilograms of organic fertilizer. 10) 10 traditional or ancestral practices recovered, 83.37 hectares cultivated. 250 households benefited. 11) 1,290 hives in operation, as part of the apicultural system. 12) 38.75 hectares of agricultural landscapes diversification. 13) 2,024 storage structures (silos) delivered. 14) 44.75 kilometers of reforestation of river banks. 15) 90 collection systems for rainwater storage, delivered or built. 16) 17 community seed banks implemented. 17) 150 gray water catchment systems. 18) 328 family gardens, specific work with women. Currently the Project continues to promote several of these adaptation measures through 14 new small grant projects, which have as main objective the formation of community networks of producers. | By the end of the project, at least 15 different types of adaptation measures (including land use, water management, forestry and agriculture measures) are implemented through community-based adaptation
https://goo.gl/ynP2eK
https://goo.gl/kxbpzy
https://goo.gl/urCd9b
Outcome 3: Socio-economic adaptive capacity of communities improved. | 3.1. Percentage of targeted households with a more secure access to income for livelihoods (disaggregated by gender). | Currently agriculture production in the communities and targeted families is of subsistence, there is a very low level of marketing of products using local markets or through direct sale to intermediaries who approach communities seasonally, but this is not practiced systematically nor in a organized way, and there are no differentiated strategies for productive chains and product marketing. A household survey on income levels is planned to take place in October 2016, which will define the baseline. | The Project led a base line study of economic income and expenditure per household, of the direct project beneficiaries: 2,491 household. The average monthly income determined per household is USD 201.33, which represents an annual income of USD 2,415.96. The average monthly expenditure determined per household is USD USD 194.14, which represents an annual expenditure of USD 2,329.72. The baseline study was conducted with a 95 % confidence level. The baseline study stablished that the average monthly income determined per household is lower than following index: - National minimum wage (USD 214.50/monthly); - Sustainable community level wage stablished by FAO (USD 219.62/ monthly); - minimum agricultural wage (USD 394.17/ monthly); - Lower than the Guatemalan index basket (USD 555.72/monthly). The baseline study stablishes that the average monthly income is slightly larger than the independent national wage (USD 176.47/monthly). The baseline study use data from the National Statistics Institute of Guatemala (INE) and the Food and Agriculture Organization of the United Nations (FAO), related to year 2016. | At project end, at least 50% of households from members of community organizations involved (approximately 1,500 Total households) have more secure income access for their livelihoods.
https://goo.gl/PKeDyV
In June 2018, the final evaluation will be conducted to determine how project actions allowed member households of community organizations to improve their income. The Project is currently promoting actions in 2,491 homes.
| 3.2. Number and type of social networks for production in the target area (indicating gender composition). | None | 4 production chains, led by community groups, have been promoted and strengthened by the project: honey, cocoa, vegetables (pea) and mashan leaf. Each network has been strengthened through its legal establishment, which allows the negotiation and sale of agricultural products. The project has promoted the establishment of two cooperative and one commercial companies. Each group of leaders has been trained in management, taxes, legal aspects and accounting. Administrative and financial manuals have been prepared to strengthen the management of the groups. The participation of the leaders in fairs and congresses where they have promoted their products was facilitated. In addition, the start of negotiations with potential customers identified for each agricultural chain is supported. Currently, 8 storage centers are under construction. | By the end of the Project, at least two social networks (associations/production cooperatives/marketing associations) formed or strengthened and operating.
https://goo.gl/YEZhQn
| 3.3. Number of feasibility studies of microfinance schemes completed; number of options identified, described and supported with project technical assistance. | Weak organization and lack of market information hinders the marketing of traditional products and reduces the potential for innovation in production processes and alternative marketing. | The project supported two microfinance mechanisms that involve the establishment of two revolving funds, with the objective to provide microcredits to two women groups on productive iniciatives that involve adaptation to climate change. | By the end of the project, access to micro-finance relevant to develop climate change adaptation initiatives by farmers associations from Sololá and Suchitepéquez will be identified and prioritized.
As reported in the previous PPRs, one study allowed the identification of four microfinance mechanisms in Guatemala, which, when set up, can support the implementation of measures to adapt to climate change; These microfinance mechanisms were socialized in a forum with experts and the public interested in the Project area. In addition, through another study, financial mechanisms were established to cover risks related to adaptation to climate change (agricultural sector), evaluating the availability of these mechanisms in Guatemala and their relationship with the Climate Change Law. The Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN), held a space for debate, socialization and dissemination of these mechanisms.
https://goo.gl/brfpfQ
https://goo.gl/871YRq
https://goo.gl/XDDxK5
https://goo.gl/ORV9pk
Outcome 4: Effective knowledge management results in informed decision-making at all levels through an integrated information system. | 4.1. Inter- institutional information system of climate change designed and operating in a coordinated manner at multiple levels, running. | Currently there are no information centers working in coordination, and no initiatives linking various levels of climate change problems. Information on climate change is not available for decision-making at all levels. | The web page for the exchange of climate information operated by the National Institute of Seismology, Vulcanology, Meteorology and Vulcanology (INSIVUMEH) has been finalized. The website allowed the interested public to download climatic information for each meteorological station in the country, information on climatic events and scenarios by municipality, weather forecasts and early warning information. In addition, INSIVUMEH issues monthly bulletins containing updated climate information; The Project has also strengthened the design of the newsletter, the content and the scope of the users of the information. The sustainability of the process is based on the creation of a work team made up of INSIVUMEH technicians, the Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN), which holds bi-monthly meetings. The website is a tool that strengthens INSIVUMEH and the national climate information system, facilitating the exchange of statistical data of each meteorological station, on early warning and climate scenarios by municipality. | From the first year of the project, an information and inter-institutional communication system will be developed for adaptation to climate change which will operate in a coordinated manner.
| 4.2. Percentage of targeted population affirming awareness of predicted adverse impacts of climate change and appropriate response. (disaggregated by gender) | At the moment there is no awareness programs focused on climate change issues. Knowledge of the population on climate change is very low. | The radio campaign that implements the awareness and promotion program on climate change was completed, in the period of March to October 2017; Its purpose was to raise awareness and promote the issue of climate change for the target population of the Project area. The campaign was broadcast on three radio stations and in four languages (Quiché, Kakchiquel, Tz'utujil and Spanich). The estimated potential audience for the 12 municipalities of the Project's jurisdiction is 240,000 women (51%) and 234,000 men (49%), including rural and urban population. Given the coverage of the three radio stations, the messages reach an even larger population outside the project area. The Interinstitutional Support Committee requested that during the first semester of 2018 the campaign be repeated, with the purpose of reinforcing the knowledge in the population on the topic of climate change. At the end of the second stage of the radio campaign, the impact data of the program will be measured. | At the end of the project, at least 70% of the rural population of municipalities (total of 85.341 rural people) in the target area are aware of predicted adverse impacts of climate change and appropriate response. (disaggregated by gender)
https://goo.gl/mrCSUu
https://goo.gl/LLEJfy
https://goo.gl/fUi1ZA
| 4.3. Number of lessons learned and best production practices included in Project dissemination strategies and shared on UNDP, MARN, and ALM websites. | There is no public information with a multicultural approach to vulnerability and adaptation practices to climate change. Information on climate change is at a large scale and does not offer the precision required for decision making at the local level. | The project has created four manuals on new, traditional, and ancestral adaptation practices at the community level. The project has been producimng and gathering knowledge through the different processes that are under implementation. During 2018, the project will invest time to produce at least 5 documents that will include best practices and lesson learns, in resilient production, traditional practices, production chains, among others. These lessons to be documented will be added to five life histories of specific beneficiaries, prepared in the previous period, which can be seen in the following links: | During the Project implementation there will be: ten lessons learned systematized and published annually, four technical standards developed, and four manuals designed and published.
https://youtu.be/jY6o2Sx7t4g
https://youtu.be/-epWWyz1g0I
https://youtu.be/4_r9Ozg_0hI
https://youtu.be/RPuhXOuTsHo
https://youtu.be/JQqzUdCdyAw
In addition, during the period, ten videos were made on the implementation of 18 small grants projects with local partner organizations; a video was also made about the area of intervention, scope and local partners of the Project.
https://goo.gl/ynP2eK
https://www.youtube.com/watch?v=gXVmwTF6Fx4
https://www.youtube.com/watch?v=xbS7V2bA0D0
(ii) As reported in the previous PPR, 2 technical standards have been developed. In the current period, no technical standard was made.
https://goo.gl/4GZigD
(iii) As reported in the previous PPR, 4 manuals have been prepared.
https://goo.gl/4aU4cw

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | (i) The hiring of local technical teams and the incorporation of local organizations as partners have facilitated the implementation of small grants projects; with which the transfer of oral knowledge to the benefits has been valued, a traditional practice used by the Quiché, Kakchiquel and Tz'utujil peoples. This is reflected in the good technical and financial execution achieved by the Project. (ii) The Project Management Unit has maintained close coordination for the implementation of field activities, with local government partners and community organizations, through monthly work meetings. To do this, it has used existing institutional and community structures so as not to duplicate or overload existing mechanisms. This has allowed the Project to coordinate and facilitate actions with local authorities, municipal and institutional technicians, as well as community producers. This is one of the strategies that has given more success to the implementation of the project, which is reflected in the execution rate reached in the current period. (iii) The project's actions have been socialized with other governmental structures, such as the mancomunidades (groupings of municipalities) and traditional indigenous authorities, which has positively favored the implementation of the project. The mancomunidades carry out planning and decision-making on common issues for several municipal governments. (iv) The sustainability of the actions undertaken by the project are guaranteed by strengthening the community organizational structure, creating legal structures that will allow the beneficiaries to market their products by accessing market windows directly. Organizations now have trained personnel in good agricultural practices with a focus on adaptation to climate change, and good practices in the manufacture of products. Through the construction and equipping of basic infrastructure, it is sought to store and preserve the products, adding a plus through the selection of the product or through pre-sale packaging. To keep an environmental balance, community organizations have forest nurseries to reforest areas devoid of forests, preserve water springs, and encourage the recovery of ancestral practices friendly to the environment. The continuity of the institutional follow-up to the actions of the Project has not been left to the Ministry of Environment and Natural Resources (MARN) alone, but to each of the Project's partners. The results achieved have been shared with the Interinstitutional Support Committee. MARN as the implementing agency will be responsible for monitoring the implementation of financial mechanisms and microfinance.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | In the current period, the Project does not present a delay in implementation. The Project has achieved an efficient financial execution in accordance with the implementation schedule, which indicates that it has overcome the risks identified in the PRODOC; its implementation percentage is faster than expected. In the month of execution 30/48, the project has executed USD 3,875,058.66 (77.50%). In addition, it has committed USD 693,920.83 for the first semester of 2018, through contracts signed with local consultants, payments to projects of small donations in execution and expenses of the project management unit, which means that the Project plans to achieve a Percentage of execution of around 91.38% at June 2018, which requires financial resources to cover the commitments acquired and maintain good execution performance.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The pace of implementation is faster than expected, thanks to the implementation of a strategy based on the incorporation of government partners and local partners in the joint decision-making process, which has made it possible to link the programming of activities directly with regional and local actions and attending to the needs of the populations, facilitating with it, a participatory process. The Project has not undergone changes in its design. Only the final goal of indicator 1.1 has been changed at the suggestion of the institutional partner, National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH), strengthening the national meteorological network with 3 stations and not with 9 stations as it was proposed in the PRODOC. The change responds to the fact that with the support of the Project, historical information of 26 meteorological stations of local agencies (Institute of Climate Change and National Coffee Association) was entered, with which INSIVUMEH now has a mutual cooperation agreement to keep updated the meteorological information of those twenty-nine (29) stations. These meteorological stations are located in the southern region of the country, covering the lower and middle part of the Nahualate River basin (target area of the Project), which is why it is no longer necessary to further densify the network in that area.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | (i) The actions undertaken by the Project have allowed women to be involved in the resolution of situations specific to community groups, participating more actively in the social, economic-political and environmental life of the community. It has been promoted to leave out the role where women have traditionally been conceptualized in rural areas, as are domestic and family spaces. The Project has provided an opportunity for women to strengthen knowledge, discuss problems, define aspirations and value their potential within community groups. (ii) The gender approach starts from the equal rights and obligations of men and women, to achieve good family and communal living. Processes were initiated to strengthen the family economy through the development of product chains in the search for market windows that allow the strengthening of the family economy. The processes initiated open spaces for both men and women, who have trained and occupy spaces at different levels of marketing chains. The Ministry of Environment and Natural Resources (MARN) as an executing entity, promotes the process through the departmental delegations, also facilitating the accompaniment of other partners such as the Ministry of Agriculture, Livestock and Food (MAGA) and the Secretary of Food Safety and Nutritional (SESAN).
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | • The creation of socio-economic networks of producers is a succesful practice as it proved to provide community groups with a competitive advantage to access local, national and international markets by negotiating group market prices iand facilitating the implementation of adaptation measures as knowledge transfer was replicated with greater ease and acceptance. • The hiring of local technical teams and the incorporation of local organizations as partners facilitates the implementation of adaptation measures and the transfer of knowledge in a manner that is valued by the beneficiaries. • The direct involvement of government institutions while important can slow down actions if project execution is affected by lengthy government planning processes; therefore it is important to separate the functions of actors, their role and capacities and plan accordingly based on realistic milestones by each party. • Producers value local crops that both reward excellent commercial and environmental benefits. It is important to keep this in mind and identify in the beginning of the intervention those crops that meet this double purpose. • The transfer of knowledge, achievements and stumbling blocks of the intervention, must contemplate a communication strategy that uses tools of broad population coverage for the area of intervention (i.e radio) and ensure to consider cultural aspects such as the language and customs of the target beneficiaries.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | • Kreditanstalt für Wiederaufbau (KFW), is currently working in upscaling the project with its own funds in the of the department of Quiché. In particular KfW has looked to replicate the structure of components 2 and 3 in its design of its project. • The Mid Term Review has signaled that the successes of PPRCC should be replicated by the Ministry of Environment and Natural Resources (MARN, for its acronym in Spanish), advising it to consider the possibility of identifying further financial resources for its replication in other more vulnerable areas of the country, particularly in areas where crop productivity is projected to decrease due to limited adaptive capacity. The project will continue to work with MARN to facilitate measures for this recommendation. • The Ministry of Agriculture, Livestock and Food (MAGA, for its acronym in Spanish), a government partner of the Project, has selected agricultural extension technicians and community leaders that make up the Learning Center for Rural Development (CADER), to carry out knowledge transfer to community groups both inside and outside the intervention zones. This has allowed these technicians to provide knowledge transfer and lessons learned from the project beyond the target areas.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | • The involvement of local governments (community mayors, indigenous leaders, spiritual leaders) has a positive effect on the implementation of adaptation measures, these entities carry out planning activities and make decisions on common issues for the communities they represent. • The creation of community resilience committees as a figure facilitates the empowerment of women in the implementation of adaptation measures, because it allows them to have a new role within the community group, in which they influence the relationship between the environment and the productive spheres by supporting in the food and economic security of their household. • Valuing the ancestral or traditional practices of the communities and contributing to recover these, can potentiate the success of the intervention. Particularly as it facilitates the participation and appropriation of the community as a whole. • For the design of similar projects, fieldwork should allow from the beginning of the interventions to identify the predominant role of women within the community and community organizations, either as leaders of these or as part of the implementation of adaptation measures. This planning is enhanced when jointly establishing the schedule in which the woman can perform extra-family activities. This can potentiate the success of specific interventions or cause their failure if not properly identified.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | • Kreditanstalt für Wiederaufbau (KFW), is currently working in upscaling the project withi its own funds in the of the department of Quiché. In particular KfW has looked to replicate the structure of components 2 and 3 in its design of its project. • The Mid Term Review has signaled that the successes of PPRCC should be replicated by the Ministry of Environment and Natural Resources (MARN, for its acronym in Spanish), advising it to consider the possibility of identifying further financial resources for its replication in other more vulnerable areas of the country, such as those where crop productivity is projected to decrease due to limited adaptive capacity. The project will continue to work with MARN to facilitate measures for this recommendation. • The MAGA has selected agricultural extension technicians and community leaders that make up the Learning Center for Rural Development (CADER), to carry out knowledge transfer to community groups both inside and outside the intervention zones. This has allowed these technicians to provide knowledge transfer and lessons learned from the project beyond the target areas.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | • The formation of socioeconomic networks of producers, grouped on the basis of productive chains such as cocoa, honey, mashan leaf and vegetables (peas). • The construction and provision of collection centers to facilitate the storage and manufacture of products. • The opening of markets and the training of leaders to negotiate prices and market windows. • The formation of resilience groups with the legal recognition of the local government (Municipal Mayor). • The transfer of technical knowledge using the local languages to enhance capacities.
What measures are/have been put in place to ensure sustainability of the project/program results? | • The high level of appropriation of the intervention: The Mid Term Review indicates that there is a good level of appropriation of project activities at all levels which is necessary to contribute to the project long term sustainability, by considering the activities as one of national and community interest. It should be noted, that community leaders and local organizations are already proving to be comfrotable managing the market for their products, a situation that will be enhanced with the availability of storage centers. • Development of planning tools: The sustainability of the project actions from the institutional point of view can be seen through the Institutional Strategic Plans and Municipal Development Plans that have been developed with the support of this project. The challenge that remains is ensuring that these are used to continue with institutional strengthening actions, ithe mplementation of adaptation measures and in dissemination of information in the short and medium term. • Generating financial mechanisms. The project identified micro-financial mechanisms to support processes of adaptation to climate change in the communities. These are in their final phase of design.
What measures are being/could have been put in place to improve project/program results? | • Developing business plans: The Mid Term Review proposes to draw up business plans to offer a better future outlook on supply, demand, prices and competition for productive chains. • Including within the budgets of small grant projects a a space for counterpart co financing. This would have perhaps strengthened the appropriation of the activities by implementing partners. In future projects, the co financing contribution that should be accounted could be included in the form of work, inputs or financial resources of local organizations.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | • The project’s communication strategy has produced abundant audiovisual content, informative and inductive activities. This has included a concerted effort to ensure correct dissemination amongst all actors through relevant mediums. This includes a radio campaign to generate knowledge, enhance participation and local sensitivity to the causes and effects of climate change as well as to existing adaptation actions for resilience. • The project also promoted the identification and rescue of ancestral practices proven effective as adaptation measures to ensure that these would be well accepted and internalized within the communities
If learning objectives have been established, have they been met? Please describe. | • The project aims, that at the end of the project, at least 70% of the rural population of the municipalities (a total of 85,341 people from rural areas) in the target area knows the expected adverse effects of climate change and adequate response (disaggregated by gender). The measurement is pending.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | • No difficulty
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | • Yes. The populations are more sensitive to the effects of climate change and the adaptation measures they must implement, mainly in the agricultural sector and to landslide risks.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | GTM/MIE/Rural/2010/1
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Guatemala
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 67000 | 7500 | 59500 | Total | 49877 | 8823 | 41054 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50.67% | 50% | % of female beneficiaries | 59.41% | 59.63% | 59.2% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 12 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 12 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 12 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 90% |  | Multi-sector |  | 0% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 7500 | 50.67% | 4: Mostly aware |  | 0 | 0% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 5885 | ha protected | 1: Ineffective | Forests | 6085 | ha protected | 4: Effective | Forests | 5944.55 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 500 | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | 749.82 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 191 | 30% | From 0 to 0.5% | Agriculture | 1500 | 30% | From 1% to 5% | Agriculture | 0 | 0% |  | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Public policy | 24 | Multi-sector | Local | Public policy | 24 | Multi-sector | Local | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.