## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | From 02/July/2016 to 31/March/2017
| Project Title: | Climate change resilient production landscapes and socio-economic networks advanced in Guatemala
| Project Summary: | The project aims to increase the resilience of production landscapes and socio-economic systems to climate change in 19 sub watersheds in the Nahualate River watershed, with jurisdiction in 12 municipalities in the departments of Sololá and Suchitepéquez that are threatened by the impacts of climate change and climatic variability; in particular this includes hydro meteorological events that are increasing in frequency and intensity. Towards the above objective, the project implements of set of interrelated actions ranging from the enhancement of institutional capabilities to support for building more resilient local economies and increasing the adaptive capacity of communities through adaptation measures in water resources management, as well as agricultural, agro-silvopastoral and land use practices.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | GTM/MIE/Rural/2010/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme - UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Guatemala | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Upper and middle watershed of the Nahualate River, in 19 sub watersheds selected based on their vulnerability: Alto Nahualate, Ugualxucube, Tzojomá, Paximbal, Igualcox, Masá, Ixtacapa, Yatzá, Panán, Mixpiyá, Nicá, Mocá, Paquiacamiyá, Tarro, Bravo, San Francisco, Chunajá, Siguacán, and Coralito. The 19 sub watersheds are located within the jurisdiction of 12 municipalities: Nahualá, Santa Catarina Ixtahuacán, Santa Lucía Utatlán, Santa María Visitación, Santa Clara La Laguna, San Juan La Laguna, and Santiago Atitlán, Department of Sololá; Santo Tomás La Unión, San Pablo Jocopilas, San Antonio Suchitepéquez, Chicacao, and Santa Bárbara, Department of Suchitepéquez. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 14/September/2013
IE-AFB Agreement Signature Date: |  | 19/December/2014 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 02/July/2015 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | April/2017
| Terminal Evaluation Date: | April/2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
1. Inception workshop report. 2. Social communication material. 3. Technical manual on climate change adaptation measures: Conservation and management of soil and water. 4. Manual for small-scale civil engineering and bioengineering works. 5. Information, awareness, and participation strategy. 6. Letters of understanding with government agencies: National Forestry Institute (INAB), National Institute of Seismology, Volcanology, Meteorology, and Hydrology (INSIVUMEH); Institute of Agricultural Sciences and Technology (ICTA); and the Agronomy Department of the Universidad de San Carlos de Guatemala (USAC). 7. Microfinance as a financial mechanism for adaptation to climate change. 8. Feasibility study of the potential of credit risk coverage mechanisms in Guatemala. 9. Evaluation and design for implementation of financial mechanisms. 10. Identification and implementation of traditional practices for adaptation.
|  | Articles: 1. http://www.gt.undp.org/content/guatemala/es/home/presscenter/articles/2015/12/03/apoyo-a-transici-n-pol-tica-de-gobiernos-locales-en-solol-para-continuar-avanzando-en-la-implementaci-n-de-la-pndri-en-la-cuenca-alta-del-r-o-nahualate 2. http://www.gt.undp.org/content/guatemala/es/home/operations/projects/environment_and_energy/paisajes-productivos-resilientes-al-cambio-climatico-y-redes-soc.html# 3. http://www.gt.undp.org/content/guatemala/es/home/operations/projects/environment_and_energy/paisajes-productivos-resilientes-al-cambio-climatico-y-redes-soc/ 4. http://www.gt.undp.org/content/guatemala/es/home/presscenter/pressreleases/2015/07/02/fortaleciendo-paisajes-productivos-y-comunidades-resilientes-al-cambio-clim-tico.html 5. http://www.marn.gob.gt/paginas/El_rol_de_las_microfinanzas_en_la_adaptacin_al_cambio_climtico 6. http://www.marn.gob.gt/paginas/ORGANIZACIONES_LOCALES_FIRMAN_ACUERDOS_DE_SUBSIDO_EN_EL_MARCO_DE_LAS_PEQUEAS_DONACIONES 7. https://goo.gl/bAKngW 8. https://goo.gl/dTXdd7 9. https://goo.gl/4Sse8y 10. https://goo.gl/oJG3HM 11. https://goo.gl/YpXful 12. https://goo.gl/ORV9pk 13. https://goo.gl/gmKCzM 14. https://goo.gl/JMsVv3 15. https://goo.gl/sPUlM0 16 Our family's livelihood: https://youtu.be/jY6o2Sx7t4g 17. In favor of the forest: https://youtu.be/-epWWyz1g0I 18. It's never too late to change: https://youtu.be/4_r9Ozg_0hI 19. Honey: an alternative to community development: https://youtu.be/RPuhXOuTsHo 20. Cocoa is my business: https://youtu.be/JQqzUdCdyAw | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://marn.gob.gt/s/pprcc | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Johnny Ayendi Toledo González | Dominican Republic
| Email: | proyecto.pprcc@gmail.com / jatoledo@marn.gob.gt | Ecuador
| Date: | 2016-05-20 | Egypt
| Government DA |  | El Salvador
| Name: | Sydney Alexander Samuels Milson | Equatoral Guinea
| Email: | sasamuels@marn.gob.gt; jceballos@marn.gob.gt; ministro@marn.gob.gt | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Flor María Bolaños | Fiji
| Email: | flor.bolanos@undp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Otto José Fernandez Gamarra | Georgia
| Email: | ojfernandez@marn.gob.gt | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 02/07/2016 a 31/03/2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 March 2017 | 1979700.7
Add any comments on AF Grant Funds. (word limit=200) | The Project has achieved an efficient financial execution according to the timeline of implementation. The pace of implementation is actually somewhat faster than expected, so the third disbursement is required to comply with the commitments. At the 21/48 execution month, the Project has executed USD 1,979,700.70 (39.6%). In addition, it has committed USD 524,914.07 through contracts signed with local consultants, payments to small grants project under implementation and to cover project management unit expenses. During the month of April 2017 the Project was to sign additional small grants adding up to an amount of USD 815,300.00, which means that the project plans to achieve an overall financial execution rate of round 66.4% during the next 6 months, and requires additonal financial resources to cover the commitments acquired and to maintain the good execution performance.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period 2 July 2016 - 31 March 2017 | ITEM / ACTIVITY / ACTION | AMOUNT
1. Institutional and policy capacity strengthened for mainstreaming climate change risks into national, departmental, municipal planning, public investment, budgeting and decision-making.
| 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities | 45270.7
| 1.2 The management strategy for the Nahualate River watershed and eleven municipalities in the Departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning. | 30704.62
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels | 74506.8
| Outcome 1 subtotal | 150482.12
2. Development and implementation of climate change resilient ecosystem management and production practices that reduce the vulnerability of communities.
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program | 92171.16
| 2.2 Ancestral and traditional productions systems and hydrometeorological risk practices implemented by community-based organizations | 26545.12
| 2.3 Investments toward climate-resilient productions practices developed by community-based organizations in target municipalities | 899876.11
| Outcome 2 subtotal | 1018592.39
3. Increased capacity of community based associations to reduce risks associated with climate-induced socioeconomic and ecosystem losses in the target municipalities
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthen in Sololá and Suchitepéquez | 21622.97
| 3.2 Institutional and social networks strengthened to build more climate resilient social environments | 9878.89
| 3.3 Technical assistance to determine the feasibility of existing microfinance mechanisms to provide financing for climate resilient activities and provide recommendations for design and implementation | 84397.12
| Outcome 3 subtotal | 115898.98
4. Documentation, dissemination and uptake of lessons learned
| 4.1 Establishment of an information system, based on existing sub-national and national centres of expertise, to support more robust science-based decision-making | 19611.84
| 4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences | 0 | Please note that the radio campaign began in March 2017 and end in March 2018. The initial payment (1/6 payments) was made outside the reporting period and will be included in the next report.
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices | 0 | Please notice that the five life stories reported during this period were financially covered and leveraged by UNDP from other sources.
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes | 13221.87
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level | 12717.09
| Outcome 4 subtotal | 45550.8
| 5. Project Administration | 40113.48
| TOTAL | 1370637.77
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period 1 April 2017 - 31 March 2018 | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
1. Institutional and policy capacity strengthened for mainstreaming climate change risks into national, departmental, municipal planning, public investment, budgeting and decision-making.
| 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities | 60000 | 2018-03-01
1.2 The management strategy for the Nahualate River watershed and eleven municipalities in the Departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning.
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels | 66500 | 2018-03-01
| Outcome 1 subtotal | 126500
2. Development and implementation of climate change resilient ecosystem management and production practices that reduce the vulnerability of communities.
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program | 245675 | 2018-03-01
| 2.2 Ancestral and traditional productions systems and hydrometeorological risk practices implemented by community-based organizations | 75400 | 2018-03-01
| 2.3 Investments toward climate-resilient productions practices developed by community-based organizations in target municipalities | 754975 | 2018-03-01
| Outcome 2 subtotal | 1076050
3. Increased capacity of community based associations to reduce risks associated with climate-induced socioeconomic and ecosystemic losses in the target municipalities
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthen in Sololá and Suchitepéquez | 1258857 | 2018-03-01
| 3.2 Institutional and social networks strengthened to build more climate resilient social environments | 64586 | 2018-03-01
| 3.3 Technical assistance to determine the feasibility of existing microfinance mechanisms to provide financing for climate resilient activities and provide recommendations for design and implementation | 126500 | 2018-03-01
| Outcome 3 subtotal | 1449943
4. Documentation, dissemination and uptake of lessons learned
| 4.1 Establishment of an information system, based on existing sub-national and national centers of expertise, to support more robust science-based decision-making | 44670 | 2018-03-01
4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices | 24600 | 2018-03-01
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes | 12730 | 2018-03-01
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level | N/A | N/A
| Outcome 4 subtotal | 82000
| 5. Project Administration | 71390 | 2018-03-01
| TOTAL | 2805883
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 55
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Services contract/No. 2015-000001 | Carlos Roberto Gómez Quiroa | 55587.72 | 2015-05-18 | 52751.67 | 2836.05
Services contract/ No. 2015-000002 | Johnny Ayendi Toledo González | 86469.7935 | 2015-05-18 | 82058.16 | 4411.6335
Services contract/No. 2015-000003 | Keny Alexander Juárez Santiago | 55587.7244 | 2015-05-18 | 52751.67 | 2836.0544
Services contract/ No. 2015-000004 | Ana Carolina Morales Monroy | 30682.49 | 2015-07-06 | 30682.49 | 0
Services contract/ No. 2015-000005 | Faustino Barrera Guerra | 56644.6 | 2015-07-06 | 48912.02 | 7732.58
Services contract/ No. 2015-000006 | Susana Andrea Marín Marroquín | 47203.83 | 2015-07-01 | 41402.87 | 5800.96
Services contract/ No. 2016-000015 | Luz Nadina Cuque Herrarte | 32823.18 | 2016-03-14 | 16411.59 | 16411.59
Services contract/ No. 2016-000021 | Corina Alejandra Mena García | 13983.3 | 2016-04-01 | 13983.3 | 0
Services contract/ No. 2016-000026 | Julio Cesar Carpio Elías | 4285.71 | 2016-08-01 | 4285.71 | 0
Lease Agreement Santo Tomás La Unión Regional Office | Zoila Aurora Letona Motta | 5125.3337 | 2015-09-07 | 5125.33 | 0.0036806
Lease Agreement Santo Tomás La Unión Regional Office | TAROKO | 5600 | 2017-02-15 | 814.11 | 4785.89
Grant Agreement | Coperativa Bella Linda | 61306 | 2016-06-16 | 43449.25 | 17856.75
Grant Agreement | Cooperativa Nahualá | 73161.33 | 2016-06-16 | 51860.99 | 21300.34
Grant Agreement | Cooperativa Tuneca | 69499.97 | 2016-06-16 | 49265.63 | 20234.34
Grant Agreement | Amigos del Río de Ixtacapa | 38446.44 | 2016-06-16 | 27253.04 | 11193.4
Grant Agreement | AGEMA | 96120 | 2016-06-16 | 68135.56 | 27984.44
Grant Agreement | AGEMA | 61867.78 | 2016-06-16 | 43855.48 | 18012.3
Grant Agreement | ALANEL | 54333 | 2016-06-16 | 38514.46 | 15818.54
Grant Agreement | ALANEL | 41593 | 2016-06-16 | 29438.56 | 12154.44
Grant Agreement | CDRO | 100000 | 2016-06-16 | 70918.22 | 29081.78
Grant Agreement | CDRO | 100000 | 2016-06-16 | 70918.22 | 29081.78
Grant Agreement | CDRO | 100000 | 2016-06-16 | 70918.22 | 29081.78
Grant Agreement | Vivamos Mejor | 87562.62 | 2016-06-16 | 62620.77 | 24941.85
Grant Agreement | Vivamos Mejor | 100000 | 2016-06-16 | 36626.93 | 63373.07
Grant Agreement | Vivamos Mejor | 100000 | 2016-06-16 | 71515.41 | 28484.59
Grant Agreement | CALMECAC | 87980 | 2016-06-16 | 35732.1 | 52247.9
Grant Agreement | Tikonel | 98769.71 | 2016-06-16 | 70045.74 | 28723.97
Grant Agreement | Tikonel | 73662.64 | 2016-06-16 | 52216.38 | 21446.26
Grant Agreement | Tikonel | 100000 | 2016-06-16 | 70918.22 | 29081.78
|  |  |  | Total | 524914.0715
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Purchase of 4 Aerial tickets for the team of Spanish professionals, who were in charge of teaching Bioclimatology, geobotany and biological indicators as tools to identify and evaluate the ecological risk to the climate change of the PPRCC -Local Purchase- Procurement process. 06-10-2016 | Viajes Tívoli | 4103.64 | 3157.52 | Selected from provider Lax Travel, S.A., for offering the best fare in the purchase of airline tickets.
| Lax Travel | 3157.52
Purchase of Hotel service for the course Bioclimatology, geobotany and biological indicators as tools to identify and evaluate the ecological risk to climate change - Garden Inn Hotel -Local Purchase- Procurement process 10-07-2016 | Hotel Hilton Garden Inn/ Hoteles Princess | 7071.67 | 7071.67 | We selected the Garden Inn Hotel / Princess Hotels, as it was the only hotel that quoted the service, however already had previous references of the hotel complying with all the required technical specifications and good prices.
Purchase of a server for institutional strengthening of the National Institute of Seismology, Volcanology, Meteorology and Hydrology (INSUVUMEH) - Local purchase- Request for Quotation -RFQ- 14-07-2016 | Martinexa | 60343.04 | 50025.32 | QUATTRO-GQ, Sociedad Anónima has been selected to comply with all the technical specifications required and present the best economic and financial offer.
| QUATTRO-GQ, Sociedad Anónima | 50025.32
| GBM | 75205.09
| IPESA | 62713.55
Printing service National Policy on Solid Waste MARN - SERVIPRENSA- Local purchase -Procurement process 03-02-2016 | Serviprensa | 6157.022 | 6157.022 | SERVIPRENSA was selected as the provider since it complied with all the technical specifications and presented the best price offer.
| Ediciones Don Quijote, S.A | 6147.1918
| Corporación Litográfica | 0
Results-based Special Services Contact/No. 2015-000007/Marvin Enrique Pineda Gómez | Saúl Roca | 23789.36 | 13028.1277 | According to the evaluation of the 4 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Mr. Marvin Enrique Pineda Gómez who was the profile that best score presents.
| José Miguel Cutzal | 10994.44
| Jorge Mario Gómez | 15490.44
| Marvin Enrique Pineda Gómez | 13028.13
Results-based Special Services Contract/ No. 2016-000010/José Gilberto García Jovel | José Gilberto García Jovel | 31000 | 31000 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is José Gilberto García Jovel who was the profile that best score presents.
| Heraldo Alfonso Escobar López | 32793.2852
Results-based Special Services Contract/ No. 2016-000017/ Hugo Adonay Altan Palencia | Hugo Adonay Altan Palencia | 7815.044 | 7815.044 | According to the evaluation of the 5 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Hugo Adonay Altan Palencia who was the profile that best score presents.
| Ana Lorena Lobos Morales | 11071.3123
| Ana del Rosario Castañeda | 15109.085
| Luis Carlos Castellanos | 11081.4718
| Billy Martín Pineda Flores | 7815.044
Results-based Special Services Contract/ No. 2016-000023/María Mildred Moncada Vásquez | Mario Alberto Fong García | 36656.9749 | 26361.698 | According to the evaluation of the 4 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is María Mildred Moncada Vásquez who was the profile that best score presents.
| Higinio Napoleon Rodíguez Rodríguez | 97047.2314
| Fernando Monterroso Nájera | 40059.8566
| Maria Mildred Moncada Vásquez | 26361.698
Results-based Special Services Contract/No. 2016-000024/Gabriela Adelina Girón Hernández | María Alejandra Chuy Donis | 20365.7039 | 16282.2252 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Gabriela Adelina Girón Hernández who was the profile that best score presents.
| Gabriela Adelina Girón Hernández | 16282.2252
Results-based Special Services Contract/No. 2016-000025/ Kimberly Vanessa Guzmán Juárez | Kimberly Vanessa Guzmán Juárez | 2642.88 | 2642.88 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Kimberly Vanessa Guzmán Juárez who was the profile that best score presents.
| René Haroldo Orozco Barrios | 7928.64
Results-based Special Services Contract/No. 2016-000028/Carlos Estuardo Coy de León | Carlos Estuardo Coy de León | 7928.64 | 7928.64 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Carlos Estuardo Coy de León who was the profile that best score presents.
| Norman Erick Ávila Gramajo | 11891.64
Results-based Special Services Contract/No. 2016-000027/Mario Martín Velásquez Villatoro | Elián Jacobo Cotto Guzmán | 9117.94 | 9071.69 | According to the evaluation of the 3 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Mario Martín Velásquez Villatoro who was the profile that best score presents.
| Mario Martín Velásquez Villatoro | 9071.69
| Ana Violeta Reyna Contreras | 12289.4
Results-based Special Services Contract/No. 2016-000029/Israel Mardoqueo Basilio Juárez | Israel Mardoqueo Basilio Juárez | 24195.57 | 24195.57 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Israel Mardoqueo Basilio Juárez who was the profile that best score presents.
| Oscar Ernesto Medinilla Sánchez | 26428.81
Results-based Special Services Contract/No. 2016-000030/Oscar Ernesto Medinilla Sánchez | Oscar Ernesto Medinilla Sánchez | 54251.11 | 54251.11 | According to the evaluation of the profile received and the curriculum evaluation, along with the evaluation of the technical and economic proposal, the consultant selected is Oscar Ernesto Medinilla Sánchez.
Results-based Special Services Contract/No. 2017-000001/Hesler Bernardo Solares Zarceño | Hesler Bernardo Solares Zarceño | 12607.83 | 12607.83 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Hesler Bernardo Solares Zarceño who was the profile that best score presents
| Rodolfo Enrique García Mencos | 13271.4
Results-based Special Services Contract/ No. 2017-000002/ Lisandro Enhain Ramírez Flores | Claudia María de Jesús Villagrán García | 17824.78 | 10676.29 | According to the evaluation of the 4 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Lisandro Enahín Ramírez Flores who was the profile that best score presents.
| Lisandro Enahín Ramírez Flores | 10676.29
| Mario Martín Velásquez Villatoro | 23473.93
| Manuel Ricardo Navarro Sosa | 24304.48
Results-based Special Services Contract/No. 2017-000003/ Carlos Ernesto Donis Meza | Carlos Ernesto Donis Meza | 16881.22 | 16881.22 | According to the evaluation of the profile received and the curriculum evaluation, along with the evaluation of the technical and economic proposal, the consultant selected is Carlos Ernesto Donis Meza.
Results-based Special Services Contract/ No. 2017-000004/ Víctor Hugo Guzmán Silva | Beathris de María Girón Revolorio | 49849.22 | 33802.72 | According to the evaluation of the 6 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Victor Hugo Guzmán Silva who was the profile that best score presents.
| Oscar Lionel Orozco Barrios | 135987.51
| Víctor Hugo Guzmán Silva | 33802.72
| Edgar Rolando Yool Rosales | 37143.8
| Arturo López y López | 26569.24
Results-based Special Services Contract/No. 2017-000005/Carlos Kenneth Loarca Velásquez | Carlos Kenneth Loarca Velásquez | 16881.22 | 16881.22 | According to the evaluation of the profile received and the curriculum evaluation, along with the evaluation of the technical and economic proposal, the consultant selected is Carlos Kenneth Loarca Velásquez.
Results-based Special Services Contract/ No. 2017-000009/ Rita Paola Estrada Barrios | Angela Ruso Díez | 16050.29 | 21400.39 | According to the evaluation of the 8 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Rita Paola Estrada Barrios who was the profile that best score presents.
| Gabriela Alejandra Ortiz de la Cruz | 39553.13
| Jean Rouch Lebeau | 0
| Juan Carlos Osorio | 28742.86
| María José Iturbide | 39061.59
| Marco Alexander Tax Marroquin | 25819.57
| Monica María Cajas Castillo | 27526.25
| Rita Paola Estrada Barrios | 21400.39
Results-based Special Services Contract/ No. 2017-000008/ Abel Benaía Abac Cochoy | Abel Benaía Abac Cochoy | 5243.95 | 5243.95 | According to the evaluation of the 4 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is Abel Benaía Abac Cochoy who was the profile that best score presents.
| Cesar Augsto Sunum Cux | 16314.05
| Iris María Santos Yanes | 5243.95
| Magda Elizabeth Sabaj Hernández | 0
Results-based Special Services Contract/No. 2017-000006/ María Goretti Pérez Franco | Hector Guzman | 31431.82 | 5243.95 | According to the evaluation of the 2 profiles received and the curricular evaluation, combined with the evaluation of the technical and economic proposal, the selected consultant is María Goretti Pérez Franco who was the profile that best score presents.
| María Goretti Pérez Franco | 5243.95

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
National elections and a change in administration lessen support for the project. | Low | (i) Realization of the course for the "Diploma in Municipal Public Management and Transparency" in support of the Municipal Development Institute (INFOM), in coordination with the General Secretariat of the Presidency (SEGEPLAN) and the Ministry of Finance (MINFIN) (INAP), National Council of Protected Areas (CONAP), Ministry of Environment and Natural Resources (MARN), international cooperation and private sector also related to the topic, within the framework of the Municipal Strengthening Policy, to promote transparency in the municipal administrations. See press release: https://goo.gl/bAKngW (ii) Bimonthly meetings were held with the Inter-Institutional Coordination Committee within the Rural Development Commission of the Departmental Development Council of Sololá, with the participation of government institutions and municipalities. These meetings contribute to: (i) mitigating the risk of personnel changes in public administration, (ii) strengthening institutions in the area of ​​adaptation to climate change, and (iii) strengthening Project governance. See press release: https://goo.gl/YpXful (iii) The participation of a representative of the Project was continued in the meetings of the Departmental Development Councils (CODEDE) and Municipal Development Councils (COMUDE) of the 12 target municipalities. The participation in these Councils contributes to socializing the results achieved jointly with the local partners to strengthen the local institutionality. (iv) The implementation of the Letters of Understanding signed with Government institutions of the Project has been supported, through joint work plans, to promote the exchange of information and implement measures to adapt to climate change. See press release: https://goo.gl/dTXdd7
Local authorities and communities in the target municipalities will not fully engage with the proposed Project activities, in particular those related to social networks | Low | The following mitigation measures have been continued and further advanced: (i) The involvement of local authorities in project activities was facilitated through the development of 12 Institutional Strategic Planning (PEI) instruments for the 2016-2020 government period and the start of updating of Municipal Development Plans (PDM) for the period 2017-2032, instruments that incorporate the variable of adaptation to climate change and that will serve as support for the decision making of local government authorities on local investment and land use. See press release: https://goo.gl/JMsVv3 (ii) The transfer of knowledge to organized groups of women and men, on soil and water management techniques in agricultural and forestry production, has been carried out by technicians originating in the Project area, which has facilitated learning by dictating. The talks in the local language. See press releases: https://goo.gl/4Sse8y; Https://goo.gl/oJG3HM (iii) The participation of women in the activities of the Project has been strengthened in activities promoted by local community projects (grants); Complementing with training in leadership and leadership role. Progress reports, monitoring and evaluation of grant projects allow the verification of these results. (iv) The communities have been informed through briefings to community leaders identified jointly with the technical teams of the municipalities, who have been socialized the actions, achievements and benefits of the results of the Project on measures to adapt to change climate. These actions have been complemented by the launch of the radio communication campaign to the population, transmitting messages in 3 local languages.
Resource use groups and other producers do not understand the need to respond to and plan for climate change risks. | Low | (i) The participation of community leaders in the participatory elaboration of the municipal territorial planning instruments, Institutional Strategic Planning (PEI) for the 2016-2020 government period and the updating of the Municipal Development Plans (PDM) for the period 2016 -2032, has been active, catering through its vision for the current needs of the population and the establishment of future welfare conditions. These territorial planning instruments involve the participation of the different actors of the municipality, in order to establish in a participatory way the development of the municipality, considering variables of adaptation to climate change, risk and economic development. (ii) The transfer of knowledge to organized groups of women and men, on risk management planning, has been carried out by technicians originating in the Project area, which has facilitated learning by dictating the talks in the local language. It is limiting for territorial planning that the populations located in the upper part of the basin have small tracts of land for both housing and agricultural production, making it difficult to implement the adaptation measures, which have been adjusted to existing conditions. (iii) The discussion and socialization on "Financial Mechanisms for Coverage of Risks Related to Adaptation to Climate Change for the Agricultural Sector", which exists in Guatemala, has been jointly supported by the Ministry of Agriculture, Livestock and Food (MAGA), for the agricultural sector, while promoting links with the Law of Climate Change. See press release: https://goo.gl/ORV9pk (iv) The communities have been informed through briefings to community leaders identified jointly with the technical teams of the municipalities, about achievements and benefits of the results of the Project on measures to adapt to change climate. These actions have been complemented by the launch of the radio communication campaign to the population in the target areas, transmitting messages in 3 local languages.
Interdependence and sequential and simultaneous nature of some activities slows project implementation | Overcome | At execution month 21/48, the Project has financially delivered USD 1,979,700.70 (39.6%). In addition, it has committed USD 524,914.07 (10.5%) through contracts signed with local consultants, for small grants, and for project management costs. The scope of this execution and commitments reached is due to the planning implemented by the Project Management Coordination Unit , which has been able to organize effectively the administrative processes and the time for the selection of external consultants, activities with community groups and institutions. These actions have been complemented by monthly technical meetings with the local technical team, which has allowed identifying and adjusting the most adequate sequence of implementation and interrelationship of the project activities.
Partners and stakeholders fail to cooperate and/or project data may not be shared between stakeholders | Low | As reported in the previous PPR, the following institutional mechanisms are continued to be used and supported to mitigate this risk: (i) In order to boost the involvement of government partners in the department of Sololá, the Inter-Institutional Coordination Committee has been established within the Rural Development Commission of the Departmental Development Council; Likewise for the Department of Suchitepéquez, the establishment of the Inter-Institutional Coordination Committee has been established within the Committee on the Environment. In both Committees, bimonthly meetings are held, presenting the results obtained by the actions of the Project through joint planning. (ii) The Departmental Development Councils of Sololá and Suchitepéquez, the highest central government authority, have appointed their representatives to the National Project Board, contributing to strengthen their governance functions. (iii) In order to promote the involvement of the partners, the implementation of the Letters of Understanding with government institutions of the Project has been promoted, through joint work plans, which have encouraged the exchange of information and implementation of adaptation measures to the climate change. These letters have been signed by the: Faculty of Agronomy of the University of San Carlos de Guatemala (USAC), National Institute of Forests (INAB), National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH) and Institute of Science and Technology Agricultural Organization (ICTA). See press release: https://goo.gl/dTXdd7 (iv) To improve technical cooperation with government partners, the training of technicians and decision makers of government institutions on climate change issues have been supported. See press release: https://goo.gl/gmKCzM; Https://goo.gl/sPUlM0
Vulnerable groups with low levels of technical, management and financial capacities are unable to make efficient use of existing micro-finance facilities for climate resilient activities | Medium | (i) The discussion and socialization/dissemination of the "Financial Mechanisms for Coverage of Risks Related to Adaptation to Climate Change" was jointly organized with the Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN) For the Agricultural Sector, "evaluating the availability of these mechanisms in Guatemala for the agricultural sector and the link with the Climate Change Law. See press release: https://goo.gl/ORV9pk Pending is the analysis of existing microfinance mechanisms to local groups.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risks remained at a low level, or were reduced from medium to low, through the following actions: (i) The bimonthly meetings of the Interinstitutional Support Committee in each department (Sololá and Suchitepéquez), within the Committee on Rural Development and the Commission on Environment and Natural Resources of the Departmental Council respectively, have made it possible to link the programming of activities directly with territorial level interventions processes of government institutions. These processes support an open attitude and engagement of the authorities and facilitate the implementation of the Project. (ii) The support provided to local governments to develop planning instruments (Institutional Strategic Plan (IEP) 2016-2020 and Municipal Development Plans (PDM) 2017-2032), has facilitated the engagement of local government authorities through the exchange of ideas at workshops and coordination meetings. (iii) The elaboration of annual work plans with each government partner has allowed the partners to be involved more effectively in the project. (Iv) The monthly planning and follow-up meetings with local organizations and the Project Management Unit have facilitated a more streamlined implementation sequencing of the Project activities, organizing processes and field activities.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: | 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities |  | 9 meteorological stations installed and functioning within the Nahualate River basin, as a strengthening to the national meteorological network. Climate information bulletins will be developed and disseminated. Professional training will be provided to members of the inter-agency team. |  | Prior to the purchase of meteorological stations, the technical capacity of the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) was strengthened through a new database by the World Meteorological Organization (WMO) standards. Information from 26 meteorological stations managed by national local bodies: the Climate Change Institute and National Coffee Association have been integrated to this database, and currently information is being integrated from 53 additional meteorological stations. A new review of the field report issued by the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) will be made, in view of this information, in order to determine the potential location of new meteorological stations in the Nahualate River basin, taking into account parameters of territoriality and representativeness Of living areas. INSIVUMEH issues bimonthly bulletins, which have up-to-date climate information; The Project will strengthen the design of the newsletter, content and reach of information users. A course was facilitated on bioclimatology, geobotany and biological indicators as tools to identify and evaluate the ecological risks to climate change, addressed to 28 technicians from 6 government institutions: National Council of Protected Areas, National Forestry Institute (INAB), Ministry of Agriculture, Livestock and Food (MAGA) and the Faculty of Agronomy of the University of San Carlos de Guatemala (USAC). The course was taught by professors of the University of Jaén (Spain) and the University of Santiago de Compostela (Spain). See press release: https://goo.gl/sPUlM0 | MS
| 1.2 The management strategy for the Nahualate River watershed and 11 municipalities in the departments of Sololá and Suchitepéquez integrate adaptation measures to climate change and variability in their planning. |  | 12 Municipal strategic plans developed and delivered to municipalities for their operationalization. 12 Municipal strategic plans in process of elaboration. The biophysical characterization of the basin and of the 19 sub-basins is completed. As a basis for developing the watershed management strategy. |  | 12 Municipal Strategic Plans 2016-2020 finalized and delivered formally to the municipalities. Plans incorporate adaptation measures into local government planning. Each plan allows municipal authorities to have guiding instruments for municipal investment and the land use planning; consider national and international regulations on irrigation, vulnerability and adaptation to climate change. See press releases: https://goo.gl/fVoFcf, https://goo.gl/JMsVv3 3 Municipal Development Plans 2017-2032 finalized (Santa Maria Visitation, Santa Clara La Laguna and Santa Lucía Utatlán). 9 Additional Municipal Development Plans in the elaboration stage. This instrument of municipal planning develops the guidelines and strategies for the administration of the territory, involving central and local government actors. Pending final edition of document. Finished the study on the biophysical characterization of the basin of the Nahualate River and 19 sub-basins. This study provides important information on the physical details, climatology and climatic scenarios, as a basis for the formulation of the management strategy of the Nahualate River basin 2018-2050, which will be elaborated during the third year of the project. | HS
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels |  | Design financial mechanisms derived from the identification of financial mechanisms implemented in Guatemala. |  | Financial mechanisms implemented in Guatemala have been identified for payments for environmental services, certifications, central and local government budget planning, with the purpose of knowing technical and legal designs, lessons learned during the implementation and the role of the actors involved. To date, the Project has facilitated the preparation of two proposals for financial mechanisms: (i) Private-private: including actors from the Ixtacapa River sub-basin, involving 9 communities located in the upper part of the sub-basin and private owners of Farms located Mainly producers of sugar cane, rubber and coffee; (ii) Public-private: includes actors of municipal government and communities; The implementation proposal is being discussed jointly with the National Forestry Institute (INAB) and the municipalities. The implementation of the financial mechanisms will be promoted in the next 12 months. The implementation route will be approved by the Interagency Coordination Committee. | HS
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program |  | 200 hectares of natural forest under conservation by means of a protected area or forestry incentive. |  | 312.90 hectares with natural forest authorized by the municipal government for conservation under the figure of protected area (Regional Municipal Park). Pending registration to the National Council of Protected Areas (CONAP) to account for the area of ​​the project indicator. These 312.90 hectares would add to the 34.35 hectares of natural forest conservation under the forestry incentive figure, reported for the previous period (July 02, 2015-July 1, 2016). | S
| 2.2 Ancestral and traditional production systems and hydrometeorological risk practices implemented by community-based organizations |  | Implementation of 10 ancestral practices identified in the Nahualate River Basin through a participatory assessment of local community organizations. Finished the study on identification of archaeological sites and indigenous ceremonial sites, with tourist potential. |  | 10 ancestral practices have been implemented through 8 small grants with local organizations. inter-planting with beans (as fertilizers), planks in orchards, contour planting, incorporation of organic matter, coverage with crop residues, minimum tillage, the milpa system, furrows with plants (beans - aboneras), selection of seeds, orchards. Likewise, 4 new value chains are strengthened: honey, cocoa, peas and mashan. The final results on area and households will be reported in the following report. Finished the study on identification of archaeological sites and indigenous ceremonial sites, generating 5 proposals of potential routes for local eco-tourism development. The proposals will be discussed at the level of the Inter-Institutional Coordination Committee to promote joint implementation with the Guatemalan Tourism Institute (INGUAT) of local tourism as an economic alternative for families, supporting watershed conservation. | S
| 2.3 Investments toward climate-resilient production practices developed by community-based organizations in target municipalities |  | Implementation of small grants projects in the Project area, with a focus on adaptation to climate change. Carried out the training in Crystal Methodology, focusing on adaptation to climate change and food security. |  | 73% progress in the implementation of 18 small grants projects, through which community organizations are encouraged to incorporate 15 different measures to adapt to climate change. The final results will be reported in the following report. 1,621 households of members of community-based organizations are improving their income through the implementation of 18 small-grant projects. 21 technicians from government institutions, small-scale project coordinators and the PPRCC Project, trained in the use of the tool "Capacity Analysis and Climate Vulnerability (ACVC) and CRiSTAL, to assess the effects of climate change on livelihoods of the communities. See press release: https://goo.gl/gmKCzM | S
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthened in Sololá and Suchitepéquez |  | Impulsing of 4 productive chains. Identification of sites for bioengineering works. |  | Through 9 projects of small grants, 4 production chains are promoted: honey, cocoa, peas and mashan (they start execution in April 2017). The impulse to these productive chains responds to the recommendations of market studies, business plans and investment plans made by the Project. The technical (design), legal and environmental studies for the construction of storage centers will be carried out within the framework of the implementation of each small grants project. Pending is the impulse to the chain of organic coffee that is under evaluation. Thirty-six sites have been identified for bioengineering, considering the small-scale manual of civil engineering and bioengineering developed by the Project. See publication: https://goo.gl/ypN1lC | S
| 3.2 Institutional and social networks strengthened to build more climate-resilient social environments |  | Proposed identification of strengthening of two institutional or social networks. |  | Through the model of productive chains, 4 networks of community groups that produce honey, cocoa, peas and mashan will be strengthened. In April 2017 will begin with the implementation of 9 projects of small grants to promote the strengthening of networks. | S
| 3.3 Technical assistance to determine the feasibility of existing microfinancing mechanisms to provide financing for climate-resilient activities and provide recommendations for design and implementation |  | The prefeasibility study completed to incorporate the insurance scheme in the climate index in Guatemala. |  | Together with the Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN), the "Financial Mechanisms for Coverage of Risks Related to Adaptation to Climate Change for the Agricultural Sector", evaluating the availability of these mechanisms in Guatemala for the agricultural sector and the link with the Law of Climate Change. See press release: https://goo.gl/ORV9pk Pending is the promotion with community groups, the implementation of microfinance mechanisms proposed in the study carried out by the Project. | S
| 4.1 Establishment of an information system, based on existing sub-national and national centers of expertise, to support more robust science-based decision-making |  | The web site for the exchange of climate information of the National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH) is implemented and in running. |  | The website is a tool for strengthening the National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH) by improving the quality of the current climate information. By improving the quality of the information, INSIVUMEH will be able to provide statistical data of each meteorological station and climatic scenarios. | S
| 4.2 Development and implementation of an awareness and advocacy programme on climate change for a range of target audiences |  | Implementation of the awareness and awareness program through a radio campaign. |  | The radio communication campaign was started, with the aim of sensitizing and promoting the theme of climate change. The campaign is broadcast in four languages: Quiché, Kakchiquel, Tz'utujil and Spanish. Use of a platform of community radios, which they transmit in the local languages. The target population is located in the urban and rural areas of the Nahualate River basin. View publication: http://marn.gob.gt/s/pprcc/paginas/Audios https://goo.gl/pBz2SV The estimated potential audience for the 12 municipalities of the Project is 240,000 women (51%) and 234,000 men (49%). At the end of the campaign in March 2018 will measure the coverage and impact data of the radial campaign. | S
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices |  | Preparation of 5 short videos about project beneficiaries and actions. |  | Five life stories were elaborated to address the current conditions of the beneficiaries and their expectation before the initial support that the Project has given them. View publication: http://marn.gob.gt/s/pprcc/paginas/Videos_2 The videos can also be found at the following links: 1. Our family's livelihood: https://youtu.be/jY6o2Sx7t4g 2. In favor of the forest: https://youtu.be/-epWWyz1g0I 3. It's never too late to change: https://youtu.be/4_r9Ozg_0hI 4. Honey: an alternative to community development: https://youtu.be/RPuhXOuTsHo 5. Cocoa is my business: https://youtu.be/JQqzUdCdyAw | S
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes |  | Technical Guidelines on Ecosystem Compensation Mechanisms and Environmental Services Associated with Forests developed. National Institute of Forests (INAB). |  | In the reported period from July 2, 2015 to July 1, 2016, a standard was formulated. During the current period, the regulations on Technical Guidelines on Ecosystem Compensation Mechanisms and Environmental Services Associated with Forests were formulated, in accordance with the provisions of Articles 6 and 19 of the Law on Promotion of Establishment, Recovery, Restoration, Management, Production And Protection of Forests in Guatemala (PROBOSQUE), Decree 2-2015. Article 6 indicates that the National Forestry Institute (INAB) will promote the operation of compensation mechanisms, so INAB, a partner of the Project, will formulate the regulations. | S
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level |  | 1 technical manual for the National Institute of Forests (INAB) developed . |  | In the period reported from July 2, 2015 to July 1, 2016, three technical manuals were formulated. During the current period, the "Manual of technical guidelines for the planning, organization, management and control of compensation mechanisms for ecosystem and environmental services associated with forests, within the framework of the PROBOSQUE Law", Decree 2-2015 was prepared. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Johnny Ayendi Toledo González
| Email: | proyecto.pprcc@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The current report has been completed at 21 months of implementation. Actions have been continued in the 4 outcomes, optimizing the sequential and simultaneous interdependence of some activities to achieve results. At the end of the second year (July 2017), the further results of several outputs is expected; including making visible in the third year the implementation of processes such as: closure of small grant projects for community organizations that support value chains and construction of storage centers, implementation of bioengineering works, implementation of financial and microfinance mechanisms . The Project has achieved a good level of financial and technical execution according to the timeline of implementation, partly thanks to the implementation of different strategies that have allowed the participation of local partners, which has facilitated the field processes. . The pace of implementation is actually faster than expected, so the issuing of the third disbursement is becoming essential to meet the commitments. At the 21/48 execution month, the Project has executed USD 1,979,700.70 (39.6%). In addition, it has committed USD 524,914.07 (10.5%) through contracts signed with local consultants, small grants, project management unit costs. During the month of April 2017 the Project will sign small grants in the amount of USD 815,300.00 (16.3%). Therefore, the project plans to achieve a financial execution of 66.4% during the next 6 months, which requires disbursement of additional financial resources in order to cover the commitments. The coordination and planning synergies have continued at three levels: (i) The two departmental inter-institutional coordination committees (Sololá, Suchitepéquez) have held bimonthly meetings; (ii) With the municipalities, a synergy has been achieved to coordinate processes ranging from administrative and territorial planning, identifying the major needs of municipalities in issues of adaptation to climate change as a transversal variable in planning. (iii) Implementation of coordination letters with partner institutions (National Institute of Forests (INAB), National Institute of Science and Technology (ICTA), National Institute of Seismology, Volcanology, Meteorology and Hydrology INSIVUMEH) and the Faculty of Agronomy of University of San Carlos of Guatemala (FAUSAC)). The route to be followed for upcoming deliverables consists of: (i) Implement studies that indicate the options of financial mechanisms, microfinance, design of engineering works, ecoproductive chains, construction of collection centers; for which the modality of small grants will be used; (Ii) Integrate the information and implement the technical agreements reached with local governments, institutional partners and the Project Management Unit, systematizing good practices as lessons learned. This is planned over a 12-month horizon.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1 Nine new meteorological stations installed and operating and climate change scenarios downscaled in the target municipalities |  | 9 meteorological stations installed and functioning within the Nahualate River basin, as a strengthening to the national meteorological network. Climate information bulletins will be developed and disseminated. Professional training will be provided to members of the inter-agency team. |  | The project facilitated the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) strengthening through a new database build under the World Meteorological Organization (WMO) standards. INSIVUMEH is now gathering information of new meteorological station, by coordinating with private sector institutions such as Climate Change Institute and National Coffee Association. The project is currently facilitating the process to identify the potential location of new meteorological stations in the Nahualate River basin, taking into account parameters of territoriality and representativeness Of living areas. | MS
| 1.2 The management strategy for the Nahualate River watershed and 11 municipalities in the departments of Sololá and Suchitepéquez integrate adaptation measures into climate change and variability in their planning. |  | 12 Municipal strategic plans developed and delivered to municipalities for their operationalization. 12 Municipal strategic plans in process of elaboration. The biophysical characterization of the basin and of the 19 sub-basins is completed. As a basis for developing the watershed management strategy. |  | The project has been an excellent bridge between the Ministry of the Environment mandate and the National Planning System. The municipalities supported by the project count with Municipal Strategic Plans, that incorporate adaptation measures for municipal investment and land use planning. The 12 municipalities supported by the project are consider the first cohort of municipalities that achieved the new planning methodology promoted by the National Presidency Secretariat for Planning - SEGEPLAN. | HS
| 1.3 Technical, legal, and financial assessments to support the design of new and innovative financial mechanisms that support adaptation processes and initiatives at the national and local levels |  | Design financial mechanisms derived from the identification of financial mechanisms implemented in Guatemala. |  | The identified financial mechanisms implemented in Guatemala analysis has led to facilitate the preparation of two financial mechanisms proposal for the Nahualate biasing: (i) Private-private: including actors from the Ixtacapa River sub-basin, involving 9 communities located in the upper part of the sub-basin and private owners of Farms located Mainly producers of sugar cane, rubber and coffee; (ii) Public-private: includes actors of municipal government and communities; The implementation proposal is being discussed jointly with the National Forestry Institute (INAB) and the municipalities. The project is currently facilitating the dialog, coordination and consultation between the local stakeholders. The financial mechanism will be a highly participatory process. | HS
| 2.1 At least 200 hectares of natural forest preserved through the protected areas mechanism and forest incentive program |  | 200 hectares of natural forest under conservation by means of a protected area or forestry incentive. |  | The process led by the project, regarding the number of hectares of natural forest under conservation by means of a protected area or forestry incentive, have been achieved and surpass. Up to the current reported period, there are 312.90 hectares with natural forest authorized by the municipal government for conservation under the figure of protected area (Regional Municipal Park). Pending registration to the National Council of Protected Areas (CONAP) to account for the area of the project indicator. These 312.90 hectares would add to the 34.35 hectares of natural forest conservation under the forestry incentive figure, reported for the previous period (July 02, 2015-July 1, 2016). | MS
| 2.2 Ancestral and traditional productions systems and hydrometeorological risk practices implemented by community-based organizations |  | Implementation of 10 ancestral practices identified in the Nahualate River Basin through a participatory assessment of local community organizations. Finished the study on identification of archaeological sites and indigenous ceremonial sites, with tourist potential. |  | The expected progress has been almost achieved during the reported period. 10 ancestral practices have been implemented through 8 small grants local projects. Examples of the ancestral practices are: inter-planting with beans (as fertilizers), planks in orchards, contour planting, incorporation of organic matter, coverage with crop residues, minimum tillage, the milpa system, furrows with plants (beans - aboneras), selection of seeds, orchards. Also, it is important to mention that 4 new value chains are strengthened: honey, cocoa, peas and mashan. The study on identification of archaeological sites and indigenous ceremonial sites has been concluded. The study generated 5 proposals of potential routes for local eco-tourism development. Currently, the project will facilitate the proposals discussions at the level of the Inter-Institutional Coordination Committee to promote joint implementation with the Guatemalan Tourism Institute (INGUAT) of local tourism as an economic alternative for families, supporting watershed conservation. | S
| 2.3 Investments toward climate-resilient productions practices developed by community-based organizations in target municipalities |  | Implementation of small grants projects in the Project area, with a focus on adaptation to climate change. Carried out the training in Crystal Methodology, focusing on adaptation to climate change and food security. |  | 18 small grant projects are currently under implementation. The projects delivery and result achievement is 73% for the 18 projects. The small grants projects include the participation and active involvement of 1,621 households of members of community-based organizations that are improving their income. The project facilitated the training of 21 technicians from government institutions, small-scale project coordinators and the PPRCC Project, in the use of the tool "Capacity Analysis and Climate Vulnerability (ACVC) and CRiSTAL, to assess the effects of climate change on livelihoods of the communities. | S
| 3.1 Mechanisms to improve conservation, storage, and handling of produce from climate resilient production systems are strengthen in Solola and Suchitepéquez |  | Impulsing of 4 productive chains. Identification of sites for bioengineering works. |  | Honey, cocoa, peas and mashan are 4 identify production chains, supported by 9 new small grant projects. Each commodity will have a storage center. Thirty-six sites have been identified for bioengineering, considering the small-scale manual of civil engineering and bioengineering developed by the Project. | S
| 3.2 Institutional and social networks strengthened to build more climate-resilient social environments |  | Proposed identification of strengthening of two institutional or social networks. |  | The honey, cocoa, peas and mashan’s community network/groups are being supported by strengthening the production line. In April 2017 will begin with the implementation of 9 projects of small grants to promote the strengthening of networks. | S
| 3.3 Technical assistance to determine the feasibility of existing microfinance mechanisms to provide financing for climate-resilient activities and provide recommendations for design and implementation |  | The prefeasibility study completed to incorporate the insurance scheme in the climate index in Guatemala. |  | The "Financial Mechanisms for Coverage of Risks Related to Adaptation to Climate Change for the Agricultural Sector" has been under discussion between the Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN). Both Ministries are discussing the feasibility of implementing this mechanism in Guatemala for the agricultural sector and the link with the Law of Climate Change. | S
| 4.1 Establishment of an information system, based on existing sub-national and national centers of expertise, to support more robust science-based decision-making |  | The web site for the exchange of climate information of the National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH) is implemented and fully operational, supporting technicians capacity with quality data. |  | The website has proven to be an excellent tool for INSIVUMEH, by strengthening the technicians capacity and quality of the data. | S
| 4.2 Development and implementation of an awareness and advocacy program on climate change for a range of target audiences |  | Implementation of the awareness and awareness program through a radio campaign. |  | The radio communication campaign has the potential to scale up due to the agreement signed between UNDP/Guatemala and the National Federation of Community Radios. The campaign aims to reach at least 240,000 women (51%) and 234,000 men (49%). By broadcasting in four languages: Quiché, Kakchiquel, Tz'utujil and Spanish, the campaign is expected to be a success. | S
| 4.3 Documentation of lessons learned and best practices derived from efforts to develop more resilient production systems, including ancestral and traditional practices |  | Preparation of 5 short videos about project beneficiaries and actions. |  | UNDP financially supported the identification of five life stories of specific beneficiaries. Each story is told by a beneficiary, a person that tell how the Ministry of the Environment and Natural Resources, thru the project, will generate a change on that person live. The videos can be seen at the following links: 1. Our family's livelihood: https://youtu.be/jY6o2Sx7t4g 2. In favor of the forest: https://youtu.be/-epWWyz1g0I 3. It's never too late to change: https://youtu.be/4_r9Ozg_0hI 4. Honey: an alternative to community development: https://youtu.be/RPuhXOuTsHo 5. Cocoa is my business: https://youtu.be/JQqzUdCdyAw | S
| 4.4 Formulation of four technical standards for mainstreaming climate change into planning and programming processes |  | Technical Guidelines on Ecosystem Compensation Mechanisms and Environmental Services Associated with Forests developed. National Institute of Forests (INAB). |  | The project facilitated the development of the regulations on Technical Guidelines on Ecosystem Compensation Mechanisms and Environmental Services Associated with Forests, in accordance with the provisions of Articles 6 and 19 of the Law on Promotion of Establishment, Recovery, Restoration, Management, Production and Protection of Forests in Guatemala (PROBOSQUE). | MS
| 4.5 Creation of four manuals on new, traditional, and ancestral adaptation practices at the community level |  | 1 technical manual for the National Institute of Forests (INAB) developed |  | The project facilitated the development of the "Manual of technical guidelines for the planning, organization, management and control of compensation mechanisms for ecosystem and environmental services associated with forests, within the framework of the PROBOSQUE Law". | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Flor de Maria Bolaños
| Email: | flor.bolanos@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The Project is rated as Satisfactory due to the advances with evidence in the fulfillment of results and the acceleration shown in the delivery rate. Project Management Unit has been adequately restructured following the change of personnel of the field technicians. Coordination actions with the Ministry of Environment and Natural Resources are dynamic and coordinated, despite the change of gov. official who serves as Project Director. It is highlighted that the present report shows the progress in the fulfillment of the 4 outcomes, in a period of time of 9 months. The Project Management Unit, the Ministry of Environment and UNDP took the decision to present this progress report to request the third disbursement to the Adaptation Fund. The reason for this request is to comply with the results presented and the financial commitments acquired by the project, current and planned in the 2017 Annual Work Plan. The third disbursement of AF is necessary to meet the commitments planned by the project in 2017. The project has facilitated the formation and strengthening of local networks, fostering inter-institutional coordination between representatives of central government institutions present in the territory, municipal authorities and civil society (women's groups, producers, local associations and others). The project catalyzes on the ground, government programs and activities. An example of this is the Rural Extension Program of the Ministry of Agriculture, through which 141 women from community groups organized in Rural Development Learning Centers (CADER) have used demonstration plots to teach conservation practices. Likewise, the project has facilitated the strengthening of the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH), by means of entering historical information of 26 meteorological stations of private associations (Institute of Climate Change and National Coffee Association) to the national network Meteorological. Progress in the identification of productive practices resilient to the climate is highlighted by the award of 9 new small grants projects, to have a total of 27. Local organizations promote through small grants 10 ancestral or traditional practices: inter-planting with beans (as fertilizers), planks in orchards, contour planting, incorporation of organic matter, coverage with crop residues, minimum tillage, the milpa system, furrows with plants (beans - aboneras), selection of seeds, orchards. Likewise, 4 new value chains are strengthened: honey, cocoa, peas and mashan. The social communication strategy is underway and the radio communication campaign in the local language has begun. At the national central level, the challenge of consolidating the national Central Inter-Institutional Coordination Committee persists, including the participation of other key actors such as the National Council of Protected Areas (CONAP) and the Ministry of Agriculture, Livestock and Food (MAGA), the National Institute of Forests (INAB), National Institute of Science and Technology (ICTA), National Institute of Seismology, Volcanology, Meteorology and Hydrology INSIVUMEH) and the Faculty of Agronomy of the University of San Carlos de Guatemala (FAUSAC) .
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective: to increase climate resilience in production landscapes and socio-economic systems in target municipalities, threatened by climate change and climatic variability impacts, in particular hydrometeorological events that are increasing in frequency and intensity | O.1. Number organizations (including cooperatives, community producers and watershed management committees) that incorporate climate change adaptation measures for reducing vulnerability. | In project target area there are community organizations only on an ad hoc and informal basis, formed in order to address specific activities (e.g. receive government assistance, maintenance work or community reforestation), but not continuously or systematically, and lacking legal foundation. Other examples are producer groups, including for honey, organic coffee and cocoa, banana (more common in Suchitepequez). Their knowledge and understanding of climate risks and adaptation measures are low. In the inception phase of the project a detailed analysis of the organizational level of communities and non-profit organizations was performed. This analysis identified seven non-governmental organizations (NGOs) and 3 cooperatives, that are called local organizations. These 10 organizations have legal registration, and have administrative capacities conditions to receive and manage small grants. These NGOs therefore serve to channel and manage small grants funds to a number of community-based producer organizations, which have no capacity for administrative and financial management and do not have legal registration. In addition, the project will support the establishment of legal watershed management committees (which currently do not exist), and also help producer and community organizations to be formalized and registered as part of the sustainability measures. In the project area there is a network of agricultural extension called CADER (Learning Centers for Rural Development),a Rural Extension System of the Ministry of Agriculture, Livestock and Food (MAGA). The CADER is a group of farmer families who practice non-formal teaching and learning processes, using collaborative and learning by doing approach. The CADER is directed voluntarily by a person of the community, which is known as a promoter, the only requirement is to have the courage to work for their benefit and that of the other members. The CADER system is supported by the Project on training issues within the framework of agreements with the Ministry of Agriculture, Livestock and Food (MAGA). | Forty (40) organizations (cooperatives, community producers and watershed management boards) have incorporated climate change adaptation measures to reduce their vulnerability. This result has been achieved through two strategies: (i) implementation of community projects; and (ii) strengthening the Ministry of Agriculture, Livestock and Food (MAGA) to support community groups organized in Rural Development Learning Centers (CADER), using demonstration plots to teach conservation practices. See press releases: https://goo.gl/O5Ceyj; Https://goo.gl/CbVnFD; Https://goo.gl/jd4Rva | At project end, at least 50 organizations (including cooperatives, community producers and watershed management committees) have incorporated climate change adaptation measures for reducing vulnerability.
| O.2. Number of funding mechanisms developed to support national processes of adaptation (payments for environmental services, certifications, budget planning at local and central government level) established to support climate change adaptation processes. | Government authorities have been considering means of funding for climate change adaptation. Although climate change is being identified as a priority, specific funding mechanisms are non existent or insufficient to address adaptation needs to current and projected climate change. | Zero (0) financial mechanisms established to date. Financial mechanisms implemented in Guatemala have been identified for payments for environmental services, certifications, central and local government budget planning, with the purpose of knowing technical and legal designs, lessons learned during the implementation and the role of the actors involved. To date, the Project has facilitated the preparation of two proposals for financial mechanisms: (i) Private-private, including actors from the Ixtacapa River sub-basin, involving 9 communities located in the upper part of the sub-basin and private owners of farms located Mainly producers of sugar cane, rubber and coffee; (Ii) Public-private, includes actors of municipal government and communities; The implementation proposal is being discussed jointly with the National Forestry Institute (INAB) and the municipalities. The implementation of the financial mechanisms will be promoted in the next 12 months. The implementation process will be approved by the Interagency Coordination Committee. | At project end, the project will have supported the implementation of at least one financial mechanism (payment for environmental services, certifications, budget planning central and local government) with a level of support agreed by the inter-institutional support committee.
| O.3. Number of Ha area under climate-adaptive agricultural practices | 0 Ha currently. In the project area there is approx. 8200 Ha area under annual cultivars and in an overused status. Current agricultural production is at subsistence level and practiced in small lots with intensive cultivation cycles of 2-3 crops per year. In these areas there are some initial and ad hoc measures pointing towards soil and water conservation (some terrace forms, contour planting, intends of irrigation), but without using effective and integrated adaptation techniques, and lacking systematic and landscape level applications. | 247 hectares have good agricultural practices to adapt to climate change; 200 hectares reported in the current period and 47 hectares reported in the previous period. During the 2017 sowing and planting season/period, it is expected to achieve the proposed target for the Project. | At project end, at least 500 Ha area under climate-adaptive agricultural practices.
Outcome 1: Local and national capacities and tools enable decision makers and communities to reduce vulnerabilities and strengthen adaptive responses. | 1.1. Availability of downscaled climate scenarios and early warning information | Currently, national capacities to manage and analyze information from weather events and risks are reduced and limited to application of regional models, and currently there is no downscaled climate projection, neither early warning information available for users in the target region. Only INSIVUMEH has trained experts on downscaling and will be supporting the project in preparing downscaled projections and in training process. | The national meteorological network was strengthened by inputting historical information from 26 weather stations of local agencies (Climate Change Institute and National Coffee Association) and managing information from 53 additional weather stations. A new review of the field report issued by the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) will be made, in view of these results, to determine the potential location of new meteorological stations in the Nahualate River basin, taking into account parameters of territoriality and representativeness Of living areas. The technical capacity of the National Institute of Seismology, Volcanology and Hydrology (INSIVUMEH) was strengthened through a new database of World Meteorological Organization (WMO) standards and the purchase of a high-capacity data storage server. With this strengthening, the inter-agency team is expected to make timely climate projections. INSIVUMEH issues bimonthly bulletins, which have up-to-date climate information; The Project will strengthen the design of the newsletter, content and reach of information users. In addition, the development of a web portal that allows users to download information about each weather station and climate projections (scenarios). | At the end of the second year, the national meteorological network will be strengthened with nine new stations, installed and operating within the river basin Nahualate. At the end of the second year, an interagency team (INSIVUMEH, MARN, MAGA, among others) will be able to create downscaled climate projections and promote its use in the reviews of national, departmental and municipal planning. At the end of the third year, early warning information generated will be available and disseminated to users in the region (including through quarterly newsletters).
| 1.2. Number of strategies and development plans adopted and implemented, incorporating information on climate change risks and adaptation measures. | Guatemala has established a Territorial Planning System (SINPET) that allows the integration of sectoral policies and strengthens development processes. In this context, the country has developed plans, which have not yet incorporated risks of climate change and adaptation measures. | 3 Municipal Development Plans prepared, pending approval by municipal authorities; 7 more plans in process of elaboration; This instrument of municipal planning provides the guidelines and strategies for the administration of the territory, involving central and local government actors. This is in addition to what was reported in the previous period, 12 Institutional Strategic Plans that incorporate adaptation measures within municipal government planning for the period 2016-2020, approved by the municipal authorities (see press releases: https://goo.gl/fVoFcf, https://goo.gl/JMsVv3 Finished the study on the biophysical characterization of the basin of the Nahualate River and 19 sub-basins. This study provides information on the physical details, climatology and climatic scenarios, important for the strategic planning of the 2018-2050 basin. | For the third year, the management strategy for the Nahualate Watershed, 12 municipal development plans and 12 municipal institutional strategic plans mainstream climate change risks and opportunities, and incorporate adaptation measures.
| 1.3. Number and type of financing mechanisms identified and assessed by MARN and relevant stakeholders. | There are no public-private partnerships to support adaptation processes, or mechanisms for national or local funding. | Financial mechanisms implemented in Guatemala have been identified for payments for environmental services, certifications, central and local government budget planning, with the purpose of knowing technical and legal designs, lessons learned during the implementation and the role of the actors involved. To date, the Project has facilitated the preparation of two proposals for financial mechanisms: (i) Private-private, including actors from the Ixtacapa River sub-basin, involving 9 communities located in the upper part of the sub-basin and private owners of farms located Mainly producers of sugar cane, rubber and coffee; (ii) Public-private, includes actors of municipal government and communities; The implementation proposal is being discussed jointly with the National Forestry Institute (INAB) and the municipalities. | At project's second year, financial mechanisms existing in Guatemala (payments for environmental services, certifications, central and local government budget planning) will be identified and assessed for suitability for target region, including mapping and evaluation of institutional capacities.
Outcome 2: Production landscape resilience increased through application of traditional and ancestral practices and other production activities, as well as targeted investments. | 2.1. Number of ha of natural forest subject to conservation through the protected area or forest incentives mechanisms | In the project area 5,885 hectares of forest areas have been declared as protected areas under the management of municipalities. However, capacities of local municipalities and communities is very limited for effective management of these areas to prevent deforestation, and especially considering capacities of fire prevention and control, risk of it being increasing with changing climatic conditions. Currently there are no areas under conservation management using forestry incentives. Nevertheless, within the Nahualate River watershed, there are areas with natural forests where protected area status can be potentially expanded and conservation management enhanced under the existing forestry incentives programs in Guatemala (PINPEP - Forestry Incentive Programme for Small-holders of Forestry and Agricultural Use, administered by the National Forest Institute). There is a need also to support the conservation of areas that are strategic for water recharge and protection of water sources that supply urban populations. | 312.90 hectares with natural forest authorized by the municipal government for conservation under the form of protected area; To account for this area to the indicator, the registration resolution of 3 protected areas under the category of Municipal Regional Parks is managed through the National Council of Protected Areas (CONAP). 34.35 hectares of conservation of natural forest under the form of forest incentive, were reported in the previous period (July 02, 2015-July 1, 2016). | By the end of the project effectiveness of protection and conservation management is enhanced in the existing 5,885 hectares of protected areas. By the end of the project at least 200 hectares of additional natural forest areas are subject to conservation through protected area or forestry incentive mechanism.
| 2.2 Number of ancestral and traditional practices recovered for increased resilience of productions landscapes adopted by the communities in the target area of the project | In the project area recovery of ancestral practices are only focused on the use of biological diversity (CONAP), however not related to production practices. | 10 ancestral or traditional practices have been identified in the Rio Nahualate. The small grants mechanism will promote the implementation of such practices. | By the end of the Project, at least two traditional or ancestral practices in target area and related to increasing the production landscapes resilience are recovered and implemented
| 2.3 Number and type of adaptation measures implemented by CBOs and NGOs (based on catalogue established by the project). | Communities are applying some initial and ad hoc measures contributing towards adaptation, mainly related to soil and water conservation (some terrace forms, contour planting, intends of irrigation), but without using effective and integrated adaptation techniques, and lacking systematic and landscape level applications. | 15 different measures of adaptation to climate change have been promoted, through local and community organizations. 21 technicians from government institutions, small-grants project coordinators and the PPRCC Project, trained in the use of the tool "Capacity Analysis and Climate Vulnerability (ACVC) and CRiSTAL, to assess the effects of climate change on livelihoods. See press release: https://goo.gl/gmKCzM). 9 demonstration plots established jointly with the Institute of Agricultural Science and Technology (ICTA), with biofortified maize and bean yield crops, as an alternative to local genetic material. | By the end of the project, at least 15 different types of adaptation measures (including land use, water management, forestry and agriculture measures) are implemented through community-based adaptation
Outcome 3: Socio-economic adaptive capacity of communities improved. | 3.1. Percentage of targeted households with a more secure access to income for livelihoods (disaggregated by gender). | Currently agriculture production in the communities and targeted families is of subsistence, there is a very low level of marketing of products using local markets or through direct sale to intermediaries who approach communities seasonally, but this is not practiced systematically nor in a organized way, and there are no differentiated strategies for productive chains and product marketing. A household survey on income levels is planned to take place in October 2016, which will define the baseline. | 1,621 households of members of community-based organizations are improving their income through the implementation of 18 small-grant projects. In addition, 1,492 households of members of community organizations will improve their economic incomes by implementing 9 new small grant projects approved by the Selection Committee to promote 4 production chains: honey, cocoa, peas and mashan 2017). The results of household income measurements will be reported in the following period. | At project end, at least 50% of households from members of community organizations involved (approximately 1,500 Total households) have more secure income access for their livelihoods.
| 3.2. Number and type of social networks for production in the target area (indicating gender composition). | None | Through the model of productive chains 4 networks of community groups will be strengthened: honey, cocoa, peas and mashan. In April 2017 will begin with the implementation of 9 projects of small grants to promote the strengthening of networks. Pending will remain the implementation of the organic coffee chain. | By the end of the Project, at least two social networks (associations/production cooperatives/marketing associations) formed or strengthened and operating.
| 3.3. Number of feasibility studies of microfinance schemes completed; number of options identified, described and supported with project technical assistance. | Weak organization and lack of market information hinders the marketing of traditional products and reduces the potential for innovation in production processes and alternative marketing. | The discussion and socialization of the "Financial Mechanisms for Coverage of Risks Related to Adaptation to Climate Change" was jointly promoted with the Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN) For the Agricultural Sector, "evaluating the availability of these mechanisms in Guatemala for the agricultural sector and the link with the Climate Change Law. See press release: https://goo.gl/ORV9pk Pending the promotion with community groups, the implementation of microfinance mechanisms proposed in the study carried out by the Project. | By the end of the project, access to micro-finance relevant to develop climate change adaptation initiatives by farmers associations from Solola and Suchitepequez will be identified and prioritized.
Outcome 4: Effective knowledge management results in informed decision-making at all levels through an integrated information system. | 4.1. Inter- institutional information system of climate change designed and operating in a coordinated manner at multiple levels, running. | Currently there are no information centers working in coordination, and no initiatives linking various levels of climate change problems. Information on climate change is not available for decision-making at all levels. | (i) Social communication strategy completed. (ii) Interaction with the institutions of government and civil society through web subportal (http://marn.gob.gt/s/pprcc). (iii) Three memorandums of understanding signed with government entities: National Forest Institute (INAB), National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH) and the Institute of Agricultural Science and Technology (ICTA) (v) A memorandum of understanding signed by a government entity: Ministry of Agriculture, Livestock and Food (MAGA). (vi) The web subportal for the exchange of climate information of the National Institute of Seismology, Volcanology, Meteorology and Volcanology (INSIVUMEH) is in preparation, where the interested public will be able to download climatic information on each meteorological station of the country and information on climatic scenarios by municipality that is (INSIVUMEH), the Ministry of Agriculture, Livestock and Food (MAGA) and the Ministry of Environment and Natural Resources (MARN). | From the first year of the project, an information and inter-institutional communication system will be developed for adaptation to climate change which will operate in a coordinated manner.
| 4.2. Percentage of targeted population affirming awareness of predicted adverse impacts of climate change and appropriate response. (disaggregated by gender) | At the moment there is no awareness programs focused on climate change issues. Knowledge of the population on climate change is very low. | The radio campaign began in March 2017, in order to raise awareness and promote the issue of climate change to the target population. The campaign is broadcasted in four languages: Quiché, Kakchiquel, Tz'utujil and Spanish. The estimated potential audience for the 12 municipalities of the Project is 240,000 women (51%) and 234,000 men (49%). At the end of the campaign in March 2018 will measure the coverage and impact data of the radial campaign. | At the end of the project, at least 70% of the rural population of municipalities (total of 85.341 rural people) in the target area are aware of predicted adverse impacts of climate change and appropriate response. (disaggregated by gender)
| 4.3. Number of lessons learned and best production practices included in Project dissemination strategies and shared on UNDP, MARN, and ALM websites. | There is no public information with a multicultural approach to vulnerability and adaptation practices to climate change. Information on climate change is at a large scale and does not offer the precision required for decision making at the local level. | Five videos were prepared on livelihood histories that address the current conditions of the beneficiaries and their expectation of the initial support provided by the Project. The final versions subtitled in English will be available in the month of April 2017. In the reported period from July 2, 2015 to July 1, 2016, a standard was formulated. During the current period, the regulations on Technical Guidelines on Ecosystem Compensation Mechanisms and Environmental Services Associated with Forests were formulated, in accordance with the provisions of Articles 6 and 19 of the Law on Promotion of Establishment, Recovery, Restoration, Management, Production And Protection of Forests in Guatemala (PROBOSQUE), Decree 2-2015. 3 manuals reported during the period from 2 July 2015 to 1 July 2016. During the current period, the "Manual of technical guidelines for the planning, organization, management and control of compensation mechanisms for ecosystem and environmental services associated with forests, within the framework of the PROBOSQUE Law", Decree 2-2015 was prepared. | During the Project implementation there will be: ten lessons learned systematized and published annually, four technical standards developed, and four manuals designed and published.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | (i) The formation of technical teams and the incorporation of local organizations facilitated the implementation of small grants projects. The administrative structure created for implementation support has worked effectively. This is reflected in the good technical and financial execution achieved by the Project in this reporting. (ii) The Project Management Unit has maintained close coordination for the implementation of field activities, with local government partners and community organizations, through monthly work meetings, incorporating existing institutional and community structures so as not to duplicate ort overburden existing stakeholder mechanisms. This has allowed the Project to coordinate and facilitate actions with local authorities, municipal and institutional technicians, as well as community producers. This is one of the strategies that have given greater success to the implementation of the project, reflected in the rate of execution. (iii) The actions of the project have been socialized with other forms of government arrangements, such as the mancomunidades (groups of municipalities), which together with the traditional indigenous authority in the municipalities with which close communication has been maintained, has positively favored Implementation of the Project. The mancomunidades carry out planning and decision making on common themes for several municipal governments. (iv) The field technicians have been placed according to the local language situation that facilitated the implementation of the Project, valuing the beneficiaries the transfer of knowledge orally and in their language.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The Project achieved a good financial execution pace according to the implementation timeline, which indicates that it has overcome the delays that were initially occurring at the startup. The pace of implementation is faster than expected, estimated to be maintained, so according to estimation, the third disbursement is expected to meet the plans and commitments. At the 21/48 execution month, the Project has financially executed USD 1,979,700.70 (39.6%). In addition, it has committed USD 524,914.07 (10.5%) through contracts signed with local consultants, small grants, project management costs. During the month of April 2017 the Project will sign small grants in the amount of USD 815,300.00 (16.3%). That is, the Project will achieve a financial execution of 66.4% during the next 6 months, which requires additional financial resources to cover the commitments acquired and not to stop the good execution performance. The scope of this execution and commitments reached is due to the planning implemented by the Coordination of the Project Management Unit, which has been able to order the administrative processes and the times to make the selection of external support of consultants, activities with community groups and institutions, optimizing linkages between activities These actions have been complemented by monthly technical meetings with the local technical team, which has allowed identifying and adjusting the sequence of implementation and interrelationship of the Project activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The pace of implementation is faster than expected, thanks to the setting up of a strategy based on the incorporation of government partners and local partners into joint decision making, which has made it possible to link the programming of activities directly with territorial level actions by the partner gov. institutions and catering to the needs of the populations by facilitating participatory processes in the definition of the small grants projects.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | (i) The implementation of means of adaptation (agricultural, forestry and bioengineering) identifies the role of women in the household economy and conservation of natural resources. The gender approach has made it possible to work in a harmonious way the initial actions of implementation of the Project with both men and women. (ii) Value chains, currently in the initial stage, have identified women's participation, mainly in manufacturing activities, but also in the organization's decision-making structures (boards of directors).
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | GTM/MIE/Rural/2010/1
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Guatemala
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 67000 | 7500 | 59500 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50.67% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 12 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 12 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 12 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 90% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 7500 | 50.67% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 5885 | ha protected | 1: Ineffective | Forests | 6085 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 500 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 191 | 30% | From 0 to 0.5% | Agriculture | 1500 | 30% | From 1% to 5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Public policy | 24 | Multi-sector | Local | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.