## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | November 1, 2020 - October 31, 2021
| Project Title: | Enhancing the Resilience of the Agriculture Sector and Coastal Areas to Protect Livelihoods and Improve Food Security
| Project Summary: | Jamaica is vulnerable to climate related hazards, in particular hurricanes, floods, storm surges and droughts, due largely to its geographical location and the exposure of social and economic assets in coastal areas. This situation is made worse by the country’s low adaptive capacity especially in the climate sensitive sectors of the economy. The agriculture sector and coastal resources are among those at greatest risk, given their significant contribution to the country’s GDP and to the labour force. The activities identified in Government of Jamaica Adaptation Fund Programme (GOJ/AFP) are drawn from the adaptation priorities that were identified in the vulnerability and adaptation assessments for the agriculture and coastal resources sectors. The GOJ/AFP focuses on environmental and natural resource management activities; namely, coastal rehabilitation, inland flood and erosion control, and land and water management. The overall objective of the GOJ/AFP is to protect livelihoods and improve food security in vulnerable communities by: • improving land and water management for the agricultural sector • strengthening coastal protection; and • building institutional and local capacity for climate change adaptation and natural resources management
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | JAM/NIE/Multi/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Planning Institute of Jamaica (PIOJ) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity (NIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jamaica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 -- Increasing the Climate Resilience of the North Eastern Coastline Location: Annotto Bay (St. Mary), Buff Bay and Orange Bay (Portland) Component 2 -- Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas, Portland and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness-raising for behaviour modification Location: Westmoreland/Hanover/St.Mary/Portland; some target communities in Component 2 | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-29
IE-AFB Agreement Signature Date: |  | 2012-07-23 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-02 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2015-08-01
| Original Completion Date: | 2016
Revised Completion Date after approval of |  | 2022-09-01
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception Report :submitted December 2012 2. Extension Requests: April 2016, July 2017; November 2018; March 2020 3. Mid-Term Report: submitted 2016 4. COVID-19 related extension: April 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.pioj.gov.jm/programmes/goj-adaptation-fund/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Claire Bernard | Dominican Republic
| Email: | cbernard@pioj.gov.jm | Ecuador
| Date: | 2011-01-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Una May Gordon | Equatoral Guinea
| Email: | unamay.gordon@megjc.gov.jm | Eritrea
| Date: | 2016-08-01 | Estonia
| National Implementing Entity |  | Ethiopia
| Name: | Shelia McDonald-Miller | Fiji
| Email: | smmiller@pioj.gov.jm | Finland
| Date: | 2012-12-03
Name:
Email:
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | I.W. Wilson | Georgia
| Email: | IWWilson@micaf.gov.jm | Germany
| Date: | 2013-02-01 | Ghana
| Executing Agency |  | Greece
| Name: | Roger Smith | Grenada
| Email: | rsmith@nwa.gov.jm | Guatemala
| Date: | 2011-12-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Sophia Mitchell | Guyana
| Email: | smitchel@odpem.org.jm | Haiti
| Date: | 2020-01-01 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of October 31, 2021 | 4903508
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 336.72
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | PROGRAMME COMPONENT | ITEM / ACTIVITY / ACTION | AMOUNT
|  | Preliminaries | 632
| COMPONENT 1 | Coastal Works-Hard Solution a. Land reclamation b. Revetment c. Parapet walls d. Geotexttile | 465952
|  | Non-structural(reforestation) a. fruit trees b. timber trees c. non-fruit timmber | 24375
|  | Engineering Services | 76684
| SUB-TOTAL 1 |  | 567643
| COMPONENT 2 | 2.2 Establishment of small scale irrigation facilities | 0
2.3 Implementation of rainwater harvesting and drip irrigation systems
|  | 2.4 Establishment and rehabilitation of soil conservation and land husbandry infrastructure | 0
| SUB-TOTAL 2 |  | 0
| COMPONENT 3 | Training of local communities and entities in disaster risk reduction (DRR) and natural resources management | 3476
Establish farmer field schools to develop solutions and demonstrate good practices
Conducting workshops and farmer training in climate smart agriculture
| SUB-TOTAL 3 |  | 3476
| EXECUTION COST |  | 20954
| GRAND TOTAL |  | 571119
0
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 | US$
| Coastal Works-Hard Solution a. Land reclamation b. Revetment c. Parapet walls d. Geotextile | 3260272 | Annotto Bay 3 - July 2022 Other sites - August 2023
| Non-structural (reforestation) a. fruit trees b. timber trees c. non-fruit timmber | 500000 | September 2022
| Engineering Services | 90450 | 2022-07-01
| Environmental Monitoring (NEPA) | 10632 | September 2022
| Execution costs | 21000
Component 3
Development of adaptation plansfor the targeted areas
| Capacity building and training in deep sea fishing, business development, natural resources management | 35439 | December 2022
| Climate Change awareness and education programmes developed and implemented in project communities | 22000 | 2022-12-01
| TOTAL | 3939793
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial: budget over-runs/under-spend; mis-use of funds; inflation/ currency depreciation leading to increased costs for goods/services | Moderate | Challenges on the original Component 1 led to a request to changes in programme outcome, outputs and related indicators. This addition to the original programme schedule meant that additional resources (over and above the AF grant ) had to be garnered towards administration/project management activities. This gap has been addressed by GOJ financial support during the reporting period. The NIE has implemented a governance framework whereby EE work plans/budgets must be approved by the Programme Steering Committee (PSC) prior to disbursement of funds to respective EE. There were no transfers of funds during the reporting period as direct payments were made by the NIE to 3rd parties on the request of EE. Despite COVID-19, ongoing monitoring visits continue to be undertaken by the Programme Management Unit (PMU) to EE and beneficiary locations to assess progress/ verify reported expenditure and activities.
Environmental: natural hazards (flood, drought, storms/hurricanes); pests and diseases. | Moderate to High | The 2021 hyperactive hurricane season brought several weeks of continuous rains which posed a challenge to the timing and completion of some activities. Due to the island's location in the Atlantic hurricane belt, there is inherent risk of 'adverse climatic events' affecting GOJ/AFP implementation. Local specialized agencies (ODPEM, Meteorological Service, etc.) continue to provide information to the public on how to prepare for and respond to such occurrences.
Stakeholder Buy-in | Low | The development of the revised Programme ensured the early involvement of communities and organisations likely to be affected by the various activities. As a result, the GOJ/AFP has gained the cooperation and positive participation of key stakeholders. The NIE continues to maintain active contact with local communities and State actors throughout the programme. thereby gaining the buy-in from stakeholders in the target communities.
Multiple Executing Entities | Low | The programme continues to enjoy the commitment of senior management teams and staff of of EE organisations. Administratively, the PMU/NIE continues to organize and coordinate activities to improve collaboration among the project teams in the respective entities. This is often an iterative process of consultation, planning and reviewing in order to balance the differing and sometimes competing priorities.
Procurement Delays | High | Some procurement delays were experienced during the reporting period. These were mainly due to the multi-layered national approval processs of the procurement oversight authorities. The situation was further exacerbated by the changes which the COVID-19 Pandemic has necessitated ( ie delay in receipt of materials sourced overseas such as turbidity barrier and geotextile material). These all served to lengthen the procurement process with a corresponding lag to the start of critical on-the-ground activities (ie shoreline protection works).
Implementation/ Operational: delays in programme implementation schedule | High | Some implementation delays are related to the COVID-19 pandemic over which the NIE and EE have little or no control. The contractor engaged to execute the shoreline protection works has had significant delays in completing deliverables as planned for various reasons (ie supply and placement of materials, equipment failure and inclement weather). The NIE continues to hold monthly/fortnightly meetings with the contractor, EE and programme team to facilitate improvements in execution.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risks associated with the installation coastal / structural works | Low | Measures for environmental risks have already been included in the Environmental and Social Management Plan (ESMP). Additionally, an Environmental and Monitoring Plan has been developed and is being utilized as part of the monitoring framework during the construction and post-construction phases.
Low disaster risk perception in some target communities | Low | Awareness-raising activities relating to climate change impacts continue to be undertaken by the programme. Stakeholders from several target communities participated in shelters and shelter management training session which have increased their awareness and understanding of the role of shelters and shelter managements in responding to natural hazards and related impacts. Additionally the NIE , Supervising Engineers and the contractor have held meetings about the importance of the shoreline protection works with the fisherfolks who will be direct beneficiaries of the intervention when complete.
Executing Entities’ readiness to implement, including availability of human resources | Moderate | The NIE continued to provide support to the Executing Entities, especially in the area of procurement, to foster improvements in the execution framework and to ensure compliance with the Procurement Guidelines. There continues to be meetings and other oversight activities aimed at minimizing the negative impacts on the programme.
Impact of COVID-19 Pandemic | Moderate | Due to restrictions associated with the Pandemic, site operations and some work schedules have had to be reorganized resulting in implementation delays. Stakeholder consultations continue to be impacted due to social distancing requirements; however, work-around using virtual platforms have mitigated this particular risk and allowed for the effective engagement of key stakeholders.
Risks associated with changing development landscape with respect to reforestation | Moderate | Since project design, it is important to note that other new projects involved in reforestation have come on stream; this has resulted in a strain on the system to provide seedlings in sufficient quantities and in a timely manner. Additionally, small holders are challenged to put their lands into long term (tree) crops at the expense of cash crops which bring quicker monetary yields to support livelihoods. To address these risks/issues, an inter-cropping strategy is being followed and additional partnerships with the Forestry Department Private Planters Programme continue to be pursued.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All mitigation steps for the risks identified above were implemented. These measures were generally effective in reducing the relevant risks. Challenges relating to the failure of the contractor to execute the planned work as per schedule have led to a generally lower level of disbursements/expenditure than planned and therefore longer time to complete the project.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Possible changes to navigation charts based on shoreline changes | Obtain approval of Harbour Master for changes in navigation chart | Harbour Master approval requested/obtained | The Programme is closely aligned to and complies with national policies, laws, plans and priorities for sustainable development and adapting to climate change | The National Environment & Planning Agency has been consulted and their requirements have been complied with.
2 - Access and equity |  |  | Disagreements related to beneficiary selection. Distribution of benefits/selection of geographical area Non-inclusion of persons with disabilities | Develop/apply transparent and objective criteria for selection. Use participatory approach, including awareness building, involving community groups and local authorities. Utilize knowledge of forest wardens and extension officers to identify planters and local forest management committee members. ABCDEA and other community groups requested to help identify individuals using participatory approach for capacity building. | Selection Criteria developed and fairly applied in beneficiary selection. Degree of involvement of local community groups. Evidence of inclusive stakeholder engagement engagement process. Level of integration of forestry mgmt protocols. |  | Inclusive stakeholder engagement process promoted and applied Forestry Dept staff and RADA extension officers used to identify planters/farmers and distribute planting material.
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Disproportionately fewer women than men engaged in labour activities. Low female participation in capacity building activities. | Implementation of activities in accordance with the National Gender Policy, 2011 and Gender Mainstreaming Manual, 2016 and with the aid of the NIE Gender Specialist. Partner with local women's organization where feasible; organize gender training; adopt/ build on methodologies previously used by rural sociologist. Special mobilisation of women; advise contractors to give special consideration to female providers of goods/services, where possible. | Gender assessment completed before implementation of project activity. Gender training conducted; project monitoring reports include sex disaggregated information. Evidence of gender requirement in procurement guidance notes; number of female participants in sensitization activities. |  | ESP & Gender sensitization sessions undertaken by NIE with executing partners and Programme Steering C'ttee members. ESP & Gender sensitization conducted with stakeholders in target communities. Specific gender sensitization sessions incorporated in shelter management training across 4 parishes (approximately 60 participants)
6 – Core labour rights |  |  | Unsuitable working conditions | Cite relevant labour laws in contracts; use grievance mechanisms to monitor complaints; provide safety training and protective gear appropriate to work hazards. | No. of work-related incidents due to non-compliance with relevant provisions. No. of safety training conducted; protective gears provided and warning/safety signs posted at work sites.
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Seagrass beds may be disturbed if they exist in project work area. River regime altered by removal of materials for construction; encoachment on coral colony; movement of WADs post-project may contribute to coastal eco-system damage. | Conduct assessments as required by permitting process. Boulders identified from areas which will not significantly alter the river regime; extract material from licensed sites/quarries. Do bathymetric/environmental assessment and develop appropriate protocols. | Compliance with conditions of permits and licenses |  | Use of Marine Benthic Survey conducted previously as pre-condition to the granting of Beach License by NEPA. Annotto Bay Benthic Features: the substrate at the Annotto Bay sites consisted of river sand and river shingle. No ecologically sensitive systems were observed within the direct project footprint nor the working footprint of the proposed structures. The diversity and abundance of the nearshore species observed was low, especially when compared to relatively healthy typical nearshore environments such as seagrass beds. Species diversity is limited to a small fish community and meiofauna. There is reportedly a low coral cover along the northeastern coast. To date, no corals have been found in the project footprint. Comprehensive bathymetric surveys were done in 2019 (see attached extract from Design Report); the near-shore data was supplemented with off shore satellite-derived bathmetric data for the entire northeastern coastline. In 2021, pre-construction topographic and bathymetric surveys were done within the project footprint (see attached).
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Waste material generated; noise and vibrations from construction equipment. Accidental spills during transportation of material. | Implement Waste Management Plan Establish and publicize a Stakeholder Engagement Plan that includes a grievance redress mechanis Conduct health and safety awareness training for workers and target community Contractor required to design/implement workplace safety procedures in line with standard industrial practices and regulations | Traffic Managementand Waste Management Plans implemented Number of Stakeholder Engagement sessions; number of complaints received and addressed Saftey standards appropriately displayed at work sites |  | Detailed environmental management plan developed by design consultant for monitoring when shoreline works begin. Consultants are explicitly required to comply with local environmental legislation, the Environment and Social Policy and Gender Policy of the Adaptation Fund and internationally agreed core labour standards, e.g. the ILO core labour standards, conventions on freedom of association and collective bargaining, elimination of forced and compulsory labour, elimination of discrimination in respect of employment and occupation, and the abolition of child labour. Contractor required to provide monthly report of environmental monitoring measures undertaken, including deployment of turbidity barriers and daily turbidity readings. Traffic control measures, including flag personnel, have been implemented to facilitate trucks entering and leaving the work site.
13 – Public health |  |  | Increased respiratory/occular irritation Traffic congestion due to movement of raw materials | provision of protective gear (eg. dust masks, gloves, goggles, helmets etc.) to workers. Preparation of appropriate plans including, traffic management and occupational health and safety standards. Compliance with applicable environmental standards | Occupational health and safety reports; evidence of gears distributed/used Dust suppression techniques in place Number of plans/implemented |  | The programme team worked closely with the local Municipal Corporation which has responsbility for public health, sanitation and safety in the target parish. Protective gear (dusk masks, goggles and helmets) are worn; first aid kit kept on site by supervisor. Health & safety toolbox talk each week and at each new activity of works; Traffic signs and barriers are in place during material on-loading and off-loading activities.
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Risk monitoring is performed according to the ESMP
Have unanticipated ESP risks been identified during the reporting period? |  | No unexpected risks have been identified during the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Quarterly Steering Committee meetings reemphasize the ESP requirements to GOJ/AFP partners. Executing Entities are required to screen their project activities against the list of ESPs. The National Environment & Planning Agency (NEPA) continues to be a member of the PSC; NEPA has responsibility for protection of the environment and ensuring that local/national development complies with relevant statutory and regulatory requirements as well as international standards. Environmental measures monitored and reported on in contractor's monthly reports and project implementation meetings. Continuous monitoring is done by the NIE for ongoing activities.
Have the implementation arrangements been effective during the reporting period? |  | Yes. Measures to minimize negative environmental and social impacts continue to be implemented and monitored.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Coordination with relevant municipal authorities and local environmental NGOs to ensure compliance during execution of project activities. Terms and conditions of the Beach License/permit issued by NEPA continue to be monitored for compliance.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, as outlined in the ESMP.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during reporting period |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Enhanced capacity to protect livelihoods and food security by improving land and water management for the agricultural sector | Outcome | Number of farmers (male/female) with increased access to irrigation water and production schemes | small % of residents (male/female) with water storage or distribution facilities | 1000+ farmers (male/female) in 21 communities have access to irrigation water and production schemes | good
Land and water management systems | Output | Number of rainwater harvesting and gravity drip irrigation systems installed in target parishes | zero irrigation and production schemes in the 21 targeted communities in 6 project parishes | 63 schemes installed and operational in 21 communities serving over 1000 male and female farmers | good
| Output | Number of irrigation and production schemes established | Inadequate access to irrigation faciities in selected communities | 60 gravity drip irrigation systems installed and operational and serving 40 male and 20 female farmers directly | good
Agriculture Capacity Building | Output | Number of climate-smart farmer field schools established select communities | No climate smart field schools in select communities | Seven climate-smart farmer field schools established and 90% farmers (male/female) trained to adopt climate smart agriculture practices | good
| Output | Number of demonstration plots established in the Upper Rio Minho Watershed | Targeted communities do not have demonstration plots in place | Five demonstration plots established imparting skills knowledge and techniques to 1510 farmers (male/female) who are adopting sustainable practices
Awareness Building and Knowledge Management | Output | Number of targeted training programmes for local entities in DRR and NRM | Limited training DRR and natural resource management for local entities; limited exposure to training with specific focus on climate change | Training programmes targeted at fishers (mostly male), male and female youth, micro and small business owners and other groups completed | good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The NIE employs a full time Gender Specialist to ensure that gender equity is incorporated in developmental initiatives. The Programme Steering Committee (PSC), which meets on a quarterly basis, generally has equal female/male attendance and participation. The NIE and partners continue to ensure that stakeholder consultations include the active participation of both men and women. A gender sensitization session was organized by the NIE for the PSC which comprises both community level as well as institutional members. The session covered, inter alia, (i) How the PSC can assist with mainstreaming gender, for example, by ensuring that gender-informed consultations are facilitated with stakeholders prior to endorsing decisions/budget/work plans; and (ii) The distinction between gender sensitive (consideration of gender norms/roles/relations and creating gender awareness) and gender responsive (gender sensitive, plus addressing inequalities by taking remedial action within a given social setting); and (iii) - The need to ensure that there is gender mainstreaming throughout the programme cycle -- the ultimate goal of mainstreaming is to take into account the concerns and experiences of both sexes in order to achieve gender equity.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Both males and females have had equal opportunity to participate in GOJ/AFP activities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Component 1: A participatory approach used in relation to activities involving community groups (eg. reforestation) to minimize low participation of women. In relation to shoreline protection/construction work which is traditionally a male-dominated sector, efforts were made to employ females as much as practicable; for example, as flag persons to alleviate traffic congestion. Project implementation is in accordance with the National Gender Policy (2011) and the AF Gender Policy.
Component 2: activities relate primarily to the agriculture sector and therefore this component targets farmers as a group. There were only a few remaining activities during this reporting period (eg. training to properly operate water harvesting infrastructure) and these were carried out by using a participatory approach to ensure equitable involvement of both males and females. Meeting registers collect sex disaggregated information. The community and Water Users Groups established/strengthened under the GOJ/AFP continue to count with very active participation of women. Execution of activities continues to be in accordance with the National Gender Policy and AF Gender Policy.
Component 3: Project execution has been proceeding in accordance with the National Gender Policy (2011) AF Gender Policy and Gender mainstreaming manual (2016). During the reporting period training was conducted in Shelters and Shelter Management (SSM) as part of the thrust to strengthen communities for disaster resilience. Gender considerations and the social inclusion of persons with disabilities were taught to the approximately 50 participants (28 females) from four parishes. A Gender Specialist was engaged for the SSM training to help participants better understand certain concepts such as gender roles, gender and climate change, the gender dimensions of natural disasters.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The arrangements continue to be effective, with growing awareness and application of gender equity principles across different project acitvities.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | None received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Governance and Oversight to Programme Implementation |  | Outcome 2 | 4 quarterly PSC meetings convened |  | 4 PSC meetings convened to provide guidance and technical inputs with due consideration to risks, progress against targets/timelines and other relevant factors. | S
| Monitoring of Programme Execution |  | Outcome 2 | 10 monitoring visits conducted |  | 11 monitoring/site visits conducted; Terms of Reference for local monitoring committee developed and approved by the PSC Project status meetings convened with contractor, executing entity and supervising engineers on at least a monthly basis | S
| Information, Education and Communication |  | Outcome 3 | Quarterly stakeholders consultations; strategic participation in partner events towards improving awareness and ownership of adaptation and climate risk reduction processes at the local/community/individual levels. |  | Virtual and in-person stakeholder consultations undertaken; ongoing engagement of key stakeholders. Preparation and dissemination of newsletters, fact sheets and GOJ/AFP reports to stakeholders. | S
S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms Claire Bernard
| Email: | cbernard@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall rating is Marginally Satisfactory. Operational changes brought on by the COVID-19 Pandemic impacted the targets set for the reporting period, especially in relation to the coastal works under Component 1. Restrictions under the Disaster Management Act such as curfews, lockdowns, no-movement days and gathering limits all had a delaying impact on implementation.The global nature of this pandemic means that most of the challenges encountered were outside of the control of the NIE and EEs to alleviate. The governance framework continued to function effectively with the convening of quarterly Programme Steering Committee meetings; stakeholder engagement has remained highly positive throughout the implementation period. The NIE conducted monitoring visits each month to project sites and provided updates to community groups as well as local government authorities. Consistent efforts made to ensure compliance with the ESPs and inclusion of gender considerations in programme implementation.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator:
| Change in land cover (Component 1) |  | Outcome 5 | 30000 trees planted |  | 20,149 trees procured; farmers and private planters engaged in reforestation activities. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelie McDonald-Miller
| Email: | smmiller@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Reforestation has proceeded at a slower than expected pace due to several factors including some parallel initiatives with similar actors and the impact of COVID-19 restrictions. To address the issue of low take-up due to small farm holdings, a change in strategy to promote inter-cropping for small holders was implemented to good effect. Other adaptive management strategies included the expansion of the number of communities and groups over and above the original target areas, thereby contributing to the islandwide target of 3 million trees to improve soil conservation and carbon sequestration. Additional supply sources (private nurseries) have been identified and virtual meetings are held in lieu of the usual face-to-face interactions. Collaboration continues with two key agencies -- RADA and the Forstry Department -- which should facilitate reaching the target before the next PPR is due for submission.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
| Enhanced resilience to coastal erosion (Component 1) |  | Outcome 4 | 600m coastline rehabilitated |  | Preliminary design has been updated; Marine Benthic assessment completed. Beach Licences obtained. Two contracts for shoreline protection works awarded. Works completed on one site (Buff Bay): construction of revetment with armour stone boulders; construction of 59m reinforced concrete wall with anchor pad. Cabinet approval obtained and work has commenced under the second contract: groyne 1 completed and revetment construction underway. | MS
| Enhanced resilience to coastal erosion (Component 1) |  | Outcome 1 | 18,000 m/2 reclaimed shoreline |  | Revetment construction underway; material source identified; shingle beach will commence as soon as this is completed. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Roger Smith
| Email: | roger.smith@nwa.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Execution of activities are underway re contract no. 2 (Shoreline protection, Annotto Bay site 3) however, work by the contractor has not kept pace with the planned programme of work, resulting in a shedule lag. Some of the challenges include malfunctioning of the contractor's equipment and quarry/boulder supply issues. The passage of tropical storm Grace coupled with the inherent high wave energy present in the project location have negatively impacted the pace of work. The impact of the COVID-19 restricios such as curfews and 'no-movement' days have had cumulated impacted the site crew. The NIE has assisted by providing exemption letters to the contractor to allow for free movement of work crews on those days. Recently, the contractor's team has repaired malfunctioning excavator and put additional equipment in place to guard against work stoppage; they have also given the assurance to increase the number of crews and to continue working on weekends to reduce the implementation lag. The management team (NIE/NWA) has taken a proactive approach in looking ahead with the contractor at upcoming work activities to clear any hurdles and minimize further schedule delays
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
| Number of targetted training programmes for local entities in DRR and NRM |  | Outcome 3 | Training programme designed, materials developed and training completed |  | Training programme for Shelters and Shelter Managers designed, materials developed and training undertaken in four parishes impacting approximately 50 persons (28 females). | S
| Number of adaptation plans for vulnerable sections of NE coast |  | Outcome 3 | One adaptation plan completed and in use |  | Risk and vulnerability assessments conducted among local community groups; Community Disaster Risk Management and Climate Change Adaptation Plan (CDRM/CCAP) prepared and handed over to St Mary Municipality Corporation as well as local NGO (ABCDEA) and disaster management agency (ODPEM). CDRM/CCAP being used for the benefit of preparing local communities . | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sophia Mitchell
| Email: | Smitchel@ODPEM.org.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Activities proceeded as planned with the participation of key partners (Municipal Corporations, PIOJ, ODPEM) and community stakeholders. The initial roll-out of the Community Disaster Risk Management and Climate Change Adaptation Plan (CDRM/CCAP) in four parishes has strengthened awareness and improved the adaptive capacities of the local communities to respond to climate-induced risks.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Outcome | Change in beach width | Annual average rate of beach erosion app 2m |  | Contractor engaged and work has started on sourcing and placing of material to create shingle beach (land reclamation). More details will be provided in the next PPR | 30m reclaimed land
| Change of land cover |  | Badly denuded slopes | 20,149 plants planted | 30,000 trees planted
| Enhanced resilience to coastal erosion | ~750 km of badly eroded shorelines in 3 towns |  | Construction completed on approximately 60m composite revetment to reduce the energy of wave run-up; 60m of retaining wall completed to reduce overtopping and protect main road network in Buff Bay. Excavation of material and laying of geotextile; One groyne construction and 78m of revetment completed in Annotto Bay. | 600m coastline rehabilitated
Outcome | Change in percentage of communities with improved land and water management practices in the agriculture sector in the project area | Physical evidence of land degrada-tion, soil erosion due to removal of trees |  | Improved irrigation systems, for better land and water management, introduced by the GOJ/AFP have improved the climate resilience of farms and communitie, with 21 communities receive water harvesting systems. The system in Lowe River, Trelawny, impacted 100 households. A total of 11 climate-smart farmer field schools established in project areas and approximately 1900 farmers (68:32 male female ratio) have been trained in skills, knowledge and techniques for sustainable practices and improved land husbandry practices such as ballasted waterways, check dams and vegetative barriers. Farmers have reported much better yields, based on application of the improved techniques and knowledge transfer from training; the Kirkvine/Windalco group in Manchester has documented a 100% increase in production based on the assistance receivied under the GOJ/AFP. The mist blowers distributed by the GOJ/AFP played a significant role in the effective management of the Citrus Greening and Citrus black spot diseases. Technical support and training have resulted in more effective use of chemicals and nutrients resulting in citrus farmers in Ballards RIver now achieving a greater than 20% increase in yield. | Sustainable land and water management practices introduced in 100% of target communities At least 50% of farmers (male/female) employing good practices 30% increase in crop yield 10% reduction in pest infestation
Change in agricultural output of project communities
| Change in the incidence of down-stream floooding and soil erosion | Reported incidence of downstream flooding and soil erosion |  | Communities in N. Clarendon and St. Mary have reported significant reduction in downstream flooding and soil erosion since the introduction of the land husbandry treatments and soil conservation measures. The GOJ/AFP intervention has reduced land degradation and soil erosion in the community of Soho, St. Thomas, and facilitated production throughout the year; thereby improving the ability of farmers to respond to market opportunities even in the long dry season. | 40% reduction in reported incidence of downstream flooding and reduced turbidity of the rivers 40% reduction in level of soil erosion
| Number of farmers (male/female) with increased access to irrigation water and production schemes | Small percentage of residents (male/female) with water storage or distribution facilities |  | 63 production and productivity schemes installed and operational in 20 communities serving over 1000 male and female farmers in St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary | 1000+ farmers (male/female) in 21 communities have access to irrigation water and production schemes
| Number of farmers (male/female) having access to rainwater harvesting and drip irrigation systems |  |  | 42 rainwater harvesting systems 27 ponds and springs/entombments 121 gravity drip irrigation systems installed/operational. Distribution network contract executed, works completed and network systems commissioned; training provided to farmers on how to properly maintain the systems. | 60 farmers (40 males/20 females) in 6 parishes have access to irrigation water and production schemes
| Number of farmers (male/female) benefiting from soil conservation and land husbandry infrastructure (in Upper Rio Minho Watershed) |  |  | 120 farmers benefited directly from GOJ/AFP interventions in Upper Rio Minho Watershed. This watershed is located in the Bull Head forest reserve which is home to some 23 communities with an estimated population of 69, 000 persons | App. 70,000 male and female residents in 31 communities experience improved environmental conditions due to the establishment of land husbandry infrastructure
| Change in availability (number) and quality of local planning tools, eg., climate risk atlas, adaptation plans and the extent to which climate resilient planning development is adopted |  | Development planning tools not climate smart nor standardized 0 community adaptation plas available for project communities | Climate Risk Atlas completed and presented to stakeholders, including the local planning authorities and hoteliers. Community Hazard Mapping exercises undertaken; draft adaptation plan validated by local stakeholders. One Community Disaster Risk Management and Climate Change Adaptation Plan for Annotto Bay completed and is in use. NEPA has recently developed Coastal Management and Beach Restoration Guidelines which clearly outline the process that should be followed when planning, designing and managing coastal management and beach restoration interventions. The guidelines help to provide strategic advice on national development planning. | Climate smart guidelines for assessing development applications institutionalized and in use in at least 50% of development applications Beach restoration activities guided by standardized approach Climate risk information integrated into development planning CCA and DRR integrated into community plans and activities
| % of farmers reporting reduced losses of income and increase of supplemental income |  | 23% of farm household in Northern Manchester below the poverty line | A group of 20 greenhouse farmers in Manchester who benefitted from the GOJ/AFP, has documented a 100% increase in production. The group sells collectively, retains 30% of gross sales for investment and maintenance, and pays out 70% to the farmers | 75% farm households have alternative sources of income
| % residents (male/female) in project communities more aware and knowledgeable of CCA and DRR issues for their community |  | (~90%) Majority of residents (male/female) believe CC risks more relevant to the country than to their community | Development of the Community Disaster Risk Management and Climate Change Adaptation (CDRM/CCA) Plan counted with the significant involvement of residents, respresentatives of the local municipalty and community groups. The stakeholders participated in exercises relating to the identification/impact of climate-related and non-climate related hazards and community vulnerability. This has brought increased awareness of evolving risks and the responsibility of each community to engage in hazard mitigation and adaptation activities | At least 75% of residents in project communities believe that climate risks are relevant to their community and are willing to accept primary responsibility for adaptation
Output | Length (m) of hard structures installed | No revetment No artificial reef | No revetment No artificial reef | Procurement process for pre-Construction/design phase Consultants completed. Conceptual designs updated; engineer's estimate done for scope of works. Marine Benthic Survey undertaken. Eight (8) NCC registered contractors prequalified to participate in tender process for shoreline protection works. Relevant licenses obtained; Coastal Engineers engaged to assist Executing Entity in providing oversight to construction works. Submission made to Public Procurement Commission (PPC) for endorsement to move forward with recommended contractor; PPC endorsement received and contract issued for one site. Based on procurement guidelines/contract threshold, the approval of the Cabinet of Jamaica was sought and obtained for the second contract/site. Contract signed in March 2021, work is proceeding (behind schedule) for this contract. One groyne completed and revetment construction underway. Shoreline protection works completed at Buff Bay (site 1). Setting out survey has been done in the area specified and construction of the first groyne has begun. Procurement being undertaken for shoreline protection works for additional sites. | 600m of revetment installed 300 m of artificial reef installed 18,000 m2 of reclaimed shoreline
Output | No. of trees (fruit/timber) planted |  | High level of deforestation | 20,149 plants procured. | 30,000 trees planted
Output | Number of micro dams constructed in North Manchester ( Revised) # small scale water catchment and irrigation systems rehabilitated/installed in North Manchester |  | 0 water catchment facility in North Manchester | Three (3) small-scale irrigations systems have been installed in Manchester ( Weir Pen and Medina x2) Rehabilitated 90,000 gal capacity concrete tank in Medina, Manchester | 19 roof-to-tank systems were implemented to compensate for the change in activity due to infeasibility (absence of the micro dam)
Output | number of irrigation and production schemes established in: St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary |  | 0 irrigation and production schemes in the 21 targeted communities in 6 project parishes | 63 schemes installed and operational in 20 communities serving over 1000 male and female farmers in St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary | 63 schemes installed and operational in 21 communities serving over 1000 male and female farmers
| number of rainwater harvesting and gravity drip irrigation systems installed in: St Thomas, St Ann, Trelawny, St Catherine, St Mary, Clarendon |  | Inadequate access to irrigation facilities in selected communities in 6 project parishes | 42 rainwater harvesting systems 27 ponds and springs/entombments 121 gravity drip irrigation systems installed/operational. Distribution network contract executed, works completed and network systems commissioned; training provided to farmers on how to properly maintain the systems; "as-built" drawings received. | 30 rainwater harvesting 20 ponds and springs 60 gravity drip irrigation systems installed and operational and serving 40 male and 20 female farmers directly
| Soil conservation and land husbandry infrastructure installed in Upper Rio Minho Watershed |  | Extensive soil erosion due to hillside farming, removal of forest cover and poor farming practices | Five (5) extension areas selected and 5 community sensitization sessions held with stakeholders. The following results have been achieved to date: Hillside Ditch (M) 20,545 Individual Basin (#) 25000 Live Barrier (M) 4218 Continuous Mound (M) 27147* Water ways (M) 1998.5 Check-dams/drop structure (M) 250 Cover crop (H) 2 Fruit Forest (ha) 16.7 Timber Forest (ha) 11 Land Preparation (H) 8.68 Ginger planted (H) 5.04 Yam planted (H) 5.1 Plantain planted (H) 4.3 Banana planted (H) 3 Vegetable planted (H) 0.2 Pineapple/veg. barrier (M) 18,000 *includes both demo plots and grants sub-component | App 18000m diversion/hillside ditches, 24600 individual basins, 3000m of waterway, 1200m continuous mound, 705 check dam/drop structures installed; 18000m pineapple (vegetable barrier) and 13ha fruit forest and 15ha timber planted impacting 5 Extension Areas
| Number of climate-smart farmer field schools established in select communities |  | No climate-smart field schools in select communities | Eleven (11) climate-smart farmers field schools have been established, namely: 1. Plantain Garden River Farmers Group, St Thomas 2. Yallahs Farmers Group, St Thomas 3. Colbeck, St Catherine 4. Braco, Trelawny 5. Medina, Manchester 6. Moffat, St Thomas 7. Woodside, St. Mary 8. Kentish, St Catherine 9. Cowley, St Ann 10. Bryce, Manchester 11. Lowe River, Trelawny Over 1900 farmers have been trained in skills, knowledge and techniques for sustainable practices and improved land husbandry practices. Tunnel Ventillated House (TVH) kit procured and erected at the College of Agriculture, Science & Education (CASE) The objective is to improve the teaching/learning environment and raise the awareness and knowledge base of the young agricultural professionals by exposing the students to the processes that would be undertaken using a TVH infrastructure within the context of climate change adaptation. | 60 gravity drip irrigation systems installed and operational and serving 40 male and 20 female farmers directly
| Number of demonstration plots established in the Upper Rio Minho Watershed |  | Targeted communities do not have demonstration plots in place | Five (5) plots have been established in the Upper Rio Minho Watershed . A land husbandry specialist (RADA) has been assigned to the project and continues to provide support to the communities. | Five demonstration plots established imparting skills, knowledge and techniques to 1510 farmers (male, female) who are adopting sustainable practices
| Number of water user groups established |  | 0 WUG in targeted communities | Twenty-one (21) groups have been established/strengthened and are functioning effectively; 14 of these groups formalized (attained legal status) as a result of the intervention of the Programme. A Rural Sociologist was engaged in 2015 and, to date, has assisted in formalizing the registration of 8 groups with the Department of Cooperatives and Friendly Societies. | At least 15 WUGs established and operational towards sustainable management of water resource
| Number and volume of awareness raising materials (audio visual) targeted to specific age groups, occupation groups, sex and persons with disability |  | No area specific public education programme | Communication plan and strategy developed spearheaded by the PMU in collaboration with executing partners. Advertorial placed in two major daily newspapers to provide specific information on the programme; FAQs and brochure prepared and disseminated to raise awareness of climate change adaptation and disaser risk reduction; Fact sheets on all 3 components developed and shared at stakeholder meetings. Six vignettes were produced highlighting the Programme’s impact on small farmers, women in agriculture and providing general programme information. The vignettes have been shared with stakeholders, including at the AF International Finance Seminar for NIEs and INMED Symposium. A video feature was produced in 2016 by the Jamaica Information Service with a focus on how the programme is making wateravailable to rural farming communities; a follow-up video was done in 2020 showing an expansion (from 70 to 100) of the original intervention to benefit more farmers and households. Fact sheets, brochures and newsletter developed and shared with stakeholders to keep them up-to-date with the GOJ/AFP. | Full roll out of awareness building programme; 70% of residents sensitized.
| Evidence of documentation and dissemination of best practices |  | No evidence of documented best practices in project areas | Developed and distributed 30 copies of a manual on Land Husbandry/ Farmer Field School Approach for use in the training of beneficiaries. Re-printed and distributed 17 Flip Charts on 'Climate Smart and Land Husbandry in Jamaica: Good Practices for Farmers' which is being used by RADA as an extension teaching aid. (The flip chart was originally developed by FAO). The GOJ/AFP continues to disseminate information through the PMU/NIE and MICAF by making presentations to several schools which are supported by the Programme. Partnerships with the Jamaica Library Service and the Jamaica 4-H Clubs have also advanced the dissemination and education objectives. Best practices implemented and documented (from prior initiatives) include the Agro Eco-system Analysis whereby farmers are trained to analyse their farms to determine action threshold before application of integrated pest management strategies. This information is currently disseminated through the RADA network and used by farmers within and outside of the project areas. A consultant was engaged prepare a Lessons Learnt Report. The objective of the consultancy was to capture and communicate the lessons learnt and change impact of the GOJ/AFP (with particular emphasis on Component 2). The consultant found, inter alia, that: o Most of the interventions can be easily replicated in other rural communities to facilitate significant increase in agricultural production and productivity. o The GOJ/AFP remains is highly relevant to the target areas o Improved water systems and water management allowed farmers to produce throughout the year thus exploiting market opportunities and taking advantage of higher prices during the dry season. | Information made available through virtual networks, RADA, parish libraries, College of Agriculture Science and Education, Jamaica Agriculture Society, Fishermen’s Cooperative, 4H Clubs and schools
| Number of (targeted) training programmes for local entities in DRR, natural resource management |  | Limited training in DRR for local entities in DRR and natural resource management, except the few hotels that have green certifications. Limited exposure to training with specific focus on climate change | 35 Small business owners/operators were trained in Business Continuity Planning (March 2016) to strengthen the capacity of these stakeholders to respond to their own risks and vulnerabilities. Training was facilitated by the Office of Disaster Preparedness and Emergency Management (ODPEM). Training Officer employed and community mobilization plan developed and executed. Six (6) sensitization/training sessions conducted in four target communities. KAP Survey completed. 150 community members trained in disaster risk management techniques. The community hazard mapping process completed -- this is a critical output which will support training component of the project by providing information about the respective communities. Vulnerability Capacity Assessment have been conducted with residents of Westmoreland and Hanover communities in partnership with the Jamaica Red Cross. Partnered with the Jamaica Fire Brigade to facilitate disaster risk management and safety warden training workshops. Shelter Management Training conducted in 4 parishes involving approximately 60 participants; procured safety gears for participants in two parishes. Training facilitated by ODPEM. | Training programmes targeted at fishers (mostly male), male and female youth , micro and small business owners and other groups completed
| Guidelines and standards for beach restoration, shoreline protection for Negril |  | No specific technical guidelines for Negril | Some preparatory work completed. Progress stymied by impasse on related component. Activity discontinued along with original component 1; associated resources reprogrammed | One set of guidelines and standards finalized and shared with community and other stakeholders This activity is related to the original Component 1 which has been discontinued. All coastal protection elements have therefore been redefined
| Number of climate risk atlas for storm surge, sea level rise (specific for Negril) |  | 0 risk atlas information for storm surge and sea-level rise for Negril | Climate Risk Atlas completed and presented to stakeholders, including the local planning authorities and hoteliers. | Climate Risk Atlas finalized and copies disseminated to key stakeholders
| Number of adaptation plans for vulnerable sections of North eastern coast |  | 0 Plan | Sensitization sessions conducted with ODPEM re AF Environmental and Social Policy and Gender Policy to govern implementation. Consultant engaged to undertake community consultations and develop Climate Change Adaptation Plan for Annotto Bay. Community Hazard Mapping exercises completed. One Community Disaster Risk Management and Climate Change Adaptation Plan (CDRM/CCA) completed. CDRM/CCA being rolled out across target parishes. Stakeholder consultations ongoing | One Adaptation Plan completed and in use

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The approach taken by the Programme is to build partnerships with key national institutions (both State and NGO) as well as local communities, in order to facilitate progress towards delivery of outputs and attainment of shared objectives. This has had positive impact and led to increased stakeholder buy-in. The continued effective functioning of the Programme Steering Committee has allowed for transparency and good governance of the implementation process. Another important positive is the speedy processing and payment of the contractor's claims by the NIE and partners which have alleviated cash flow issues and facilitated procurement of goods and services. On the negative side: the tardiness of the contractor to execute based on agreed work schedule has had a significant delay in the completion of activities under component 1
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. In compliance with the legal requirements, the relevant permits/licenses have been applied for and granted re shoreline protection work. Monitoring of the permit conditions is ongoing during the construction phase. The contractor submits monthly environmental reports and turbidity tables/reading which are reviewed by the NIE and the Supervising Engineers for compliance. From a social standpoint, the NIE and partners continue to regularly consult with/inform the stakeholders of the ESP requirements and obtain their feedback.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | with the inclusion of other stakeholders taking the total to 66% of target at the end of the reporting period. Despite the restrictions imposed by the COVID-19 Pandemic, the PMU continued to undertake monitoring visits (fully observant of the safety protocols) and ensured the engagement of stakeholders at various levels.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. In compliance with the legal requirements, the relevant permits/licenses have been applied for and granted re shoreline protection work. Monitoring of the permit conditions will be done during the construction phase. A marine benthic assessment has also been carried out to determine the potential impact of activities within the project footprint. From a social standpoint, the NIE and partners continue to regularly consult with/inform the stakeholders of the ESP requirements and obtain their feedback.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Executing Entities, partner agencies and the Programme Steering Committee have been made aware/reminded of AF Gender Policy and its applicability during the programme cycle. Workshops, stakeholder sensitization sessions, etc., are planned and executed on select days and during hours which guarantee greater participation of both men and women from the target communities. As a result, both men and women continue to be actively involved in programme activities. The NIE had earlier provided training to our partners and will continue to emphasize gender mainstreaming throughout the programme cycle. Separate Gender sensitization sessions were incorporated in the roll-out of the CDRM/CCA Plan which was facilitated by ODPEM across 3 parishes. The sessions covered, inter alia (i) Gender and Climate Change; (ii) the distinction between gender sensitive (consideration of gender norms/roles/relations and creating gender awareness) and gender responsiveness; and (iii) - The need to ensure that there is gender mainstreaming throughout the programme cycle -- the ultimate goal of mainstreaming is to take into account the concerns and experiences of both sexes in order to achieve gender equity. Emphasis was also placed on the collection of sex disaggregated data as a starting point for integrating gender into shelter management.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Lessons learnt include: - The importance of introducing a robust communication strategy early in the programme to provide sufficient information before the specific components are implemented. Audience segmentation / awareness of group dynamics should be applied in the initial series of stakeholder consultations to ensure that all views are represented in group decisions. - Building a structure for adaptive management so that where design changes are necessary, these may be carried out for improved results. - Choosing the right lead executing entity is critical to both the design and implementation of future programmes. The matrix management structure adopted by the GOJ/AFP did not work as well as intended; as a result, the NIE has had to work hard to bring together the perspectives and balance the differing priorities of implementing partners - A realistic timeframe is needed for start-up activities and inter/intra- institutional coordination. - There needs to be an awareness of different stakeholders’ agendas and the potential impacts on programme implementation. - Low capacity for some technical elements should be recognized and adequate provisions made to improve the time efficiency of implementation
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is great potential for replication of the climate resilience measures undertaken by the GOJ/AFP, especially in Component 2. The establishment/strengthening of the Water Users Groups (WUG) has had positive impact beyond the project, with 14 of the 21 groups gaining legal registration with the Department of Cooperatives and Friendly Societies. Three examples will illustrate the sustainability activities of the WUG: (i) Windalco Kirkvine Joint Council of Farmers Group, located in Manchester, has established another lined pond which supports a number of other greenhouses . The group’s income has also reportedly doubled due to these interventions; (ii) the Farmers Height /Seville Group in St Ann, developed a project proposal and applied for a grant to increase their production of pineapples; the grant was approved and the project is doing well; and (iii) the Walkerswood Farmers Association in St Ann has identified another tank/ cathchment approximately 1200ft from higher than the system installed by the GOJ/AFP . The additional tank has been fitted with connection pipes and is being used to supplement the group’s water supply. These groups display good collaboration, members support each other and market their products as a group which allows them to have economies of scale.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The early involvement/ participation of local actors (municipal corporations, private sector, local institutions and community) in an integrated way has fostered buy-in and local ownership of the programme
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Some beneficiaries have been involved in the design of the adaptation measures for their communities; this has engendered their support of the project implementation with a sense of commitment and ownership.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful component to date is Component 2 – enhancing the climate resilience of the agricultural sector -- which has seen beneficiaries being taught new techniques and climate smart agriculture methodology. This has resulted in the tangible benefits of higher yields, improved food security and increased incomes from implementing new farming practices. Another successful element is the strengthening the Water Users Groups (WUG) towards improved water management and group dynamics. To date, 21 groups have been established/ strengthened and 14 have gained registration as legal entities as with the Department of Cooperatives and Friendly Societies. This increases the potential of the WUG to access additional resources, thereby enhancing their effectiveness and sustainability.
What measures are/have been put in place to ensure sustainability of the project/program results? | Incorporating local communities and actors in project execution and ensuring that they have a voice in decision-making has worked well for stakeholder buy-in. Helping to make local stakeholders aware of and understand the importance of the effects of climate change and the adaptation measures that are being implemented through the project and their role in monitoring and safeguarding these interventions/outputs. Some assets produced/enhanced under the programme will be turned over to government agencies under whose mandate they fall (eg. National Works Agency)
What measures are being/could have been put in place to improve project/program results? | It was necessary to create partnerships/alliances in order to replicate successes and to have more impact at both the local and national levels. Working closely with the government agencies, consultants and contractor under Component 1, the GOJ/AFP proactively addressed all ESP issues and ensured steps were taken to minimize any negative impacts on the surrounding environment.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | An Environmental Impact Assessment (EIA) was commissioned and carried out. The EIA study and Natural Resource Valuation (NRV) were prepared by independent consultants and provided objective bases for assessing the proposed interventions against other alternatives. Communities/groups under component 2 were initially identified by the RADA network of extension officers in accordance with the Ministry of Agriculture and Fisheries' (MOAF) plans for food security. During implementation MOAF continued to utilize information on food security and priority crops to inform the nature and timing of interventions in the target communities. To improve land and water management, the Farmer Field School concept was chosen to provide crop training in a group-based, practical setting using the demonstration plots and other farms. This approach to training helped to maximise the limited resources and the ‘learning by doing’ approach enhanced the knowledge transfer for sustainable agricultural practices. WUGs were also established to bring communities/farmers together for better water management. The WUG approach helped to build social capital formation and promoted inclusiveness which facilitates sustainability.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Information/data/knowledge used in project implementation include: case studies, videos, newsletters. Channels of information and dissemination include presenting programme results to local community groups and other local stakeholders; presenting at meetings/conferences and publication in national newspapers.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | Community Disaster Risk Management and Climate Change Adaptation (CDRM/CCA) Plans for Annotto Bay
If learning objectives have been established, have they been met? Please describe. | Several learning objectives were established: 1. The main aim of the training in Disaster Risk Reduction (DRR) was to empower residents of the target communities with the capacity and knowledge to which would enable them to support efforts to build climate resilience in their own locale. This objective was met as a result of the nine (9) modules of DRR training delivered. The training in DRR had participation from a cross-section of stakeholders including fisher folk, vendors, small business owners and community leaders. 2. Another learning objective was in respect of the implementation of climate smart land husbandry technology, using the farmer field school methodology. A training of trainers (ToT) approach was adopted by the GOJ/AFP which resulted in more than 1900 farmers being subsequently trained 3. Increasing climate change awareness of the school population and the general public was an important learning objective of the programme. A comprehensive communication strategy was collaboratively developed and several elements of the strategy used to support the awareness-raising activities; these include partnership with 17 educational institutions (primary, secondary and tertiary), as well as the Jamaica 4-H clubs. 4. Learning how to integrate gender considerations into programme implementation was an important objective of the GOJ/AFP. To this end 2 gender training workshops were organized for the NIE and partners with the Institute of Gender & Development Studies, UWI. In this regard, the learning objectives were to: (a) understand why gender is important to climate change adaptation and disaster risk reduction; and (b) identify basic tools used to mainstream gender in CC and DRR programmes to build resilience and adaptive capacity.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Training and capacity building initiatives have contributed to enhanced Climate Change Adaptation capabilities across the target parishes, which directly links to the expected outcomes of the programme. Farmers themselves have also testified of the advantages of learning and implementing the techniques taught by the programme. There is evidence that the identification of the learning objectives have contributed to the outcomes of the project: - Improved the production and productivity of inputs; Increased efficiency in the use of irrigation water and general land resources; Integration of gender considerations in project implementation; Improved institutional capacity and climate change awareness among youth and adults; Reduced vulnerabilities of target communities evidenced by : Reduction of land degradation in case of flooding; Improved livelihood security and improvement in socio-economic conditions of the target communities. Importantly, Component 3 has facilitated awareness-raising around the importance of including gender considerations in shelter management operations.
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | 1. GCCA+ (Hills to Ocean Project) 2. World Bank (JDVRP Project) 3. GoJ/European Union (Improved Forestry Management) 4. IDB (PPCR- Adaptation Programme & Financing Mechanism)
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | JAM/NIE/MULTI/2011/1
Implementing Entity | Planning Institute of Jamaica
Type of implementing entity | NIE
Country | Jamaica
Region | Latin America and Caribbean
Sector | Coastal management
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 12000 | 3000 | 9000 | Total | 10032 | 2508 | 7524 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 50.8% | 30% | 20.8% | % of female beneficiaries | 35% | 23.5% | 12% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 10% |  |  | % of Youth beneficiaries | 4% | 2% | 2% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 30 | Agriculture | 2: Low capacity | Total | 30 | Agriculture | 3: Medium capacity | Total | 30 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 16% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 30 | 16% | Public |  | 30 | 20% | Public |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 3: Medium capacity | Public | National | Agriculture | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 6 | National | Multi-sector | 2: Low capacity | 6 | National | Multi-sector | 2: Low capacity | 6 | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 25% |  | Multi-sector |  | 60 |  | Multi-sector |  | 45 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 10000 | 30% | 3: Partially aware |  | 3000 | 35% | 4: Mostly aware |  | 2508 | 25% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | National | 3: Moderately responsive (Some defined elements) |  | Multi-sector | National | 3: Moderately responsive (Some defined elements) |  | Multi-sector | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target Performance at Completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 5: Very effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 2 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 16 | ha protected | 4: Effective | Cultivated land/Agricultural land | 16 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1000 | 20% | 2: Limited improvement |  | 1000 | 25% | 4: High improvement |  | 1000 | 20% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 10 | Adaptation strategies | Agriculture | Strengthening infrastructure | 110 | Adaptation strategies | Agriculture | Strengthening infrastructure | 108 | Adaptation strategies | Agriculture | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 401 | Agricultural-related |  | 7800 | 2700 | Agricultural-related |  | 12000000 | 2400 | Agricultural-related |  | 1000000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Communication & Information policy | 1 | Multi-sector | National | Communication & Information policy | 1 | Multi-sector | National | Climate Change Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
[6 empty] | Food Security | National | Innovation scaled-up |  | Food Security | National | Innovation replicated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
[6 empty] | 1 | Disaster risk reduction | Undertaking innovative practices | 5: Very effective | 1 | Disaster risk reduction | Undertaking innovative practices | 4: Effective
[6 empty] | 1 | Food Security | Undertaking innovative practices | 5: Very effective | 1 | Food Security | Undertaking innovative practices | 5: Very effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on D62: Shelia Mcdonald-Miller: Ees, ODPEM, RADA, etc.
Note on I95: Shelia Mcdonald-Miller: 1. Change in vegetative cover in Pencar/Buff Bay watershed; 2. change in land/water mgmt practices in agri sector.