## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | November 1, 2017 -October 31, 2018
| Project Title: | ENHANCING THE RESILIENCE OF THE AGRICULTURE SECTOR AND COASTAL AREAS TO PROTECT LIVELIHOODS AND IMPROVE FOOD SECURITY
| Project Summary: | Jamaica is vulnerable to climate related hazards, in particular hurricanes, floods, storm surges and droughts, due largely to its geographical location and the exposure of social and economic assets in coastal areas. This situation is made worse by the country’s low adaptive capacity especially in the climate sensitive sectors of the economy. The agriculture sector and coastal resources are among those at greatest risk, given their significant contribution to the country’s GDP and to the labour force. The activities identified in Government of Jamaica Adaptation Fund Programme (GOJ/AFP) are drawn from the adaptation priorities that were identified in the vulnerability and adaptation assessments for the agriculture and coastal resources sectors. The GOJ/AFP focuses on environmental and natural resource management activities; namely, coastal rehabilitation, inland flood and erosion control, and land and water management. The overall objective of the GOJ/AFP is to protect livelihoods and improve food security in vulnerable communities by: • improving land and water management for the agricultural sector • strengthening coastal protection; and • building institutional and local capacity for climate change adaptation and natural resources management
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | JAM/NIE/Multi/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Planning Institute of Jamaica (PIOJ) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity (NIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jamaica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 -- Increasing the Climate Resilience of the North Eastern Coastline Location: Annotto Bay, Buff Bay and Orange Bay Component 2 -- Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas, Portland and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness-raising for behaviour modification Location: Westmoreland/Hanover/St.Mary/Portland; some target communities in Component 2 | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-29
IE-AFB Agreement Signature Date: |  | 2012-07-23 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-02 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2015-08-01
| Terminal Evaluation Date: | 31/10/2020 (Current extension scheduled to end March 2019, extension request submitted by NIE)
|  | List documents/ reports/ brochures / articles that have been prepared about the programme. | Cyprus
Czech Republic
List the Website address (URL) of project. |  | http://adaptja.pioj.gov.jm | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: | GOJ/AFP featured in PIOJ's Green Team Newsletter (December 2017) The GOJ/AFP also sponsored an outside broadcast segment on Power106 FM to increase the public’s awareness of climate change and their role of taking care of the environment. Newspaper article published on June 21, 2018 under the Earth Day section with article entitled “Jamaica gets approval for climate resilience work in Annotto Bay” http://jamaica-gleaner.com/article/news/20180621/earth-today-jamaica-gets-approval-climate-resilience-work-annotto-bay The article highlighted the contribution of the programme to Vision 2030 Jamaica - National Development Plan through the ongoing import-substitution initiative of the government, particularly for selected crops, such as potatoes and onions. The county’s food security has also been enhanced through import substitution, with farmers reaping 750 tonnes of Irish potatoes and 174 tonnes of onions with assist from the Programme. A total of 2,500 farmers in 100 communities have benefited to date. The referenced article was re-published in the Partnership for Environment and Disaster Risk Reduction (PEDRR) weekly news Alert Issue 265- July 2-6, 2018 http://pedrr.org/pedrr/wp-content/uploads/2013/09/PEDRR-is-at-the-Asian-Ministerial-Conference-on-Disaster-Risk-Reduction-taking-place-this-week.html One (1) corporate brochure developed entitled “Facing Climate Change: Jamaica’s Journey with the Adaptation Fund” and copies disseminated to share updates with stakeholders One (1) Youth brochure developed entitled “Building Climate Champions” and copies disseminated among the youth population The brochures helped to inform stakeholders about the achievements of the Programme and to document testimonials by beneficiaries. Reference was made to Gleaner article of June 21, 2018. | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Una May Gordon | Equatoral Guinea
| Email: | unamay.gordon@megjc.gov.jm | Eritrea
| Date: | 2016-08-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Shelia McDonald-Miller | Fiji
| Email: | smmiller@pioj.gov.jm | Finland
| Date: | 2012-12-03 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D26: Shelia Mcdonald-Miller: Material change approved by AFB in 2018. Revised project activities started subsequently
Note on D28: Shelia Mcdonald-Miller: Current duration will expire on 31/03/2019. Anticipting favourable response to extension request submitted Nov. 2018

## Financial data
128.6018
Financial information: cumulative from project start to October 31, 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [October 31, 2018] | 3827190
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 1037.76 |  | 2017-2018
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period - (Nov 2017 -Oct 2018) | Programme Component | ITEM / ACTIVITY / ACTION | AMOUNT US$
| Component 1: Increasing the climate resilience of the Negril coastline | Installation of breakwater structures (preparatory activities including design and modelling; EIA process)
|  | North Eastern Coastal | 498
Environmental monitoring (NEPA)
Project Execution (NWA)
| Total Component 1 |  | 498
| Component 2: Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities | 2.1 Establishment of Micro-dam | 0
|  | 2.2 Establishment of small scale irrigation facilities | 175257.4
|  | 2.3 Implementation of rainwater harvesting and drip irrigation systems | 103314.57
|  | 2.4 Establishment and rehabilitation of soil conservation and land husbandry infrastructure | 9940.77
2.5 Establishment of Demonstration Plots
|  | Project Execution | 3813.85
| Total Component 2 |  | 292326.59
| Component 3: Improving institutional and local level capacity for sustainable management of natural resources and disaster risk reduction in the targeted vulnerable areas | Training of Local Communities in Disaster Risk Reduction and Natural Resources Management
|  | Development of Climate Risk Atlas |  | No expenditure in current reporting period. Total expenditure of US$147,430 reported in previous periods.
|  | Development of Adaptation Plans for vulnerable areas along Negril coastline (Rescheduled) |  | Rescheduled along with revised component 1
|  | Establish farmer field schools to develop solutions and demonstrate good practices | 7179.66
Conducting workshops and farmer training in climate smart agriculture
|  | Climate change awareness and education programmes developed and implemented in project communities | 2674.9
Project Execution
| Total Component 3 |  | 9854.56
| Programme Implementation (NIE) |  | 60249
| TOTAL | 0 | 362928.15
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST US$ | Est. Completion Date
| Component 1 Procurement and other preliminary activities underway | 1826000 | 2019-10-31
Component 2
| Implementation of rainwater harvesting and drip irrigation systems | 244344.3672 | 2019-03-31
| Establishment of small scale irrigation facilities | 13811.7969 | 2019-03-31
| Establishment and rehabilitation of soil conservation and land husbandry infrastructure | 54687.5 | 2019-03-31
| Closing ceremony (Component 2) | 11718.75 | 2019-03-31
Component 3
| Development of adaptation plansfor the targeted areas | 74000 | 2019-09-30
| Capacity building and training in deep sea fishing, business development, natural resources management | 70000
| TOTAL | 2294562.4141
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A
Note on E9: Shelia Mcdonald-Miller: Includes $30000 PFG

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial: budget over-runs/under-spend; mis-use of funds; inflation/ currency depreciation leading to increased costs for goods/services | Moderate | The material change which has occurred (revised Component 1) has necessitated the need for further extension of the programme timeline. As a result, additional resources (over and above the AF grant) need to be garnered towards administration activities. NIE developed financial reporting templates/procedures and provided training to partners in use thereof. Executing Entities (EE) are required to provide monthly/quarterly financial reports. The NIE has implemented an effective governance framework as follows: (a) EE work plans/budgets must be approved by the Programme Steering Committee (PSC) prior to disbursement of funds; (b) periodic monitoring visits are undertake by the Programme Management Unit (PMU) to EE locations to review supporting documents for reported expenditure. Two external audits have been undertaken since the inception of the programme.
Environmental: natural hazards (flood, drought, storms/hurricanes); pests and diseases. | Moderate | Key stakeholders have been apprised of the AF ESP and Gender Policy in order to ensure adherence to the respective stipulations. The Agriculture Ministry continues to implement the integrated pest management and disease control programme across all parishes, ensuring the judicious use of pesticides. This helps to minimize the risk to the environment associated with pesticide applications. Implementation plans and schedules are designed to take account of the official peak 'adverse climatic events' period (June-November) each year. Specialized agencies (ODPEM, MET Service, etc.) provide information to the public on how to respond in the event of such occurrences.
Stakeholder Buy-in | Low | The NIE remains committed to deepening stakeholder involvement in the target communities, as well as keeping stakeholders informed on a wider level beyond the Executing Entities and target communities. This has been done via annual stakeholder consultations, interviews of partners and beneficiaries with local media houses (print and electronic), linkages with key national stakeholders and participation in related partner forums.
Multiple Executing Entities | Moderate | The involvement of the Programme Steering Committee (PSC) continues to be strong, with regular meetings convened by the NIE; this ensures that an effective governance structure remains in place. Administratively, the PMU/NIE continues to successfully organize and coordinate activities involving the different stakeholder groupings. This is often an iterative process of consultation, planning and reviewing resulting in a good balance of the differing and sometimes competing priorities.
Procurement Delays | High | Procurement has been de-centralized to the respective Executing Entities to increase flexibility; however, this has not worked as effectively as anticipated. The PMU continues to support Executing Entities by providing appropriate templates as per the GOJ Procurement Guidelines, as well as direct procurement support, and procedural review via the 'no-objection process'.
Implementation/ Operational: delays in programme implementation schedule | Moderate to High | The need to revise component 1 and related elements has led to the Programme submitting a request for a 3rd extension of the original duration in order to complete revised activities. One of the main risk-drivers identified is in the area of procurement, especially for Component 2; in this regard, additional resources have been provided (dedicated procurement officer) to minimize delays and increase the likelihood of timely completion of procurement activities. To improve results on the ground, the PMU continued to provide direct assistance in coordinating/scheduling some critical activities (Component 1) and following up with the National Contracts Committee (Component 2)
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risks associated with the installation of revetments and other structural works | Low | This Component of the Programme, as originally proposed, was discontinued in mid-2016 and has been re-defined. Measures for environmental risks have been included in the Environmental and Social Management Plan (ESMP) and will be utilized as part of the monitoring framework during the implementation cycle.
Low disaster risk perception in some target communities | Low | A mobilization plan was developed and implemented in 2015 leading to improved awareness and more positive responses from the target communities. Increased communication and awareness-raising activities relating to climate change impacts have been undertaken by the programme as well as on a national level and have led to a more informed populace.
Executing Entities’ readiness to implement, including availability of human resources | Moderate | The NIE continued to provide support to the Executing Entities to foster improvements in the execution framework, including the provision of additional human resources. The PMU hosted a follow-up Procurement Workshop with partners in January 2017 to provide clarity on the provisions and improve the rate of compliance with the procurement guidelines. There continues to be regular meetings and other monitoring activities aimed at minimizing negative impacts on the programme.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The NIE continues to bring together the perspectives, knowledge and expertise of different stakeholders through an iterative process of consultation and planning; this close collaboration has been an effective risk mitigation measure.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Awareness Raising and Visibility |  | Implementation of Communication Strategy and Action Plan |  | The GOJ/AFP promoted climate knowledge and awareness and climate smart actions as follows: o Raised awareness about environmental management, towards climate change adaptation among the youth population through partnership with the Jamaica Library Service and Multi-Care Environmental in the hosting of their annual summer camps. Approximately 300 students were impact across 4 parishes (St. Thomas, Kingston, St Andrew and Manchester). Participated in 4H National Achievement Expo in April at Denbigh Agricultural Showground in Clarendon showcasing best practices primary and secondary-level schools. o Visibility of the programme was boosted by it being featured, since June, on the UN Sustainable Development Knowledge Platform (https://sustainabledevelopment.un.org/content/documents/19481Facing_Climate_Change_Jamaicas_Journey_with_the_Adaptation_Fund.pdf) o Produced a youth brochure (Building Climate Change Champions) as well as a corporate brochure (Facing Climate Change) to advance climate literacy among beneficiaries; 500 copies distributed across 7 parishes. Sponsored segment of outside broadcast on Power 106 FM on October 5, 2018 in celebration of International Day of Forests. Supported the Forestry Department (Forest Trek II) in commemoration of their 80th Anniversary celebrations. o A story map was developed to highlight the progress of the GOJ/AFP is currently hosted on the programme’s webpage http://adaptja.pioj.gov.jm . o Mounted exhibitions at the Regional Consultations on the Sustainable Development Goals (SDGs) for Eastern and Southern regions (St. Thomas and Manchester) | S
| Monitoring |  |  |  | Ten (10) monitoring visits were made by the PMU to various project sites for the period under review. Visits were also made to and meetings convened with all Executing Entities (EE) as part of the NIE’s oversight responsibilities. The team verified reported expenditure against supporting documentation and provided guidance, as appropriate. Executing Entities reports were reviewed and feedback provided with recommendations for improvements, where necessary. The team also conducted two asset verification exercises. | S
| Knowledge Management/Sharing: |  |  |  | o Participated as resource persons in two AF Readiness Webinars: Sustainable Development Officer and Programme Manager, respectively, made presentations on April 19th titled ‘Mainstreaming environmental social and gender issues in adaptation projects/programmes’ o Programme Director participated in 'Readiness Workshop and Accreditation' session Nairobi, Kenya; Programme Manager participated in the 5th Annual NIE Seminar held from August 28-31, 2018 in Washington DC: served as a panellist and participated in interview for AF feature. o Participated as a presenter in Climate Finance Webinar in October; the webinar discussion articulated the rationale for change in project / programmes, highlighting the dynamic and often shifting conditions in developing countries. Contributed information for AF Community of Practice for Direct Access Entities (CPDAE newsletter) and coordinated input of CPDAE participants in the Caribbean and South Africa. | HS
| Governance and Oversight to Programme Implementation |  | Governance and Oversight Framework established and functioning effectively |  | The Programme Steering Committee (PSC) continued to serve as the main mechanism for the provision of technical advice and oversight. There were four (4) PSC meetings convened for the period under review (Dec. 2017; March/June/October 2018. The PSC has effectively assisted with resolving strategic level issues and addressing risks that have the potential to adversely affect the smooth implementation of the programme. Following PSC approval, the NIE made timely disbursements to faciliate implementation of approved activities by EE. Seven (7) 'no-objection' requests were processed by the PMU during the period under review. The 'no-objection' process helps to minimize procurement breaches going undetected. o External audit conducted – unqualified audit report received. Special Evaluation completed – GOJ/AFP assessed as being relevant and exhibiting a high level of outcome effectiveness. o Convened sensitization sessions with Executing partners (NWA, NEPA, ODPEM, Ministry of Finance and the Public Service, Forestry Department) re the Adaptation Fund’s Environmental and Social Policy requirements. | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelia McDonald-Miller
| Email: | smmiller@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The NIE has successfully carried out its planned activities and continues to work collaboratively with partners
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 Increasing the climate resilience of the North Eastern Coastline |  | Preparatory work for coastal protection |  | Preparatory work including procurement activities currently underway. Updating of preliminary designs expected to be completed by Q1 2019; this will then be followed by contractor engagement and mobilization for works to begin. | MS
| Component 2 Enhanced climate resilience of the agricultural sector through improved water and land management in select communities |  | Land husbandry curriculum developed; demonstration plots established and farmers have access to increased irrigation water and producion schemes |  | Forty (40) systems using roof catchment and tanks have been installed; sixteen (16) schools have been impacted, some of which run meal assistance and environmental awareness programmes for students. An additional 11 rainwater harvesting systems using tanks and catchment were established All five (5) demonstration plots for land husbandry practices have been established and over 500 farmers have received training in diversion and hillside ditches techniques, continuous mounds, building of ballasted water ways and other soil conservation techniques. Forty-six (46) of the required production and productivity schemes have been established (1 more than the target of 45). 832 farmers in 20 communities/7 parishes have received increased access to irrigation facilities. Approximately 2300 farmers successfully completed training in skills, knowledge and techniques on sustainable land husbandry practices. The final version of the curriculum has been produced by RADA and training was accelerated in 2017. 224 gravity drip irrigation systems have been installed in 7 parishes with the direct assistance of the GOJ/AFP. Eleven (11) Farmer Field Schools (FFS) have been mobilized and the training of farmers in land husbandry and water management has been facilitated. Twenty-one (21) Water Users' Groups (WUG) with a membership of approximately 1200 have been mobilized and strengthened. Fourteen (14) groups have since been formally registered with the Department of Cooperatives and Friendly Societies and others are in various stages of the registration process. The capacity of partner agency, RADA, has been built with the training of thirty (30) Extension Officers in skills, knowledge and techniques of climate smart agriculture. | MS
| Component 3 Improved institutional and local capacity for sustainable management of natural resources and in disaster risk reduction in the targeted vulnerable areas. Raising awareness for behaviour modification |  | Completion of draft adaptation plans; Completion of Climate Risk Atlas NRM training W-I-P |  | Climate Risk Atlas completed. The finalized atlas has been disseminated to key stakeholders. The Adaptation Plans and Guidelines will not be completed as originally planned; these activities are related to Component 1 which has been revised; the activities will therefore be undertaken in the upcoming reporting period. The GOJ/AFP has partnered with the College of Agriculture (CASE), Portland and provided support for a tunnel ventilated poultry house. This collaboration is aimed at enhancing CASE’s productive capacity and teaching/ learning environment within the context of adapting to climate change | MS
MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Claire Bernard
| Email: | cbernard@pioj.gov.jm
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Progress on Component 2 is at approximately 85%, with one lagging activity (network distribution) continuing to experience implementation delay, mainly relating to procurement challenges. The approval of the National Contracts Committee, a pre-requisite for proceeding to the contracting stage, took several months to be obtained despite the best efforts of the NIE and EE. These challenges have been compounded by insufficient contract management/follow-up. Revision of Component 1 was completed and approval of the AF Board obtained. Pre-contract activities have commenced (procurement and pre-qualification exercises). The pace of implementation has been slower than planned due to unexpected absence/departure of key staff at partner agencies (NWA and ODPEM); however, things are moving in the right direction. The current project end date of March 2019 will not allow sufficient time for the scope of works under Components 1 and 3 to be completed; therefore more time will be requested to facilitate completion of all outstanding programme elements.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT INDICATORS
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Length (m) of hard structures installed | No revetment No artificial reef | In early 2018, the NIE and partners developed a revised component resulting in changes in outcome, outputs and related indicators. Procurement process for pre-Construction/design phase Consultants in progress Three community/stakeholder sensitization sessions facilitated in St. Mary; five other sessions convened with partners to chart the way forward. Expressions of Interest (EoI) issued as a prequalification exercise for the construction phase; responses received are currently being evaluated. Terms of reference prepared for Technical Officers (NEPA) to carry out monitoring activities during the construction phase Preliminary designs completed; efforts underway to update prior to commencement of construction activities | 8500m of revetment installed 300 m of artificial reef installed 18,000 m2 of reclaimed shoreline
| Denuded areas of land reforested 150 acres reforested | High level of deforestation | Meetings held with community as well as organizational stakeholders to engender buy-in. RADA and Forestry Department senior management engaged; areas for reforestation identified. Preliminary species list for timber and fruit trees defined | 30,000 trees planted on 150 acres of land
| Number of micro dams constructed in North Manchester ( Revised - scope change) # small scale water catchment and irrigation systems rehabilitated/installed in North Manchester | 0 water catchment facility in North Manchester | Three (3) small-scale irrigations systems have been installed in Manchester ( Weir Pen and Medina x2) Rehabilitated 90,000 gal capacity concrete tank in Medina, Manchester 19 roof-to-tank systems have been implemented to compensate for the absence of the micro dam. | 20 small scale water catchment/ irrigation systems installed in N. Manchester
| Number of irrigation and production schemes established in: St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary | 0 irrigation and production schemes in the 21 targeted communities in 6 project parishes | Forty-six (46) Production & Productivity schemes have been approved and activated. (Target of 45 exceeded) | 45 schemes installed and operational in 15 communities serving over 750 male and female farmers
| Number of farmers with increased access to water and production schemes | Small %of farmers (male/female) with water storage or distribution facilities | 832 farmers in 20 communities (7 parishes) have increased access to irrigation facilities | 1000+ farmers (male/female) in 15 communities have access to irrigation water and production schemes
| Number of rainwater harvesting and gravity drip irrigation systems installed in: St Thomas, St Ann, Trelawny, Mancheter, St Catherine, St Mary, Clarendon | Inadequate access to irrigation facilities in selected communities in 7 project parishes | Forty (40) systems using roof catchment and tanks have been installed, including at 16 schools, some with meal-assistance programmes for students. Twenty (20) rainwater harvesting systems using ponds and catchment were rehabilitated. Eleven (11) of 30 rainwater harvesting /gravity drip irrigation systems implemented across the parishes of St. Thomas, Manchester and St. Ann. 224 gravity drip irrigation systems have been installed in 7 parishes: 117 entirely with AF resources and an additional 107 in collaboration with another agriculture project. | 40 roof-based rainwater harvesting; 20 ponds and spring -linked systems 210 gravity drip irrigation systems installed and operational Target significantly exceeded, attributable in part to collaboration with another development partner.
| Unit of Soil conservation and land husbandry infrastructure installed in Upper Rio Minho Watershed | Extensive soil erosion due to hillside farming, removal of forest cover and poor farming practices | Six (6) extension areas selected and community sensitization sessions held with stakeholders. The following results have been achieved to date: Hillside Ditch (M) 20,545 Individual Basin (#) 25,000 Live Barrier (M) 4218 Continuous Mound (M) 18,992 Water ways (M) 1998 Check-dams/drop structure 160 Cover crop (H) 2 Fruit Forest (H) 108 Timber Forest (H) 11 Ginger planted (H) 5.04 Yam planted (H) 5.1 Plantain planted (H) 4.3 Banana planted (H) 3 Vegetable planted (H) 0.2 | App 18000m diversion /hillside ditches, 24600 individual basins, 3000m of waterway, 1200m continuous mound , 705 check dam/drop structures installed, 18000 m pineapple (vegetable barrier) and 13ha fruit forest and 15ha timber planted impacting 5 Extension Areas | 16988 | re-check Micaf's reports
| Number of climate-smart farmer field schools established in select communities | No climate-smart field schools in select communities | Eleven (11) climate-smart farmers field schools have been established, namely: 1. Plantain Garden River Farmers Group, St Thomas 2. Yallahs Farmers Group, St Thomas 3. Colbeck, St Catherine 4. Braco, Trelawny 5. Medina, Manchester 6. Moffat, St Thomas 7. Woodside, St. Mary 8. Kentish, St Catherine 9. Cowley, St Ann 10. Bryce, Manchester 11. Lowe River, Trelawny Over 1923 farmers have been trained in skills, knowledge and techniques for sustainable practices and improved land husbandry | Eleven (11) climate-smart farmer field schools established and 90% farmers (male/female) trained to adopt climate smart agriculture practices
| Number of demonstration plots established in the Upper Rio Minho Watershed | Targeted communities do not have demonstration plots in place | Five (5) plots have been established in the Upper Rio Minho Watershed . A land husbandry specialist (RADA) has been assigned to the project and continues to provide support to the communities. | Five demonstration plots established imparting skills, knowledge and techniques to 1510 farmers (male, female) who are adopting sustainable practices
| Number of water user groups established | 0 WUG in targeted communities | Target exceeded; twenty-one(21) groups have been established/strengthened and are functioning effectively; 14 of these groups formalized (attained legal status) as a result of the intervention of the Programme. A Rural Sociologist was engaged in 2015 and, to date, has assisted in formalizing the registration of 8 groups with the Department of Cooperatives and Friendly Societies. | At least 15 WUGs established and operational towards sustainable management of water resource
| Number and volume of awareness raising materials (audio visual) targeted to specific age groups, occupation groups, sex and persons with disability | No area specific public education programme | Communication plan and strategy developed spearheaded by the PMU in collaboration with executing partners. Advertorial placed in two major daily newspapers to provide specific information on the programme; FAQs and brochure prepared and disseminated to raise awareness of climate change adaptation and disaser risk reduction; Fact sheets on all 3 components developed and shared at stakeholder meetings. Three vignettes were produced highlighting the Programme’s impact on small farmers, women in agriculture and providing general programme information. The vignettes have been shared with stakeholders, including at the AF International Finance Seminar for NIEs and INMED Symposium. A video feature was produced in 2016 by the Jamaica Information Service with a focus on how the programme is making wateravailable to rural farming communities . | Full roll out of awareness building programme; 70% of residents sensitized.
| Evidence of documentation and dissemination of best practices | No evidence of documented best practices in project areas | Developed and distributed 30 copies of a manual on Land Husbandry/ Farmer Field School Approach for use in the training of beneficiaries. Re-printed and distributed 17 Flip Charts on 'Climate Smart and Land Husbandry in Jamaica: Good Practices for Farmers' which is being used by RADA as an extension teaching aid. (The flip chart was originally developed by FAO). The GOJ/AFP continues to disseminate information through the PMU/NIE and MICAF by making presentations to several schools which are supported by the Programme. Partnerships with the Jamaica Library Service (specifically the summer camp iniatitives in Kingston/St. Andrew, St. Thomas and Manchester) and the Jamaica 4-H Clubs have also advanced the dissemination and education objectives. Best practices implemented and documented (from prior initiatives) include the Agro Eco-system Analysis whereby farmers are trained to analyse their farms to determine action threshold before application of integrated pest management strategies. This information is currently disseminated through the RADA network and used by farmers within and outside of the project areas. | Information made available through virtual networks, RADA, parish libraries, College of Agriculture Science and Education, Jamaica Agriculture Society, Fishermen’s Cooperative, 4H Clubs and schools
| Number of (targeted) training programmes for local entities in DRR, natural resource management | Limited training in DRR for local entities in DRR and natural resource management, except the few hotels that have green certifications. Limited exposure to training with specific focus on climate change | 35 Small business owners/operators were trained in Business Continuity Planning (March 2016) to strengthen the capacity of these stakeholders to respond to their own risks and vulnerabilities. Thirty -Five (35) persons benefited from this training which was facilitated by the Office of Disaster Preparedness and Emergency Management (ODPEM). Training Officer employed and community mobilization plan developed and executed. Six (6) sensitization/training sessions conducted in four target communities. KAP Survey completed. 150 community members trained in disaster risk management techniques. The community hazard mapping process completed -- this is a critical output which will support training component of the project by providing information about the respective communities. Vulnerability Capacity Assessment have been conducted with residents of Westmoreland and Hanover communities in partnership with the Jamaica Red Cross. Partnered with the Jamaica Fire Brigade to facilitate disaster risk management and safety warden training workshops. | Training programmes targeted at fishers (mostly male), male and female youth , micro and small business owners and other groups completed
| Guidelines and standards for beach restoration, shoreline protection for Negril | No specific technical guidelines for Negril | Some preparatory work completed. Progress affected by impasse on related component. Activity discontinued along with original component 1; associated resources reprogrammed | One set of guidelines and standards finalized and shared with community and other stakeholders This activity is related to Component 1 which has been discontinued. All coastal protection elements have therefore been redefined
| Number of climate risk atlas for storm surge, sea level rise (specific for Negril) | 0 risk atlas information for storm surge and sea-level rise for Negril | Climate Risk Atlas completed and presented to stakeholders, including the local planning authorities and hoteliers. | Climate Risk Atlas finalized and copies disseminated to key stakeholders
| Number of adaptation plans for vulnerable sections of North eastern coast | 0 Plan | Since receiving notice of AFB approval, meetings have been convened with the Office of Disaster Preparedness and Emergency Management (ODPEM) which is the lead agency on this activity. Sensitization session conducted re AF Environmental and Social Policy and Gender Policy to govern implementation | Community Disaster Risk Mangement and Adaptation Plan for at least one north eastern community
Note on G10: Shelia Mcdonald-Miller: Revised target due to infeasibility of micro dam

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive lessons included: The approach taken by the Programme is to build partnerships with key national institutions (both State and NGO) as well as local communities, in order to facilitate progress towards delivery of outputs and attainment of shared objectives. This has had positive impact and led to increased stakeholder buy-in. The continued effective functioning of the Programme Steering Committee has allowed for transparency and good governance of the implementation process. On the negative side: adequacy of technical capacity, procurement rigidities, lack of dedicated resources and competing priorities within Executing Entities continued to stymie progress of implementation, although to a lesser extent than in the preceding years.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Implementation delays continued on Component 1. The NIE and partners developed a revised Component which maintained the focus of the original project and submitted it to the AF Secretariat for technical review and subsequently for Board approval. Notification of Fund approval came in early May 2018. Several stakeholder discussions have since been convened and procurement activities are underway to identify suitable consultants to begin execution of scope of work. Procurement delays also continued to be experienced in the design and installation of rainwater harvesting system using ponds/ tanks (Component 2). There was unsuccessful tendering which led to retendering exercises. It took several months after the submission to the National Contracts Committee was reviewed and a decision re contracting obtained. The contractor was eventually engaged in August 2018 to complete work on the distribution systems. Other implementation delays resulted from the absence of dedicated personnel and competing priorities within partner agencies. Measures implemented were the engagement of short-term staff and reallocation of human resources within Executing Entities; the PMU/NIE also continued to provide direct procurement support to EE. A significant amount of development assistance goes to agriculture adaptation, the paradox is that this can have the effect of dispersing the energy and attention of the actors in the sector. For the period under review, the NIE has sought to enlist the support of senior management within partner agencies and will continue to provide the requisite support to our partners.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The original Component 1 (breakwater project in Negril) was discontinued along with related elements of Component 3,and a revised project developed by the NIE and partners to replace the aborted elements. The new component 1 maintained the focus on climate change adaptation through coastal resilience building. The new location was the north eastern section of the island, specifically Annotto Bay, Buff Bay and Orange Bay. During the reporting period, the NIE commissioned a Special Evaluation. The Agreement between the NIE and the AFB makes provision for two evaluations to be done, and a mid-term evaluation was conducted in 2015. However, given the significant extensions to the original project duration and the fact that some elements of the GOJ/AFP have been discontinued while others will continue through to 2019 or beyond, the NIE decided that a Special Evaluation was necessary in order to preserve important elements which may be lost because of dimmed memory, changed personnel in partner agencies and/or relocation of key stakeholders by the time the final evaluation becomes due. | have not a number of activities been discontinued along with the discontinuation of the original component 1? Also re the dam? | My understanding is that the focus is on the reporting year, not since inception, so would not mention the dam, for example.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Executing Entities have been made aware/reminded of AF Gender Policy and its applicability during the programme cycle. Workshops, stakeholder sensitization sessions, etc., are planned and executed on select days and during hours which guarantee greater participation of both men and women from the target communities. As a result, both men and women continue to be actively involved in programme activities. The NIE had earlier provided training to our partners and will continue to emphasize gender mainstreaming throughout the programme cycle.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The programme design was evaluated as being both logical and theoretically sound. Lessons learnt include: - The importance of introducing a robust communication strategy early in the programme to provide sufficient information before the specific components are implemented. Audience segmentation / awareness of group dynamics should be applied in the initial series of stakeholder consultations to ensure that all views are represented in group decisions. - Building a structure for adaptive management so that where design changes are necessary, these may be carried out. In this regard, because of the built-in flexibility and the assessed willingness of the NIE management to be responsive to the needs of implementing partners the following adjustments were made: (a) additional personnel not initially written into the GOJ/AFP were approved to bolster existing EE capacity; (b) changes to the recommended communication flow and (c) direct implementation support/shared responsibility between the NIE and EE (Component 3) to allow for improved pace of implementation and enhanced sustainability. - Choosing the right lead executing entity is critical to both the design and implementation of future programmes. The matrix management structure adopted by the GOJ/AFP did not work as well as intended; as a result, the NIE has had to work hard to bring together the perspectives and balance the differing priorities of implementing partners - A realistic timeframe is needed for start-up activities and inter/intra- institutional coordination. - There needs to be an awareness of different stakeholders’ agendas and the potential impacts on programme implementation. -Geo-technical information is needed ahead of time to support choice of specific sites for introducing adaptation measures. - Low capacity for some technical elements should be recognized and adequate provisions made to improve the time efficiency of implementation
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The adaptive farming techniques introduced (farmer field school technology) were reinforced by formalized training support (land husbandry curriculum) and will allow for replication within and outside of the programme target areas. - Organization of communities into Water Users Groups (WUG): this measure can be scaled up as the evidence shows that there are improvements in water management where community groups are organized. -The climate risk atlas can be used as a reference tool by other coastal communities - Completing proper technical feasibility of the complex works to be undertaken (Component 1) is a positive and should be replicated
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Same as above
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Land Husbandry training undertaken across all target parishes (over 1900 farmers trained) yielded positive results both at the individual as well as the community levels. The use of erosion control and drought mitigation techniques (contouring, ballasted waterways, irrigation systems, etc.) proved to be very useful adaptation measures. These are practical because farmers were integrally involved in developing these structures and therefore are able to continue implementing these technologies to other farms. The involvement of female farmers (many of whom are heads of households) has had a positive impact on the livelihoods of their families
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful component to date is Component 2 – enhancing the climate resilience of the agricultural sector. Beneficiaries are enthusiastic about the new techniques learnt and the tangible benefits of higher yields and increased incomes from implementing new farming practices. On the economic level the alignment of the GOJ/AFP with the national import-substitution programme via the agro parks (onions and irish potato) has helped to save foreign exchange as well as contribute to better food security. Another successful element is the hiring of a Rural Sociologist who has supported the efforts at strengthening the Water Users Groups (WUG) towards improved water management. To date, 21 groups have been established/ strengthened and 14 have gained registration as legal entities as with the Department of Cooperatives and Friendly Societies. This increases the potential of the WUG to access additional resources, thereby enhancing their effectiveness and sustainability. Training in conflict resolution and group dynamics has helped to improve social bonding and group cohesiveness.
What measures are/have been put in place to ensure sustainability of the project/program results? | Measures put in place to ensure sustainability include: -Institutional strengthening of key national organisation: training of RADA extension officers in climate smart agricultural techniques. - Training of a cadre of community members in disaster risk management to ensure they understand the link between climate change and development. -providing support to rural schools to strengthen their agricultural science programme; an estimated 3000 students have been impacted. - Continued engagement with the Jamaica 4-H Clubs and JaREEACH project has expanded the number of schools/students being exposed to climate change awareness. This increased youth involvement will no doubt contribute to spreading the CCA message even after the project cycle ends. - Transfer of knowedge: farmers learn to use new farming techniques that produce higher yields and greater incomes and are able to transfer these techniques to other farms/communities. - Community empowerment and strengthening of WUGs via formal registration to achieve legal status. This makes them more effective as bargaining units and better able to access additional resources. - The climate risk atlas for Negril will enhance the local decision-making landscape. - Strategic alignment of the GOJ/AFP with national priorities via collaboration with Vision 2030 Jamaica National Development Plan.
What measures are being/could have been put in place to improve project/program results? | To improve results, the GOJ/AFP has created strategic linkages with partners such as the Canadian Hunger Foundation/ PROPEL project, JaREEACH project, Jamaica Red Cross, Food for the Poor and JSIF/REDI project. These partnerships have helped to maximise benefits to stakeholders without duplicating effort. A new partnership was formed in 2017 with the Jamaica Bauxite Institute to support 20 greenhouse farmers with guttering facilities to harvest rainwater from roof to recharge lined reservoirs in the parish of Manchester. There has been re-engagement of additional personnel to bolster the capacity of executing entity staff in implementation activities.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | A number of studies were used to inform the development of the revised components of the programme; these include the ODPEM Multi-Hazard Risk Assessment Study, 2013; Stanley Consultant Inc Comprehensive Drainage and Flood Control Study; 2011 censu; the poverty map and the State of Jamaica Climate, 2015. The role of the local community group - Annotto Bay Community Development Environmental Association (ABCDEA) has also been critical in this process. Community consultations with targeted groups (eg. fisherfolk) also provided local knowledge to inform programme development. To improve land and water management, the Farmer Field School concept was chosen to provide crop training in a group-based, practical setting using the demonstration plots and other farms. This approach to training helps to maximise the limited resources and the ‘learning by doing’ approach enhances the knowledge transfer for sustainable agricultural practices. Communities/groups under component 2 were initially identified by the RADA network of extension officers in accordance with the Ministry of Agriculture and Fisheries' (MOAF) plans for food security. During implementation MOAF has continued to utilize information on food security and priority crops to inform the nature and timing of interventions in the target communities. Water Users' Groups (WUGs) were also established to bring communities/farmers together for better water management. The WUG approach helps to build social capital formation and promotes inclusiveness which facilitates sustainability.
If learning objectives have been established, have they been met? Please describe. | Several learning objectives were established: 1. The main aim of the training in Disaster Risk Reduction (DRR) was to empower residents of the target communities with the capacity and knowledge to which would enable them to support efforts to build climate resilience in their own locale. This objective was met as a result of the nine (9) modules of DRR training delivered. The training in DRR had participation from a cross-section of stakeholders including fisher folk, vendors, small business owners and community leaders. 2. Another learning objective was in respect of the implementation of climate smart land husbandry technology, using the farmer field school methodology. A training of trainers (ToT) approach was adopted by the GOJ/AFP which resulted in more than 1900 farmers being subsequently trained 3. Increasing climate change awareness of the school population and the general public was an important learning objective of the programme. A comprehensive communication strategy was collaboratively developed and several elements of the strategy used to support the awareness-raising activities; these include partnership with 17 educational institutions (primary, secondary and tertiary), as well as the Jamaica 4-H clubs. 4. Learning how to integrate gender considerations into programme implementation was an important objective of the GOJ/AFP. To this end 2 gender training workshops were organized for the NIE and partners with the Institute of Gender & Development Studies, UWI. In this regard, the learning objectives were to: (a) understand why gender is important to climate change adaptation and disaster risk reduction; and (b) identify basic tools used to mainstream gender in CC and DRR programmes to build resilience and adaptive capacity.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Training and capacity building initiatives have contributed to enhanced CCA capabilities across the target parishes, which directly link to the expected outcomes of the programme. For example: there were unseasonal heavy rains during March to June 2017 and the Macro Socio-Economic and Environmental Impact Assessment of the damage and loss caused by these rains cited the GOJ/AFP contributions to resilience building. The Report noted that communities which practiced climate smart agricultural techniques experienced minimal damage. Farmers themselves have also testified of the advantages of learning and implementing the techniques taught by the programme. There is evidence that the identification of the learning objectives have contributed to the outcomes of the project: - Improved the production and productivity of inputs; Increased efficiency in the use of irrigation water and general land resources; Integration of gender considerations in project implementation; Improved institutional capacity and climate change awareness among youth and adults; Reduced vulnerabilities of target communities evidenced by : Reduction of land degradation in case of flooding; Improved livelihood security and improvement in socio-economic conditions of the target communities.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | JAM/NIE/MULTI/2011/1
Implementing Entity | Planning Institute of Jamaica
Type of implementing entity | NIE
Country | Jamaica
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total | 10032 | 2508 | 7524 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries | 35% | 23.5% | 12% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 4% | 2% | 2% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 30 | Agriculture | 2: Low capacity | Total | 30 | Agriculture | 3: Medium capacity | Total | 30 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 16% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 30 | 16% | Public |  | 30 | 20% |  |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Agriculture | 2: Low capacity | Public | National | Agriculture | 3: Medium capacity | Public | National | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 25% |  | Multi-sector |  | 60 |  | Multi-sector |  | 45 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 10000 | 30% | 3: Partially aware |  | 3000 | 30% | 4: Mostly aware |  | 2508 | 25% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 3: Moderately responsive (Some defined elements) |  | Multi-sector | National | 4: Mostly responsive (Most defined elements) |  | Multi-sector | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 5: Very effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 16 | ha protected | 5: Very effective | Catchment area/Watershed/Aquifer | 16 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1000 | 20% | 2: Limited improvement |  | 1000 | 25% | 4: High improvement |  | 1000 | 20% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 110 | Adaptation strategies | Agriculture | Irrigation system | 110 | Adaptation strategies | Agriculture | Irrigation system | 108 | Adaptation strategies | Agriculture | Irrigation system
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 401 | Agribusiness |  | 78248 | 2700 | Agricultural-related |  | 12000000 | 2400 | Agricultural-related |  | 10000000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 67 | Handicrafts
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20 | Agribusiness
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Communication & Information policy | 1 | Multi-sector | National | Climate Change Policy | 1 | Multi-sector | National | Climate Change Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.