## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 2021 until July 2022
| Project Title: | Community Adaptation for Forest-Food Based Management in Saddang Watershed Ecosystem
| Project Summary: | The main objective of this project is to increase resilience to food security of the community of Saddang Watershed Ecosystem, in South Sulawesi Province, Indonesia as an effort to adapt to climate change that focuses on: (1) Strengthening Social Forestry in Encouraging Forest Food in the Upstream Saddang Watershed; (2) Improvement of coastal governance and carrying capacity in supporting climate change adaptation in the downstream Saddang watershed; (3) Strengthening Cross-Sectoral Policies to Ensure the Sustainability of Climate Change Adaptation; (4) Strengthen stakeholder capacity and support through knowledge management. Component 1: 5,291 hectares of Social Forestry were expanded and strengthened as a result of this project, of which 3,590 ha were distributed to provide legal access and strengthening and 1,701 ha were used to improve group institutions and business management. 18 forest food seed homes were constructed in 10 intervention villages in the Saddang Watershed upstream. On 60 hectares of critical land in forested areas, the Multi-purpose Tree Species (MPTS) plant nursery's findings, which had a growing percentage of about 71 percent, were used to rehabilitate with the agroforestry technique. Candlenuts, palm sugar, coffee, and sikapa (tubers) are among the products that this project has generated through community-based forest food businesses. Component 2: At the village and sub-district levels, five (5) Climate Change Care Groups (Kelompok Peduli Perubahan Iklim/KPPI) with a combined membership of 100 people were established as the driving force. By planting 1,4 km of mangroves with 25.000 seedlings and propagules, the coastal area downstream of the Saddang Watershed has been given an enhanced carrying capacity. Five (5) home industry groups have been developed to support the growth of livelihoods; these organizations, which are vulnerable to manufacturing a variety of foods, are made up of women's groups. This group has the infrastructure and production tools necessary to process seaweed and snakefruit, two common commodities. Component 3: Strengthening the system and institutional capacity was carried out in collaboration with the Regional Government of South Sulawesi through the signing of an MoU between the Provincial Government, KAPABEL and KEMITRAAN which was carried out at the start of the program. Strengthening the capacity of members of the Regional Low Carbon Development Working Group (POKJA PRKD) and the Social Forestry Acceleration Working Group (POKJA PPS) through a series of training and workshops. Due to the involvement of this project, internalization of climate change adaptation issues, forest food-based social forestry management, and gender mainstreaming have been realized and elevated to the status of key points in the South Sulawesi Social Forestry Acceleration Roadmap. With the formation of the Social Forestry Acceleration Working Group, institutional strengthening in integrating climate change adaptation efforts at the district level has been accomplished (POKJA PPS). In order to ensure the sustainability of the program for addressing climate change, 12 of the 15 communities that the program has aided have enrolled or are registered with the Climate Village Program. Component 4: Program dissemination to support and promote policies and alignments was accomplished through the creation of 1 documentary film, 1 best practice book, 5 scientific papers, 8 infographics, 1 poster, 1 digital media (website), and 8 climate change adaptation promotional billboards. This component has created a platform for an early warning system for coping with climate change in the Saddang Watershed community in addition to disseminating products. The "Climate Smart Community" application, which provides statistics and information on rainfall forecasts, temperature, air humidity, weather warnings, land-use patterns, land cover, and mangroves in the Saddang Watershed area, can be used by stakeholders to monitor climate change adaptation. The technological platform is designed using a system that is easier for different parties to access. Both WebGIS and mobile apps can be used to access the apps. In order to support microclimate data that can be tracked in real-time and be installed in selected Village/Kelurahan offices from the program's assisted villages, the program will also provide two units of weather stations in the upstream area of the Saddang Watershed as part of the planning to build this platform.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IDN/NIE/Food/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | KEMITRAAN | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Indonesia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Villages in SADDANG Watershed Ecosystem Area: 1) Toraja Utara Regency: Karre Limbong, Sapan Kua-Kua, and Bokin Village; 2) Tana Toraja Regency: Randan Batu, Parindingan, Paku, and Sese Salu Village; 3) Enrekang Regency: Tungka, Pundilemo, Ranga, and Paladang Villages; 4) Pinrang Regency: Paria, Bababinanga, Salipolo, Massewae, and Katomporang Village. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-07-08
IE-AFB Agreement Signature Date: |  | 2019-10-24 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-10-20 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2021-08-15
2022-04-20
Original Completion Date:
Revised Completion Date after approval of |  | 2022-07-31
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Revised the environmental and social management plan outlining clear roles and responsibilities for implementation and adaptive management
| Current Status | Condition met and cleared by the AFB Sec
Planned actions, including a detailed time schedule
| Category of condition | Gender
| Condition or Requirement | Revised gender assessment in line with the Adaptation Fund environmental and social policy and gender policy
| Current Status | Condition met and cleared by the AFB Sec
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report of this project was submitted on 1st November 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | http://adaptasi.tlkm.or.id | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dewi Rizki | Dominican Republic
| Email: | dewi.rizki@kemitraan.or.id | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ir. Laksmi Dhewanthi, M.A. | Equatoral Guinea
| Email: | ldhewanthi@menlhk.go.id | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laode M. Syarif, PhD | Fiji
| Email: | laode.syarif@kemitraan.or.id | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Muh. Ichwan K | Georgia
| Email: | muhichwank@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | M. Gusti Zainal | Grenada
| Email: | mgusti.zainal@gmail.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Muchlas Dharmawan Tualle | Guyana
| Email: | uttaamdt@gmail.com | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] | [5 empty] | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [October 31, 2021] | 374174 |  |  | Estimated cumulative total disbursement as of [July 22] | 461291.4792 |  |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Uncommitted figures not yet disbursed to executing entities to date = USD 389,754 (exclude budget audit in PEC ) |  |  | Add any comments on AF Grant Funds. (word limit=200) | The budget absorption until the end of July 2022 is USD 835.465, including the project audit. |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Activity 1.1.1.1 Multistakeholder meetings proposing social forestry schemes | 1312.6351 |  |  | Activity 1.1.1.1 Multistakeholder meetings proposing social forestry schemes | 0 | 1312.6351 | 1312.6351 | TRUE
| Activity 1.1.1.2 Facilitation of document preparation and legal advocacy for Social Forestry | 15297.8572 |  |  | Activity 1.1.1.2 Facilitation of document preparation and legal advocacy for Social Forestry | 4500.901 | 19798.7582 | 19798.7582 | TRUE
| Activity 1.1.1.3 Operationalization of Social Forestry Outcome Leader | 29076.9792 |  |  | Activity 1.1.1.3 Operationalization of Social Forestry Outcome Leader | 4267.3908 | 33344.3701 | 33344.3701 | TRUE
| Activity 1.1.2.1 Need assessment of forest land rehabilitation area | 0 |  |  | Activity 1.1.2.1 Need assessment of forest land rehabilitation area | 965.3461 | 965.3461 | 965.3461 | TRUE
| Activity 1.1.2.2 Rehabilitation of forest land with agroforestry pattern | 0 |  |  | Activity 1.1.2.2 Rehabilitation of forest land with agroforestry pattern | 2778.8583 | 2778.8583 | 2778.8583 | TRUE
| Activity 1.1.2.3 Nursery development | 23742.2117 |  |  | Activity 1.1.2.3 Nursery development | 11527.1937 | 35269.4054 | 35269.4054 | TRUE
| Activity 1.2.1.1 Field Officer Training | 5280.7143 |  |  | Activity 1.2.1.1 Field Officer Training | 139.6579 | 5420.3721 | 5420.3721 | TRUE
| Activity 1.2.1.2 Facilitation of Field Officer operationalization | 75178.0845 |  |  | Activity 1.2.1.2 Facilitation of Field Officer operationalization | 14043.0023 | 89221.0868 | 89221.0868 | TRUE
| Activity 1.2.1.3 Dissemination of information on social forestry in each project target village | 1742.9742 |  |  | Activity 1.2.1.3 Dissemination of information on social forestry in each project target village | 208.8665 | 1951.8407 | 1951.8407 | TRUE
| Activity 1.2.1.4 Regular meetings in each village to strengthen group capacity | 2613.6455 |  |  | Activity 1.2.1.4 Regular meetings in each village to strengthen group capacity | 4522.1142 | 7135.7597 | 7135.7597 | TRUE
| Activity 1.2.2.1 Facilitation of KTH establishment | 1675.0786 |  |  | Activity 1.2.2.1 Facilitation of KTH establishment | 0 | 1675.0786 | 1675.0786 | TRUE
| Activity 1.2.2.2 Workshop on the management and utilization of sustainable forest resources | 407.8755 |  |  | Activity 1.2.2.2 Workshop on the management and utilization of sustainable forest resources | 1852.4021 | 2260.2777 | 2260.2777 | TRUE
| Activity 1.2.2.3 POKJA-PPS training in supporting climate change adaptation | 2256.5298 |  |  | Activity 1.2.2.3 POKJA-PPS training in supporting climate change adaptation | 1253.199 | 3509.7288 | 3509.7288 | TRUE
| Activity 1.2.2.4 Multistakeholder meetings to internalize climate change adaptation actions | 90.639 |  |  | Activity 1.2.2.4 Multistakeholder meetings to internalize climate change adaptation actions | 0 | 90.639 | 90.639 | TRUE
| Activity 1.2.2.5 Workshop on climate change adaptation actions | 1550.1083 |  |  | Activity 1.2.2.5 Workshop on climate change adaptation actions | 0 | 1550.1083 | 1550.1083 | TRUE
| Activity 1.2.3.1 Multistakeholder meeting on Social Forestry acceleration in each intervention area | 725.4955 |  |  | Activity 1.2.3.1 Multistakeholder meeting on Social Forestry acceleration in each intervention area | 3490.2739 | 4215.7694 | 4215.7694 | TRUE
| Activity 1.2.3.2 Workshop on Social Forestry Acceleration and MoU signing | 163.8474 |  |  | Activity 1.2.3.2 Workshop on Social Forestry Acceleration and MoU signing | 7832.1748 | 7996.0222 | 7996.0222 | TRUE
| Activity 1.2.3.3 Regular FGDs to monitor the achievements of the POKJA PPS | 1493.8297 |  |  | Activity 1.2.3.3 Regular FGDs to monitor the achievements of the POKJA PPS | 1984.3936 | 3478.2233 | 3478.2233 | TRUE
| Activity 1.2.3.4 Operationalization of Officer Coord. in the upstream area | 976.1124 |  |  | Activity 1.2.3.4 Operationalization of Officer Coord. in the upstream area | 5110.5515 | 6086.6639 | 6086.6639 | TRUE
| Activity 1.3.1.1 Technical training on agroforestry model forest processing | 1246.7871 |  |  | Activity 1.3.1.1 Technical training on agroforestry model forest processing | 1985.4745 | 3232.2616 | 3232.2616 | TRUE
| Activity 1.3.1.2 Product packaging training | 0 |  |  | Activity 1.3.1.2 Product packaging training | 6931.165 | 6931.165 | 6931.165 | TRUE
| Activity 1.3.1.3 Facilitation of module preparation for forest food cultivation | 2620.8478 |  |  | Activity 1.3.1.3 Facilitation of module preparation for forest food cultivation | 4551.3902 | 7172.238 | 7172.238 | TRUE
| Activity 1.3.1.4 Regular discussions among forest farmer, women’s and vulnerable groups | 474.809 |  |  | Activity 1.3.1.4 Regular discussions among forest farmer, women’s and vulnerable groups | 2119.4152 | 2594.2242 | 2594.2242 | TRUE
| Activity 1.3.1.5 Comparative study of flagship forest food management | 0 |  |  | Activity 1.3.1.5 Comparative study of flagship forest food management | 21977.0208 | 21977.0208 | 21977.0208 | TRUE
| Activity 1.3.1.6 Entrepreneurship training | 0 |  |  | Activity 1.3.1.6 Entrepreneurship training | 7180.6355 | 7180.6355 | 7180.6355 | TRUE
| Activity 1.3.2.1 Facilitation of processing permits for household products | 0 |  |  | Activity 1.3.2.1 Facilitation of processing permits for household products | 2374.081 | 2374.081 | 2374.081 | TRUE
| Activity 1.3.2.2 Provision of forest food processing equipment | 2112.9891 |  |  | Activity 1.3.2.2 Provision of forest food processing equipment | 36780.6451 | 38893.6342 | 38893.6342 | TRUE
| Activity 1.3.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 30.279 |  |  | Activity 1.3.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 4618.9964 | 4649.2754 | 4649.2754 | TRUE
| Activity 1.3.3.1 Study of supply chain and value chain of forest food products | 2062.8044 |  |  | Activity 1.3.3.1 Study of supply chain and value chain of forest food products | 1753.0861 | 3815.8905 | 3815.8905 | TRUE
| Activity 1.3.3.2 Dissemination of supply chain and value chain study results | 0 |  |  | Activity 1.3.3.2 Dissemination of supply chain and value chain study results | 2518.868 | 2518.868 | 2518.868 | TRUE
| Activity 1.3.3.3 Meetings of business actors at the supply and demand level | 4224.8671 |  |  | Activity 1.3.3.3 Meetings of business actors at the supply and demand level | 2883.6759 | 7108.543 | 7108.543 | TRUE
| Activity 2.1.1.1 Dissemination of information and meetings on group formation | 2773.2085 |  |  | Activity 2.1.1.1 Dissemination of information and meetings on group formation | 145.6423 | 2918.8508 | 2918.8508 | TRUE
| Activity 2.1.1.2 Facilitation of regular KPPI meetings | 3194.5997 |  |  | Activity 2.1.1.2 Facilitation of regular KPPI meetings | 1969.5959 | 5164.1957 | 5164.1957 | TRUE
| Activity 2.1.1.3 Operasionalisasi pendamping lapanganWil. HilirOperationalization of Downstream Field Officer | 15687.5205 |  |  | Activity 2.1.1.3 Operasionalisasi pendamping lapanganWil. HilirOperationalization of Downstream Field Officer | 28161.8143 | 43849.3348 | 43849.3348 | TRUE
| Activity 2.1.2.1 Leadership training for climate change care groups | 2057.4629 |  |  | Activity 2.1.2.1 Leadership training for climate change care groups | 0 | 2057.4629 | 2057.4629 | TRUE
| Activity 2.1.2.2 Training on facilitation and mentoring | 1716.912 |  |  | Activity 2.1.2.2 Training on facilitation and mentoring | 0 | 1716.912 | 1716.912 | TRUE
| Activity 2.1.2.3 Mangrove cultivation training | 3690.1155 |  |  | Activity 2.1.2.3 Mangrove cultivation training | 180.1242 | 3870.2396 | 3870.2396 | TRUE
| Activity 2.1.2.4 Regular consultation meetings | 843.8004 |  |  | Activity 2.1.2.4 Regular consultation meetings | 1489.1645 | 2332.9648 | 2332.9648 | TRUE
| Activity 2.1.2.5 Study of pond aquaculture | 6184.3692 |  |  | Activity 2.1.2.5 Study of pond aquaculture | 0 | 6184.3692 | 6184.3692 | TRUE
| Activity 2.1.2.6 Operationalization of Downstream Fled Officer Coord | 0 |  |  | Activity 2.1.2.6 Operationalization of Downstream Fled Officer Coord | 10822.8772 | 10822.8772 | 10822.8772 | TRUE
| Activity 2.1.3.1 Provision of coastal land rehabilitation equipment | 10631.2584 |  |  | Activity 2.1.3.1 Provision of coastal land rehabilitation equipment | 816.3891 | 11447.6475 | 11447.6475 | TRUE
| Activity 2.1.3.2 Facilitation of technical guidelines preparation for the operation and maintenance of equipment | 3851.7395 |  |  | Activity 2.1.3.2 Facilitation of technical guidelines preparation for the operation and maintenance of equipment | 3195.1309 | 7046.8704 | 7046.8704 | TRUE
| Activity 2.1.3.3 Planting area distribution meeting for each group | 1366.2785 |  |  | Activity 2.1.3.3 Planting area distribution meeting for each group | 0 | 1366.2785 | 1366.2785 | TRUE
| Activity 2.1.3.4 Procurement of mangrove seeds | 2844.6704 |  |  | Activity 2.1.3.4 Procurement of mangrove seeds | 0 | 2844.6704 | 2844.6704 | TRUE
| Activity 2.1.3.5 Mangrove plantings | 4724.1399 |  |  | Activity 2.1.3.5 Mangrove plantings | 5955.2932 | 10679.4331 | 10679.4331 | TRUE
| Activity 2.2.1.1 Entrepreneurship training | 0 |  |  | Activity 2.2.1.1 Entrepreneurship training | 2953.6232 | 2953.6232 | 2953.6232 | TRUE
| Activity 2.2.1.2 Creative business training from coastal resources products | 0 |  |  | Activity 2.2.1.2 Creative business training from coastal resources products | 3755.7971 | 3755.7971 | 3755.7971 | TRUE
| Activity 2.2.1.3 Cultivation and post-harvest training | 0 |  |  | Activity 2.2.1.3 Cultivation and post-harvest training | 1601.8528 | 1601.8528 | 1601.8528 | TRUE
| Activity 2.2.1.4 Operationalization of coastal outcome leader | 6969.8956 |  |  | Activity 2.2.1.4 Operationalization of coastal outcome leader | 8137.1569 | 15107.0525 | 15107.0525 | TRUE
| Activity 2.2.2.1 Procurement of processing equipment for coastal natural resources | 3065.0835 |  |  | Activity 2.2.2.1 Procurement of processing equipment for coastal natural resources | 18788.9672 | 21854.0507 | 21854.0507 | TRUE
| Activity 2.2.2.2 Procurement of diversified food processing equipment (on-farm and off farm) | 0 |  |  | Activity 2.2.2.2 Procurement of diversified food processing equipment (on-farm and off farm) | 878.6232 | 878.6232 | 878.6232 | TRUE
| Activity 2.2.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 0 |  |  | Activity 2.2.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 1579.3651 | 1579.3651 | 1579.3651 | TRUE
| Activity 2.2.3.1 Study of supply chain and value chain of forest food products | 1189.637 |  |  | Activity 2.2.3.1 Study of supply chain and value chain of forest food products | 2583.2896 | 3772.9266 | 3772.9266 | TRUE
| Activity 2.2.3.2 Dissemination of supply chain and value chain study results | 525.009 |  |  | Activity 2.2.3.2 Dissemination of supply chain and value chain study results | 0 | 525.009 | 525.009 | TRUE
| Activity 2.2.3.3 Meetings of business actors at the supply and demand level | 1055.1827 |  |  | Activity 2.2.3.3 Meetings of business actors at the supply and demand level | 2036.2455 | 3091.4281 | 3091.4281 | TRUE
| Activity 3.1.1.1 Multistakeholder meeting for the formation of POKJA-API for the Saddang Watershed Ecosystem | 83.3182 |  |  | Activity 3.1.1.1 Multistakeholder meeting for the formation of POKJA-API for the Saddang Watershed Ecosystem | 1849.3039 | 1932.6221 | 1932.6221 | TRUE
| Activity 3.1.1.2 Workshop on the establishment of POKJA API for the Saddang Watershed Ecosystem | 0 |  |  | Activity 3.1.1.2 Workshop on the establishment of POKJA API for the Saddang Watershed Ecosystem | 3238.3058 | 3238.3058 | 3238.3058 | TRUE
| Activity 3.1.1.3 Training on preparing climate change adaptation action plans | 0 |  |  | Activity 3.1.1.3 Training on preparing climate change adaptation action plans | 6397.7304 | 6397.7304 | 6397.7304 | TRUE
| Activity 3.1.1.4 Facilitation of regular meetings with POKJA API for the Saddang Watershed Ecosystem | 298.2651 |  |  | Activity 3.1.1.4 Facilitation of regular meetings with POKJA API for the Saddang Watershed Ecosystem | 3497.3657 | 3795.6307 | 3795.6307 | TRUE
| Activity 3.1.2.1 Multistakeholder meetings in climate change adaptation action plan of Saddang Watershed ecosystem | 0 |  |  | Activity 3.1.2.1 Multistakeholder meetings in climate change adaptation action plan of Saddang Watershed ecosystem | 3553.1672 | 3553.1672 | 3553.1672 | TRUE
| Activity 3.1.2.2 Vulnerability and risk assessment of climate change | 8973.4639 |  |  | Activity 3.1.2.2 Vulnerability and risk assessment of climate change | 6848.5374 | 15822.0014 | 15822.0014 | TRUE
| Activity 3.1.2.3 Facilitation of regular meetings of POKJA-API in preparing the Climate Change Adaptation Action Plan at the Regional Level | 0 |  |  | Activity 3.1.2.3 Facilitation of regular meetings of POKJA-API in preparing the Climate Change Adaptation Action Plan at the Regional Level | 3502.6556 | 3502.6556 | 3502.6556 | TRUE
| Activity 3.1.2.4 Facilitation of proposed climate change adaptation action plan into Village Regulations | 0 |  |  | Activity 3.1.2.4 Facilitation of proposed climate change adaptation action plan into Village Regulations | 9695.6522 | 9695.6522 | 9695.6522 | TRUE
| Activity 3.1.2.5 Facilitation of proposed Climate Change Adaptation Action Plan into Local Regulations | 13.3703 |  |  | Activity 3.1.2.5 Facilitation of proposed Climate Change Adaptation Action Plan into Local Regulations | 4809.0935 | 4822.4638 | 4822.4638 | TRUE
| Activity 3.1.2.6 Multistakeholder meetings in integrating the Climate Change Adaptation Action Plan into the Strategic Plan of the Local Government Unit (Renstra SKPD) | 3346.671 |  |  | Activity 3.1.2.6 Multistakeholder meetings in integrating the Climate Change Adaptation Action Plan into the Strategic Plan of the Local Government Unit (Renstra SKPD) | 8233.7336 | 11580.4047 | 11580.4047 | TRUE
| Activity 3.1.3.1 Training on preparing climate change adaptation monitoring system | 0 |  |  | Activity 3.1.3.1 Training on preparing climate change adaptation monitoring system | 3213.9781 | 3213.9781 | 3213.9781 | TRUE
| Activity 3.1.3.2 Facilitation in developing climate change adaptation action monitoring application | 5856.6743 |  |  | Activity 3.1.3.2 Facilitation in developing climate change adaptation action monitoring application | 10791.6375 | 16648.3118 | 16648.3118 | TRUE
| Activity 3.1.3.3 Dissemination of climate change adaptation monitoring system | 0 |  |  | Activity 3.1.3.3 Dissemination of climate change adaptation monitoring system | 1671.3428 | 1671.3428 | 1671.3428 | TRUE
| Activity 3.1.3.4 Training on operationalizing the application to stakeholders | 2968.4275 |  |  | Activity 3.1.3.4 Training on operationalizing the application to stakeholders | 4077.6136 | 7046.041 | 7046.041 | TRUE
| Activity 4.1.1.1 Making and launching of documentary film related to climate change adaptation action | 5090.1125 |  |  | Activity 4.1.1.1 Making and launching of documentary film related to climate change adaptation action | 5286.8205 | 10376.933 | 10376.933 | TRUE
| Activity 4.1.1.2 Development and launching of best practice and lessons learned book on climate change adaptation and climate change adaptation journal | 8217.4295 |  |  | Activity 4.1.1.2 Development and launching of best practice and lessons learned book on climate change adaptation and climate change adaptation journal | 22586.3801 | 30803.8096 | 30803.8096 | TRUE
| Activity 4.1.1.3 Development of policy brief related to the climate change adaptation strategy based on sustainable forest food security | 0 |  |  | Activity 4.1.1.3 Development of policy brief related to the climate change adaptation strategy based on sustainable forest food security | 4084.6976 | 4084.6976 | 4084.6976 | TRUE
| Activity 4.1.1.4 Development of leaflets, posters, banners | 2753.3342 |  |  | Activity 4.1.1.4 Development of leaflets, posters, banners | 1019.8951 | 3773.2293 | 3773.2293 | TRUE
| Activity 4.1.1.5 Development of website and social media on climate change adaptation in Saddang watershed ecosystem | 2225.2035 |  |  | Activity 4.1.1.5 Development of website and social media on climate change adaptation in Saddang watershed ecosystem | 0 | 2225.2035 | 2225.2035 | TRUE
| Activity 4.1.1.6 Facilitation of partnership with providers in publication of climate change adaptation action | 10.4583 |  |  | Activity 4.1.1.6 Facilitation of partnership with providers in publication of climate change adaptation action | 661.4106 | 671.8689 | 671.8689 | TRUE
| Activity 4.1.1.7 Rental of promotional billboard on climate change adaptation in Saddang watershed ecosystem | 2295.6072 |  |  | Activity 4.1.1.7 Rental of promotional billboard on climate change adaptation in Saddang watershed ecosystem | 97.7008 | 2393.308 | 2393.308 | TRUE
| Activity 4.1.2.1 Facilitation of multistakeholder cooperation for the application of disaster response early warning system | 1160.0399 |  |  | Activity 4.1.2.1 Facilitation of multistakeholder cooperation for the application of disaster response early warning system | 1719.3619 | 2879.4018 | 2879.4018 | TRUE
| Activity 4.1.2.2 Development of application and supporting tools for disaster response early warning system | 0 |  |  | Activity 4.1.2.2 Development of application and supporting tools for disaster response early warning system | 16140.9242 | 16140.9242 | 16140.9242 | TRUE
| Activity 4.1.2.3. Training on the use of applied technology for disaster response early warning system | 0 |  |  | Activity 4.1.2.3. Training on the use of applied technology for disaster response early warning system | 2339.3047 | 2339.3047 | 2339.3047 | TRUE
| Activity 4.1.2.4. Dissemination of information/ Workshop on the application of disaster response early warning system | 376.5005 |  |  | Activity 4.1.2.4. Dissemination of information/ Workshop on the application of disaster response early warning system | 1734.1716 | 2110.6721 | 2110.6721 | TRUE
| Activity 4.1.2.5 Monitoring and Evaluation | 6568.808 |  |  | Activity 4.1.2.5 Monitoring and Evaluation | 11629.6315 | 18198.4395 | 18198.4395 | TRUE
| A. Project/Program Excecution Cost | 45893.82 |  |  | A. Project/Program Excecution Cost | 31271.4571 | 77165.2771 | 77165.2771 | TRUE
| B. Project Cycle Managemet Services | 29313.133 |  |  | B. Project Cycle Managemet Services | 36137.8747 | 65451.0077 | 65451.0077 | TRUE
| TOTAL | 374173.5215 |  |  | TOTAL | 461291.4792 |  |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE | [5 empty] | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activity 1.1.1.1 Multistakeholder meetings proposing social forestry schemes | 0 | 2022-07-30 |  | Activity 1.1.1.1 Multistakeholder meetings proposing social forestry schemes | 0 | -
| Activity 1.1.1.2 Facilitation of document preparation and legal advocacy for Social Forestry | 2579.5889 | 2022-07-30 |  | Activity 1.1.1.2 Facilitation of document preparation and legal advocacy for Social Forestry | 0 | -
| Activity 1.1.1.3 Operationalization of Social Forestry Outcome Leader | 1760.9154 | 2022-07-30 |  | Activity 1.1.1.3 Operationalization of Social Forestry Outcome Leader | 0 | -
| Activity 1.1.2.1 Need assessment of forest land rehabilitation area | 891.3043 | 2022-07-30 |  | Activity 1.1.2.1 Need assessment of forest land rehabilitation area | 0 | -
| Activity 1.1.2.2 Rehabilitation of forest land with agroforestry pattern | 15905.0478 | 2022-07-30 |  | Activity 1.1.2.2 Rehabilitation of forest land with agroforestry pattern | 0 | -
| Activity 1.1.2.3 Nursery development | 0 | 2022-07-30 |  | Activity 1.1.2.3 Nursery development | 0 | -
| Activity 1.2.1.1 Field Officer Training | 732.2733 | 2022-07-30 |  | Activity 1.2.1.1 Field Officer Training | 0 | -
| Activity 1.2.1.2 Facilitation of Field Officer operationalization | 14143.5822 | 2022-07-30 |  | Activity 1.2.1.2 Facilitation of Field Officer operationalization | 0 | -
| Activity 1.2.1.3 Dissemination of information on social forestry in each project target village | 0 | 2022-07-30 |  | Activity 1.2.1.3 Dissemination of information on social forestry in each project target village | 0 | -
| Activity 1.2.1.4 Regular meetings in each village to strengthen group capacity | 6342.8128 | 2022-07-30 |  | Activity 1.2.1.4 Regular meetings in each village to strengthen group capacity | 0 | -
| Activity 1.2.2.1 Facilitation of KTH establishment | 0 | 2022-07-30 |  | Activity 1.2.2.1 Facilitation of KTH establishment | 0 | -
| Activity 1.2.2.2 Workshop on the management and utilization of sustainable forest resources | 1463.139 | 2022-07-30 |  | Activity 1.2.2.2 Workshop on the management and utilization of sustainable forest resources | 0 | -
| Activity 1.2.2.3 POKJA-PPS training in supporting climate change adaptation | 0 | 2022-07-30 |  | Activity 1.2.2.3 POKJA-PPS training in supporting climate change adaptation | 0 | -
| Activity 1.2.2.4 Multistakeholder meetings to internalize climate change adaptation actions | 895.5929 | 2022-07-30 |  | Activity 1.2.2.4 Multistakeholder meetings to internalize climate change adaptation actions | 0 | -
| Activity 1.2.2.5 Workshop on climate change adaptation actions | 3948.8605 | 2022-07-30 |  | Activity 1.2.2.5 Workshop on climate change adaptation actions | 0 | -
| Activity 1.2.3.1 Multistakeholder meeting on Social Forestry acceleration in each intervention area | 4520.8813 | 2022-07-30 |  | Activity 1.2.3.1 Multistakeholder meeting on Social Forestry acceleration in each intervention area | 0 | -
| Activity 1.2.3.2 Workshop on Social Forestry Acceleration and MoU signing | 2218.0366 | 2022-07-30 |  | Activity 1.2.3.2 Workshop on Social Forestry Acceleration and MoU signing | 0 | -
| Activity 1.2.3.3 Regular FGDs to monitor the achievements of the POKJA PPS | 1984.4312 | 2022-07-30 |  | Activity 1.2.3.3 Regular FGDs to monitor the achievements of the POKJA PPS | 0 | -
| Activity 1.2.3.4 Operationalization of Officer Coord. in the upstream area | 5110.8441 | 2022-07-30 |  | Activity 1.2.3.4 Operationalization of Officer Coord. in the upstream area | 0 | -
| Activity 1.3.1.1 Technical training on agroforestry model forest processing | 4383.6477 | 2022-07-30 |  | Activity 1.3.1.1 Technical training on agroforestry model forest processing | 0 | -
| Activity 1.3.1.2 Product packaging training | 6144.9275 | 2022-07-30 |  | Activity 1.3.1.2 Product packaging training | 0 | -
| Activity 1.3.1.3 Facilitation of module preparation for forest food cultivation | 5467.558 | 2022-07-30 |  | Activity 1.3.1.3 Facilitation of module preparation for forest food cultivation | 0 | -
| Activity 1.3.1.4 Regular discussions among forest farmer, women’s and vulnerable groups | 2242.5823 | 2022-07-30 |  | Activity 1.3.1.4 Regular discussions among forest farmer, women’s and vulnerable groups | 0 | -
| Activity 1.3.1.5 Comparative study of flagship forest food management | 16927.5362 | 2022-07-30 |  | Activity 1.3.1.5 Comparative study of flagship forest food management | 0 | -
| Activity 1.3.1.6 Entrepreneurship training | 6477.5362 | 2022-07-30 |  | Activity 1.3.1.6 Entrepreneurship training | 0 | -
| Activity 1.3.2.1 Facilitation of processing permits for household products | 5072.4638 | 2022-07-30 |  | Activity 1.3.2.1 Facilitation of processing permits for household products | 0 | -
| Activity 1.3.2.2 Provision of forest food processing equipment | 44604.4022 | 2022-07-30 |  | Activity 1.3.2.2 Provision of forest food processing equipment | 0 | -
| Activity 1.3.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 2466.8224 | 2022-07-30 |  | Activity 1.3.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 0 | -
| Activity 1.3.3.1 Study of supply chain and value chain of forest food products | 2267.6304 | 2022-07-30 |  | Activity 1.3.3.1 Study of supply chain and value chain of forest food products | 0 | -
| Activity 1.3.3.2 Dissemination of supply chain and value chain study results | 1297.8261 | 2022-07-30 |  | Activity 1.3.3.2 Dissemination of supply chain and value chain study results | 0 | -
| Activity 1.3.3.3 Meetings of business actors at the supply and demand level | 3173.0259 | 2022-07-30 |  | Activity 1.3.3.3 Meetings of business actors at the supply and demand level | 0 | -
| Activity 2.1.1.1 Dissemination of information and meetings on group formation | 109.0415 | 2022-07-30 |  | Activity 2.1.1.1 Dissemination of information and meetings on group formation | 0 | -
| Activity 2.1.1.2 Facilitation of regular KPPI meetings | 2222.067 | 2022-07-30 |  | Activity 2.1.1.2 Facilitation of regular KPPI meetings | 0 | -
| Activity 2.1.1.3 Operasionalisasi pendamping lapanganWil. HilirOperationalization of Downstream Field Officer | 23442.9143 | 2022-07-30 |  | Activity 2.1.1.3 Operasionalisasi pendamping lapanganWil. HilirOperationalization of Downstream Field Officer | 0 | -
| Activity 2.1.2.1 Leadership training for climate change care groups | 17.1747 | 2022-07-30 |  | Activity 2.1.2.1 Leadership training for climate change care groups | 0 | -
| Activity 2.1.2.2 Training on facilitation and mentoring | 70.0446 | 2022-07-30 |  | Activity 2.1.2.2 Training on facilitation and mentoring | 0 | -
| Activity 2.1.2.3 Mangrove cultivation training | 0 | 2022-07-30 |  | Activity 2.1.2.3 Mangrove cultivation training | 0 | -
| Activity 2.1.2.4 Regular consultation meetings | 3990.0708 | 2022-07-30 |  | Activity 2.1.2.4 Regular consultation meetings | 0 | -
| Activity 2.1.2.5 Study of pond aquaculture | 337.3699 | 2022-07-30 |  | Activity 2.1.2.5 Study of pond aquaculture | 0 | -
| Activity 2.1.2.6 Operationalization of Downstream Fled Officer Coord | 9130.4348 | 2022-07-30 |  | Activity 2.1.2.6 Operationalization of Downstream Fled Officer Coord | 0 | -
| Activity 2.1.3.1 Provision of coastal land rehabilitation equipment | 396.6402 | 2022-07-30 |  | Activity 2.1.3.1 Provision of coastal land rehabilitation equipment | 0 | -
| Activity 2.1.3.2 Facilitation of technical guidelines preparation for the operation and maintenance of equipment | 3077.246 | 2022-07-30 |  | Activity 2.1.3.2 Facilitation of technical guidelines preparation for the operation and maintenance of equipment | 0 | -
| Activity 2.1.3.3 Planting area distribution meeting for each group | 354.736 | 2022-07-30 |  | Activity 2.1.3.3 Planting area distribution meeting for each group | 0 | -
| Activity 2.1.3.4 Procurement of mangrove seeds | 0 | 2022-07-30 |  | Activity 2.1.3.4 Procurement of mangrove seeds | 0 | -
| Activity 2.1.3.5 Mangrove plantings | 7232.3818 | 2022-07-30 |  | Activity 2.1.3.5 Mangrove plantings | 0 | -
| Activity 2.2.1.1 Entrepreneurship training | 2225.3623 | 2022-07-30 |  | Activity 2.2.1.1 Entrepreneurship training | 0 | -
| Activity 2.2.1.2 Creative business training from coastal resources products | 3440.5797 | 2022-07-30 |  | Activity 2.2.1.2 Creative business training from coastal resources products | 0 | -
| Activity 2.2.1.3 Cultivation and post-harvest training | 3748.9744 | 2022-07-30 |  | Activity 2.2.1.3 Cultivation and post-harvest training | 0 | -
| Activity 2.2.1.4 Operationalization of coastal outcome leader | 8247.4957 | 2022-07-30 |  | Activity 2.2.1.4 Operationalization of coastal outcome leader | 0 | -
| Activity 2.2.2.1 Procurement of processing equipment for coastal natural resources | 11611.5469 | 2022-07-30 |  | Activity 2.2.2.1 Procurement of processing equipment for coastal natural resources | 0 | -
| Activity 2.2.2.2 Procurement of diversified food processing equipment (on-farm and off farm) | 10797.1014 | 2022-07-30 |  | Activity 2.2.2.2 Procurement of diversified food processing equipment (on-farm and off farm) | 0 | -
| Activity 2.2.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 2568.7861 | 2022-07-30 |  | Activity 2.2.2.3 Facilitation of technical module preparation for operation and maintenance of equipment | 0 | -
| Activity 2.2.3.1 Study of supply chain and value chain of forest food products | 3419.0587 | 2022-07-30 |  | Activity 2.2.3.1 Study of supply chain and value chain of forest food products | 0 | -
| Activity 2.2.3.2 Dissemination of supply chain and value chain study results | 202.5272 | 2022-07-30 |  | Activity 2.2.3.2 Dissemination of supply chain and value chain study results | 0 | -
| Activity 2.2.3.3 Meetings of business actors at the supply and demand level | 994.0927 | 2022-07-30 |  | Activity 2.2.3.3 Meetings of business actors at the supply and demand level | 0 | -
| Activity 3.1.1.1 Multistakeholder meeting for the formation of POKJA-API for the Saddang Watershed Ecosystem | 902.9137 | 2022-07-30 |  | Activity 3.1.1.1 Multistakeholder meeting for the formation of POKJA-API for the Saddang Watershed Ecosystem | 0 | -
| Activity 3.1.1.2 Workshop on the establishment of POKJA API for the Saddang Watershed Ecosystem | 2413.7681 | 2022-07-30 |  | Activity 3.1.1.2 Workshop on the establishment of POKJA API for the Saddang Watershed Ecosystem | 0 | -
| Activity 3.1.1.3 Training on preparing climate change adaptation action plans | 6639.1304 | 2022-07-30 |  | Activity 3.1.1.3 Training on preparing climate change adaptation action plans | 0 | -
| Activity 3.1.1.4 Facilitation of regular meetings with POKJA API for the Saddang Watershed Ecosystem | 5498.8364 | 2022-07-30 |  | Activity 3.1.1.4 Facilitation of regular meetings with POKJA API for the Saddang Watershed Ecosystem | 0 | -
| Activity 3.1.2.1 Multistakeholder meetings in climate change adaptation action plan of Saddang Watershed ecosystem | 3804.3478 | 2022-07-30 |  | Activity 3.1.2.1 Multistakeholder meetings in climate change adaptation action plan of Saddang Watershed ecosystem | 0 | -
| Activity 3.1.2.2 Vulnerability and risk assessment of climate change | 4396.8259 | 2022-07-30 |  | Activity 3.1.2.2 Vulnerability and risk assessment of climate change | 0 | -
| Activity 3.1.2.3 Facilitation of regular meetings of POKJA-API in preparing the Climate Change Adaptation Action Plan at the Regional Level | 2717.3913 | 2022-07-30 |  | Activity 3.1.2.3 Facilitation of regular meetings of POKJA-API in preparing the Climate Change Adaptation Action Plan at the Regional Level | 0 | -
| Activity 3.1.2.4 Facilitation of proposed climate change adaptation action plan into Village Regulations | 10217.3913 | 2022-07-30 |  | Activity 3.1.2.4 Facilitation of proposed climate change adaptation action plan into Village Regulations | 0 | -
| Activity 3.1.2.5 Facilitation of proposed Climate Change Adaptation Action Plan into Local Regulations | 5261.992 | 2022-07-30 |  | Activity 3.1.2.5 Facilitation of proposed Climate Change Adaptation Action Plan into Local Regulations | 0 | -
| Activity 3.1.2.6 Multistakeholder meetings in integrating the Climate Change Adaptation Action Plan into the Strategic Plan of the Local Government Unit (Renstra SKPD) | 9175.0681 | 2022-07-30 |  | Activity 3.1.2.6 Multistakeholder meetings in integrating the Climate Change Adaptation Action Plan into the Strategic Plan of the Local Government Unit (Renstra SKPD) | 0 | -
| Activity 3.1.3.1 Training on preparing climate change adaptation monitoring system | 4815.2174 | 2022-07-30 |  | Activity 3.1.3.1 Training on preparing climate change adaptation monitoring system | 0 | -
| Activity 3.1.3.2 Facilitation in developing climate change adaptation action monitoring application | 7476.659 | 2022-07-30 |  | Activity 3.1.3.2 Facilitation in developing climate change adaptation action monitoring application | 0 | -
| Activity 3.1.3.3 Dissemination of climate change adaptation monitoring system | 1413.0435 | 2022-07-30 |  | Activity 3.1.3.3 Dissemination of climate change adaptation monitoring system | 0 | -
| Activity 3.1.3.4 Training on operationalizing the application to stakeholders | 8355.8479 | 2022-07-30 |  | Activity 3.1.3.4 Training on operationalizing the application to stakeholders | 0 | -
| Activity 4.1.1.1 Making and launching of documentary film related to climate change adaptation action | 7307.8224 | 2022-07-30 |  | Activity 4.1.1.1 Making and launching of documentary film related to climate change adaptation action | 0 | -
| Activity 4.1.1.2 Development and launching of best practice and lessons learned book on climate change adaptation and climate change adaptation journal | 15447.7878 | 2022-07-30 |  | Activity 4.1.1.2 Development and launching of best practice and lessons learned book on climate change adaptation and climate change adaptation journal | 0 | -
| Activity 4.1.1.3 Development of policy brief related to the climate change adaptation strategy based on sustainable forest food security | 2097.8261 | 2022-07-30 |  | Activity 4.1.1.3 Development of policy brief related to the climate change adaptation strategy based on sustainable forest food security | 0 | -
| Activity 4.1.1.4 Development of leaflets, posters, banners | 1811.1586 | 2022-07-30 |  | Activity 4.1.1.4 Development of leaflets, posters, banners | 0 | -
| Activity 4.1.1.5 Development of website and social media on climate change adaptation in Saddang watershed ecosystem | 0 | 2022-07-30 |  | Activity 4.1.1.5 Development of website and social media on climate change adaptation in Saddang watershed ecosystem | 0 | -
| Activity 4.1.1.6 Facilitation of partnership with providers in publication of climate change adaptation action | 2221.4257 | 2022-07-30 |  | Activity 4.1.1.6 Facilitation of partnership with providers in publication of climate change adaptation action | 0 | -
| Activity 4.1.1.7 Rental of promotional billboard on climate change adaptation in Saddang watershed ecosystem | 965.2624 | 2022-07-30 |  | Activity 4.1.1.7 Rental of promotional billboard on climate change adaptation in Saddang watershed ecosystem | 0 | -
| Activity 4.1.2.1 Facilitation of multistakeholder cooperation for the application of disaster response early warning system | 4825.4674 | 2022-07-30 |  | Activity 4.1.2.1 Facilitation of multistakeholder cooperation for the application of disaster response early warning system | 0 | -
| Activity 4.1.2.2 Development of application and supporting tools for disaster response early warning system | 9850.5072 | 2022-07-30 |  | Activity 4.1.2.2 Development of application and supporting tools for disaster response early warning system | 0 | -
| Activity 4.1.2.3. Training on the use of applied technology for disaster response early warning system | 6489.8551 | 2022-07-30 |  | Activity 4.1.2.3. Training on the use of applied technology for disaster response early warning system | 0 | -
| Activity 4.1.2.4. Dissemination of information/ Workshop on the application of disaster response early warning system | 1398.8618 | 2022-07-30 |  | Activity 4.1.2.4. Dissemination of information/ Workshop on the application of disaster response early warning system | 0 | -
| Activity 4.1.2.5 Monitoring and Evaluation | 11732.6413 | 2022-07-30 |  | Activity 4.1.2.5 Monitoring and Evaluation | 0 | -
| A. 5.1 Project/Program Excecution Cost | 27257.18 | 2022-07-30 |  | A. 5.1 Project/Program Excecution Cost | 0 | -
| B. Project Cycle Managemet Services | 36138.0173 | 2022-07-30 |  | B. Project Cycle Managemet Services | 0 | -
| TOTAL | 461291.1618 | 2022-07-30 |  | TOTAL | 0 |  |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
Note: Based on PPR AF Chechlist in Finansial Information Section page 11, "please confirm that all remaining funds wiil be spent by the project closing date i.e. By Aril 2022". Initially, EE confirmed to spend the remaining funds by the project closing date in April 2022. But the last undertaken Project Evaluation identified that not all outputs can be achieved at the closing date in Aprill 2022, so EE asked for an additional three months for extention request. The project will spend the remaining fungs in July 2022 to achieve the output target. See the attachement request for extention. | [9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[10 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[10 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[10 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Weak commitment built by EE (Excecuting Entity) with central/provincial/local government due to changes in government structure and lack of coordination and communication. | Low | Strengthening stakeholder involvement was pursued by promoting action plan documents to become regional policies in order to maintain the government's commitment or support. Government employees are also given training to help them comprehend the context of climate change and what must be done to promote adaptation in the hopes that this information will be shared with other employees.
Changes in project personnel can affect the availability of qualified staff | Low | In establishing working relationships with the PMU, the Consortium implements a recruitment system with output of work contracts during the project. With this mechanism, the personnel attachment with the consortium in achieving the project goal will be the legal basis.
Delays in disbursement of funds, procurement and institutional efficiency (long-term approval process and others) that delay project implementation. | Low | Building active communication with the grant and fulfilling all forms of financial procedures in budget disbursement. The roles and responsibilities of the Tim Layanan Kehutanan Masyarakat Foundation (TLKM Foundation) as a consortium leader to anticipate if at any time a delay in disbursement of funds can hamper the course of activities through the pre-fund. Procurement efficiency through OPG Annex
Lack of community (direct beneficiaries) support to the project | Low | - Building good relationships with key actors (suah as local government in village level and the communities) before the project starts - The formation of groups at the village level can gather all people/levels that are in target community - Utilization of activities in the form of training/workshops/group discussions to provide understanding of the project
Communities are less aware of climate change and have lack of enthusiasm to respond to disasters. If beneficiaries are not fully aware of the impacts of climate change, it is difficult to gain their commitment in forest food development and climate change adaptation | Low | This project have been implementing and introducing participatory methods to the communities so that they can be provided with understanding on the impacts of climate change. In addition, the mentoring process have been undertaking at the village level by utilizing field facilitators in each of the project target village.
Conflict of community interest in land use by PMU in nursery development | Low | This project has built trust with stakeholders in the use of nursery land. The nurseries have been established in all project target villages.
Low technical knowledge of farmers and communities to use modern forest food mining technology. | Low | This project have been providing technical support to project beneficiaries in the use of forest food development technologies in the form of training, counseling and discussion room to transfer knowledge.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic outbreak | High | - Reduce face to face meeting - Deploy field facilitators in each target village to lived-in - Increase online meeting and coordination with local authorities.
Residents and local government officials have demonstrated their opposition to field activities, as occurred in Paku village, Tana Toraja Regency. | Low | KAPABEL as EE implements the 'Grievance Mechanism' by addressing complaints from field staff concerning program operations. By personally visiting the Paku village head's house and conducting persuasive communications, the Project Coordinator has used a compelling strategy. The second visit included a field tour by the Project Coordinator and a team of specialists in Forest and Environmental Management, as well as a team of experts in Social Gender.
Temporary stoppage of activities that have changed after the inception report's publication. | Medium | KAPABEL (EE) and KEMITRAAN (NIE) collaborate and seek approval from the Directorate General of Climate Change, MoEF as the National Designated Authority in Indonesia for modifications to the program's Outcomes and Outputs with documented explanation. KAPABEL coordinates and reports on activity progress to South Sulawesi Regional Development Planning, Research and Development Agency (Bappelitbangda), requesting approval for adjustments through minutes.
Delay in Technical Verification of Social Forestry Permit Proposal Documents due to the fact that KLHK is presently suspending all incoming permits while the new MoEF Regulation on Social Forestry Management draft is being discussed. | Low | EE initiate a permission system for the collection of NTFP products, a Partnership Pattern with the Provincial Government, and consulted with a team of specialists on the mitigation strategy. The mitigation strategy did not work since, in early June, the MoEF published a new rule, No. 9/2021, allowing the request for social forestry permits to proceed.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Increasing the capacity of the direct beneficiaries at the grassroot level is the most important part in sustaining the climate change adpatation action and so becomes the most essential risk mitigation measure. In other words, increased direct beneficiaries' capacity is therefore a strong indicator for sustainability. This targeted village community are the ones who bring strong influence in determining the policy direction of the village authority, especially since the Head of Village is appointd through a direct election. Hence, the broader knowledge this community have related to climate change adaptation actions, the stronger they would drive the village authority to imporove and propoerly apply climate change adaptation policy. The Indonesian governance system encourage programmes that are developed based on inputs and recommendation from the villagers during an Assembly for Village Development Plan, which are forwarded to the sub-district, then to regency level. Climate change adaptation programmes can only be prioritized by the regency level through strong support and strong urge from the village community, especially to mitigate risks of local political impact affecting village authorities through personnel substitution and mutation within the structural local government organisation. Through the capacity building, the community of targeted villages has been taking part in the Village Development Assembly and addressed their inputs and recommendation for Climate Adaptation policy. Indeed, it is a long process until inputs and recommendations are integrated within the policy, so and instant impact is yet not visible.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] (Refer to Colom G) | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] (refer to Colom F) | Describe remedial action for residual impacts that will be taken. [7] (Refer to colom K)
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups |  |  | The risks identified that require safeguards are: a) vulnerable groups who cannot be involved in the use of forest products; b) women's groups who are not involved in the membership of the Social Forestry Group | 1) Identify vulnerable groups and vulnerable women's groups; 2) Identify women's groups; 3) Identify female family heads; 4) Identify groups of young women; 5) Establish home industry groups for vulnerable groups and women's groups; 6) Coordinate with the Social Forestry and Environmental Partnership Agency to provide greater opportunities to be involved in social forestry business groups; and 7) Conducting research related to the mainstreaming of women's gender in the implementation of social forestry. | a) Number of vulnerable groups who are direct beneficiaries b) Number of groups of women who are direct beneficiaries c) Number of women involved in social forestry enterprise groups d) A list of participants' attendance at every routine meeting in the village. e) Participation of participants in each meeting f) There is an increase in capacity related to climate change adaptation issues g) There is an increase in institutional capacity, both for forest farmer groups, home industry groups, and groups concerned with climate change. h) There is an increase in knowledge in producing forest food i) There is an increase in the economy from forest area management activities | There is no baseline condition for each monitoring indicator | During this PPR reporting period, a social assessment was conducted in 10 villages in the upstream area of the Saddang watershed, with the following information obtained: - There are 166 people belonging to vulnerable groups, and 19 women belonging to vulnerable groups. - There are 21 Social Forestry Business Groups (KUPS), mainly led by women - There are 7 women as heads of households - There is no special group for young women, but in KUPS there are 12 young women who are members. Social Forestry Business Groups (KUPS) are home industry groups focused on transforming forest resources into valuable products. There are 21 KUPS with a combined membership of 832 individuals, primarily led by women. These groups encompass members from vulnerable populations, including groups of vulnerable women. EE has actively engaged in coordinating and communicating with the Social Forestry and Environmental Partnership Agency (BPSKL) to promote the active participation of women and vulnerable groups in village-level social forestry development. Consequently, women have taken the lead in the social forestry business groups, and these groups have received official recognition in the form of a Social Forestry Business Group Decree from the relevant authorities, namely, the Social Forestry and Environmental Partnership Agency. Research on gender mainstreaming in social forestry management has been conducted, and the result has been a scientific article on injustice to women's groups in social forestry as well as a policy brief on gender mainstreaming policy in social forestry prepared in collaboration with academics from Hasanuddin University: 1) The scientific article was prepared by PMU KAPABEL as EE with the title "Injustice against Women in a Social Forestry Program: Case Studies from Two Indonesian Villages" and has been published in the Forest and Society Journal. 2) The policy brief has been prepared that highlights the inequality of women's involvement and access in social forestry management from a policy perspective. The policy brief has been disseminated to stakeholders (government, community, CSOs, and academics). | Vulnerable groups and women's groups have been registered as members of Social Forestry Business Groups (KUPS) that manage non-timber forest products in each management area. They are also included in capacity building activities such as socialization and training. | The remedial action has been taken is to conduct research and disseminate the research findings in form of research article and policy brief. The research findings aimed to mainstream the gender equality and justice in the design of social forestry policies and impelementation. In addition, gender mainstreaming aspects are also advocated in the policy-making. As a result, this issue has been internalized in one of the provincial government planning documents, namely in the Social Forestry Roadmap of South Sulawesi Province.
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | There is no. unanticipated ESP riks identified.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes, it is still relevant
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | KEMITRAAN required quarterly report and final project report being submitted by Executing Entity, and external evaluation report from independent third-party to monitor and evaluate the project implementation closely to comply with the required AF safeguard. Risk Mitigation Strategies by IE: - Monitoring and Review the process ESMP implementation - Set up the grievance mechanism at IE level - Disposal of grievances - Site visit monitoring - Sample check and verify ESMP in the project village
Have the implementation arrangements been effective during the reporting period? |  | Yes. By having 3 monthly (quarterly) reports, site visit monitoring and evaluation, final project report, and also external evaluation, IE could evaluate the project implementation thoroughly.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Executing Entity providing quarterly reports and final project report to Implementing Entity. Reports submitted to the Implementing Entity are made based on monthly reports made by each level in the PMU. Risk Mitigation Strategies by EE: - Identification of Environmental and Social Problems at the Project Site. Each month, PMU identifies of Environmental and Social problem and writes in to the monthly report. The expert of forest management and environmental and the expert of social and gender review the monthly document. - PMU coordinate with the experts if there is critical risk (case of Paku Village as example). - Public disclosure: Program designs and activity budgets are diseeminated to the public, specially to direct beneficaries in the intevention villages, both in oral and written form during meetings. The program design also has a dissemintation component. Dissemination activities are in the form of publications in report documents, inforgraphics, modules, books, and documentaries as well as information posted on websites. - Creation of grievance mechanism: Form complaint for grievance mechanism have been posted at the government offices of the assisted villages, the secretariat of the Forest Farmers Group, and in public places. The form complaint also posted on the website: https://adaptasi.tlkm.or.id/
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, by having the monthly report, various risks can be anticipated immediately and obstacles can be overcome immediately.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Yes, at the beginning of the project we said that if there were grievance, they could be made by filling out the grievance mechanism form. Grievance can be submitted to EE, if there is no response, we provide the contact of the Adaptation Fund secretariat on the document form, so that stakeholders can immediately submit their grievance. So far, we have handled grievance well.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
The Paku Village Head expressed dissatisfaction with a program or activity taking place in his village, particularly with the acquisition of porang seeds. Complaints are submitted to the FO, PO, PM, and PC through WhatsApp/Telephone. |  | The Paku Village Head expressed disappointment that the quantity of porang seeds delivered fell short of his expectations. His complaint was based on his intention to procure porang seeds, but it was denied due to the extremely high price and quantity supplied in comparison to the general market pricing. The porang seeds were supplied based on information from a co-worker, one of the Nasdem Party regional legislator's of Tana Toraja. This unhappiness persisted since the program's promised porang seed was delayed, which constituted a compelling reason for the head of the village to believe that the program would fail and so on. However, persuasive communication at the PMU level persists. Additionally, the Project Coordinator visited with the village head personally, gathered all necessary information, and described the project and its execution mechanism, particularly the acquisition of porang seedlings. The grievance has been kept confidential, since this could cause social unrest amongst the village community. Moreover, by making the grievance public, it could have been jeopardizing the communication between project and Paku Village Head that in turn could put the continuation of the project at risk. In the end, the head of Paku Village came to place their trust in this project after attending multiple district-level meetings, which featured a variety of stakeholders ranging from office heads to the Regent of Tana Toraja. As a result of these meetings, the village head came to believe that the project was a bona fide initiative directly supported by the local government, with particular support from the district head. So that in the end, we were able to secure the village head's support and participation in the project, and that it can be said that the complaints submitted can be resolved satisfactorily.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, it was
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, it is. For the project purposes, it is expected that 30% of women will be the direct beneficiaries of all activities. For otucome in Component 1 and 2, the direct beneficiaries of home industry activities are women and vulnerable gorups. For output in the upstream areaf of Saddang River, 30% women of the 250 direct beneficiaries have increased capacity in managing forest food. In the downtream area of Saddang River, 20% women of 175 of the direct beneficiaries have increased capacity in development of creative business.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Increased skills of Forest Farmer, Women and Vulnerable Group in managing sustainable forest food | Output 1.3.1. | 250 persons, including women, from 10 Social Forestry, women and vulnerable groups have increased capacity to manage sustainable forest food | 0 % women of 250 direct beneficaries. | 99 women of Forest farmers, women and vulnerable gorups of home industry | Satisfactory
Increased capacity of facilitators and local communities in Social Forestry scheme | Output 1.2.1. | 260 people have increased capacity to encourage social forestry | 0 % women of 260 direct beneficaries. | 7 women facilitators and 90 local women communities in Social Forestry | Satisfactory
Increased capacity of stakeholders in sustainable forest management | Output 1.2.2. | 50 people from POKJA PPS have increased capacity in sustainable forest management | 0 % women of 50 direct beneficaries. | 20 women | Good
Increased capacity and skills of KPPI and stakeholders in improving coastal governance and carrying capacity downstream of watershed | Output 2.1.2. | 75 people have increased skills in improving coastal governance and carrying capacity | 0 % women of 75 direct beneficaries. | 37 women | Satisfactory
Improving the skills of KPPI, women, and vulnerable groups in the development of creative businesses and food diversification | Output 2.2.1. | 175 persons, including women, have increased capacity in development of creative business | 0 % women of 75 direct beneficaries | 37 women of KPPI, 35 women and vulnerable gorups of home indusry | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Incorporate the topic of gender equity into the Roadmap for Accelerating Social Forestry, the provincial policy statement for social forestry. In light of this, consideration must be given to how many women are involved in social forestry initiatives, from pre-approval (group formation, discussion, and proposal document production) to post-approval (capacity building and business development). |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | KEMITRAAN required quarterly report being submitted by Executing Entity, to monitor project implementation closely to comply with the required AF safeguard.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. By having 3 monthly reports, IE could evaluate the project implementation thoroughly.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | To carry out identification of women's groups in each intevention village, women's roles in managing forest product sources, and women's opportunities in social forestry policies.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes it has been effective.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Yes, it has. There is a capacity gap that effects GP compliance, namely social forestry policies (Regulation of Ministry Environmental and Forestry, Number 9 Year 2021) that address to neutral gender which provides equal opportunities for men and women in the same family. So that in the implementation, because of social and culture construction, men are more dominant in terms of members of the social forestry group (Kelompok Perhutanan Sosial-KPS). This has an impact on the formation of the Social Forestry Business Group (Kelompok Usaha Perhutanan Sosial-KUPS) for women's group because KUPS members must be KPS members, according the regulation. In extablishing Home Industry as a Social Forestry Business Groups, the executing entity have coordinated with Social Forestry and Environmental Partnership Agency for Sulawesi Region so that the requirements for KUPS members could be taken from outside KPS members so that women could be involved in Sosial Forestry Program in business management.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There is No. grievace received gender-related matters.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1. Strengthening of Social Forestry in encouraging for forest food in the upstream of Saddang watershed |  | Outcome 5 | Social Forestry Permit Issuanced. Forest food based provided. |  | The permit is still under development with significant progress. The forest food based have been provided well. | S
| 2. Improved coastal governance and carrying capacity in support of climate change adaptation downstream of Saddang Watershed |  | Outcome 6 | Climate Change Care Group (KPPI) established and get skill and knowledge improvement. |  | KPPI established and actively run. | HS
| 3. Strengthened cross-cutting policies in ensuring the sustainability of climate change adaptation |  | Outcome 7 | Climate Change Adaptation Working Group Established and Improved. |  | The WG established by Provincila Govenrnment. The project is improving the WG capacity. | S
| 4. Strengthening of capacity and support of stakeholder through knowledge management |  | Outcome 3 | Program being disseminated, improve local EWS. |  | Program has been disseminted. Data and Information feeder application is under development. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dewi Rizki
| Email: | dewi.rizki@kemitraan.or.id
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Overall project has been conducted well with few changing in the type of species being implemented (that is having more economic value) and also the type of support given to the working group to strengthen and ensuring the sustainability of climate change adaptation. At the downstream level, the establishmnet of Climate Change Care Group (KPPI) has made a big change in the mindset of related stakeholders: local government, communities, students, youth group - on how to respond to the impact of climate change. While the social forestry permit is under progress, the forest food based have been provided and ready to be put in the market. The Head of Regent of Enrekang highly supported the development of forest food based. Regent regulation is being established to support the implementation of sustainable forest food based develompment. To strenghten cross-cutting policies to ensure the sustainability of climate change adaptation, the support to the existing Working Group to internalized adaptation plans to local government policies will be important. The EWS data and information feeder application needs to be effectively introduced and harmonized with the EWS at the sub-provincial and provincial levels.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1. Strengthening of Social Forestry in encouraging for forest food in the upstream of Saddang watershed |  | Outcome 5 | The farmers Group could have a Social Forestry permit to be able to manage their forest including forest food based. |  | 10 social forestry agreements reached with a total social forestry area of ​​more than 5,000 ha strengthened | S
| 2. Improved coastal governance and carrying capacity in support of climate change adaptation downstream of Saddang Watershed |  | Outcome 6 | Establish Climate Change Care Group (Kelompok Peduli Perubahan Iklim/KPPI) at local level. Improve KPPI's skills and knowledge. |  | KPPI Established. Together with communities established and conducted Mangrove nursery and planting. Capacity building on KPPI has been conducted. | S
| 3. Strengthened cross-cutting policies in ensuring the sustainability of climate change adaptation |  | Outcome 7 | Internalized Climate Change Adaptation Plans to Local Government policies and Low Carbon Development Working Group members increasing their capacity for climate change adaptation. |  | The project strengthening the capacity of the working group as well as improving Climate Change Adaptation Documents namely Roadmap for Social Forestry Accelaraation in Province level and Regencies level that internalize climate change adaptation issues. | S
| 4. Strengthening of capacity and support of stakeholder through knowledge management |  | Outcome 3 | Disseminated program to strengthen and encourage policies and alignments; Improve Existing early warning system platform for Climate Change Adaptation among Saddang Watershed Ecosystem Community. |  | The program has been disseminated to related multi-stakeholders through a film, a book, scientific articles, posters, billboards, and videos. The early warning system has been established namely Climate Smart Community platform that can be accessed via website (WebGIS) and mobile apps (iOS and android). | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | M. Gusti Zainal
| Email: | mgusti.zainal@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Component I, this component's activities have resulted in several outputs, including an increase in the capacity of facilitators and local communities to engage in social forestry (SF), an increase in the capacity of stakeholders to engage in sustainable forest management, an increase in the level of support from parties for accelerating social forestry, and an increase in the availability of facilities and infrastructure for managing forest food products. There were 5,606 beneficiaries, including 4,016 males and 1,590 females. There are 90 vulnerable individuals, 31 males, and 59 females. The customary group consists of 31 males. In October 2021, the plan for Social Forestry for Community Forest husks totaling 4,145.98 hectares was formally verified. The Ministry of Environment and Forestry has not yet released the technical verification results. In 10 intervention villages in the Upper Saddang watershed, 18 forest food seed homes were created. Farmers are now involved in tasks such as operating nurseries and nurturing seedlings for planting in January–February 2022. Component II, The component's activities resulted in several outputs, including the establishment of the Climate Change Care Group (Kelompok Peduli Perubahan Iklim-KPPI) as a driving force at the village and sub-district levels, the development of the capacity and skills of KPPI members and stakeholders to increase the Saddang watershed's coastal carrying capacity and downstream carrying capacity, and the rehabilitation of coastal areas downstream of the Saddang watershed along 1.4 kilometers with a total of 25,000 seeds and propagation. In component III, activities were delayed for many months while the Directorate General of Climate Change Recognition (Dirjen PPI) approved adjustments to the output of the proposal document as described in the Inception Report. Nevertheless, the core activity has been carried out in this component, namely the Assessment of VUlnerability and Climate Change Risk in the Saddang Watershed as one of the guiding documents in the preparation of government strategic plans at the provincial and district levels. And COmponent IV, activites resulted in output, namely the distribution of programs that support and encourate police and alignments via seven inforgraphics, one poster, and one website. Menawhile, documentary films are beind edited, scientific articles are beind reviewed, and lessone learned/best practice books are being written. Currently, the activity of building an application for disaster response Early Warning System is running as a legacy program for community and government.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1. | 5,000 ha of forest area using social forestry scheme (proposal/IUP/scheme strengthening) 5,000 ha of land are planned for rehabilitation in the Saddang watershed area through Social Forestry | 0 | 5.291 ha social forestry reinforced | 5.291 ha
Output 1.1.1. | 5.000 ha area from 10 Social Forestry Permit obtaining Legal Access/ Reinforcement | 0 | 5.291 ha of social forestry reinforced: - 3,590 ha of social forestry area with a new approval, and strengthens the institutional and business management - 1.701 ha of social forestry area which strengthens the institutional and business management | 5.291 ha
Output 1.1.2. | 60 ha of land rehabilitated / planted from nurseries | 0 | 61 ha | 60 ha of land rehabilitated / planted from nurseries
Output 1.1.2. | 70% of seedlings grown from cultivation | 0 | 71% | 70%
Outcome 1.2. | 10 Institutions/Groups in the Social Forestry Scheme are formed and increase their capacity to support climate change adaptation | 0 | 18 Forest Farmer Group (Kelompok Tani Hutan/KTH) and 10 Forest Farmer Group Association (Gabungan Kelompok Tani Hutan/Gapoktanhut) are formed | 18 Forest Farmer Group 10 Forest Farmer Group Association
Outcome 1.2. | 3 proposing and planning Social Forestry prioritized in vulnerable areas affected by climate change | 0 | 10 social forestry agreements have been issued and a Social Forestry Management Plan has been developed which includes climate change adaptation issues | 10 social forestry permit
Output 1.2.1. | 260 persons have increased capacity to encourage social forestry | 0 | 1.025 persons. This cumulative accomplishment is the sum of all training activities, regular discussions, and study tours conducted by PMU and local communities (Forest Farmers and Home Industry groups). | 1.000 persons
Output 1.2.2. | 50 members of POKJA PPS have increased capacity in sustainable forest management | 0 | 64 persons (Male: 55, Female 9). The aim was accomplished through a series of initiatives, including (1) the preparation of the Roadmap of Social Forestry Acceleration; (2) the Socialization of Social Forestry; and (3) initiate the forming of Social Forestry Acceleration Working Group (POKJA PPS) in Regency level. | 50 persons
Output 1.2.3. | 1 MoU on Social Forestry Acceleration | 0 | 1 MoU on program assistance and development for climate change adaptation in South Sulawesi. By the Provincial Government, KEMITRAAN (Partnership), and TLKM | 1 MoU
Outcome 1.3. | Sold 2 types of food products from the social forestry group Improve value added by 30% from selling 2 kind of forest food products (honey and palm sugar) | 0 | 4 types of forest food products are sold namely honey, palm sugar, coffee, and sikapa (local tubers) Honey products improves added value by 50%, palm sugar products improves added value by 75% | 75 % of each 2 kind of food production are sold 30% improved added value
Output 1.3.1. | 250 persons from 10 Social Forestry, women and vulnerable groups have increased capacity to manage sustainable forest food | 0 | 1.235 persons: 1.008 of farmer groups and 227 home industry groups that includes women and vulnerable people have been enhanced through a variety of activities, including machine and equipment operation training, innovative business training, and institutional training. | 250 persons
Output 1.3.2. | 10 units of forest food processing facilities | 0 | 14 units for home industries | 10 units
Output 1.3.3. | 75 % of each 2 kind of food production are sold | 0 | 100% sold | 75%
Outcome 2.1. | 75 people have increased capacity | 0 | 100 Climate Change Care Group (Kelompok Peduli Perubahan Iklim/KPPI) members in total improve the capability as the result of training accumulated over the activity process. | 100 persons
Outcome 2.1. | 1.2 km of land and coastal areas are rehabilitated | 0 | Along 1.4 kilometers land on downstream watershed and coastal were planted by 25,000 mangrove seedlings and propagules. This accomplishment well exceeded the objective. | 1,4 km with 25.000 mangrove seedings.
Output 2.1.1. | 5 KPPIs are established and running (Kelompok Peduli Perubahan Iklim) | 0 | 5 Climate Change Care Group (Kelompok Peduli Perubahan Iklim/KPPI) have been established and running well | 5 KPPI
Output 2.1.2. | 75 persons have increased skills in improving coastal governance and carrying capacity | 0 | 100 persons. The improvement in capability of KPPI members is the result of training accumulated over the activity process. | 100 persons
Output 2.1.3. | 1.2 km coastal land is rehabilitated | 0 | Along 1.4 kilometers, 25,000 mangrove seedlings and propagules were planted. This accomplishment well exceeded the objective. | 1,4 km with 25.000 mangrove seedings.
Outcome 2.2. | 100 people have increased income from creative businesses and food diversification | 0 | 100 persons women and vulnerable groups | 100 persons
Output 2.2.1. | 175 people have increased capacity in development of creative business and food diversification | 0 | 200 persons. 100 persons are KPPI members, and 100 persons are from Home Industry Groups including women and vulnerable. | 175 persons
Output 2.2.2. | 5 units of household-scale processing tools used in creative business and food diversification | 0 | 5 (five) home-based industry have been established. Each intervention village is self-sufficient in a single industry. | 5 units of home industry
Output 2.2.3. | 2 marketing networks for creative business and food diversification | 0 | 3 marketing networks, there are MoU to ensure the marketing of products | 2
Output 2.2.3. | 75% of each 2-production sold | 0 | 95% | 75%
Outcome 3.1. | 3 policy products that support climate change adaptation | 0 | 3 document policy products that includes the climate change adaptation issues: (1) Social Forestry Roadmap of South Sulawesi Province (2) Social Forestry Roadmap of Tana Toraja Regency (3) Social Forestry Roadmap of Toarja Utara Regency | 3 policy products
Output 3.1.1. | 40 members of PKRD increase their capacity on Drafting Adaptation Climate Change Plan | 0 | 43 members of South Sulawesi Regional Low Carbon Development Working Group (POKJA PRKD Sulsel) through regular meeting and workplan preparation meeting. | 40
Output 3.1.2. | 2 regional planning documents that have RAN API internalized within | 0 | 3 document policy products that includes the climate change adaptation issues: (1) Social Forestry Roadmap of South Sulawesi Province (2) Social Forestry Roadmap of Tana Toraja Regency (3) Social Forestry Roadmap of Toarja Utara Regency | 2 documents
Output 3.1.3. | 1 adaptation monitoring application system used in supporting the implementation of the policy | 0 | 1 apps for climate change adaptation program monitoring in South Sulawesi namely "LONTARA" apps | 1 adaptation montoring applicationa system used.
Outcome 4.1. | 27,143 people received information from the dissemination process | 0 | 33.853 people received information from project dissemination. Derived using data from the Bureau Central Statistics (2022) regarding the total population in all intervention villages and added with social media audiences and other recipients during the dissemination phase. | 27,143 people
Outcome 4.1. | 47 key actors who use and utilize information and knowledge for resilience to climate change | 0 | 107 people as key actors that using and utilize the information and knowledge of climate change adaptation through the Climate Smart Community initiative (socializations, workshop and training) | 47 key actors
Output 4.1.1. | 1 film 1 lesson learned/best practice book 1 journal 1 poster 1 digital media 1 infographic | 0 | - 1 documentary film - 1 lesson learned book - 5 research articles, 1 article is published in an international journal namely Journal Forest and Society (Scopus Rank Q2) - 9 posters - 4 digital media (1 website, 2 social media, 1 video stream platform) - 8 infographics | 1 film documenter 1 book 1 journal (7 articles of science) 1 digital media 7 infographic 1 poster
Output 4.1.2. | 1 early warning system platform | 0 | 1 early warning system platform namely Climate Smart Community apps. This apps can be accessed via WebGIS and mobile apps (iOS and Android) | 1 platform

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | To construct people's thinking in adapting to climate change, requires intensive assistance with a longer time. In principle, people can understand how the impacts of climate change and environmental dynamics impact their livelihoods. But before further awakening the public to be more aware of the environment, we as community developers need to ensure that people's livelihoods can be guaranteed.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There are some delay in implementation of activities. 1) Delay in establishing a forest farmer group (KTH) in Lemabng Randan Batu, South Makale Sub-DIstrict, Tana Toraja Regency because the administrative boundaries of the Lembang Randan Batu administration area are not yet known by the village government and the community. There is a hamlet of Lembang Randan Batu in forest area inhabited by different residents of village and sub-district, Lembang Perindingan, Gandangbatu Silangan sub-District. Executing Entity coordinated with the two village governments, the two sub-district government and the district government. As the reuslt, residents of Lembang Perindingan who live in the forest area in the viillage area of Randan Batu have to be members of the social forestry group so that this took time for administrative arrangements in both villages and sub-districts. The Proposal for Social Frestry Management Permit was carried out by the Association of Forest Farmers at the Regency level whish was signed by the head of Tana Toraja Regency. 2) Delay of procurement of Porang seeds for 3 months. Commodity changes in the proposal from Japanese Talas to Porang must obtain approval from Adaptation Fund Board and NDA, Directorat Genderal of Climate Change Control. The steps taken were submitting notes, approval from the Regional Research and Development Planning Agency and finally pushing to the NDE. 3) Delay the Technical Verification of the Social Forestry Permit Proposal. Ministry of Environmental and Forestry cut off all the Social Forestry Permit Proposal since April to June, 2021. Ministry of Environment and Forestry was still waiting the new regulation on Social Forest Management. It has an impact on the schedule for implementing technical verification in the location by Social Forestry and Environmental Parthenrship Agency. 4) Delay of activities related Working Group of Low Carbon Development. Board AF asks to temporarily stop all activities in the changed output until it gets approval from the NDE. Change in ouput: establishment and operation of Climate Change Adaptation Working Group (POKJA-API) to Strengthening the Regional Low Carbon Development Working Group (POKJA PRK). Prior to the project/program run in October 2020, the provincial goverment of South Sulawesi has established Working Group of Low Carbon Development. So that the output of the establishmen of the Working Group of Climate Change Adaptation is no longer relevant. all activities rekated ti this output are delayed to implement for four months because the approval of the NDE on output change completed in September. The Executing entity increase capacity builiding on adaptation issues to members of PRK and internalizes adaptation action in the program of PRK.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The changes on the Inception Report are in Output 1.1.1. where the project proposal states that the Social Forestry scheme is only limited to the Village Forest (HD) / Community Forest (HKm) scheme. In the Inception Report, the proposed Social Forestry scheme is no longer limited to that two Social Forestry schemes but opens up opportunities for other Social Forestry schemes. Then related to the type of tubers to be planted, in addition to taro plants, other tubers will be added, namely uwi/sikapa and porang. Furthermore, changes in Output 3.1.1. what previously was “Formation and Operation of the Climate Change Adaptation Working Group (POKJA-API)” was changed to “Strengthening the Regional Low Carbon Development Working Group Team (POKJA-PPRKD)”. This change in output also affects the change in indicators where previously the output indicator was "One (1) Decree of POKJA-API in the South Sulawesi region" to "40 members of the POKJA-PPRKD Team to increase their capacity in preparing climate change adaptation plans". Another change is the PMU structure where four Field Officer positions will be replaced into one Administration position, one Content Dissemination Officer position, and two Field Officer of Dissemination positions.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, it is effective in avoiding unwanted negative impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Women have a role in processing agricultural products so this is an important consideration in designing non-timber forest products througt the Social Forestry Businsess Groups. Some important lessons in the implementation program, namely:The results of scientific article research show that women are the group most at risk for the impact of climate change because women have social, cultural, and economic vulnerable due to existting socual constructions. Women also have physiological and biological vulnerabilities so that implementing entities will make a policy brief on gender mainstreaming in the environment and forestry sector, especially in the design of social forestry regulation.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | (1) Encouraging agroforestry patterns in the management and utilization of forests and land with the main crop of Multipurpose Trees with the aim of increasing environmental sustainability, increasing community income, and food security. Beneficiaries of village communities who are members of the Social Forestry Group and Social Forestry Business Group as a model for sustainable forest management. (2) Encourage the formation of working groups on Social Forestry at the district level that are responsive to climate change. In Indonesia, the Social Forestry Working Group exists only at the provincial level, thereby encouraging collaboration between stakeholders at the district and site levels. Various problems of people living in forest areas such as tenure conflicts, poverty, lack of access, and so on require the involvement of stakeholders at the district level. This initiation departs from the results of discussions between the parties at the beginning of the program running in January 2021 when discussing the work program of the South Sulawesi Province Social Forestry Working Group. (3) Promote joint policies in Integrated Watershed Management that are connected to the conditions and interests of the upstream and downstream watershed areas. Policy encouragement for climate change adaptation actions through the Assessment of Vulnerability and Climate Change Risk in the Saddang Watershed as a reference document plan in making strategies both at the provincial and district levels.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | (1) Internalization of program related to climate change adaptataion and mitigation into the Social Forestry Workplan of Permit Holders such as encouraging the development of forest food crops both for planting on community land and in rehabilitation activities in critical lands. (2) In the cultivation of the community's main commodities, the selection of seeds must be adaptive to climate change.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | Lessons learned from the preparation of future concrete adaptation projects, namely building knowledge and conception with the government and the community about climate change issues in designing future concrete adaptation projects. In the early stages of implementation, it is better to carry out studies in obtaining data and information in building knowledge. One of the strategic steps in project implementation is to disseminate information related to the results of the study to stakeholders at the provincial, district, village and community levels of government. So that the implementation of the project received strong support in producing policies related to climate change adaptation. The implementation of a concrete adaptation project takes a longer time, at least 3 years, because adaptation actions are associated with a better and deeper level of understanding among all parties.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | It is very helpful in project/programme implementation.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The positive lessons learned to the preparation and design of real adaptation projects/programs in the future are: (1) The project proposal should have carried out the studies related to program implementation so that field activities run well without waiting for the studies to be carried out in the implementation period. (2) There should be a policy analysis study related to the program/project in the proposal so that interventions are designed and carried out based on the recommendations of the policy review results.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential for the concrete adaptation intervention undertaken by the project/programme: (1) The design of the leveled project management unit according to the needs of science. Field Officers at the village level carry out activities by collecting data and facts, Program Officers at the district level analyze field data and facts to produce information, and program managers at the regional level (upstream and downstream of the watershed) analyze information to generate knowledge. the Project Coordinator manages knowledge to encourage policies in obtaining support for climate change adaptation programs. (2) To establish working groups of Social Forestry at the regency level whose members are stakeholders from different agencies so that communication in forest management and utilization could be well integrated and comprehensive. To Encourage the development of forest food crops as a food security program.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Capaciity building for non-timber forest product management and Legal access in the multi-use of forest resources by Social Forestry.
What measures are/have been put in place to ensure sustainability of the project/program results? | To ensure the sustainability of project/program results is the internalization of adaptation programs in relevant agencies at the provinsial level, district, and village levels: (1) Farmers who are members of social forestry groups, women and vulnerable gorups who are members of the home industry as social forestry business groups already have the capacity and their institutions registered with district and village goverments so that they can collaborate on adaptation programs including livelihood. (2) To Establish Working Group of Social Forestry at the District Level involving the relevant institutional government which will later ensure the sustainability of the program. The working group has a Roadmap as a reference for the five years whise main points are in facilitationg legal access activities, post-permit assistance, and product development. In addition, the Roadmap is oriented towards adaptation and mitigation to climate change.
What measures are being/could have been put in place to improve project/program results? | Actions that are being taken to improve project/rpogram results: (1) disseminate knowledge of project/program results; (2) conduct advocacy on the importance of forest food-based cclimate change adaptation; (3) To strengthen gorup capacity both in the management and utilization fo social forestry, facilitationg communication of the need of Social Forestry Group and Social Forestry Business Group to the related institutional government regarding the obstacles or problems faced, as well as conductiong a series of studies for market certainly for forest food products.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Data/Information knowledge has been analyzed to use in many activities such as workshops, dissemination, writing report, social media, and audiovisual. Data/information knowledge used are: (1) Monthly Technical Progress Report; (2) Quartal Technical Progress Report; (3) Report on the level of community vulnerability and risk of climate change in the Saddang Watershed; (4) Land Suitability Study Report; (5) Report on Market Study of Porang, Taro, Gadung, and Uwi Commodities; (6) Report on Supply and Value Chain of Forest Food Products (Coffee, honey, candlenut, sikapa/local tubers and palm sugar); (6) Basic and Middle Survey Monev; (7) Forest food cultivation module; (8) Mangrove Nursery Module; (9) Technical design document for mangrove planting; and (10) Report of Pond Study.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Information/data/knowledge can be accessed via the website http://adaptasi.tlkm.or.id, and other dissemination products such as book, film, learning modules, and scientific articles. Stakeholders can submit requests for data or information to the TLKM Foundation (KAPABEL consortium leader), which is in charge of knowledge management. The climate information system has been established to provide the knowledge about climate change adaptation that can be used by local and regional stakeholders (include the communities as the direct beneficiaries)
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | (1) Report on Market Study of Porang, Taro, Gadung, and Uwi Commodities; (2) Report on Supply and Value Chain of Forest Food Products (Coffee, honey, candlenut, sikapa/local tubers and palm sugar); (3) Basic and Middle Survey Monev; (4) Forest food cultivation module; (5) Mangrove Nursery Module; (6) Technical design document for mangrove planting; and (7) Report of Pond Study.
If learning objectives have been established, have they been met? Please describe. | The learning objectives of this project are: 1) integrating adaptation issues across sectors at the provincial, district, and village levels of government; 2) managing forest areas based on forest food in preserving the environment, improving the economy, and food security; 3) encourage the mainstreaming of women's gender in the implementation of social forestry; and 4) building youth organizations that focus on environmental issues. In the one-year process of this project, the first lesson in integrating adaptation issues across sectors encountered problems because forestry issues were handled by the government at the provincial level, so EE encouraged the formation of a social forestry working group at the district level. The second lesson is still in the process of proposing a management permit so the learning objectives are not yet. The third lesson is in the effort to form a social forestry business group. The lessons learned in encouraging the mainstreaming of women's gender are the constraints to the design of social forestry policies. In the design of the policy, the mainstreaming of women's gender is not yet strong so the dominance of men in the formation of social forestry groups is still dominant. Forest stereotypes are a male domain that is still strong both in the government and in society. So that one of the policy brief points that will be encouraged in this project is the mainstreaming of women's gender in the implementation of social forestry through affirmative policies. The fourth lesson, the formation of a Climate Change Care Group consisting of young people in Pinrang Regency, downstream of the Saddang watershed, provides positive values because the environmental spirit of the younger generation develops in the village both in terms of advocacy and socialization.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Data collection through relevant stakeholders was challenging at the start of the project period. Due to the project implementers' lack of interest, the institutional setting has not yet developed a relationship of trust. When the project runs, EE establishes strong coordination and communication while the project is in progress to make data and information more available. Finally, stakeholders were brought together to create an information system for exchanging data on climate change, using the LONTARA application for program data and the Climate Smart Community for microclimate data. This application has to be improved before it can be used more effectively and offer wider benefits.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The identification of project learning objectives contributes to accelerating and strengthening climate change adaptation actions through Working Group for Social Forestry Acceleration in South Sulawesi through strengthening the Working Group for the Social Forestry Acceleration at both the provincial and district levels. In the work program of Social Forestry Schemes, the project drive issues of forest food-based management, gender mainstreaming issues, and cross-sectoral integration at the government level. These three learning targets are project outputs. These three aspects have not received attention in the previous period's work program of social forestry schemes.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | (1) This project develops an information system and monitoring of climate change adaptation programs in South Sulawesi, namely LONTARA apps. This application allows users to access data and information regarding climate change adaptation programs in South Sulawesi so that later if there is an idea the program will not overlap with other programs. (2) Developing a technology-based early warning system through the Climate Smart Community apps. This application allows people to share data, information and knowledge about the climate in their area. This application is integrated with intelligence weather stations (can receive climate data via sensors, send it to the server, and using algorithms can provide information that is easily understood by regular users).
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | Yes, after the project ends in July 2022, several initiatives resulting from this project have been emerged, including by obtaining climate finance support via Adaptation Fund funding through the Innovation Small Grant, as well as from other Funds/Organizations.
If you answered yes above, kindly specify the name of the Fund/Organization. | - Adaptation Fund Small Grant Innovation: The initial AF Small Grant Innovation project proposal is to ehnance the Climate Smart Community system. Then the second AF Small Grant Innovation project proposal is the idea of developing adaptive coffee plants and developing alternative livelihood sources through ecotourism based on Social Forestry. These ideas represent the scale-up ideas from the Adaptation Fund Small-Sized project that has been carried out previously. Both project proposals have been accepted by the AF Board and will be implemented soon. - The Asia Foundation: Initiatives in strengthening social forestry were developed after the Adaptation Fund project ended. These initiatives are related but do not overlap with the outcome of the previous Adaptation Fund project. One of the initiatives in encouraging Social Forestry to be more developed at the District level is encouraging the Integrated Area Development based on Social Forestry policy in Enrekang District.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | KEMITRAAN
Type of implementing entity | NIE
Country | Indonesia
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 27674 | 531 | 27143 | Total | 5206 | 1327 | 3879 | Total | 34804 | 1649 | 33155
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 60% | 30% | 30% | % of female beneficiaries | 34% | 4% | 30% | % of female beneficiaries | 65.15% | 16% | 49.15%
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 10% | 5% | % of Youth beneficiaries | 18% | 8% | 10% | % of Youth beneficiaries | 17% | 7% | 10%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 27143 | Inland flooding | 5: Very effective | Total | 1247 | Inland flooding | 2: Partially effective | Total | 34645 | Inland flooding | 5: Very effective
|  | % of female targeted |  |  |  | % of female targeted | 30% |  |  | % of female targeted | 39.34% |  |  | % of female targeted | 48.76%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Regional | 1: No plans conducted or updated | 1 | Multi-sector | Regional | 2: Undertaking or updating of assessments in progress | 0 |  |  |  | 1 | Multi-sector | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 4 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 4
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 6 | 3: Dissemination and communication | Geographical coverage | Regional | 3 | 3: Dissemination and communication | Geographical coverage | Regional | 7 | 3: Dissemination and communication | Geographical coverage | Regional
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 4 |  |  | Number of municipalities | 4 |  |  | Number of municipalities | 4
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 40 | Multi-sector | 4: High capacity | Total | 35 | Multi-sector | 3: Medium capacity | Total | 43 | Multi-sector | 3: Medium capacity
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted | 37.14% |  |  | % of female targeted | 51.16%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 40 | 30% | Public |  | 35 | 37.14% | Public |  | 43 | 51.16% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 4: High capacity | Public | Local | Multi-sector | 4: High capacity | Public | Local | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Forests | 3: Medium capacity | 2 | National | Forests | 4: High capacity | 0 | National | Forests | 1: No capacity | 2 | National | Multi-sector | 3: Medium capacity
|  | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | Local | Multi-sector | 3: Medium capacity | 40 | Local | Multi-sector | 4: High capacity | 47 | Local | Multi-sector | 3: Medium capacity | 47 | Local | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100% |  | Multi-sector |  | 4.889% |  | Multi-sector |  | 122.1% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 27143 | 30% | 4: Mostly aware |  | 1327 | 11% | 2: Partially not aware |  | 33155 | 49.15% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 3 | 20% to 39% | 4: Mostly aware |  | 3 | 20% to 39% | 2: Partially not aware |  | 3 | 20% to 39% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | Local |  | 1 | Training manuals | Local |  | 1 | Training manuals | Local |  | 1 | Training manuals | Local
|  | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | handbooks | National |  | 1 | Handbooks | National |  | 0 | Handbooks | National |  | 1 | Handbooks | National
|  | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Regional |  | 1 | Technical guidelines | Regional |  | 4 | Technical guidelines | Regional |  | 6 | Technical guidelines | Regional
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha protected | 2: Partially effective | Forests | 5000 | ha protected | 2: Partially effective | Forests | 0 | ha protected | 2: Partially effective | Forests | 0 | ha protected | ha protected
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves |  | km protected | 2: Partially effective | Mangroves | 1.2 | km rehabilitated | 3: Moderately effective | Mangroves | 1.4 | km rehabilitated | 2: Partially effective | Mangroves | 1.4 | km rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 200 | 27% | 2: Limited improvement |  | 1227 | 16% | 4: High improvement |  | 1235 | 30% | 4: High improvement
|  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 100 | 27% | 2: Limited improvement |  | 100 | 35% | 4: High improvement |  | 100 | 35% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Human capital | Agriculture | Community-based adaptation | 10 | Human capital | Agriculture | Community-based adaptation | 34 | Human capital | Agriculture | Community-based adaptation | 18 | Human capital | Agriculture | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | 0 | Forestry |  | 0 | 225 | Forestry |  |  | 1227 | Agricultural-related |  | 0 | 1235 | Agricultural-related |  | 0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | 0 | other |  | 0 | 100 | Aquaculture |  |  | 100 | other |  | 0 | 100 | other |  | 0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most |  |  |  | 3: Some |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Regional | Other policy | 3 | Multi-sector | Regional | Other policy | 1 | Multi-sector | Regional | Other policy | 1 | Multi-sector | Regional | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Disaster risk reduction | Subnational | Innovation accelerated |  | Disaster risk reduction | Sub-national | Innovation accelerated |  | Disaster risk reduction | Sub-national | Innovation accelerated |  | Disaster risk reduction | Sub-national | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Disaster risk reduction | No innovative practices | 2: Partially effective | 2 | Disaster risk reduction | Completed innovation practices | 4: Effective | 2 | Disaster risk reduction | No innovative practices | 2: Partially effective | 2 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness