## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | July 2021 - June 2022
| Project Title: | Safekeeping-Surviving-Sustaining towards Resilience: 3S Approach to Build Coastal City Resilience to Climate Change Impacts and Natural Disasters in Pekalongan City, Central Java Province
Resilience: 3S Approach to Build Coastal
City Resilience to Climate Change Impacts
and Natural Disasters in Pekalongan City,
Central Java Province
| Project Summary: | Adaptation measures taken in Pekalongan City to address climate change issue. This programme focus on building resilience to climate change impacts in Pekalongan City, one of the coastal cities in Central Java Province (in North Coast of Java region), by conducting interventions in the form of not only hard structure but also soft structure. This approach will be implemented at 4 governance levels; starting from community (kelurahan) level, city level, provincial level up to the national level. Capacity building and developing adaptation plan as well as implementing the corresponding plan will be the fundamental of the approach. Meanwhile at provincial and national level, mainstreaming and advocacy will be the primary component. Climate risk assessment process will be done at Pekalongan City utilizing Vulnerability Index Data Information System (Sistem Informasi Data Indeks Kerentanan/SIDIK), a vulnerability assessment tool developed by the Ministry of Environment and Forestry. SIDIK is a web-based data and information system that can be used to assess the vulnerability level of an area and/or sector to climate change impact. SIDIK has a standardized data and methodology which enable the user to compare vulnerability level across different areas in Indonesia. For the purpose of this programme, given that the system is initially built for land-based region, adjustment will be made to SIDIK. Furthermore, a Participatory Climate Risk Assessment will also be applied. The initial step of the programme will be establishing community working groups delivering some series of trainings to build their knowledge on climate change adaptation and coastal resilience. Seeing these risks faced by the area, resilience building process in this proposed programme will be focusing its work in strengthening food security, enhancing community livelihood while simultaneously preserving the environment. Overall, the target communities within the municipality of Pekalongan City consist of Pekalongan Utara constitutes of 7 kelurahan (an administrative area similar to Kampongs); there are kelurahan Degayu, kelurahan Krapyak, kelurahan Panjang Wetan, kelurahan Panjang Baru, kelurahan Kandang Panjang, kelurahan Padukuhan Kraton and kelurahan Bandengan. This programme will also include kelurahan Pasirkraton Kramat Kampong in Pekalongan Barat Sub-district that assessed as prone to coastal flooding.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IDN/NIE/Multi/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Kemitraan (The Partnership for Governance Reform) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | INDONESIA | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The City of Pekalongan comprises of 4 sub-districts with a total administrative area of 45.25 km2 and a total population of 296,533 people, where 31.3% of the population lives in Pekalongan Barat subdistric. Geographically, the city is located in lowland plain with an average height of 1 m above sea level (a.s.l) and highest point within the city at 6.5 m a.s.l. Seven rivers flow through the city and disembogue into the Java Sea, with Pekalongan River as the main river. There are several rivers that often overflow during high intensity rain event. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-09-23
IE-AFB Agreement Signature Date: |  | 2020-12-20 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2022-07-15 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2023-01-15
| Original Completion Date: | 2024-07-15
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.kemitraan.or.id/program-tiap-provinsi/adaptation-fund-project-pekalongan | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dewi Rizki | Dominican Republic
| Email: | dewi.rizki@kemitraan.or.id | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ir. Laksmi Dhewanthi, M.A. | Equatoral Guinea
| Email: | ldhewanthi@menlhk.go.id | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laode M. Syarif, PhD | Fiji
| Email: | laode.syarif@kemitraan.or.id | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Andi Kiky | Georgia
| Email: | andi.kiki@kemitraan.or.id | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 July 2022] | 314052.8457 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Uncommitted figures not yet disbursed to date = USD 5.615.170 (exclude budget audit in PEC ) |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1. Establishment of 6 kilometres of Mangrove Ecosystem | 588.6317
| Output 1.1.2. Construction of 300 m parapet at Slamaran Beach in kelurahan Degayu | 18622.6111
| Output 1.1.3. Coastal embankment (geo-tube/sand trap) at Kandang Panjang | 10073.8429
| Output 2.1.1. Pekalongan City Climate Working Group reactivatedOy | 18500.2125
| Output 2.1.2. Climate working group established and functioning in each of the 8 target kelurahan | 3072.0713
| Output 2.1.3. Enhancing coastal community capacity in developing kelurahan’s information system and implementing the ensuing climate change adaptation actions | 1199.4638
| Output 2.1.4. Engaging youth groups and building their capacity to become Agents of Change in climate change adaptation actions of Pekalongan City | 81770.8784
| Output 2.2.1. RAD API developed based on Pekalongan City Climate Risk Assessment and Climate Coastal Impact | 3023.632
| Output 2.2.2. Strategy to integrate CCA into local government planning processes (annual work plan or mid-term development plan of city) is developed | 0
| Output 2.3.1. Innovative and collaboration adaptation actions are implemented in collaboration with private sector, Government bodies and NGO ( i.e. technology for main productive sectors, model on collaborative CCA programme across coastal villages/ upstream and downstream villages); and also evaluated for future reference | 0
| Output 2.4.1. Climate change training and knowledge sharing conducted | 0
| Output 2.4.2. Knowledge product, Advocacy materials (i.e. lessons learned, research paper, newsletter) published and shared | 0
| Output 2.4.3. Local knowledge sharing platform established | 1016.0164
| Output 3.1.1. Enhanced provincial capacity to develop RAD API | 0
| Output 3.1.2. Appropriate strategy to integrate CCA into Provincial government planning processes (annual work plan or mid-term development plan of city) is developed | 0
| Output 4.1.1. Knowledge product in the form Handbook on how to use SIDIK for risk assessment at coastal city is published and shared. This handbook is targeted to be used by local government, NGOs and civil society organizations | 126.1554
| Output 4.1.2. Strengthened vertical coordination and collaboration between national and local government in climate adaptation context | 4866.6471
| Output 5.1.1. Aquafarming in mangrove ecosystem developed and implemented by community | 0
| Output 5.1.2. Mangrove ecotourism improved and involving wider participation of affected coastal community of Pekalongan City | 4922.2043
| Output 5.1.3. Improved cultural economy through application of ecological batik using mangrove based colouring product | 0
| Output 5.1.4. Improved food security through the application of urban farming as alternative to conventional agriculture practices | 173.6422
| Output 5.1.5. Developed circular economy through initiation integrated waste management system and processing | 430.9768
| Output 5.1.6. Improve sanitation and clean water facility in 8 targets Kelurahan to mitigate risk of waterborne diseases | 53597.6147
| A. Project/Program Excecution Cost | 107568.5627
| B. Project Cycle Managemet Services | 4499.6825
| TOTAL | 314052.8457 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1. Establishment of 6 kilometres of Mangrove Ecosystem | 27189.1461 | July 2023
| Output 1.1.2. Construction of 300 m parapet at Slamaran Beach in kelurahan Degayu | 486377.3889 | July 2023
| Output 1.1.3. Coastal embankment (geo-tube/sand trap) at Kandang Panjang | 454258.4071 | July 2023
| Output 2.1.1. Pekalongan City Climate Working Group reactivatedOy | 43722.0097 | July 2023
| Output 2.1.2. Climate working group established and functioning in each of the 8 target kelurahan | 92187.188 | July 2023
| Output 2.1.3. Enhancing coastal community capacity in developing kelurahan’s information system and implementing the ensuing climate change adaptation actions | 15837.5733 | July 2023
| Output 2.1.4. Engaging youth groups and building their capacity to become Agents of Change in climate change adaptation actions of Pekalongan City | 86006.8993 | July 2023
| Output 2.2.1. RAD API developed based on Pekalongan City Climate Risk Assessment and Climate Coastal Impact | 20865.2569 | July 2023
| Output 2.2.2. Strategy to integrate CCA into local government planning processes (annual work plan or mid-term development plan of city) is developed | 51777.7778 | July 2023
| Output 2.3.1. Innovative and collaboration adaptation actions are implemented in collaboration with private sector, Government bodies and NGO ( i.e. technology for main productive sectors, model on collaborative CCA programme across coastal villages/ upstream and downstream villages); and also evaluated for future reference | 22962.963 | July 2023
| Output 2.4.1. Climate change training and knowledge sharing conducted | 38888.8889 | July 2023
| Output 2.4.2. Knowledge product, Advocacy materials (i.e. lessons learned, research paper, newsletter) published and shared | 27777.7778 | July 2023
| Output 2.4.3. Local knowledge sharing platform established | 60983.9836 | July 2023
| Output 3.1.1. Enhanced provincial capacity to develop RAD API | 35185.1852 | July 2023
| Output 3.1.2. Appropriate strategy to integrate CCA into Provincial government planning processes (annual work plan or mid-term development plan of city) is developed | 23333.3333 | July 2023
| Output 4.1.1. Knowledge product in the form Handbook on how to use SIDIK for risk assessment at coastal city is published and shared. This handbook is targeted to be used by local government, NGOs and civil society organizations | 69133.1039 | July 2023
| Output 4.1.2. Strengthened vertical coordination and collaboration between national and local government in climate adaptation context | 38651.8714 | July 2023
| Output 5.1.1. Aquafarming in mangrove ecosystem developed and implemented by community | 330666.6667 | July 2023
| Output 5.1.2. Mangrove ecotourism improved and involving wider participation of affected coastal community of Pekalongan City | 246198.092 | July 2023
| Output 5.1.3. Improved cultural economy through application of ecological batik using mangrove based colouring product | 111481.4815 | July 2023
| Output 5.1.4. Improved food security through the application of urban farming as alternative to conventional agriculture practices | 142048.58 | July 2023
| Output 5.1.5. Developed circular economy through initiation integrated waste management system and processing | 312161.6158 | July 2023
| Output 5.1.6. Improve sanitation and clean water facility in 8 targets Kelurahan to mitigate risk of waterborne diseases | 333821.952 | July 2023
| A. Project/Program Excecution Cost | 191625.8077 | July 2023
| B. Project Cycle Managemet Services | 48947 | July 2023
| TOTAL | 3312089.9498 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Weak commitment built by project implementers with central/provincial/local government due to changes in government structure and lack of coordination and communication. | Low | - Coordinate with cross sectoral Municipal Offices related to the implementation of the Climate Adaptation Programme through quarterly regular meeting, - PMU AF Pekalongan prepares and provides quarterly narrative report on the Climate Change Adaptation programme implementation that is disseminated to related stakeholders
Changes in project personnel can affect the availability of qualified staff | Low | - Formulate strategic managerial measures and share roles between personnel within the PMU structure that will contribute to the achivement of programme target, - Provide coordination mechanism/flow between personnel in the review of the development of the programme implementation every month
Delays in disbursement of funds, procurement and institutional efficiency (long approval process and others) that delay project implementation | Medium | Optimize implementation mechanism/flow inline with the goods/services procurement SOP through coordination between PMU AF Pekalongan with the Procurement and Human Resources division of the Head Office
Lack of community (direct beneficiaries) support to the project | Medium | Optimize the impemlementation of activities that directly involve in the 8 target sites (Kel. Kandang Panjang, Panjang Wetan, Panjang Baru, Degayu, Krapyak, Bandengan, Padukuhan Kraton, Pasir Kraton Kramat) The step details are: 1. Program socialization, including: adaptation action programs in each intervention location, coverage of beneficiaries and community involvement in the program. 2. Establishment of a climate change village working group that has the role of planning, coordinating, mobilizing the community, and monitoring program evaluation climate change village working group members include various elements in the community (representatives of the kelurahan government, community institutions, women's groups and youth groups). It is hoped that the representation of members of this community group can be a forum for suggestions from the community.
Communities are less aware of climate change and have lack of enthusiasm to respond to disasters. If beneficiaries are not fully aware of the impacts of climate change, it is difficult to gain their commitment in urban farming development and climate change adaptation | Low | This step to manage risk is related to managing the risk described above. 1. Program socialization in 8 intervention villages 2. Village facilitators facilitate the identification of local actors who have the potential to be agents of change 3. Building awareness among youth groups starting with wactching film SEMESTA, facilitating FGDs to explore challenges and potentials in responding to climate change, Field trips and youth competitions describing their living conditions (community participation method). 4. Facilitators and community representatives are provided increase knowledge on climate change and the role of the kelurahan climate change working group. 5. The kelurahan facilitator facilitates the formation of a kelurahan climate change working group based on a list of previously identified local actors, consisting of elements from the kelurahan government, community institutions, youth groups and women's groups. (Community participatory method). 6. This step will continue in the second year, the kelurahan facilitator will facilitate the kelurahan climate change working group to prepare a work plan, develop profile of kelurahan climate resilience and climate change regional action plans (musrembang).
Conflict of community interest in selection of location | Medium | To establish and develop feedback system on the implementation of Climate Change programme in the community
Low technical knowledge of urban farming and eco-tourism | Low | - To recruit urban farming and eco-tourism experts - Involve multi-stakeholders in discussion and experiene sharing in the management of urban farming and eco-tourism
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change of location and type of coastal protection | Medium | - Coordinate with the Municipal Government of Pekalongan City on the Spatial Planning to be syhnergized with the changes in the development of Pekalongan City, - Communicate occurring changes of activities to AF Secretariat
Covid 19 pandemic outbreak | Medium | - Reschedule pending activities, - Implement changes in implementation strategy and approach
Tidal Flood | High | - Accessing the nformation from the National Meteorological Agency (BMKG) and disseminate to the community as a pre-warning of tidal flood, - Educate the community on the danger of tidal flood to minimize damage, - Take lessons from the previous tidal floods to develop strategy to enrich the effort of climate adaptation measures.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In the beginning of the programme implementation in Pekalongan, changes of the Urban Spatial Plannning of Pekalongan City has been acknowledged in respon to the frequently occuring tidal flood. The respond to protect the community of Pekalongan City was not only conducted by the Municipal Government but also by the Provincial and Central Government. The changes in the Urban Spatial Plan affected the Otuput 1.1.2 and 1.1.3 of the AF Pekalongan programme's SAFE KEEPING component. Stretegy applied by the PMU Pekalongan was to facilitate a multt-stakeholder discussion (Municipal and Provincial Governement, academics and community leaders). The discussion was held to identified needs resulted by the changes of Urban Spatial Planning and to collect inputs to AF Pekalongan programme related to SAFE KEEPING approach. Further, changes to SAFE KEEPING approach was communicated to AF Secretariat for approval. Another issue, the increasing frequency of tidal flood occured on the coast of Pekalongan City caused the deeper inundation of the City's Mangrove Information affecting the planned mangrove restoration and eco-tourism site. The PMU Pekalongan continues intensive coordination with the Municipal Government of Pekalongan City and coastal experts to seek common solution to anticipate the condition. Indeed, the risk management action has so far not result in significant achievement.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, in addition to gender assessment done during the preliminary assessment for this proposal, Kemitraan’s has also conducted additional gender assessment in Pekalongan City within the period of 2017 to 2018. The result of this gender assessment is added on the last page of Annex 3 of this document.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Increased coastal community resilience in Pekalongan City | Output 1.1.1 | Establishment of 6 kilometres of Mangrove Ecosystem | 0 | Activities planting, restoring and maintaining involve 30% female about 18 | 26% (88 from 335)
| Output 1.1.2 and 1.1.3 | Construction of 300 m parapet at Slamaran Beach in kelurahan Degayu | 0 | Social framework and inaguration involving 17 and 30 female
Enhanced capacity of local actors in identifying, initiating, strengthening, and escalating community-based actions to address climate risk and natural disaster; including capacity in integrating the actions to community development plan | Output 2.1.1 | Pekalongan City Climate Working Group reactivated | 0 | Activities, Kick off, FGD, Workshop, Seminar involve 243 female (30%) | 43% (78 from 181)
| Output 2.1.2 | Climate working group established and functioning in each of the 8 target kelurahan | 0 | 936 female (30%) involve in workshop CWG and VWG or other awareness activities and participation of the community and local governance service | 35% (114 from 328)
| Output 2.1.3 | Enhancing coastal community capacity in developing kelurahan’s information system and implementing the ensuing climate change adaptation actions | 0 | 120 (30%) female involve to help make decision on the ensuring adaptation action through implemented kelurahan's information system | 25% (2 from 8)
| Output 2.1.4 | Engaging youth groups and building their capacity to become Agents of Change in climate change adaptation actions of Pekalongan City | 0 | 428 (30%) youth Female are participating at the competition, movie screening and youth camp also in supporting climate change adaptation actions through social media, socialization | 53% (834 from 1583)
Enhanced capacity of local government and other city stakeholders’ in developing climate risk assessment and utilizing the results to develop local climate change adaptation action plan (RAD API) | Output 2.2.1 | RAD API developed based on Pekalongan City Climate Risk Assessment and Climate Coastal Impact | 0 | 30 female invloving at the development of RAD API document through training and writing workshop 1 document on mainstreaming gender and marginalized group incorporated within RAD API
| Output 2.2.2 | Strategy to integrate CCA into local government planning processes (annual work plan or mid-term development plan of city) is developed | 0 | Assessment on government commitment to the implementation of climate change budget and 60 (30%) female participation attended the FGD and workshop
Enhanced resilience of coastal community from the Implementing Climate smart initiatives, including those fostering sustainable utilization of natural resources, with implementation and financing scheme that can be replicated and disseminated to broader audience | Output 2.3.1 | Innovative and collaboration adaptation actions are implemented in collaboration with private sector, Government bodies and NGO | 0 | 102 (30%) Female participate in FGD, workshop, seminar in the climates smart initiatives | The implementation of the innovative and collaboration adaptation actions was to be conducted in the 2nd year
Established knowledge management network at city-level | Output 2.4.1 | Climate change training and knowledge sharing conducted | 0 | 93 (30%) Female participate in the training of increasing knowledged capacity, skills and knowledge management in climate change at community, city and province staff 30% of women Established community-led climate network | Not yet done, will implement in 2sd Year through community training and municipal city and provincial staff training
| Output 2.4.2 | Knowledge product, Advocacy materials (i.e. lessons learned, research paper, newsletter) published and shared | 0 | no targeted
| Output 2.4.3 | Local knowledge sharing platform established | 0 | 225 (30%) female are invlove in Establishment of local knowledge sharing network in level community and goverment level to enable knowledge exchange amongst stakeholders and Community through FGD or workshop | 38% (34 from 90)
Enhancing provincial government’s capacity in mainstreaming climate change adaptation and resilience into Central Java Province development plan | Output 3.1.1 | Enhanced provincial capacity to develop RAD API | 0 | 36 (30%) female are involve through training RAD API, resfresher course, shortcourse to Increasing the capacity of the provincial govt. to develop RAD-API involving key-stakeholders in the consultation and development process 1 document on mainstreaming gender and marginalized group incorporated within RAD API
| Output 3.1.2 | Appropriate strategy to integrate CCA into Provincial government planning processes (annual work plan or mid-term development plan of city) is developed | 0 | 60 (30%) female involve at FGD, workshop of accelerate climate change adaptation actions to be integrated into local government development planning in Province level
Increased economic income and improved community’s health in 8 target kelurahan of Pekalongan City | 5.1.1. Aquafarming in mangrove ecosystem developed and implemented by community | Introduce and apply capture fishery to community (including women groups) through enrichment of mangrove ecosystem with consumable fish and other sea species, such as shrimps and crabs (integrated aquaculture) | 0 | Fisherman/women in 8 villages
| 5.1.2. Mangrove ecotourism improved and involving wider participation of affected coastal community of Pekalongan City | Development of community based ecotourism, that includes women with full support of the municipal govt |  | Mangrove information centre, coastal mangrove belt | 27% (81 from 303)
| 5.1.3. Improved cultural economy through application of ecological batik using mangrove based colouring product | Introducing ecological batik colouring technic to the batik craftsmen community incl. women groups, and increase capacity of batik maker to improve designs |  | Batik maker in 8 villages | The implementation of the livelihood and sanitation programme components was to be conducted in the 2nd year. However, there has been identification of local actors from the 8 target sites that will be involved in the implemention. Identified local female actors reached 46% (69 from 150 women) coming from various initiatives among others representative of the Family Empowerment and Walfare (PKK), Waste Bank, Sustainable Food House Movement, Urban Farming Movement, Natural Batik Dyeing Entrepreneur etc.
| 5.1.4. Improved food security through the application of urban farming as alternative to conventional agriculture practices | Introducing and implementing urban farming based on local seeds to community (including women groups) as an alternative agriculture practices to strengthen local food security |  | 4 pilot sites in 4 of the target Kelurahan
| 5.1.5. Developed circular economy through initiation integrated waste management system and processing | Establishment of a functioning waste management facility that can offer jobs and business opportunities both for the city and for the community that also gender mainstreamed in the development of employment opportunity |  | 1 Kelurahan (pilot site)
| 5.1.6. Improve sanitation and clean water facility in 8 targets Kelurahan to mitigate risk of waterborne diseases | Improvement of domestic public sanitation and / or waste water facilities in 8 villages by involving the community (including women) and local governments from the start of planning, development and maintenance |  | 8 target Kelurahan
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4]
Gender Role: This programme will assist these specific groups i.e womens group PKK, Dharma Wanita, Muslimat-NU, and other marginalised groups by providing alternative livelihood to increase their income as well as possible adaptation actions they are able to implement themselves
Gender Activities: In community activities at the project location, the activities of women's groups have begun to appear. However, the proportion of involvement of women's groups is still weak in terms of quality of participation and involvement.
Gender Needs: Flood impacted groups especially groups of women are lack of knowledge in adaptation to climate change. In addition, the ability to create alternative livelihoods and voicing up the needs of women and children, is still very limited.
Opportunities and Challanges/Risks: During our first year building communities in site location in 2017, the eagerness of women in involvement towards policy making is relatively increasing whenever it match their interest and time. The risk is whether women as head of families can still be involved in the program activities since their time is limited.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | KEMITRAAN required quarterly report being submitted by Executing Entity, to monitor project implementation closely to comply with the required AF safeguard.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. The submitted quarterly reports help IE to evaluate the project implementation thoroughly.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The provision of the quarterly reports (note: Kemitraan is both the Implementing Entity and the Executing Entity for this project)
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes, so far it is effective
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Yes, it has. The gaps in general in Pekalongan City represent the national gap in gender equality despite of the existence of the Presidential Instruction No. 9/2000 on Gender Mainstreaming. The programme has therfore planned to dewploy a gender specialisst to assisst the implementation and engage youth and women gorups to be involved in any discussion and/o activities.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Yes
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | There is no griaveances report during the reporting period

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | 1. Physical environment disrruption from mobilization and construction process 2. Minor physical environment disruption from mobilization and construction process such as minor damage to road access from construction material | 1. Prepare and submit the required environmental documents prior to the implementation of adaptation actions, where this environmental document will be in coherent with the program’s ESMP 2. The required environmental documents are: o Individual and communal sanitation facilities (latrine): SPPL document o Aquaculture: UKL-UPL document o Rubbelmound breakwater : UKLUPL document o Eco-tourism: UKL-UPL document 3. Report the implementation and montioring of UKP-UPL to the City's Environmental Agenct in six monthly basis | 1. Number of Issued Environmental Permit 2. Number of monitoring report for breakwater and eco-tourism site | 0 | 1. No progress was done | 1. Physical environment disrruption from mobilization and construction process 2. Minor physical environment disruption from mobilization and construction process such as minor damage to road access from construction material | 1 & 2.UKL-UPL will be submited in the year to come.
2 - Access and equity |  |  | Social conflict arising from selection of community member that will be the implementer of adaptation actions and alternative livelihood at city level | 1. Conduct stakeholders mapping during project planning stage as the basis for determining the appropriate project implementer and beneficiaries, allocating fair roles and responsibilities among stakeholders, and selecting the appropriate activities site location (including knowledge board location) that could benefit wider community 2. Assign village working groups and city working group (which members include community representative) to lead the selection process at village and city level respectively. The beneficiaries’ critieria include: affected communities, poor and vulnerable people, farmer groups. Specifically for individual latrine, the beneficiaries will be women headed households 3. Coordination between village working group, city working group and financial institution to assess and select the most appropriate beneficiaries for the revolving fund Select working group member that could really represent the voiceand interest of all layers of community and city stakeholder | 1. Background of working group member 2. % of women representative in working group 3. % of women representative attendace in working group meeting 4. Number of stakeholder mapping document | no exissting WG. 0 0 0 | No progress was done | there is still possibility of social conflict | Monitoring reguraly with the following action: 1. Stakeholder mapping will be completed in the coming year 2. Working group municipal and kelurahan level will be established in the coming year 3. Coordination will only follow after WG is established
3 – Marginalized and vulnerable Groups |  |  | Social conflict arising from selection of priority activities site and design at city level which could raise envy from other community member that will not directly exposed to the program | 1. Conduct social impact assessment and develop the corresponding management plan on potential adaptation actions during prioritization process. This impact assessment and management plan will be in coherent with Program’s ESMP 2. Social impact assessment and management plan for the adaptation options will be integrated under UKL-UPL and SPPL document and will be submitted to the city agency 3. Put priority on pro-poor adaptation actions (action that could benefit those who have the least economic adaptive capacity but has a high exposure to climate risk) 4. Adaptation action design (the site location and structural design) will take account of the needs and suitability for elderly, children groups, and disable groups 5. Develop visibility materials that outlines background from the selection and communicate the materials to wider community 6. Involving village working groups (which members are community representative) in the selection process 7. Select working group member that could really represent the voice and interest of all layers of community and city stakeholder | 1. Number of Social Impact Assessment and Management Plan 2. Background of working group member 3. Number of input on technical details and site selection for the adaptation actions 4. Number of produced visibility materials 5. Number of people received the visibility materials | 0 0 0 0 0 | No progress was done | there is still possibility of social conflict | monitoring regularly with the following action: 1. the social impact assessment will be completed in the coming year 2. Once the social and management assessment are finalezed, will be integrated to the UKL-UPL and SPPL document 3. Put priority on pro-poor adaptation actions 4. Adaptation action design for sanitation facillity and waste management will be taken to action of the needs and suitabilities elderly children and disable groups 5. Develop visibility materials that outlines background from the selection and communicate the materials to wider community 6. Involving village working groups in the selection process 7. Select working group member that could really represent the voice and interest of all layers of community and city stakeholder
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | 1. Mobilization and planting process of mangrove belt could potentially impact the surrounding ecosystem 2. Potential impact to the surrounding ecosystem during construction and operational process of floating sanitation facilities 3. The impact of rubllemound breakwater mobilization and construction process to the existing surrounding coastal ecosystem 4. Waste generation and water pollution from ecotourism site preparation, development and operational activities could pollute the water and subsequently disrupt natural habitat 5. Minor environmental and ecological disruption from alteration of resource management from introduction of new mangrove species to the environment 6. Potential social conflict (resistance) with land-owner to allocate their unproductive private land for mangrove restoration site 7. Potential impact to the surrounding ecosystem during construction and operational process of floating sanitation facilities 8. Ecosystem disruption from mobilization and construction process of rubblemound breakwater 9. Waste generation and water pollution from ecotourism site preparation, development and operational activities could disrupt natural habitat and ecosystem balance, Large number of human presence and noise could disturb natural fauna in the area | 1. Develop environmental procedure that cover steps under for mangrove restoration activity 2. Activities conducted in the natural habitat area will follow Law 32 Year 2009 on Environmental Protection and Management and its derivative regulations, particularly section on natural habitat protection 3. Implement impact mitigation measures outline in the SPPL document of the said facilities 4. Design the floating facilities so that its construction phase will not adversely impact the water body and surrounding ecosystem 5. Activities conducted in the natural habitat area will follow Law 32 Year 2009 on Environmental Protection and Management and its derivative regulations, particularly section on natural habitat protection 6. Build temporary sediment and oil trap during facilities construction to prevent sedimentation and inflow of oil-based material to body of water (for floating design) 7. Implement impact mitigation measures outline in the Rona Lingkungan/UKL-UPL/AMDAL document of the said structure 8. Activities conducted in the natural habitat area will follow Law 32 Year 2009 on Environmental Protection and Management and its derivative regulations, particularly section on natural habitat protection 9. Build temporary sediment and oil trap during rubble mound breakwater construction process to control abrasion, sedimentation, oil-based material flow to ecosystem 10. Implement impact mitigation measures outline in the UKL-UPL document of the said structure 11. Develop sound and applicable environmental procedures for day to day operations of the eco-tourism site that comply with local regulation for ecotourism site, including waste management plan 12. Activities conducted in the natural habitat area will follow Law 32 Year 2009 on Environmental Protection and Management and its derivative regulations, particularly section on natural habitat protection 13. Build temporary sediment trap during ecotourism site development to control abrasion and sedimentation within mangrove ecosystem | 1. Number of environmental procedure for mangrove restoration activity 2. Number of SPPL document 3. Number of operating sediment and oil trap facilities during construction phase 4. Number of UKL-UPL document 5. Number of operating sediment and oil trap facilities during construction phase 6. Number of UKL-UPL document 7. Number of operating sediment and oil trap facilities during construction phase 8. Number of environmental procedures for eco-tourism site operations 9. Number of UKL-UPL monitoring report 10. Number of environmental procedure for mangrove restoration activity 11. Number of assessment on appropriateness of the proposed mangrove species for mangrove belt planting activity in the proposed location 12. Number of map 13. Number of land-owner attending the workshops 14. Number of SPPL document 15. Number of operating sediment and oil trap facilities during construction phase 16. Availiability of document on floating facilities design 17. Number of UKL-UPL document 18. Number of operating sediment and oil trap facilities during construction phase 19. Number of UKL-UPL document 20. Number of operating sediment and oil trap facilities during construction phase 21. Number of environmental procedures for eco-tourism site operations 22. Number of UKL-UPL monitoring report | 0 0 0 0 0 0 0 0 0 0 0 | No progress was done | There is possibility polution to the sorunding ecosystem such as: coastal ecosystem, the natural habitat. There is possibility in social conflict on land owner | In order to cope with the residual impact, the activity will be follow: 1. Develop environmental procedure that cover steps under for mangrove restoration activity 2. Activities conducted in the natural habitat area will follow Law 32 Year 2009 on Environmental Protection and Management and its derivative regulations, particularly section on natural habitat protection 3. Implement impact mitigation measures outline in the SPPL document of the said facilities 4. Design the floating facilities so that its construction phase will not adversely impact the water body and surrounding ecosystem 5. Build temporary sediment and oil trap during facilities construction to prevent sedimentation and inflow of oil-based material to body of water 6. Implement impact mitigation measures outline in the UKL-UPL document of the said structure 7. Develop sound and applicable environmental procedures for day to day operations of the eco-tourism site that comply with local regulation for ecotourism site, including waste management plan
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | 1. Water pollution from mobiliization and construction process of rubblemound breakwater , Sedimentation from mobiliization and construction process of rubblemound breakwater 2. Increase in water turbidity during mangrove restoration process 3. Water pollution due to solid waste generation and effluent from the site's toilet facilities, and other operational activities in the eco-tourism site 4. Ground water or sea water pollution from construction process of the facilities, effluent from sanitation facilities (during its operational phase), and potential leakage from the facilities | 1. Implement impact mitigation measures outline in the UKL-UPL document of the said structure 2. Build temporary sediment and oil trap during rubble mound breakwater construction process to control abrasion, sedimentation, oil-based material flow to ecosystem 3. Develop sound environmental procedure that cover steps under for mangrove restoration activity, including temporary waste management plan 4. Develop UKL-UPL for ecotourism activities, implement impact mitigation measures outline in the said document, and submit the relevant monitoring report to City Agency every 6 months 5. Develop sound and applicable environmental procedures that comply with local regulation for ecotourism site, including waste management plan; in which the procedure is an integrated part to the submitted UKL-UPL 6. Provide training on the environmental procedures to community member that are involved in managing the eco-tourism site Equipped the site with adequate signage regarding environmentally friendly practices in the area 7. Coordinate with Cleanliness Agency of Pekalongan City in the waste management activities 8. As a community-based ecotourism, involve the community in the waste management process, including train them to be able to utilize the waste as additional income; either by creating added value to the waste (compost, recycling) from the waste or collect waste that has monetary value (plastic, paper, metal) 9. Submit SPPL document for communal sanitation facilities to obtain environmental permit for its implementation 10. Design the sanitation facilities in accordance with SNI 03-2398-2002 and SNI 03-2399-2002 11. Rigorous assessment on the most appropriate sanitation facilities for the area’s characteristics (including geographical and soil characteristics), to minimize potential risks of pollution 12. Regular water quality monitoring on the body of water where the sanitation facilities effluent is being conveyed 13. Together with the community develop utilization and maintenance procedure for the facilities, where the said procedures will be undertaken by them 14. Educate the community on good sanitation behaviour | 1. Number of UKL-UPL document 2. Number of operating sediment and oil trap facilities during construction phase 3. Number of UKL-UPL monitoring report for rubble mound breakwater 4. Number of environmental procedure for mangrove restoration activity 5. Number of UKL-UPL document 6. Number of operating sediment and oil trap facilities during construction phase 7. Number of environmental procedures for eco-tourism site operations 8. Number of community member involved in the ecotourism management being trained for environmental proceures 9. Number of UKL-UPL monitoring report 10. Number of community member involved in waste management activity Number of SPPL document 11. Number of operating sediment and oil trap facilities during construction phase 12. Availability of document on floating facilities design 13. Number of surface water quality monitoring report 14. Number of utilization and maintenance procedure for the facitlies 15. Number of trainings and visibility materials on good sanitation behaviour | 0 0 0 0 0 0 0 0 0 | no progress was done | There is possibility polution to the sorunding ecosystem such as: water turbiditycoastal ecosystem, the natural habitat. | In order to cope with the residual impact, the activity will be follow: 1. Implement impact mitigation measures outline in the UKL-UPL document of the said structure 2. Build temporary sediment and oil trap during rubble mound breakwater construction process to control abrasion, sedimentation, oil-based material flow to ecosystem 3. Develop sound environmental procedure that cover steps under for mangrove restoration activity, including temporary waste management plan 4. Develop UKL-UPL for ecotourism activities, implement impact mitigation measures outline in the said document, and submit the relevant monitoring report to City Agency every 6 months 5. Develop sound and applicable environmental procedures that comply with local regulation for ecotourism site, including waste management plan; in which the procedure is an integrated part to the submitted UKL-UPL 6. Provide training on the environmental procedures to community member that are involved in managing the eco-tourism site Equipped the site with adequate signage regarding environmentally friendly practices in the area 7. Coordinate with Cleanliness Agency of Pekalongan City in the waste management activities 8. As a community-based ecotourism, involve the community in the waste management process, including train them to be able to utilize the waste as additional income; either by creating added value to the waste (compost, recycling) from the waste or collect waste that has monetary value (plastic, paper, metal) 9. Submit SPPL document for communal sanitation facilities to obtain environmental permit for its implementation 10. Design the sanitation facilities in accordance with SNI 03-2398-2002 and SNI 03-2399-2002 11. Rigorous assessment on the most appropriate sanitation facilities for the area’s characteristics, to minimize potential risks of pollution 12. Regular water quality monitoring on the body of water where the sanitation facilities effluent is being conveyed 13. Together with the community develop utilization and maintenance procedure for the facilities, where the said procedures will be undertaken by them 14. Educate the community on good sanitation behaviour
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | 1. Soil pollution from solid waste, oilbased waste and waste water during mobilization and construction process of rubblemound breakwater 2. Soil pollution from waste generation and waste water contamination during operational activities in the eco-tourism site 3. Soil pollution from construction process of the facilities and potential soil contamination from effluent of sanitation facilities (during its operational phase), and potential leakage from the facilities (if the facilities are not floating design) | 1. Develop and submit UKL-UPL document for rubble mound breakwater construction to obtain environmental permit for its implementation, and subsequently implement impact mitigation measures outline in the said document 2. Build temporary sediment and oil trap during coastal embankment construction process, to control oil infiltration to the soil layer, and also to prevent abrasion and sedimentation 3. Develop and submit UKL-UPL for ecotourism activities and implement impact mitigation measures outline in the said document 4. Submit monitoring report of UKL-UPL to the City Agency every 6 months 5. Develop sound and applicable environmental procedures that comply with local regulation for ecotourism site, including waste management plan; in which the procedure is an integrated part to the submitted UKL-UPL 6. Provide training on the environmental procedures to community member that are involved in managing the eco-tourism site 7. Equipped the site with adequate signage regarding environmentally friendly practices in the area 8. Coordinate with Cleanliness Agency of Pekalongan City in the waste management activities 9. As a community-based ecotourism, involve the community in the waste management process, including train them to be able to utilize the waste as additional income; either by creating added value to the waste (compost, recycling) from the waste or collect waste that has monetary value (plastic, paper, metal) 10. Submit SPPL document for communal sanitation facilities to obtain environmental permit for its implementation 11. Design the sanitation facilities in accordance with SNI 03-2398-2002 and SNI 03-2399-2002 12. Develop Environmental Management and Monitoring Plan for coastal sanitation facilities' construction process 13. Together with the community develop utilization and maintenance procedure for the facilities, where the said procedures will be undertaken by them 14. Rigorous assessment on the most appropriate sanitation facilities for the area’s characteristics (including geographical and soil characteristics), to minimize potential risks of pollution 15. Regular water quality monitoring on the body of water (including community's ground water source and sea water) where the sanitation facilities effluent is being conveyed 16. Water tight construction for the sanitation facilities (particularly the waste water management installation) to minimize potential leakage to the soil 17. Educate the community on good sanitation behaviour | 1. Number of UKL-UPL document 2. Number of operating sediment and oil trap facilities during construction phase 3. Number of UKL-UPL monitoring report for rubble mound breakwaterGeo tube Number of UKL-UPL document 4. Number of operating sediment and oil trap facilities during construction phase 5. Number of environmental procedures for eco-tourism site operations 6. Number of community member involved in the ecotourism management being trained for environmental proceures 7. Number of UKL-UPL monitoring report 8.Number of community member involved in waste management activity Number of SPPL document 9. Number of operating sediment and oil trap facilities during construction phase 10. Availability of document on facilities design 11. Number of surface water quality monitoring report 12. Number of trainings and visibility materials on good sanitation behavior | 0 0 0 0 0 0 0 0 0 | no proggress was done | There is possibility polution to the sorunding ecosystem such as: soil pollution, oil-based waste, coastal ecosystem. | In order to cope with the residual impact, the activity will be follow: 1. Develop and submit UKL-UPL document for rubble mound breakwater construction to obtain environmental permit for its implementation, and subsequently implement impact mitigation measures outline in the said document 2. Build temporary sediment and oil trap during coastal embankment construction process, to control oil infiltration to the soil layer, and also to prevent abrasion and sedimentation 3. Develop and submit UKL-UPL for ecotourism activities and implement impact mitigation measures outline in the said document 4. Submit monitoring report of UKL-UPL to the City Agency every 6 months 5. Develop sound and applicable environmental procedures that comply with local regulation for ecotourism site, including waste management plan; in which the procedure is an integrated part to the submitted UKL-UPL 6. Provide training on the environmental procedures to community member that are involved in managing the eco-tourism site 7. Equipped the site with adequate signage regarding environmentally friendly practices in the area 8. Coordinate with Cleanliness Agency of Pekalongan City in the waste management activities 9. As a community-based ecotourism, involve the community in the waste management process, including train them to be able to utilize the waste as additional income; either by creating added value to the waste (compost, recycling) from the waste or collect waste that has monetary value (plastic, paper, metal) 10. Submit SPPL document for communal sanitation facilities to obtain environmental permit for its implementation 11. Design the sanitation facilities in accordance with SNI 03-2398-2002 and SNI 03-2399-2002 12. Develop Environmental Management and Monitoring Plan for coastal sanitation facilities' construction process 13. Together with the community develop utilization and maintenance procedure for the facilities, where the said procedures will be undertaken by them 14. Rigorous assessment on the most appropriate sanitation facilities for the area’s characteristics, to minimize potential risks of pollution 15. Regular water quality monitoring on the body of water where the sanitation facilities effluent is being conveyed 16. Educate the community on good sanitation behaviour
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, the monitoring will take place after the visibility studies for breakwater construction, assesment for sanitation, eco-tourism and waste management are finalised
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks identified during the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | In this case we will update our ESMP in accordance with the occuring risks
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | KEMITRAAN required quarterly report being submitted by PMU Pekalongan to monitor project implementation closely to comply with the required AF safeguard.
Have the implementation arrangements been effective during the reporting period? |  | Yes. By having 3 monthly reports, IE could evaluate the project implementation thoroughly (note: Kemitraan is both the Implementing Entity and the Executing Entity for this project).
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The provision of the quarterly reports
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. All obstacle could be reported and identified immidiately if any to come up with solution.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance reported so far to the PMU Pekalongan Office
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Note on E65: Moch. Ghufron: Di isi untuk mematau jika ada pengaduan atas program yang berjalan

## Rating
Page: 103
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1.1. Increased coastal community resilience in Pekalongan City |  | Outcome 4 | Approx. 75% of targeted coastal areas is protected through a combination of mangrove ecosystem, coastal embankment and parapet construction At least, the coastal areas in 3 kelurahan is protected through mangrove ecosystem |  | 1. The DED of coastal protection is currently in preces and targeted to be finalised in October 2022, 2. Mangrove enrichment currently conducted outside of the City's Mangrove Information Centre due to deepening of the inundation (Planting currently not visible) | MU
| 2.1 Enhanced capacity of local actors in identifying, initiating, strengthening, and escalating community-based actions to address climate risk and natural disaster; including capacity in integrating the actions to community development plan |  | Outcome 3 | 160 community members from 8 kelurahan become agent of change in coping better with climate-change through adaptation and actions. The targets will be counted from the achievement in each outcome. |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. The youth groups, high schools, universities and community groups/organizations that have been identified are built bonding through awareness activities on the impact of climate change through SEMES7A film screening which were attended by 1,368 participants. 2. Community groups/organizations that have the potential to be involved in the kelurahan working group involved in socialization about climate change and the formation of the kelurahan working group with a total of 328 participants. | MU
| 2.2 Enhanced capacity of local government and other city stakeholders’ in developing climate risk assessment and utilizing the results to develop local climate change adaptation action plan (RAD API) |  | Outcome 7 | Increased capacity of local government and city’s key stakeholders in the development of climate risk assessment and utilizing the results to develop local climate change adaptation action plan that is mainstreamed in the Municipal Development Plan with regards to gender equity |  | The target will achive in 3th year, in 1st year progress of achievement: 1. Hired Consultant (PIAREA) to fasilitate develop local climate change adaptation action plan (RAD API) 2. Kickoff RAD API Kickoff RAD API and signing Cooperation Agreement (PKS) with 82 participant from government organization and community organization to involve in working group city and village level. Working group city and village level for next step will coordinate develop RAD API | MU
| 2.3. Enhanced resilience of coastal community from the Implementing Climate smart initiatives, including those fostering sustainable utilization of natural resources, with implementation and financing scheme that can be replicated and disseminated to broader audience |  | Outcome 8 | Improved livelihoods and ecosystem resilience, as well as developed social behavioural changes in community through applied Climate Smart Initiative. Adoption and application of developed online technology systems were developed in collaboration with local governments |  | After the MoU signing with the Municipal Government and the 9 Municipal Offices, the programme is in the process of developing RAD-API document and Sub-Distric Information System (SIK) related to Climate Change Adaptation in terms of responding to the climate change impact affected Pekalongan City. | MU
| 2.4 Established knowledge management network at municipality level |  | Outcome 3 | The knowledge management network established in each target kelurahan that are actively engage and communicate with each other. |  | The target will be achieved in 3th year, in 1st year progress of achievement: coordinated and discuss with Regional Development Planning (BAPPEDA) provincial level about Kemitraan program and potential capacity of Offices to develop local climate change adaptation action plan provincial level. | MU
| 3.1. Enhancing provincial government’s capacity in mainstreaming climate change adaptation and resilience into Central Java Province development plan |  | Outcome 2 | Increased capacity of local governments and key city stakeholders (at least 7 municipal offices) in developing climate risk assessments and utilize the results to develop local climate change adaptation action plans that are mainstreamed in the Provincial Development Plans with regards to gender equality (Environmental Office, Bappeda, Maritime and Fisheries Office, agriculture Office, public works Office, women empowerment, Health Office) |  | The target will be achieved in 3th year, in 1st year progress of achievement: coordinated and discuss with Regional Development Planning (BAPPEDA) provincial level about Kemitraan program and potential capacity of Offices to develop local climate change adaptation action plan provincial level. | U
| 4.1. Enriching SIDIK as risk assessment tools for coastal area based on local experience |  | Outcome 1 | SIDIK Handbook developed, introduced and disseminated to broader stakeholder at all governmental level (local, provincial and national) with input from multi-stakeholders (i.e civic society, local government, private sectors and national government) in the re-formulation of SIDIK indicators. Introducing SIDIK as risk assessment tools for coastal area based on local experience at two ministries which include Ministry of Marine and Fisheries, and Ministry of Environment and Forestry Two technical ministries on forestry and coastal management is actively involved in governing Climate Change Adaptation through SIDIK system. |  | The target will be achieved in 3th year | MU
| 5.1. Increased economic income and improved community’s health in 8 target kelurahan of Pekalongan City |  | Outcome 6 | At least 4 (four) sustainable livelihood are adopted and applied as climate change adaptation strategies by communities in each kelurahan through inclusive approach, by involving women and other marginalized group. The sustainable livelihood includes community fisheries at coastal areas, urban farming strategies, community-based ecotourism and integrated-waste management in communities. Institutionalization of circular economics to improve average income in each Kelurahan, both in normal seasonal condition and in the mid of increasing of climate change consequences (i.e. El-Nino, La-Nina, Long drought, or wet-dry seasons). Furthermore, decreasing the health problems and risk in 8 Kelurahan. |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. Identified pond group, urban farming group, batik maker group 2. Learning study implementation waste management-circular economic program (DAYA OOPS MAMI) by office of environment 3. Discuss preparation assessment communal latrines in 8 kelurahan | MU
| 5.1. Increased economic income and improved community’s health in 8 target kelurahan of Pekalongan City |  | Outcome 4 | Income or health level of beneficiaries of sustainable economic empowerment as well as improved watsan facilities at the program location, Male = 1.394 persons or 60% Female = 697 persons or 30%, include women headed family Vulnerable = 232 persons or 10% |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. Identified pond group, urban farming group, batik maker group 2. Learning study implementation waste management-circular economic program (DAYA OOPS MAMI) by office of environment 3. Discuss preparation assessment communal latrines in 8 kelurahan | MU
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dewi Rizki
| Email: | dewi.rizki@kemitraan.or.id
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Within the time gap between the initial concept note development and the approval of the full proposal of AF Pekalongan Project (approx. 4 years), dynamic changes occurred in the Pekalongan City’s Urban Spatial Planning, among others the construction of parapet on the coast of Pekalongan City stretching from Kelurahan Kandang Panjang to Kelurahan Degayu and the construction of retention pond. These changes constitute to the effort of the Municipal Government under the mandate of the Provincial and Central Government to protect the municipal community affected by the high tidal flood occurred in 2010. These changes therefore affected the initial plan for the parapet construction of AF Pekalongan Project in Kelurahan Degayu as outlined in the approved proposal. Dealing with this matter, the Municipal Government of Pekalongan City and KEMITRAAN developed new plan to establish coastal protection in the area of Kelurahan Kandang Panjang and Bandengan, where the area of the Mangrove Information Centre (MIC) is located. The planned coastal protection is expected to reduce coastal abrasion and to develop sedimentation in the MIC for the purpose of mangrove restoration. The process of the diversion of the initial plan has involved coastal experts and academics from the IPB University of Bogor, the Technology Institute of Bandung (ITB) and the Diponegoro University of Semarang City). Currently, KEMITRAAN works with a coastal construction planning company (PT NPA) to develop the Detailed Engineering Design (DED) supervised by coastal expert consultant of ITB. The DED will serve as reference for the construction of the most effective wave breaker for the target coastal site.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1.1. Increased coastal community resilience in Pekalongan City |  | Outcome 4 | Approx. 75% of targeted coastal areas is protected through a combination of mangrove ecosystem, coastal embankment and parapet construction At least, the coastal areas in 3 kelurahan is protected through mangrove ecosystem |  | 1. The DED of coastal protection is currently in preces and targeted to be finalised in October 2022, 2. Mangrove enrichment currently conducted outside of the City's Mangrove Information Centre due to deepening of the inundation (Planting currently not visible) | S
| 2.1. Enhanced capacity of local actors in identifying, initiating, strengthening, and escalating community-based actions to address climate risk and natural disaster; including capacity in integrating the actions to community development plan |  | Outcome 3 | 160 community members from 8 kelurahan become agent of change in coping better with climate-change through adaptation and actions. The targets will be counted from the achievement in each outcome. |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. The youth groups, high schools, universities and community groups/organizations that have been identified are built bonding through awareness activities on the impact of climate change through SEMES7A film screening which were attended by 1,368 participants. 2. Community groups/organizations that have the potential to be involved in the kelurahan working group involved in socialization about climate change and the formation of the kelurahan working group with a total of 328 participants. | MU
| 2.2. Enhanced capacity of local government and other city stakeholders’ in developing climate risk assessment and utilizing the results to develop local climate change adaptation action plan (RAD API) |  | Outcome 7 | Increased capacity of local government and city’s key stakeholders in the development of climate risk assessment and utilizing the results to develop local climate change adaptation action plan that is mainstreamed in the Municipal Development Plan with regards to gender equity |  | The target will achive in 3th year, in 1st year progress of achievement: 1. Hired Consultant (PIAREA) to fasilitate develop local climate change adaptation action plan (RAD API) 2. Kickoff RAD API Kickoff RAD API and signing Cooperation Agreement (PKS) with 82 participant from government organization and community organization to involve in working group city and village level. Working group city and village level for next step will coordinate develop RAD API | MU
| 2.3. Enhanced resilience of coastal community from the Implementing Climate smart initiatives, including those fostering sustainable utilization of natural resources, with implementation and financing scheme that can be replicated and disseminated to broader audience |  | Outcome 8 | Improved livelihoods and ecosystem resilience, as well as developed social behavioural changes in community through applied Climate Smart Initiative. Adoption and application of developed online technology systems were developed in collaboration with local governments |  | After the MoU signing with the Municipal Government and the 9 Municipal Offices, the programme is in process of developing RAD-API document and Sub-Distric Information System (SIK) related to Climate Change Adaptation in terms of responding to the climate change impact affected Pekalongan City. | MU
| 2.4 Established knowledge management network at municipality level |  | Outcome 3 | The knowledge management network established in each target kelurahan that are actively engage and communicate with each other. |  | The target will achive in 3th year, in 1st year progress of achievement: coordinated and discuss with Regional Development Planning (BAPPEDA) provincial level about Kemitraan program and potential capacity of Offices to develop local climate change adaptation action plan provincial level. | MU
| 3.1 Enhancing provincial government’s capacity in mainstreaming climate change adaptation and resilience into Central Java Province development plan |  | Outcome 7 | Increased capacity of local governments and key city stakeholders (at least 7 municipal offices) in developing climate risk assessments and utilize the results to develop local climate change adaptation action plans that are mainstreamed in the Provincial Development Plans with regards to gender equality (Environmental Office, Bappeda, Maritime and Fisheries Office, agriculture Office, public works Office, women empowerment, Health Office) |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. Identified pond group, urban farming group, batik maker group 2. Learning study implementation waste management-circular economic program (DAYA OOPS MAMI) by office of environment 3. Discuss preparation assessment communal latrines in 8 kelurahan | U
| 4.1 SIDIK as risk assessment tools for coastal area based on local experience enriched |  | Outcome 8 | SIDIK Handbook developed, introduced and disseminated to broader stakeholder at all governmental level (local, provincial and national) with input from multi-stakeholders (i.e civic society, local government, private sectors and national government) in the re-formulation of SIDIK indicators. Introducing SIDIK as risk assessment tools for coastal area based on local experience at two ministries which include Ministry of Marine and Fisheries, and Ministry of Environment and Forestry Two technical ministries on forestry and coastal management is actively involved in governing Climate Change Adaptation through SIDIK system. |  | The target will achive in 3th year | MU
| 5.1. Increased economic income and improved community’s health in 8 target kelurahan of Pekalongan City |  | Outcome 6 | At least 4 (four) sustainable livelihood are adopted and applied as climate change adaptation strategies by communities in each kelurahan through inclusive approach, by involving women and other marginalized group. The sustainable livelihood includes community fisheries at coastal areas, urban farming strategies, community-based ecotourism and integrated-waste management in communities. Institutionalization of circular economics to improve average income in each Kelurahan, both in normal seasonal condition and in the mid of increasing of climate change consequences (i.e. El-Nino, La-Nina, Long drought, or wet-dry seasons). Furthermore, decreasing the health problems and risk in 8 Kelurahan. |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. Identified pond group, urban farming group, batik maker group 2. Learning study implementation waste management-circular economic program (DAYA OOPS MAMI) by office of environment 3. Discuss preparation assessment communal latrines in 8 kelurahan | MU
| 5.1. Increased economic income and improved community’s health in 8 target kelurahan of Pekalongan City |  | Outcome 4 | Income or health level of beneficiaries of sustainable economic empowerment as well as improved watsan facilities at the program location, Male = 1.394 persons or 60% Female = 697 persons or 30%, include women headed family Vulnerable = 232 persons or 10% |  | The target will achive in 2nd and 3th year, in 1st year progress of achievement: 1. Identified pond group, urban farming group, batik maker group 2. Learning study implementation waste management-circular economic program (DAYA OOPS MAMI) by office of environment 3. Discuss preparation assessment communal latrines in 8 kelurahan | MU
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Andi Kiky
| Email: | andi.kiki@kemitraan.or.id
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The implementation of some programme components during the first year was delayed based on changes in Pekalongan City’s Urban Spatial Planning and the increased frequency and height of tidal flood. Intensive dialogue with the Municipal Government has therefore been conducted to review the programme in regards to anticipate the impact. Meanwhile, in parallel to the dialogue and discussions, PMU Pekalongan has conducted identification of local actors and explored the circular economy and alternative economic potential at kelurahan level that could drive the increase of community’s economic resilience. Identification of the current sanitation condition has also been conducted. Local youth actors are also involved as agent of change in the community. The adaptation action forum is facilitated through the Climate Change Working Group at kelurahan level..
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective 1 | 50% of the total households or equal to 12,573 households has gained impact from protection along coast line from sea level rise causing tidal flood and inundation | Base on Monografi Kelurahan Period July-Dec 2021, the total of HHs in Pekalongan Utara sub district: 23,798 HHs | Still in progress | 12,573 households has gained impact from protection along coast line from sea level rise causing tidal flood and inundation
Outcome 1.1 | Approx. 75% of targeted coastal areas is protected through a combination of mangrove ecosystem, coastal embankment and parapet construction. At least, the coastal areas in 3 kelurahan is protected through mangrove ecosystem | • Abrasion/coastal erosion data • Mangrove degradation data • Degradation of the vegetation data • Land salinization/salt water intrusion data • Ecosystem degradation and increased waste production lead to health issues especially in poor urban communities data | Still in progress | 6,3 km
Output 1.1.1 | 3 hectares of targeted coastal areas is protected through established mangrove ecosystem. | Existing MANGROVE in PIM area 6.48 ha from 31.14 ha. The Pekalongan city government targets the mangrove conservation area in PIM to be 5.7 ha (the land status belongs to the city government). The location of the Kelurahan (village) of Kandang Panjang and Bandengan is very close to the PIM area with 9168 HHs (31,337 person). | Mangrove enrichment of 0.4 ha has been conducted. Planting in the area of Mangrove Information Centre is facing constrains due to natural causes | 3 ha of Mangrove Ecosystem,
| At least, the coastal areas in 3 kelurahan is protected through mangrove ecosystem |  | As a result of FGD, there are three potential areas to plan mangrove in Kelurahan Degayu, Kandang Panjang and Bandengan with estimation planting area of: - Degayu 8x17 m² and length 98 m - Kandang Panjang 5264 m² - Bandengan 1000x3 m² and 20x20 m²
| 60 persons are involved in expanding mangrove cover in coastal areas by planting, restoring, and maintaining. The involved community consists approximately of 36 male and 18 female, and additional 6 persons identified as vulnerable |  | 33 persons (26 males, 7 females) are involved in FGDs to identify potential mangrove restoration area | 60 persons
Output 1.1.2 | 300 meters of coastline are rehabilitated through the construction of parapet | The Coastal embankment has been built with funding from the Central and Municipal Governments | Merged in output 1.1.3 | 300 m parapet,
| 1 Kelurahan is protected by parapet construction in Slamaran beach. |  |  | 1 Kelurahan,
| 56 local people were socialized about livable and healthy settlements and were involved in the construction of a 300 meter long parapet infrastructure in Kelurahan Degayu. Amongst the 56 are 34 male, 17 female and 5 persons identified as vulnerable |  |  | 56 persons
Output 1.1.3 | 1.400 meters of Coastal embankment (geo-tube/sand trap) construction at Kelurahan Kandang Panjang established. | Current conditions in the coastal area: 1. Existing geotube/sand trap are mostly submerged 2. Expanding inundation 3. Road damage due to tidal flooding The location of the Kelurahan (village) of Kandang Panjang and Bandengan is very close to the PIM area with 9168 HHs (31,337 person). | in process to development of Design Engineering Document | 1.400 m Coastal embankment,
| 97 local people have increased awareness and participated in the protection of coastal areas and mangrove planting, especially in Kelurahan Kandangan Panjang. Amongst the above number of people are 58 male, 29 female and 10 persons identified as vulnerable |  | in process to development of Design Engineering Document | 97 persons
Objective 2 | 8 (eight) CCA-specific activities with allocated budget are included in City Developmet Plan |  | Still on progress | 1. Regional Development Planning (Bappeda) 2. Office of Communication and Information (Diskominfo) 3. Office of Agriculture and Food (Dinperpa) 4. Office of Tourism, Youth and Sport (Dinparbudpora) 5. Office of Environment (DLH) 6. Office of Marine and Fishery (DKP) 7. Office of Public Works and Spatial Planning (DPUPR) 8. Health Office (Dinkes) 9. Office of Trade and Cooperative (Dindagkop).
Outcome 2.1 | 160 community members from 8 kelurahan become agent of change in coping better with climate-change through adaptation and actions. The targets will be counted from the achievement in each outcome. | • Local actors have limited capacity to prepare for and respond to climate change and natural hazards • The most vulnerable areas and groups receive limited infrastructure support and no targeted object to receive resilience building support because of limited capacity and resources. • Detailed/specific climate change threat and hazard information / evidence is not available at community scale in Pekalongan City, which means the local government and communities can’t plan for appropriate adaptation actions | 29 Community Members | 160 community members
Output 2.1.1 | The existing City Climate Working Group reactivated and actively involved in the planning of adaptation action at municipal level, both community based and government led. | Pekalongan city government does not yet have a working group and action plan for climate change adaptation program | in process to identify city working group existing and discuss next strategy to encourage the city working group active to implement adaptation action plan | 1 City Climate
| 80% of the members of the Pekalongan City climate working group, representatives of regional stakeholders and / or program cadres that they are active in FGD forums, workshops and meetings organized by the program |  | in process to identify city working group existing and discuss next strategy to encourage the city working group active to implement adaptation action plan | Working Group (80% of the members of the Pekalongan City climate working group representatives of regional stakeholders and / or program cadres)
| 30% of climate working group members in Pekalongan city, representations of women groups and vulnerable groups |  | in the process to identify potential city working group members and discuss next strategy to encourage the city working group to actively implement adaptation action plan | 30% representations of women groups and vulnerable groups
Output 2.1.2 | 8 climate working group established in each kelurahan and actively involved in the development of community based adaptation action plan | Identification of potential groups and/or community organizations to be involved in the Kelurahan working group with following results: 1. Apsara 2. Mapan 3. DFTF (Degayu For The Future) 4. Kencana Jaya 5. Pengurus Taman Cabe Sakura 6. LKK (Lembaga Kemasyarakatan Kelurahan) in each village 7. Save Pekalongan Community | in process to publish legality of Kelurahan working group | 8 Kelurahan Climate Working Group
| 80% of the members of the Kelurahan climate working group in 8 Kelurahan are represented by programme cadres. They are to be active in FGD forums, workshops and meetings organized by the programme |  | Village working group just was formed so not yet any development activities for members of village working group | 80% of the members of the Kelurahan climate working group representatives of programme cadres
| 30% of climate working group members at Kelurahan level represented by women and vulnerable group |  | 41% of women representative in working group | 30% representations of women groups and vulnerable groups
| There is a document of lesson learned or best practice about women and vulnerable groups related to climate change adaptation |  | targeted in the third year of programme implementation | 1 document of lesson learned or best practice
Output 2.1.3 | Climate change information system (CCIS) developed and ensuing climate change adaptation actions implemented | Development of a village information system called Rumah Data (management of information and data collection, etc) | CCIS is cirrently in the process of development | 1 Climate change information system (CCIS)
Output 2.1.4 | At least 3 (three) youth groups established across 8 targeted Kelurahan with developed action plan agreed upon | Identify university and High School, youth group (Karang Taruna, IPNU, etc) in Pekalongan City | Establishment of youth group KOBAR | At least 3 youth groups
Outcome 2.2 | Increased capacity of local government and city’s key stakeholders in the development of climate risk assessment and utilizing the results to develop local climate change adaptation action plan that is mainstreamed in the Municipal Development Plan with regards to gender equity | • Lack of capacity of the local governments officer and related stakeholders to lead climate change adaptation and disaster risk reduction plan • Any interventions in the proposed intervention areas will continue as small-scale and stand- alone projects that lack integration and miss important opportunities for synergies. They also will not consider the impact of future climate change and the need to include consideration in the design of community level interventions. • The most vulnerable communities are not targeted/reached | in process | 1 document of RAD API (CC Adaptation Action Plan) incorporated within annual work-plan or mid-term development plan at municipal level
Output 2.2.1 | Climate change adaptation action plan adopted and developed to RAD API documents and incorporated within annual work-plan or mid-term development plan at municipal level | Pekalongan city government does not yet have an action plan for climate change adaptation program. | in process | 1 draft document of RAD API incorporated CC-Adaptation within annual work-plan or mid-term development plan at municipal level
| Mainstreaming gender and marginalized groups adopted and developed to RAD API documents and incorporated within annual work-plan or mid-term development plan at municipal level |  | in process | 1 document on mainstreaming gender and marginalized group incorporated within RAD API and annual work-plan or mid-term development plan at municipal level
Output 2.2.2 | At least, 5 municipal offices (Regional Development Planning (Bappeda), Office of Marine and Fisherie, Office of Environment, Public Work and Spatial Planning in collaboration Office of Sanitary and Health, and Office of Tourism) have actively involved in governing Climate-change adaptation and involved in the development of a strategy to integrate CCA into local government planning. | Information about RCBT regional climate Budget Tagging Mercy / Per-OPD (process) Note: OPD = Municipal Offices | involvement: • Municipal Development Agency • Municipal Environment Office • Municipal Public Works and Spatial Planning Office • Municipal Tourism, Culture, Youth and Culture Office • Municipal Trading and Small and Medium Enterprise Office • Municipal Health Office • Municipal Communication and Information Office • Municipal Agriculture and Food Office • Municipal Marine and Fishery Office | At least 5 municipal offices (Regional Development Planning-Bappeda, Office of Marine and Fisherie, Office of Environment, Public Work and Spatial Planning in collaboration Office of Sanitary and Health, and Office of Tourism)
Outcome 2.3 | Improved livelihoods and ecosystem resilience, as well as developed social behavioural changes in community through applied Climate Smart Initiative. Adoption and application of developed online technology systems in collaboration with local governments | • Poor adaptive capacities • Lack of mechanism for disseminating proven strategies to adapt to risks has led to relatively high fatality rates, disease incidence and food security, especially for vulnerable people (child, elderly and women-headed household) • High exposure to hazards can be considered as co-drivers of poverty and compounded social problems such as, disease, sanitation, food security issues. • Slow onset event such as sea level rise and droughts have affected the social well-being and cohesion of local communities and reduce their ability to cope climate change impacts. | Targeted in the third year of programme implementation
Output 2.3.1 | Established community-led climate network, that consists at least 30% of Women | Identify the village information system called Rumah Data (kind of information, manajemen, collecting data, etc) | not done yet
| Developed smart-phone based climate warning systems across 8 Kelurahan. |  | not done yet | 8 Kelurahan
Outcome 2.4 | The knowledge management network established in each target kelurahan that are actively engage and communicate with each other. | Lack of capacity of the local governments officer and related stakeholders to lead climate change adaptation and disaster risk reduction plan | not done yet | 4 knowledge management networks
Output 2.4.1 | Training and knowledge sharing conducted across 8 target kelurahan involving different community groups | Pekalongan City has initiated a climate change impact program called Kawasan Rumah Pangan Lestari/Pekarangan Pangan Lestari through its Office of Agriculture and Food and Program Kampung Iklim Climate Village Programme) through its Office of Environment | Initiation of a regular weekly discussion on Climate Change by one vocational high school (SMKN 1 Pekalongan) to educate raise awarenees of the students. This is the school's voluntary follow up from the SEMESTA movie screening | 3 times
Output 2.4.2 | Publications related to climate change adaptation produced by each group during the course of the project | Pekalongan City has not yet produced media that publishes issues on climate change. There are two films initiated by KEMITRAAN with SAVE PEKALONGAN Community in the previous programme with the title "Pekalongan 34cm" and "Ada Juang di tanah Tergenang" | not done yet | 8 Knowledge product, Advocacy materials
Output 2.4.3 | Knowledge management network established and consists at least of 5 different community groups in each target kelurahan (i.e youth group, women group, farmers and fishermen groups, local enterpreneurs, other marginalized group, and academician or urban planners) that are actively engage and communicate with each other. | Identification of potential groups and/or community organizations to be involved in the CCA Programme, with following results: 1. Apsara 2. Mapan 3. DFTF (Degayu For The Future) 4. Kencana Jaya 5. Pengurus Taman Cabe Sakura 6. LKK (Lembaga Kemasyarakatan Kelurahan) in each village 7. Save Pekalongan Community 8. University and High School 9. Youth Group | not done yet | 40 sharing knowledge network
Objective 3 | Climate change and adaptation context included in Central Java Province Development Plan (RPJMD/RKP) | - 2035 flood risk analysis report by Mercy Corp as reference - Program identification report data in the 2018-2023 Provincial Mid-term Development Plan (RPJM) as reference | Still in progress | RPJMD/RKP Province and Pekalongan Municipal
Outcome 3.1 | Increased capacity of local governments and key city stakeholders (at least 7 municipal offices) in developing climate risk assessments and utilize the results to develop local climate change adaptation action plans that are mainstreamed in the Provincial Development Plans with regards to gender equality (Environmental Office, Bappeda, Maritime and Fisheries Office, agriculture Office, public works Office, women empowerment, Health Office) | Lacking capacity of provincial government officer to put forward climate change adaptation issue in development plan as well as incapability to lead by example in mainstreaming the issue | targeted in the third year programme implementation | 7 municipal offices
Output 3.1.1 | Climate change adaptation action plan adopted and developed to RAD API documents and incorporated within annual work-plan or mid-term development plan at provincial level. | - Document of disaster management plan at kelurahan level by FPRB (Disaster Risk Reduction Forum) as reference. - Data adn information from the Municipal Mid-term Development Plan (RPJM) activities that intersect with climate change (Bappeda) - 2035 flood risk analysis report from Mercy Corp as reference - Program identification report data in the 2018-2023 Provincial Mid-term Development Plan (RPJM)  DPMPPA Program  PKH Program  KOTAKU Program  PAMSIMAS Program  BSPS Program (Program from the Government that is already running) | not done yet | 1 document of RAD API incorporated CC-Adaptation within annual work-plan or mid-term development plan at provincial level.
| Mainstreaming gender and marginalized groups adopted and developed to RAD API documents and incorporated within annual work-plan or mid-term development plan at province level |  | not done yet | 1 document on mainstreaming gender and marginalized group incorporated within RAD API and annual workplan or mid-term development plan at provincial level
Output 3.1.2 | At least, 5 provincial offices (Regional Development Planning (Bappeda), Office of Marine and Fisheries, Office of Environment, Public Work and Spatial Planning in collaboration Office of Sanitary and Health, and Office of Tourism) have actively involved in governing Climate-change adaptation and involved in the development of a strategy to integrate CCA into local government planning |  | not done yet | At least 5 provincial office (Regional Development Planning-Bappeda, Office of Marine and Fisherie, Office of Environment, Public Work and Spatial Planning in collaboration Office of Sanitary and Health, and Office of Tourism)
Objective 4 | Establishing knowledge management network between national and local government in climate adaptation context | 0 | still in progress | SIDIK is enhanced with local-based vulnarability indicator
| At least, one knowledge product is produced in each output | 0 | Still in progress to produce knowledge document about establishment climate working group (supported by PIAREA consoultant) | 5 knowledge products
Outcome 4.1 | SIDIK Handbook developed, introduced and disseminated to broader stakeholder at all governmental level (local, provincial and national) with input from multi-stakeholders (i.e civic society, local government, private sectors and national government) in the re-formulation of SIDIK indicators. | • SIDIK unable to appropriately and accurately assess the vulnerability and risk of coastal region • Adaptation programmes planned at ministry level (national level) often incompatible with the needs of adaptation actions at city/local level | will trgeted fot the third year programme implementation | 1 document
Introducing SIDIK as risk assessment tools for coastal area based on local experience at two ministries which include Ministry of Marine and Fisheries, and Ministry of Environment and Forestry
Two technical ministries on forestry and coastal management is actively involved in governing Climate Change Adaptation through SIDIK system.
Output 4.1.1 | Input from multi-stakeholders (i.e civic society, local government, private sectors and national government) in re-formulation of SIDIK indicators collected and integrated in the handbook. SIDIK as risk assessment tools for coastal area based on local experience at two ministries which include Ministry of Marine and Fisheries, and Ministry of Environment and Forestry introduced and disseminated | - 2035 flood risk analysis report from Mercy Corp as reference - Data and information from the 2018-2023 Provincial Mid-term Development Plan (RPJM), especially that relates to climate change | not done yet | 8 (workshops, FGDs) 1 handbook (7000 expl.)
Output 4.1.2 | Two technical ministries on forestry and coastal management respectively are actively involved in governing Climate Change Adaptation through SIDIK system. |  | not done yet | 2 technical ministries on forestry and coastal management
Objective 5 | The indicator of the objective include: 1. Group of capture fisheries are developed; 2. Urban farming introduced and applied by community; 3. Developed and improved community-based ecotourism; 4. Constructed integrated-waste management facility. | List of community groups have been obtained from the related Municipal Offices (i.e. for Urban Farming, batik industry and aqua/siloculture) within the 1st implementation year. Validation process based on vulnerability was conducted to the obtained list to identify the vulnerable groups/community. | still in progress | Established livelihood alternatives and circular economy.
Outcome 5.1 | At least 4 (four) sustainable livelihood are adopted and applied as climate change adaptation strategies by communities in each kelurahan through inclusive approach, by involving women and other marginalized group. The sustainable livelihood includes community fisheries at coastal areas, urban farming strategies, community-based ecotourism and integrated-waste management in communities. Institutionalization of circular economics to improve average income in each Kelurahan, both in normal seasonal condition and in the mid of increasing of climate change consequences (i.e. El-Nino, La-Nina, Long drought, or wet-dry seasons). Furthermore, decreasing the health problems and risk in 8 Kelurahan. | • Economic losses, physical infrastructure loss and also loss or disruption to livelihood options • Low cost-effectiveness of investments in the main productive sectors • Continuous decline in populations’ revenue • Poor adaptive capacities • Lack of mechanism for disseminating proven strategies to adapt to risks has led to relatively high fatality rates, disease incidence and food security, especially for vulnerable people (child, elderly and women-headed household) • High exposure to hazards can be considered as co-drivers of poverty and compounded social problems such as, disease, sanitation, food security issues. • Slow onset event such as sea level rise and droughts have affected the social well-being and cohesion of local communities and reduce their ability to cope climate change impacts. | trageted in second and third implementation year | 4 sustainable livelihood are adopted and applied as climate change adaptation strategies by communities
| Income or health level of beneficiaries of sustainable economic empowerment as well as improved water and sanitation facilities at the program location, Male = 1.394 persons or 60% Female = 697 persons or 30%, include women headed family Vulnerable = 232 persons or 10% |  | trageted in second and third implementation year | 2.324 beneficiaries of sustainable economic empowerment as well as improved water and sanitation facilities at the program location
Output 5.1.1 | Capture fisheries (number of group developed) developed and applied | - Identified aquaculture groups (Migunani, PKH, Pemuda Kramat Sari, Mina Mulya, Mandiri Jaya) - Pond data from office of Marine and Fishery | in the process to identify potential of aquaculture in target Kelurahan | 8 Kelurahan
Output 5.1.2 | Community-based ecotourism (number of group developed and improved) developed and/or improved There is a journal about livelihood women and vulnerable groups related lo climate change adaptation | Identification of existing land and mangrove species in the KelurahanKandang Panjang, Bandengan and Degayu |  | 8 Kelurahan 1 Journal
Output 5.1.3 | ecological batik using mangrove based colouring product applied and cultural economy improved | Identification of batik maker, especially in Pekalongan City within the prioritised Kelurahan Kandang Panjang, Krapyak and Pasir Kraton Kramat | in the process to identify potential of ecological batik in trget Kelurahan | 8 Kelurahan
Output 5.1.4 | urban farming introduced and applied by community (yields and number of plots applied urban farming) | Pekalongan City has initiated a climate change impact program called Kawasan Rumah Pangan Lestari/Pekarangan Pangan Lestari (Sustainable Food House/Sustainable Food Garden) through its Office of Agriculture and Food | in the process to identify urban farmindg potential in target Kelurahan | 8 Kelurahan
Output 5.1.5 | Integrated-waste management facility constructed and running | Identfication of existing TPS3R (Intermediary 3R Waste Processing Facility), TPA (landfill) and Bank Sampah (Waste Bank) in 8 target Kelurahan | in the process to identify waste management system and processing in target Kelurahan | 8 Kelurahan
Output 5.1.6 | Water and sanitation condition in 8 target kelurahan improved through construction of communal facilities | Identification of existing water and sanitation facility | in the process to identify sanitation facility in target Kelurahan | 24 Units

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | There is a change in coastal area city planning related to coastal protection buildings.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, because project need input about coastal protection buildings from stakeholders through FGDs and studies in coastal area Pekalongan city.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Make changes to the location and design of the coastal protection building
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, its still effective in avoiding unwanted negative impacts
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender issues are considered in identify beneficiaries, identify roles and decision making; e.g to establish the organizational structure of the climate change village working group, number of male and female members are equal
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 21-02
Implementing Entity | Kemitraan (The Partnership for Governance Reform)
Type of implementing entity | NIE
Country | Indonesia
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 109011 | 10477 | 98534 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50.2% | 30% | 20.3% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 24% | 10% | 14% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding |  | Total | 220 | Coastal flooding | 3: Moderately effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Coastal management | Local |  | 1 | Coastal management | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  |  |  | Coastal management |  | 50 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
[6 empty] | 1548 | 52% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
[6 empty] | 1 | Handbooks | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  |  |  | Coastal management |  | 3: Moderately effective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 6 | km rehabilitated |  | Mangroves | 3 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0%
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  | Aquaculture | 2164 | 30% | From 20% to 30% | Aquaculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
0
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 |  |  | 0 | 0 |  |  | 0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Coastal management | Local | Environmental policy | 3 | Coastal management | Local | Environment Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 |  |  |  | 1 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness