## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 26 Aug 2021-26 Aug 2022
| Project Title: | Climate Change Adaptation through small-scale and protective infrastructure interventions in the coastal settlements of Cambodia (CCA4CS)
| Project Summary: | The proposed project’s main objective is “to enhance climate change adaptation and resilience of the most vulnerable coastal human settlements of Cambodia through concrete adaptation actions, particularly in areas where eco-tourism has the potential to sustain such interventions”. It is structured around the following three components: Component 1: Community-scale knowledge and capacity enhanced to sustain the adaptation benefits of the project’s investments. Component 2: Government planning and technical capacity enhanced and knowledge captured and disseminated to sustain and enhance the project’s adaptation benefits. Component 3: Resilience built through investment in small-scale protective and basic service infrastructure and natural assets.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | KHM/MIE/Urban/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Human Settlements Programme (UN-Habitat) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cambodia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Kep Province and Prey Nob District of Preah Sihanouk Province along the coastal regions of Cambodia | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2021-01-26
IE-AFB Agreement Signature Date: |  | 2021-03-25 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-08-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2025-03-25
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception report - submitted on 26 August 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Vanna Sok | Dominican Republic
| Email: | vanna.sok@un.org | Ecuador
| Date: | 2021-01-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | H.E Tin Ponlok - Ministry of Environment (National Council for Sustainable Development) | Equatoral Guinea
| Email: | etap@online.com.kh | Eritrea
| Date: | 2021-07-14 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laxman Perera - UN-Habitat | Fiji
| Email: | laxman.perera@un.org | Finland
| Date: | 2021-01-01 | France
| Executing Agency |  | Gambia
| Name: | Mao Hak- National Council for Sustainable Development (NCSD) | Georgia
| Email: | maohakccd.se@gmail.com | Germany
| Date: | 2021-07-14 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [26 Aug 2022] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [26 Aug 2022] | 1064998 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | As per the signed agreement, the first installment of USD 1,064,998 was received from AF. Out of this, the amount of USD 901,176 is committed to Executing Entity (EE). The actual expenditure by 26 Aug 2022 to EE is USD 225,294 while USD 675882 has been already obligated to the EE. As some field activities have to be rescheduled due to COVID-19 travel restrictions , the expenditure is relatively lower. However it is expected to increase the expenditure within short period as activities are now under implementation. Therefore , it is anticipated that over 80% of the AOC value will be utilized within next two to four weeks |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | N/A |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Community capacity built to collect and manage solid waste | 48928
| Output 1.2: Communities in target areas have been trained on resilient house construction techniques | 36378
| Output 1.3: Communities have been organised to manage, monitor and maintain the infrastructure investments under Component 3 | 39602
| Output 2.1: Government officers at the provincial and districts/cities trained to plan effectively for sustaining and enhancing the project’s adaptation benefits | 35967
| Output 2.2: Government officers at the provincial and district provided with comprehensive technical training to manage, operate and maintain the infrastructure | 34601
| Output 2.3: Institutional systems strengthened to monitor adaptation investments and replicate their benefits | 24700
| Output 3.1: 134ha of Mangroves restored in Kep City and Angkaol Communes, Kep Province | 79000
| Output 3.3: Prevention of salt water ingress through improved channels | 29000
| Output 3.4: Bank strengthening work at Roness reservoir to provide additional water retention and safety | 348500
| Output 3.5: Resilient Housing designs developed and demonstrations constructed (both provinces) | 48500
| Output 3.6: Green-grey protective infrastructure in Ou Ohkna Heng Commune, P. Sihanouk Province | 96000
| Output 3.7: Drainage and Rainwater Harvesting installed at Veal Rinh Market, P. Sihanouk Province | 80000
| PROJECT EXECUTION COST | 94151
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 69671
| TOTAL | 1064998 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Community capacity built to collect and manage solid waste | 52467 | Apr-Jun 2023
| Output 1.2: Communities in target areas have been trained on resilient house construction techniques | 46617 | Apr-Jun 2023
| Output 1.3: Communities have been organised to manage, monitor and maintain the infrastructure investments under Component 3 | 51167 | Jul-Sep 2023
| Output 2.1: Government officers at the provincial and districts/cities trained to plan effectively for sustaining and enhancing the project’s adaptation benefits | 39717 | Apr-Jun 2023
| Output 2.2: Government officers at the provincial and district provided with comprehensive technical training to manage, operate and maintain the infrastructure | 50048 | Jul-Sep 2023
| Output 2.3: Institutional systems strengthened to monitor adaptation investments and replicate their benefits | 38278 | Jan-Apr 2023
| Output 2.4: Knowledge from the project implementation is captured and disseminated to local and national stakeholders, focusing on sustainable adaptation actions and policy enhancement | 17089 | Jan-Apr 2023
| Output 3.1: 134ha of Mangroves restored in Kep City and Angkaol Communes, Kep Province | 160000 | Jul-Sep 2023
| Output 3.2: (a) Water gates repaired in 3 locations in Pong Teuk and Angkaol; (b) Canals Rehabilitated in Pong Teuk and Angkaol Communes | 30341 | Apr-Jun 2023
| Output 3.3: Prevention of salt water ingress through improved channels | 150000 | Jul-Sep 2023
| Output 3.4: Bank strengthening work at Roness reservoir to provide additional water retention and safety | 550000 | Jul-Sep 2023
| Output 3.5: Resilient Housing designs developed and demonstrations constructed (both provinces) | 50000 | Apr-Jun 2023
| Output 3.6: Green-grey protective infrastructure in Ou Ohkna Heng Commune, P. Sihanouk Province | 100000 | Jul-Sep 2023
| Output 3.7: Drainage and Rainwater Harvesting installed at Veal Rinh Market, P. Sihanouk Province | 250000 | Jul-Sep 2023
| ESP Compliance | 60000 | Jul-Sep 2023
| PROJECT EXECUTION COST | 123150 | Jan-Sep 2023
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 79223 | Jan-Sep 2023
| TOTAL | 1848097 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental/ social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities Impact: 3 Prob: 2 | Low | -Not applicable as the infrastructure construction is not started in Ythe reporting period
Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. Impact: 4 Prob: 1 | Low | - Establishment of a project management committee for enhance government support for project implementation. - UN-Habitat has signed legal agreements (MoUs and AoCs) with the NCSD to ensure that the executing partner to deliver project activities and outputs as planned . - Assigneent of dedicated staff for the project by NSCD
Institutional: Capacity constraints of local institutions may limit the effective implementation of interventions Impact: 2 Prob: 1 (1: low - 5 : high) | Medium | Training needs assessment was conducted and training materials were developed during reporting period
Institutional/social: Lack of commitment/buy-in from local communities may result in delay at intervention sites. Impact: 2 Prob: 1 (1: low - 5 : high) | Medium | Community stakeholders were infomred of the project.
Institutional/social: Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. Impact: 3 Prob: 2 (1: low - 5 : high) | Low | Site confirmations has been obtained with the consultations with local communities and provincial/district/municipal/commune/Sangkat government officials.
Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance Impact: 2 Prob: 2 (1: low - 5 : high) | Medium | Communities were identified for capacity building and training to improve their awareness and understanding of the benefits of the activities, including infrastructure maintenance (Component 1).
Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity Impact: 3 Prob: 2 (1: low - 5 : high) | Medium | Financial management arrangements have been defined with EA - Standard of Operation, procurement and recruitment framework have been completed by the NCSD as signed Agreement of Cooperation.
Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions Impact: 1 Prob: 2 (1: low - 5 : high) | Medium | -N/A
Institutional: A lack of coordination between and within national government Ministries and Departments. Impact: 1 Prob:2 (1: low - 5 : high) | Low | The Project Management Committee (PMC) has been established under the leadership of NCSD (EA) to ensure coordination and UN-Habitat as secreteriat to observe coordination problems and to resolve issues directly with concerned parties and or the PMC.
Legal: Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues. Impact 4 Prob 1 (1: low - 5 : high) | Low | N/A
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
State administration process: EE internal procedure to request for permission to sign on AoC needs a lot of clarification and takes time, affecting the start of the implemention. Level of impact: 4 (1: low - 5 : high) | High | The request for permission to sign on AoC took longer. Speeded up through continous follow ups resulted in signing the AoC with EA
Financial: Delay of grant transfer to the implementing partner is highly affecting the implementation of project's committed activities. Level of impact: 3 (1: low - 5 : high) | Medium | Grant transfer ( 1st installment ) was effectve. 2nd installment is pending due to the PPR approval process.
Covid-19 Pandemic: Cambodia witnessed community outbreak of Covid-19 in February 2021 that the Government has put in place travel restrictions, social distancing and restrictions of people gathering. Level of impact: 3 (1: low - 5 : high) | Medium | Followed all national and UN Guidelines on COVID 19 during gthe reproting period. That resulted some significant delayes such as stakeholder meetings, particulalry wit hthe communties.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law | [7 empty] | No residual impact | No remedial action required
2 - Access and equity |  |  | Activities could lead to preferential access to training (3.5) or denial of services (3.7) for some people if management and/or mitigation measures are not taken. | N/A | - Output 3.5: Register/list of trainees. Training needs assessment/trainee identification exercise completed. - Output 3.7: Surveys with market traders before and after construction completed. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement | - Output 3.5: Women are excluded from education and training opportunities and then earn less as a consequence. - Output 3.7: Some market traders may lose more income than others effectively because of where they are located in the market. | N/A - The measures for this ESP principle under output 3.5 and 3.7 are expected to start implementing in the 2nd year of the project implementation. | Activities could lead to preferential access to training (3.5) or denial of services (3.7) for some people if management and/or mitigation measures are not taken. | Output 3.5: Register/list of trainees. Training needs assessment/trainee identification exercise will be completed. - Output 3.7: Surveys with market traders before and after construction to be completed. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement ( commencing in year 2)
3 – Marginalized and vulnerable Groups |  |  | - There is some risk in terms of access and equity in investments 3.5 and 3.7. - This particularly relates to people living below the poverty line. | N/A | - Output 3.5: Identification of the poorest, most vulnerable and most in-need people using the ID Poor programme. Also captured through the training needs assessment/trainee identification exercise, as above.This could be captured through the training needs assessment/trainee identification exercise. - Output 3.7: Surveys with market traders before and after construction completed. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement. | - Output 3.5: There is a possibility that people could be excluded from the housing investment activity in Investment 3.5 based on poverty. - Output 3.7: The market traders would have a substantial impact on the local economy and the incomes of local, low-income people. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | Activities could lead to preferential access to training (3.5) or denial of services (3.7) for some people particularly relates to people living below the poverty line, if management and/or mitigation measures are not taken. | extra training sessions would be organized for individulas who will not be able to attened the traning Attemps will be made to minimize the residual impact ( in up coming reporting period). For example, devloping a list of trainings for cpacity building and assessments
4 – Human rights |  |  | - Human rights risks relate primarily to land rights, and are discussed in involuntary resettlement, below. | N/A | - Output 3.3: Regular (at least quarterly) site visits documented by photographs and, where necessary, informal discussions. At least 6-monthly meeting between the project (represented by the M&E officer), PDoWRAM and PDLMUPC conducted . - Output 3.4: Regular (at least quarterly) site visits documented by photographs and, where necessary, informal discussions conducted. At least 6-monthly meeting between the project (represented by the M&E officer), PDoWRAM and PDLMUPC condcuted . If evidence of encroachment is found during the construction period, additional monitoring measures will be proposed to the PMC. - Output 3.7 : As Access and Equity plus a survey of foot traffic into the market to ensure that there has not been a decline in the number of people using it (a proxy for ensuring that there has been no loss of income). | -Human rights issues mainly present themselves in terms of involuntary resettlement, core labour rights and gender equality. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | Human rights risks relate primarily to land rights, and are discussed in involuntary resettlement, below. | Output 3.3 and 3.4 : Regular site visits documented by photographs and, where necessary, informal discussions. At least 6-monthly meeting between the project (represented by the M&E officer), PDoWRAM and PDLMUPC conducted . - Output 3.7 : As Access and Equity plus a survey of foot traffic into the market to ensure that there has not been a decline in the number of people using it (a proxy for ensuring that there has been no loss of income). continously monitoring on human rights impacts
5 – Gender equality and women’s empowerment |  |  | - As identified in the gender assessment, compared with some other least developed countries, women in Cambodia face comparatively little discrimination including many indicators of socio-economic development, such as literacy, remain lower for women. - There is therefore a risk across the project that women are not included in the project, and as such their potential to benefit is reduced. Women are the primary beneficiaries in investment 3.7. | N/A | - Output 3.5: Register/list of trainees. Training needs assessment/trainee identification exercise completed. - Output 3.7: Surveys with market traders before and after construction completed. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement. | - Output 3.5: Without proactive measures to include and ensure women’s participation, services will tend to be oriented towards men and benefit them disproportionately (if we assume agricultural extension services are comparable with architectural training). - Output 3.7: There is a potential impact which could cause a loss of income to market traders, who are primarily women. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | Women in Cambodia face comparatively little discrimination including many indicators of socio-economic development, such as literacy, remain lower for women. - There is therefore a risk across the project that women are not included in the project, and as such their potential to benefit is reduced. Women are the primary beneficiaries in investment | Output 3.5: Register/list of trainees. Training needs assessment/trainee identification exercise to be completed. - Output 3.7: Surveys with market traders before and after construction completed. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement.
6 – Core labour rights |  |  | - The project will use unskilled and semi-skilled labour sourced from the communities for the planting and construction works that will take place in investments 3.1, 3.2, 3.3, 3.4, 3.6, and 3.7. - Without management and mitigation measures, there is a risk that these labourers could be mistreated. This includes low salaries below minimum wage or market rate, hiring school-age workers, discrimination against women, poor facilities, lack of safety equipment and informality. | N/A | - Output 3.1, output 3.2, output 3.3, output 3.4, output 3.5, output 3.6, output 3.7: Example contracts (personal details redacted) made available and comments invited from ILO representatives and the Ministry of Labour. Worker testimony gained through informal discussions. | -There is a risk to people working on construction and planting activities under the project. This risk must be seen in the context of fairly high rates of informality in unskilled and semi-skilled work in Cambodia. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | The project will use unskilled and semi-skilled labour sourced from the communities for the planting and construction works that will take place in investments 3.1, 3.2, 3.3, 3.4, 3.6, and 3.7. - Without management and mitigation measures, there is a risk that these labourers could be mistreated. This includes low salaries below minimum wage or market rate, hiring school-age workers, discrimination against women, poor facilities, lack of safety equipment and informality. | Outputs 3.1, 3.2, 3.3, 3.4, 3.5, 3.6, 3.7: contracts (personal details redacted) made available and comments invited from ILO representatives and the Ministry of Labour. Worker testimony gained through informal discussions.
7 – Indigenous peoples | [7 empty] | N/A | N/A
8 – Involuntary resettlement |  |  | - This risk has been identified for all physical components of the project, with the exception of 3.8. - While all target sites have been evaluated, most recently in November 2019 and it has been concluded that no one is living at the site or making a livelihood from it. Moreover, all investments are being made entirely on public land, and all site access is possible by public road, with the exception of investment 3.3. - Investment 3.3 includes the provision to build a temporary access track, which will be cited entirely on public land. At present, this land is not occupied, but the situation can change rapidly in Cambodia. - However, this risk has been triggered acknowledging that Cambodia has experienced involuntary resettlement in the past throughout the country, and the rapid nature of development in the country, including investment in nearby Sihanoukville, means that UN-Habitat can’t be certain at this moment that there won’t be informal settlers on the sites between now and project commencement. | N/A | - Output 3.1, output 3.2, output 3.3, output 3.6 : Regular (at least quarterly) site visits documented by photographs and, where necessary, informal discussions. At least 6-monthly meeting between the project (represented by the M&E officer), PDoE and PDLMUPC conducted - Output 3.4: Regular (at least quarterly) site visits documented by photographs and, where necessary, informal discussions. At least 6-monthly meeting between the project (represented by the M&E officer), PDoWRAM and PDLMUPC conducted . If evidence of encroachment is found during the construction period, additional monitoring measures will be proposed to the PMC. - Output 3.7: Surveys with market traders before and after construction. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement. Plus a survey of foot traffic into the market to ensure that there has not been a decline in the number of people using it (a proxy for ensuring that there has been no loss of income). | - Output 3.1,output 3.4, and output 3.6 : There is some evidence for historical (illegal, and failed) attempts at agriculture at the mangrove (3.1, 3.6) and Roness (3.4) sites. - Output 3.2, output 3.3: There are potential risk that people are living along the canals. - Output 3.7: Temporary eviction or inability to access the market to trade could lead to serious economic, loss of income impacts for local people without management or mitigation measures. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | This risk has been identified for all physical components of the project, with the exception of 3.8. - While all target sites have been evaluated, most recently in November 2019 and it has been concluded that no one is living at the site or making a livelihood from it. Moreover, all investments are being made entirely on public land, and all site access is possible by public road, with the exception of investment 3.3. - Investment 3.3 includes the provision to build a temporary access track, which will be cited entirely on public land. At present, this land is not occupied, but the situation can change rapidly in Cambodia. - However, this risk has been triggered acknowledging that Cambodia has experienced involuntary resettlement in the past throughout the country, and the rapid nature of development in the country, including investment in nearby Sihanoukville, means that UN-Habitat can’t be certain at this moment that there won’t be informal settlers on the sites between now and project commencement. | - Outputs 3.1, 3.2, 3.3, 3.6 : Regular (at least quarterly) site visits documented by photographs and, where necessary, informal discussions. At least 6-monthly meeting between the project (represented by the M&E officer), PDoE and PDLMUPC will be conducted -- Output 3.7: Surveys with market traders before and after construction. This will include discussing the construction plans (i.e. specific procedures to ensure continued trading) with the traders for their suggestion and agreement. Plus a survey of foot traffic into the market to ensure that there has not been a decline in the number of people using it (a proxy for ensuring that there has been no loss of income).
9 – Protection of natural habitats |  |  | - Investments 3.1, 3.2, 3.3, 3.4, 3.6 and 3.8 take place in or near critical habitats. - Investments under 3.1 inherently involve mangrove areas. - Investments 3.2, 3.3 and 3.4 are in peri-urban or rural areas at the edge of Kep. - 3.6 and 3.8 are located close of the Kampong Smach protected area. - With this proximity in mind, there is potential for disruption of habitats through construction activities, transporting materials to and from the sites and the presence of casual labour. Investment 3.1 also carries risks – while the investment is intended to benefit the natural habitat, there is a risk, without management or mitigation measures that the investment could be counterproductive and damage the mangrove it is designed to help. For example, without a mangrove planting and management plan, there is a risk that invasive or incompatible species could be introduced to the area, risking both project failure and existing mangroves. | Under Output 3.1: Mangrove Planting and Management Plan has been established in consultation with local communities and provincial/district/municipal government officials ensuring no negative impact of the actions. - | - Output 3.1, output 3.6: Mangrove Planting and Management Plan in place before planting starts. The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.2, output 3.3: Weekly report by the site manager. Pre and post construction site inspection by the M&E officer submitted. - Output 3.4: Site manager’s weekly report and periodic inspection by the Project M&E Officer submitted. - Output 3.8: Pre and post installation inspection by the Project M&E Officer. | - Output 3.1, ouput 3.6: Mangrove forests have been in alarming decline in Cambodia in recent years. The country lost 42 per cent of its mangroves in the period 1989-2017. Mangrove loss has been especially high in Preah Sihanouk Province, where 52 per cent of forests have been lost. 34 per cent have been lost in Kep in the same period. - Output 3.2, output 3.3: There are risks arising from ineffective oversight of development activities and thus local impacts arising from damage to or loss of local habitats. - Output 3.4: The non-demarcated area of natural habitat immediately to the north of the reservoir is a particular area of potential impact to the reservoir. - Output 3.8: There is potential disruption of the local environment in installing equipment | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | Investments 3.1, 3.2, 3.3, 3.4, 3.6 and 3.8 take place in or near critical habitats. - Investments under 3.1 inherently involve mangrove areas. - Investments 3.2, 3.3 and 3.4 are in peri-urban or rural areas at the edge of Kep. - 3.6 and 3.8 are located close of the Kampong Smach protected area. - With this proximity in mind, there is potential for disruption of habitats through construction activities, transporting materials to and from the sites and the presence of casual labour. Investment 3.1 also carries risks – while the investment is intended to benefit the natural habitat, there is a risk, without management or mitigation measures that the investment could be counterproductive and damage the mangrove it is designed to help. For example, without a mangrove planting and management plan, there is a risk that invasive or incompatible species could be introduced to the area, risking both project failure and existing mangroves. | Output 3.1, 3.6: Mangrove Planting and Management Plan in place before planting starts. The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.2, 3.3: Weekly report by the site manager. Pre and post construction site inspection by the M&E officer submitted. - Output 3.4: Site manager’s weekly report and periodic inspection by the Project M&E Officer submitted. - Output 3.8: Pre and post installation inspection by the Project M&E Officer. .
10 – Conservation of biological diversity |  |  | See above. In particular, 3.1, 3.6 and 3.8 are in areas that are important for biodiversity (though note that none of the project is implemented in an officially designated biodiversity conservation area). Investments 3.1, 3.6 and 3.8 are implemented in or close to mangrove areas, and as such this ecosystem is critical to support marine biology as well as coastal human livelihoods (particularly crab fishing, which is a common form of livelihood, especially in Kep) | Under Output 3.1: Mangrove Planting and Management Plan has been established in consultation with local communities and provincial/district/municipal government officials ensuring no negative impact of the actions. - | - Output 3.1: Mangrove Planting and Management Plan in place before planting starts. The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.4: Site manager’s weekly report and periodic inspection by the Project M&E Officer submitted . - Output 3.6: Mangrove Planting and Management Plan in place before planting starts. The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.8: Pre and post installation inspection by the Project M&E Officer conducted . | Output 3.1: The Mangrove Planting and Management Plan will ensure that appropriate mangrove species will be chosen, planted correctly and management and maintained in a way that ensures they have a long lifespan. This is critical as mangrove is only effective as a coastal adaptation measure. - Output 3.4: The works will enhance the ability of the reservoir to store and distribute water, improving water access in the dry season (which is projected to be longer and warmer). Moreover, as the southern embankment has been classified as unsafe by two international engineers who inspected, the works proposed under this project also have a safety benefit as full or partial failure of the southern embankment would – at minimum – flood surrounding farmland, damage houses and damage the nearby railway line. - Output 3.6: The mangroves will also be planted in accordance with a to-be developed mangrove planting and management plan (see 3.1 – though a separate, location specific plan will be developed). The water gate repairs will restore water management to original design standards (together with mangroves they will enhance adaptation). - Ouput 3.8: The weather station and tide gauge will be imported, but no emissions are generated from their operation. Regional suppliers for the equipment will be sought, but it may not be possible to avoid importing equipment from North America or Europe. | - The Mangrove Planting and Management Plan has been developed awaiting the approval from PMC. -The other measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | In particular, 3.1, 3.6 and 3.8 are in areas that are important for biodiversity (though note that none of the project is implemented in an officially designated biodiversity conservation area). Investments 3.1, 3.6 and 3.8 are implemented in or close to mangrove areas, and as such this ecosystem is critical to support marine biology as well as coastal human livelihoods (particularly crab fishing, which is a common form of livelihood, especially in Kep) | Output 3.1: Mangrove Planting and Management Plan in place before planting starts. The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.4: Site manager’s weekly report and periodic inspection by the Project M&E Officer submitted . - Output 3.6: Mangrove Planting and Management Plan in place before planting starts. The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.8: Pre and post installation inspection by the Project M&E Officer conducted .
11 – Climate change |  |  | Maladaptation risks occur throughout the project. | N/A | 3.5, 3.8 Bidding/tender documents must explicitly identify sources of wood and other construction materials and explain why such materials are sustainable options are being chosen. |  |  | Maladaptation risks occur throughout the project. | 3.5, 3.8 Bidding/tender documents must explicitly identify sources of wood and other construction materials and explain why such materials are sustainable options are being chosen.
12 – Pollution prevention and resource efficiency |  |  | There are some small risks arising from the construction. With the exception of 3.1, all investments under Component 3 involve construction using common building materials, such as concrete and building sand/fill material. Without management and mitigation measures, there is a risk of small-scale, localized pollution in and around the construction sites. This risk is exacerbated by the solid waste management system in Cambodia being imperfect in its coverage. No construction will involve hazardous materials such as chemicals other than basic paints (for painting water gates, for example). | N/A | - Output 3.2, output 3.3, output 3.4, output 3.5, output 3.6, output 3.7 : Weekly report by the site manager submitetd . Pre and post construction site inspection by the M&E officer (merged with Protection of Natural Habitats) conducted | - Output 3.2, output 3.3, output 3.4, output 3.5, output 3.6, output 3.7: All investments will generate waste materials resulting from the construction. None of the investments will generate significant waste products or pollutants from their ongoing use/operation. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | There are some small risks arising from the construction. With the exception of 3.1, all investments under Component 3 involve construction using common building materials, such as concrete and building sand/fill material. Without management and mitigation measures, there is a risk of small-scale, localized pollution in and around the construction sites. This risk is exacerbated by the solid waste management system in Cambodia being imperfect in its coverage. No construction will involve hazardous materials such as chemicals other than basic paints (for painting water gates, for example). | Output 3.2, output 3.3, output 3.4, output 3.5, output 3.6, output 3.7 : Weekly report by the site manager to be submitetd . Pre and post construction site inspection by the M&E officer (merged with Protection of Natural Habitats) to be conducted
13 – Public health |  |  | There are some localised to risks to public health arising from the project. In all investments, except 3.1 and 3.8 involve creating a temporary construction site during implementation. This carries typical construction site risks (i.e. risks from vehicles entering and leaving the site, risk to children, etc). Sites that involve embankments – investments 3.3 and 3.4 – and the retention of water carry a risk throughout the lifespan of the infrastructure (i.e. during the project and beyond). If the embankment were to fail, there could be outflow of substantial amounts of water (especially Investment 3.4). Management and mitigation measures are required. Sites that involve water gates (3.2a&b, 3.6) also carry small health and safety risks throughout the lifespan of the infrastructure, particularly relating to broken parts or accidental misuse. Investment 3.7 involves construction works in a large market that is busy (at any point in the day there are hundreds of people working or shopping in it) and sells food products including meat, fish and vegetables. Without management and mitigation measures, there is a risk that construction works would pose a health hazard to people shopping or working in the market, and of food contamination. | N/A | - Output 3.2, output 3.3, output 3.4, output 3.5, output 3.6, output 3.7 : Training completed prior to construction starting. All signs, fences and other safety equipment are in place, as signed off by the site manager and M&E Officer. Weekly site reports by the site manager and inspection by the M&E Officer submitted | - Output 3.2, ouput 3.6: The investments involve relatively small construction sites with no heavy equipment beyond cement mixers and basic construction tools. - Output 3.3, output 3.4, output 3.7: The investments involve larger sites with larger, more complex equipment. | N/A The measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | There are some localised to risks to public health arising from the project. In all investments, except 3.1 and 3.8 involve creating a temporary construction site during implementation. This carries typical construction site risks (i.e. risks from vehicles entering and leaving the site, risk to children, etc). Sites that involve embankments – investments 3.3 and 3.4 – and the retention of water carry a risk throughout the lifespan of the infrastructure (i.e. during the project and beyond). If the embankment were to fail, there could be outflow of substantial amounts of water (especially Investment 3.4). Management and mitigation measures are required. Sites that involve water gates (3.2a&b, 3.6) also carry small health and safety risks throughout the lifespan of the infrastructure, particularly relating to broken parts or accidental misuse. Investment 3.7 involves construction works in a large market that is busy (at any point in the day there are hundreds of people working or shopping in it) and sells food products including meat, fish and vegetables. Without management and mitigation measures, there is a risk that construction works would pose a health hazard to people shopping or working in the market, and of food contamination. | Output 3.2, output 3.3, output 3.4, output 3.5, output 3.6, output 3.7 : Training to be completed prior to construction starting. All signs, fences and other safety equipment are in place, as signed off by the site manager and M&E Officer. Weekly site reports by the site manager and inspection by the M&E Officer to be submitted
14 – Physical and cultural heritage | [7 empty] | N/A | N/A
15 – Lands and soil conservation |  |  | There is some negligible risk to land and soil conservation. Investments 3.1 and 3.6 involve mangroves, the planting of which involves disturbing soil. Investments 3.3 and 3.4 involve using embankment fill material, which will be procured on the open market. Investment 3.3 involves creating a temporary access track on public land, which nevertheless will disturb soils. For those reasons, this risk has been triggered. | Under Output 3.1: Mangrove Planting and Management Plan has been established in consultation with local communities and provincial/district/municipal government officials ensuring no negative impact of the actions. - | - Output 3.1, output 3.6 : Mangrove Planting and Management Plan is in place before planting starts.The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.3, output 3.4, : Weekly report by the site manager. Pre and post construction site inspection by the M&E officer submitted . | - Output 3.1, ouput 3.6: Mangrove forests have been in alarming decline in Cambodia in recent years. The country lost 42 per cent of its mangroves in the period 1989-2017. Mangrove loss has been especially high in Preah Sihanouk Province, where 52 per cent of forests have been lost. 34 per cent have been lost in Kep in the same period. - Output 3.3: There are risks arising from ineffective oversight of development activities and thus local impacts arising from damage to or loss of local habitats. - Output 3.4: The non-demarcated area of natural habitat immediately to the north of the reservoir is a particular area of potential impact to the reservoir. | - The Mangrove Planting and Management Plan has been developed awaiting the approval from PMC. - The other measures for this ESP principle are expected to start implementing in the 2nd year of the project implementation | There is some negligible risk to land and soil conservation. Investments 3.1 and 3.6 involve mangroves, the planting of which involves disturbing soil. Investments 3.3 and 3.4 involve using embankment fill material, which will be procured on the open market. Investment 3.3 involves creating a temporary access track on public land, which nevertheless will disturb soils. For those reasons, this risk has been triggered. | Output 3.1, output 3.6 : Mangrove Planting and Management Plan is in place before planting starts.The Plan has been approved by the Project Management Committee and is subject to annual technical review. - Output 3.3, output 3.4, : Weekly report by the site manager. Pre and post construction site inspection by the M&E officer submitted .
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No,
Have unanticipated ESP risks been identified during the reporting period? |  | No,
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Since the inception workshop (26 Aug. 20201), UN-Habitat has supported implementing partners (NCSD) to establish PMC and Project Team. Under supervision of PMC, and collaboration with Project Team in target provinces, UN-habitat and NCSD, aim to conduct technical monitoring and supervision to implementing the project's activities, especially monitoring the identified and unanticipated ESP risks. The technical officers will be recruited in the second year. They will support to directly monitor the on-site activities.
Have the implementation arrangements been effective during the reporting period? |  | The current implementation arrangement has been effective to push the project moving forward. Planned activities of the 1st year are either delivered or on-going.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | PMC and Project Team in target provinces were established monitor the ESP safeguard measures.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | PMC nad project team have been built with members from NCSD, various ministries, provincial departments, and sub-nationals in target provinces. PMC and project team has funtioned well in both project management and techincal supervision. The field offices and techincal officers will be hired and arranged in the second year for the on-site activity implementation.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There is no grievance received during the first year project implementation
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework has gender-responsive indicators for some key outcomes and outputs.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Component 1 - Community-scale knowledge and capacity enhanced to sustain the adaptation benefits of the project’s investments | Output 1.1. | No. of female training beneficiaries | 0 | 50% of trainees are women | Good, gender equality has been integrated in all capacity building activities planned for the 1st year implementation
| Output 1.2. | No. of female beneficiaries | 0 | 200 people 50% of whom women trained | Poor, this output is related with carpenters in construction sector. This kind of career is not common for women.
| Output 1.3. | No. of women trained | 0 | 50% of the eventual total are female. | Good, gender equality has been integrated in all capacity building activities planned for the 1st year implementation
Component 2 - Government planning and technical capacity enhanced and knowledge captured and disseminated to sustain and enhance the project’s adaptation benefits | Output 2.1. | No. of government staff trained disaggregated by sex | 0 | 60 government officers trained, at least 20 of whom are women | Good, gender equality has been integrated in all capacity building activities planned for the 1st year implementation
| Output 2.2. | No. of female government staff trained | 0 | 25 government officers trained, at least 10 of whom women | Good, gender equality has been integrated in all capacity building activities planned for the 1st year implementation
| Output 2.3. | No. of monitoring systems in place | 0 | A system in place to systematically monitor adaptation investments and plan and advocate for replication, upscaling and further funding | Good, gender disparities between men and women are considered in institutional review planned for the 1st year implementation
| Output 2.4. | No of knowledge products produced and estimated number of people reached | 0 | At least 20 local good practice documents (which could include local language articles, radio broadcasts or brochures) and 3 major policy recommendations. At least 3 of the knowledge products will focus specifically on the adaptation priorities and actions of women. At least 100,000 people reached with knowledge products. | N/A (the activities of the this output were designed for the 2nd year project's implementation)
Component 3- Resilience built through investment in small-scale protective and basic service infrastructure and natural assets | Output 3.1. | No. of people who benefit from the restored mangrove, disaggregated by sex | 0 | This land and 17,754 people, at least 50% of whom are women have greater protection from coastal flooding, erosion and salt-water incursion. There will be $600 benefit to fishermen per hectare of mangrove planted | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.2. | No. of people who benefit from the repaired water gates and rehabilitated canals, disaggregated by sex | 0 | 1960ha of paddy with greater water access. Increased rice yield for agricultural families, and water access for non-agri families A total of 19,553 people, at least 50% are women, benefit | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.3. | No. of people who benefit from the rehabilitated canals | 0 | 3,500 people, at least 50% of whom are women will benefit | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.4. | No. of people who have improved access to water No. of ha land protected | 0 | 24,470 people, of whom 50% are women, will have year-round access to water even during especially dry years, 600ha of rice paddy will be irrigated. People will be protected from the unsafe embankment | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.5. | No. of locally appropriate housing designs developed No. of demo houses constructed | 0 | 9,720 people, of whom, 50% are women, benefit from design, training and 4 demo houses built | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.6. | No of people whose land is protected from saltwater incursion, disaggregated by sex No. of ha of land protected | 0 | 20,000 people, of whom 50% women, in the area (of a total population of 27,667) and 2,000ha of rice fields protected | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.7. | The number of days’ income lost to flooding events | 0 | The market retains 365 day per year functionality, not losing any days to heavy rainfall. The market has access to harvested rainwater 4,500 people, up to 90% of whom are women, have improved year-round income | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
| Output 3.8. | No. of people who have improved access to tidal information and early warning, disaggregated by sex | 0 | An estimated 30,000 people, of whom, 50% are women have access to early warnings. Tidal information is also available to the local government and beneficiaries in the coastal area. | N/A (the activities of the component 3 were designed for the 2nd year project's implementation)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | PMC with support from UN-Habitat has planned for mainstreaming gender equality in the first year project's capacity building activities ensuring at least 40% of women access and participate in capacity building events.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, the participation of women has been encouraged and recorded in events organized by the project. The planned activities have included gender equality targets.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | - NCSD has established PMC with 1/11 female members. Similarly, the Project Team has been established with 2/18 female experts in different technical areas. - NCSD is well aware of gender equality and prioritize gender integration in the project's activities and implementation. They with support from UN-Habitat have led the PMC to commit gender-sensitive and gender-responsive activities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes, with the leadership by NCSD, gender equality and gender integration have been practiced by consultants in the first-year capacity building activities. It is expected that the 2nd year on-site activities will be more gender sensitive and gender responsive.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Gender bias as well as gender needs in the project sites have not been well understood to support gender integration planning for the 2nd year activities. It is planned that a gender assessment will be conducted in the targeted provinces. Findings will help to integrate gender in developed technical guidelines and training materials for risk/vulnerability assessment, climate change mainstreaming in development plans.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There is no grievance received during the first year project implementation
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: UN-Habitat Cambodia Office | Outcome 1 Community-scale knowledge and capacity enhanced to sustain the adaptation benefits of the project’s investments |  | Outcome 3 | - All trainees defined by month 6 - All baseline knowledge/training needs assessments completed by month 12 - All training materials prepared by month 15 |  | - All trainees were defined - All basedline knowleddge/training needs assessments were completed - All training materials were drafted and finalized | S
| Outcome 2 Government planning and technical capacity enhanced to sustain and enhance the project’s adaptation benefits |  | Outcome 2 | - All trainees defined by month 6 - All baseline knowledge/training needs assessments completed by month 12 - All training materials prepared by month 15 - Institutional review complete by month 12 |  | - All trainees defined - All baseline knowledge/training needs assessments completed - All training materials prepared - Institutional review complete All trainees defined | S
| Outcome 3 Resilience built through investment in small-scale protective and basic service infrastructure and natural assets |  | Outcome 4 | Output 3.1 - MPMP complete and approved (month 9) - Plantation underway (Month 12) Output 3.3 - ESS reconfirmation complete by month 9 Output 3.4 - UXO clearance report complete by month 6 Output 3.5 - Detailed designs complete by month 12 Output 3.7 - Re-consultations complete by month 9 - Works underway by month 12 |  | Output 3.1 - MPMP complete and approved (month 9) - Plantation underway (Month 12) Output 3.3 - ESS reconfirmation complete by month 9 Output 3.4 - UXO clearance report complete by month 6 Output 3.5 - Detailed designs complete by month 12 Output 3.7 - Re-consultations complete by month 9 - Works underway by month 12 | MS
Outcome 5
Outcome 6
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Vanna Sok
| Email: | vanna.sok@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
UN-Habitat Cambodia office has recruited a project assistant to coordinate the project's activties in collaboration with the executing entity. The exchange communication between project team members remains effective, transparent, frequent and organized to ensure all the activities planned in the 1st year are well managed and controled. UH-Habitat provides timely technical advices and inputs to works faciliated by the executing entity as well as provide managerial support to activties they manage and coordinate. UN-Habitat requests the executing entity to plan with care for all activities that they will implement and update their progress regulary. Any issue unfavorable to the activity implementation will be discussed and solutions are then identified.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: NCSD | Outcome 1 Community-scale knowledge and capacity enhanced to sustain the adaptation benefits of the project’s investments |  | Outcome 3 | - All trainees defined by month 6 - All baseline knowledge/training needs assessments completed by month 12 |  | - All trainees were defined - All basedline knowleddge/training needs assessments were completed - All training materials were drafted and finalized | S
| Outcome 2 Government planning and technical capacity enhanced to sustain and enhance the project’s adaptation benefits |  | Outcome 2 | - All trainees defined by month 6 - All baseline knowledge/training needs assessments completed by month 12 - Institutional review complete by month 12 |  | - All trainees defined - All baseline knowledge/training needs assessments completed - All training materials prepared - Institutional review complete All trainees defined | S
| Outcome 3 Resilience built through investment in small-scale protective and basic service infrastructure and natural assets |  | Outcome 4 | Output 3.1 - MPMP complete and approved (month 9) - Plantation underway (Month 12) Output 3.2 - Construction complete by month 18. Physical work on 3.2b to take place during the dry season Output 3.3 - ESS reconfirmation complete by month 9 Output 3.4 - UXO clearance report complete by month 6) Output 3.5 - Detailed designs complete by month 12 Output 3.7 - Re-consultations complete by month 9 - Works underway by month 12 |  | Output 3.1 - MPMP complete and approved (month 9) - Plantation underway (Month 12) Output 3.3 - ESS reconfirmation complete by month 9 Output 3.4 - UXO clearance report complete by month 6 Output 3.5 - Detailed designs complete by month 12 Output 3.7 - Re-consultations complete by month 9 - Works underway by month 12 | S
Outcome 5
Outcome 6
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mao Hak National Council for Sustainable Development
| Email: | maohakccd.se@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
NCSD under supervision and direction of PMC and Project Team in both provinces has managed and coordinated well the project's activties for the first year. Although facing challenges induced by Covid-19 pandemic, NCSD has recruited various consultants with expertise and implemented most of activties planned for the 1st AoC. With support from UN-Habitat, NCSD is delivering expected outputs in the right track of time with good quality and high commitment.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Level of knowledge capacity at the community increased, measured by the number of community groups performing basic maintenance, clean-ups or house maintenance | Communities in the target area are not organised to manage or maintain infrastructure, collect solid waste or repair houses |  | At least one community group per investment and one group per commune formed and functional, performing these tasks. Each group should include 50% women
Output 1.1 | No. and type of trainings conducted to strengthen capacity on solid waste management No. of female training beneficiaries | No training has been conducted on solid waste management, and solid waste is a critical factor in preventing the functionality of critical infrastructure | The trainings have not been conducted yet. One trainee group was identified per commune (at least 50% are women). The training needs assessment was completed and training materials are under development. | 2x trainings per commune completed. 50% of trainees are women
Output 1.2 | No. of people trained on resilient house construction techniques No. of female beneficiaries | There are few if any local carpenters that have sufficient capacity to build resilient houses. | The trainings have not been conducted yet. 214 trainees are defined (14% of whom women). There is the challenge tht the local carpenters are mostly men. The training needs assessment was completed and training materials are under development. | 200 people (50% of whom women) trained
Output 1.3 | No. of trainings provided to communities on managing, monitoring and maintaining infrastructure investments No. of women trained | Communities have not received training of infrastructure management, monitoring and maintenance and are unaware of the need and approaches | Not yet bugun | 8 Training clusters implemented with 50% participation from women
Outcome 2 | Level of capacity at the sub-national level increased, measured by the number of adaptation actions planned in the target area | Capacity is limited, especially outside the national level. It is unclear if any adaptation projects have been planned |  | 5 projects prepared and planned for through the government system that enhance this project’s adaptation benefits, and extend climate change adaptation to a greater number of people in the target area. These projects should include the particular, differentiated adaptation needs of women
Output 2.1 | No. of government staff trained disaggregated by sex | There is constrained capacity (both in terms of manpower and technical know-how) to plan for the replication and upscaling of climate change actions | The trainings have not been conducted yet. 76 trainees are defined (31% of whom women). The training needs assessment was completed and training materials are under development. | 60 government officers trained, at least 20 of whom are women
Output 2.2 | No. of government staff trained No. of female government staff trained | There is constrained capacity (both in terms of manpower and technical know-how) to manage, operate and maintain infrastructure | have not begun yet | 25 government officers trained, at least 10 of whom women
Output 2.3 | No. of monitoring systems in place | There is currently no systematic way to review ‘what works’ in terms of climate change adaptation and to upscale its benefits | The institutional review was completed to define the key challenges and capacities taken into account the development of a monitoring system. | A system in place to systematically monitor adaptation investments and plan and advocate for replication, upscaling and further funding
Output 2.4 | No of knowledge products produced and estimated number of people reached | There is currently no systematic approach to capturing successful or autonomous adaptation practices, and no ‘anchoring’ of urban adaptation issues within either MoE or NCSD | have not begun yet | At least 20 local good practice documents (which could include local language articles, radio broadcasts or brochures) and 3 major policy recommendations. At least 3 of the knowledge products will focus specifically on the adaptation priorities and actions of women At least 100,000 people reached with knowledge products
Outcome 3 | No of people that benefit from climate change resilient infrastructure, access to natural assets and improved livelihood options to withstand conditions resulting from climate variability and change | 62,521 people, at least 50% of whom women, have been assessed as vulnerable to climate change impacts | have not begun yet | 100% of the vulnerable population (62,521 people) of which at least 50 percent women have access to resilient infrastructure and/or protective natural assets
Output 3.1 | No. of people who benefit from the restored mangrove, disaggregated by sex | Approximately 1140ha of land is vulnerable to coastal flooding, erosion, and salt-water incursion | have not begun yet | This land and 17,754 people, at least 50% of whom are women have greater protection from coastal flooding, erosion and salt-water incursion. There will be $600 benefit to fishermen per hectare of mangrove planted
Output 3.2 | No. of people who benefit from the repaired water gates and rehabilitated canals, disaggregated by sex | Water shortages arising from inadequate water management | have not begun yet | 1960ha of paddy with greater water access. Increased rice yield for agricultural families, and water access for non-agri families. A total of 19,553 people, at least 50% are women, benefit
Output 3.3 | No. of people who benefit from the rehabilitated canals | 3,500 people in the target area lack basic water management infrastructure and suffer from saltwater incursion | have not begun yet | 3,500 people, at least 50% of whom are women will benefit
Output 3.4 | No. of people who have improved access to water No. of ha land protected | 24,470 people have unreliable access to water, are vulnerable to poor conditions or the reservoir, and rely on rainfed agriculture. The same number of people are threatened by the unsafe embankment People in the coastal area are highly vulnerable to coastal flooding | have not begun yet | 24,470 people, of whom 50% are women, will have year-round access to water even during especially dry years, 600ha of rice paddy will be irrigated. People will be protected from the unsafe embankment. The same number of people will benefit from increased protection from flooding
Output 3.5 | No. of locally appropriate housing designs developed No. of demo houses constructed | Up to 200 houses per commune are destroyed or severely damaged by strong​ winds every year. Women are more likely to be injured or affected from or by damaged houses. Houses are not well constructed and use poor materials | have not begun yet | 9,720 people, of whom, 50% are women, benefit from design, training and 4 demo houses built
Output 3.6 | No of people whose land is protected from saltwater incursion, disaggregated by sex No. of ha of land protected | The landside of the embankment and water gates is severely affected by salt water, meaning that rice paddies are unproductive and surface water used for drinking is unusable | have not begun yet | 20,000 people, of whom 50% women, in the area (of a total population of 27,667) and 2,000ha of rice fields protected
Output 3.7 | The number of days’ income lost to flooding events | The market floods every time there is heavy rain. Sellers lost around 30 days’ income per year as a result. The vast majority of sellers (up to 90%) are women. | have not begun yet | The market retains 365 day per year functionality, not losing any days to heavy rainfall. The market has access to harvested rainwater. 4,500 people, up to 90% of whom are women, have improved year-round income
Output 3.8 | No. of people who have improved access to tidal information and early warning, disaggregated by sex | There is no accurate or local tidal information provided to people, and no early warning system | have not begun yet | An estimated 30,000 people, of whom, 50% are women have access to early warnings. Tidal information is also available to the local government and beneficiaries in the coastal area.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - The internal procedure to request for permission to sign on AoC has affected the start of the project, resulting in delay of the AoC signing and thus the project's implementation. - Covid-19 pandemic also affected the progress of the project's implementation. To be organized, the consultations and field missions need to be delayed until the travel restrictions are lifted. - Delay in fund transfer to implementing partners affected the start of activities, especially the ones that use consultancy services. - Transparent and effective communication among/between UN-Habitat and NCSD helped save time for decision making and contribute to the success of the activities' deployment. - Active participation of project team in both provinces helped address difficulties and challenges quickly, hastening the implementation of activities. - Active coordination between NCSD, UN-Habitat, and Project team in both provinces also helped speed up the progress of the project's implementation - Executive leadership and active participation of NCSD play an important role in speeding up all implementation processes. - Careful advanced planning is critical for activity implementation and result accomplishment
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The project was expected to start in September 2021 after the inception workshop, but due to theLengthy administrative procedure at NCSD for the fsigning the Agreement of Coorperation and the travel rectrcitoin impossed during Covid-19 pandemic over a year , the project has just started its activities in April 2022. Measures have been taken to reduce delays: - Advance preparation for project's readiness. Activties can start right after AoC signed. - Adoption of weekly meeting method to monitor and manage the project activities
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | N/A
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, but in the first year the effectiveness of applying these measures was not clear as all the activities focus on capacity building.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | During the reporting period, gender equality was taken into serious consideration to integrate in all the capacity building events. The participation of women in the project activties is expected to reach at 30%-50% based on outputs. As reported in the GP compliance section, next year gender will be integrated in the technical guidance and training materials for 1) risk and vulnerability assessment and 2) climate change mainstreaming in strategies, planning, and action plans.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A for the first year
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A for the first year
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A for the first year
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A for the first year
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A for the first year
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A for the first year
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A for the first year
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A for the first year
What measures are being/could have been put in place to improve project/program results? | N/A for the first year
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A for the first year
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A for the first year
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A for the first year
If learning objectives have been established, have they been met? Please describe. | N/A for the first year
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A for the first year
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A for the first year
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | NCSD supports the consultants to conduct data collection for training needs assesssment via digital platform, KoboCollect App.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | KHM/MIE/Urban/2017/1
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Cambodia
Region | Asia-Pacific
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 129497 | 62521 | 66976 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 60 | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type |  | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | Local | Multi-sector | 2: Low capacity | 14 | Local | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 400 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 5 | ha rehabilitated | 1: Ineffective | Mangroves | 391 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 150 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1143 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 150 | ha protected | 1: Ineffective | Protected areas/National parks | 600 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
[6 empty] | 8 | Physical capital | Multi-sector | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 4500 | Trading |  | 0 | 4500 | Trading |  | 10
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Urban development | National | Urban policy | 3 | Urban development | National | Urban Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness