## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 October, 2018 - 1 October, 2019
| Project Title: | Flood Resilience in Ulaanbaatar Ger Areas – Climate Change Adaptation through community-driven small-scale protective and basic-services interventions
| Project Summary: | The Project's objective is “to enhance the climate change resilience of the seven most vulnerable Ger khoroo settlements focusing on flooding in Ulaanbaatar City.” The project is being implemented by UN-Habitat as an integral part of the UN-Habitat Mongolia Country Programme with inputs from the UN-Habitat Climate Change in Cities Initiative through the Regional Office for Asia and the Pacific. A Project Implementing Unit (PIU) has been established. The seven target Ger communities in Ulaanbaatar are characterized by a high exposure to multiple climate hazards ranging from wind and dust storms, air pollution, and particularly by floods - cited as the main climate issue that required addressing by the communities - during the rapid needs assessment. Climate sensitivity is underpinned by rapid urbanization and population growth, leading to people residing in high-risk areas, in unsanitary conditions engaging in unhygienic behaviour, which exacerbates public health risks. Underlying vulnerabilities are poverty, limited social ties, limited access to basic services, gender inequalities and environmental degradation. Moreover, the adaptive capacities at household, community and governance level are barriers for change due to very limited knowledge and awareness of risks and their own vulnerability. Project investments will alleviate vulnerabilities and dismantle identified barriers by implementing four interconnected components: Component I: Improving the knowledge on flood hazard and risk exposure and vulnerability for these areas. Component II: Improving the resilience and adaptive capacity of the Ger settlements through a Community-Based approach (i.e. building social cohesion per Khoroo). Component III: Increasing resilience ger area physical infrastructure and services, supported by enhanced capacities of responsible district level and khoroo authorities. Component IV: Strengthened institutional capacity to reduce risks and capture and replicate lessons and good practices.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ? | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mongolia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Ulaanbaatar city northern Ger-Area (including the three high risk target districts covering the seven most vulnerable khoroos) 1. Songinokhairkhan district (SkhD): 7, 24, 25th khoroo; 2. Bayanzurkh district (BZD): 9th khoroo; and, 3. Sukhbaatar district (SBD): 12, 13, 16th khoroo | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-07-16
IE-AFB Agreement Signature Date: |  | 2018-09-24 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-02-28 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2021-02-01
| Terminal Evaluation Date: | 2023-02-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
1. Reports: a) Inception report b) Quarterly report to ROAP
|  | 2. Advocacy materials: 1 pager Project Introduction | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Enkhtsetseg Shagdarsuren, Project manager, UN-Habitat Mongolia | Dominican Republic
| Email: | enkhtsetseg.shagdarsuren@un.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Batjargal Zamba, Special Envoy for Climate Change | Equatoral Guinea
| Email: | z_batjargal@yahoo.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laxman Perera, Project Leader, Human Settlements Officer, UN-Habitat Regional Office | Fiji
| Email: | laxman.perera@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | World Vision International Mongolia (WVIM) | Georgia
| Email: | munkhbayar_bayasgalan@wvi.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Climate Change Impact on Society NGO (CCNS) | Grenada
| Email: | ccnsmongolia@gmail.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Mongolian Taiwanese Technology Transfer Center (MTTTC) | Guyana
| Email: | daniduudee@gmail.com | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 4 October 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement as of 4 October 2019 | 985662
Add any comments on AF Grant Funds. (word limit=200) | AF funds received up to now, the first instalment has been utilized per the breakdown below. The difference between disbursement and expenditure is $102,071. This will carry over into the planned expenditure for year 2. There is a difference of $5,884 between procurements by EEs and the amount transferred by UN-Habitat to the EEs. This is explained by some small shortfalls and the procurement of some IT equipment, which was done directly by UN-Habitat. These numbers are presented in detail in the pink shaded boxes in columns J-P on this tab. These funds will also carry over (where they are unspent)
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | UDRC 1 | UDRC 2 | MTTTC | CCINS | WV | Community contracting | PC Mall
| Output 1.1One (1) Ulaanbaatar northern GerArea* Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction - building on 1.21 | 30000 |  |  |  |  | 15000 | 15000
| Output 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established | 15000 | [5 empty] | 15000
| Output 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people | 29715 |  |  |  |  | 14730 | 14985
| Output 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 | 2079 |  |  |  | 819 |  |  | 1260
| Output 2.2 Khoroo community level interventions operation & maintenance* and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. An Estimated 20.nos. of trainings | 79232 |  |  |  | 9632 |  |  | 69600
| Output 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3. | 42064 | [6 empty] | 42064
| Output 3.1 Physical assets developed in response to climate change related flood impacts as prioritized by Khoroo communities the core concrete interventions are flood protection and drainage infrastructure5 and resilient sanitation6 to reduce floods impacts – implemented through community contracting. | 248922 | [6 empty] | 222045 | 26877
| Output 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services | 171859.9 |  |  | 13443.9 | 4432 |  |  | 153984
| Output 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate mechanisms. & Output 4.2 Workshops and trainings will be organised targeting city- and district government officials (50 percent women where possible) with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans | 79088.84 |  |  | 11526.84 |  |  |  | 67562
| Output 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity | 54496 | [6 empty] | 54496
| Activities Total | 752456.74
| PROJECT EXECUTION COST | 69112
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 62022
| TOTAL | 883590.74 |  |  | 24970.74 | 14883 | 29730 | 44985 | 611011 | 26877 | 0 | 752456.74 | SUBTTL
| Difference between Disbursement and expenditure | 102071.26 |  | Difference | #REF! | #REF! | 0 | 0 | 0 | 0 | 4538.37 | #REF!
PLANNED EXPENDITURE SCHEDULE | [11 empty] | #REF! | Procurement Total
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | Community contracting | New community contracts | UDRC 2 | MTTTC | CCINS | WV |  | UN-Habitat
| Output 1.1 One (1) Ulaanbaatar northern GerArea* Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction - building on 1.21 | 77000 | 2020-08-31 |  |  |  |  | 35000 | 35000 | 7000
| Output 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established | 35000 | 2020-07-31 | [5 empty] | 35000
| Output 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people | 110335 | 2020-08-31 |  |  |  |  | 34370 | 34965 |  |  | 41000
| Output 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 | 56085 | 2021-12-31 |  |  |  | 3085 |  |  | 8000 |  | 45000
| Output 2.2 Khoroo community level interventions operation & maintenance* and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. An Estimated 20.nos. of trainings | 39703.76 | 2021-12-31 |  |  |  | 4400 |  |  | 10000 |  | 25303.76
| Output 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3. | 49364 | 2020-05-31 | [6 empty] | 42364 |  | 7000
| Output 3.1 Physical assets developed in response to climate change related flood impacts as prioritized by Khoroo communities the core concrete interventions are flood protection and drainage infrastructure5 and resilient sanitation6 to reduce floods impacts – implemented through community contracting. | 1076877.5 | 2021-12-31 |  | 26877.5 | 650000 |  |  |  | 400000
| Output 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services | 252632 | 2021-12-31 |  |  |  | 2632 |  |  | 200000 |  | 50000
| Output 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate mechanisms. & Output 4.2 Workshops and trainings will be organised targeting city- and district government officials (50 percent women where possible) with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans | 42849 | 2022-02-01 | [6 empty] | 20849 |  | 22000
| Output 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity | 75000 | 2022-02-02 | [6 empty] | 45000 |  | 30000
| PROJECT EXECUTION COST | 130000 | 2022-02-27
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 136140 | 2022-02-28 | [8 empty] | 130000
| TOTAL | 2080986.26 | [9 empty] | 136140
[5 empty] | 26877.5 | 650000 | 10117 | 69370 | 104965 | 733213 |  | 486443.76
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental/social:
Current climate and seasonal variability and long winters (October – April) result in infrastructure construction delays | The risk is not relevant at this stage as the construction of the flood facilities is envisaged to start from May 2020. | To avoid any delay due to winter season, the PIU along with IP team have prepared an intensive work plan to complete all procurement and contractual processes regarding the selection of a construction company by end of April so that the company can utilize the entire construction season starting from 1 May 2019 for the construction.
Institutional:
Loss of government support (at ministerial and municipal level) for the project (activities and outputs) may result in lack of prioritization of AF project activities | The PIU and IPs are working closely with the Municipality and the MOET . So far they are very supportive. | The PIU and IPs have been working closely with the Municipality and MOET through the secretary of PWG and NDA regularly updating and engaging them in important milestones of the project.
Loss of government support (at Khoroo / community level) for the project (activities and outputs) may result in lack of prioritization of AF project activities; Due to communist history and many immigrant communities, organisation is limited. | The PIU and IPs are working closely with the 7 target khoroo administrations. So far they are very supportive. | The PIU and IPs have been working closely with the target khoroo administrations regularly engaging them in the field activities and community consultations under the project. Khoroo governors and officers have been supporting the project through provision of meeting venues, reaching out the communities, validation of the community action plans and supporting the community initiatives under the project.
Communities may not adopt activities during or after the AF project, including infrastructure maintenance | The risk significance is very low as the project is tackling the flood resilience building and sanitation improvement which are the most priority issues of the traget communities. Communities are very active and willing to get involved in the project. | Under the project, UN-Habitat's People's Process approach is being introduced for community mobilisation and organisation. The approach aims to empower communities for their common problem solving.
A lack of coordination between and within national government Ministries and Departments. | The risk significance is very low at this stage as PWG and Sub-working groups at the districts are facilitating the project team in coordination with the government counterparts. | The PIU and IPs are working closely with PWG and NDA regularly updating and engaging them to the extent possible.
Financial:
Inflation and instability of the national currency leading to budget issues and increased prices for infrastructure delivery | The risk was not relevant for the reporting period.
Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | The risk was not significant. | The PIU is working closely with ROAP and IPs to avoid any delays and integrity issues in administrative and procurement processes
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
No critical risks identified.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
N/A

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law: Insufficient alignment with laws and technical standards, especially related to implementation of concrete interventions under components 3. |  |  | N/A. Below are summaries of impacts identified in the final proposal, Table 13 | Each person associated with the project is aware of domestic and interna-tional laws and compliance needs to technical standards requirements | N/A | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
2 - Access and equity: Activities would exclude any potentially affected stakeholders from fully participating in decisions that may affect them; risk of unequal distribution among target population / communities and households of project benefits. |  |  | Exclusion of any potentially affected stakeholders or vulnerable group. Disruption due to the drainage construction activities | Community organization processes (through Community Development Councils) and quotas (> 50 percent women and to-be-defined percent-ages for other groups) will be used to ensure vulnerable groups are repre-sented during meetings, trainings, decision-making. For the drainage interventions, all households potentially affected by the construction of the channels are included in decision-making processes. Interventions are also designed in a way so as to not disrupt daily life in terms of access or reduced mobility – in addition to guaranteeing access to plots at all times, there will be no restrictions on access to main roads. | Meeting attendance sheets with quota numbers and photographs. | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
3 – Marginalized and vulnerable Groups: Some vulnerable affected groups may not participate in decisions making processes regarding design and planning of activities that may affect them. |  |  | See access and equity | See access and equity | Construction of food bridge Check drainage channel dimen-sions before Construction Consultation notes | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
4 – Human rights: Risk that land and tenure arrangements and/or community-based property rights are affected; failure to proactively protect the rights (i.e. international standards) of all stakeholders affected by the project. |  |  | Violating tenure security and property rights (by working without consent/agreement) in the flood wall and other drainage channel in Khoroos 7&9 | Community Development Councils will be formed with membership of all households benefitting from construction. The design of drainage sections will be managed in neighborhood sections which are small enough so that they can be managed by these Community Development Councils. Construction of the drainage channels will only start when all possibly affected households sign that they agree with the intervention. This will be done through a participatory planning process through the Community Development Councils. Besides that, a clause will be included in all con-tracts stating that contractors will comply to human rights markers (and other relevant safeguard areas). The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need to tempo-rary relocate during construction. Moreover, an alternative drainage plan has been developed (and has already been considered) if inhabitants don’t agree. The UN-Habitat Human rights officers and PAG will check compliance. The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need to temporary relocate during con-struction. | Signed sheet Check contracts on HR markers | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
5 – Gender equality and women’s empowerment: Women and men do not have equal opportunities to participate in the project and do not benefit equally from interventions. |  |  | Women and men do not have equal opportunities to participate in the project and do not benefit equally from interventions | Measure to ensure equal participation in planning and decision-making processes for women and to enable them as agents of change: It will be ensured women will be able to participate through participation quota. The project included gender targets and involves existing women committees at Khoroo level and women representatives at the ministerial level. Trainings only inviting women will be organized | Number of participants, sex disaggre-gated Number of special needs of communities integrated to the de-sign of the proposed interventions | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
6 – Core labour rights: Employing underage people and to support underpayment and unsafe working conditions; executing entities for the project may not adhere to the ILO labour Standards and national labour laws. |  |  | Lack of adherence to national labour laws and/or ILO standards. | Measure to ensure compliance to ILO standards during construction: employment and working conditions following ILO standards will be included in legal agreements with all subcontractor. | Check contract and signs | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
7 – Indigenous peoples: Indigenous groups may not participate in decisions making processes regarding design and planning of activities that may affect them. |  |  | N/A - No indigenous people in the target area. | N/A | N/A | N/A |  | No residual impacts identified | N/A
8 – Involuntary resettlement: Temporary or permanent and full or partial physical displacement (see also principle 4) |  |  | Displacement in Koroos 7 and 9. Disruption to access and quality of life during works period, especially relating to the drainage activities, which will go under some plots | Community Development Councils will be formed with membership of all households benefitting from construction. The design of drainage sections will be managed in neighborhood sections which are small enough so that they can be managed by these Community Development Councils. Construction of the drainage channels will only start when all possibly affected households sign that they agree with the intervention. This will be done through a participatory planning process through the Community Development Councils. Besides that, a clause will be included in all con-tracts stating that contractors will comply to human rights markers (and other relevant safeguard areas). During project implementation, UN-Habitat will monitor and guarantee access to plots by all affected house-holders in Khoroo 40 (Former Khoroo 7).The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need temporary accommodation during construction, following agreement by all parties via the People’s Process consultations. . The UN-Habitat Human rights officers and PAG will check compliance. | See Principle 4, Human Rights | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
9 – Protection of natural habitats |  |  | N/A | N/A | N/A | N/A |  | No residual impacts identified | N/A
10 – Conservation of biological diversity |  |  | N/A | N/A | N/A | N/A |  | No residual impacts identified | N/A
11 – Climate change |  |  | N/A | N/A | N/A | N/A |  | No residual impacts identified | N/A
12 – Pollution prevention and resource efficiency: Consumption of raw materials will have a negative effect (elsewhere). |  |  | Unsustainable purchase or disposal of construction materials |  | Materials on bills/BOQ’s | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
13 – Public health: Potential risk: elements of activity construction, operation, or decommissioning pose potential safety risks to local communities (see also principle 6). |  | . | Elements of activity construction, operation, or decommissioning pose potential safety risks to local communities | It will be ensured that ICSC international health and safety standards are clearly accessible and understood. e.g. by putting clearly visible signs detailing health and safety standards to be located at projects sites and by supplying protective equipment. | See Principle 6, Core Labour Rights | No baseline was established at project proposal stage |  | No residual impacts identified | N/A
14 – Physical and cultural heritage: Proposed interventions will affect physical or cultural heritage negatively. |  |  | N/A | N/A | N/A | N/A |  | No residual impacts identified | N/A
15 – Lands and soil conservation: Proposed interventions will have a negative effect on lands and soil conservation. |  |  | N/A | N/A | N/A | N/A |  | No residual impacts identified | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Briefing and familiarisation has been done with all EEs. International consultant has provided a presentation on ESMP/ESP of the Adaptation Fund. More measures proposed for Y2, before and during major construction works
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | EEs were only contracted between 1-3 months prior to the end of the reporting period. Nevertheless, each EE has begun to put measures in place. This especially relates to the sanitation and drainage infrastruture, where community consultations have already taken place
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, but greater measures will be required in year 2, when physical works get underway
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | During the project preparation phase, the gender assessment had been done through desk research, surveys, women focus group discussions and community needs assessments. UN-Habitat headquarter gender specialist had been involved in the project preparation/review process to ensure compliance with the AF Gender Policy as well as the UN-Habitat gender mainstreaming guidelines.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The result framework includes gender-responsive indicators at outcome and output levels.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Women participating in planning process | Output 1.1. | Women participation by percentage | 0 | > 50 % | good
Women participating in planning process | Output 1.3. | Women participation by percentage | 0 | > 50 % | good
Women participating in planning process | Output 2.1. | Women participation by percentage | 0 | > 50 % | good
Number of awareness campaigns and trainings | Output 2.2. | Women participation by percentage | 0 | > 50 % | good
Toilets | Output 3.1 | Toilets are appropriate for women, elderly and disabled where required | 0 | >50 % of toilets adapted to specific needs | satisfactory
Women participating in planning process | Output 4.1. | Women participation by percentage | 0 | > 50 % | good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | 1. A sex disaggregated template for a meeting/event attendance was developed for meeting participants' data collection. 2. A sex disaggregated database for workshops and consultations was developed and has been regularly updated to monitor the participation and gender disparity during the project implementation. 3. A template for communities' consent to establish a primary group was developed for sex dissagregated data collection of the community members. As per the collected data, 28 Primary Groups (PG) have been established with 357 households represented. Of this 130 women represent their household. in total have been established in the target 7 khoroos.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Gender equity and women empowerment are main principles of the People's Process approach introduced for the project implementation and have been monitored closely by the PEU. 43 women (51.2%) hold leadership position in the PG groups. In 21 of the 28 PG groups there are women in leadership positions.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | For the reporting period, four executing entities have been engaged by the project. Percentage of female members in the EE teams is above 50%. All of EEs are using sex dissagregated templates for recording information on meeting attendance, meeting database and communities internal agreement to ensure gender disparity and women engagement. Based on these tools, GP compliance has been closely monitored. For the community organizations established as part of the People’s Process, gender equality in the composition of training participants was monitored. Also gender parity and gender considerations in the planning and implementation of Components 2 & 3 were closely guided and monitored.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes. The record shows so far that women engagement in different activities under EEs is more than 50%.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Capacity Building Strategy:
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Objective is to enhance the climate change resilience of the seven most vulnerable Ger khoroo settlements focusing on flooding in Ulaanbaatar City.
| Project commencement with fully functioning project team and implementation mechanism in place |  | The fully functional Project Implementing Unit (PIU) is in place; Organisation of an Inception Workshop; |  | The Project Implementing Unit (PIU) composed of an International Project Manager at the UN-Habitat Regional Office for Asia and the Pacific, a national project manager at the UN-Habitat Country Office in Ulaanbaatar and 2 drivers was established by UN-Habitat. The PIU is an integral part of the UN-Habitat Mongolia Country Programme. Inputs are received from the UN-Habitat Climate Change in Cities Initiative through the Regional Office for Asia and the Pacific. The Inception Workshops were conducted at two levels: national and district. On 28 February 2019, the main workshop was conducted at the national level, inviting the national and city level stakeholders and interested parties. This was followed by three District level Inception Workshops in the target districts of Ulaanbaatar City, which were conducted on 15, 19 and 20 March 2019. More than 237 (67 percent women) participants representing the Government, relevant NGOs, and key stakeholders of the Project target areas attended these workshops. The objective was to introduce the Project goals and objectives and its implementation mechanisms; oversight, monitoring and Logical framework with indicators and provide background information on the status of flooding of the seven most vulnerable Ger khoroo settlements, ecosystem vulnerability to climate change impacts as well as the Adaptation Fund in the context of global climate finance mechanisms. | Satisfactory
|  |  | The Project Advisory Committee at National Level and Project Coordination Team at the Municipal level are established, EE are engaged. |  | As advised by the national partners based on their working practices, a Project Working Group was established in place of the Project Advisory Committee suggested in the project proposal. Also, a sub-working group was established at each of target districts as suggested and agreed by the participants during the inception workshops in place of the Project Coordination Team proposed in the project proposal. The general manager of Ulaanbaatar city and National Designated Authority for AF co-chair the Project Working Group. The first meeting of the Project Working Group (PWG) was held on 19 April 2019. The District Deputy Governor works as a chair of the sub-working group and it is composed of specialists from the key district divisions and target Khoroo Governors. The Sub-working group under the target district’s Governor’s Office was officialised in May 2019 through District’ Governor’s resolution. The Terms of References of the working groups was discussed and finalized during the first meeting of the Project Working Group (PWG). | satisfactory
|  |  | PEU is in place |  | • Recruitment of PEU staff started in August with the advertisement of the required national posts on local popular daily newspaper. The staff recruitment including advertisement, evaluation, selection and contracting was done according to the WVIM rules and regulations. • National staff recruitment was completed by end of August and staff contracts were issued effective 1 September 2019. • Posts of international consultants were advertised using the WVIM website and local newspaper. Contract negotiation with a candidate for Community Engagement and Infrastructure Advisor was carried out after the selection process. The contract with the selected candidate was signed with effect from 1 October 2019. • The process of recruiting Climate Change Expert is ongoing. • Note that information about the delay in selecting the EE is provided in the implementing entity section, below | satisfactory
Outcome 1: Relevant threat, hazard information, evidence and recommendations (on land use and zoning) generated for increasing resilience at the city level.
| 1.1 One (1) Ulaanbaatar northern Ger-Area* Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction -building on 1.2 (includes the three (3) high risk target districts covering the seven (7) most vulnerable khoroos) |  | A northern Ger-Area Territorial Land Use Plan is being developed. |  | MTTTC only became engaged in the project shortly before the end of the reporting period, but as of October 2019 work is underway on collecting data, meeting communities and working with government, as prescribed in the project document and agreement of cooperation to delivery outputs under 1.1. Delivery of these activities is on-schedule | satisfactory
| 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established.20 |  | The city wide simulation models forecasting impacts of the current and future Climate Change and flooding, which includes a) simulation of extreme flood case using hydro meteorological model; b) projection and downscaling of climate change and extreme event (flood, heat wave etc) frequency and intensity; c) flood producing rainfall intensity analysis around the Ulaanbaatar city; d) impact and risk assessment of flood on targeted area are being developed. |  | Like the other EE’s, CCNS only became an EE toward the end of the project reporting period. However, work is already underway on the simulation model, including gathering the data, detailing the scope of the assessment and preparing the outline of the report. A detailed draft of the modelling cab be presented to UN-Habitat and the other partners in January or February 2020. Delivery of these activities is on-schedule | satisfactory
| 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people21 |  | The Detailed Ger-khoroo level Land Use Plans for the 7 most-at-risk Ger-areas are being developed. |  | Please see 1.1. This work begun just before the end of Y1 reporting, but will rapidly scale-up in year 2, and progress is therefore satisfactory | satisfactory
Outcome 2: Target community members are aware of resilience building and climate risk reduction processes and have ownership over proposed interventions at the District, Khoroo and community level.
| 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3.22 |  | A series of District, Khoroo and community level consultations / workshops introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 is being held |  | World Vision has now begun the detailed work on these activities, including detailed designs, community survey/consultation, detailing compliance with the ESMP/Environmental and Social and Gender Policies of the AF. Works are projected to start in the next reporting period (i.e. Y2 of the project, 2020). | satisfactory
| 2.2 Khoroo community level interventions operation & maintenance and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. An Estimated 20.nos. of trainings *(Awareness will also cover potential risks mitigation) |  | The communities are being involved in the planning and execution of the proposed interventions under component 3; to ensure the proper operation and maintenance (and implementation of potential risk mitigation measures) of these interventions through community involvement. |  | Activities under this result area did not take place during the reporting period, and are projected to begin next year.
| 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3. |  | The TORs for engineering and technical hydrological studies for the implementation of the flood protection and drainage infrastructure have been prepared. |  | No EE has yet been selected for this activity. The TORs for the engineering and hydrology study and detailed design of the flood facilities have been developed and finalized by the PEU. The CFP for the work has been advertised in local popular daily newspaper on 30 September 2019. | satisfactory
Outcome 3: Increased adaptive capacity within prioritized community assets
| 3.1 Developing or strengthening physical assets in response to climate change related flood impacts as prioritized by Khoroos. |  | As a response to the Khoroo-specific climate change resilience building needs and intervention prioritization by communities, flood resilient latrines are being developed by the communities |  | Contracts were signed with World Vision, the EE, on August 19th, 2019. A workplan for October 2019 - October 2020 has been prepared jointly by PIE and PEU teams. As per the workplan the construction of flood facilities is envisaged to start from 1 May 2020. | satisfactory
[5 empty] | • Works through Community Implementation Agreement (CIA): o PEU helped the communities to prepare a sub-project proposal to solve the first priority problem of the flooded pit latrine in the CAP through construction of small-scale drainage and improved pit-latrines. The PEU engineer and urban planner helped the communities with development of the technical designs and budget estimate. o The first CIA was signed with the Community Development Council established in SBD 13th Khoroo with effect from 9 September 2019. o Communities are currently implementing labor intense works including clearing the land for ground preparation, digging the drainages by hand, removing the excavated soils and placing the gravel to the drainage under the close supervision of the PEU engineer and planner. o It was planned to construct drainages to remove excess stagnant water on the ground in 3 places then construct 14 improved pit-latrines with holding tanks and 14 holding tanks for sludge disposal for 28 households under the CIA. As of end of the reporting period, all ground works including the excavation of the land and placing the concrete holding tanks into the pit were completed. | satisfactory
| 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services |  | Not relevant at this stage |  | This work was not planned to commence until year 2.
Outcome 4: Institutional capacity strengthened to develop and replicate this approach.
| 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate |  | Lessons learned on increasing the flood resilience of communities are being captured; and municipal and district level government officials exposed to these principles and trained on lessons learned to ensure buy-in and the sustainability of this project for effective replication of best practices. |  | Project visibility activities have included Project visibility: • A domain name was purchased and a web-site to disseminate the project information is being designed by the PEU team. • A PEU staff name cards are being designed, for use by the PEU staff. • The FRUGA Facebook page is being maintained by the PIU and PEU. As of 1 Ocobert 2019, the page was reached by 4,417 people. 214 people liked during past 28 days. Through the page PUI and PEU have been disseminating information on the project and its activities in the target areas. The posts illustrated the community activities under the project helping themselves and neighbourhoods to drain the stagnant water in their plots to the nearest drainage channels were the most liked by people. These works were done as part of the community implementation agreement between organized communities and UN-Habitat as a prerequisite for construction of improved toilets. • For the project visibility, designs of t-shirts and vest jackets with AF, UN-Habitat and FRUGA project logos have been prepared and 50 t-shirts and 40 vest jackets were purchased. T-shirts are envisaged to be distributed to the community members and project stakeholders during the project events. Vest jackets are envisaged to be used by the Project team members during their activities in the field. •Video documentation of community activities for improved pit-latrine construction is being developed. | satisfactory
| 4.2 Workshops and trainings to be organised targeting city- and district government officials with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans |  | Trainings are being conducted for city- and district government officials from other potential high-risk areas on the project approach and knowledge generated for replication based on demand by the communities and local authorities. |  | • A workshop for exploration of solutions of household sanitation in flood prone, rocky and permafrost areas was organized on 21 June 2019 inviting researchers, academia, projects and programmes with similar purpose, representatives of beneficiary communities, MUB and MOET. The workshop was attended by 46 representatives of above groups with 65% women participation. The workshop aimed to provide a platform for the residents from target area to get informed about the available household sanitation solutions at the market and assess them in terms of the feasibility and affordability in their area context. Although different solutions were presented during the workshop, only one of them was tested for the areas with high ground water table and permafrost. The test results were provided in the presentation by Ultrasonic Company. However, the tested solution was not affordable and suitable for a single household in UB ger areas in terms of cost and technical requirements. The solution could work for a group of 5-10 households. The overall conclusion from the workshop was to find a better solution through testing out some technologies with close engagement of the host households while giving them sense of responsibility and ownership. | Satisfactory
| 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity |  | Relevant activities have been started
[5 empty] | Overall Rating | satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Enkhtsetseg Shagdarsuren, National Project Manager
| Email: | enkhtsetseg.shagdarsuren@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Activities discussed in PMC with all partners
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Project commencement with fully functioning project team and implementation mechanism in place |  | The fully functional Project Implementing Unit (PIU) is in place; Organisation of an Inception Workshop; The Project Advisory Committee at National Level and Project Coordination Team at the Municipal level are established, EE are engaged. PEU in place |  | UN-Habitat is in full agreement with the assessment above . The mechanisms described above have been implemented. The inception workshops described were conducted and received enthusiastic participation from the stakeholders and more than adequate representation women. UN-Habitat envisaged in the proposal that it will engage the UNOPS for the execution of the hardware components for climate adaptation in the Ger areas, harnessing their operational capacity to deliver technical infrastructure outputs as done in other countries in Asia Pacific through establishment of a Project Execution Unit (PEU). Even after extensive negotiations, the costs proposed by UNOPS was found to be much beyond the available budget in the proposal. UN-Habitat the decided to go for an open selection of an Executing Partner. The Call for Proposal and TOR for the Executing Partner was finalized and advertised on 21 March 2019 with the deadline 22 April 2019. Five proposals were received and “World Vision International Mongolia” an international NGO was selected. The Agreement of Cooperation with WVIM was signed on 19 August 2019. | S
Outcome 1: Relevant threat, hazard information, evidence and recommendations (on land use and zoning) generated for increasing resilience at the city level.
| 1.1 One (1) Ulaanbaatar northern Ger-Area* Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction -building on 1.2 (includes the three (3) high risk target districts covering the seven (7) most vulnerable khoroos) |  | A northern Ger-Area Territorial Land Use Plan is being developed. |  | A Call for Proposal (CFP) and TOR for selection of a non-profit executing entity for the delivery of Output 1.1 and Output 1.3 was prepared and advertised on 29 March 2019 with the deadline on 22 April 2019. • The evaluation committee was established composed of the representatives of ROAP, Mongolia Office and individual consultant. Among the 3 NGOs which submitted technical and budget proposals, the Mongolian Taiwanese Technology Transfer Center (MTTTC) was selected. The contract negotiations with the MTTTC started on 13 June 2019 and was finalized. • The Agreement of Cooperation between UN-Habitat and MTTTC for the development of Ulaanbaatar northern Ger-Area Territorial Land Use Plan was signed on 5 July 2019. • The work has been started from 1 August 2019. • The first instalment under the contract was released by UN-Habitat on 2 August 2019. • The UN-Habitat Project manager has been working with the team during the reporting period closely guiding and monitoring the progress of the work. | HS
| 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established |  | The city wide simulation models forecasting impacts of the current and future Climate Change and flooding, which includes a) simulation of extreme flood case using hydro meteorological model; b) projection and downscaling of climate change and extreme event (flood, heat wave etc) frequency and intensity; c) flood producing rainfall intensity analysis around the Ulaanbaatar city; d) impact and risk assessment of flood on targeted area are being developed. |  | A CFP and TOR for preparation of simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas and data collection for the Output 1.1 and Output 1.3 was prepared and advertised on 29 March 2019 with the deadline on 24 April 2019. • The evaluation committee was established composed of the representatives of ROAP, Mongolia Office and individual consultant. Among the 3 NGOs which submitted technical and budget proposals, the Climate Change on Nature and Society (CCNS) NGO was selected. The contract negotiations with the CCNS were held on 12 and 21 June 2019. • The Agreement of Cooperation between UN-Habitat and CCNS was signed on 4 July 2019. • The first instalment under the contract was released by UN-Habitat on 2 August 2019. • The work has been started from 1 August 2019. • The UN-Habitat Project Manager (PIU) has been working with the team during the reporting period closely guiding and monitoring the progress of the work. | S
| 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people |  | The Detailed Ger-khoroo level Land Use Plans for the 7 most-at-risk Ger-areas are being developed. |  | The activities under this output have been merged with the Output 1.1 and CFP for delivery of Output 1.1 and Output 1.3 was advertised on 29 March 2019 with the deadline on 22 April 2019. • The evaluation committee was established composed of the representatives of ROAP, Mongolia Office and individual consultant. Among the 3 NGOs which submitted technical and budget proposals, the Mongolian Taiwanese Technology Transfer Center (MTTTC) was selected. The contract negotiations with the MTTTC were held on 13 and 21 June 2019. • The Agreement of Cooperation between UN-Habitat and MTTTC was signed on 5 July 2019. • The first instalment under the contract was released by UN-Habitat on 2 August 2019. • The work has been started from 1 August 2019. • The UN-Habitat Project Manager (PIU) has been working with the team during the reporting period closely guiding and monitoring the progress of the work. | HS
Outcome 2: Target community members are aware of resilience building and climate risk reduction processes and have ownership over proposed interventions at the District, Khoroo and community level.
| 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 |  | A series of District, Khoroo and community level consultations / workshops introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 is being held |  | The People's Process Manual to be used for the participatory planning and community development was developed considering the context of Ulaanbaatar ger areas. • The community mobilization and organization activities have started in the target khoroos soon after holding the district level inception workshops. • In parallel, with the community mobilization and organization activities, the PIU started community mapping exercises of flood prone areas and households with bad sanitation condition through two rounds of community consultations. The purpose of this activity was to detail out and validate the flood hazard maps prepared during the project preparation stage with kheseg leaders and area communities. • Under the first round, seven consultations were organized and attended by all kheseg leaders in the target 7 khoroos. Maps of kheseg sub-division, flood prone areas and households in bad condition in terms of sanitation were prepared during the consultations. • The second round was aimed for attendance of residents of each kheseg area to improve and detail out the above mapping with grass root communities’ knowledge and past experiences. 29 community consultation workshops were organized and attended by 718 residents from 62 project kheseg where 68.8% were female. • The second-round consultations also included a session for communities' needs assessment in terms of flood protection and sanitation improvement. • 28 primary groups have been established during the reporting period in the project khoroos. • 7 workshops were held for Community Action Planning for flood resilience during September in the target 7 khoroos. Through the workshops 7 Khoroo Community Action Plans for flood resilience were prepared. • The workshop for exploration of solutions of household sanitation in flood prone, rocky and permafrost areas was organized on 21 June 2019 inviting researchers, academia, projects and programmes with similar purpose, representatives of beneficiary communities, MUB and MOET. The workshop was attended by 46 representatives with 65% women participation. The workshop aimed to provide a platform for the residents from target area to get informed about the available household sanitation solutions at the market and assess them in terms of the feasibility and affordability in their area context. Although different solutions were presented during the workshop, only one of them was tested for the areas with high ground water table and permafrost. The test results were provided in the presentation by Ultrasonic Company. However, the tested solution was not affordable and suitable for a single household in UB ger areas in terms of cost and technical requirements. The solution could work for a group of 5-10 households. The overall conclusion from the workshop was to find a better solution through testing out some of state of art technologies with the close engagement of the host households while giving them sense of responsibility and ownership. | HS
| 2.2 Khoroo community level interventions operation & maintenance and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. |  | The communities are being involved in the planning and execution of the proposed interventions under component 3; to ensure the proper operation and maintenance (and implementation of potential risk mitigation measures) of these interventions through community involvement. |  | Activities under this result area did not take place during the reporting period, and are projected to begin next year. | S
| 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3 |  | The TORs for engineering and technical hydrological studies for the implementation of the flood protection and drainage infrastructure have been prepared. |  | The TORs for the engineering and hydrology study and detailed design of the flood facilities have been developed and finalized by the PEU. The CFP for the work has been advertised in local popular daily newspaper on 30 September 2019. | S
Outcome 3: Increased adaptive capacity within prioritized community assets
| 3.1 Developing or strengthening physical assets in response to climate change related flood impacts as prioritized by Khoroos. |  | As a response to the Khoroo-specific climate change resilience building needs and intervention prioritization by communities, flood resilient latrines are being developed by the communities |  | • A CFP and TOR for selection of an Executing Entity for the delivery of the Output 3.1 was prepared and advertised on 29 March 2019 with the deadline on 22 April 2019. Five NGOs submitted technical and budget proposals. • The evaluation committee was established composed of the representatives of ROAP, Mongolia Office and individual consultant. World Vision International Mongolia (WVIM) was the most qualified candidate. The contract negotiation with the WVIM was done on 12 June 2019 . •The Agreement of Cooperation with WVIM was signed on 19 August 2019. • A workplan for October 2019 - October 2020 has been prepared jointly by PIE and PEU teams. As per the workplan the construction of flood facilities is envisaged to start from 1 May 2020. | S
| 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services |  | Not relevant at this stage |  | Begins in 2020 | S
Outcome 4: Institutional capacity strengthened to develop and replicate this approach.
| 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate |  | Lessons learned on increasing the flood resilience of communities are being captured; and municipal and district level government officials exposed to these principles and trained on lessons learned to ensure buy-in and the sustainability of this project for effective replication of best practices. |  | Inception workshops were organized at the national and district levels to inform the stakeholders and the intended beneficiaries about the project, hear from them about their past experience and lessons learned and best practices and to establish a network for further exchange of information during the project implementation. | HS
| 4.2 Workshops and trainings to be organised targeting city- and district government officials with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans |  | Trainings are being conducted for city- and district government officials from other potential high-risk areas on the project approach and knowledge generated for replication based on demand by the communities and local authorities. |  | This activity has been implemented as described above, led by the Project Coordinator | HS
| 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity |  | Relevant activities have been started |  | To begin in 2020 | S
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Laxman Perera, Human Settlements Officer, UN-Habitat Regional Office
| Email: | laxman.perera@un.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | See above.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Output 1.1 | Number of Territorial land use plans with identified flood risks developed | 0 | Related activity is ongoing. Please note that the contract with the EE was only signed on August 19th, 2019. However, initial meetings are taking place at the end of year 1 and this activity is, therefore, on track | One (1)
| Women participating in planning process | 0 | It is still early to assess. However, there has been very good participation of women in the early meetings. | > 50 % women
Output 1.2 | Number of flood simulation models developed | 0 | Related activity is ongoing. The contract was signed with the EE on July 4th, and work began on August 1st. Initial research work, meetings and secondary research have proceeded well | One (simulation model)
Output 1.3 | Number of Territorial land use plans with identified flood risks developed | 0 | Related activity is ongoing. See Output 1.1 | Seven (7)
| Women participating in planning process | 0 | It is still early to assess. See Output 1.1 | > 50 % women
Outcome 2.1 | Percentage of targeted population aware of predicted flood risks and appropriate responses | 0 | It is still early to assess. However, the activities are underway and are described below. | Mid-term: 30 % End: 50 % > 50 % women
Output 2.1 | Number of Khoroo level flood resilience action plans | 0 | Seven (7) Khoroo-level annual Community Action Plans (CAP) under development. Initial meetings have taken place that have seen over 65% attendance by women | Seven (7)
| Women participating in planning process | 0 | 158 representations of beneficiary communities in total with 68.3% female participation attended the workshops. | > 50 % women
Output 2.2 | Number of awareness campaigns and trainings | 0 | 1 workshop per Khoroo so far. These workshops will continue in 2020, and participation has been good so far. | 4 per Khoroo
| Women participating in planning process | 0 | 158 representations of beneficiary communities in total with 68.3% female participation attended the trainings. | > 50 % women
Output 2.3 | Number of studies | 0 | It is still early to assess. ToRs developed but this activity has not yet started. | 1
Output 3.1 | Number of physical assets strengthened, constructed, and/or modified. to reduce or withstand floods | 0 | It is still early to assess. The EE was selected in August 2019. Initial work is underway, with construction expected in 2020 | Four (4) for the flood protection and drainage intervention: 1x Khoroo 7 2x Khoroo 9 1 x Khoroo 24
| Toilets are appropriate for women, elderly and disabled where required | 0 | 28 improved toilets have been constructed by the communities. 100% of them are considered to be adapted to specific needs. Community contracting has been done and initial units are being delivered | >50 % of toilets adapted to specific needs
Output 4.1 | Number of institutions trained | 0 | It is still early to assess. Initial workshops have taken place with good participation, including from women (65%) and activities in this regard will continue to scale up as other elements of the project scale up in year 2 of the project | >1 municipal >3 districts
| Women participating | 0 | It is still early to assess. As above | > 50 % women

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress?
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There was a delay in an Executing Entity selection for Component 3 implementation as UN-Habitat was envisaged in the proposal that it will engage the UNOPS for the component. However, the negotiation took longer than expected, UN-Habitat decided to go for an open selection of an Executing Partner. 5 proposals were received and “World Vision International Mongolia” International NGO was selected. The contract with WVIM as an EE for the Component 3 started from 19 August 2019.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. Changes in project organigram: As advised by the national partners based on their working practices, a Project Working Group was established in place of the Project Advisory Committee suggested in the project proposal. Also, a sub-working group was established at each of target districts as suggested and agreed by the participants during the inception workshops in place of the Project Coordination Team proposed in the project proposal. The District Deputy Governor works as a chair of the sub-working group and it is composed of specialists from the key district divisions and target Khoroo Governors. The Sub-working group under the target district’s Governor’s Office was officialised in May 2019 through District’ Governor’s resolution. 2. “Bringing Global Knowledge on best practices to in-country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity” is added as output 4.3 after considering following reasons: During the inception workshop and during consultations with the government partners, it was observed that there is a greater need to implement a comprehensive knowledge management strategy aiming multi-level stakeholders bringing international expertise under different components more integrated manner. The objective is to address the knowledge gaps on climate change and resilience at difference levels including among government partners and communities. This requires inputs from global experience integrating into local context customizing widely used tools and peer reviews on flood resilience action plans, guideline documents etc. Similarly, knowledge management strategy outcomes should be informing the development of regional and global capacity development tools and normative products. Therefore, a separate outcome was established incorporating International experts’ inputs under new output which links to all outputs. Accordingly Outputs of 1.1-d; 1.2-b,2.1-d, 2.2 a subcomponent 1; were moved to Output4.3
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | It is not yet relevant as the construction activities are envisaged to start from May 2020. However, initial briefings have taken place for EEs and Communities that describe the project's ESMP and the ESP of the Adaptation Fund, understanding that environmental and social safeguards are a new concept for all communities and many organisations in Mongolia
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | 1. A sex disaggregated template for a meeting/event attendance was developed for meeting participants' data collection. 2. A sex disaggregated database for workshops and consultations was developed and has been regularly updated to monitor the participation and gender disparity during the project implementation. 3. A template for communities' consent to establish a primary group was developed for sex dissagregated data collection of the community members. As per the collected data, 28 Primary Groups (PG) have been established with 357 households represented. Of this 130 women represent their household. in total have been established in the target 7 khoroos.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UN-Habitat
Type of implementing entity | RIE
Country | Mongolia
Region | Asia-Pacific
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 194149 | 89439 | 104710 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 |  |  |  | 1 | Urban development | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Urban development | 2: Low capacity | Public | Local | Urban development | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 97075 | 50%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.