## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 Oct 2019 - 1 March 2021
| Project Title: | Flood Resilience in Ulaanbaatar Ger Areas – Climate Change Adaptation through community-driven small-scale protective and basic-services interventions
| Project Summary: | The Project's objective is “to enhance the climate change resilience of the seven most vulnerable Ger khoroo settlements focusing on flooding in Ulaanbaatar City.” The project is being implemented by UN-Habitat with supports from executing entities such as World Vision, UDRC, CCNS and MTTTC in cooperation with the Ministry of Environment and Tourism, Municipality of Ulaanbaatar city, Governor's offices of Bayanzurkh, Songinokhairkhan and Sukhbaatar districts and target subdistricts and their Ger-communities as an integral part of the UN-Habitat Mongolia Country Programme with inputs from the UN-Habitat Climate Change in Cities Initiative through the Regional Office for Asia and the Pacific. The seven target Ger communities in Ulaanbaatar are characterized by a high exposure to multiple climate hazards ranging from wind and dust storms, air pollution, and particularly by floods - cited as the main climate issue that required addressing by the communities - during the rapid needs assessment. Climate sensitivity is underpinned by rapid urbanization and population growth, leading to people residing in high-risk areas, in unsanitary conditions engaging in unhygienic behaviour, which exacerbates public health risks. Underlying vulnerabilities are poverty, limited social ties, limited access to basic services, gender inequalities and environmental degradation. Moreover, the adaptive capacities at household, community and governance level are barriers for change due to very limited knowledge and awareness of risks and their own vulnerability. Project investments will alleviate vulnerabilities and dismantle identified barriers by implementing four interconnected components: Component I: Improving the knowledge on flood hazard and risk exposure and vulnerability for these areas. Component II: Improving the resilience and adaptive capacity of the Ger settlements through a Community-Based approach (i.e. building social cohesion per Khoroo). Component III: Increasing resilience ger area physical infrastructure and services, supported by enhanced capacities of responsible district level and khoroo authorities. Component IV: Strengthened institutional capacity to reduce risks and capture and replicate lessons and good practices.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | MNG/MIE/DRR/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mongolia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Ulaanbaatar city northern Ger-Area (including the three high risk target districts covering the ten most vulnerable khoroos) 1. Songinokhairkhan district (SkhD): 7, 24, 25, 40, 41, 42nd khoroo; 2. Bayanzurkh district (BZD): 9th khoroo; and, 3. Sukhbaatar district (SBD): 12, 13, 16th khoroo | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-07-16
IE-AFB Agreement Signature Date: |  | 2018-09-24 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-02-28 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2021-05-01
| Terminal Evaluation Date: | 2023-02-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
1. Reports: a) Inception report b) Quarterly report to ROAP c) Annual PPR 2020 to AF
|  | 2. Advocacy materials: 1 pager Project Introduction, Project Brochure in Mongolian and English, 2 posters with project information | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.frugamongolia.com | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Enkhtsetseg Shagdarsuren, Project manager, UN-Habitat Mongolia | Dominican Republic
| Email: | enkhtsetseg.shagdarsuren@un.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Batjargal Zamba, Special Envoy for Climate Change | Equatoral Guinea
| Email: | z_batjargal@yahoo.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laxman Perera, Project Leader, Human Settlements Officer, UN-Habitat Regional Office | Fiji
| Email: | laxman.perera@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | World Vision International Mongolia (WVIM) | Georgia
| Email: | munkhbayar_bayasgalan@wvi.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Climate Change Impact on Society NGO (CCNS) | Grenada
| Email: | ccnsmongolia@gmail.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Mongolian Taiwanese Technology Transfer Center (MTTTC) | Guyana
| Email: | daniduudee@gmail.com | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 1 March 2021
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement as of 1 March 2021 | 2216555
Add any comments on AF Grant Funds. (word limit=200) | 75% of the funds received up to now have been utilized for the project implementation.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1One (1) Ulaanbaatar northern Ger Area Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction - building on 1.21 | 100485.53
| Output 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established | 52640.23
| Output 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people | 95919.15
| Output 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 | 6100.7037
| Output 2.2 Khoroo community level interventions operation & maintenance and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. An Estimated 20.nos. of trainings | 104172.13
| Output 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3. | 42064
| Output 3.1 Physical assets developed in response to climate change related flood impacts as prioritized by Khoroo communities the core concrete interventions are flood protection and drainage infrastructure5 and resilient sanitation6 to reduce floods impacts – implemented through community contracting. | 1187303.77
| Output 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services | 171859.9
| Output 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate mechanisms. & Output 4.2 Workshops and trainings will be organised targeting city- and district government officials (50 percent women where possible) with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans | 79088.8353
| Output 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity | 54496
| PROJECT EXECUTION COST | 182802.51
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 139622.66
| TOTAL | 2216555.419
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 One (1) Ulaanbaatar northern Ger Area Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction - building on 1.21 | 16341 | 2021-12-31
Output 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established
| Output 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people | 37334 | 2021-12-31
| Output 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 | 5000 | 2021-12-31
| Output 2.2 Khoroo community level interventions operation & maintenance and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. An Estimated 20.nos. of trainings | 38950 | 2022-02-01
| Output 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3. | 15147 | 2021-12-31
| Output 3.1 Physical assets developed in response to climate change related flood impacts as prioritized by Khoroo communities the core concrete interventions are flood protection and drainage infrastructure5 and resilient sanitation6 to reduce floods impacts – implemented through community contracting. | 1012661 | 2021-12-31
| Output 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services | 100150 | 2022-02-01
| Output 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate mechanisms. & Output 4.2 Workshops and trainings will be organised targeting city- and district government officials (50 percent women where possible) with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans | 55000 | 2022-02-01
| Output 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity | 26525 | 2022-02-01
| PROJECT EXECUTION COST | 91000 | 2022-02-01
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 118839.18 | 2022-02-01
| TOTAL | 1516947.18
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental/social:
Current climate and seasonal variability and long winters (October – April) result in infrastructure construction delays | The project has not experienced to the date any delay related to this risk. | To avoid any climate-related delay, the PIU and IP team prepared an intensive work plan to complete all procurement and contractual processes to select a construction company by the end of April. The selected company could then utilize the entire construction season starting from 1 May 2020 and ending on 15 October for the construction activities.
Institutional:
Loss of government support (at ministerial and municipal level) for the project (activities and outputs) may result in lack of prioritization of AF project activities | The project has not experienced to the date any problem related to this risk. | During the reporting period, the Project Working Group met eight times and provided directives for the project implementation. Also, sub-working groups in the three target districts were very active and provided support in project implementation.
Loss of government support (at Khoroo / community level) for the project (activities and outputs) may result in lack of prioritization of AF project activities; Due to communist history and many immigrant communities, organisation is limited. | The project has not experienced to the date any problem related to this risk. | The PIU and IPs have been working closely with the target khoroo administrations, regularly engaging them in-field activities and community consultations. Khoroo governors and officers have supported the project by liaising with the communities, validating the community action plans, supporting the community initiatives under the project, and providing meeting venues.
Communities may not adopt activities during or after the AF project, including infrastructure maintenance | The project has not experienced to the date any problem related to this risk. | As the project supports the local communities in building their resilience for flooding and climate change and improving the quality of life, the communities have been very active. So far, 334 community events have been organized in the target ten khoroos attended by 5832 community members with 64.2% women's participation. The events include 183 community consultations for community mobilization and organization for resilience building, nine workshops for community action planning for resilience building, 142 trainings for disaster risk reduction and mitigation, environmental hygiene, disinfection and disease prevention, waste management, operation & maintenance, climate change and flood risk awareness-raising, sustainable resilience building, and People's Process. As a result of the community mobilization and organization activities, 49 primary groups (representing 603 households) and 5 Community Development Councils (one in Khoroo 9, one for Khoroo 7, 24, 25, 40, 41 and 42, one in Khoroo 12, one in Koroo 13, one in Khoroo 16) were established and trained to be key stakeholders for climate resilience building at their neighborhood areas.
A lack of coordination between and within national government Ministries and Departments. | The project has not experienced to the date any problem related to this risk. | The PIU and IPs work closely with PWG and NDA, regularly updating and engaging them to the extent possible. During the reporting period, Project Working Groups met eight times and provided directives and support to the project. The sub-working groups in the three target districts were very active and supported in the project implementation.
Financial:
Inflation and instability of the national currency leading to budget issues and increased prices for infrastructure delivery | The COVID-19 related restrictions by the government have been impacted the socio-economic sectors of the country. One of the results so far, there is a drastic increase in the costs of imported construction materials. However, the risk was not significant for the project to the date. | The cost increase of construction material did not impact the project implementation during the reporting period. The project team mitigated the potential risk by putting the prior requirements for selecting the construction companies. The companies were selected based on their years of experience in constructing flood control facilities and financial credibilities.
Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | The project has not experienced to the date any problem related to this risk. | The PIU worked closely with ROAP and IPs to avoid delays and integrity issues in administrative and procurement processes.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Infection of significant number of project team members with COVID-19 may result in delays of project implementation until full recovery of the team members | No one in the project team was confirmed with COVID-19. | The PIU requests all the PEU and IP team members to take all necessary measures to prevent the COVID-19 transmission. All the team members were encouraged to get vaccinated.
A partial lockdown of the target areas as preventive measure of the government against COVID-19 spread may result in delays of the project implementation | There were partial lockdowns in the target khoroos and also the complete lockdown of the city was announced 3 times in 2020. | During the three times of complete lockdown of the city (Mar 2020, Nov-Dec 2020, Feb 2021), the PIU and PEU members worked from home. The project activities, including the community consultations, meetings, and workshops, were organized using online tools. The construction activities implemented from August to October 2020 were not affected by the lockdowns.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
COVID-19 outbreak was the main unprecedented risk in 2020 for the project implementation. The modality of working from home was applied to all team members of the PIU, PEU, and IP to mitigate COVID-19 infection risk for the project staff members. No one in the team was infected with the virus during the reporting period. Therefore, no significant delay occurred in the project implementation in 2020.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law: Risk of Insufficient alignment with laws and technical standards, especially related to implementation of concrete interventions under components 3 |  |  | Insufficient alignment with laws and technical standards, especially related to implementation of concrete interventions under components 3 | References to standards and laws to which the activity will need to comply will be included in all legal agreements with all sub-contractors, including steps and responsibilities for compliance. | Check list | N/A | The project procured all activities following the procurement rules and regulations. The PIU and EEs have been working under the directives and support of the Project Working Group and Sub-working Groups in the target districts to ensure the compliance of the technical standards during the design development under component 3 and land use plan development under component 1. The final designs of construction activities were examined by the Construction Development Center under the Ministry of Construction and Urban Development against the national building standards and norms and approved for implementation. The construction activities were also done and supervised according to Mongolian law. | None
2 - Access and equity: (Unintentional) risk of excluding any potentially affected stakeholders from fully participating in decisions that may affect them; risk of unequal distribution among target population / communities and households of project benefits. |  |  | No specific concerns of unfair treatments have been raised during consultations, but this can still occur (unintentionally) during project implementation | 1. Community organization processes (through Community Development Councils) and quotas (> 50 percent women and to-be-defined percentages for other groups) will be used to ensure vulnerable groups are represented during meetings, trainings, decision-making. 2. For the drainage interventions, all households potentially affected by the construction of the channels are included in decision-making processes. 3. For the latrines, criteria for beneficiaries’ selection (including poverty rate, women-headed households, willingness to make contribution) have been established but will be confirmed again with community members / vulnerable groups once the project starts | Meeting attendance sheets with quota numbers and photographs |  | Sex disaggregated databases for meetings and community profiles were developed and maintained by the EE field staff and monitoring officer to ensure the beneficiaries' equal participation. UN-Habitat and EE have established a grievance redress mechanism for the project that uses communication tools accessible for target communities such as grievance boxes in the target areas, project email, phone call and message, Facebook page, and website. A template for complaint was developed and placed at the target khoroo offices to provide the target communities an accessible, transparent, fair, and effective means of communication if there are any concerns regarding project implementation. EE field staff and community leaders were provided training in procedures for receiving messages, recording, and reporting of any grievances. The Grievance Redress system information is published on the project website and Facebook page and placed in the target khoroo offices to allow communities to voice their opinions or complaints. Email and post addresses of the AFB, PIU, and PEU are published on the project website and FB page. | None
3 – Marginalized and vulnerable Groups: (Unintentional) risk of excluding vulnerable and marginalized groups from being involved drainage intervention activities |  |  | No specific concerns of inequitable or discriminatory practices have been raised during consultations, but this can still occur (unintentionally) during project implementation. | 1. Community organization processes (through Community Development Councils) and quotas (> 50 percent women and to-be-defined percentages for other groups) will be used to ensure vulnerable groups are represented during meetings, trainings, decision-making. 2. For the drainage interventions, all households potentially affected by the construction of the channels are included in decision-making processes. 3. For the latrines, criteria for beneficiaries’ selection (including poverty rate, women-headed households, willingness to make contribution) have been established but will be confirmed again with community members / vulnerable groups once the project starts | Construction of foot bridge - Check drainage channel dimensions before construction - Consultation notes |  | Sex disaggregated databases for meetings and community profiles were developed and maintained by the EE field staff and monitoring officer to ensure the beneficiaries' equal participation. UN-Habitat and EE have established a grievance redress mechanism for the project that uses communication tools accessible for target communities such as grievance boxes in the target areas, project email, phone call and message, Facebook page, and website. A template for complaint was developed and placed at the target khoroo offices to provide the target communities an accessible, transparent, fair, and effective means of communication if there are any concerns regarding project implementation. EE field staff and community leaders were provided training in procedures for receiving messages, recording, and reporting of any grievances. The Grievance Redress system information is published on the project website and Facebook page and placed in the target khoroo offices to allow communities to voice their opinions or complaints. Email and post addresses of the AFB, PIU, and PEU are published on the project website and FB page. | None
4 – Human rights: Tenure arrangements and property rights are violated in the three northern drainage sections in Khoroo 7 |  |  | Although land is public (along the road) for most of the proposed drainage channels, the proposed drainage in the norther three section of Khoroo 7 planned to go through 37 plots. | Community Development Councils will be formed with membership of all households benefitting from construction. The design of drainage sections will be managed in neighborhood sections which are small enough so that they can be managed by these Community Development Councils. Construction of the drainage channels will only start when all possibly affected households sign that they agree with the intervention. This will be done through a participatory planning process through the Community Development Councils. Besides that, a clause will be included in all contracts stating that contractors will comply to human rights markers (and other relevant safeguard areas). The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need to temporary relocate during construction. Moreover, an alternative drainage plan has been developed (and has already been considered) if inhabitants don’t agree. The UN-Habitat Human rights officers and PAG will check compliance. The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need to temporary relocate during construction. References to relevant Humans rights declarations will be included in all legal agreements with all sub-contractors. | Signed sheet Check contracts on HR markers |  | As per the layout design of the flood control facilities planned in khoroo 40, four private residential plots and one private company were affected. Consultations were held with affected plot owners and company, design firms, and CDC, slight realignement was applied without affectign the expected results fo the design to keep the affected land and assets as minimum. With that, the project reached an agreement with the plot owners and company to install the drainage channel through the plots with the minimum inconvenience so the potential involuntary resettlement was avoided for the plots. | None
5 – Gender equality and women’s empowerment: Unintentional) risk of not providing fair and equitable access to employment opportunities for women |  |  | No specific concerns of inequitable or discriminatory practices have been raised during consultations, but this can still occur (unintentionally) during project implementation. | Measure to ensure equal participation in planning and decision-making processes for women and to enable them as agents of change: It will be ensured women will be able to participate through participation quota. The project included gender targets and involves existing women committees at Khoroo level and women representatives at the ministerial level. Trainings only inviting women will be organized as necessary. |  |  | Sex disaggregated databases for meetings and community profiles were developed and maintained by the EE field staff and monitoring officer to ensure the beneficiaries' equal participation. UN-Habitat and EE have established a grievance redress mechanism for the project that uses communication tools accessible for target communities such as grievance boxes in the target areas, project email, phone call and message, Facebook page, and website. A template for complaint was developed and placed at the target khoroo offices to provide the target communities an accessible, transparent, fair, and effective means of communication if there are any concerns regarding project implementation. EE field staff and community leaders were provided training in procedures for receiving messages, recording, and reporting of any grievances. The Grievance Redress system information is published on the project website and Facebook page and placed in the target khoroo offices to allow communities to voice their opinions or complaints. Email and post addresses of the AFB, PIU, and PEU are published on the project website and FB page. | None
6 – Core labour rights: Non-compliance to ILO standards when contracting community members |  |  | At the local level there is limited knowledge of ILO standards and procedures and communities often work informally | Employment and working conditions following ILO standards will be included in legal agreements with all subcontractor. The project will monitor that international and national labour laws and codes are respected, for any work that may be carried out in relation to the project. This includes the eight International Labour Organization Convention (ILO) core labour standards related to fundamental principles and rights of workers, as well as ILO Convention No. 169, which concerns rights of indigenous and tribal peoples. | Check contract and signs |  | IE and EE have assured that all contract documents with subcontractors require adherence to ILO standards for employment and working conditions. The subcontractors must monitor that international and national labour laws and codes are respected during project implementation. | None
7 – Indigenous peoples |  |  | Indigenous groups may not participate in decisions making processes regarding design and planning of activities that may affect them. | No indigenous groups have been identified in the target areas |  |  | Sex disaggregated databases for meetings and community profiles were developed and maintained by the EE field staff and monitoring officer to ensure the beneficiaries' equal participation. UN-Habitat and EE have established a grievance redress mechanism for the project that uses communication tools accessible for target communities such as grievance boxes in the target areas, project email, phone call and message, Facebook page, and website. A template for complaint was developed and placed at the target khoroo offices to provide the target communities an accessible, transparent, fair, and effective means of communication if there are any concerns regarding project implementation. EE field staff and community leaders were provided training in procedures for receiving messages, recording, and reporting of any grievances. The Grievance Redress system information is published on the project website and Facebook page and placed in the target khoroo offices to allow communities to voice their opinions or complaints. Email and post addresses of the AFB, PIU, and PEU are published on the project website and FB page. | None
8 – Involuntary resettlement: Risk of (unintentional) involuntary resettlement |  |  | Although inhabitants (including directly affected) proposed and agreed with the planned drainage in Khoroo 7, which will go through 37 plots during the 2nd and 3rd round of consultations, the project needs to ensure inhabitants are not resettled involuntarily | Community Development Councils will be formed with membership of all households benefitting from construction. The design of drainage sections will be managed in neighborhood sections which are small enough so that they can be managed by these Community Development Councils. Construction of the drainage channels will only start when all possibly affected households sign that they agree with the intervention. This will be done through a participatory planning process through the Community Development Councils. Besides that, a clause will be included in all contracts stating that contractors will comply to human rights markers (and other relevant safeguard areas). The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need to temporary relocate during construction. Moreover, an alternative drainage plan has been developed (and has already been considered) if inhabitants don’t agree. The UN-Habitat Human rights officers and PAG will check compliance. The intervention is budgeted in a way that inhabitants can be compensated for expenses if they need to temporary relocate during construction. | Signed sheet Check contracts on HR markers |  | As per the realigned layout design of the flood control facilities planned in khoroo 40, four private residential plots and one private company were affected. As a result of the consultations between the affected plot owners and company, design firms, and CDC, an alternative layout design was designed by slightly shifting the layout to minimize the effect and inconvenience and avoid any involuntary resettlement. | None
9 – Protection of natural habitats |  |  | The intervention is not within or adjacent to critical habitats and/or environmentally sensitive areas | 1.The project will ensure the principle will be taking into account when developing land use plans and technical studies, thus ensuring compliance to the AF ESP also for the ‘supporting’ measures under component 1-2. Standard clauses requiring the compliance with the safeguard areas will be included in AoC and contracts and the plans will be screening for consideration of the risk areas. 2.Although the practice is that soil and rocks are purchased through Mongolian companies, a risk preventive measure is proposed to ensure these are not mined from areas where it can have a negative effect, such as from the river. This will be done by checking the sources of material before purchase by companies. |  |  | The Agreements of Cooperation between UN-Habitat and EEs for Output 1 included a requirement for compliance with the principle. The final reports and plans were screened for consideration of the risk areas. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, included detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. | None
10 – Conservation of biological diversity |  |  | The intervention has no impact on biodiversity (see also above) | 1.The project will ensure the principle will be taking into account when developing land use plans and technical studies, thus ensuring compliance to the AF ESP also for the ‘supporting’ measures under component 1-2. Standard clauses requiring the compliance with the safeguard areas will be included in AoC and contracts and the plans will be screening for consideration of the risk areas. 2.Although the practice is that soil and rocks are purchased through Mongolian companies, a risk preventive measure is proposed to ensure these are not mined from areas where it can have a negative effect, such as from the river. This will be done by checking the sources of material before purchase by companies. |  |  | The Agreements of Cooperation between UN-Habitat and EEs for Output 1 included a requirement for compliance with the principle. The final reports and plans were screened for consideration of the risk areas. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, included detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. | None
11 – Climate change |  |  | The intervention will not result in significant greenhouse gas emissions or maladaptation | 1.The project will ensure the principle will be taking into account when developing land use plans and technical studies, thus ensuring compliance to the AF ESP also for the ‘supporting’ measures under component 1-2. Standard clauses requiring the compliance with the safeguard areas will be included in AoC and contracts and the plans will be screening for consideration of the risk areas. 2.Although the practice is that soil and rocks are purchased through Mongolian companies, a risk preventive measure is proposed to ensure these are not mined from areas where it can have a negative effect, such as from the river. This will be done by checking the sources of material before purchase by companies. |  |  | The Agreements of Cooperation between UN-Habitat and EEs for Output 1 included a requirement for compliance with the principle. The final reports and plans were screened for consideration of the risk areas. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, included detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. | None
12 – Pollution prevention and resource efficiency: Risk of requiring significant consumption of materials |  |  | Consumption of raw materials will have a negative effect (elsewhere). | 1.The project will ensure the principle will be taking into account when developing land use plans and technical studies, thus ensuring compliance to the AF ESP also for the ‘supporting’ measures under component 1-2. Standard clauses requiring the compliance with the safeguard areas will be included in AoC and contracts and the plans will be screening for consideration of the risk areas. 2.Although the practice is that soil and rocks are purchased through Mongolian companies, a risk preventive measure is proposed to ensure these are not mined from areas where it can have a negative effect, such as from the river. This will be done by checking the sources of material before purchase by companies. | Materials on bills/BOQ’s |  | The Agreements of Cooperation between UN-Habitat and EEs for Output 1 included a requirement for compliance with the principle. The final reports and plans were screened for consideration of the risk areas. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, included detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. | None
13 – Public health:Risk of not ensuring safety measures during construction and maintenance |  | . | At the local level there is limited knowledge of ILO standards and procedures and communities often work informally without safety measures | It will be ensured that ICSC international health and safety standards are clearly accessible and understood. e.g. by putting clearly visible signs detailing health and safety standards to be located at projects sites and by supplying protective equipment. | Check contract and signs |  | The contracts between WVIM, the executing entity, and the construction companies included the Supplier Code of Conduct as an annex, which required that the ICSC international health and safety standards are complied by the contractor. The EE field engineer and the community monitoring team monitored the standards' compliance at the construction sites during the project implementation. | None
14 – Physical and cultural heritage |  |  | No heritage sites were identified in target areas | The project will ensure the principle will be taking into account when developing land use plans and technical studies, thus ensuring compliance to the AF ESP also for non-concrete measures under component 1-2. Standard clauses requiring the compliance with the safeguard areas will be included in AoC and contracts and the plans will. |  |  | The Agreements of Cooperation between UN-Habitat and EEs for Output 1 included a requirement for compliance with the principle. The final reports and plans were screened for consideration of the risk areas. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, included detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. | None
15 – Lands and soil conservation |  |  | The intervention will focus on area where’old fashion’ latrines are already constructed | The project will ensure the principle will be taking into account when developing land use plans and technical studies, thus ensuring compliance to the AF ESP also for non-concrete measures under component 1-2. Standard clauses requiring the compliance with the safeguard areas will be included in AoC and contracts and the plans will. |  |  | The Agreements of Cooperation between UN-Habitat and EEs for Output 1 included a requirement for compliance with the principle. The final reports and plans were screened for consideration of the risk areas. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, included detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. | None
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | During the reporting period UN-Habitat and the Executing Entities, including the Community Development Councils and primary groups, implemented the project ESPM under the national project manager's direct oversight. The Agreement of Cooperation with WVIM, the main Executing Entity of the project, includes detailed reference to the project ESMP and GP. The National Project Manager and EE's monitoring officer have monitored the compliance to the AF ESP. UN-Habitat and EE established a grievance redress mechanism for the project that uses communication tools accessible for target communities such as grievance boxes in the target areas, project email, phone call and message, Facebook page, and website. A template for complaints about the project was developed and placed at the target khoroo offices to provide the target communities an accessible, transparent, fair, and effective means of communication if there are any concerns regarding project implementation. The EE field staff and community leaders were trained in receiving messages, recording and reporting any grievances. The Grievance Redress system information is published on the project website and Facebook page and placed in the target khoroo offices to allow communities to voice their opinions or complaints. Email and post addresses of the AFB, PIU, and PEU are published on the project website and FB
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements were effective during the reporting period.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Sex disaggregated databases for meetings and community profiles were developed and maintained by the EE field staff and monitoring officer to ensure the beneficiaries' equal participation. As per the realigned layout design of the flood control facilities planned in khoroo 40, four private residential plots and one private company were affected. As a result of the consultations with affected plot owners, design firms, and CDC, the agreement was reached with the plot owners and company to construct the drainage channel through the concerned plots with minimum inconvenience so the potential involuntary resettlement was avoided for the plots. Besides the EE field monitoring and supervision, the CDCs conducted community monitoring over the construction activities in Khoroo 40 and 9 in 2020. Thanks to their close monitoring and regular interaction with the neighboring plots, the construction companies could complete their work without any complication and negative impacts to the respective areas.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements at the EE including CDC and communities were effective.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
The project received the following complaints from the residents during the construction of flood dikes in Khoroo 9: 1. (in-person) An owner of a plot requested the project team to shift the dike alignment in Khoroo 9 a bit further from his plot to save his fruit bushes from the construction area. 2. (by phone) A plot owner complained about the blockage of car access to his plot entrance due to nearby excavated earth from the dike construction area. 3. (by phone) A plot owner requested to widen the bridge over the constructed flood channel. The bridge was meant for access by medium-sized cars to the plots from the road over the channel. However, residents found out that big trucks were using the bridge during the night and damaging the bridge's frames. 4. Governor of Khoroo 9 informed about the flooding by the stream which suddenly emerged in the middle of the settlement. The stream water was running along the slope and accumulated near the flood channel, causing flooding. |  | The complaints were recorded in the logbook and addressed as follows, and the project informed the communities in writing through the CDC: 1. The EE worked with the design firm to work on re-alignment. Within one week, the design firm was able to complete the task. 2.The EE communicated with the construction company (CC) and made them remove the earth. Within one day car access was restored. 3.The EE communicated with the CC and conveyed the complaint. The company checked and agreed to make a small improvement within its budget limitation. The bridge improvement was consulted with the design company and neighborhood community and executed by the CC. The ESP compliance was put as a main requirement by the EE for the work and monitored by the EE field engineer during the construction.The process took three days. 4. EE urgently communicated with the CC and requested to make arrangements to drain the accumulated water to the channel. The accumulated water was drained by CC on the spot. However, according to the EE engineer's assessment, there was a potential of a reccurence of the problem when snow melts during next spring. So the EE tasked the CC to consult the design company to fully address the problem. Accordingly, the revised design was sent to Khoroo Governor for information and community consultation. After that the revised design was incorporated into the flood channel design. The flood channel is being constructed now.
The project received the following complaints from the residents during the construction of flood dikes in Khoroo 40: 1. (by phone) One resident complained that the waste collection truck could not access the plots in his locality as the street was blocked due to the ongoing construction of the dike. 2. (by phone) One resident complained that the construction company put the excavated soil blocking access to his plots. 3. (by phone) One resident complained that the construction company did not properly restore the street after its completion of the construction work, and the cars were getting stuck in the loose soil. 4. (by phone) Two complaints were received from the residents during and after installing the street lights. The company cut the electricity for few hours for installation. Few of the street lights did not work after the restoration of the electricity |  | The complaints were recorded in the logbook and addressed as follows, and the project informed the communities in writing through the CDC: 1. EE requested the construction company (CC) to provide access for the truck as needed. 2. The excavated soil was temporarily shifted by the CC as it was required for later refilling. The CC explained this in writing through the CDC. 3. The CC rechecked the area and leveled and compacted the uneven surfaces. 4. The CC brought in the district electricity company to fix the technical problem.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Note on J16: Laxman:

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | During the project preparation phase, the gender assessment had been done through desk research, surveys, women focus group discussions and community needs assessments. UN-Habitat headquarter gender specialist had been involved in the project preparation/review process to ensure compliance with the AF Gender Policy as well as the UN-Habitat gender mainstreaming guidelines.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The result framework includes gender-responsive indicators at outcome and output levels.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Women participating in planning process | Output 1.1. | Women participation by percentage | 0 | > 50 % | good
Women participating in planning process | Output 1.3. | Women participation by percentage | 0 | > 50 % | good
Women participating in planning process | Output 2.1. | Women participation by percentage | 0 | > 50 % | good
Number of awareness campaigns and trainings | Output 2.2. | Women participation by percentage | 0 | > 50 % | good
Toilets | Output 3.1 | Toilets are appropriate for women, elderly and disabled. | 0 | >50 % of toilets adapted to specific needs | satisfactory
Women participating in planning process | Output 4.1. | Women participation by percentage | 0 | > 50 % | good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
The Project Working Group has 13 members, including the chair and co-chair. The members were nominated based on their functional titles at the Ministry of Environment and Tourism and in the Municipality. When the PWG was established, 23% of the members were women. After the municipal election in 2020, some of the members were replaced by new ones. The new mayor was appointed in December 2020, and another restructuring is ongoing. So the gender composition of the PWG is expected to change again. |  | The National Project Manager requested the PWG and District sub-working groups to maintain the women's representation at 35-40% as a minimum when they have a meeting. In case women are under-represented, women representations from the member organizations were to be invited. So far, the result of the arrangement has been satisfactory. The project team has been able to have the meetings with women's participation rate as required.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | As a gender focal point for the project, the national project manager of the Implementing Entity has been monitored the activities of the PWG, Sub Working Groups at the districts, EEs and beneficiary communities for the compliance of the gender policy of the project. EE were requested to submit the sex disaggregated reports on quarterly and delivery basis. The Project Working Group and District Sub Working Groups were requested to have their meetings at least with 35-40% women representation by inviting women representations from the member organisations when women are under-represented.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. The sex-disaggregated data regularly reported by EE shows the state of gender equity and whether there is a need for additional measures for improvement.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | 1. A template for recording attendance at meetings is being used for gender-specific data collection. 2. An Excel database has been maintained by the monitoring officer and field staff of EE to monitor the participation and gender equity during the project implementation. 3. A template for community consent from the primary group was developed for sex-disaggregated data collection. 4. A community profile database was developed to monitor gender equity in the community organizations' composition and is being used for data collection.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes. With the help of the above tools, EE has monitored gender equity and women empowerment. Data shows that 43 women (51.2%) hold the leadership position in the PG groups. In 21 of the 28 PG groups, there are women in leadership positions. 28 Primary Groups (PG) have been established representing 357 households. One hundred thirty women members represent their households. The collected data shows that women's engagement in different activities under EEs is more than 50%.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Capacity Building Strategy:
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
The following feedback and complaints were received in regard of the improved toilet design: 1. The seat design of the newly constructed toilets by the community is somewhat problematic for person with disabilities. A toilet seat should have support at both sides where elderly or disabled can push on both hands. 2. The insulation of the outdoor toilet is good in a way of protecting from wind and cold especially for women and girls. But it causes a frosting inside of the toilet during winter and makes the floor slippery. 3. A support handle needs to be installed at both sides of the wall to help disabled. 4. A wastewater holding tank for a latrine and household grey water should be separate as the greywater disposal from washing fills up the tank and makes the latrine useless. It is hard especially during the winter. |  | The complaints were recorded in the logbook and addressed as follows, and the project informed the communities in writing through the CDC: 1. The EE team worked with the communities and changed the seat design to have hand support on both sides. 2. The EE team worked with communities on the toilet chamber design and added a small window to release humidity during winter. 3. The support handles were solved with the integration of the No. 1 solution above. 4. As an additional holding tank construction has a cost implication, the EE proposed that the communities put a subdivision in the holding tank to separate the greywater and feces collection.
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Objective is to enhance the climate change resilience of the seven most vulnerable Ger khoroo settlements focusing on flooding in Ulaanbaatar City.
Outcome 1: Relevant threat, hazard information, evidence and recommendations (on land use and zoning) generated for increasing resilience at the city level.
| 1.1 One (1) Ulaanbaatar northern Ger-Area Territorial Land Use Plan, with legal framework recommendations and a specific focus on flood risk reduction -building on 1.2 (includes the three (3) high risk target districts covering the seven (7) most vulnerable khoroos) |  | A northern Ger-Area Territorial Land Use Plan is developed. |  | 1. UN-Habitat signed an AOC with the Mongolian Taiwanese Technology Transfer Centre (MTTTC) NGO for the deliveries of Output 1.1 and 1.3 in July 2019. The consultant completed the assignment on 31 December 2020. 2. The compilation, assessment, and analysis of data collected for Ulaanbaatar city's northern ger areas and ten target khoroos related to Output 1.2 were completed. A draft land use regulation with the maps of high flood risk areas and recommendations for spatial development and land use plans for northern ger areas and ten target khoroos were prepared and finalized through stakeholder consultations. 3. Two consultative workshops were held in Ulaanbaatar city on 10 October and on 17 December 2020 to discuss the main findings and outcomes of the studies under Output 1 that fed into the policy documents' development. Total 87 persons (45 male and 42 female) from line departments of UB city, research and science institutions, khoroo and district Governments, locals, primary groups, and CDCs participated in these workshops. The national consultant team received valuable recommendations and comments from the participants, which were crucial to improving the studies' quality. The second consultative workshop with urban planning, land management, and urban standards departments was organized online and attended by 67 participants. 4. The consultant submitted the land use plan for the northern ger area (final report) to the FRUGA project team in Mongolian and English. | satisfactory
| 1.2 Simulation model for forecasting future impacts of climate change flooding in UB city & Ger-areas established. |  | The city wide simulation model forecasting impacts of the current and future Climate Change and flooding, which includes a) simulation of extreme flood case using hydro meteorological model; b) projection and downscaling of climate change and extreme event (flood, heat wave etc) frequency and intensity; c) flood producing rainfall intensity analysis around the Ulaanbaatar city; d) impact and risk assessment of flood on targeted area is developed. |  | 1. The UN-Habitat signed an AOC with the Climate Change on Nature and Society (CCNS) NGO for the delivery of Output 1.2 in July 2019. The consultant completed the assignment on 31 December 2020. 2. The consultant started the assignment with participatory data collection, mapping, and preliminary study to prepare a simulation model for forecasting future impacts of climate change and flooding in UB city & Ger-areas (Output 1.1 and 1.3). Maps of current flood risks and projected risks for 30, 50, and 80 years for UB city, northern ger areas, and target ten khoroos were developed using the model. 3. The Consultant presented their findings and maps of current and future food risks to the project stakeholders, including the target areas' communities. 4. The Consultant submitted the final report in Mongolian and English. | satisfactory
| 1.3 Seven (7) Detailed Ger-khoroo level Land Use Plans with specific focus on flood risk reduction and building resilience of the most vulnerable areas and people |  | The Detailed Ger-khoroo level Land Use Plans for the 7 most-at-risk Ger-areas are developed. |  | 1. UN-Habitat signed an AOC with the Mongolian Taiwanese Technology Transfer Centre (MTTTC) NGO for the deliveries of Output 1.1 and 1.3 in July 2019. The consultant completed the assignment on 31 December 2020. 2. The compilation, assessment, and analysis of data collected for Ulaanbaatar city's northern ger areas and ten target khoroos related to Output 1.2 were completed. A draft land use regulation with the maps of high flood risk areas and recommendations for spatial development and land use plans for northern ger areas and ten target khoroos were prepared and finalized through stakeholder consultations. 3. Two consultative workshops were held in Ulaanbaatar city on 10 October and on 17 December 2020 to discuss the main findings and outcomes of the studies under Output 1 that fed into the policy documents' development. Total 87 persons (45 male and 42 female) from line departments of UB city, research and science institutions, khoroo and district Governments, locals, primary groups, and CDCs participated in these workshops. The national consultant team received valuable recommendations and comments from the participants, which were crucial to improving the studies' quality. The second consultative workshop with urban planning, land management, and urban standards departments was organized online and attended by 67 participants. 4. The final reports with detailed land use plan for 10 target khoroos were submitted to the FRUGA project team in Mongolian and English. | satisfactory
Outcome 2: Target community members are aware of resilience building and climate risk reduction processes and have ownership over proposed interventions at the District, Khoroo and community level.
| 2.1 Seven (7) Khoroo-level floods resilience action plans to implement the interventions identified under component 3; A series of District, Khoroo and community level consultations / workshops (50 percent women where possible) introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3.22 |  | A series of District, Khoroo and community level consultations / workshops introducing the People's Process and Community Based Disaster Risk Reduction approach, focused on building social cohesion and consensus on community level implementation of interventions under component 3 is being held |  | 1. The AOC signed between UN-Habitat and World Vision International Mongolia in 2019 covers the delivery of the first-ever Khoroo-level community action plans for flood resilience building. 2. Between the start of the project and the end of February 2021, the field team organized 192 consultations for community mobilization and organization. The consultations were attended by 2649 representatives of beneficiary communities, with 58.9 percent female participation. 3. The first community action plans for flood resilience building in 10 target khoroos were prepared by the respective khoroo communities in 2019. Seven workshops for community action planning were organized and attended by 158 community members, with 68.3% female participation. 4. Based on the review of the above plans' implementation status, khoroo-level workshops were organized in August 2020 to prepare new action plans for 2020. The community action planning workshops were conducted in 2020 in the ten target khoroos as follows: on 25 August in 24, 41, 40, 7, 25 and 42nd khoroos, on 28 and 31 August in 13, 12 and 16th khoroos, and on 26 August 2020 in 9th khoroo. These planning workshops were attended by 204 community members, with 64.7% female participation. The communities will repeat this exercise in 2021 to prepare plans for 2022. | satisfactory
| 2.2 Khoroo community level interventions operation & maintenance and awareness campaigns and trainings (50 percent women where possible) to support the sustainable implementation of interventions under component 3. An Estimated 20.nos. of trainings *(Awareness will also cover potential risks mitigation) |  | The communities are being involved in the planning and execution of the proposed interventions under component 3; to ensure the proper operation and maintenance (and implementation of potential risk mitigation measures) of these interventions through community involvement. |  | 1. Under the AOC with WVIM, various trainings on community organizations were conducted to organize target khoroo communities into community organizations. The objectives for the formation of community organizations were a) to support the implementation of the project through community participation and monitoring and b) to further ensure the sustainability of the project achievements in terms of flood resilience after the project completion. 2. During 2019, the field team organized 54 consultations at the community level and 36 at the primary group level. As the results, 451 households (13 in khoroo 9, 5 in Khoroo 7, 6 in Khoroo 24, 5 in Khoroo 25, 4 in Khoroo 40, 1 in Khoroo 41, 1 in Khoroo 42, 4 in Khoroo 12, 7 in Khoroo 13, 8 in Khoroo 16) formed their groups. 3. The community organization trainings continued during 2020. The field team organized 88 consultations at the community level. The process resulted in the formation of 49 primary groups (representing 603 households) and 5 Community Development Councils (one in Khoroo 9, one for Khoroo 7, 24, 25, 40, 41 and 42, one in Khoroo 12, one in Koroo 13, one in Khoroo 16). The Community Development Councils (CDC) were established with the composition of the leaders and deputy leaders of the primary groups of the khoroo through a CDC formation workshop in each project khoroo. Ninety-four people (70.2 percent female) attended CDC formation workshops. 4. The project organized the following capacity-building activities for the target primary groups, CDCs, local people, and kheseg leaders until December 2020, taking sufficient preventive measures against the Covid-19 transmission. - Two Trainings of Trainers on Disaster preparedness were conducted in December 2019 attended by 72 and 31 community members. The following year the community trainers, with assistance from project social organizers, completed ten subsequent training on disaster preparedness and mitigation. Two hundred sixty-five community members (65.28% female) participated in these trainings. - 10 trainings on environmental hygiene and disinfection were organized and attended by 116 community members (94.83% female). - 3 trainings on lessons learned and best practices for community organisations were organized and attended by 324 community members (72.24% female). - 13 trainings on Operation & Maintenance; Awareness Campaigns; Sustainable Implementation were organized and attended by 161 community members (74.53% female). - One training on household finance management with a focus on creating savings was organized and attended by 20 community members (70% female). The purpose of this training was to facilitate the community members to come up with ideas for a collective fund creation for emergency use to help each other. - 3 training on project proposal preparation for resource mobilization at the khoroo level was organized and attended by 66 community members (63.64% female). - 9 trainings on community monitoring were organized and attended by 75 community members (72% female).
| 2.3 Technical studies – Engineering and hydrological - required to implement the interventions under component 3. |  | The engineering and hydrological studies for the implementation of the flood protection and drainage infrastructure are completed. |  | 1. On 25 October 2019, WVIM signed a contract with BD Engineering Company for a hydrology study and preparation of detailed engineering design for the required flood interventions in the target khoroo areas. 2. Based on its hydrology study, the Consultant proposed constructing the below facilities to protect the population in the target khoroos, and they prepared the detailed engineering designs: - 3 Drainage channels in khoroo 40 - 1 Flood retention dike in khoroo 24 - 1 Drainage channel in khoroo 9 - 1 Flood protection channel in khoroo 9 - 1 Flood retention dike in khoroo 9 - 2 Drainage channels in khoroo 13 - 1 Flood retention dike in khoroo 16 | satisfactory
Outcome 3: Increased adaptive capacity within prioritized community assets
| 3.1 Developing or strengthening physical assets in response to climate change related flood impacts as prioritized by Khoroos. |  | As a response to the Khoroo-specific climate change resilience building needs and intervention prioritization by communities, flood control facilities and flood resilient latrines are being developed by the communities |  | 1. In September 2020, AFB approved UN-Habitat's proposal to realign the drainage infrastructure planned under this output in Khoroo 40 (former Khoroo 7) 2. The project published the list of the proposed infrastructure and the below mentioned physical assets prioritized by Khoroo communities in response to climate change-related flood impacts on the local newspaper and WVIM and UN Mongolia websites for the selection of companies to construct: o Drainage channel SO1 in khoroo 40 o Drainage channel SO3 in Khoroo 40 o Drainage channel B2 in Khoroo 9 o Flood retention dike B1 in Khoroo 9 3. Three construction companies were selected and contracted according to the WVIM procurement rules and regulations and started their work in 2020. By the end of 2020, the construction of the drainage channels SO3, and B1 were completed. As the construction season ended, the construction companies suspended the work on the SO1 channel with 90% and B2 flood channel with 80% completions. The companies will resume their work as soon as the construction season starts in 2021. | satisfactory
[5 empty] | • Works through Community Implementation Agreement (CIA): the communities constructed 203 new outdoor toilets adapted to the specific needs of women, children, disabled people, and the elderly with support from the project team. With these interventions, 1600 people from 410 households now have improved sanitation facilities. The project delivered nine indoor portable toilets to the nine households with who have a disabled person. | satisfactory
| 3.2 Management & operations; design & supervision of assets / physical infrastructure to comply with national and local regulations and processes – procured as consulting services |  | Respective procurement and financial management of the design preparation, construction and supervision activities for the construction of the flood facilities are being done |  | 1. During 2020, WVIM completed respective procurement and financial management of the design preparation, construction, and supervision activities to construct the flood facilities. 2. The BD Engineering Company was contracted in 2020 for the author's monitoring and supervision for all the construction activities under the contract with WVIM. 3. The WVIM field engineer and planner have completed the client's monitoring and supervision of the flood facilities' construction activities. 4. Monitoring of the toilets' construction has been done by the communities with support from the WVIM social mobilizers. | satisfactory
Outcome 4: Institutional capacity strengthened to develop and replicate this approach.
| 4.1 Lessons learned and best practices regarding flood-resilient urban community development are generated, captured and distributed to other Districts and khoroo communities, civil society, and policymakers in government appropriate |  | Lessons learned are being captured; and municipal and district level government officials exposed to these principles and trained on lessons learned to ensure buy-in and the sustainability of this project for effective replication of best practices. |  | • WVIM Monitoring and reporting officer has been conducting regular monitoring and evaluation of the overall project implementation, prepared and submitted progress reports to UN-Habitat every quarter. • A sex-disaggregated database for meetings and consultations was developed and maintained to monitor gender equity among the participants. • The lessons learned and best practices during the project have been captured and documented by WVIM social mobilizers for further potential use in similar projects and programs. • The FRUGA Branding Guideline for the project visibility was developed by the PEU team in consultation with the PIU team and used for the project visibility activities. The guideline was developed based on the UN-Habitat Branding Guideline for Donor Visibility and consists of ten parts such as printing materials, branded merchandise, on-site project donor visibility, presentations, audio and visual material, and photographs. • The PEU has maintained the FRUGA Facebook page and website to inform the general public on the project progress, lessons learned and best practices under the project regarding flood-resilient community development and adaptation measures. Over the past five months, 2,181 hits were recorded, with an average of 12 per day. The page had a lifetime “likes” of 55,903. To the date, the page had 381 followers, and 371 people liked it. | satisfactory
| 4.2 Workshops and trainings to be organised targeting city- and district government officials with a focus on replication of processes, land use plans and interventions and to discuss how lessons can be integrated into existing strategies and plans |  | Trainings are being conducted for city- and district government officials from other potential high-risk areas on the project approach and knowledge generated for replication based on demand by the communities and local authorities. |  | • The PIU held the Inception Workshop at two levels (1 national level, 3 district level) to inform the interested stakeholders and beneficiary communities about the project and engage them from the beginning of the project implementation. In total, 237 (67.51% women) representations of the Ministry of Environment and Tourism, Ministry of Construction and Urban Development, Mayor's Office, Municipal Departments, and target Districts and Khoroo; representatives of potential partners and interested parties including UN sister agencies, international communities, non-governmental organizations, individual experts and residents from flood-prone areas attended the workshops and were consulted and informed on the project. The inception workshop at the national level was participated in by 54 persons (57.4 percent women). The workshop in Songino-khairkhan district was attended by 54 (74.07 percent women), in Sukhbaatar by 83 persons (68.67 percent women), and Bayanzurkh by 46 persons (69.57 percent women) participants. • The Project Working Group (PWG) meetings were organized eight times in 2020 and provided necessary, timely support and guidance for the project's design and construction activities. • The project organized meetings of sub-working groups in the districts after PWG meetings (1 in Sukhbaatar District, 3 in Songinohaitkhan District) to inform and discuss the PWG decisions. • For the project visibility, T-shirts, flash drives, and calendar with the AF and FRUGA project logos have been prepared and distributed to the community members and project stakeholders during the project events. The project team members have been using vest jackets with AF and the project's logos during their field activities. • The project posters were designed and published, and used during training and workshops for project information dissemination. • The FRUGA website was developed and has been functional since 25 June 2020 in two languages: Mongolian and English. The website has become an essential tool to share and disseminate information, knowledge, and experience and publicize the project activities and achievements to the public. The PEU team members have been trained to update and maintain the website. Please refer to www.frugamongolia.com for the website.
| 4.3 Technical Support and Coordination: Bringing Global Knowledge on best practices to in country Implementing Partners and communities, customized widely used appropriate tools on adaptation building local capacity |  | Relevant activities have been started |  | On 18-22 November 2019, UNICEF hosted the 2019 World Toilet Day Events and 5th China Toilet Revolution Innovation Expo in Shanghai, China. A group of 20 representatives of FRUGA project stakeholders, including target community members, Governor's offices of two project districts and Ulaanbaatar City, Ministry of Environment and Tourism, and the FRUGA project team participated in the workshop, learned about the experiences and good practices from India, China, Nepal, Pakistan, Cambodia, and Bangladesh and introduced to the proven solutions of the sanitation improvements during the China Toilet Revolution Campaign. All participants acknowledged the workshop's importance for their work and initiated the "MGL toilet revolution" Facebook group to further share relevant information and practices among the group.
[5 empty] | Overall Rating | satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Enkhtsetseg Shagdarsuren, National Project Manager
| Email: | enkhtsetseg.shagdarsuren@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Despite the challenging situation due to the covid-19 outbreak, the project team has made excellent progress, especially in implementing Outputs 1 and 3. Restrictions in travel and holding community meetings/training/workshops that have been put in force in Mongolia since 27 January 2020 were an unprecedented challenge for the project in 2020, particularly for the implementation of Outputs 2 and 4. However, the project team managed to implement the planned activities by applying different alternatives. Online meetings and training were designed and implemented. It has been challenging for the project team to train the community members to organize online workshops and community mobilization activities as the accesses and capabilities of the target area communities to use the internet vary and many limitations.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1: Relevant threat, hazard information, evidence and recommendations (on land use and zoning) generated for increasing resilience at the city level. |  | 90% of the work is completed |  | The development of simulation model, land use plans and legal framework recommendations have been completed during the reporting period. The remaining work is an integration of the land use plans and recommendations in the 2021 annual land management plans of the city and districts and be approved by the Ulaanbaatar City Council for implementation. | satisfactory
| Outcome 2: Target community members are aware of resilience building and climate risk reduction processes and have ownership over proposed interventions at the District, Khoroo and community level. |  | 50% of the planned activities are implemented |  | The planned activities for the reporting period have been completed. | satisfactory
| Outcome 3: Increased adaptive capacity within prioritized community assets |  | 50% of the planned activities are implemented |  | The planned activities for the reporting period have been completed. | satisfactory
| Outcome 4: Institutional capacity strengthened to develop and replicate this approach. |  | 50% of the planned activities are implemented |  | The planned activities for the reporting period have been completed. | satisfactory
[5 empty] | Overall Rating | satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Laxman Perera, Project Leader, Human Settlements Officer, UN-Habitat Regional Office
| Email: | laxman.perera@un.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | See above.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Output 1.1 | Number of territorial land use plans with identified flood risks developed | 0 | Work has been completed. Respective integrations to the annual land management plans of the city and target districts is remaining. | One (1)
| Women participating in planning process | 0 | 52% were women | > 50 % women
Output 1.2 | Number of flood simulation models developed | 0 | The work is completed. | One (simulation model)
Output 1.3 | Number of Territorial land use plans with identified flood risks developed | 0 | The work is completed. The land use plans with consideration of flood risks for 10 khoroos were developed. | Seven (7)
| Women participating in planning process | 0 | 52% were women | > 50 % women
Outcome 2.1 | Percentage of targeted population aware of predicted flood risks and appropriate responses | 0 | 30% of the targeted population have been informed about the flood risks and appropriate response and adaptation measures through their participation in workshops, trainings, and physical involvements in the design and implementation of the flood resilient toilets and planning and implementation monitoring of flood control facilities. | Mid-term: 30 % End: 50 % > 50 % women
Output 2.1 | Number of Khoroo level flood resilience action plans | 0 | Ten (10) Khoroo-level annual Community Action Plans (CAP) developed | Seven (7)
| Women participating in planning process | 0 | 192 consultations for community mobilization and organization were organized from the project start to the end of February 2021. The consultations were attended by 2,649 representatives of beneficiary communities, with 58.9 percent female participation. | > 50 % women
Output 2.2 | Number of awareness campaigns and trainings | 0 | Total 142 consultations and trainings for awareness-raising at the community level were organized (21 in khoroo 9, 6 in Khoroo 7, 8 in Khoroo 24, 6 in Khoroo 25, 10 in Khoroo 40, 2 in Khoroo 41, 3 in Khoroo 42, 11 in Khoroo 12, 8 in Khoroo 13, 10 in Khoroo 16) were organized. | 4 per Khoroo
| Women participating in planning process | 0 | 3,183 community members attended the above consultations and trainings, with 68.6% women participation. | > 50 % women
Output 2.3 | Number of studies | 0 | EE completed a hydrology study. Based on the hydrology study, 6 flood facilities in the target three khoroos were proposed, and the design firm prepared detailed designs. | 1
Output 3.1 | Number of physical assets strengthened, constructed, and/or modified. to reduce or withstand floods | 0 | Construction of two (2) flood channels (Khoroo 7 and Khoroo 9) was 100% completed. Two flood channels (Khoroo 9 and Khoroo 7) are being constructed with 80% and 90% implementation rates, respectively. | Four (4) for the flood protection and drainage intervention: 3x Khoroo 40; 2x Khoroo 9
| Toilets are appropriate for women, elderly and disabled where required | 0 | The communities have constructed 203 improved toilets. 100% of them are adapted to the specific needs of the community | >50 % of toilets adapted to specific needs
Output 4.1 | Number of institutions trained | 0 | Total 16 trainings were conducted and attended by 460 representatives from Ministry of Environment and Tourism, two municipality organizations, and three district governors offices, Mongolian University for Science and Technology and target communty organizations. | >1 municipal >3 districts
| Women participating | 0 | 50.6% women participation | > 50 % women

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project implementation has been put under a risk of a potential delay by the restrictions in organizing community meetings, trainings, and workshops and the ban on international travel since 27 January 2020 imposed by the Mongolian Government to manage the COVID-19 situation. There were citywide and partial lockdowns (1st citywide lockdown was in March 2020, 2nd in November 2020 for two months, and 3rd in February 2021). The staff had to work from home and arrange for online activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Initially, the construction of flood protection facilities in Khoroo 40 (former khoroo 7) was planned to start in April 2020 but had to be postponed. UN-Habitat requested AFB approval to change the flood drainage alignment designed in Khoroo 40. Due to COVID-19 related restrictions, the AFB approval came in September 2020, and the construction work started soon after. Despite the start-up delay, the project team worked closely with the selected companies to complete the maximum amount of work during the remaining construction season. Of the four construction activities started in 2020, two were fully completed, while in the other sites, 80% and 90% of the work was completed.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Along with the 1st PPR submitted in March 2020, UN-Habitat requested approval from AFB to change the alignment of drainage infrastructure planned in Khoroo 40 under Output 3.1. AFB approved the change in September 2020.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | With the planned environmental and social safeguard measures, the project team avoided any negative impacts during the reporting period.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | UN-Habitat National Project Manager worked as a gender focal point, ensuring that gender equity was considered during the implementation of all the activities. Women in the communities were encouraged to participate in the project. Their attendance was tracked and using a sex-disaggregated attendance sheet. Women beneficiaries were very active and instrumental in defining the specific needs of the women, disabled, children, and elderly in terms of flood resilient improved toilet's design and implementation, and application of safety measures for women and children during and after construction of the flood facilities. As per the sex-disaggregated attendance data collection, 63.5% of the total 6292 participants in the project activities such as consultations, meetings, trainings, and workshops were women. 55.1% of members of organized primary groups and CDCs, and 53.09% of community leaders were women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | - The communities contributed in the design of the adaptation measures under the project, bringing in their life experiences to address the climate impact in the daily lives. The interventions have incorporated these lessons and experiences. '- The beneficiaries have been involved in the design of the adaptation measures. So they have been supporting the implementation with a sense of commitment and ownership.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is a high potential for replication and scaling up of the project's activities within and outside the project area. As the beneficiaries were involved in decision-making and implementation, the knowledge and experience will remain in the community. Also, the beneficiary communities were trained as trainers for disaster risk reduction and resilience building. So, they can teach others and share their experiences in and outside the project area.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | - The communities contributed in the design of the project, bringing in their life experiences to address the climate impact in the daily lives. The interventions have incorporated these lessons and experiences. - The beneficiaries have been involved in the design of the adaptation measures. So they have been supporting the implementation with a sense of commitment and ownership.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is a high potential for replication and scaling up of the project's activities within and outside the project area. As the beneficiaries were involved in decision-making and implementation, the knowledge and experience will remain in the community. Also, the beneficiary communities were trained as trainers for disaster risk reduction and resilience building. So, they can teach others and share their experiences in and outside the project area.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | All soft and hard interventions under the project have contributed to the local resilience-building, particularly at the household and community level. The primary purpose of concrete adaptation measures was to address the priorities of the high-risk communities and vulnerable Ger-residents and demonstrate quick improvement in the living condition. The People's Process approach introduced under the project helps and trains the target communities to get organized into and work as community organizations for the disaster resilience building that can be operational even after the project completion.
What measures are/have been put in place to ensure sustainability of the project/program results? | The People' Process approach for community organizations was introduced to ensure the sustainability of the project results. Organized communities will be key stakeholders to maintain the project's achievements and continue the resilience-building activities at the community level.
What measures are being/could have been put in place to improve project/program results? | The community monitoring approach was applied during the implementation of all the activities, assuring participation by the beneficiaries, regularly observing what is going on in the field, and avoiding any negative environmental and social impacts on the ground. Working closely with the consultants and construction companies, the project addressed all safety issues and mitigated any negative impact on the surrounding environment. The beneficiaries were trained in the approach.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Two versions of the project brochures were developed and disseminated to inform the general public and the international community about the project's proposed activities. The leaflet for the general public was in the Mongolian language with simplified content. The one for the international community was in English. Both versions were designed such that the project could add updates as the implementation progressed. The monitoring system was designed to collect sex-disaggregated data for the number of community consultations, meetings, and training; the number of participants; the number of community organizations; and community members, etc.
If learning objectives have been established, have they been met? Please describe. | All the evidence and information on climate change-related impacts and risks in the ten khoroos of northern ger areas of Ulaanbaatar city were generated after consultation with the municipality, target district, and khoroo administrations and communities. These include the simulation model to forecast future climate change and flooding impacts and land use plans considering flood risk for ten target khoroo and northern ger areas of Ulaanbaatar city. The knowledge and information generated by the project were presented during the community consultations to raise awareness about the climate impacts in their regions and possible adaptation measures.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The project team has not faced any difficulties accessing and retrieving existing information relevant to the project as the project team is working closely with the municipality. However, some of the required data were not available or of poor quality. For instance, there is GIS data of the existing flood infrastructure, but it was incomplete.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project's learning objectives provided evidence and information that facilitated the understanding of the project stakeholders and target communities about the climate change and flood impacts and potential risks. Based on their understanding, the communities participate actively in the project to learn and implement adaptation measures and reduce potential risks in their living areas. For the city, district, and khoroo authorities, the study by the project revealed that the city's development policies and plans, including the urban development master plan, lack the consideration about climate change impacts and an urgent need to improve the strategies reflecting potential flood risks.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UN-Habitat
Type of implementing entity | RIE
Country | Mongolia
Region | Asia-Pacific
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 194149 | 89439 | 104710 | Total | 195536 | 90826 | 104710 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 50.6% | 50.22% | 51% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 50 |  | Disaster risk reduction |  | 30 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 44719.5 | 50% | 4: Mostly aware |  | 27247.8 | 30% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 1: Non responsive (Lacks all elements ) |  | Disaster risk reduction | Local | 3: Moderately responsive (Some defined elements) |  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
[6 empty] | 1 | Urban development | Local |  | 1 | Urban development | Local | Land use plan
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
[6 empty] | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 2: Partially not enforced (Most elements not implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.