## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 09th, 2021 - October 10th, 2022
| Project Title: | Strengthening Drought Resilience for Smallholder Farmers and Pastoralists in the IGAD Region Djibouti, Kenya, Sudan and Uganda- DRESSEA
| Project Summary: | The IGAD member states face severe water constraints and prolonged droughts. Moreover, the region faces uncontrolled activities such as deforestation and poor agricultural practices that lead to reduced water retention capacities, surface runoffs, and soil cover losses. Such activities, not only impact negatively on water resources, the environment and other ecosystems that serve as community livelihood sources, but also increase their vulnerability to droughts. Significantly reduced precipitation levels lead to food insecurity, civil strife over water, food and pastures, drying-up of rivers, streams and aquifers, as well as loss of plant available water in the soils on which smallholder farmers and pastoralists derive their livelihoods. The "Strengthening Drought Resilience for Smallholder Farmers and Pastoralists in the IGAD Region" proejct is a regional project, funded by the Adaptation Fund for a period of 4 years with a cost 13 079 KUS$. The DRESSEA project aims at providing support to promote and increase the resilience of smallholder farmers and pastoralists to drought-related climate change risks by establishing appropriate early warning systems (EWS) and by implementing drought adaptation actions in the IGAD region.The project targets to consolidate synergies and adopt innovative and resilient drought management actions from selected IGAD region countries including Djibouti, Kenya, Sudan and Uganda. Specific objectives of the project are to: - Develop and promote regional investments in drought early warning systems (EWS) and improving the existing ones - Strengthen and improve the capacity of key stakeholders in drought risk management at regional, national and local levels - Facilitate smallholder farmers and pastoralists with inputs to undertake innovative adaptation actions that reinforce their resilience to drought - Enhance knowledge management and information sharing on drought resilience. To achieve the above specific objectives, the project is structured around four main components that were elaborated considering drought dimension from the regional, national and local contexts.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFR/RIE/DRR/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entiy | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Djibouti, Kenya, Sudan and Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | • Djibouti (in Bieidley in Ali Sabieh region, and Wadi Gobaad and Hanle sector in Dikhil Region); • Kenya (in Kitui and Samburu counties); • Sudan (in Kosti in El Salam); and • Uganda (in the Lokere Catchment). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | October 11, 2019
IE-AFB Agreement Signature Date: |  | December 24, 2019 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | October 10, 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | October 2022
| Original Completion Date: | October 2024
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | • Inception workshop reports (04 Nov, 2020) | Czech Republic
Communication Material
Articles: • https://www.gwp.org/en/GWP-Eastern-Africa/WE-ACT/News/gwp-eastern-africa-chair-shares-insights-on-the-impact-of-the-dress-ea-project/ DRESSEA project video • https://youtu.be/wuFS5IsKNRA Due diligence mission • https://www.facebook.com/media/set/?set=a.2935760689793262&type=3 • http://www.oss-online.org/en/igad-region-preparations-%E2%80%98drought-resilience-small-farmers-and-pastoralists%E2%80%99-project-start-february GWP signature signing ceremony • https://www.facebook.com/OSSCommunity/posts/340388388298093 • http://www.oss-online.org/fr/signature-du-nouveau-projet-d%E2%80%99adaptation-au-changement-climatique-%C2%AB-dress-ea-%C2%BB-financ%C3%A9-par-le • http://www.oss-online.org/fr/signature-du-nouveau-projet-d%E2%80%99adaptation-au-changement-climatique-%C2%AB-dress-ea-%C2%BB-financ%C3%A9-par-le- • fonds?fbclid=IwAR0ddn6DJiVwdShvO_icX2IhGstHvNsvKZ9ZJQnnTSmf1zf2Jte-UrFlYDw• GWP launch • https://www.facebook.com/OSSCommunity/posts/3559135560789102 • https://www.facebook.com/OSSCommunity/posts/3539240939445231 • https://www.gwp.org/en/GWP-Eastern-Africa/WE-ACT/News/multi-million-dollar-project-targeting-drought-resilience-in-the-horn-of-africa-launched/ 2nd RSC and 1st supervision mission • http://www.oss-online.org/fr/mission-djibouti_fr 3rd RSC and 2nd supervision mission • https://www.gwp.org/en/GWP-Eastern-Africa/ABOUT-GWPEA/press-room/News/dressea-3rd-rsc/ • https://faithcherono.pixieset.com/3rddress-earegionalsteeringcommittee/ • https://youtu.be/_gTdz-FtcLk • https://youtu.be/4Mialuqd7Mw • https://youtu.be/WUMGgHJtAxg Uganda Launch • http://www.oss-online.org/en/kick-strengthening-resilience-small-holder-farmers-pastoralits-igad-region-project-march-10-2021 • https://www.facebook.com/OSSCommunity/posts/3957454014290586 • https://www.facebook.com/OSSCommunity/posts/3956345817734739 •https://twitter.com/min_waterUg/status/1369768570515767296?t=A4aEoBYLLbhT_J99sBwj5g&s=19 • https://m.facebook.com/story.php?story_fbid=3716148761836936&id=1235333893251781 Djibouti launch • https://www.facebook.com/INFOS.DJ/videos/552561292598936 • https://fb.watch/9EllwL0rLI/ • https://www.facebook.com/OSSCommunity/posts/4362157203820263 Sudan launch • https://www.suna-sd.net/read?id=739861 • https://dress-ea.hrc-sudan.sd/ Kenya launch • https://m.facebook.com/story.php?story_fbid=pfbid026H55QMUHe7oCsyRjHvzrf8m5obaQvR7QqoR2KyLsChuUxt3F4HWk94Q1iKeJHWyXl&id=100010170183804&sfnsn=mo&mibextid=6aamW6 • https://twitter.com/Environment_Ke/status/1519735197327110148?t=Q1yrlCOwxoNZauqJ0dDgSQ&s=08 Tweets • https://twitter.com/OSS_Comms/status/1372209251490410500?s=20 • https://twitter.com/OSS_Comms/status/1371441205981147136?s=20 • https://twitter.com/min_waterUg/status/1369763172383621121?s=20 • https://twitter.com/min_waterUg/status/1369761797536952321?s=20 • https://twitter.com/min_waterUg/status/1369762240400945152?s=20 • https://twitter.com/min_waterUg/status/1369765939932192772?s=20 • https://twitter.com/min_waterUg/status/1369764232036818953?s=20 • https://twitter.com/min_waterUg/status/1369768570515767296?s=20 • https://twitter.com/OSS_Comms/status/1369607762892759044?s=20 • https://twitter.com/MuhanjiSteve/status/1369554271620972546?s=20 • https://twitter.com/MuhanjiSteve/status/1369555671612612612?s=20 • https://twitter.com/MuhanjiSteve/status/1369569994883952641?s=20 • https://twitter.com/OSS_Comms/status/1442482043926028297?s=20 • https://twitter.com/MuhanjiSteve/status/1369572405400768512?s=20 • https://twitter.com/MuhanjiSteve/status/1369591195899486210?s=20 • https://twitter.com/MuhanjiSteve/status/1369601583869292544?s=20 • https://twitter.com/adaptationfund/status/1313482605917097993?s=20 • https://twitter.com/GWPSAF/status/1313471093152374793?s=20 Knowledge Products • https://www.gwp.org/globalassets/documents/gwpea/files-and-documents/stung-by-climate-change.pdf • https://www.gwp.org/globalassets/documents/gwpea/files-and-documents/dress-ea-policy-brief.pdf • https://www.gwp.org/globalassets/documents/gwpea/files-and-documents/joint-resource-mobilization.pdf • https://www.gwp.org/globalassets/documents/gwpea/files-and-documents/policy-brief-on-knowledge-management.pdf
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | http://www.oss-online.org/en/strengthening-drought-resilience-small-farmers-and-pastoralists-igad-region-dress-ea | Democratic Republic of the Congo
Denmark
Djibouti
| Project contacts: |  | Dominica
| Regional Project Manager/Coordinator |  | Dominican Republic
| Name: | Mr.Gerald Kairu | Ecuador
| Email: | gerald.kairu@gwpea.org | Egypt
| Date: | August 20th, 2020
| National Project Manager/Coordinator |  | El Salvador
| Name: | Mr. Mokhtar Mohamoud (Djibouti) | Equatoral Guinea
| Email: | xared2004@yahoo.fr | Eritrea
| Date: | January 28th, 2020 | Estonia
Ethiopia
| Name: | Eng. Nazik Abdullahi M. Ahmed (Sudan) | Fiji
| Email: | nazikabdullahi@gmail.com | Finland
| Date: | March 13th, 2022 | France
Gambia
| Name: | Mr. Thomas Lerenten Lelekoitien (Kenya) | Georgia
| Email: | lerenten12@gmail.com | Germany
| Date: | February 19th, 2021 | Ghana
Greece
| Name: | Dr.Callist Tindimugaya (Uganda) | Grenada
| Email: | callist_tindimugaya@yahoo.co.uk | Guatemala
| Date: | November 30th, 2020 | Guinea
| Government DA |  | Guinea Bissau
| Name: | [Djibouti] Mr.Dini Abdallah Omar | Guyana
| Email: | dini.omar12@gmail.com | Haiti
| Date: | March 28th, 2019 | Honduras
| Government DA |  | Hungary
| Name: | [Sudan] Prof. Rashid Mekki Hassan | Iceland
| Email: | hcenr2005@yahoo.com | India
| Date: | April 3rd, 2019 | Indonesia
| Government DA |  | Iran (Islamic Republic of)
| Name: | [Kenya ] Dr. Chris Kiptoo | Iraq
| Email: | kiptoochrs@gmail.com | Ireland
| Date: | March 14th, 2019 | Israel
| Government DA |  | Italy
| Name: | [Uganda] Mr. Keith Muhakanizi | Jamaica
| Email: | keith.muhakanizi@finance.go.ug | Japan
| Date: | June 5th, 2019 | Jordan
| Implementing Entity |  | Kazakhstan
| Name: | Sahara and Sahel Obervatory | Kenya
| Email: | boc@oss.org.tn | Kiribati
| Date: | August 5th, 2019 | Kuwait
| Regional Executing Agency |  | Kyrgyzstan
| Name: | Global Water Partnership Eastern Africa (GWPEA) hosted by the Nile Basin Initiative (NBI) secretariat | Lao People’s Democratic Republic
| Email: | info@gwpea.org | Latvia
| Date: | August 26th, 2020 | Lebanon
| National Executing Agency |  | Lesotho
| Name: | [Djibouti] -Ministry of Agriculture, Water, Fisheries, Livestock and Halieutic Resources | Liberia
| Email: | ibrahimelmimed@gmail.com | Libyan Arab Jamahiriya
| Date: | October 11th, 2020 | Liechtenstein
| National Executing Agency |  | Lithuania
| Name: | [Sudan] Ministry of Water Resources and Electricity - Hydraulic Research Centre (HRC) | Luxembourg
| Email: | info@moiwr.gov.sd | Madagascar
| Date: | May 27th, 2021 | Malawi
| National Executing Agency |  | Malaysia
| Name: | [Kenya] Ministry of Environment and Natural Resources - Climate Change Directorate | Maldives
| Email: | ps@environment.go.ke | Mali
| Date: | January 22nd, 2021 | Malta
| National Executing Agency |  | Marshall Islands
| Name: | [Uganda] Ministry of Water and Environment - Directorate of Water Resource Management | Mauritania
| Email: | mwe@mwe.go.ug | Mauritius
| Date: | November 16th, 2020 | Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information: cumulative from project start to 30 September 2021 |  |  |  | Financial information PPR 2: cumulative from project start to 30 September 2022 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of septembre 2021 | 666505 |  |  | Estimated cumulative total disbursement as of 30th Septembre 2022 | 1650018 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date from the Adaptation fund to OSS amounts US $ 2,100,000 (US $ 1,868,000 for project execution and US $ 232,000 as implementing fees). The disbursement to date amounts to US $ 666,505,00 from October 2020 to September 2021 and represents 35% of the first fund disbursed tranche and 5,5 % of the total funding. The Payments to date have reached US $ 302,742. They represent around 45% of the first disbursement and 2 % of the Grant total amount. The commitments at the end of September 2021 amounted to US $ 502,655.43 The low expenditure can be explained by: (i) the difficulty in developing, finalizing and fulfilling the entry into force stipulated by the Grant Agreement and the first disbursement namely by Sudan and Kenya; (ii) the delay in fulfilling the entry into force of the grants have had an impact on the establishment and composition of project management units; (iii) the organization of the project launch workshops which payments have not yet been effected; (iv) the Covid-19 pandemic and its related lockdowns with restrictions that led to organizing virtual meetings instead of physical attendance ones that are time consuming and limited attendance experienced; and (v) the political factors related to the last elections in Uganda. Efforts are being made to bring project activities and the funds absorption in line with the project activities. As a recommendation towards project execution, similar and complementary activities have been proposed to be undertaken concurrently. This will fast track and ensure efficiency in funds utilization. This will further guarantee the uniformity of the expected results given that this is a regional project that needs a minimum of coherence and complementarity. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date from the Adaptation fund to OSS amounts USD 5,800,000 (USD 5,293,000 for project execution and USD 507,000 as implementing fees). The disbursement to date amounts to USD 1,650,018 from October 2020 to September 2022 and represents 31 % of the total funding received with 13.7 % of the total funding of the project. The undisbursed balance amount is USD 3,642,982 from USD 5,293,000. The Payments to date have amounted to USD 842,145. They represent around 51% of the disbursement amount and 6.5 % of the Grant total amount. The commitments at the end of September 2022 amounted to USD 745,453.10. The low expenditure is due to: (i) The long procurement processes that in some cases are initiated by the EE hosting Ministry, requires specific clearances from Ministries of Justice and Finance according to the national procurement regulations, (ii) The under-staffing of project management units that have been addressed recently, (iii) The political factors related to the last elections and instability, (iv) Limited expertise at national level limiting responses to call for bids to undertake consultancies Efforts are being made to align project activities and the disbursement schedule as per the project plan. In fact one of the major corrective measures undertaken was the development of a common Action plan with OSS support during the second supervision mission to detail all the required steps to implement the activities. This action plan takes into account the various delays and obstacles as well as promoting the regional dimension through clinics and work sessions regularly to fast-track the interventions. As this is a regional project with country specific operational environments, M&E is key to implementation of activities which would be recommended as an operational key activity post mid-term. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1: Efficient and effective EWS in place/developed | 78613 |  |  | Output 1.1.1: Efficient and effective EWS in place/developed | 185552.5498
| Output 1.1.2: Institutional linkages for EW information established | 0 |  |  | Output 1.1.2: Institutional linkages for EW information established | 37058.7891
| Output 1.1.3: Feedback mechanism for EW information developed | 0 |  |  | Output 1.1.3: Feedback mechanism for EW information developed | 18938.9179
| Output 1.1.4: Emergency plan for Drought management is put in place | 14768 |  |  | Output 1.1.4: Emergency plan for Drought management is put in place | 13012.5546
| Output 2.1.1: Drought management plans (DMPs) integrating CC aspects and adaptation actions developed | 0 |  |  | Output 2.1.1: Drought management plans (DMPs) integrating CC aspects and adaptation actions developed | 3558.4575
| Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved | 6287 |  |  | Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved | 128869.7637
| Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported | 36353 |  |  | Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported | 64447
| Output 3.1.1: Innovative water and soil conservation structures constructed | 0 |  |  | Output 3.1.1: Innovative water and soil conservation structures constructed | 3782.0965
| Output 3.1.2: Ground water sources established/ improved | 0 |  |  | Output 3.1.2: Ground water sources established/ improved | 0
| Output 3.1.3: Adaptive agricultural practices for improving crop production promoted | 0 |  |  | Output 3.1.3: Adaptive agricultural practices for improving crop production promoted | 0
| Output 3.1.4: Adaptive livestock and rangeland practices enhanced | 0 |  |  | Output 3.1.4: Adaptive livestock and rangeland practices enhanced | 10146.5981
| Output 3.1.5: Enabling environment for smallholder farmers and pastoralists adaptive activities created | 0 |  |  | Output 3.1.5: Enabling environment for smallholder farmers and pastoralists adaptive activities created | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Output 3.1.6: Environmentally friendly IGAs ([e.g., Pottery, Bee keeping, Energy saving stoves, Briquettes making, and interlocking bricks) promoted | 0 |  |  | Output 3.1.6: Environmentally friendly IGAs ([e.g., Pottery, Bee keeping, Energy saving stoves, Briquettes making, and interlocking bricks) promoted | 0
| Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | 0 |  |  | Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | 9945.9716 |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
| Output 4.1.2 Drought information management strengthened | 0 |  |  | Output 4.1.2 Drought information management strengthened | 0 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activities SUB-TOTAL | 136021 |  |  | Activities SUB-TOTAL | 475312.6988
| Execution costs | 166721.19 |  |  | Execution costs | 366832.6337
| (Executing Entities) SUB-TOTAL | 302742.19 |  |  | (Executing Entities) SUB-TOTAL | 842145.3325
| Implementation costs | 137462.71 |  |  | Implementation costs | 289095.7074
| TOTAL | 440204.9 |  |  | TOTAL | 1131241.0399
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1: Efficient and effective EWS in place/developed | 685000 | October, 2022 |  | Output 1.1.1: Efficient and effective EWS in place/developed | 470000 | August, 2023
| Output 1.1.2: Institutional linkages for EW information established | 250000 | November, 2022 |  | Output 1.1.2: Institutional linkages for EW information established | 325000 | September, 2023
| Output 1.1.3: Feedback mechanism for EW information developed | 145000 | November, 2022 |  | Output 1.1.3: Feedback mechanism for EW information developed | 228500 | August, 2023
| Output 1.1.4: Emergency plan for Drought management is put in place | 600000 | November, 2022 |  | Output 1.1.4: Emergency plan for Drought management is put in place | 600000 | October, 2023
| Output 2.1.1: Drought management plans (DMPs) integrating CC aspects and adaptation actions developed | 200000 | November, 2022 |  | Output 2.1.1: Drought management plans (DMPs) integrating CC aspects and adaptation actions developed | 329000 | August, 2023 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved | 400000 | November, 2022 |  | Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved | 303832.5 | October, 2023
| Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported | 140000 | October, 2022 |  | Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported | 180000 | September, 2023 | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| Output 3.1.1: Innovative water and soil conservation structures constructed | 165000 | October, 2022 |  | Output 3.1.1: Innovative water and soil conservation structures constructed | 341972.9861 | October, 2023 | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
| Output 3.1.2: Ground water sources established/ improved | 200000 | October, 2022 |  | Output 3.1.2: Ground water sources established/ improved | 327500 | September , 2023
| Output 3.1.3: Adaptive agricultural practices for improving crop production promoted | 140000 | October, 2022 |  | Output 3.1.3: Adaptive agricultural practices for improving crop production promoted | 270158.7302 | October, 2023 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| Output 3.1.4: Adaptive livestock and rangeland practices enhanced | 110000 | September, 2022 |  | Output 3.1.4: Adaptive livestock and rangeland practices enhanced | 214495 | October, 2023
| Output 3.1.5: Enabling environment for smallholder farmers and pastoralists adaptive activities created | 140000 | October, 2022 |  | Output 3.1.5: Enabling environment for smallholder farmers and pastoralists adaptive activities created | 296200 | October, 2023 | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
| Output 3.1.6: Environmentally friendly IGAs ([e.g., Pottery, Bee keeping, Energy saving stoves, Briquettes making, and interlocking bricks) promoted | 80000 | November, 2022 |  | Output 3.1.6: Environmentally friendly IGAs ([e.g., Pottery, Bee keeping, Energy saving stoves, Briquettes making, and interlocking bricks) promoted | 137465 | October, 2023
| Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | 70000 | October, 2022 |  | Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | 218098.7838 | October, 2023
| Output 4.1.2 Drought information management strengthened | 63000 | October, 2022 |  | Output 4.1.2 Drought information management strengthened | 120000 | October, 2023
| Execution costs | 340000 | October, 2022 |  | Execution costs | 384777 | October, 2023
| TOTAL | 3728000 |  |  | TOTAL | 4747000

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Political conflicts in some countries. | High | Sudan The country is currently experiencing political instability. The RIE put in place stopchecks to support the project coordinator in mobilising the permanent administration at the ministries to ensure that all conditions will be favourable to execute activities.
Inter-clan/tribe conflicts in pastoral areas | Medium | Uganda The project site is experiencing clashes related to animal pastures and water resources which are limiting execution of activities in the intervention site located in Karamoja region hence the NEE is limiting its staff engagement in the area prior to these clashes been resolved by the central government. The establishment of the local committees from previous projects where as a lesson learnt are being engaged so as to facilitate mediations and support the DRESSEA planning, execution, monitoring and evaluation processes of the project.
Low collaboration amongst the relevant technical institutions | Low | • The relevant institutions have been identified and have been engaged in the early stages of project implementation such as the collaboration with ICPAC in the development of the EWS. • The identification of focal points in the institutions to work with the EEs has been undertaken and appoitment has been completed. • The SC members have engaged with technical staff from supporting insitutions to collaborate and offer services required to operationalise the project and other vital processes and procedures.
Local communities (small-scale farmers and pastoralists) with limited participation and willingness to promote project initiatives | Low | • The project plans included sensitization at local community level and ensured active involvement of community leaders especially the target audiences i.e. the farmers and pastoralists. • The use of tanslated project description information into local languages has been done in Sudan and Uganda to ensure understanding of the project. • The undertaking of workshops at the local level has been in Djibouti, Kenya, Sudan and Uganda during the baseline assessment as well to ensure all local communities have been included taking into account the FPIC process to include the indigenous people in the project sites.
Poor monitoring and evaluation and delayed delivery of outputs | Low | • The project has developed an M&E system that is being used to monitor the project activities and indicators. • The use of bi-weekly meetings has been explored to include all coordinators by the RIE and cascaded down to the REE to manage. • The application of supervision missions to the countries has been undertaken and is a countinous process to ensure actual physical monotoring of all project asspects. • The development of additional tools such as the stoplight template for monthly reporting as well as monthly interim financial report template have been deployed to the EEs. • The appoitment of M&E assistants has been conducted to ensure that all M&E has been decentralised and a bottom up and top bottom approach has been applied.
Limited capacity, especially in areas of water security and integrated drought management in the targeted sites | Low | •Training manuals have been elaborated to conceptualise the needs of the stakeholders in relation to project interventions. •The KAP survey has been undertaken in Uganda and Djibouti to undertstand the schematics of the communities and their perceived expectations of the DRESSEA Project. • A capacity needs assessment has been undertaken to identify the capacity building needs within the target sites. • A training plan has been developed to identify relevant additional training modules for Integrated Water Resources Management tools for drought risk management. •The establishment of the National Steering Committees has been undertaken. It includes representatives from NGOs and Private sector. They will establish the linkages with the project beneficiaries to on-going capacity development efforts of resilience building in the countries which will also ensure synergies.
Management of funds by countries- accountability etc. | Low | • The RIE has developed tools and has taken the EEs through a training on how to use and apply the financial monotoring tools with the fiduciary units which include procurement and accounts with the coordinators. project will undertake training in financial management targeting the financial managers and project managers in the countries. -Training on finance to non-finance personnel will be organized to provide basic knowledge in the financial handling of project funds. It is proposed that the slot to support financial management will be incorporated as part of M&E
High expectations by the targeted audiences (small-scale farmers and pastoralists) | Medium | • The REE has supported the coordinators to participate in IGAD related activities and further disseminate the knowledge to the community representatives on the importance of the project within the region and to support the transboundary shared resources. •The baseline as a recommendation required the NEEs to undertake fact finding missions where Sudan executed a follow-up mission to raise awareness and gather additonal information for water resources and NPMU establishment. •The RIE has developed project sheets and dissemniated to the EEs where Uganda and Sudan have translated them to local languages to be used during sensitization and aware sessions scheduled. • The involvement of the beneficiaries through representatives in decision making organs has been undertaken such as the PSCs.
Dependence on handouts- NGO’s in the project site providing free materials without ensuring ownership | Medium | • The project has undertaken a baseline study to identify complementary projects to reduce on duplication and fatigue of stakeholders. • The project through components 1, 2 and 3 have engaged at the regional as well as at the local level to include and establish multi-stakeholder’s forum in the targeted sites and share the mode of operations and codes of conduct in service delivery with the use of the steering committee members. • The development of the DMP as an example ensures all stakeholders in the project sites are being engaged and consulted so as to have a buy in and promote project ownership. • The project is also collaborating with existing institutions operating in the project sites with aim of streamlining the support to communities, encouraging them to be more productive utilizing the project funds for interventions.
Project financial management | Medium | • Uganda is currently phasing to the IFMIS system to ensure alignment with international standards of reporing. •The RIE has engaged a specialist dedicated to the DRESSEA project to support, monitor and train the EEs in financial management. •The project has developed Financial reporting templates and tools to be applied by the EEs. • The Financial managers have been trained in the use of these tools and are reporting on a monthly, quarterly and annually basis with the use of supporting documents. • In Kenya, the use of the national software - IFMIS- provided by the National Treasury will complememnt the tools provided by the OSS. • The EEs are supported on a day to day basis by the fiduciary unit of OSS when required. • The establishment of the PMUs with the inclusion of finance and procurement support ensures that all procedures that were provided are been implemented and align with OSS regulations and standards.
Communication in the project | Low | • The project has ensured that the project staff within National Executing Entities are fluent in the local language of the project execution sites. • As a bilingual organization, OSS can facilitate the exchange and sharing of information between the Francophone country (Djibouti) and the Anglophone countries (Kenya, Sudan, Uganda) of the project with the suppport of the GWP as well as the use of arabic to specific communities in Djibouti and Sudan. • The RIE has also provided the stoplight template where all EEs report on a monthly basis the activities' execution and the communication undertaken for visibility. • Under component 4, the project has ensured inclusivity of all stakeholders. Refer to overview section for communication and material utilised as of this reporting as an addition.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Government Election | High | Kenya Government elections during the initially planned execution period led to a delay in commencing the project activities.However, as soon as the new administration will be in place, the project will fast track execution of activities to catch up with the planned schedule. The project is a high priority of the Government, and will receive support where difficulties are encountered. Sudan The government administration is constantly changing with different ideologies hence the constant changing of regimes which is coupled with unpredictable elections thus limiting government involvement in project steering.
Delays in finalization of entering into force (EIF) of project conditions | Low | • All the EEs have complied with the Entry into force conditions. However due to the changing climate of governement procedures in Sudan and Kenya, the EIF will require updates on a rolling basis until they are stabilized.
Government bureaucracy- For example in procurements, they take a long time. Also alignment to national rules and regulations related to tracking external funds by the national treasury and Ministry of Finance. | Low | • Continuous engagement with government officials in Kenya and Sudan to align on agreed measures. • Assessment of activities that could be undertaken in tandem • Use of framework contracts and force on accounts methods of procurement.
Re-surgence of COVID19 pandemic | Low | • Utilize innovative ways of project interventions e.g. enhancing online interactions, utilizing existing government systems etc. • NEE has adopted the proposed action e.g. using web-based communication tools (zoom, MS team. WhatsApp and Telephone)
Delays in establishment of Project Management Units and execution of project activities by NEE | Medium | • The RIE has taken into account the utilization of the National Steering Committees members to fast track activities due to their high level positions in the countries. • The RIE transmitted delay letters to the NEEs stating the delay of the PMU establishment as well as activity lag • The RIE has assisted in development of draft ToRs and transmitted to the EEs to fast track of the actvities. • The RIE has expedited the NO process to ensure timely submissions of the decisions.
Delays in constituting the Project Management Units and execution of project activities by REE | Medium | • Recruitment of some project staff has been done. • Meeting with the Finance and Administration units to fast-track the recruitments of additionnal technical staff has been undertaken by the RIE. • Appointing REE representatives to be stationed in the countries has been proposed as a mitigation measure and discussions are underway • The communication Assistant evaluation process is underway
Institutional linkages and arrangements challenges faced by the REE during execution | Medium | • The REE is facing internal changes changes related to the management and administration of its fiduciary and legal units hence a transitional phase is underway. The RIE is taking the lead in undertaking some activities directly to avoid gaps a dn additional delays in execution at regional level
Delays in execution of project activities by REE and NEE | Medium | • The RIE has assisted the EEs in integration of some year one project activities in the second-year annual work planning and fast track preparation of AWP and PP •The annual wok plans and budgets have been revised to take into account the activities to be executed through an action plan linking the REE and NEE to work in tandem where some activities will be undertaken jointly. •The use of inhouse expertise provided by various govenment agencies has been proposed to facilitate fasttracking of activities as well as taking into account limited expetise in the countries like Djibouti and Sudan.
Flooding in Sudan | Medium | • Flooding in Sudan experienced during 2020-2022 factored in inaccessibilty to project areas as well as hindered meetings at the local community level and mobility of the EE to the project sites. •The NPMU continue to communicate using the available web-based technologies like the zoom, teams, WhatsApp and telephone
Drought in Djibouti | High | •An action plan has been developed to respond to the call for support based on the alert issued by the Government of Djibouti which includes activities related to water and livestock management even though they are planned for the 3rd year.
Lack of communication between PMU staff and local communities due to native language in project sites | Medium | Sudan A technical assistant will be hired to support the execution of project acvities taking into account specificities of the native language. This will ensure community buyin and better communication with and between the beneficiairies and the NPMU.
Limited technical capacity for processing climate data and generating relevant climate information products | Medium | •A baseline assessment has been conducted in the 4 countries covering the project sites. More data is also being collected under other regional studies related to the EWS and KAP surveys. •A dynamic process of updating the reference data is being adopted in the framework of the project through its different missions.
Low rate of technology uptake by communities | Low | The project has a plan to carry out trainings to improve capacity of communities to adopt to new technology and also sensitizes them on their advantages to facilitate the use of mobile application •Uganda has identified community climate champions who are been facilitated with mobile phones and further training to cascadew the information to the beneficiaries.
Low regional collaboration to establish a regional EWS | Low | ICPAC has initiated engagement with 4 countries to assess the status of countries EWS and Regional consultations have been undertaken to determine the status of existing EWS
Vandalism of the weather stations after the installation phase due to insecurity in some sites | Medium | Uganda and Sudan •Securing the equipment will be taken into account while constructing the stations such as fencing and positioning a guard with CCTV when and where necessary.
Ebola outbreak in Uganda | Medium | The emergence of the ebola virus in Uganda may affect the project interventions and close monitoring is been undertaken.
Inadequate capacity in populating project documents e.g. No-objection tracker and limited capacity of PMUs to provide high quality documents e.g. No objections to the RIE | Low | REE Organised a workshop which enabled the Executing Entities to discuss NO tracker and involved training by the RIE.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Overall, the risks identified above are manageable during this reporting period. The risks have been managed through: (i) The establishment of MoUs and SLAs to support the execution of the project activities in house (ii) The Organization of clinic sessions and project philosophy understanding to facilitate the activities progress in a regional dimension, (iii) The elaboration of concrete action plans for the third year detailing the actions, responsibilities and deadlines that would bring a better dynamism to the project and reduce the delays experienced (iv) The creation of a sharing platform (sharepoint) to act as a repository for all the Project related documents, ToRs, CNs, reports developed which is continuously being updated by all EEs to ensure alignment and promote the regional dimension of the project not forgeting communication and lessons learnt (v) The constant engagement and monitoring of project partners has been enhanced to promote knowledge management and ensure delivery of products such as the EWS Husika feedback mechanism and alerts (vi) Bi-weekly meeting and technical assistance/support to the EEs is a constant day to day of the RIE to enable alignment of all entities to achieve globally.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | NTR | NTR | NTR | NTR | Currently no risk has been identified regarding conformity with the law
2 - Access and equity |  |  | 1- Project beneficiaries will be in general rural people (pastoralists and smallholder farmers) who have difficulties to access to the decision-making process, this may limit their opportunities to benefit from projects outcomes. 2- Women and youth are characterized by poor access to land and related resources over agricultural production. These findings imply that there is limited capacity to cope due to high levels of poverty and dependency among the women and youth and may limit their opportunities to benefit from projects outcomes. | • The different beneficiaries were mapped and their needs assessed as part of the baseline and capacity needs study taking into consideration the training materials and tools. • Grievance/reporting mechanisms have been set up to capture complaints, feedback, inputs and updates from the concerned communities • Meetings have been undertaken using a broad approach / selection criterion to include women and youth. | •Nb of workshops •Nb of participants to These workshops and gender distribution •Nb of complaints |  | • Consultations have been held with the target beneficiaries. • The involvement of women to at least 40% of the membership of the committees has been evidenced • Women and youth groups are actively being involved in focused group discussions and their views are being considered.
3 – Marginalized and vulnerable Groups |  |  | 1- Insufficient knowledge and access/use of technological devices such as mobile phones or lack of good cellular connectivity specially required in component 2 on Early Warning System design and implementation. 2- During construction activities, risk of reducing or prohibiting the temporary access of certain populations, especially women, to the resources on which they depend (pastures, water, fruit trees, crops, fishing grounds,forest, public services). 3-Component 3 involves setting up a competitive small grant scheme (CSGS) for undertaking innovative climate change adaptation interventions. Given the funds available dedicated to the small grants, it is hard to cover all the beneficiaries | • Workshops and project launches have been undertaken at communities’ level in Uganda and Sudan including all stakeholders at local and national levels. • Project information’s has been translated into local languages to facilitate inclusivity in the project. • FPIC has been applied and is still being applied in the consultation process to include all beneficiaries. | •Nb/ Frequency of radio awareness campaigns per day (in local language) •Nb of indication panels put in place •Nb of workshops •Nb of participants in These workshops and gender distribution •Validation of the process for selecting the intervention area •Nb of complaints •Nbr of people belonging to the marginalized groups benefiting from grants •Nb of complaints |  | • Messages are being broadcasted using local channels, posters, pictorals and traditional methods through skits, plays and songs to reach all beneficiaries • All activities implementations will be decided in consultation with of all concerned communities. • An selection criteria will be elaborated for selection of the grant beneficiaries taking into account all beneficiaries. • Grievance register will be updated on a rolling basis when and where necessary.
4 – Human rights |  |  | NTR | NTR | NTR | NTR | NTR
5 – Gender equality and women’s empowerment |  |  | 1-The cultural and social norms of the project region lead to a greater role for women to question male dominance and claim their role in decision-making. So, there is a risk that women will not benefit equitably from the proposed adaptation measures and the capacity building interventions due to men leadership. 2- Under component 3, it is intended to provide competitive small grants targeting small holder farmers and pastoralist associations including women to improve their livelihoods. There is a risk of gender inequality if the Fund does not provide facilities for women's access to the scheme due to social norms and pressures linked to men leaderships. | • Workshops and project launches have been undertaken at communities’ level in Uganda, Sudan and Djibouti including women and youth at local and national level. • The project uses the Gender Assessment and Action Plan (GAAP) prepared during the project development phase to monitor engendering of the project and it has been updated during the Inception Phase in the M&E platform. • Grievance/reporting mechanisms have been set up to capture women’s complaints, feedback, inputs and updates at the regional, national and local levels. | •% of women and youth participating in workshops and trainings •% of women beneficiaries of IGAs •Nb of complaints •Nbr of Women and youth benefiting from grants •Nb of complaints |  | • Women and young people are being involved in all the stakeholder consultative processes. •Beneficiaries of all project activities will be selected based on an selection criteria taking into account all gender aspects. •Women will constitute over 40% of the membership and beneficiaries of the committees that will award the competitive grants. • To note, the EE coordinators on the ground are women creating a positive image of engendering the project.
6 – Core labour rights |  |  | 1- Risk of accidents and occupational hazards during the project preparation and implementation. 2- Risk of late or unpaid salaries or remuneration non- compliant with the countries labor legislations and laws. 3- Risk of Children’s labor. 4- Risk of Remuneration inequity between men and women. | NTR | •Nb of training sessions on the risks related to construction sites •Nb of participants to these sessions and gender distribution •% of companies that comply with safety standards •% workers equipped with protective clothing •Signature of people involved in works ; •% of spot checks validated |  | • Labor intensive activities with risks in this category have not yet started.
7 – Indigenous peoples |  |  | The project activities will generate the same risks on Indigenous people as the risks on all project communities. There will be no major risk on their assets, resources, culture, land and rights. The main risks that could raise are related to the ways they use water resource, transhumance routes, livestock management, agricultural practice etc. | • The indigenous people were mapped out and their needs assessed as part of the baseline and capacity needs study taken into consideration the training materials and tools. • The FPIC process is being applied in the consultation process to include indigenous people. | •% indigenous people involved •Nb of studies/ analysis carried out |  | • Community representatives, including traditional elders are being actively involved in project meetings. • Detailed water resources assessments are carried out to guide on water resources use. •The use of the FPIC process will be continuously undertaken not only to the IP but also to ensure inclusivity.
8 – Involuntary resettlement |  |  | The construction of appropriate and innovative water harvesting and storage infrastructure as well as mini-irrigation and water delivery systems will occupy spaces and may affect private lands or related activities. | NTR | •Nb of beneficiaries affected by the project activities ; •% of beneficiaries affected and offset through IGAs |  | •A consultative process for identification of potential sites for water harvesting structures will be conducted based on specific and agreed upon selection criteria to avoid and minimize temporary resettlements. •The engagement of all community related activities will ensure consultations using a bottom-up approach
9 – Protection of natural habitats |  |  | The presence of labor and construction equipment, if this is necessary for carrying out the works or activities planned by the project, could have an impact on the fauna and flora of certain intervention sites. The implementation of solar-pumped boreholes, water harvesting and storage infrastructure (e.g simplified water tanks, water jars, sunken dams, micro-dams, sand dams, water pans, etc) can result in the vegetation and wildlife habitats destabilization in the implantation site. | NTR | •Nb of monitoring reports including specific section on activities related to the protection and management of ecosystems •Nb of E&S impacts assessments •Nb of stakeholders meetings around the implementation of policies and laws on the protection of natural habitats •Nb of awareness sessions on the protection of the ecosystems •Nb of participants to these sessions and gender distribution |  | •Continous monitoing of natural habitats with the inclusion of various agencies representatives in the NPSC is undertaken where the link with the EEs is pertinent as it promotes E&S screening upto community level •Activities involving construction have been moved away from natural and game reserves in specific project sites. • ToRs, CN, methodologies et al. for identification of potential sites will include the environmental impact assessment at the proposed sites if and when required
10 – Conservation of biological diversity |  |  | Vegetation clearance for water harvesting and storage sites construction may represent a form of disturbance for bird habitat and wildlife | NTR | •Nb of monitoring reports including specific section on activities related to the protection and management of ecosystems •% reforested land in relation to deforested land •Nb surveys established •% of surveys indicating that the area has high diversity of indigenous plants •Nb of awareness sessions on the protection of the ecosystems •Nb of participants in these sessions and gender distribution |  | • Project is planning for activities of biodiversity conservation such as compensatory reforestation. •The use of climate and environment community advocates is underway taking into account women and youth as direct flag bearers.
11 – Climate change |  |  | A potential change of the land use due to the field clearing to construct innovative water harvesting and storage infrastructure (e.g. simplified water tanks, water jars, sunken dams, micro-dams, etc) the may generate the sequestration decrease. |  | •% reforested land in relation to deforested land |  | •Additional tree planting will be encouraged as part of source protection •The draft training manuals developed, take into account climate change actions to reduce CC impacts related to drought, resilent cropping and water mangement. •The KAP survey was also used to further collect local climate data to support project interventions and undertsanding by both the EE and communities. • Community led meetings and training sessions are planned to support climate change awareness through the capacity building initiative envisioned by the Project.
12 – Pollution prevention and resource efficiency |  |  | 1- Potential contamination of water reservoir through introduction of impurities, wastewater and solid waste. 2-Increase in dust levels 3-Vandalism of water pipelines infrastructure, Wastage of water and leakages at consumer points 4-Over abstraction of water 5-Air pollution by gas emissions from machinery during field work or consultants and various stakeholders’ vehicles during workshops and field visits. Generation of waste related to the presence of the workers, construction engines, and equipment, etc. during the execution of the project different activities. | NTR | •Nbr of conformity certificates issued ; •Nb of awareness sessions on water Resource management and conservation •Nb of participants in these sessions and gender distribution •Nb of facilities set up near each tank for the watering of livestock •% companies applying measures to limit the dust level increase •Nb of awareness sessions on water Resource management and conservation •Nb of participants in these sessions and gender distribution •Nb of frauds related to vandalism •Nb of frauds and irregularities •Nb of waste management plans •Quantities/volumes of recycled wastes •Quantities/volumes of compost produced |  | • Protection of water sources is being promoted and source protection plans will be incorporated through the water assessments to be elaborated by the EEs. • Water quality monitoring for surface and groundwater sources is regularly conducted by Kyoga Water Management Zone as part of upscaling activities from a previous project supporting complementarity as a measure being employed in Uganda. • NEMA guidelines will the followed by contractors during the identification and construction process of water retention structures. • Robust to pico EIAs will be undertaken to ensure E&S safeguards are considered during any construction and/ or works.
13 – Public health |  |  | 1-Water storage constructions may lead to water-related diseases (such as Malaria) increase 2-The presence of workers at construction sites near the project beneficiary villages could increase the risk of spread of sexually transmitted diseases (STD) especially that most vulnerable members of communities among the smallholder farmers and pastoralists in the proposed project areas are women, youth and People Living with HIV/AIDS (PLWHAs). 3-Noise and odour nuisance 4-Risk of persons safety in maintaining the tanks or dams (in particular risk of fall of man or cattle) 5-Risks of health problems due to tank water low quality or the proliferation of insects near the water points | NTR | •Nb of awareness sessions on diseases •Nb of participants in these sessions and gender distribution •Nb of programmes translated in local language and distributed •Nb of awareness sessions on diseases •Nb of participants in these sessions and gender distribution •Nb of workers provided by prevention kits •% companies complying with labor safety •Nb of working hours per day (Conformity) •% of workers provided with the appropriate tools •% reservoirs equipped with security measures •Nb of security measures set up at each reservoir •Nb of trainings on the risks of low water quality •Nb of participants and gender distribution •Nb of families provided with sanitary kits for water purification |  | • Activities with risks related to health in this category have not yet started.
14 – Physical and cultural heritage |  |  | NTR | NTR | NTR | NTR | NTR | NTR | NTR
15 – Lands and soil conservation |  |  | Risk of increased soil erosion. 1-There is a minimal risk of soil compaction by the machinery during construction or maintenance. 2- There is risk of surface runoff and eutrofication of water bodies near or around the project sites related to construction, irrigational agriculture and animal husbandry from pastoralists. | NTR | •Nb of soil and water conservation measures % refreshed land in relation to compacted land •Nb of awareness sessions on the effective management of soil and land •Nb of participants in these sessions and gender distribution |  | • Activities with risks related to soil and land degradation duee to works and interventions such as water harvesting have not yet started. •Furthermore, ToRs will highlight the importance of the E&S safeguards while executing works related.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | yes , unanticipated ESP risks is being carried out by the RIE and M&E officer at the regional and local level.
Have unanticipated ESP risks been identified during the reporting period? |  | NTR
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the IE has put in place the following arrangements: (i)Review of reports on project progress that include MIFs and stoplight project tracker (ii) Sensitization sessions during supervision and monitioring missions as well as in coordination meetings (iii) Review of CN and ToRs to ensure that the ESP safeguards have been taken into consideration when and where necessary (iv) Conduct spotchecks on actvitites related to E&S (v) Development of 15 principles explanatory note on how to identify and monitor E&S for the EEs
Have the implementation arrangements been effective during the reporting period? |  | YES, these arrangements have been effective during the reporting period through monitoring and holding of sessions with the PMUs and other technical staff from alocated to support the project like the Kenya climate change units. The RIE has liaised with EEs to ensure that PMUs have M&E/gender/technical assistants onboard.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures, the IE with PMUs have: (i) Appointment of relevant agency staff (project coordinator, technical) (ii) Onboarding of new technical staff to support the E&S monitoring (iii)Involvement of technical staff from the various supporting institutions in the understanding and execution of activities as well as through the PSC (iv) Undertaking KYC to frequently sensitize actors and stakeholders such as local communities on the E&S safeguards related to activities within their scope of operations and interventions
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. The arrangements were implemented by the EEs throughout the project in a continuous process.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | •As indicated in the DRESSEA Project Document, all identified USPs are mainly related to climate change concrete adaptation actions and to the Income Generating Activities (IGAs). •No USPs have been identified at this stage however, arrangements are underway within the PMUs to include, technical/M&E assistants (backed by national units and the project coordinators) who are in charge of monitoring the USP categories/ activities and ensuring compliance with the E&S safeguards to comply with the project ESMP and GAAP. The IE is constantly providing backstopping to the ESMP. •As an example of a preliminary screening of project impacts, the use of the KAP survey, the development of the training manuals and the clinic sessions constantly identify and highlight the E&S safeguards on the activities carried out in the project areas, thus defining the most vulnerable ones per sector.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | NA
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of the project's first submission as a full proposal an initial report on the gender analysis "Report on the integration of gender in the DRESSEA project activities" was conducted.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework includes gender-responsive indicators broken down at the outcome and output levels
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.1.1: Efficient and effective EWS in place/developed | Output | • % of women attending to consultative workshops % of women accessing to weather information | 0 | •50% of women attending to consultative workshops • 40% of women accessing to weather information | Satisfactory (project is on track to achieve this end-of-project indicator as in all the meeting there has been 50% women attendance )
Output 1.1.2: Institutional linkages for EW information established | Output | • % of women attending to consultative workshops % of women attending to decision making workshop | 0 | • 50 % of women attending to workshops • 50 % of women attending to decision making workshop | Poor, as the activity has not been initiated and once this is done then it can be evalauted more precisely.
Output 1.1.3: Feedback mechanism for EW information developed | Output | • % of women attending to workshops • % of vulnerable groups (women, youth, elders, indigenous people, etc…) participating to KAP surveys on EW information • % of user friendly tools focused on vulnerable groups (women, youth, elders, indigenous people, etc…) | 0 | • 50 % of women attending to workshops • 60 % of vulnerable groups (women, youth, elders, indigenous people, etc…) participating to KAP surveys on EW information • 60 % of user friendly tools are focused on vulnerable groups (women, youth, elders, indigenous people, etc…) | Satisfactory (project is on track to achieve this end-of-project indicator as in all the meeting there has been 50% women attendance )
Output 1.1.4: Emergency plan for Drought management is put in place | Output | • % of women attending to decision making workshop • % of women participating to blank operations • % of women attending to consultative workshops | 0 | • 50 % of women attending to decision making workshop • 40 % of women participating to blank operations • 50 % of women attending to consultative workshops | Poor, as the activity has not been initiated and once this is done then it can be evalauted more precisely.
Output 2.1.1: Drought management plans (DMPs) integrating CC aspects and adaptation actions developed | Output | • % of women attending to decision making workshop • % of women attending to consultative workshops | 0 | • 50 % of women attending to decision making workshop • 50 % of women attending to consultative workshops | Poor, as the activity has not been initiated and once this is done then it can be evalauted more precisely.
Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved | Output | • % of women attending to decision making workshop • % of women attending to consultative workshops and trainings | 0 | • 50 % of women attending to decision making workshop • 50 % of women attending to consultative workshops and trainings | Poor, as the activity has not been initiated and once this is done then it can be evalauted more precisely.
Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported | Output | • % of women attending to decision making workshop • % of women attending to consultative workshops | 0 | • 50 % of women attending to decision making workshop • 50 % of women attending to consultative workshops | Poor, as the activity has not been initiated and once this is done then it can be evalauted more precisely.
Outcome 3.1: Increased uptake and usage of concrete and innovative drought adaptation actions | Outcome | • % of women attending to decision making workshop • % of women attending to consultative workshops • % of women participating to ground intervention • % of vulnerable groups (women, youth, elders, indigenous people, etc…) benefiting from project activities • Number of business enterprises promoted by women and youth groups | 0 | • 50 % of women attending to decision making workshop • 50 % of women attending to consultative workshops • 40 % of women participating to ground intervention • 60 % of vulnerable groups (women, youth, elders, indigenous people, etc…) benefiting from project activities • At least 5 IGAs undertaken by women groups in each country | Satisfactory (project is on track to achieve this end-of-project indicator as in all the meeting there has been 50% women attendance )
Outcome 4.1: Increased uptake and usage of concrete and innovative drought adaptation actions | Outcome | • Number of knowledge products e.g.documents on lessons and best practices from project interventions • Number of case studies and lessons learned documented and shared projects • % of women attending to consultative workshops • Number of sensitization sessions • Number of women and vulnerable groups equipped | 0 | • 2 brochures, 2 publications (documents) on lessons and best practices from project interventions per country • At least 4 case studies /lessons learn documented, packaged and shared with key stakeholders for upscaling and informing project interventions • 50 % of women attending to consultative workshops • 3000 women and vulnerable groups equipped | Poor, as the activity has not been initiated and once this is done then it can be evalauted more precisely.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In order to ensure that the GP safeguards are addressed, the -The Implementing Entity and Executing Entities, have all made efforts to comply with the principle of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity, gender-inclusive, and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the local or household baseline incorporated sex disaggregated data and gender-specific questions. 2 - Encouraging project partners/ executing entities/consultants/national stakeholders to hold gender-sensitive consultations and assessments, for example conducting separate focus group discussions for men and women, therefore allowing women's views to be better captured without being overshadowed by men. 3 - Ensuring Local, National, Regional Workshops and Trainings have the participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during consultation and work planning meetings - for example, the question of how activities are designed so as to encourage full participation and engagement of women
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes the implementation arrangements at the IE for Gender Policy compliance has been effective but with some disparities due to long administrative processes in the EE countries. Discussions regarding gender issues or participation are held during project activities implementation and work planning meetings, ensuring: 1) all partners consider the needs (language, cultural, ensure equal participation of women and men) and constraints (allowing women participants to present their views etc.) of women participation in project activities; 2) ensure Gender participation (checking availabilities from their schedule) in all activities; 3) aim for assigning activity leadership to women and 4) capture sex-disaggregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | During the different sensitization and awareness workshops and sessions, the EE required the participation of different categories of the local population, including women, young, aged people, and PLWD using a selection criteria to identify and ensure cross-cutting participation. Further to this during Consultation and implementation of activities , the experts involved in the implementation of the activities are made aware of Gender policy consideration and ensure the involvement of women, youths as much as possible in their activities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes, this arrangement has been effective with the appointment of recruited staff/ specialist/ consultants with gender considerations specified in the terms of reference/ engagements.The implementation arrangements for Gender Policy compliance has been effective to some extent but not in all. Women's participation in project activities, as well as their engagement in leadership and training roles have been below expectations due to cultural barriers or lack of women at management or decision-makers level at the National services of the six countries. The effectiveness of the EEs efforts has also varied from country-to-country (For example: at Ghana, there are more consultations with women working in the field of Hydro-meteorological services as compared to Women) and activity to activity. The EEs will continue to emphasize or implement Gender-specific, sensitive or inclusive approach among stakeholders.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps have been identified to hinder execution.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received and recorded during this reporting period. According to OSS processes, identified and substansive grievances will be reported using the defined GM when they occur and the applicable procedures undertaken to address and resolve the grievance.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Output 1.1.1: Efficient and effective EWS in place/developed |  | Outcome 1 | • An EWS status report per country • One EW prototype at national and regional levels developed • Two modern weather station set up in project sites of each country • Two existing weather station upgraded in project sites of each country • One EW information center constructed/renovated in project sites of each country • At least 70% of farmers and pastoralists utilize EW information in their farming calendars • 4 baseline report |  | At regional Level: •Consultative meetings were organized with the 4 countries to assess the status of in-country EWS. Following the consultative process, ICPAC had enhanced an existing regional Early Warning Prototype known as “Eastern Africa Drought Watch (EADW)”. •A validation workshop with national executing entities was conducted. •The establishment of the baseline study was finalized at all levels and the final version is on going to be consolidate and shared with EEs. At national level: •The status of EWS in the project areas have been assessed in Uganda. The 3 others countries are in the process of undertaking in-house approaches with the relevant departments in order to save time and avoid the procurement delays. •Also to note, Djibouti has limited technical expetise in the country as most are in the government hence the solution to change the activity from consultancy to in-house. •The technical specifications of weather stations were shared by ICPAC to Uganda, Djibouti and Kenya with the procurement process ongoing. | MS
| Output 1.1.2: Institutional linkages for EW information established |  | Outcome 2 | • 1 EW information framework agreement developed/reviewed in each country • One strategic document developed • 1 inter-ministerial Meeting minutes at regional • 32 meetings minutes at the national level (8 per country) • 32 meetings minutes at thesub-national level (8 per country) • 3 meetings minutes at regional level (fora) • 24 meetings minutes at national level (fora) • 24 meetings minutes at subnational level (fora) • 4 document copy of approved plans incorporating EW information |  | At regional level: •A meeting of the IGAD water forum was organized in Entebbe-Uganda where the DRESSEA team participated and engaged key stakeholder for increased collaboration. •They further presented the project to promote awareness. At national level: •Training meetings were conducted to support local level Early Warning Information Sharing among small holder farmers and pastoralists in Uganda. •Meetings were also conducted to support the incorporation of Head of Departments as well as their training on EWI. | MS
| Output 1.1.3: Feedback mechanism for EW information developed |  | Outcome 3 | • 64 copies of Minutes (16 meetings per country) • 32 joint meetings per country • 4 KAP survey report • At least 16 press releases per country • A tool for accessing, utilizing and reporting |  | At regional level: •Stakeholder meetings were held at regional and national level to enhance the HUSIKA mobile application, which is a common platform where all users can share information and receive weather feedback and alerts. •A Training of Trainers (ToT) workshop was conducted targeting NPMUs on how to use the platform and how to cascade it to community level. At national level: •Interviews were used to get feedback on the performance of seasonal forecasts for the months of September, October, November and December (SOND) 2021 from 97 farmers and pastoralists in Uganda. •Knowledge, Attitude and Practices (KAP) Surveys have been concluded in Uganda using 6 trained enumerators who administered questionnaires and the consolidated report for the KAP survey has been prepared. •Djibouti has conducted the activity and the KAP survey is under review and validation. | MS
| Output 1.1.4: Emergency plan for Drought management is put in place |  | Outcome 1 | • 5 emergency response plan for Drought disasters at the regional and national levels • 80 % of the equipment needed for the contingency response is acquired by the end of the project. • 2 of blank operations (including regional and national levels) • 4 warning messages dissemination kit (beacons, flags, sirens, signaling, speakers, telephone, local radio ...) |  | At national level: •Terms of Reference (ToR) were developed and finalized for the development of the national emergency response plan for drought disasters in Uganda and the procurement processes has been initiated. • This ToR was combined with the activity for development of emergency drought response plan. •Two project vehicles have been procured in Djibouti •Uganda is in the final processes of receiving one vehicle. •Sudan is processing the acquisition of 2 vehicles. •Kenya has recieved approval for the technical specifications of one vehicle. | MS
| Output 2.1.1: Drought management plans (DMPs) integrating CC aspects and adaptation actions developed |  | Outcome 4 | • At least 1 national and 1sub-national plan reviewed/developed per country being implemented • At least 1 national and 1sub-national plans translated per country • At least 2 DMPs, integrated into national and subnational plans per country • At least 2 By-laws and 2 ordinances formulated per country |  | At national level: •ToRs have been finalised and approved and procurement has been initiated for Uganda and Djibouti. •Consultations on the existing by-laws and ordinances at district and sub county levels have been conducted in Uganda. | MU
| Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved |  | Outcome 2 | • 4 Capacity needs assessment report • 4 Copies of capacity building plans • 4 Copies of training manuals • 12 exchange visits (3 per country) • 8 trainings for staff managing EW information centers (2 per country) • 36 trainings for extension staff and artisans in drought adaptation (9 per country) • 96 community training workshops (24 per country) • At least 80% of targeted stakeholders trained • 12 learning centers for farmers and pastoralists established per country |  | At regional level: •The capacity needs assessment study has been completed •Training plans and four training manuals have been elaborated including the thematics of Drought Risk Management, Early Warning systems/drought, Resilient cropping&Livestock, Water Restoration and Management. | MS
| Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported |  | Outcome 8 | • 3 copies of Minutes of regional meeting • 24 copies of meetings Minutes (3 national and 3 sub-national meetings per country) • At least 8 press releases each year per country • At least 4, partnership agreements/MOUs, • 4 platform events each year per country • At least 4 regional proposals developed and submitted for funding |  | At regional level: •One regional meeting was held in Entebbe to discuss on the existing drought Management platforms. | MU
| Output 3.1.1: Innovative water and soil conservation structures constructed |  | Outcome 5 | • 4 assessment reports on surface water potential and WMP • 32 Units of water harvesting and storage constructed (Djibouti 2 units; Kenya 10 Units; Sudan 12 units and Uganda 8 Units) • 14 mini-irrigation systems constructed (Djibouti 3 units; Kenya 4 Units; Sudan 4 units and Uganda 3 Units) • 9 water wells, springs/oases protected (Djibouti 0 unit; Kenya 3 Units; Sudan 3 units and Uganda 3 Units) • At least 12 Soil and water conservation measures promoted • At least 70% of smallholder farmers and pastoralists undertaking water and soil conservation measures |  | At national level: Uganda and Djibouti: • ToR have been finalised and procurement has been initiated. The ToRs were combined for two activities i.e., 3.1.1.1& 3.1.2.1. Uganda: • Communities meetings were held with the water users and water committees on source protection measures in Moroto district. Djibouti: •A mission to identify project sites to promote soil and water conservation measures was undertaken. | MU
| Output 3.1.3: Adaptive agricultural practices for improving crop production promoted | Output 3.1.3: Adaptive agricultural practices for improving crop production promoted | Outcome 5 | • At least 70% of the targeted farmers and pastoralists have accessed droughtresistant crop varieties • At least 15 tons of seeds/cuttings for droughtresistant crop varieties distributed in each country • At least 50% of the target pastoralists have accessed drought tolerant and fast growing pasture seeds • At least 100 hectares of degraded landscapes restored in each country • At least 36 irrigation units (Djibouti 10 units; Kenya 8 Units; Sudan 10 units and Uganda 8 Units) • At least 28 Climate smart agricultural units are developed (Djibouti 6 units; Kenya 6 Units; Sudan 8 units and Uganda 8 Units) • At least 60% of targetedfarmers undertake Climat |  | Uganda: •Meetings were held with Ministry of Agriculture on modalities of engagement for execution of agriculture related activities towards maximum outputs. | MU
| Output 3.1.4: Adaptive livestock and rangeland practices enhanced | Output 3.1.4: Adaptive livestock and rangeland practices enhanced | Outcome 5 | • At least 4 stock route agreements signed per country • About 40% Area/acreage of rangeland improved with rangeland management practices • 160 pastoralists supported with improved livestock breeds per country • 170 livestock bought and distributed in each country • At least 70% of the target pastoralists supported with high value silage • Livestock mortality attributed to droughtreduced by 10% • 80 hydroponic units established per country • At least 16 tonnes of improved grass varieties distributed in each country • At least 80 households with improved feeds and pastures • 12 meetings for at least 5 associations per country |  | Uganda: •Meetings were held with Ministry of Agriculture to discuss their involvement in execution of activity 3.1.4.5 for the support of farmer and pastoralists associations establishments and their operationalization. | MU
| Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | Outcome 8 | • 4 brochures, 4 publications (documents) on lessons and best practices from project interventions per country • At least 8 case studies /lessons learn documented, packaged and shared with key stakeholders for upscaling and informing project interventions |  | At regional level: • IEC materials were developed including: 5 brochures; 3 policy briefs; 4 posters; and video uploaded on existing platforms. | MU
| Output 4.1.2 Drought information management strengthened | Output 4.1.2 Drought information management strengthened | Outcome 8 | • Minutes of 4 regional meetings held • Minutes of 8 meetings on policy engagement at the national level • At least 8 information sharing events organized et regional level • A gender responsive and scale up strategy per country |  | At regional level: •The DRESSEA project contributed to the Greater Horn of Africa Climate Outlook Forum (GHACOF 59 and 62) to create visibility and knowledge. •The coordinators from the EEs were facilitated to attend the GHACOF and share experience as well as gain knowledge from other initiatives within the IGAD Region and within the same bioclimatic zones. | MS
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs. Khaoula Jaoui
| Email: | khaoula.jaoui@oss.org.tn
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During this second year of project implementation, the main challenges encountered are political barriers, changes at institutional internal arrangements and security-related actions that hindered the implementation of the project, leading to considerable delays. At the regional level, delays have been encountered particularly transitions related to institutional arrangements and the establishment of a technically sound RPMU. Regional drought EWS prototype known as Eastern Africa Drought Watch (EADW) was enhanced consultatively and validation workshop with National Executing Entity was conducted.An application mobile Husika was enhanced by new feedback feature. This reporting period was marked by the production of three regional studies, namely: i) baseline study ii) capacity need assessment, and iii)Training plans for the various execution levels . At the national level, the project has been considerably delayed due to several political constraints, particularly in Sudan and Kenya due to government elections. In addition, security problems have made which has hampered the execution of project activities, particularly in Uganda. Despite the difficulties mentioned, the national project's executing entities have worked to carry out several activities and have made progress. Activities were mostly recorded as follows: Uganda i) Assessment of the status of early warning system and options of transforming traditional EWS with modern EW technologies (activity 1.1.1.1) ii) Realization of Knowledge Attitude and Practises (KAP) survey (activity 1.1.3.3). Different consultations, meetings and workshop were held related to drought management and environmental conservation in the project sites and were organized to select beneficiary groups at the project site. Djibouti i)Elaboration of ToRs ,concept notes, and visiting project sites. Kenya and Sudan are still in the early stages of the project execution. The experience of conducting these project activities in Uganda is being capitalized for the benefit of the PMUs teams in Djibouti, Kenya and Sudan . The approach of developing a sharepoint platform for documents and experience sharing is being utilised to optimize time and facilitate the effective start of activities in order to respect the regional dimension and complexities of the project.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
GWPEA/Project Coordinator: | Output 1.1.1: Efficient and effective EWS in place/developed |  | Outcome 1 | • An EWS status report • One EW prototype at national and regional levels developed • 4 baseline reports |  | • Consultative meetings were organized with the 4 countries to assess the status of in-country EWS. Following the consultative process, ICPAC had enhanced an existing regional Early Warning Prototype known as “Eastern Africa Drought Watch (EADW)”. A validation workshop with national executing entities was conducted. • The establishment of the baseline study was finalized at all levels and the final version is on going to be consolidate and shared with EEs. | S
| Output 1.1.2: Institutional linkages for EW information established |  | Outcome 2 | • One strategic document developed • 1 inter-ministerial Meeting minutes at regional • 3 meetings minutes at regional level (fora) |  | • A stakeholder’s consultation on the Inter-Ministerial meeting for data sharing and support regional and national partners to jointly mobilize resources for drought management was held on 19-22 October 2021 in Khartoum. • A meeting of the IGAD water forum was organized in Entebbe-Uganda from 25th to 27th January 2022 where the DRESSEA team participated and engaged key stakeholder for increased collaboration. | MS
| Output 1.1.3: Feedback mechanism for EW information developed |  | Outcome 3 | • A tool for accessing, utilizing and reporting |  | • The stakeholder meetings were held at regional and national level to enhance the HUSIKA mobile application, which is a common platform where all users can share information and receive weather feedback and alerts. • A Training of Trainers (ToT) workshop was conducted targeting NPMUs on how to use the platform. • A weekly forecast module as added fashioned to the one available here was developed and integrated with HUSIKA. | S
| Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved |  | Outcome 2 | • 4 Capacity needs assessment report • 4 Copies of capacity building plans • 4 Copies of training manuals • 12 exchange visits (3 per country) |  | • The capacity needs assessment study was completed. • The training plans for the various execution levels were developed and the four training manuals were elaborated including the thematics of Drought Risk Management, Early Warning systems/drought, Resilient cropping and Livestock and Water Catchment Restoration and Water Resource Management. | S
| Output 2.2.1: New/existing regional and National arrangements /networks for drought management supported |  | Outcome 8 | • 3 copies of Minutes of regional meeting • At least 8 press releases each year per country • 4 platform events each year per country • At least 4 regional proposals developed and submitted for funding |  | • 1 regional meeting held to support the development of drought management networks. • Discussions on proposal development is underway and one planning meeting held at the regional level. • A project philosophy training was conducted in june 2022 to discuss the DRESSEA project execution philosophy | MS
| Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated | Outcome 8 | • 4 brochures, 4 publications (documents) on lessons and best practices from project interventions per country • At least 8 case studies /lessons learn documented, packaged and shared with key stakeholders for upscaling and informing project interventions |  | IEC materials were developed including: • 5 brochures • 3 policy briefs • 4 posters | MS
| Output 4.1.2 Drought information management strengthened | Output 4.1.2 Drought information management strengthened | Outcome 8 | • Minutes of 4 regional meetings held • At least 8 information sharing events organized et regional level |  | • The DRESSEA project contributed to the Greater Horn of Africa Climate Outlook Forum (GHACOF 59 and 62) to create visibility and knowledge. The coordinators from the EEs were facilitated to attend the GHACOF and share experience as well as gain knowledge from other initiatives within the IGAD Region and within the same bioclimatic zones. •Two reports available for GHACOF-60 event •Three reports/minutes in support of drought information (it includes the governance-as it targets high-level policy actors | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr.Gerald Kairu
| Email: |  | gerald.kairu@gwpea.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Justification of the rating Based on the approved AWPB and PP 2021/2022, some key planned activities were executed. These were majorly the global activities. These activities provided opportunity for the National Executing Entities to build on. For example, EWS prototypes such as Eastern African Drought watch and Husika platforms. These will be used by the NEE (including at the site level). In addition, the project established a baseline to which the monitoring and evaluation of the activities will be based. The capacity needs assessment of the stakeholders also was successfully conducted. Thus, it allowed to establish the training manual and training plans. To monitor the project activities, through a consultative processes, an online M&E system was developed and it accessible to the project executing entities. Positive Progress made by the project The RPMU is engaging all relevant stakeholders to ensure progress on project execution. Despite the lengthy process, efforts were concentrated towards achieving quality results. During this reporting period (2nd year annual cycle), progress has been registered in completion of the baseline information. This is critical to track project progress. Further, the capacity needs assessment was conducted and training of stakeholders in the areas identified have been accomplished. This provided good grounds to expedite the projects activities that has been dwarfed due to the long wait since inception. Through the various monitoring techniques like conducting biweekly meetings, field monitoring and bilateral meetings between the REE and NEEs, progress is has been made, including developing quality reports highlighted the major achievements made. Negatives that affected the project These include political instability in some countries delayed interventions to progress. There was also delay of fund reaching the bank accounts of some countries e.g., for Sudan and Kenya which as part of operations from the countries, they require funds directly in the accounts and according to contractual procedures. The other issues that affected progress is the busy schedules of key government officers from the Nationbal Executing Entities-which caused postponement of scheduled activities. For the latter, the project team engage the key government staff and project steering committee to ensure the activities are on track to minimize on the delays. Specific recommendations for next steps An action plan was developed for the third year to avoid delays taking into account rapid results initiatives and prioritization.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Uganda/Project Coordinator: | Output 1.1.1: Efficient and effective EWS in place/developed |  | Outcome 1 | • An Early Warning System status report prepared. • Modern weather stations setup or upgraded. Two existing weather station upgraded in project sites of each country • One EW information center constructed/renovated in project sites of each country • One early warning information centre including database constructed or renovated and equipped. • At least 70% of farmers and pastoralists utilize EW information in their farming calendars |  | • The Early Warning System (EWS) have been conducted in collaboration with Uganda National Meteorology Authority (UNMA). The assessment was carried out through holding consultative meetings and identified proposed sites for setting up new weather stations and the stations for upgrading and documented of indigenous knowledge of weather forecasting. • the project team participated in the in-country consultations on the regional prototype early warning system being developed by the IGAD Climate Predictions and Applications Centre (ICPAC). • Uganda has identified sites for four weather stations. The sites for upgrading of stations include Matany Sub County. New stations are proposed for Nadunget and Tapac sub counties. Specifications for the stations have been prepared and have been reviewed and approved by ICPAC. • The team in Uganda has identified and assessed the proposed location for the Early Warning information centre. The EW information centre will be housed in the head office of the Uganda National Meteorological Authority in Luzira, Kampala . • Uganda has identified the gadgets needed by the farmers to support EW information dissemination. These gadgets include radios and phones. The specifications for the gadgets have been prepared and are currently under review by the Uganda NEE. • Uganda team participated in the baseline study conducted by GWPEA for the project area and identified hotspot area for the issues to be addressed by the DRESSEA project. | S
| Output 1.1.2: Institutional linkages for EW information established |  | Outcome 2 | • An EW information sharing framework and action plan to operationalize the EW framework developed. • 32 meetings minutes at the national level (8 per country) • 32 meetings minutes at the sub-national level (8 per country). • 24 meetings minutes at national level (fora) • 24 meetings minutes at subnational level (fora) • 4 document copy of approved plans incorporating EW information |  | •Three meetings were held with representatives of the sub counties covered by the project; farmer groups; development partners to develop three early warning information sharing frameworks at district level for Moroto, Napak and Nabilatuk. Those meetings were attended by a total of 54 participants attended the district level meetings (32 Male, 22 Female). • Three training meetings were conducted to support local level early warning information sharing among small holder farmers and pastoralists. Those meetings were attended by 30 lead farmers (10 females and 20 males). The trainees were selected from the model farmers within the districts of the project area that ensured fair representation from all project sub counties as well as representation from crop farmers and pastoralists. • The national meeting was organised to support early warning information sharing and it was part of the National Climate Outlook Forum where the seasonal forecasts for June, July, and August (JJA) were disseminated at national level. • Two meetings have been held to support the incorporation of Early Warning Information into district planning and budgeting processes in Moroto and Napak districts respectively; those meeting was attended by 23 Head of Departments | MS
| Output 1.1.3: Feedback mechanism for EW information developed |  | Outcome 3 | • 64 copies of Minutes (16 meetings per country) • 32 joint meetings per country • 4 KAP survey report • At least 16 press releases per country |  | • Uganda conducted an assessment on the performance of seasonal forecasts for the months of September, October, November, and December (SOND) and the collection of feedback from communities in the project area. This assessment was undertaken using a sample of 97 farmers and pastoralists in the districts of Moroto and Napak and 9 focus group discussions. • Knowledge, Attitude and Practices (KAP) Surveys have been carried out in the districts of Moroto, Napak, and Nabilatuk. Overall, 335 participants participated in this study with 9 focused group discussions conducted. | MS
| Output 1.1.4: Emergency plan for Drought Management is put in place. |  | Outcome 1 | • 5 emergency response plan for Drought disasters at the regional and national levels • 80 % of the equipment needed for the contingency response is acquired by the end of the project. • 4 warning messages dissemination kit (beacons, flags, sirens, signaling, speakers, telephone, local radio ...) |  | • The Terms of Reference for the developing national emergency response plan for drought disasters were finalised. Currently, the procurement of the consultant is underway. • The bids of supplying vehicle of the project have been received, evaluated, and approved. The contract for supply of vehicle was drafted and submitted to the selected bidder (Toyota-Uganda) for signature. | MS
| Output 2.1.1 Drought management plans (DMPs) integrating CC aspects and adaptation actions developed |  | Outcome 4 | • At least 1 national and 1sub-national plan reviewed/developed per country being implemented • At least 1 national and 1sub-national plans translated per country • At least 2 DMPs, integrated into national and subnational plans per country • At least 2 Bye-laws and 2 ordinances formulated per country |  | •Different consultations were conducted at national level. It was noted that there are no drought management plans at national and sub-national level. The Terms of References (ToRs) were also developed to establish drought management plans at national and subnational level. •The consultations on the existing byelaws and ordinances at district and sub county levels have been conducted to facilitate the formation of byelaws and ordinances. This activity was conducted using key informant interviews with officials of District Local Governments. | MU
| Output 2.1.2: Adaptive capacity of institutions, farmers and pastoralists in drought management improved |  | Outcome 2 | • 8 trainings for staff managing EW information centers (2 per country) • 36 trainings for extension staff and artisans in drought adaptation (9 per country) • 96 community training workshops (24 per country) • At least 80% of targeted stakeholders trained • 12 learning centers for farmers and pastoralists established per country |  | • The DRESS-EA team of Uganda participated in the capacity needs assessment conducted by GWPEA to identify gaps and hinderances to effective drought management. The team held consultations with key institutions involved in capacity building of farmers and pastoralists. The institutions consulted include: District and Sub County Local Governments, Nabuin ZARDI, Private Sector Foundation, and Center for Cooperation and Development. • Four Learning Centers were assessed for the possibility of collaboration with the DRESSEA project. The learning centers that were consulted include: Loputuk, Nadunget, Nakicumet, and Nabuin Zonal Agricultural Research and Development Institute (ZARDI). | MS
| Output 3.1.1 Innovative water and soil conservation structures constructed |  | Outcome 5 | • 4 assessment reports on surface water potential and WMP • 32 Units of water harvesting and storage constructed (Djibouti 2 units; Kenya 10 Units; Sudan 12 units and Uganda 8 Units) • 14 mini-irrigation systems constructed (Djibouti 3 units; Kenya 4 Units; Sudan 4 units and Uganda 3 Units) • 9 water wells, springs/oases protected (Djibouti 0 unit; Kenya 3 Units; Sudan 3 units and Uganda 3 Units) • At least 12 Soil and water conservation measures promoted • At least 70% of smallholder farmers and pastoralists undertaking water and soil conservation measures |  | • Terms of reference for assessing surface water utilization/potential/availability have been finalised. The procurement processes of recruiting a consultant have been initiated. This activity will be conducted in parallel with assessing the groundwater activity. • Four inception community meetings were held with the water user committees from Moroto district. These meetings were attended by 131 participants (82 Male, 49 Female). • Sites for soil and water conservation have been identified in the baseline study, however, no measures have been undertaken yet. The quantification of the required inputs for implementation are to be determined from the water management plans to be developed. | MS
| Output 3.1.2 Ground water sources established/ improved |  | Outcome 5 | • 4 Groundwater assessment report • At least 8 sets of Guidelines for groundwater regulation ( 2 per country being implemented) • At least 60% of the degraded sites restored |  | • The project management team prepared ToRs for assessing groundwater utilisation/potential/ availability. This study will be conducted in parallel with assessments for surface water activity.
| Output 3.1.3 Adaptive agricultural practices for improving crop production promoted |  | Outcome 5 | • At least 70% of the targeted farmers and pastoralists have accessed droughtresistant crop varieties • At least 15 tons of seeds/cuttings for droughtresistant crop varieties distributed in each country • At least 50% of the target pastoralists have accessed drought tolerant and fast growing pasture seeds • At least 100 hectares of degraded landscapes restored in each country • At least 36 irrigation units (Djibouti 10 units; Kenya 8 Units; Sudan 10 units and Uganda 8 Units) • At least 28 Climate smart agricultural units are developed (Djibouti 6 units; Kenya 6 Units; Sudan 8 units and Uganda 8 Units) • At least 60% of targetedfarmers undertake Climat |  | • Uganda has consulted the Zonal Agricultural Research Institute (ZARDI), as well as the Ministry of Agriculture, Animal Industry and Fisheries (MAAIF) on the varieties of drought tolerant crops to be provided to the farmers. Farmers’ groups have been identified and screened to determine the beneficiaries, so far 2319 farmers belonging to 84 farmers’ groups have been screened as beneficiaries in the promotion of drought tolerant varieties. | MS
| Output 3.1.4 Adaptive livestock and rangeland practices enhanced |  | Outcome 5 | • At least 4 stock route agreements signed per country • About 40% Area/acreage of rangeland improved with rangeland management practices • 160 pastoralists supported with improved livestock breeds per country • 170 livestock bought and distributed in each country • At least 70% of the target pastoralists supported with high value silage • Livestock mortality attributed to droughtreduced by 10% • 80 hydroponic units established per country • At least 16 tonnes of improved grass varieties distributed in each country • At least 80 households with improved feeds and pastures • 12 meetings for at least 5 associations per country |  | • Terms of Reference for the consultant to undertake the preparation of rangeland management plans have been prepared and currently under review. • Uganda has consulted the Zonal Agricultural Research Institute (ZARDI), as well as the Ministry of Agriculture, Animal Industry and Fisheries (MAAIF) on the breeds of drought tolerant livestock to be provided to the farmers. • Consultation on the technical specifications of the hydroponic systems have been conducted with MAAIF. • Twelve focused group discussions (FGDs) were held with identified farmers’ groups in the project area. A total 144 participants were involved and subsequently profiled | MS
| Output 3.1.5 Enabling environment for smallholder farmers and pastoralists adaptive activities created |  | Outcome 6 | • At least 15% of smallholder farmers and pastoralists have an Index-based weather insurance scheme • 4 report on drought risk assessments on the agriculture value chain • 12 meetings for at least 5 farmer and/or pastoralist associations or cooperatives in each country |  | • Concept note for drought risk assessments on the agriculture value chain has been prepared is currently being reviewed.
| Output 4.1.1 Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated. |  | Outcome 8 | • 4 brochures, 4 publications (documents) on lessons and best practices from project interventions per country • At least 8 case studies /lessons learn documented, packaged and shared with key stakeholders for upscaling and informing project interventions |  | •The project management unit prepared Information, Education and Communication (IEC) materials to promote visibility of the DRESS-EA project during the Water and Environment Week in March 2022. The major IEC materials developed include brochures, pamphlets, videos, and radio talks. • Three members of PMU from Uganda were facilitated by the REE to attend and contribute to the GHACOF 60 workshops held in Mombasa, Kenya. This was an opportunity to present and share the expected feedback from the GHACOF workshops to achieve the expected interventions of DRESSEA project that address the impact of climate change in Karamoja sub-region. | MS
| 5. 1 Executing Entity Budget/Project launch activities |  | Outcome 7 | • Hold National Launch of the project • Appoint the National Project Steering Committee • Hold the first National Project Steering Committee Meeting |  | • National Project Launch of the project • National Project Steering Committee constituted • The first National Project Steering Committee Meeting held • One additional sociologist (Ms. Lydia Lapwonya) has been recruited to support the DRESS-EA project team in Moroto mainly responsible for community mobilization. She will be paid by the Government of Uganda for the duration of the project. •The IT equipments were procured and delivered to Moroto Office •The Uganda was involved in the development of the online M&E system and in the stakeholder consultations (lokere catchment) • The Uganda project team participated in the drought platforms meeting organised by the GWPEA. | S
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr Callist Tindimugaya
| Email: | callist_tindimugaya@yahoo.co.uk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Justification of the rating Project activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs. However, insecurity due to cattle raiding presented a significant shortcoming on the achievement of most of the indicators within the project sites. Now that the security situation has improved since then, the project is expected to progress rather smoothly in the next reporting period. Positive progress During year 2: i) an assessment of early warning systems has been completed; ii)feedback on the performance of forecasts has been collected, iii)specifications for weather stations have been prepared, iv)communities have been sensitized on the importance of water source protection and inputs for source protection have been quantified. v)learning Centers have been assessed for the establishment of collaboration mechanisms in the capacity building of farmers and pastoralists. The above activities will inform the procurement of supplies for weather stations, gadgets, renovation of early warning centre and database. MoUs are also going to be prepared to establish the collaboration between DRESS-EA and the Learning Centers. Negative progress However, due to the insecurity that occurred in the project area during the months of March, April, and May in 2022, community meetings were discouraged, and this significantly affected the progress of various activities at sub national level. The security situation has now normalised since then and the community engagements are going on smoothly. Specific recommendations for next steps To speed up, procurements for complementary activities have been combined and the process have been initiated. MoUs with C&D and NARO are being fast tracked to kick start community trainings in drought adaptation following a community based field school approach.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Djibouti/Project Coordinator: | Output 1.1.1: Efficient and effective EWS in place/developed |  | Outcome 1 | • An Early Warning System status report prepared. • Modern weather stations setup or upgraded. Two existing weather station upgraded in project sites of each country • One EW information center constructed/renovated in project sites of each country • One early warning information centre including database constructed or renovated and equipped. • At least 70% of farmers and pastoralists utilize EW information in their farming calendars |  | • A meeting was held between members of the National Meteorological Agency (NMA) and ICPAC to collect data on the EWS in Djibouti • The NMA on the request of NEE-DJ has designated a focal point to follow the EWS activities with ICPAC; • 2 meetings (NEE - NMA) were held for the EWS activities to be carried out jointly and to prepare a first draft of the MoU between the two parties; • ToR to asses the EWS status are being published for the 3rd time as there are no valid bids or offers • The technical specifications document of the new agrometeorological stations is validated • The technical team with the Baseline consultant held contact meetings in the various technical departments during the literature review. Then, a field mission was organized to collect the socio-economic parameters of the baseline study through focus groups with the administrative and customary leaders of the project sites. | MS
| Output 1.1.3: Feedback mechanism for EW information developed |  | Outcome 3 | • 64 copies of Minutes (16 meetings per country) • 32 joint meetings per country • 4 KAP survey report • At least 16 press releases per country |  | • Launch reports and KAP survey questionnaires have been provided. | S
| Output 1.1.4: Emergency plan for Drought Management is put in place. |  | Outcome 1 | • 5 emergency response plan for Drought disasters at the regional and national levels • 80 % of the equipment needed for the contingency response is acquired by the end of the project. • 4 warning messages dissemination kit (beacons, flags, sirens, signaling, speakers, telephone, local radio ...) |  | • The contract for the purchase of these two vehicles is being signed | MS
| Output 2.1.1 Drought management plans (DMPs) integrating CC aspects and adaptation actions developed |  | Outcome 4 | • At least 1 national and 1sub-national plan reviewed/developed per country being implemented • At least 1 national and 1sub-national plans translated per country • At least 2 DMPs, integrated into national and subnational plans per country • At least 2 Bye-laws and 2 ordinances formulated per country |  | • The draft terms of reference for a national consultant to develop the drought management plan are completed and submitted for validation | MS
| Output 2.2.1: New/existing regional and national arrangement/ networks for drought management supported |  | Outcome 8 | • 24 copies of meetings Minutes (3 national and 3 sub-national meetings per country) • At least 8 press releases each year per country • At least 4, partnership agreements/MOUs, • 4 platform events each year per country |  | • Meetings between NEE and the technical departments (ANM, Risk and Disaster Management-GRC, Directorate of Environment, Directorate of Major Works-DGT, Directorate of Livestock-DESV, Directorate of Agriculture-DAG, Ministry of Women and Families-MFF) were held to develop a draft of the MoU for activities' execution; • NEE received the designation of the focal points of the technical departments (ANM, Environment, DGT, DESV and DAG) | MS
| Output 3.1.1 Innovative water and soil conservation structures constructed |  | Outcome 5 | • 4 assessment reports on surface water potential and WMP • 32 Units of water harvesting and storage constructed (Djibouti 2 units; Kenya 10 Units; Sudan 12 units and Uganda 8 Units) • 14 mini-irrigation systems constructed (Djibouti 3 units; Kenya 4 Units; Sudan 4 units and Uganda 3 Units) • 9 water wells, springs/oases protected (Djibouti 0 unit; Kenya 3 Units; Sudan 3 units and Uganda 3 Units) • At least 12 Soil and water conservation measures promoted • At least 70% of smallholder farmers and pastoralists undertaking water and soil conservation measures |  | • A technical mission in collaboration with the direction of the rural hydraulics is organized in order to elaborate the technical specifications for the rehabilitation of the hydraulic infrastructures of drinking water of the village of Behidleh • A joint mission with the DGT visited the project sites to identify suitable areas for the implementation of surface water retention structures. | MS
| Output 3.1.2 Ground water sources established/ improved |  | Outcome 5 | • 4 Groundwater assessment report • At least 8 sets of Guidelines for groundwater regulation ( 2 per country being implemented) • At least 60% of the degraded sites restored |  | • The project team has developed terms of reference for a combined groundwater and surface water availability, use and management plan. This study will be conducted by a national water consultant. | MS
| Output 3.1.4 Adaptive livestock and rangeland practices enhanced |  | Outcome 5 | • At least 4 stock route agreements signed per country • About 40% Area/acreage of rangeland improved with rangeland management practices • 160 pastoralists supported with improved livestock breeds per country • 170 livestock bought and distributed in each country • At least 70% of the target pastoralists supported with high value silage • Livestock mortality attributed to droughtreduced by 10% • 80 hydroponic units established per country • At least 16 tonnes of improved grass varieties distributed in each country • At least 80 households with improved feeds and pastures • 12 meetings for at least 5 associations per country |  | • A field mission in partnership with the Directorate of Livestock was conducted to identify the number of livestock in each site of the project and to group the beneficiaries in the form of association or committee | MS
| Output 4.1.2 Drought information management strengthened | Output 4.1.2 Drought information management strengthened | Outcome 8 | • Minutes of 8 meetings on policy engagement at the national level • A gender responsive and scale up strategy per country |  | • The coordinator and focal point of the National Meteorological Agency (ANM), responsible for the drought early warning system activities participated in the GHACOF 60 in Mombasa during 16-18 February 2022. • The technical team made contributions on the status of the project at the drought early warning level on the one hand, and at the national level in general through presentations | MS
| Project inception launch activities (Consultancies, Workshop and travel) |  | Outcome 7 | • 1 workshop to launch the project • 3 working documents of the first year • 1 national steering committee meeting • 5 NEE members appointed. |  | • The Minister appointed the members of NEE (Coordinator, Technical Assistant, Administrative Assistant, Procurement Officer, Accountant); • NEE organized under the patronage of the Minister of Agriculture the launching workshop of the DRESS-EA project on July 27, 2021; • NEE organized under the auspices of the Secretary General of the Ministry of Agriculture the first meeting of the National Steering Committee on August 10, 2021; • NEE, in collaboration with the OSS technical team, developed the procurement plan (PP), the annual work plan (AWPB) and the dashboard for the first year; • NEE organized under the aegis of the Secretary General of the Ministry of Agriculture the first meeting of the national steering committee on August 10, 2021 to validate the documents (AWPB and Dashboard) | S
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Eng. Mouktar Mohamed
| Email: | xared2004@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Justification of the rating Project activities planned for current reporting period are progressing, However lack of offers from national consultants and limited capacities to write ToRs and CN has also been a shortfall. Positive progress During year 2, The purchase of IT equipment, Office furniture, 2 vehicles, the recruitment of technical assistants have been launched, the ToRs have been initiated ( Ac 1.1.1.1, Ac 3.1.1.1 &Ac 3.1.2.1 & and AC 2.1.1.1 ) and KAP survrey actvity is under execution Negative progress During this second year of project implementation, the main challenge encountered is limited expertise at national level limiting responses to call for bids to undertake consultancies Specific recommendations for next steps An action plan was developed for the third year to avoid delays
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Sudan /Project Coordinator: | output 1.1.1:Efficient and effective EWS in place/developed |  | Outcome 1 | • An EWS status report • One EW prototype at national level developed • Two modern weather station set up in the project sites • Two existing weather station upgraded in the project sites • One EW information center constructed/renovated • At least 70% of farmers and pastoralists utilize EW information in their farming calendars |  | • An SLA agreement has been drafted between SMA and HRC to conduct the assessment of the status in EWS in Al Salm Locality. • The in-country consultation on the status of the drought early warning was conducted; the inputs and key recommendations had facilitated REE to develop an easter drought watch prototype. • An online meeting was conducted between the Sudan PMU and the ICPAC to discuss the prototype that was developed • Sudan facilitated and conducted data collection from the field for the baseline study. In addition, a meeting was conducted with the consultant that was appointed by the GWPEA to conduct the baseline study with the directors of the Ministry of Irrigation and water resources, and the feedback from the directors was incorporated by the consultant in the baseline report. | MU
| Output 1.1.3: Feedback mechanism for EW information developed |  | Outcome 3 | • 64 copies of Minutes (16 meetings per country) • 32 joint meetings per country • 4 KAP survey report • At least 16 press releases per country |  | • Sudan had contributed to the development of the Husika mobile application. Through the in-country consultation, the nominated focal point person for drought early warning systems, Sudan presented the needs of which need to be incorporated in the Husika mobile application | MU
| Output 2.1.1 Drought management plans (DMPs) integrating CC aspects and adaptation actions developed |  | Outcome 4 | • At least 1 national and 1sub-national plan reviewed/developed per country being implemented • At least 1 national and 1sub-national plans translated per country • At least 2 DMPs, integrated into national and subnational plans per country • At least 2 Bye-laws and 2 ordinances formulated per country |  | • Sudan participated both in data collection and validation of capacity needs assessment of the stakeholders of DRESS-EA project. The different stakeholders consulted at the national level, state level, community level and private sector representatives. | MU
| Output 2.2.1: New/existing regional and national arrangement/ networks for drought management supported |  | Outcome 8 | • 24 copies of meetings Minutes (3 national and 3 sub-national meetings per country) • At least 8 press releases each year per country • At least 4, partnership agreements/MOUs, • 4 platform events each year per country |  | • Three member of project management unit were facilitated to attend and contribute to the workshop which sought to establish the regional and national drought platforms. | MU
| output 4.1.1:Good practices and lessons on drought management, EWS and Climate Change impacts documented and disseminated |  | Outcome 8 | • 4 brochures, 4 publications (documents) on lessons and best practices from project interventions • At least 8 case studies /lessons learn documented, packaged and shared with key stakeholders for upscaling and informing project interventions |  | • Project document has been translated into local languages for dissemination. | MU
| Output 4.1.2 Drought information management strengthened | Output 4.1.2 Drought information management strengthened | Outcome 8 | • Minutes of 8 meetings on policy engagement at the national level • A gender responsive and scale up strategy per country |  | • A follow-up mission to the WNS and a meeting was conducted in the Ministry of production and economic resources and was shared in the local news • During the GHACOF 60, Sudan had participated in the GHACOF 60 where they presented the interventions expected from DRESS-EA project. Overall, two member of PMU had attended this workshop- held in Mombasa, Kenya. | MU
| Executing Entity Budget/Project launch activities |  | Outcome 7 | • Hold National Launch of the project • Appoint the National Project Steering Committee • Hold the first National Project Steering Committee Meeting |  | • On the 2nd of February 2021 the NSC and the RSC was formed later on the 17th of April 2022 the Private sector Representative was added to the NSC • Set up of new PMU Conduct a follow up mission to the project site • Participation in online biweekly meeting | MU
[6 empty] | Overall Rating | U
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms. Nazik Abdulahi
| Email: | nazikabdullahi@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Justification of the rating The Delay in receiving the funds and the political instability is the reason for not executing the activities according to that the overall rating of Un Satisfactory Positive progress The purchase of IT equipment, office furniture, 1 vehicle and the recruitment of technical assistants have been launched and the ToRs have been initiated. Negative progress Generally, the delays of fund disbursement and political instability had slowed down the project activities execution. Specific recommendations for next steps SLA between SMA and PMUs will be signed to execute core activities, and ToRs will be elaborated for combined activities.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Kenya/Project Coordinator: | output 1.1.1:Efficient and effective EWS in place/developed |  | Outcome 1 | • An EWS status report • One EW prototype at national level developed • Two modern weather station set up in the project sites • Two existing weather station upgraded in the project sites • One EW information center constructed/renovated • At least 70% of farmers and pastoralists utilize EW information in their farming calendars |  | • Kenya had participated in the in-country consultation on the drought early warning. This had facilitated GWPEA in collaboration with ICPAC to develop an Eastern Africa Drought Watch. • Kenya had facilitated the baseline data collection for the DRESSEA project in both Kitui and Samburu Counties. In addition, Kenya in collaboration with GWPEA organized a validation workshops of baseline findings in the workshops held in Nakuru in February 2022. The major inputs from the validation workshop was incorporated in the final report of baseline study | MU
| Output 1.1.3: Feedback mechanism for EW information developed |  | Outcome 3 | • 64 copies of Minutes (16 meetings per country) • 32 joint meetings per country • 4 KAP survey report • At least 16 press releases per country |  | • Kenya had participated in the development of Husika mobile drought watch through the nominated early warning focal point. | HU
| Output 2.1.1 Drought management plans (DMPs) integrating CC aspects and adaptation actions developed |  | Outcome 4 | • At least 1 national and 1sub-national plan reviewed/developed per country being implemented • At least 1 national and 1sub-national plans translated per country • At least 2 DMPs, integrated into national and subnational plans per country • At least 2 Bye-laws and 2 ordinances formulated per country |  | • The data collection and capacity need assessment were conducted in Kenya. The different department consulted include National Government organizations, County Government of Kitui, County Government of Samburu, Non-Governmental Organizations and Faith-Based Organizations. Kenya also participated and validated the findings of the capacity need at national level and regional level. • Kenya had participated in the preparation and validation of the training manuals developed based on the capacity need assessment | MU
| Output 4.1.2 Drought information management strengthened | Output 4.1.2 Drought information management strengthened | Outcome 8 | • Minutes of 8 meetings on policy engagement at the national level • A gender responsive and scale up strategy per country |  | • The Kenya PMU participated in and contributed the Great Horn of Africa Climate outlook forum (GHACOF) 60 held in Mombasa, Kenya. The Kenyan PMU had then the opportunity to present the interventions of DRESS-EA project in the counties of Samburu and Kitui. | MU
| 5. 1 Executing Entity Budget/Project launch activities |  | Outcome 7 | • Hold National Launch of the project • Appoint the National Project Steering Committee • Hold the first National Project Steering Committee Meeting |  | • Appoitment of the project coordinator • Project was launched • National Project Steering Committee constituted • The first National Project Steering Committee Meeting held • The work plan and procurement plan for the 2 years was approved | MS
[6 empty] | Overall Rating | U
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Thomas Lerenten
| Email: | lerenten12@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Justification of the rating The Republic of Kenya delayed launching the project officially, due to the planned presidential elections as well as technical issues in opening the bank account, the overall rating is Unsatisfactory Positive progress The PMU has participated in the regional activities significantly strengthening the capacity of PMU. Kenya officially launched the Project in April 2022 and had the first meeting of the National Steering Committee. The committee also discussed and approved the annual work plan that has been signed off by the Principal secretary Ministry of Environment and Forestry. Kenya has launched the procurement procedure for the 1 vehicle and Project technical officer and iniated the elaborattion of ToRs to undertake activities taking into account lessons learnt from progressing entities. Negative progress Generally, the political instability and elections had slowed down the project activities execution. Specific recommendations for next steps Agreement between CCD & KMD and PMUs will be signed to spearhead activities as well as the promotion of close collaboration with agencies and other EEs.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective:1 | • Number of EWS beneficiaries and users • Number of beneficiary communities of adaptation measures • Proportion (%) of smallholder farmers and pastoralists with increased incomes | 0 | 0 | • Number of EWS beneficiaries and users (to be determined) • Number of beneficiary communities of adaptation measures (to be determined) • At least 60% of smallholder farmers and pastoralists with increased incomes
Outcome 1.1 | • Proportion of targeted farmers and pastoralists that access and integrate EW information into seasonal calendars | 0 | 0 | • At least 70% of targeted smallholder farmers and pastoralists access and integrate EW information into seasonal calendars
Output 1.1.1 | • EWS status report • Number of weather stations set up and upgraded with Remote sensing derived products, time series of bioclimatic variables • Number EW prototypes at national and regional levels developed • Number of EW information centers constructed, renovated and equipped • Number of times EW information has been released by mandated institutions as planned • Number of farmers and pastoralists utilizing EW information • Number of baseline reports | 0 | • 1 EWS status report (Uganda) • 1 EW prototype at national and regional levels (GWPEA) • 2% of farmers and pastoralist utilize EW information • 4 baseline reports are developed | • An EWS status report per country • One EW prototype at national and regional levels developed • Two modern weather station set up in project sites of each country • Two existing weather station upgraded in project sites of each country • One EW information center constructed/renovated in project sites of each country • At least 70% of farmers and pastoralists utilize EW information in their farming calendars • 4 baseline report
Output 1.1.2 | • Framework agreement document • A strategy document • Minutes of meetings • Approved plan (document) incorporating EW information | 0 | • 1 EW information framework agreement is developed in Uganda • 1 inter-ministerial Meeting held at regional level • 1 meeting at national level held in Uganda • 1 meeting at sub-national level held in Uganda | • 1 EW information framework agreement developed/reviewed in each country • One strategic document developed • 1 inter-ministerial Meeting minutes at regional; • 32 meetings minutes at the national level (8 per country) and • 32 meetings minutes at the sub-national level (8 per country) • 3 meetings minutes at regional level (fora) • 24 meetings minutes at national level (fora) • 24 meetings minutes at subnational level (fora) • 4 document copy of approved plans incorporating EW information
Output 1.1.3 | • Minutes of stakeholder meetings • Number of information sharing platforms established • Number of Press releases • KAP survey report • A tool for accessing, utilizing and reporting EW information developed | 0 | • 1 copy of minutes at regional level • 3 press releases (1 regional , 2 national) | • 64 copies of Minutes (16 meetings per country) • 32 joint meetings per country • 4 KAP survey report • At least 16 press releases per country • A tool for accessing, utilizing and reporting
Output 1.1.4 | • Number of emergency response plan for Drought disasters at the regional and national levels. • Percentage of the equipment needed for the contingency response is acquired by the end of the project • Number of blank operations (including regional and national levels) • Number of warning messages dissemination kit (beacons, flags, sirens, signaling, speakers, telephone, local radio ...) | 0 | • 6 vehicles were procured | • 5 emergency response plan for Drought disasters at the regional and national levels. • 80 % of the equipment needed for the contingency response is acquired by the end of the project. • 2 of blank operations (including regional and national levels) • 4 warning messages dissemination kit (beacons, flags, sirens, signaling, speakers, telephone, local radio ...)
Outcome 2.1 | • Number of staff in targeted institutions at regional and national and local level with enhanced capacity in drought management • Percentage of farmers and pastoralists with increased knowledge and skills in drought adaptation actions | 0 | •25 (engagements with the NEE Project Management units) | • Number of staff in targeted institutions trained (to be determined) • At least 80% of targeted farmers and pastoralists trained
Output 2.1.1 | • Number of DMP,s • Number of DMPs translated and distributed • Number of national and sub-national plans with DM component integrated • Bye-laws and ordinances formulated | 0 | 0 | • At least 1 national and 1 sub-national plan reviewed/developed per country being implemented • At least 1 national and 1 sub-national plans translated per country • At least 2 DMPs, integrated into national and subnational plans per country • At least 2 Bye-laws and 2 ordinances formulated per country
Output 2.1.2 | • Capacity needs assessment report • Copies of capacity building plans, • Copies of training manuals • Number of stakeholders trained • Number of learning centers established | 0 | 0 | • 4 Capacity needs assessment report • 4 Copies of capacity building plans • 4 Copies of training manuals • 12 exchange visits (3 per country) • 8 trainings for staff managing EW information centers (2 per country) • 36 trainings for extension staff and artisans in drought adaptation (9 per country) • 96 community training workshops (24 per country) • At least 80% of targeted stakeholders trained • 12 learning centers for farmers and pastoralists established per country
Outcome 2.2: | • Number of Functional frameworks for drought management at different levels per country | 0 | 0 | • At least 6 Functional frameworks for drought management established
Output 2.2.1 | • Number of minutes of regional meeting • Number of minutes for national and subnational meetings • Number of platform events organized and press releases on drought management issues • Number of partnership agreements or MOUs reviewed or developed • Number of Platforms • Number of drought adaptation proposals developed jointly | 0 | • 1 meeting held at regional level | • 3 copies of Minutes of regional meeting • 24 copies of meetings Minutes (3 national and 3 sub-national meetings per country) • At least 8 press releases each year per country • At least 4, partnership agreements/MOUs, • 4 platform events each year per country • At least 4 regional proposals developed and submitted for funding
Outcome 3.1 | • Percentage of farmers and pastoralists undertaking drought adaptation actions • Percentage increase in crop and livestock production | 0 | 0 | • At least 60% of farmers and pastoralists are undertaking drought adaptation actions • At least 60% of smallholder farmers and pastoralists have alternatives
Output 3.1.1 | • Number of assessment reports on surface water potential and WMP • Number of water harvesting and storage structures constructed • Number of mini-irrigation systems constructed • Number of water wells and springs protected • Number of Soil and water conservation measure • Number of farmers and pastoralists undertaking soil and water conservation technologies | 0 | 0 | • 4 assessment reports on surface water potential and WMP • 32 Units of water harvesting and storage constructed (Djibouti 2 units; Kenya 10 Units; Sudan 12 units and Uganda 8 Units) • 14 mini-irrigation systems constructed (Djibouti 3 units; Kenya 4 Units; Sudan 4 units and Uganda 3 Units) • 9 water wells, springs/oases protected (Djibouti 0 unit; Kenya 3 Units; Sudan 3 units and Uganda 3 Units) • At least 12 Soil and water conservation measures promoted • At least 70% of smallholder farmers and pastoralists undertaking water and soil conservation measures
Output 3.1.2 | • A report on groundwater assessment • A report/Guidelines/regulation on groundwater resources developed • Area (acreage) of degraded site restored | 0 | 0 | • 4 Groundwater assessment report • At least 8 sets of Guidelines for groundwater regulation ( 2 per country being implemented) • At least 60% of the degraded sites restored
Output 3.1.3 | • Number of farmers and pastoralists supported with crop varieties, • Kilograms of seed/cuttings of droughtresistant crop varieties bought and distributed • Number of agroforestry tree seedlings bought and distributed • Quantities of inputs for irrigated agriculture • Number of small irrigation units • Number of CSA Units • Number of farmers engaged in climatesmart agricultural practices | 0 | 0 | • At least 70% of the targeted farmers and pastoralists have accessed droughtresistant crop varieties • At least 15 tons of seeds/cuttings for droughtresistant crop varieties distributed in each country • At least 50% of the target pastoralists have accessed drought tolerant and fast growing pasture seeds • At least 100 hectares of degraded landscapes restored in each country • At least 36 irrigation units (Djibouti 10 units; Kenya 8 Units; Sudan 10 units and Uganda 8 Units) • At least 28 Climate smart agricultural units are developed (Djibouti 6 units; Kenya 6 Units; Sudan 8 units and Uganda 8 Units) • At least 60% of targetedfarmers undertake Climat
Output 3.1.4 | • Number of stock routes agreements • Area/acreage of rangeland improved with rangeland management practices • Number of pastoralists supported with improved animal breeds • Livestock numbers bought and distributed • Percentage reduction in mortality of livestock • Number of hydroponic units established • Quantities of improved grass varieties seed • Number of households with improved feeds and pastures • Number of meetings of associations/groups/cooperatives of livestock | 0 | 0 | • At least 4 stock route agreements signed per country • About 40% Area/acreage of rangeland improved with rangeland management practices • 160 pastoralists supported with improved livestock breeds per country • 170 livestock bought and distributed in each country • At least 70% of the target pastoralists supported with high value silage • Livestock mortality attributed to droughtreduced by 10% • 80 hydroponic units established per country • At least 16 tonnes of improved grass varieties distributed in each country • At least 80 households with improved feeds and pastures • 12 meetings for at least 5 associations per country
Output 3.1.5 | • Number of pastoralists and smallholder farmers accessing Indexbased weather insurance • A report on drought risk assessments on the agriculture value chain • Minutes of meetings and workshops for farmer and pastoralists associations/cooperatives meetings | 0 | 0 | • At least 15% of smallholder farmers and pastoralists have an Index-based weather insurance scheme • 4 report on drought risk assessments on the agriculture value chain • 12 meetings for at least 5 farmer and/or pastoralist associations or cooperatives in each country
Output 3.1.6 | • Number of business enterprises promoted by women and youth groups • Number of households undertaking IGAs • Number of groups supported by grants • Number of groups/cooperatives supported to undertake value addition for their agricultural products | 0 | 0 | • At least 9 IGAs undertaken by households, women and youth groups in each country • At least 240 Households supported to undertake IGAs per country • At least 10 groups given grants to undertake adaptation actions per country • At least 9 cooperatives supported to add value to their crop and livestock products for each country
Outcome 4.1 | • Percentage of households of targeted farmers and pastoralists practicing drought adaptation actions | 0 | 0 | • At least 80% of the targeted actors participating in regional information sharing plateforms
Output 4.1.1 | • Number of knowledge products e.g. documents on lessons and best practices from project interventions • Number of case studies and lessons learned documented and shared projects | 0 | • 5 brochures • 3 policy briefs • 4 posters • video uploaded on existing platforms | • 4 brochures, 4 publications (documents) on lessons and best practices from project interventions per country • At least 8 case studies /lessons learn documented, packaged and shared with key stakeholders for upscaling and informing project interventions
Output 4.1.2 | • Number of meetings for information generation and sharing • Number meetings on policy engagement at the national level • Number of platforms or fora organized jointly • Number of information sharing events organized at regional level • A gender responsive and scale-up strategy document for drought, CC and early warning technologies for vulnerable groups | 0 | • 2 regional meetings | • Minutes of 4 regional meetings held • Minutes of 8 meetings on policy engagement at the national level • At least 8 information sharing events organized et regional level • A gender responsive and scale up strategy per country

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Negative • Early capacity building of the executing parties is critical. These enables team to understand the project philosophy. • Covid-19 was one of the force majeure events that affected the execution of project activities in addition to the administrative issues experienced in the operationalization. • The security situation in Uganda contributed to delay in execution and inadequate data collection. This was coupled by difficulties in organising meetings in the project sites. Also the securing of equipment and permanently locating the weather stations in the project sites was identified as a barrier in Uganda. •The general political elections and barriiers hampered the project initiate in the project sites •Inadequate capacity in populating project documents e.g. No-objection tracker and limited capacity of PMUs to provide high quality documents e.g. No objections to the RIE
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | • Delay to start the activity due to meeting grant agreement conditions of entry into force conditions • Government bureaucracy- For example in procurements, they take a long time • Lack of communication between PMU staff and local communities due to native language in project sites • Limited technical capacity for processing climate data and generating relevant climate information products Measures: • Continuous engagement with government officials in Kenya and Sudan to align on agreed measures. • Assessment of activities that could be undertaken in tandem • Use of framework contracts and force on accounts methods of procurement. • The RIE is in constant discussions and follow up directly with the responsible departments/persons on execution of tasks. • NPMU members will be hired to support the execution of project acvities taking into account specificities of the native language. • A dynamic process of updating the reference data is being adopted in the framework of the project through its different missions.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | • No necessary change in project design, but engagement of the Steering Committee members and principal secretaries enhances the execution processes. • No changes were undertaken per say given that the concrete actions had not yet commenced.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | N/A
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes. The project has made deliberate effort to ensure gender inclusion in the various nominations of participants and committee membership. However, the ratio of Women to Men remains low i.e. in the ratio of 1:5. Further engagement at the different levels will have to be done to improve this outlook. This will include discussions and presentations to the project steering committee at Regional and National levels and also engaging the principal /under secretaries of countries.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | AFR/RIE/DRR/2017/1
Implementing Entity | Sahara and Sahel Observatory
Type of implementing entity | RIE
Country | Djibouti
Country | Sudan
Country | Kenya
Country | Uganda
Region | Africa
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 771786 | 701624 | 70162 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 42% | 41% | 41% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 18% | 17% | 17% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 2: Partially effective | Total | 674811 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 4 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated | 8 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 2 | 2: Monitoring and warning service | Geographical coverage | Regional | 9 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | National | 4 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 8 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 46 | 0% | Public |  |  | 30%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Disaster risk reduction | 1: No capacity | Public | National | Disaster risk reduction | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 771212 | 30% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 2 | 20% to 39% | 1: Aware of neither |  | 5 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 1 | Training manuals | National |  | 4 | Training manuals | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Regional | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Health | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Health | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Other | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Other | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Health | 2 | Community |  | Health
|  | 0 | Community |  | Water management | 2 | Community |  | Water management
|  | 0 | Community |  | Agriculture | 1 | Community |  | Agriculture
|  | 1 | National |  | Disaster risk reduction | 4 | National |  | Disaster risk reduction
|  | 0 | Community |  | Other | 4 | Community |  | Other
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 2 | Disaster risk reduction | National | Water policy | 4 | Disaster risk reduction | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness