## Overview
Project Performance Report (PPR)-III
* Refers to both projects and programs
| Period of Report (Dates) | 26 June 2021 -25 June 2022
| Project Title: | Integrating Flood and Drought management and Early warning for climate change adaptation in the Volta Basin (VFDM)
| Project Summary: | The VFDM project will provide the first large scale and transboundary implementation of Integrated Flood and Drought Management by empowering the National Meteorological and Hydrological Services (NMHS) and other competent authorities of the six riparian countries (Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali, and Togo) with robust and innovative solutions for disaster risk reduction and climate change adaptation, including ecosystem-based solutions and gender-sensitive participatory approaches. An early warning system (EWS) will be designed to reach the civil security services and other private and public stakeholders. The three specific objectives of the project are to: 1)Develop capacity and established frameworks at the local, national and regional levels to ensure risk-informed decision-making; 2) Develop concrete adaptation and environmentally friendly actions with an integrated approach; 3) Strengthening policy and institutional capacity for integrated flood and drought management at the local, national, and transboundary levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | Not available at the project page at the Adaptation Fund website https://www.adaptation-fund.org/project/integrating-flood-drought-management-early-warning-climate-change-adaptation-volta-basin-benin-burkina-faso-cote-divoire-ghana-mali-togo/ | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Meteorological Organization(WMO) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali, and Togo | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Volta River Basin covering an area of about 400,000 km2 with a population of 29 Million (2016) and extending from semi-arid to sub-humid areas | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-10-12
IE-AFB Agreement Signature Date: |  | 2019-02-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-06-25 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 09/03/2022 (start date) and 22/07/2022 (completion date)
| Original Completion Date: | 2023-06-25
Revised Completion Date after approval of |  | 2024-06-25
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | No approval condition or clause was listed during the approval of the VFDM project | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.floodmanagement.info/floodmanagement/volta-basin/ | Democratic Republic of the Congo
https://public.wmo.int/en/projects/integrating-flood-and-drought-management-and-early-warning-climate-change-adaptation-0
https://www.adaptation-fund.org/project/integrating-flood-drought-management-early-warning-climate-change-adaptation-volta-basin-benin-burkina-faso-cote-divoire-ghana-mali-togo/
Denmark
List documents/ reports/ brochures / articles that have been prepared about the project. |  |  | Denmark
https://www.floodmanagement.info/vfdm-newsletter-july-2022/
http://abv.int/en/training-of-experts-in-flood-and-drought-management-in-the-volta-basin/
https://www.youtube.com/watch?v=SCtIb_qyiFs
https://www.ghanaweb.com/GhanaHomePage/NewsArchive/Workshop-on-Nature-based-Solution-to-flood-and-drought-opens-in-Accra-1471052
https://www.ghanaiantimes.com.gh/workshop-on-volta-basin-countries-opens-in-accra/
https://www.graphic.com.gh/news/general-news/stakeholders-deliberate-on-management-of-volta-river-basin.html
https://newsinafrica.blog/workshop-on-volta-basin-countries-opens-in-accra
https://www.ghanaenvironment.com/apply-environmentally-sound-nature-based-solutions-in-the-forecasting-of-programmes-dapaah/
https://youtu.be/-On5jXhwNUs
https://news.abidjan.net/articles/702669/inondation-et-secheresse-le-bassin-de-la-volta-a-la-recherche-de-solution
https://www.linfodrome.com/societe/72869-bassin-de-la-volta-un-atelier-organise-pour-ameliorer-les-plans-de-gestion-des-inondations-et-de-secheresse
https://youtu.be/9jPAImZbDFY
https://www.aip.ci/cote-divoire-aip-les-acteurs-du-bassin-de-la-volta-a-la-recherche-de-solutions-fondees-sur-la-nature/
https://linterview.info/2021/11/29/8187/
https://www.linfodrome.com/societe/72716-bassin-de-la-volta-les-acteurs-renforcent-leurs-capacites-sur-les-solutions-fondees-sur-la-nature
https://www.floodmanagement.info/we-are-on-climate-home-news/
https://newsghana.com.gh/west-african-volta-basin-countries-seek-ways-to-manage-severe-flooding-drought/
https://www.facebook.com/100001412423848/posts/5339740806082947/?sfnsn=mo
https://newsghana.com.gh/bongo-kunkua-is-new-site-for-hydro-meteorological-station/
http://www.faapa.info/blog/hydro-meteorological-station-installed-at-bongo-kunkua/
https://www.ghanaweb.com/region/canardafriq/Upper-East-Region-ORGIS-Ghana-Assist-Kunkua-Community-in-the-Bongo-District-2402
https://www.floodmanagement.info/vfdm-project-two-back-to-back-regional-workshops-on-going-in-lome-togo-2/
https://www.floodmanagement.info/three-day-hybrid-training-on-mydewetra-voltalarm-ews-for-the-volta-basin-countries/
https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2020/04/Project-Factsheet-EN.pdf
https://public.wmo.int/en/media/news/wmo-leads-new-flood-and-drought-management-project-volta-basin
https://public.wmo.int/en/resources/bulletin/integrated-approach-flood-and-drought-management-volta-basin
https://wmoomm.sharepoint.com/:b:/s/Services/ET-6ZVR9Lg1MhA8leqfnnesBJm9B2miya5mEy-XiZ5Bthg?e=uk1wNI
https://www.gwp.org/en/GWP-West-Africa/WE-ACT/News--Events/a-new-project-to-support-transboundary-climate-change-resilience-in-the-volta-basin/
https://www.gwp.org/fr/GWP-Afrique-Ouest/GWP-in-Action/News--Activities/un-nouveau-projet-pour-soutenir-la-resilience-au-changement-climatique-dans-le-bassin-de-la-volta/
https://public.wmo.int/en/events/workshops/inception-workshop-and-executive-partners-meeting-planned-under-framework-of-volta
https://www.fratmat.info/article/91460/62/gestion-des-inondations-et-de-la-secheresse-l-autorite-du-bassin-de-la-volta-lance-un-projet
Mali – https://www.maliweb.net/environnement/lutte-contre-les-inondations-et-secheresses-au-mali-des-cartes-de-risques-bientot-disponibles-2934422.html
Ghana – https://www.graphic.com.gh/news/general-news/new-floods-and-drought-maps-to-help-tackle-floods-in-ghana.html
Togo – https://www.ecoconscience.tv/bientot-le-bassin-de-la-volta-disposera-des-cartes-de-risque-des-inondations-et-de-la-secheresse/
Burkina Faso – https://www.burkinademain.com/2021/06/24/vfdm-au-burkina-renforcement-des-capacites-des-acteurs-nationaux-a-koudougou/
Bénin – https://matinlibre.com/2021/07/07/atelier-national-de-formation-sur-la-cartographie-mieux-faire-face-aux-risques-des-inondations-et-de-secheresse-dans-le-bassin-de-la-volta/
https://www.gwp.org/fr/GWP-Afrique-Ouest/GWP-in-Action/News--Activities/un-nouveau-projet-pour-soutenir-la-resilience-au-changement-climatique-dans-le-bassin-de-la-volta/
Denmark
| Project contacts: |  | Djibouti
WMO Project Manager/Coordinator |  |  | Dominica
| Name: | Mr Ramesh Tripathi, World Meteorological Organization Secretariat | Dominican Republic
| Email: | rtripathi@wmo.int | Ecuador
| Date: | 2022-09-16 | Egypt
Government DA Benin
| Name: | Prof. Martin Pépin AINA Directeur Général de l’Environnement et du Climat | Equatoral Guinea
| Email: | maina@gouv.bj/mouinakonhan@gouv.bj | Eritrea
| Date: | 2022-08-22 | Estonia
Government DA Burkina Faso
| Name: | Mr. Inoussa Ouiminga Directeur General de la Cooperation
| Email: | jouiminga@yahoo.fr
| Date: | 2022-08-22
Government DA Côte d’Ivoire
| Name: | Mr. Marcel Ignace Fodjo, Economist, Engineer Environmental
| Email: | marcelfodjo@live.fr
| Date: | 2022-09-22
Government DA Ghana
| Name: | Mr. Peter Justice Dery, Director for Environment
| Email: | Peterjdery@yahoo.com
| Date: | 2022-09-22
Government DA Mali
| Name: | Mrs. Niambele Aminata Diarra Ingénieur d’Agriculture et du Génie Rural
| Email: | mineyitou@yahoo.fr
| Date: | 2022-09-22
Government DA Togo
| Name: | Mme Méry Yaou Directeur de l’Environnement
| Email: | ymery69@yahoo.fr; joaljesus@gmail.com; joaljesus1@gmail.com
| Date: | 2022-09-22
Implemeting Agency-WMO
| Name: | Jean-Paul Gaudechoux, WMO
| Email: | jpgaudechoux@wmo.int | Finland
| Date: | 2022-09-15 | France
| Name: | Dr Hwirin Kim, Head, HWR, Services Department | Gambia
| Email: | hkim@wmo.int | Georgia
| Date: | 2022-09-15 | Germany
| Executing Agency-WMO |  | Ghana
| Name: | Giacomo Teruggi, Scientific Officer, HWR, WMO
| Email: | gteruggi@wmo.int
| Date: | 2022-09-22
| Name: | Mr Ramesh Tripathi, Project officer
| Email: | rtripathi@wmo.int
| Date: | 2022-09-22
| Executing Agency-VBA |  | Greece
| Name: | Mr Robert Dessouassi , Executive Directorate | Grenada
| Email: | rdessouassi@abv.int | Guatemala
| Date: | 2022-09-15 | Guinea
| Name: | Mr Boukary NIAMPA, Project Technical Manager
| Email: | b.niampa@abv.int
| Date: | 2022-09-15
| Executing Agency-GWP-WA |  | Guinea Bissau
| Name: | Mr Armand Houanye, Executive Secretary | Guyana
| Email: | armand.houanye@gwpao.org | Haiti
| Date: | 2022-09-15 | Honduras
| Name: | Mr Maxime TEBLEKOU, Project Technical Assistant
| Email: | maxime.teblekou@gwpao.org
| Date: | 2022-09-15
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from 26/06/2019 to 25/06/2020 | [5 empty] | Financial information PPR 2: cumulative from 26/06/2019 to 25/06/2021 | [6 empty] | Financial information PPR 3: cumulative from 26/06/2019 to 25/06/2022
DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS | [6 empty] | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [6 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement (USD) as of 25/06/2020 |  | 2095000 |  |  |  | Estimated cumulative total disbursement (USD) as of 25/06//2021 including PFG1 and PFG2 |  | 4386400 |  |  |  |  | Estimated cumulative total disbursement (USD) as of 25/06//2022 including PFG1 and PFG2 |  | 4154432
Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements made to the Executing Entities, with VBA and GWP-WA receiving funds for the project staffs in September 2019. The IE hired the Project Manager based at the WMO Secretariat using the IE Fee.The IE Trust Fund and the implementation contracts with the Executing Partners and External Implementing Partners are contracted in the same currency (USD) as provided by the Adaptation Fund.This will avoid losses due to currency fluctuation. The IE and EEs are utilising the project execution costs as indicated in the project document. The Project Inception workshop was organized and conducted on 25 and 26 June 2019 and Inception workshop report was submitted to the AF Secretariat on July 24 2019. Out of the total 2,09,5000 amount received from the Adaptation Fund: 20,000 USD was received as PFG1, 80,000 USD as PFG2 and 1,995,000 USD as first year project disbursement |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements were made to the Executing Entities, with VBA and GWP-WA receiving funds for the project staffs in September 2019, June 2020 and November-December 2020. The IE hired and paid the Project Manager based at the WMO Secretariat using the IE Fee.The IE Trust Fund and the implementation contracts with the Executing Partners and External Implementing Partners are contracted in the same currency (USD) as provided by the Adaptation Fund. This will avoid losses due to currency fluctuation but Executing entity reported is a minor loss of currency due to Bank Transfer to the National agencies or partners. The IE and EEs are utilising the project execution costs as indicated in the project document. The Project Inception workshop was organized and conducted on 25 and 26 June 2019 and Inception workshop report was submitted to the AF Secretariat on July 24 2019. The first PPR-I report was succesfully approved on 21 September 2021 by the Adaptation Fund Secretariat/Board and the funds for the second year implementation was received on 15 October 2020 Out of the total 4,386,400 amount received from the Adaptation Fund: 20,000 USD was received as PFG1, 80,000 USD as PFG2, 1,995,000 USD as the first year and 2,291,400 USD as the second year project disbursements |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements were made to the Executing Entities, with VBA and GWP-WA receiving funds for the project staffs in 2019, 2020, 2021 and 2022. The IE hired and paid the Project Manager based at the WMO Secretariat using the IE Fee.The IE Trust Fund and the implementation contracts with the Executing Partners and External Implementing Partners are contracted in the same currency (USD) as provided by the Adaptation Fund. This will avoid losses due to currency fluctuation but IE and Executing entity reported is a minor loss of currency due to Bank Transfer to the National agencies or partners. The IE and EEs are utilising the project execution costs as indicated in the project document. The Project Inception workshop was organized and conducted on 25 and 26 June 2019 and Inception workshop report was submitted to the AF Secretariat on July 24 2019 The PPR-I and PPR-II reports were succesfully approved on 21 September 2021 and 18 January 2022 by the Adaptation Fund Secretariat/Board and the funds for the third year implementation was received around end of January 2022 Out of the total 7,222,000 USD amount received from the Adaptation Fund: 20,000 USD was received as PFG1, 80,000 USD as PFG2, 1,995,000 USD as the first year, 2,291,400 USD as the second year and 2,835,600 USD as project related disbursements
INVESTMENT INCOME |  | 0 |  |  |  | INVESTMENT INCOME |  | 0 |  |  |  |  | INVESTMENT INCOME |  | 0
Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant | [6 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA | [6 empty] | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION (PFG1: Project Formulation Grant 1, PFG2: Project Formulation Grant 2, A: Project activity) | AMOUNT SPENT (USD) (Assuming 1 CHF approximately equal to 1 USD for some of the expenses) | AMOUNT PENDING WITH OBLIGATION (USD) | COMMENTS OR REMARKS | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION (exculding PFG1: Project Formulation Grant 1, PFG2: Project Formulation Grant 2, showing Project activity) | AMOUNT SPENT (USD) (Assuming 1 CHF approximately equal to 1 USD for some of the expenses) | AMOUNT PENDING WITH OBLIGATION (USD) | COMMENTS OR REMARKS |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION (exculding PFG1: Project Formulation Grant 1, PFG2: Project Formulation Grant 2, showing Project activity) | AMOUNT SPENT (USD) (Assuming 1 CHF approximately equal to 1 USD for some of the expenses) | AMOUNT PENDING WITH OBLIGATION (USD) | COMMENTS OR REMARKS
|  | First installment amount received from the Adaptation Fund | 1995000 |  |  |  |  | First and second installment amount received from the Adaptation Fund | 4286400 | [5 empty] | First, secondand third installment amount received from the Adaptation Fund | 7122000
Output | 1.1.1-Inventory of information on VCERs for floods and drought in the Volta Basin is conducted | A: 1.1.1.1-Conduct a desk study and field visits to identify VCERs, gaps and additional needs | 77000 | 0 | Mostly completed. National Consultation reports are available here: https://wmoomm.sharepoint.com/:f:/s/Services/EnvmhBfd9RVCtrufTGCqFnABC-xCWUernat8Ja0T4FWeXw?e=Ry86KG | Output | 1.1.1-Inventory of information on VCERs for floods and drought in the Volta Basin is conducted | A: 1.1.1.1-Conduct a desk study and field visits to identify VCERs, gaps and additional needs | 77000 | 0 | Completed National Consultation report with the action plan is available below https://www.floodmanagement.info/volta-basin/deliverables/ |  | Output | 1.1.1-Inventory of information on VCERs for floods and drought in the Volta Basin is conducted | A: 1.1.1.1-Conduct a desk study and field visits to identify VCERs, gaps and additional needs | 77000 | 0 | Completed National Consultation report with the action plan is available below https://www.floodmanagement.info/volta-basin/deliverables/
|  | A: 1.1.1.2-Develop an action plan to complement gathered information on the VCERs and fulfil technical gaps (maps, satellite data requirements) | 0 | 21000 | It was planned to be done during the National workshops (initially planned during February and March 2020) under 1.1.1.3 but due to Covid-19 Pandemic situation, National workshops are currently planned from 21 September -13 October 2020. |  |  | A: 1.1.1.2-Develop an action plan to complement gathered information on the VCERs and fulfil technical gaps (maps, satellite data requirements) | 21000 | 0 |  |  |  |  | A: 1.1.1.2-Develop an action plan to complement gathered information on the VCERs and fulfil technical gaps (maps, satellite data requirements) | 21000 | 0
|  | A:1.1.1.3-Organize workshops/meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | 136000 | 32000 | It was planned for February -March 2020, but due to Covid-19 situation.National workshops are currently planned from 21september -13 October 2020. |  |  | A:1.1.1.3-Organize workshops/meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | 136000 | 0 | National workshops organized https://www.floodmanagement.info/vfdm-national-workshop/ and the workshop reports are available here https://www.floodmanagement.info/volta-basin/deliverables/ |  |  |  | A:1.1.1.3-Organize workshops/meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | 136000 | 0 | National workshops organized https://www.floodmanagement.info/vfdm-national-workshop/ and the workshop reports are available here https://www.floodmanagement.info/volta-basin/deliverables/
|  | A.1.1.1.4 Conduct pilot field studies with 60 communities to identify multi-drivers of vulnerabilities and risks | 59000 | 37000 | on-going |  |  | A.1.1.1.4 Conduct pilot field studies with 60 communities to identify multi-drivers of vulnerabilities and risks | 59000 | 37000 | Completed Community consultation report is available here https://www.floodmanagement.info/volta-basin/deliverables/ |  |  |  | A.1.1.1.4 Conduct pilot field studies with 60 communities to identify multi-drivers of vulnerabilities and risks | 96000 | 0 | Completed Community consultation report is available here https://www.floodmanagement.info/volta-basin/deliverables/
|  | A 1.1.1.5 Draft the field studies reports and the Volta-atlas | 0 | 5000 | on-going |  |  | A 1.1.1.5 Draft the field studies reports and the Volta-atlas | 5000 | 0 | Completed |  |  |  | A 1.1.1.5 Draft the field studies reports and the Volta-atlas | 5000 | 0 | Completed
| 1.1.2-Database of VCERs, floods and drought related risk maps are developed | A 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise | 8000 | 5000 | preparartion on-going. Require visit to the project countries. |  | 1.1.2-Database of VCERs, floods and drought related risk maps are developed | A 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise | 8000 | 5000 | Mostly completed. Survey, Missing information sheet and Visit to countries were organized to collect necessary available information. |  |  | 1.1.2-Database of VCERs, floods and drought related risk maps are developed | A 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise | 13000 | 0 | Mostly completed. Survey, Missing information sheet and Visit to countries were organized to collect necessary available information.
|  | A 1.1.2.2 Create the Volta Basin information exchange IT network | 0 | 10000 | On-going |  |  | A 1.1.2.2 Create the Volta Basin information exchange IT network | 10000 | 0 | Almost completed. National draft reports are available here https://www.floodmanagement.info/volta-basin/deliverables/ |  |  |  | A 1.1.2.2 Create the Volta Basin information exchange IT network | 9418 | 0 | Almost completed. National draft reports are available here https://www.floodmanagement.info/volta-basin/deliverables/
|  | A 1.1.2.4 Develop web-based flood and drought risk maps | 0 | 30000 | Integration of existing information available globally, nationally and through completed and on-going projects |  |  | A 1.1.2.4 Develop web-based flood and drought risk maps | 150000 | 49200 | Integration of existing information available globally, nationally and through completed and on-going projects. Risks maps and data and information are already integrated under https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta Integration of other projects at the regional level is on-going. There are issues in connecting databases and outputs of the other projects as they are not open-sources or Internet security is not allowing the access. The project is solving the issue with the National stakeholders or project partners. First face-to-face National workshops on developing risk maps with the Technicians were conducted between 23rd June 2021- 06 July 2021 https://www.floodmanagement.info/hybrid-national-training-workshop-with-the-technicians/ The next steps would be to develop the hazard, exposure and vulnerabilities layers for creating the risk maps. This is expected to be completed by November 2021 |  |  |  | A 1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 0 | 99900 | The procurement process to purchase national servers and IT system are on-going. Possibly installed by December 2022
| 1.2.3 | Impact on environmental and ecosystem services indicators is evaluated for current and future scenarios | 62878 | 51622 | Some activities are conducted virtually due to covid-19 and others will be implemented looking at the covid-19 situation |  |  | A1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 0 | 10000 | Could not be implemented as activity 1.2.2.2 was delayed due to the Global Covid-19 situation. On-going will be completed by December 2021 |  |  |  | A 1.1.2.4 Develop web-based flood and drought risk maps | 170000 |  | Integration of existing information available globally, nationally and through completed and on-going projects. Risks maps and data and information are already integrated under https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta Integration of other projects at the regional level is on-going. There are issues in connecting databases and outputs of the other projects as they are not open-sources or Internet security is not allowing the access. The project is solving the issue with the National stakeholders or project partners. First face-to-face National workshops on developing risk maps with the Technicians were conducted between 23rd June 2021- 06 July 2021 https://www.floodmanagement.info/hybrid-national-training-workshop-with-the-technicians/ The next steps would be to develop the hazard, exposure and vulnerabilities layers for creating the risk maps. This is expected to be completed by November 2021
| 2.1.2 The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | A 2.1.2.1-Define the needs related to facilities, equipment, technical capacities, human resources | 18000 | 3000 |  |  |  | Activity 1.1.2.5 Assign roles and responsibilities to the agencies and organisations forming a task team to regularly complement and improve the database and risk maps and also to monitor and report on the new updates | 0 | 5000 | On-going and will be completed by September 2021 |  |  |  | Activity 1.1.2.5 Assign roles and responsibilities to the agencies and organisations forming a task team to regularly complement and improve the database and risk maps and also to monitor and report on the new updates | 0 | 5000 | On-going and will be completed by January 2023
|  | A 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 55000 | 0 | On-going and will continue for the next three years of the project duration. Development of the VOLTALRAM and integration of existing information is on-going.Check below VOLTALRM EWS website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta |  | 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | Activity 1.1.3.1 Organize training workshop for local professionals (hydrologists, disaster managers, GIS experts etc.) to convey knowledge and improve skills needed for using risk maps | 0 | 100000 | On-going and will be completed by end of September 2021 The National training workshops will be organized during September 2021 |  |  | 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | Activity 1.1.3.1 Organize training workshop for local professionals (hydrologists, disaster managers, GIS experts etc.) to convey knowledge and improve skills needed for using risk maps | 97488 | 0 | Completed. Workshop reports are available here https://www.floodmanagement.info/volta-basin/deliverables/
|  | A 2.1.2.5-Run and maintain the VoltAlarm system | 10000 | 0 |  |  |  | Activity 1.1.3.2 Organize joint workshops for stakeholders to deliver knowledge on VCERs and Floods and Drought risk maps of Volta Basin and to gather feedbacks and suggestions for improvement | 0 | 0 | On-going and will be completed by December 2022 |  |  |  | Activity 1.1.3.2 Organize joint workshops for stakeholders to deliver knowledge on VCERs and Floods and Drought risk maps of Volta Basin and to gather feedbacks and suggestions for improvement | 41150 | 0 | On-going and will be completed by December 2022
| 2.3.2 | 2.3.2.1-Finalization of the Training Manual for Mainstreaming Gender in the E2E-EWS-FF & IFM | 0 | 14500 |  |  |  | Activity 1.1.3.3 Take advantage of community meetings to raise awareness of a larger number of Floods and Drought risk maps’ beneficiaries | 0 | 0 | On-going and will be completed by December 2022 |  |  |  | Activity 1.1.3.3 Take advantage of community meetings to raise awareness of a larger number of Floods and Drought risk maps’ beneficiaries | 0 | on-going | On-going and will be completed by December 2022
|  | Total Project Implementation and Execution cost (June 2019-June 2020) | 287000 |  |  |  | Output 1.1.4: Reports and communication documents on vulnerabilities, capacities, exposure and risks (VCERs) and Floods and Drought risk maps of the Volta Basin are available | 1.1.4.1 Produce technical report on the added value, success and challenges of VCERs and Floods and Drought risk maps | 0 | 0 |  |  |  | Output 1.1.4: Reports and communication documents on vulnerabilities, capacities, exposure and risks (VCERs) and Floods and Drought risk maps of the Volta Basin are available | 1.1.4.1 Produce technical report on the added value, success and challenges of VCERs and Floods and Drought risk maps | 0 | 7000 | on-going and will be completed by December 2022
|  | TOTAL | 712878 | 209122 |  |  |  | 1.1.4.2 Develop documentation for raising public awareness (infographics, videos, mobile phone applications, educational tools for children and students, etc.) | 0 | 0 |  |  |  |  | 1.1.4.2 Develop documentation for raising public awareness (infographics, videos, mobile phone applications, educational tools for children and students, etc.) | 0 | 3000 | on-going and will be completed by December 2022
|  | Total Expenditure (PFG1+PFG2+First implementation installment) including obligations | 922000 | [5 empty] | 0 | 0 |  |  |  | Output 1.2.1: Scenarios for socio-economic and environment development along with the climate change projections are collected | 1.2.1.1 Gather all available information on climate change scenarios | 11000 | 0 | Completed Final report is available here in English https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_English.pdf and in French https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_French.pdf
|  | Total Funds unspent from the first year funds (which will be used in the second year) | 1073000 |  | Due to COVID-19 pandemic situtaion, it was not possible to implement some of the planned activities due to travel restrictions, baseline information cannot be collected as National Agencies were not allowed to work from office, vendors or suppliers are not available for procurement etc. so the funds are unspent but they will be utilized in the second year of the project along with the second year activities |  | Output 1.2.1: Scenarios for socio-economic and environment development along with the climate change projections are collected | 1.2.1.1 Gather all available information on climate change scenarios | 0 | 0 |  |  |  |  | 1.2.1.2 Gather the data on input for socio-economic scenarios of the Volta Basin region over the next decades | 8000 | 0
[8 empty] | 1.2.1.2 Gather the data on input for socio-economic scenarios of the Volta Basin region over the next decades | 0 | 0 |  |  |  |  | 1.2.1.3 Organize the data on climate and socio-economic predictions for further integration with VCERs and risk maps developed under outcome 1.1 | 11000 | 0
|  | Total amount disbursed to the other executing Partner-WMO | 623005 |  |  |  |  | 1.2.1.3 Organize the data on climate and socio-economic predictions for further integration with VCERs and risk maps developed under outcome 1.1 | 0 | 0 |  |  |  | Output 1.2.2: Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | Activity 1.2.2.1 For areas covered with hydrological and hydraulic models (White Volta, Oti for example) perform a series of runs | 11000 | 0
|  | Total amount disbursed to the other executing Partner-VBA | 110351 |  |  |  | Output 1.2.2: Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | Activity 1.2.2.1 For areas covered with hydrological and hydraulic models (White Volta, Oti for example) perform a series of runs | 0 | 0 |  |  |  |  | Activity 1.2.2.2 For areas not covered with numerical models, carry out a first qualitative assessment of the possible evolution of VCERs and risk maps under future changes | 24000 | 0
|  | Total amount disbursed to the other executing Partner-GWP-WA | 188644 |  |  |  |  | Activity 1.2.2.2 For areas not covered with numerical models, carry out a first qualitative assessment of the possible evolution of VCERs and risk maps under future changes | 0 | 0 |  |  |  |  | Activity 1.2.2.3 Draft report with the methodologies and tools used for studying the impacts of future scenarios | 4000 | 0
[8 empty] | Activity 1.2.2.3 Draft report with the methodologies and tools used for studying the impacts of future scenarios | 0 | 0 |  |  |  | 1.2.3 Impact on environmental and ecosystem services indicators is evaluated for current and future scenarios | 1.2.3.1 Define indicators related to environment and ecosystem services (wetlands) conditions | 120000 |  | Some activities are conducted virtually/face-to-face due to the covid-19 Pandemic and sub-activities related to future environmental impacts will be implemented during January 2023 Reports are available here https://www.floodmanagement.info/volta-basin/deliverables/
[7 empty] | 1.2.3 Impact on environmental and ecosystem services indicators is evaluated for current and future scenarios | 1.2.3.1 Define indicators related to environment and ecosystem services (wetlands) conditions | 110000 | 4500 | Some activities are conducted virtually/face-to-face due to the covid-19 Pandemic and sub-activities related to future environmental impacts will be implemented during November 2021 |  |  |  | 1.2.3.2 Collect and process information for various environmental indicators,
PLANNED EXPENDITURE SCHEDULE | [7 empty] | 1.2.3.2 Collect and process information for various environmental indicators, | [6 empty] | 1.2.3.3 Select thresholds and carry out analysis for current and future climate scenarios
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date | Comment/Remarks |  |  | 1.2.3.3 Select thresholds and carry out analysis for current and future climate scenarios | [6 empty] | 1.2.3.4 Identify 2 to 3 areas (Ramsar Bagré dam for example) with appropriate dataset on ecosystem services to test the methodology
|  | A1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 293300 | 2021-03-30 | Moved to second-year.Could not be implemented due to Global Covid-19 situation |  |  | 1.2.3.4 Identify 2 to 3 areas (Ramsar Bagré dam for example) with appropriate dataset on ecosystem services to test the methodology | [6 empty] | 1.2.3.5 Draft report with the methodologies and tools used for studying the impacts of environmental flow58 and experience of pilot tests.
|  | A1.1.2.4 Develop web-based flood and drought risk maps using the VCER database and existing maps developed in Ghana through the past projects funded by the World Bank and the Global Environment Facility (see part G for more information) | 139200 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation |  |  | 1.2.3.5 Draft report with the methodologies and tools used for studying the impacts of environmental flow58 and experience of pilot tests. | [6 empty] | 1.2.3.6Drafting an integrated basin-wide wetland guidelines to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) and capacity building of relevant stakeholders
|  | A1.1.2.5 Assign roles and responsibilities to the agencies and organisations to regularly complement and improve the database and risk maps | 5000 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation |  |  | 1.2.3.6Drafting an integrated basin-wide wetland guidelines to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) and capacity building of relevant stakeholders | [6 empty] | 1.2.3.7 Support for developing bankable national projects for promoting sustainable aquatic/terrestrial transition zone (ATTZ) for the depended bio-diversity
|  | Output 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | 274000 | 2021-06-01 |  |  |  | 1.2.3.7 Support for developing bankable national projects for promoting sustainable aquatic/terrestrial transition zone (ATTZ) for the depended bio-diversity | [5 empty] | 1.3.1: Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 1.3.1.1 Design and develop the guideline presenting the whole process of risk maps | 0 | 7000 | Will be completed by December 2022
|  | Output 1.1.4 Reports and communication documents on vulnerabilities, capacities,exposure and risks (VCERs) and Floods and Drought risk maps of the VoltaBasin | 10000 | 2021-06-01 |  |  | 1.3.1: Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 1.3.1.1 Design and develop the guideline presenting the whole process of risk maps | 0 | 0 |  |  |  |  | 1.3.1.2 Develop supplementary means of communication to reach a wider population (infographics, leaflets for schools, etc.) | 0 | 5000 | Will be completed by March 2023
|  | Output 1.2.1 Scenarios for socio-economic and environment development along with the climate change projections are collected | 30000 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation |  |  | 1.3.1.1 Develop supplementary means of communication to reach a wider population (infographics, leaflets for schools, etc.) | 0 | 0 |  |  |  | 1.3.2: Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 1.3.2.1 Organize trainings and workshops with stakeholders | 0 | 150000 | On-going and to be completed by January 2023
|  | Output 1.2.2 Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | 31000 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation |  |  |  | 0 | 0 |  |  |  |  | 1.3.2.2 Design capacity building courses for NMHSs improving their competencies to periodically perform scenarios and assessments | 0 | 10000 | On-going and to be completed by January 2023
|  | Output 1.3.1 Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 12000 | 2021-03-01 |  |  | 1.3.2: Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 1.3.2.1 Organize trainings and workshops with stakeholders | 0 | 0 |  |  |  |  | 1.3.2.3 Develop safeguard action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders | 0 | 10000 | On-going and to be completed by January 2023
|  | Output 1.3.2 Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 170000 | 2021-07-01 |  |  |  | 1.3.2.2 Design capacity building courses for NMHSs improving their competencies to periodically perform scenarios and assessments | 0 | 0 |  |  |  | 2.1.1 Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 2.1.1.1 Select the participants (hydrologists, meteorologists, IT and GIS experts, etc.) within the NMHSs and flood or drought related services (Defence, Agriculture, etc.) | 30000 | 0 | Preparation is on-going and baseline information collection will be carried out. The first capacity development activity is planned to start around September 2021.Planned completion by Dec-22
|  | A 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 91000 | 2021-07-31 | Ongoing activity up to end of project.Development of the VOLTALRAM and integration of existing information is on-going.Check below website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta |  |  | 1.3.2.3 Develop safeguard action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders | 0 | 0 |  |  |  |  | 2.1.1.2 Develop the curriculum on the basis of the capacity building documentation developed by GWP and WMO for their programmes on flood and drought management taking into account hydro-meteorological and socio-economic conditions of target areas | 180421 |  | Final stage . Various distance learning courses were organized. Link to courses are available are: https://www.floodmanagement.info/volta-basin/deliverables/knowledge-and-learning/ final distance learning course will be started in January 2023
|  | A 2.1.2.5-Run and maintain the VoltAlarm system | 120000 | 2021-07-01 |  |  | 2.1.2 The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | 2.1.2.1-Define the needs related to facilities, equipment, technical capacities, human resources | 18000 | 3000 | National consultations were carried out together with the activity 1.2.2 and reports are available here: |  |  |  | 2.1.1.3 Organize the training sessions at the transboundary level (with participants from each riparian country) including theoretical trainings and practical exercises |  | 71000 | Planing is on-going. Will be completed by March 2023
|  | Output 2.1.1 Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 80000 | 2021-07-31 | Preparationand baseline information collection will be carried out is on-going. Planned completion by Dec-21 |  |  | 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 55000 | 0 | On-going and will continue for the next three years of the project duration. Development of the VOLTALRAM and integration of existing information is on-going.Check below EWS website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta |  |  | 2.1.2 The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | 2.1.2.1-Define the needs related to facilities, equipment, technical capacities, human resources | 18000 | 3000 | National consultations were carried out together with the activity 1.2.2 and reports are available here: https://www.floodmanagement.info/volta-basin/deliverables/
|  | A 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | 21000 | 2021-06-01 |  |  |  | 2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm | 0 | 0 |  |  |  |  | 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 55000 | 0 | On-going and will continue for the next three years of the project duration. Development of the VOLTALRAM and integration of existing information is on-going.Check below EWS website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta
|  | A2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Web-based EWS | 61000 | 2021-07-31 |  |  |  | 2.1.2.4 Write the operational manual including procedures and responsibilities | 0 | 0 |  |  |  |  | 2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm | 0 | 0
|  | A2.1.2.4 Write the operational manual including procedures and responsibilities | 17000 | 2021-07-01 |  |  |  | 2.1.2.5-Run and maintain the VoltAlarm system | 50000 | 0 |  |  |  |  | 2.1.2.4 Write the operational manual including procedures and responsibilities | 0 | 0
|  | Output 2.1.6 The web-based Early Warning dissemination interface forVoltAlarm is designed and developed | 20000 | 2021-07-01 | Ongoing activity up to end of project. |  | Output 2.1.3 The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | Activity 2.1.3.1 Make an inventory of the gauging stations with real-time data transfer (or pseudo real-time) in the Volta Basin and prepare descriptive sheets for each station (location, equipment, data series, etc.) Activity 2.1.3.2 Perform a field/desk study to check the availability and quality of the data and information related to runoff, rainfall and other relevant meteorological and agrometeorological data Activity 2.1.3.3 Develop the database of hydro-meteorological parameters, or interconnect with existing platforms Activity 2.1.3.4 Organize training for the NMHSs staff related to data collection, calibration and maintenance of equipment following WMO standards | 0 | 0 |  |  |  |  | 2.1.2.5-Run and maintain the VoltAlarm system | 87000 | 0
|  | Output 2.2.3 Development and implementation of community-based flood and drought management | 234000 | 2021-07-30 | Planning and preparation will start before June-21 (contract for the activities will be signed and local stakeholders will implement the activities). Planned completion by June-22 |  | 2.1.4 Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | Activity 2.1.4.1 Use topographic data, VCERs database, Floods and Drought risk maps to mark out the boundaries of the basin, sub-basins, highly vulnerable areas Activity 2.1.4.2 Describe the thresholds for flood events and for drought period based on VCERs and risk maps for various risk levels (level 0: no risk, level 1: very low, level 2 : low, level 3: moderate, level 4: high) through consultations with technical services and local representatives supported by evidence-based experiences. Activity 2.1.4.3 Define the values of the thresholds for floods and for drought events for each zone or area close to a gauging station, in relationship with past events Activity 2.1.4.4 Link the environment threshold with the threshold of flood and drought | 0 | 0 |  |  |  | Output 2.1.3 The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | Activity 2.1.3.1 Make an inventory of the gauging stations with real-time data transfer (or pseudo real-time) in the Volta Basin and prepare descriptive sheets for each station (location, equipment, data series, etc.) |  | 50000 | On-going and will be completed by July 2023
|  | Output 2.3.1 Knowledge and capacity development FFG or using the IUCN -Nature-based solution and ecosystem-based approaches and standards (starting with activity 2.3.1.1.) | 122000 | 2020-07-31 | Ongoing activity up to July-20. Entinre output will be completed by Dec 22 |  | 2.1.5 The procedure for producing impact-based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | Activity 2.1.5.1 For the areas with available forecast models in the sub-basins (e.g. White Volta, Oti), create the procedure to use the outputs of the existing models within the network of centers producing VoltAlarm (NMHSs and VBA) Activity 2.1.5.2 For the areas not covered with hydrological models, develop charts and graphs (with various standard icons and images) to define the flood and drought indicators using hydro-meteorological data from past events Activity 2.1.5.3 Write the software to collect the meteorological and hydrological forecasts and to calculate the daily warning levels for each of the sub-basin and vulnerable areas Activity 2.1.5.4 Design and develop the interface to gather all individual warning levels on the main system at the VBA observatory | 0 | 0 |  |  |  |  | Activity 2.1.3.2 Perform a field/desk study to check the availability and quality of the data and information related to runoff, rainfall and other relevant meteorological and agrometeorological data |  | 100000 | On-going and will be completed by July 2023
|  | A 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2EEWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | 282000 | 2021-07-31 | Planning and preparation will start before June-21 and atleast one National workshop will be conducted before July-21 and others will be planned and carried out between July 21-Dec 21. |  | 2.1.6 The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | Activity 2.1.6.1 Organize consultations with the end-users from national and regional agencies and from communities to gather their expectations related to their future use of the prototype proposed on Figure 11 (background maps, zooms, types of graphs, location of evacuation centre, hospital, emergency centre, first-aid, etc.) Activity 2.1.6.2 Develop and test the web-based dissemination interface Activity 2.1.6.3 Write the user guide to convey all available knowledge on the interface to the various groups of users (forecasters, IT staff, decision-makers, etc.) | 0 | 0 |  |  |  |  | Activity 2.1.3.3 Develop the database of hydro-meteorological parameters, or interconnect with existing platforms |  | 42000 | On-going and will be completed by July 2023
|  | Ouput 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 64000 | 2021-06-01 | Ongoing activity up to end of project. |  | 2.1.7 Knowledge and awareness about VoltAlarm are increased within the user groups. | Activity 2.1.7.1 Carry out trainings and capacity development workshops with the NMHS professionals, local/national agencies and users of the web-based EWS Activity 2.1.7.2 Gather feedbacks, suggestions and scope for improvements from the workshop participants Activity 2.1.7.3 Organize a workshop to discuss with the trained participants how similar risk maps and early warning systems can be developed for areas outside of the Volta Basin | 0 | 0 |  |  |  |  | Activity 2.1.3.4 Organize training for the NMHSs staff related to data collection, calibration and maintenance of equipment following WMO standards | 0 | 62000 | On-going and will be completed by July 2023
|  | A3.1.3.1 Draft a report with evidence-based experiences at local level | 22500 | 2021-06-01 | Ongoing activity up to end of project. |  | 2.3.2 Capacity development based on the Training Manual for mainstreaming gender in the E2E -EWS-FF and integrated flood management | 2.3.2.1-Finalization of the Training Manual for Mainstreaming Gender in the E2E-EWS-FF & IFM | 14500 | 0 | Draft version of the training manual for mainstreaming gender is available here. https://wmoomm.sharepoint.com/:w:/s/Services/EdhLp_1pZG1LmmMaW7eGrs0BA0THwJx9JMVBuUFT8R5WlQ?e=Yy8UUb GWP-WA is now adapting the manual to the Volta Basin context and planning for the National training workshops are at the final stage with the selection of participants and workshop location |  |  | 2.1.4 Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | Activity 2.1.4.1 Use topographic data, VCERs database, Floods and Drought risk maps to mark out the boundaries of the basin, sub-basins, highly vulnerable areas | 0 | 10000
[8 empty] | 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | 0 | 210000 | Planning and preparation on-going. National training workshops are planned to be conducted during end of July 2021-September 2021 |  |  |  | Activity 2.1.4.2 Describe the thresholds for flood events and for drought period based on VCERs and risk maps for various risk levels (level 0: no risk, level 1: very low, level 2 : low, level 3: moderate, level 4: high) through consultations with technical services and local representatives supported by evidence-based experiences. | 0 | 150000
|  | Project Implementation and Execution costs (July 2020-June 2021) | 355000 |  |  |  |  | 2.3.2.3 Collect feedbacks from the workshop participants on their views and knowledge sharing on mainstreaming gender in E2E-EWS-F and IFM with other stakeholders | 0 | [5 empty] | Activity 2.1.4.3 Define the values of the thresholds for floods and for drought events for each zone or area close to a gauging station, in relationship with past events | 0 | 60000
[8 empty] | 2.3.2.4 Recommend actions that would improve the participation of women into flood management and early warning | 0 | [5 empty] | Activity 2.1.4.4 Link the environment threshold with the threshold of flood and drought | 0 | 18000
|  | TOTAL Amount to be spent between July 2020-July 2021 | 1732500 |  |  |  | 2.2.3 Development and implementation of community-based flood and drought management | 2.2.3.1 Conduct participative community consultations to identify and select the appropriate local measures or equipments | 0 | 234000 | Planning and preparation on-going. Local partners identified in each countries. Inception from end of July -21 (contract for the activities will be signed and local stakeholders will implement the activities). Planned completion by June-22 |  |  | 2.1.5 The procedure for producing impact-based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | Activity 2.1.5.1 For the areas with available forecast models in the sub-basins (e.g. White Volta, Oti), create the procedure to use the outputs of the existing models within the network of centers producing VoltAlarm (NMHSs and VBA) Activity 2.1.5.2 For the areas not covered with hydrological models, develop charts and graphs (with various standard icons and images) to define the flood and drought indicators using hydro-meteorological data from past events Activity 2.1.5.3 Write the software to collect the meteorological and hydrological forecasts and to calculate the daily warning levels for each of the sub-basin and vulnerable areas Activity 2.1.5.4 Design and develop the interface to gather all individual warning levels on the main system at the VBA observatory | 0
[8 empty] | 2.2.3.2 Develop and install the local measures as identified with the communities under activity 2.2.3.1. | 0 |  |  |  |  | 2.1.6 The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | Activity 2.1.6.1 Organize consultations with the end-users from national and regional agencies and from communities to gather their expectations related to their future use of the prototype proposed on Figure 11 (background maps, zooms, types of graphs, location of evacuation centre, hospital, emergency centre, first-aid, etc.) Activity 2.1.6.2 Develop and test the web-based dissemination interface Activity 2.1.6.3 Write the user guide to convey all available knowledge on the interface to the various groups of users (forecasters, IT staff, decision-makers, etc.) | 0
[8 empty] | 2.2.3.3 Capacity building and formation of local community flood and drought management committees | 0 |  |  |  |  | 2.1.7 Knowledge and awareness about VoltAlarm are increased within the user groups. | Activity 2.1.7.1 Carry out trainings and capacity development workshops with the NMHS professionals, local/national agencies and users of the web-based EWS Activity 2.1.7.2 Gather feedbacks, suggestions and scope for improvements from the workshop participants Activity 2.1.7.3 Organize a workshop to discuss with the trained participants how similar risk maps and early warning systems can be developed for areas outside of the Volta Basin | 0 | 0
|  | Total Funds unspent from the first year funds (which will be used in the second year) | 1073000 |  |  |  |  | 2.2.3.4 Development of community-based flood and drought management manuals including safety and safeguard measures for preservation of natural habitats, land and soil conservation, biological diversity. | 0 |  |  |  |  | 2.2.1 Pilot testing for a number of areas over the basin during the monsoon and dry seasons are performed | 2.2.1.1 Finalize the selection of the pilot tests areas with the concerned agencies and communities on the basis of the draft list | 0 | 18000 | Pilot sites identified and consultation with the National partners at the pilot location done. Reporting is on-going
[8 empty] | 2.2.3.5 Organize meetings to share knowledge and experience of added-value of local measures or equipments | 0 | [5 empty] | 2.2.1.2 Organize meetings on each of the pilot areas to assign the roles and responsibilities | 0 | 0
[7 empty] | 2.3.1 Knowledge and capacity development using the IUCN -Nature-based solution and ecosystem-based approaches and standards (starting with activity 2.3.1.1.) | 2.3.1.1 Develop the Training Curriculum of the FGG | 0 | 384000 | Ongoing activity. National workshops to start from end of August 2021. Entire output will be completed by June 22 The project partners would like to propose the use of IUCN standards for nature-based solutions instead of WWF Flood Green Guide (FGG as endorsed in the project proposal. This is inline with the initial study report and guidance document prepared together with the National stakeholders under output 1.2.3 and it is available here: https://www.floodmanagement.info/volta-basin/deliverables/ The project team is informing the Adaptation Fund Secretariat and National Designated Authorities about the modification of the activities 2.3.1.1 and 2.3.1.2 as per decision B.29/32 (OPG-ANNEX-7-Project-Programme-Implementation) of the Adaptation Fund Under the Activity 2.3.1.1, Training curriculum for IUCN standards for nature-based solutions will be developed Under Activity 2.3.1.2, short courses on IUCN standards for nature-based solutions will be delivered in each of the Volta Basin countries and feedback from the stakeholders will be collected |  |  |  | 2.2.1.3 Identify the good practices, challenges and limitations of products and services during the Flood and Drought events at each of the pilot testing locations | 0 | 0
|  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | [5 empty] | 2.3.1.2 Organize dedicated short courses (at least one per country) on the FFG approaches and concepts for targeted beneficiaries to disseminate knowledge on natural and nature-based solutions for flood management | 0 | [5 empty] | 2.2.1.4 Raise awareness about the pilot testing using multi-media channels | 0 | 0
|  | How much of the total co-financing as committed in the Project Document has actually been realized? |  | 0 |  |  |  | 2.3.1.3 Collect feedbacks from the workshop participants on their views and perception of FGG tools | 0 | [5 empty] | 2.2.1.5 Develop an action plan to further improve products and services after the pilot testing | 0 | 0
[8 empty] | 2.3.1.4 Recommend actions to increase the use of natural and nature-based solutions and environmentally friendly methodologies with the involvement of local population a | 0 |  |  |  |  | 2.2.2 Feedback from the series of pilot testing is collected | Activity 2.2.2.1 Organize national consultative workshops (participants from local/national agencies involved in Floods and Drought management) to share the knowledge (new methodologies, concepts and tools for effective forecasting and dissemination of early warnings) from the pilots tests Activity 2.2.2.2 Collect feedbacks from the workshop participants highlighting their views and perception of developed products and services Activity 2.2.2.3 Draft the series of reports on the experiences from the pilot testing and provide a summary of recommendations Activity 2.2.2.4 Develop communication materials to disseminate the results of the pilot testing and describe the added value of VoltAlarm |  | 0
|  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  | 0 | N/A. Information will be added after the Mid-term Review(MTR) or Terminal Evaluation(TE) |  |  | 2.3.1.5 Conduct workshops to provide support for developing bankable project proposals | 0 |  |  |  |  | 2.2.3 Development and implementation of community-based flood and drought management | 2.2.3.1 Conduct participative community consultations to identify and select the appropriate local measures or equipments | 207000 | 27000 | Implementation is completed in the Six countries. Reporting is on-going. Some press releases and news item are available here https://www.floodmanagement.info/community-based-flood-and-drought-management-cbfdm-activities-in-the-volta-basin-countries/
[7 empty] | 2.1.1 Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 2.1.1.1 Select the participants (hydrologists, meteorologists, IT and GIS experts, etc.) within the NMHSs and flood or drought related services (Defence, Agriculture, etc.) | 0 | 298000 | Preparation is on-going and baseline information collection will be carried out. The first capacity development activity is planned to start around September 2021.Planned completion by Dec-22 |  |  |  | 2.2.3.2 Develop and install the local measures as identified with the communities under activity 2.2.3.1.
|  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | None |  |  |  | 2.1.1.2 Develop the curriculum on the basis of the capacity building documentation developed by GWP and WMO for their programmes on flood and drought management taking into account hydro-meteorological and socio-economic conditions of target areas | [6 empty] | 2.2.3.3 Capacity building and formation of local community flood and drought management committees
[8 empty] | 2.1.1.3 Organize the training sessions at the transboundary level (with participants from each riparian country) including theoretical trainings and practical exercises | [6 empty] | 2.2.3.4 Development of community-based flood and drought management manuals including safety and safeguard measures for preservation of natural habitats, land and soil conservation, biological diversity.
[7 empty] | 2.2.1 Pilot testing for a number of areas over the basin during the monsoon and dry seasons are performed | 2.2.1.1 Finalize the selection of the pilot tests areas with the concerned agencies and communities on the basis of the draft list | 0 | 18000 | Pilot sites identified and consultation with the National partners to start soon. |  |  |  | 2.2.3.5 Organize meetings to share knowledge and experience of added-value of local measures or equipments
[8 empty] | 2.2.1.2 Organize meetings on each of the pilot areas to assign the roles and responsibilities | 0 | 0 |  |  |  | 2.3.2 Capacity development based on the Training Manual for mainstreaming gender in the E2E -EWS-FF and integrated flood management | 2.3.2.1-Finalization of the Training Manual for Mainstreaming Gender in the E2E-EWS-FF & IFM | 14500 | 0 | Draft version of the training manual for mainstreaming gender is available here. https://wmoomm.sharepoint.com/:w:/s/Services/EdhLp_1pZG1LmmMaW7eGrs0BA0THwJx9JMVBuUFT8R5WlQ?e=Yy8UUb GWP-WA is now adapting the manual to the Volta Basin context and planning for the National training workshops are at the final stage with the selection of participants and workshop location
[8 empty] | 2.2.1.3 Identify the good practices, challenges and limitations of products and services during the Flood and Drought events at each of the pilot testing locations | 0 | 0 |  |  |  |  | 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | 225000 | 0 | National training workshops completed. Reports available here https://www.floodmanagement.info/volta-basin/deliverables/
[8 empty] | 2.2.1.4 Raise awareness about the pilot testing using multi-media channels | 0 | 0 |  |  |  |  | 2.3.2.3 Collect feedbacks from the workshop participants on their views and knowledge sharing on mainstreaming gender in E2E-EWS-F and IFM with other stakeholders
[8 empty] | 2.2.1.5 Develop an action plan to further improve products and services after the pilot testing | 0 | 0 |  |  |  |  | 2.3.2.4 Recommend actions that would improve the participation of women into flood management and early warning | 0 | 20000
[7 empty] | 2.2.2 Feedback from the series of pilot testing is collected | Activity 2.2.2.1 Organize national consultative workshops (participants from local/national agencies involved in Floods and Drought management) to share the knowledge (new methodologies, concepts and tools for effective forecasting and dissemination of early warnings) from the pilots tests Activity 2.2.2.2 Collect feedbacks from the workshop participants highlighting their views and perception of developed products and services Activity 2.2.2.3 Draft the series of reports on the experiences from the pilot testing and provide a summary of recommendations Activity 2.2.2.4 Develop communication materials to disseminate the results of the pilot testing and describe the added value of VoltAlarm | [5 empty] | 2.3.1 Knowledge and capacity development using the IUCN -Nature-based solution and ecosystem-based approaches and standards (starting with activity 2.3.1.1.) | 2.3.1.1 Develop the Training Curriculum of the FGG | 325000 | 55000 | Completed with final report from the EE is pending . Reports are available here https://www.floodmanagement.info/volta-basin/deliverables/
[7 empty] | Output 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 3.1.1.1 Conduct a desk study, and hold meetings with partners, to identify the status of climate and future socio-economic changes in the transboundary governance plans, policies and guidelines for flood and drought management | 0 | 114400 | Desk studies initiated and consultations with the National stakeholders to start soon. |  |  |  | 2.3.1.2 Organize dedicated short courses (at least one per country) on the FFG approaches and concepts for targeted beneficiaries to disseminate knowledge on natural and nature-based solutions for flood management
[8 empty] | 3.1.1.2 Develop a short report underlining the strengths together with the identified gaps and additional needs related to climate and development impacts | 0 | [5 empty] | 2.3.1.3 Collect feedbacks from the workshop participants on their views and perception of FGG tools
[8 empty] | 3.1.1.3 Propose long-term actions for strengthening resilience and capacities at transboundary level to be implemented by VBA and the other regional agencies | 0 | [5 empty] | 2.3.1.4 Recommend actions to increase the use of natural and nature-based solutions and environmentally friendly methodologies with the involvement of local population a
[7 empty] | Output 3.1.2 Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 3.1.2.1 Describe the network of the relevant policy-makers responsible for floods and drought management as well as other related fields | 0 | 0 |  |  |  |  | 2.3.1.5 Conduct workshops to provide support for developing bankable project proposals
[8 empty] | 3.1.2.2 Organize and conduct national workshops to identify the gaps and needs in policies and plans with special attention on safeguard actions for minimizing Version 2: September 03, 2018 48 direct and indirect risks arising from the project activities , and to highlight the key long-term strategies for floods and drought management | 0 | 0 |  |  |  | Output 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 3.1.1.1 Conduct a desk study, and hold meetings with partners, to identify the status of climate and future socio-economic changes in the transboundary governance plans, policies and guidelines for flood and drought management | 44000 | 0 | Desk studies initiated and consultations with the Regional and national stakeholders were completed. National level workshops pending
[8 empty] | 3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies | 0 | 0 |  |  |  |  | 3.1.1.2 Develop a short report underlining the strengths together with the identified gaps and additional needs related to climate and development impacts | 22000
[8 empty] | 3.1.2.4 Present the recommendations to the policy-makers and ministries | 0 | 0 |  |  |  |  | 3.1.1.3 Propose long-term actions for strengthening resilience and capacities at transboundary level to be implemented by VBA and the other regional agencies | 48000
[7 empty] | Output 3.1.3 Experiences of local communities on key long-term strategies for floods and drought management are collected | Activity 3.1.3.1 Draft a report with evidence-based experiences at local level Activity 3.1.3.2 Organize and conduct local workshops to get a wider input of communities on possible solutions and arrangements for improving socio-economic development. Activity 3.1.3.3 Collect feedbacks and recommendation at local level and provide input on the needs for relationships to national policies | 0 | 0 |  |  |  | Output 3.1.2 Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 3.1.2.1 Describe the network of the relevant policy-makers responsible for floods and drought management as well as other related fields | 0 | 0
[7 empty] | Output 3.2.1 Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines | Activity 3.2.1.1 Organize and conduct workshops to disseminate the revised, or new, plans, policies and guidelines on climate adaptation measures in the Volta Basin. Activity 3.2.1.2 Collect feedbacks, suggestions and recommendations from the workshop participants on the links between activities of National Programmes and the Volta basin project Activity 3.2.1.3 Identify roles and responsibilities of the individual organizations and define the coordination mechanism to improve the implementation of the climate change adaptation measures | 0 | 0 |  |  |  |  | 3.1.2.2 Organize and conduct national workshops to identify the gaps and needs in policies and plans with special attention on safeguard actions for minimizing Version 2: September 03, 2018 48 direct and indirect risks arising from the project activities , and to highlight the key long-term strategies for floods and drought management | 0 | 0
[7 empty] | Output 3.2.2 Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | Activity 3.2.2.1 Launch national consultations in the six countries to gather feedback on the effective coordination between national and transboundary policies in the framework of floods and drought management and climate adaptation Activity 3.2.2.2 Draft a report with recommendations from the consultations Activity 3.2.2.3 Organize the dissemination of the report to policy-makers | 0 | 0 |  |  |  |  | 3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies | 0 | 0
[7 empty] | Output 3.3.1 Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | Activity 3.3.1.1 Conduct a desk study and consultation of local stakeholders to gather examples of best practices for flood and drought risk reduction and climate adaptation related measures Activity 3.3.1.2 Develop capacity building documentation for local communities with the help of the local stakeholders Activity 3.3.1.3 Draft report on recommendations from local communities | 0 | 0 |  |  |  |  | 3.1.2.4 Present the recommendations to the policy-makers and ministries | 0 | 0
[7 empty] | Output 3.3.2 Collaboration with local communities and organizations in finalizing policies and procedures to manage risks and to adapt to climate change | Activity 3.3.2.1 Prepare a framework of safeguard actions for community involvement on long term disaster risk reduction with local stakeholders Activity 3.3.2.2 Conduct community-based workshops with agencies, local communities and organizations to prioritize adaptation measures Activity 3.3.2.3 Collect feedbacks, suggestions and recommendations Activity 3.3.2.4 Propose action plans at local and national levels to increase local participation | 0 | 0 |  |  |  | Output 3.1.3 Experiences of local communities on key long-term strategies for floods and drought management are collected | Activity 3.1.3.1 Draft a report with evidence-based experiences at local level Activity 3.1.3.2 Organize and conduct local workshops to get a wider input of communities on possible solutions and arrangements for improving socio-economic development. Activity 3.1.3.3 Collect feedbacks and recommendation at local level and provide input on the needs for relationships to national policies | 0 | 0
[7 empty] | Project Implementing Entity Fee | WMO staff cost (Project Coordinator) -Overall coordination and management with the Adaptation Fund Secretariat - Management of project implementation with the Executing agencies and project development with the Advisory Committee | 179180 |  |  |  |  | Output 3.2.1 Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines | Activity 3.2.1.1 Organize and conduct workshops to disseminate the revised, or new, plans, policies and guidelines on climate adaptation measures in the Volta Basin. Activity 3.2.1.2 Collect feedbacks, suggestions and recommendations from the workshop participants on the links between activities of National Programmes and the Volta basin project Activity 3.2.1.3 Identify roles and responsibilities of the individual organizations and define the coordination mechanism to improve the implementation of the climate change adaptation measures | 0 | 0
[8 empty] | Financial management including accounting and grant management to the EE and project partners | 0 | 0 | Will be provided at the end of the project |  |  | Output 3.2.2 Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | Activity 3.2.2.1 Launch national consultations in the six countries to gather feedback on the effective coordination between national and transboundary policies in the framework of floods and drought management and climate adaptation Activity 3.2.2.2 Draft a report with recommendations from the consultations Activity 3.2.2.3 Organize the dissemination of the report to policy-makers | 0 | 0
[8 empty] | WMO staff and partners travels including Project Technical Advisory Committee - meeting participation |  | 0 | Travel of WMO project manager and partners possibly from September 2021 |  |  | Output 3.3.1 Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | Activity 3.3.1.1 Conduct a desk study and consultation of local stakeholders to gather examples of best practices for flood and drought risk reduction and climate adaptation related measures Activity 3.3.1.2 Develop capacity building documentation for local communities with the help of the local stakeholders Activity 3.3.1.3 Draft report on recommendations from local communities | 0 | 0
[8 empty] | VFDM Project Monitoring and Evaluation | 9947 |  | Travel of WMO project manager and partners will be possible from September 2021 |  |  | Output 3.3.2 Collaboration with local communities and organizations in finalizing policies and procedures to manage risks and to adapt to climate change | Activity 3.3.2.1 Prepare a framework of safeguard actions for community involvement on long term disaster risk reduction with local stakeholders Activity 3.3.2.2 Conduct community-based workshops with agencies, local communities and organizations to prioritize adaptation measures Activity 3.3.2.3 Collect feedbacks, suggestions and recommendations Activity 3.3.2.4 Propose action plans at local and national levels to increase local participation | 0 | 0
[8 empty] | Quality assurance including internal and external audits | 0 |  | Will be provided at the end of the project |  |  | Project Implementing Entity Fee | WMO staff cost (Project Coordinator) -Overall coordination and management with the Adaptation Fund Secretariat - Management of project implementation with the Executing agencies and project development with the Advisory Committee | 330000
[8 empty] | Information and communication management | 8040 | [5 empty] | Financial management including accounting and grant management to the EE and project partners | 0 | 0 | Will be provided at the end of the project with the the completion financial report
[7 empty] | Project Executing Entities Fee | Project personnel WMO | 179179 | [5 empty] | WMO staff and partners travels including Project Technical Advisory Committee - meeting participation | 21482
[8 empty] | Project personnel VBA | 96000 | [5 empty] | VFDM Project Monitoring and Evaluation | 42000
[8 empty] | Project personnel GWP-WA | 70000 | [5 empty] | Quality assurance including internal and external audits | 0 |  | Will be provided at the end of the project with the the completion financial report
[8 empty] | GWP-WA and VBA administration cost | 15000 | [5 empty] | Information and communication management | 11704
[8 empty] | GWP-WA and VBA communication cost | 10000 |  |  |  |  | Project Executing Entities Fee | Project personnel WMO | 330000
[8 empty] | VFDM project Inception workshop | 59393 | [5 empty] | Project personnel VBA | 96000
[8 empty] | Project Technical Advisory Committee - virtual meeting | 1476 | 35000 | Yearly PTAC meeting planned to present the project progress and work plan for the next year The first PTAC meeting was held on 27th July 2021 and the second year PPR-II report was presented and discussed with the PTAC Members and partners. The meeting report is available below. https://www.floodmanagement.info/volta-basin/project-advisory-committee/ |  |  |  | Project personnel GWP-WA | 96000
[7 empty] | Total Project Implementation and Execution cost (June 2019-June 2021) | 628215 | [6 empty] | GWP-WA and VBA administration cost | 22500
[8 empty] | TOTAL | 1341715 | 1507100 |  |  |  |  | GWP-WA and VBA communication cost | 15000
[8 empty] | Total Expenditure (First and second implementation installment) including obligations | 2848815 | [5 empty] | VFDM project Inception workshop | 59393
[8 empty] | Total Funds unspent from the first and second year funds | 1437585 |  | Due to the COVID-19 pandemic situtaion, it was not possible to implement some of the planned activities due to travel restrictions, baseline information were not available from the National Agencies (not allowed to work from office) or there were less engagement from their side due to their day-to-day work responsibilities, difficulties in identifying vendors or suppliers for procurement or unavailability of consultants or experts for activities etc. Below are some other points for consideration: 1) The second year work plan was prepared in September 2020. However negotiation with other executing partners (identifying roles and responsibilities and signing of agreement for project activities implementation) took more time than expected. Presently, the agreement between the partners are in place and implementation is on-going in joint consultation and engagement of the National stakeholders. 2) Starting from March 2020, most of the planned activities at the local, National and Regional level could not be timely implemented (or were implemented later through virtual training or consultations) due to the covid-19 pandemic situation (travel restriction to the project countries and within cities, restriction of having more than 20 people at the same place, availability of data and information from the National agencies as most of them were working from home). During this period, the Project Management Team (PMT) continued to do preparation and implementation design of several activities with the National stakeholders (having virtual discussions and email exchanges) to collect baseline information as well as defining roles and responsibilities. During mid-September 2020, National workshops were organized to discuss the project consultation report with action plan, challenges, identify roles and responsibilities as well as roadmap for the implementation in the subsequent years. 3) The project activities needs to be implemented step-by-step meaning many activities are linked with each other or once we complete one activity then only we can implement the next sub-activity/activity. The PMT is presently identify activities of the project which could be simultaneously executed (atleast the preparation and planning could be initiated in advance). This will help to implement delayed activities and deliver planned outputs/outcome on time. So some of the funds are unspent but they will be utilized in the third year of the project along with the implementation of the third year activities | The PMT will ensure activities are implemented parallelly in the project countries with the support of the National and local stakeholders (communities) ensuring proper engagement of the stakeholders as well as linkages with the completed, on-going or upcoming activities . |  |  | Project Technical Advisory Committee - virtual and face to face meeting | 18976 | 17500 | Yearly PTAC meeting planned to present the project progress and work plan for the next year The first PTAC meeting was held on 27th July 2021 and the second year PPR-II report was presented and discussed with the PTAC Members and partners, second PTAC was held face to face on 6 May 2022 and third PTAC meeting is planned during early December 2022. The meeting reports are available below. https://www.floodmanagement.info/volta-basin/project-advisory-committee/
[14 empty] | Currency exchange loss | Due to funds transfer to the EEs and Technical partners from WMO or fluctuation in currency, there are loss of funds from the transfered project value | 55000
[8 empty] | Total amount disbursed to the other executing Partner-WMO | 1076120 |  |  |  |  | Total Project Implementation and Execution cost (June 2019-June 2021) | 1043055
[8 empty] | Total amount disbursed or with obligation to the other executing Partner-VBA | 753601 | [5 empty] | TOTAL | 3154032 | 1000400
[8 empty] | Total amount disbursed to the other executing Partner-GWP-WA | 1019094 | [5 empty] | Total Expenditure (First, second and third implementation installments) including obligations | 4154432
[15 empty] | Total Funds unspent from the first, second and third year funds | 2967568 |  | Due to the COVID-19 pandemic situtaion until February 2022, it was not possible to implement some of the planned activities due to travel restrictions, baseline information were not available from the National Agencies (not allowed to work from office) or there were less engagement from their side due to their day-to-day work responsibilities, difficulties in identifying vendors or suppliers for procurement or unavailability of consultants or experts for activities etc. So some of the funds are unspent but they will be utilized in the fourth year of the project along with the implementation of the third year activities WMO in joint agremeent of other Executing entities (VBA and GWP-WA) , also recommended by the Independent consultant(conducted the mid-term evaluation) are requesting for a one-year no cost extensionof the VFDM project in order to implement the pending activities at the regional, national and local levels. The extension is requested from 25 June 2023 until 25 June 2024 | The PMT will ensure activities are implemented parallelly in the project countries with the support of the National and local stakeholders (communities) ensuring proper engagement of the stakeholders as well as linkages with the completed, on-going or upcoming activities .
[6 empty] | PLANNED EXPENDITURE SCHEDULE | [8 empty] | Total amount disbursed to the other executing Partner-WMO | 2119487
[6 empty] | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date | Comment/Remarks |  |  |  | Total amount disbursed or with obligation to the other executing Partner-VBA | 1015851
[8 empty] | A1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 283300 | 2021-12-30 | Moved to third-year.Could not be implemented as 1.2.2.2 was delayed due to the Global Covid-19 situation. | Budget already available |  |  | Total amount disbursed to the other executing Partner-GWP-WA | 1019094
[8 empty] | Output 1.1.4 Reports and communication documents on vulnerabilities, capacities,exposure and risks (VCERs) and Floods and Drought risk maps of the VoltaBasin | 10000 | 2021-12-01 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available
[8 empty] | Output 1.2.1 Scenarios for socio-economic and environment development along with the climate change projections are collected | 30000 | 2021-12-01 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available
[8 empty] | Output 1.2.2 Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | 31000 | 2021-12-01 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available | PLANNED EXPENDITURE SCHEDULE
[8 empty] | Output 1.3.1 Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 12000 | 2021-12-01 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date | Comment/Remarks
[8 empty] | Output 1.3.2 Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 170000 | 2021-12-31 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available |  |  | A1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 183300 | 2023-06-30 | Moved to fourth-year.Could not be implemented as 1.2.2.2 was delayed due to the Global Covid-19 situation. | Budget already available
[8 empty] | A 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 91000 | 2023-06-30 | Ongoing activity up to end of project.Development of the VOLTALRAM and integration of existing information is on-going.Check below website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta | Budget already available |  |  | A 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 91000 | 2023-06-30 | Ongoing activity up to end of project.Development of the VOLTALRAM and integration of existing information is on-going.Check below website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta | Budget already available
[8 empty] | A 2.1.2.5-Run and maintain the VoltAlarm system | 120000 | 2023-06-30 |  |  |  |  | A 2.1.2.5-Run and maintain the VoltAlarm system | 120000 | 2023-06-30
[8 empty] | A 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | 21000 | 2021-12-01 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available |  |  | A 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | 21000 | 2023-06-01 | Moved to fourth-year.Could not be implemented due to the Global Covid-19 situation | Budget already available
[8 empty] | A2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Web-based EWS | 61000 | 2021-12-31 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available |  |  | A2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Web-based EWS | 61000 | 2023-07-31 | Moved to fourth-year.Could not be implemented due to the Global Covid-19 situation | Budget already available
[8 empty] | A2.1.2.4 Write the operational manual including procedures and responsibilities | 17000 | 2021-12-01 | Moved to third-year.Could not be implemented due to the Global Covid-19 situation | Budget already available |  |  | A2.1.2.4 Write the operational manual including procedures and responsibilities | 17000 | 2023-06-01 | Moved to fourth-year.Could not be implemented due to the Global Covid-19 situation | Budget already available
[8 empty] | Output 2.1.6 The web-based Early Warning dissemination interface forVoltAlarm is designed and developed | 50000 | 2021-12-01 | Ongoing activity and regional workshop will be organized during December 2021 | Budget already available |  |  | Output 2.1.6 The web-based Early Warning dissemination interface forVoltAlarm is designed and developed | 50000 | 2023-12-01 | regional workshop will be organized during December 2022 | Budget already available
[8 empty] | Activity 2.3.2.3 Collect feedbacks from the workshop participants on their views and knowledge sharing on mainstreaming gender in E2E-EWS-F and IFM with other stakeholders | 0 | 2021-11-30 | Planned with the activity 2.3.2.2 (National Traning workshops) and will be completed before end of October 2021 | Budget already available |  |  | A 2.2.1.2 Organize meetings on each of the pilot areas to assign the roles and responsibilities of the different groups of stakeholders during the tests and present the coordination and collaboration mechanism enabling first responders to receive and use efficiently the early warning information | 149485 | 2022-05-01 | Activity to start during May 2022 | Budget already available
[8 empty] | Activity 2.3.2.4 Recommend actions that would improve the participation of women into flood management and early warning | 25000 | 2021-10-31 |  |  |  |  | Output 3.1.2 Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 203500 | 2023-12-01 | Activity to start during May-June 2022 | Budget already available
[8 empty] | Ouput 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 64000 | 2023-06-01 | Ongoing activity up to end of project. | Budget already available |  |  | A3.1.3.1 Draft a report with evidence-based experiences at local level | 22500 | 2023-03-01 | Ongoing activity up to end of project. | Budget already available
[8 empty] | A3.1.3.1 Draft a report with evidence-based experiences at local level | 22500 | 2022-03-01 | Ongoing activity up to end of project. | Budget already available |  |  | A 3.1.3.2 Organize and conduct local workshops to get a wider input of communities on possible solutions and arrangements for improving socio-economic development. | 76800 | 2023-12-01 | Ongoing activity up to end of project. | Budget already available
[8 empty] | A 3.1.3.2 Organize and conduct local workshops to get a wider input of communities on possible solutions and arrangements for improving socio-economic development. | 76800 | 2022-04-01 | Ongoing activity up to end of project. | Budget already available |  |  | 2.3.2.1-Finalization of the Training Manual for Mainstreaming Gender in the E2E-EWS-FF & IFM | 15000 | 2023-12-01 |  | Budget already available Draft version of the training manual for mainstreaming gender is available here. https://wmoomm.sharepoint.com/:w:/s/Services/EdhLp_1pZG1LmmMaW7eGrs0BA0THwJx9JMVBuUFT8R5WlQ?e=Yy8UUb GWP-WA is now adapting the manual to the Volta Basin context and planning for the National training workshops are at the final stage with the selection of participants and workshop location
[8 empty] | Output 3.1.2 Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 203500 | 2022-06-01 | Activity to start during May-June 2022 | Budget already available |  |  | 2.1.5 The procedure for producing impact-based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | 140000 | 2023-12-01 | Development of the VOLTALARM EWS | Budget already available
[8 empty] | A 2.2.1.2 Organize meetings on each of the pilot areas to assign the roles and responsibilities of the different groups of stakeholders during the tests and present the coordination and collaboration mechanism enabling first responders to receive and use efficiently the early warning information | 149485 | 2022-05-01 | Activity to start during May 2022 | Budget already available |  |  | 2.1.6 The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | 140050 | 2023-12-01 | Finalization of the VOLTALARM EWS with the Bulletin | Budget already available
[15 empty] | Output 2.1.7 Knowledge and awareness about VoltAlarm are increased within the user groups. | 65500 | 2023-12-01 | Capacity development workshop until 2024 | Budget already available
[8 empty] | TOTAL Amount to be spent between July 2021-July 2022 | 1437585 | [5 empty] | Output 2.2.1 Pilot testing for a number of areas over the basin during the monsoon and dry seasons are performed | 1182000 | 2024-06-01 | Capacity development session until 2024 | Budget already available
[8 empty] | Planned Implementing fee for the period July 2021-June 2022 | 167500 |  | VFDM project manager staff costs, IE staff cost, communication costs, M&E, Internal Audit and financial management |  |  |  | Output 2.2.2 Feedback from the series of pilot testing is collected | 212000 | 2024-06-01 | Capacity development session until 2024 | Budget already available
[8 empty] | Planned Execution fee for the period July 2021-June 2022 | 187500 |  | VBA and GWP-WA staff costs, administration and communication fee |  |  |  | Output 3.2.1 Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines | 50000 | 2024-06-01 | Capacity development session until 2024 | Budget already available
[8 empty] | Total Project Implementation and Execution costs (July 2021-June 2022) | 355000 |  | The third tranche inludes implementing and executing fees which are necessary for the project management and coordination (mainly it includes the salary of the three project staffs, as well as for travels to the regional and national level activities, communication, monitoring and evaluation etc.) Requesting the project Implementation and Execution costs for the period July 2021-June 2022 from the Adaptation Fund Secretariat/Board in order to continue the contract of VFDM project management team. | Budget required from the Adaptation Fund for the period July 2021- June 2022 |  |  | Output 3.2.2 Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | 190000 | 2024-06-01 | Capacity development session until 2024 | Budget already available
[15 empty] | TOTAL Amount to be spent between July 2022-July 2023 | 2990135
[15 empty] | Planned Implementing fee for the period July 2022-June 2023 | 167500 |  | VFDM project manager staff costs, IE staff cost, communication costs, M&E, Internal Audit and financial management
[15 empty] | Planned Execution fee for the period July 2022-June 2023 | 187500 |  | VBA and GWP-WA staff costs, administration and communication fee
[15 empty] | Total Project Implementation and Execution costs (July 2021-June 2022) | 355000 |  | The third tranche inludes implementing and executing fees which are necessary for the project management and coordination (mainly it includes the salary of the three project staffs, as well as for travels to the regional and national level activities, communication, monitoring and evaluation etc.) Requesting the project Implementation and Execution costs for the period July 2021-June 2022 from the Adaptation Fund Secretariat/Board in order to continue the contract of VFDM project management team. | Budget required from the Adaptation Fund for the period July 2022- June 2023
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[15 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  | 0
[15 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  | 0 | Government of Burkina faso has requested WMO to support them in the implementation of national hydro-met project funded by World Bank. They will build synergies with the on-going implementation of the Volta Basin project. Discussion are on-going with the government of Burkina Faso
[15 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | National agencies of the Six countries, WMO, VBA and GWP-WA have provided in-kind staff contribution to implement several activities of the VFDM project
Note on E31: Ramesh TRIPATHI: WMO PM-167500 VBA+GWP-WA-95500 WMO Staff and partners travel-15000 Communication-7000 M&E-2000
Note on E37: Ramesh TRIPATHI: Implementing Arrangement-54250 LoA-56101
Note on E38: Ramesh TRIPATHI: Implementing Arrangement-41250 LoA-146394
Note on P117: Ramesh TRIPATHI: Implementing Arrangement-54250 +54250 LoA-56101 LoA new - 589000
Note on P118: Ramesh TRIPATHI: Implementing Arrangement-41250 + 41250 LoA-146394 new LoA- 790200
Note on AA122: Ramesh TRIPATHI: Implementing Arrangement-54250 +54250 +54250 LoA-56101 LoA new - 589000 + amendment 208,000
Note on AA123: Ramesh TRIPATHI: Implementing Arrangement-41250 + 41250 LoA-146394 new LoA- 790200

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Acceptance of the project activities Even though detailed needs assessments have been conducted since 2013, the support of the stakeholders to the proposed activities can differ in the six countries. This results in differential levels of acceptance and slows down of the inception phase of the project. | Low | During the third year implementation phase of the project, all relevant stakeholders (government, agencies, departments and communities) were/are clearly identified, so that they fully share the vision and goal of the project activities and are aware of their contribution to the project, hence fostering ownership over the process. - MoU and agreement will be signed with the participating stakeholders. - Roles and responsibilities of the national working group are defined in the initial stages of the project so that all the activities are completed in a coordinated way. From the inception phase, the project team is involving all the stakeholders at the Local, National and Regional level for their participation and engagement in the project activities. Also, regional workshops or meetings is providing participants to share their experiences and learn from each other.
Technical/quality risks Component 1 and 2 of the project is too technical and not adapted to specific area or countries. This results in low commitment and interest from stakeholders | Low | The third year project activities (through ToR and concept note) were shared and reviewed with the support of National Focal Points, local decision-makers and participants from community to understand the expectations and suggestions from the participants. The feedbacks and suggestions from the participants will be integrated. From the Inception phase, the project team is ensuring to collect sggestions and feedback from local , National and Regional stakeholders on all the activities and associated reports. The concept note and Terms of Reference are shared in advance to ensure the implementation of activities is accepted by their services and they provide active participation during implementation.
Financial/resources risks ▪ Inadequacy of the financial management system: procurement system, financial availability, monitoring, reporting and auditing system, etc. ▪ Availability of project resources ▪ This will result in slowing down the project activities | Low | During the third year implementation, project and financial monitoring/reviews are conducted to ensure efficient management of project resources. From the Inception phase, the yearly workplan with Budget allocation is shared with the executing partners to ensure adequate financial management as well as timely availability of funds for implementing the activities. Funds are tansfered only after having an legal agreement with the local, National, Regional or External technical Implementing partner. The procurement process is in place and used for any procurements of equipments or resources.
Physical risks Administrative barriers hinder sharing of hydro-meteo, social and topographic data. This will result in difficulties to implement activities and delivery of timely outcome | Low | During the third year of the implementation, the executing and implementing entities requested National Focal Points and National Implementation Structures that the required data and information are shared. Furthermore, VBA is mandated for regional exchange of information and can request the enforcement of the agreements. From the Inception phase, several discussions are carried out with the National stakeholders for data sharing for the development of the products and tools under the project. Letters are shared with them to ensure administrator approvals are provided and also provide assurance of use of data and tool only for the scope of the project activities.
Restructuring in the government work structure may cause possible shifts of responsible persons at local and national levels to a different location or agency. This can result in delays and loss of support. | Low | During the third year of the implementation, few national focal points were transfered to other agencies, alternative persons from the departments were involved in most of the activities so that implementation of project activities will not be hampered at any time. From the Inception phase, multiple staffs are involved in the implementation of activities which will allow us to work continously in the countries with the active involvement and engagement of stakeholders.
Human resources/capacity risks ▪ Lack of skills or human resources availability ▪ Adequacy between existing and required experience and skills This results in slowing down the project activities | Low | During the third year, - National support was obtained at the level of the governmental agencies to ensure sufficient human resources are provided for the project activities at both national and local levels From the Inception phase, several activities of the project is involving National and local agencies staff and they are trained with the concept and methodologies so that they provide support to the tasks of the activities. This will ensure long-term sustainability of developed products, tools or processes.
Gender neutral approach Techniques and technology developed are not accepted by all groups of the communities. This decreases the gender equality compliances | Low | During the third year, the VFDM project includes gender sensitive approach in all the activities.As the project activities mainly deals with the national hydrological and meteorological services, disaster management, environmental, geographic institute etc (having or required technical expertise), it is observed that the proportion of male and female staffs in these agencies are not in equal parity both at the national and local levels. In the implemenation of various activities related to the development of the EWS, requests are made to have equal participation of male and female participants in trainings and workshop, however due to limited staff it is not possible to involve or have equal number of men and women in each activities. Wherever possible, women participants were given preference over men considering having the same technical competence required for the implementation or conducting of the activities. Project has trained several women participants (risk maps development, Nature-based solutions, EWS) and they have been requested to dissiminate knowedge to other new young professionals if they join in their national or local agencies in future.Also in future, training of the VoltAlarm will be organized dedicated to women participants from the national agencies. Also, during the gender mainstreaming capacity dveelopment training activities, women participants were involved together with men, and it was suggested to carry out several outreach and career events at the high school or universities in the Volta Basin to ensure students take career in the field of hydrology, meteorologiy and disaster management. Wherever required non-technological or traditional methods were adopted to reach and get participation from every group of the communities. From the Inception phase, gender inclusive appraoch is implemented in all the activities at the local levels. Women leaders or representatives of communities are always encouraged and preferred for the participation and support to the project activities.
Political risks Interference from the local/national political parties This will result in delaying the project activities | Medium | The project is adhering to the goals, laws, and policies of the respective project countries. Whenever and wherever required, permission of national consensus of the countries will be shown. From the Inception phase, the Executing partners are taking prior permissions from the relevant Ministers and also inviting them to attend the workshops or meetings for checking the progress and benefits provided at the National, local and regional levels.
Documentation/Reporting risks ▪ Lack of available tools and templates for developing reports and progress report ▪ Delays of reporting by the partners ▪ This results in delays in the reporting process and financial access to funding | Low | Appropriate tools/templates and reporting structures and procedures were put in place by WMO to ensure proper documentation and reporting so that donor agencies and steering committee receive timely reports. From the Inception phase, reporting tools and templates are made available to the partners and the National structures. Project communication plan is developed and shared with the executing partners so as to ensure usage of tools and dissemination information are carrried out
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The outbreak of covid-19 pandemic (at national, regional and Global) or political crisis which can cause travel restrictions for the project partners and stakeholders | Major | As there was no travel possible to the Countries in 2020 and 2021, the meetings were held virtually through Zoom, Teams or telephone and discussion documents are shared via emails. As a measure, National agencies professions or consultants were hired and trained so as to provide technical support in the implementation. Whatsapp groups are created so as to share project information directly with the National stakeholders or to receive information from them
On-going Civil war/civil security risks in Mali (https://wmoomm.sharepoint.com/:b:/s/Services/ERuhyRnAiWNDgtKIwSG7riwBUrqOjCYGd4PXV_HfPxrmig?e=sh1AIL) and also in the parts of Burkina Faso (https://wmoomm.sharepoint.com/:b:/s/Services/EdU2ZQRpKBFPj1ll9IXEXuEBX4jpliTF0CmpvpnqFm6JHg?e=S2kDJt), which is leading to travel restrictions for the National stakeholders for attending the regional workshop in both the countries and also for project partners to travel to the countries. | Major | Most of the National workshops to present the project acitvities or finalize the reports are carried out virtually with the project team. In case of organizing and participating to the regional workshops, the workshops are moved to other Volta Basin with minimum financial implications and ensuring right numbers of stakeholders are invited. The two project executing partners VBA and GWP-WA are based in Ouagadougou, Burkina Faso and during project design, most of the regional workshop was expected to be organized in Ouagadougou but as we need to move to other countries, the costing for additional travel of the project EEs resource persons have increased.
Volta Basin's vulnerability to natural hazards, capacity and resource limitations could constrain sustainability of the project achievements. Even if the Project succeeds in developing resilience and capacities at National level through EWS and Risk maps, it may not be enough for preparedness to the climate change events. | Critical | The Project Team is regularly informing the benefits of the project and how National investments could help in building resources and capacities at local, national and regional level. The project team is continously building synergies with the on-going initiatives and complementarities with the future projects and initiatives so that a joint effort for preparedness is developed.
VFDM Risk Matrix prepared by WMO with mitigation measures https://wmoomm.sharepoint.com/:x:/s/Services/Eee2xcKpaYNHq3Pl1CzWwBwBQIy8lser9lbpbwMy7lzHFA?e=X1fMb1
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the third year of the implementation, the Implementing Partner conducted regular risk monitoring and evaluation of the implemented activities, and the results were tracked and reported in WMO’s internal monitoring system. In addition to this, a dedicated Monitoring and Evaluation (M&E) expert was hired to prepare project risk monitoring framework. In case of delays in the implementation, or possible risk occurence, risk mitigation measures as indicated above were executed as and when needed, ensuring that the likelihood of occurrence of any risks remained the same or lower than at the time of project submission and did not affect the project implementation. The implementation of first-year, second-year and third year activities were severely impacted by the Covid-19 Pandemic situation and civil security issues in two countries of the Volta Basin. Delays are encountered to complete the agreed current activities as well as future upcoming activities (many activities are linked with each other). Contingency plan or approach were defined and adopted so as to ensure continuation in the implementation of the activities (virtual consultations with the Countries, Email communication and Whatsapp group are created for quick communication, Identification and capacity development of local staffs or partners to execute the activities and remote assistance by Implementing Partner and External consultants) . The management of risks has been facilitated through close and open lines of communications with the project stakeholders as well as with regular interaction among project partners at the regional and national level. As stated above, risk mitigation measures proved efficient so far, including those addressing the COVID-19 imposed risks, and as a result the implementation of project activities were not halted but maintained and gained momentum, especially from first half of 2022. Together with use of virtual meeting platforms, measures such as the identification and capacity building of local and national staff or consultants allowed to carry out activities as planned. During the reporting period, VFDM risk matrix was updated to identify the risks under each outcome and associated treatment measures to have better monitoring and accountability to the project partners and Adaptation Fund. No grivenances were reported during the reporting period of the project (July 2021- June 2022)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | During the third year, lack of compliance with local and national laws during the implementation of project activities. | Measure to avoid: 1) The project design and implementation is compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. 2) Management: In case of a lack of compliance, the ESP risk management plan procedure will be executed. 3) No USPs or any project activities is conducted if they do not comply with local, national and international laws. | - Activity Concept notes, Terms of References, Feedback survey, Minutes of the meetings/ reports of consultations with regional, national and local authorities will be monitored for compliance during designing and implementation phase - The adaptation action plans and investments will be reviewed to ensure adequate compliance with the laws | National and regional stakeholders sharing the information and knowledge on the laws related on ESP. The project design was made to be compliant with all relevant regional and national laws following extensive consultation or requirements formulation with national and regional stakeholders. Before the implementation of all the activities, a concept note or Terms of Reference is drafted and shared with the National and regional stakeholders for review including compliances with law. | During the implementation period of third year, activities are regularly screened for the ESP principles and are made compliant with all relevant regional and national laws following extensive awareness and consultation with the EEs, national and regional stakeholders. During the design of the each project activities both regional and national stakeholders are consulted to update data sharing protocol/laws between the six countries. | The project involves stakeholders for screening of ESP principles and inclusion of National and regional laws during the implementation of various activities in the third year. It could be possible some in-direct updated national and regional laws or guidelines are not screened (instead the older version are considered) by the experts and can lead to non-compliance. Following this, there might be possibility of risks arising on non-compliance. Howvever, no risks were reported until now. | None at the moment In case of any non- inclusion or non-adherence of regional and national laws for any activities or USPs, measures will be designed through an expert and implemented during the course of the project. If required international laws on data sharing protocol among different countries are consulted and utilized.
2 - Access and equity |  |  | Lack of access to project resources and outputs of the activities implemented. The project has capacity development activities to which only small percentage of the communities will be able to participate. | Given that the project will provide support to shared natural resources, the project team is ensuring that outputs or developments through activities do not negatively affect community rights to shared natural resources as well as ensuring equitable benefits from concrete adaptation investments and other project activities. Any activities involving shared resources was screened and conducted in the context of the relevant local or national laws and in joint consultation with the National and local stakeholders. The selection of beneficiaries or participants are made in consultation with local practices, traditions and access to social facilities. The project is ensuring that representatives of communities participating in capacity development activities will further disseminate the information to wider groups. | - Minutes of the meetings/ reports of consultations with regional, national and local authorities will be monitored for access and equity compliance during designing and implementation phase of the activities - The project activities is providing impartial and equitable access to project benefits for the stakeholders of the six countries - The community-based action plans and investments will be reviewed to ensure equal access and quity to the community individuals. | Presently, the activity design is carrying out requirements and need analysis of the communities during which access and equity riks are or will be considered at a maximum level -Disparity are identified between mens and womens on the ownership of assets for building self-help resilience | - During this reporting period, a sensitivity design of the project activities at the local, regional and national levels are conducted by the project team ensuring access and equity principles being screened thoroughly. - The project team or experts carries out consultation with both men and women, considering different social and economic status, so as to ensure the project activity delivers resources in both equity and accessibility | The project acknowledges there could be tasks or activities (skills and knowlegde) which are involving more men than women. For example: Direct access to the EWS to men via mobile phone ( as in these Volta Basin countries, mobile phones are less utilized by women) | None at the moment In case of access or equity issues, the project will ensure the ESRMP plan are activitated for immediate action. The project team will propose different solutions and joint decision-making to ensure there are no access and equity issues.
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalised and vulnerable groups from project activities. There is a risk that vulnerable and marginalized groups will have insufficient knowledge and access to technological devices such as mobile phones or lack of good cellular connectivity specially required for component 2.1 of the proposed activities. To avoid the exclusion of marginalized and vulnerable communities, local radio channels and traditional practices will be implemented to reach these groups especially women, girls, elderly, physically challenged individuals. | Avoidance, management or mitigation There is a risk that vulnerable and marginalized groups will have insufficient knowledge and access to technological devices such as mobile phones or lack of good cellular connectivity especially required for component 2.1 of the proposed activities. To avoid the exclusion of marginalized and vulnerable communities, needs and assessment for dissemination channels are identified i.e. local radio channels and traditional practices will be implemented to reach these groups especially women, girls, elderly, physically challenged individuals. Management- Ensure participation of all relevant stakeholders in project activities without social discrimination and with the aim of providing voice in decision making and gaining benefits including for women and elderly as well as marginalized groups. Avoidance: Ensure community consultation from the design and planning phase so the project activities target and support the most marginalized and vulnerable groups to become more resilient to climate change events including women, women-headed households, children and the youth. | Terms of Reference prepared for the consultations with communities and MoM with communities and local authorities | Knowledge and awareness on the gendered impacts of climate hazards and climate change is low. -Lack of tools and guidelines to integrate marginalized and vulnerable groups in the design, implementation and sustainabililty of the project activities | Concept note and ToR are developed after screening the AF ESP and Gender policy ensuring all the criteria are added in the selection of participants and beneficiaries. These concept note and ToRs are shared with the national working group designate at each countries. After review and approval, implementation of activities are carried out by the project team. Experts with experiences of working with social integration and engagement are involved in local level activities so as to ensure activity design includes marginalized and vulnerable groups. | The project team acknowledges that not all the vulnerable and marginalized groups in the Volta Basin region could be invited to various consultation meeting and also they might not have sufficient knowledge and access to technological devices such as mobile phones or lack of good cellular connectivity to access the EWS. This will result in receiving direct warning or advisory servcies from the hydro-met offices. | None at the moment In case of residual impacts, the project will consult with the marginal and vulnerable groups and also to identify traditional ways for accessing early warning for their preparedness and resilience. Also, sharing of experience and knowledge from the groups who have been participating in various capacity dveelopment workshops will be encouraged.
4 – Human rights |  |  | No further impact assessment is required. The proposed activities are or will not be against any of the established national and international human rights. Moreover, the proposed project is promoting the basic human rights of access to water, food and information. The project provides an opportunity for every individual to give their views, perceptions and needs in developing better climate change adaptation measures. | N/A | N/A | N/A | No Human rights violation was carried out during the reporting period. The project team ensures there is freedom of speech, freedom of participation etc. in the project activities | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Lack of gender equality and women’s empowerment in project implementation and outcomes. The proposed project is targeting region where men occupy the majority of the leadership positions. Women participation to disaster preparedness and decision making is often limited due to cultural and social norms. There is therefore a risk that women will not benefit equitably from the proposed adaptation measures and capacity-development interventions. | Avoidance or Mitigation: The proposed project is improving the gender equity and women empowerment through the WMO developed tool: Training Manual for mainstreaming gender in End to End Early Warning system for Floods and integrated Flood Management through a participatory design approach. This will help in increasing the participation of women, girls and other vulnerable groups in Flood and Drought management activities as well as decision making processes. Planning of the participative activities will ensure that women and representative of women associations will be sufficiently well represented Avoidance: - sex disaggregated data and gender specific tools will be made available for consultations Management: Aim for 50% participation of women in project activities Management- Provision of forming Women Self Help Group to be part of decision-making processes (under local community-based flood and drought management activities planned part of output 2.2.3) | Percentage or number of women, men, elderly or youths involved in the project activities Concept note and technical report of the activities including capacity development workshops/trainings | - Lack of knowledge and awareness on the gendered impacts of climate hazards and climate change . -lack of tool and guidelines to support the community based planning pocesses and various trainings. - Womens presence in project activities and leadership positions varies from country to country and activity to activity. | During the third reporting period - All the Activities are designed and implemented with a participatory approach including participation and engagement of women, youths etc. - Identifying actions based on the development and testing of Training Manual for mainstreaming Gender in the end to end early warning system for floods and flood management. - All workshops and training have incorporated both men and women as participants with the need for gender parity and having women in key roles and decision making processes - Seperate discussion with women and men respectively were carried out to better understand the needs and capabilities for development resilience and adaptation measures -Sex-disaggregated data collection tool for community consultation -Involvement of the National and International Gender focal points in the designing and implementation of activities | The project acknowledges there could be tasks or activities (skills and knowlegde) which requires specific technical skills, knowledge and experience which are not equally available in both men and women of the Volta Basin countries. For example: involvement in the development of risk maps.It could be possible that there are less women who have knowlegde of GIS and risk assessment than men in the Volta Basin countries | In case of residual impacts, the project will ensure that the extended participation call for women are made so that more women could join the implementation of the activities and can have opportunity to gain required knowledge and skills in developing risk maps or flood and drought management A seperate meeting or session will be organized to dissiminate knowledge and skills to women working in the local and national agencies
6 – Core labour rights |  |  | No further impact assessment is required. The project will be implemented and managed in compliance with the countries designated labour laws. No individual will be hired without pay and the payment will be according to the countries labour legislation/laws. Children’s labour are forbidden and it will not be accepted from other project partner agencies. Local communities will be involved in the adaptation measures but will not be exposed to any risk of accidents. Core labour rights is respected and considered in project design and implementation. | N/A | N/A | N/A | N/A During the reporting period, no labour laws were violated. All the local consultants and staffs (for data collection) hired were paid as per local standard rates. | N/A | N/A
7 – Indigenous peoples |  |  | There is a risk that the traditional use of water resources; irrigation system and land use pattern will be challenged. Therefore, a detailed analysis will be carried out by local and national agencies to understand the traditional use of natural resources especially regarding water access and land use. | Avoidance, management or mitigation The indigenous population in the region are consulted and involved during the design and implementation of the project activities. The traditional knowledge of indigenous people on Flood and Drought management are useful and considered when preparing the risk maps, the early warnings and information dissemination. | Minutes of meetings with the indigenous people -Voices from the field | - Lack of knowledge and awareness on the impacts of climate hazards and climate change on the indigenous people. -Involvement of indigenous communities in the project activities (may be due to the accessibility to the indigenous communities) | During the reporting period, -Selection of indigenous communities and individuals were carried out to develop their resilience to climate change impact -Use of local traditional practices and skills in the management of flood and drought events in order to ensure solutions and tools are tailored to the needs | N/A | N/A
8 – Involuntary resettlement |  |  | There are no activities proposed in the project which will create direct involuntary resettlement of communities. However, the risks of displacement of the population after the mapping of floods and drought risk areas could be possible as some areas could be classified as high risk for the loss of life. | A built-in safeguard approach will be defined for minimizing the negative effects of involuntary settlements. In case of involuntary resettlement, the population will be informed of their rights in a timely manner, made aware of grievance mechanism, consulted on their options and, offered technical, economically resettlement alternatives or fair and adequate compensation. The displaced population will face challenge in terms of acquiring resources for living (house, food and livelihood) and social integration with the new communities. The project will ensure that activities, especially with the local administrative services provide support in terms of strategies or actions in case of population displacement. Management: The National stakeholders will be informed of risk zones and impacted sectors (human-life, economy, environment, bio-diversity etc.) and joint consultation and discussion will be planned for managing risks and impacts. | National consultation reports, National action plan and guidelines for management of risks and impacts. | - Lack of knowledge and awareness on the risk zones and impacts of future climate hazards and climate change variability at all locations of the Volta Basin region. | During the reporting period, on the basis of evidence-based and scientific information, the National agencies are informed about the high risk zones (places where flooding or drought happened in the past years) and possible impact areas. Risk prevention and management strategies are developed jointly with the stakeholders - Capacity development of stakeholders at every stage of the activities (designing, data collection, development, finding and analysis, reporting, decision making ). | The project acknowledges there could be some in-direct impacts related to Involuntary resettlements once the risk maps is developed and shared with the National agencies. No direct risks or impacts were notified durign the reporting period | In case of any residual impacts, the project team will ensure the national agencies are informed and follow the human-right laws and ensure the people who will be moved to a new locations will have access to basic resources. The project will also propose a new prevention plan to prohibit future settlement in the high risk areas.
9 – Protection of natural habitats |  |  | There are no potential direct risks to the protection of ecosystems and its natural habitats and biological diversity through the project activities. There is a possibility of indirect risks through the revised policies and plans at national and transboundary scale decreasing the protection level of critical habitats. | Avoidance, management or mitigation: Capacity development activities with the National stakeholders will be carried out for example: Natural and nature-based solutions will be promoted using the IUCN standards for Nature-based solutions or Flood Green Guide by WWF( but they will not be implemented in the course of the Volta project as they would need detailed ecological assessment) | Technical reports, Consultation meeting notes, voices from the field | - Limited knowledge and awareness on the impacts to the habitat due to climate hazards and climate change | During the reporting period, - Capacity development of stakeholders at every stage of the activities (designing, data collection, finding and analysis, reporting, decision making ).were initiated especially during the trainings related to Nature-based solutions -Development of joint effective measures to mitigate or manage the risks (providing support of international and national experts to the National Agencies) related to protection of natural habitats Furthermore the activities under output 1.2.3 and component 2 are considering native species characteristics and critical values for defining environmental thresholds. | The project acknowledges there could be lack of integration of local environmental and ecosytem related data and information in the early warning and risk maps as these might not be available or shared by the local authorities | In case of such situation, the project team will ensure to use the global available data and will continously request the environmental agencies in the Volta Basin countries to provide local data and information Capacity building activities will be carried out on importance of sharing local and national level data and information The existing and new policies, plans and activities to protect natural habitats will be screened with the stakeholders to ensure that the critical habitats are legally protected through the convention on wetlands such as RAMSAR, Iran, 1971. and consultation with authoritative sources like IUCN, UNESCO as well as indigenous communities.
10 – Conservation of biological diversity |  | The conversation of biological diversity principle was screened during ESIA but no direct risks or impact was identified due to project activities | There will be no direct risks associated with the conservation of biological diversity as the project activities are not involving any physical action on natural resources and introduce any known invasive species. The project activities (activities under output 1.1.1, 1.2.1, 1.2.2, 1.2.3, 2.1.3, 2.1.4) is and will provide opportunities to improve the understanding of natural processes in relationship with the water cycle. Nevertheless, the project activities could trigger changes in agricultural and irrigation practices and the use of pesticides. Also, the outcomes (flood and drought risks maps, EWS information) of the project might lead to encroachment on the protected areas, buffer zones and natural habitats. | Avoidance, management or mitigation: The project activities will ensure that the principles of the Convention on Biological Diversity (CBD) which has been signed by the six countries between 2011 and 2017 are followed and supported. Furthermore, the National Biodiversity Strategy and Action Plan of the countries is providing valuable information and methodologies, opportunities to disseminate information as well as coordination at the national level and for the transboundary level. The project is promoting planning for activities of biodiversity conservation, such as reforestation, nature-based solutions through an assessment at pilot sites with the concerned national agencies. The project is developing capacity building and peer learning to strengthen the efficient management of natural resources, including aquatic species, animals and forests. -Wherever required, the project will carry out consultation and capacity development activities with the local, national and regional stakeholders so that the protected areas, buffer zones and natural habitats are preserved from encroachment | Consultation meeting reports, voices from the fields | - Lack of knowledge and awareness on the impacts to the biological diversity due to climate hazards and climate change | During the reporting period - Capacity development of stakeholders at every stage of the activities (requirement gathering, data collection, finding and analysis, designing of solutions, reporting and decision making). -Development of joint effective measures to mitigate or manage the risks (providing support of international and national experts to the National Agencies) especially through the developed ESRMP | There could be new biological sites which might not be provided by the local and national authorities and experts in the countries or are impacted by recent flood and drought events. | The project will continue have regular consultations with the National experts to ensure they provided information to the project team. No direct impacts were reported during the third year of implementation
11 – Climate change |  | The climate change principle was screened during ESIA but no impact was identified | The proposed project activities will not result in any greenhouse gas emission to the atmosphere and deforestation, so there will not be any impact to climate change. Furthermore, the project does not only increase the flood and drought adaptation capacities and resilience of the local population but also contributes to develop better governance structure, policies and plans at both national and regional level for climate change adaptation. | N/A | N/A | N/A | During the reporting period, climate change projections and impacts were identified and reported to the national stakeholders. Under Output 1.3.1, risk prevention and management strategies are defined and will be implemented. | N/A | N/A
12 – Pollution prevention and resource efficiency |  | The pollution prevention and resource efficiency principle was screened during the ESIA but no impact was identified | None of the project activities implementation are expected to result in any form of water, air and soil pollution. | N/A | N/A | N/A | No pollution generating related activities were implemeted during the repoting period | N/A | N/A
13 – Public health |  | The public health principle was screened during the ESIA but no impact was identified | The project activities should not have negative effect on public health. On the contrary, it will contribute to prevent the population from natural disasters, to improve income for getting access to health facilities, etc. Nevertheless in case of disaster, the displacements of the populations can be sources of epidemics due to the lack of hygiene (not due to project activities) The project will identify the communities at risks (that are prone to inundation) and provide awareness of best practices for health related safety during various capacity building activities.The project will regularly promote, inform and sensitize the populations on diseases related to the presence of flood water (malaria, typhoid fever, Amoebiasis, Cholera etc.); | N/A | N/A | N/A | public health related activities were improved through capacity development on first-aids measures during the repoting period | N/A | N/A
14 – Physical and cultural heritage |  | The physical and cultural heritage principle was screened during the ESIA but no impact was identified | The project does not have any activity related to affecting physical and cultural heritage. The purpose of the project is to develop better management of water resources and have traditional and cultural integration among the individuals. Participatory design and mapping approach under output 2.2.3–will involve local communities and authorities to identify areas of physical and cultural significance and ensure that community-based flood and drought management activities will not negatively impact them. | N/A | N/A | N/A | During the third year implementation, physcial and cultural heritage were requested to be identified for preservation | N/A | N/A
15 – Lands and soil conservation |  | The Lands and soil conversation principle was screened during the ESIA but no impact was identified | The project will promote the conservation of soil and land resources, especially through the selection of natural and nature-based solution with environmental-friendly solutions. Also, the project activities will contribute to improve agricultural practices and help to build the capacity of farmers and technicians. | N/A | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | During project formulation, a detailed ESIA study was carried out. For any unanticipated ESP risks, the project is continously monitoring for any risks in the implementation so that it will be mitigated at the initial stage
Have unanticipated ESP risks been identified during the reporting period? |  | None till present date In the second and subsequent year, many activities are planned at both community and national level which might lead to any unanticipated ESP risks
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | During the third reporting period, the IE has monitored the risks identified during the project design or planning stage and also informed to the other EEs as well as all National stakeholders about the ESMP availability with the project and potential risks to Environmental and Social Safeguards. Also, during any planning of new activities, the IE is informing the concerned partners about the potential risks which could arise from the implementation. The Project Management Unit (PMU) also informs the technical partners for ensuring the solution which are designed and developed do not lead to any risks or impacts to the stakeholders at the Local, National and Regional levels. In case of any possible risks, the partners are requested to immediately inform the IE focal points for necessary action. Partners are informed for reporting any grievance, issues or risks, the IE has made available the following page to the partners, users and stakeholders https://www.floodmanagement.info/volta-basin/contacts/ for reporting any grievances. Once the complaint or grievance is received, necessary actions will be handled by the project coordination and management unit, who will investigate firstly through a call or on-site visit. The IE will form a committee and may invite other relevant agencies (local/national/transboundary) to participate in the investigation. During the investigation, the root causes of the risks or issues will be identified and the concerned individuals or agencies responsible for correcting or resolving the issue will be assigned. The committee will produce a report of its findings such as causes of issues, involvement of concerned agencies, time taken to resolve, recommendations and actions. Complainants may request or will be sent a copy of the reports related to the complaint. All the complaints (if received any) and measures taken will be stored in a database of the project coordination and management unit and will also be reported to Adaptation Fund along with the yearly progress report.
Have the implementation arrangements been effective during the reporting period? |  | Yes for the reporting period, the implementation arrangements at the IE for risk monitoring is currently effective as there have been no Environmental or social risks reported to the IE or EEs.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EEs have been reaching out to the National and local partners to check for potential risks during the entire phase of implementation. In case of any risks or issues at the National or local level, it should be reported to them via email, telephone or visits to their headquaters and it will be then reported to the IE for a joint action.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes for the reporting period, the implementation arrangements at the EEs for risk or isues monitoring is currently effective as there have been no Environmental or social risks reported to the EEs.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs. |  |  |  | N/A as the VFDM project does not have any USPs
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | N/A
N/A for the first, second and third PPR reports
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Grievance mechanism can be submitted through: https://www.floodmanagement.info/floodmanagement/volta-basin/contacts/ |  | No grievances have been reported during the third reporting period to the Implementing and Executing Partners as well as to the Adaptation Fund. Any Grievence or issues can be reported through the project webage https://www.floodmanagement.info/floodmanagement/volta-basin/contacts/ or directly to the Adaptation Fund or the Implementing Partner. If any greivance or issues are reported in future, it will be informed to the Adaptation Fund directly or through the PPR report, describing also the measures taken to resolve or mitigate it.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | During the preparation phase, gender considerations were taken into account mainly highlighting the following aspects for ensuring integration of gender-sensitive and inclusive approach during project implementation and outcomes: 1) Baseline with sex-disaggregated data and gender-specific questions at regional, national, sub-national, and local levels. 2) Use of participatory tools for gender-sensitive community consultation and M&E of the activities implemented. 3) Use of Training Manual developed by WMO for mainstreaming gender in End-to-End EWS for Flood forecasting and Integrated Flood Management and tool for Nature-based solutions 4) Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities building resilience of women or women groups to climate change events. 5) Foster equal participation of men and women in institutions and decision-making processes related to the project. 6)Ensure women are involved in maintaining long-term sustainability of the project outcomes.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. The results framework includes baseline as well as targeted indicators at the objective, outcome, and output level which either refer to targets for women's participation or engagement as well as to identify gender-disaggregated data for capacity development and usage of tools and products delivered through project activities.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Percentage of households (including female headed households) with improved livelihoods or economic benefits | Overall Objective | % of household(including female headed) with improved livelihood or economic benefits | 0 | 50% | To be measured at the end of project
Capacity of stakeholders to develop Floods and Drought risk maps is enhanced | Output 1.1.2 | number of women trained | 0 | 20 | Satisfactory Justification: For the target of 20 staff, the project was succesfully able to identify and provide training to 13 women technicians in the six countries. The criteria's for selecting the National agencies staff for training on development of the floods and drought risk maps and climate scenarios were 1) Knowledge and experience of using Geographical Information System tool (ArcGis, QGis) 2) Basic Experience and knowledge in risk assessment and mapping, exposure and vulnerability assessment, hazard and risk modelling 3) Knowledge of existing databases for exposure, vulnerability and hazards available in the country 4) Basic Knowledge of the disaster risk management system of the country etc. The concept note for identifying techncians was circulated to the National agencies and even after the deadline for submission, the National focal points were requested to provide additional women candidates for training sessions. It was not possible to train a candidate without knowledge and experience mentioned above.
Capacity of stakeholders to use Floods and Drought risk maps is enhanced | Output 1.1.3 | % of women participated | 0 | 50% | 13 female particiapnts were trained for the development of flood and drought risks. It was challenging to identify female candidates with 1) Knowledge and experience of using Geographical Information System tool (ArcGis, QGis) 2) Basic Experience and knowledge in risk assessment and mapping, exposure and vulnerability assessment, hazard and risk modelling 3) Knowledge of existing databases for exposure, vulnerability and hazards available in the country 4) Basic Knowledge of the disaster risk management system of the country etc. The concept note for identifying techncians was circulated to the National agencies and even after the deadline for submission, the National focal points were requested to provide additional women candidates for training sessions. It was not possible to train a candidate without knowledge and experience mentioned above.
Risk Management strategies in short, medium and long term to be integrated into development plans (economic, social, environmental aspects) | Outcome 1.3 | % of women participated | 0 | 50% | Activity under progress. EEs are informed to involve atleast 50% female participants during the national consultation processes . To be measured at the end of year 4
Development and dissemination of risk management strategies and action plan for their integration into development plans | Output 1.3.1 amd 1.3.2 | Number of women involved on risk management strategies and action plan | 0 | 100% | Activity under progress.In terms of dissemination, specific tools and materials will be developed targeting women groups, youth, scholl childrens etc. To be measured at the end of year 4
Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities | Outcome 2.1 | Number of women participated | 9 | 5000 | Activity under progress. EWS will be deisgned with consultation of women. Specific bulletin will be requested targting women groups involved with economical and livelihood activities. To be measured at the end of year 4
Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities | Outcome 2.1 | Number of beneficiaries (male and female – data disaggregated by gender) and regions are identified for forecasting and EWS | 0 | 1000 | Activity under progress. Number of beneficiaries will include both female and male participants. To be measured at the end of project
The web-based Early Warning dissemination interface for VoltAlarm is designed | Output 2.1.6 | Percentage of the population (men, women, elderly, and youths) understanding the added-value of the early warning system | 0 | 1000 | Activity under progress. More than 200 participants (50% women) in the country were presented with the VOLTALARM EWS for understanding and sharing the usability experince . Once finalized with modelling and forecasting, additional participants from the countries and regional levels will be trained. To be measured at the end of project
Pilot testing for a number of areas over the basin during the monsoon and dry seasons is performed | Output 2.2.1 | % of women participated in coordination meeting and decision-making | 0 | 50% | Activity to be initiated after availability of EWS. Dring the initial consultations at the 10 pilot sites, women representatives provided information related to issues and need for better ways for early warning dissemination. This will be conisidered during the design and developemnt of the EWS.To be measured at the end of project
Development and implementation of community-based flood and drought management | Output 2.2.3 | % of women participated and benefitting from the local system and capacity development | 0 | 1000 | Approximately around 1000 women participated and benefited from the community based flood management activities implemeted in the six communities of the Volta Basin
Knowledge and capacity development using the IUCN Nature-based standards | Output 2.3.1 | % of women participated and trained | 0 | 50% | More than 200 women (around 40%) were trained on the IUCN nature-based solutions. To be reported at the final reporting.
Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management . | Output 2.3.2 | % of women participated with dialog and advocacy Percentage of women with physical, social, political and economic empowerment | 0 | 50% | Good For the 8 National workshops training on Mainstreaming Gender, we had more than 60 percentage women participants as compared to men. The project team were able to get women decision makers, gender focal points in each countries who were eager to provide support in developing road map as well as providing budgeting for mainstreaming gender into E2E-EWS-FF and IFM. Please check the below link https://www.floodmanagement.info/national-training-workshops-for-mainstreaming-gender-into-e2e-ews-ff-and-ifm/
Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environmental impact is strengthened | Output 3.1.2 | % of women participated | 0 | 50% | To be measured at the end of year 4
Experiences of local communities on key long term strategies for floods and drought management are collected | Output 3.1.3 | number of women, elderly and youths consulted | 0 | 50% | To be measured at the end of year 4
Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies | Outcome 3.2 | number of women participated | 0 | 50 | To be measured at the end of year 4
A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context | Outcome 3.3 | number of women, elderly and youths consulted | 0 | 50% | To be measured at the end of year 4
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed and shared with final PPR |  | N/A - to be completed for final PPR as per guidance notes.
N/A - to be completed and shared with final PPR |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Entities, have all made efforts to comply with the principle of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity, gender-inclusive, and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the local or household baseline incorporated sex disaggregated data and gender-specific questions. 2 - Encouraging project partners/ executing entities/consultants/national stakeholders to hold gender-sensitive consultations and assessments, for example conducting separate focus group discussions for men and women, therefore allowing women's views to be better captured without being overshadowed by men. 3 - Ensuring Local, National, Regional Workshops and Training (including VFDM Inception workshop) has the participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during consultation and work planning meetings - for example, the question of how activities are designed so as to encourage full participation and engagement of women
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements at the IE for Gender Policy compliance has been effective during the third year of implementation. The Gender Focal points of the IE was/is involved in designing activities including also during the mid-term evaluation. Discussions regarding gender issues or participation are held during project activities implementation and work planning meetings, ensuring: 1) all partners consider the needs (language, cultural, ensure equal participation of women and men) and constraints (giving floor to women participants to present their views etc.) of women participation in project activities; 2) ensure Gender participation (checking availabilities from their schedule) in all activities; 3) aim for assigning activity leadership to women and 4) capture sex-disaggregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project. -During the hiring of technicians, consultants or experts, a higher selection weightage is and will be given to female applicants.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | WMO: During Consultation and implementation of activities (workshops, development of products, and tools), a review is carried out through a Gender expert or with a Gender Lens while designing activities or requirement gatherings. The experts involved in the implementation of the activities are made aware of the AF Gender policy consideration and ensure the involvement of women, youths as much as possible in their activities.
VBA: The VBA at the regional level ensures National gender focal points, where available are involved, in project planning meetings and on review of reports, concept notes, and documents to ensure the incorporation of gender aspects. - While organizing workshops and training both men and women are invited as participants. In the project Inception workshop, more than 40% percent of participants were female -During the hiring of consultants, a higher selection weightage is given to female applicants.
GWP-WA: - While organizing workshops and training as well as during implementation both men and women are invited as participants and engaged in tasks. In the activities related to the gender mainstreaming, more than 60% percent of participants were female -During the hiring of consultants, a higher selection weightage is given to female applicants.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements for Gender Policy compliance has been effective to some extent but not in all. Women's participation in project activities, as well as their engagement in leadership and training roles have been below expectations due to cultural barriers or lack of women at management or decision-makers level at the National services of the six countries. The effectiveness of the EEs efforts has also varied from country-to-country (For example: at Ghana, there are more consultations with women working in the field of Hydro-meteorological services as compared to men) and activity to activity. The EEs will continue to emphasize or implement Gender-specific, sensitive or inclusive approach among stakeholders.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | During the reporting period, no major capacity gaps affecting Gender Policy compliance have been identified at both IE or the EEs. In the project countries, it is always challenging to have expected participation of women in the project activities (identified in other completed projects due to social and cultural barriers). IE and EEs will continue to implement or comply with the GP of the Adaptation Fund during the remaining implementation phase.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Grievance mechanism can be submitted through: https://www.floodmanagement.info/floodmanagement/volta-basin/contacts/
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A-No Grievances related to Genders matters were received during the reporting period but suggestions related to gender participation and involvement are highlighted during meetings |  | N/A- no grievance related to the gender issues were reported to the IE and Ees
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing and Executing Entity: WMO | Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms |  | Outcome 1 | The project team has identified premilinary existing information in relation to floods and drought risk maps in each of the six countries and integration of existing information through different projects on risk maps and national data and information collection is on-going |  | 1. The baseline information has been completed for all six countries and National reports are validated and available. 2. The missing information or new required data survey sheet is shared with the countries 3. Identification of Globally available datasets and integration in the web-based EWS is completed 4. National and local data and information (hazard, hydrology and meteorolgy, social and structural) are collected from the National Agencies 5.Trainings (virtual and face-to-face) with the 62 National technicians are completed to develop the GIS layers of hazards, vulnerabilities and risk maps. 6. Final risk maps on floods and drought are presently developed by the technical partners integrating and merging the National level GIS layers of exposure, vulnerabilities and impact maps (check here for the final report https://www.floodmanagement.info/volta-basin/deliverables/) 7. Development of the National centralized database for storing and managing the Hydrological,Meteorological, Climatological, Social, Structural and environmental data and information is under final stage. Discussion with countries are completed and national agencies hosting the database has been identified 8. Procurement of the IT and Database equipments are on-going (planned completion by Dec 2022) | Satisfactory (Planned completion by December 2022)
| Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge |  | Outcome 6 | Identification of existing information on climate change predictions, social and structural etc. Building awareness of future risks and impacts on economic, urban, climate, environment etc. due to climate change and variability |  | 1. Global information related to climate projections are collected and visualized 2. Discussion with the National stakeholders are completed to share National data and information 3. Discussion with other completed, on-going project's are completed and used for the development of the climate scenario 4. Model to simulate climate change impacts to various sectors ( population, urban, water resources, etc) are identified and simulation have been completed | Satisfactory (completed)
| Outcome 1.3: Risk management strategies in short, medium and longterm to be integrated into development plans (economic, social, environmental aspects) |  | Outcome 7 | Capacity development of relevant stakeholders for integrating risk management strategies into development plans with assigned roles and responsibilities |  | 1. Secondary literature review and discussion with the National stakeholders are carried out to identify existing information (plans, policies or guidelines) for managing risks related to floods and drought events at local, national and regional levels 2. Based on the risk maps, risk management strategies and framework will be developed- planned ompletion by January 2023 | Marginal Satisfactory (On-going as planned and will be reported in PPR4)
| Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Outcome 2 | At least 70 % of the population in Volta Basin region has Forecasting and EWS and it is been utilized. |  | 1. Design and development of the web-based EWS is on-going 2.Integration of the existing data (static and real-time) information from the National and Regional projects or initiatives are on-going 3. Customization of the EWS for the context of the Volta Basin countries (availability and design of the Bulletin for the National agencies, Volta Basin regional maps, etc) | Marginal Satisfactory (On-going as planned and final completion will be reported in PPR 4)
| Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Outcome 2 | Atleast one pilot locations of each Volta Basin countries have been tested with developed tool and models |  | Identification of the pilot sites in each of the project countries in joint consultation with the National agencies are finalized and initial consultation meetings with the stakeholders have been held | Marginal Satisfactory (Pilot sites have been finalized and initial consultation have been done with the support of the National Working group )
| Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Outcome 3 | More than 100 participants are trained on hydro-meteorological risks, prevention, preparedness, and response strategies. These participants disseminate knowledge and tools to other stakeholders. |  | Identification of the National Agencies staffs and local representatives for capacity building trainings and skill development activities are completed. 8 workshops on mainstreaming gender into E2E-EWS-FF and IFM and 6 workshops on IUCN standards for nature-based solutions are completed Action plan for gender mainstreaming at the regional, national and local levels are under development. Concept note for the bankable project on nature based solutions for flood and drought management is available and discussion for funding are on-going with various donors and fnancial institutions | Satisfactory (On-going as planned and final status will be reported in PPR 4)
| Outcome 3.1: Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin |  | Outcome 3 | Strengthened plans, policies and guidelines documents with necessary amendments. |  | Existing plans, policies and guidelines documents available at national and transboundary level are identified and reviewed. | Marginal Satisfactory (On-going as planned and final status will be reported in PPR 4)
| Outcome 3.2: Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Outcome 7 | Locals/national/regional stakeholders integrate risk management policies, plans into national and transboundary development plans. |  | Identification of the National Agencies staffs and local representatives (policy-makers) for capacity development and awareness activities is completed. Capacity building will continue throughout the duration of the project. | Will be reported in PPR 4
| Outcome 3.3: A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Outcome 7 | Risk management instruments and strategies is adapted and applied at the local level |  | Identification and consultation with the local communities representatives for capacity development and awareness activities will be started in March 2022 | Will be reported in PPR 4
[6 empty] | Overall Rating | Marginal Satisfactory
The VFDM project has been progressing satisfactorily positive in terms of technical design and development of the tools and products jointly with National and Regional stakeholders especially VOLTALARM EWS, building capacity on risk mapping, climate scenarios, risk prevention and management strategies, gender mainstreaming, IUCN NbS, coordination and engagement of the National stakeholders, developing synergies with other projects and initiatives etc. Nevertheless, some delays were encountered initially due to identification of roles and responsibilities and signing of agreements between the executing partners. The implementation was on track until the COVID-19 pandemic situation imposed travel restrictions and organization of activities/meetings at both National and regional level.The project management team continued virtual discussions with the Regional and National stakeholders and planned measures for implementing upcoming activities. Starting from March 202, the implementation of activities have been started now at National level and it is expected to continue at the National and local levels through trained national and local consultants. The overall IP rating is Marginal Satisfactory based on the overall status of completion of the outputs/activities.
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ramesh Tripathi, VFDM Project Manager
| Email: | rtripathi@wmo.int
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
For the third reporting perido, the project implementation is proceeding well. Due to the third covid-19 outbreak situation, some of the activities from the second year have been postponed to the third year as the project team and external partners were not allowed to travel to the project countries as well as some of the National Agency’s staff were working from home. It was expected that by the end of December 2022, major activities will be on schedule in line with milestones in the logframe, particularly for the development of EWS (integration of local datasets,development of impact based forecasting, project-specific information, etc.) along with capacity development planned under Component 2 and component 3. Coordination between the implementing entity and executing entities has been good with regular meetings and communication being held to ensure integration between project activities as well as with the different partners and levels (regional to local level). Several workshops at National and Regional level are organized to present the project progress to the stakeholders and get their commitment to what is considered an innovative and tailored project for the Volta Basin region. Completion of baseline data collection and National consultation reports (which will provide benchmarks to measure project impacts), local risk mapping in the 60 sites, Nationalized/Centralized Database development have been completed and visualized and have laid the foundation for implementation of the impact based forecasting The project team sometimes go through challenging situation in terms of organizing activities in the six countries for example organization of National consultation meetings with the Project Team and External implementing partners taking into consideration availability of project team and national stakeholders, budget limitation, and other logistical issues. The Project Technical Advisory Committee (PTAC) i meetings are held bi-annually/annually and the PTAC Members are reviewing yearly project progress, risks encountered and mitigation measures, provide suggestions and technical assistance on the implementation of activities in the subsequent years. Completed outputs: 1) National consultation reports, local risk mapping, identification of ecosystem and environment indicators as well as development of the guidance note under Component 1 are completed. 2) IT/DB Assessment to understand the current capacities and needs for establishing centralized database and accessing EWS is almost completed, and draft reports are shared with the National partners.3) risk maps and climate scenarios are developed and visualized under the VOLTALARM EWS Major recommendations for future activities: 1) The project team will involve national focal points in the organizing and implementation of sub-activities or tasks where National agencies' staff support will be needed. 2) Ensure timely preparation of the concept note or Terms of Reference which will be shared in advance to the regional and national Stakeholders 3) Regular consultation through face-to-face or virtual meetings with different National stakeholders for setting-up of the National Integrated databases and forecasting and early warning system 4) Ensure activities are implemented parallelly in different countries through active National and local stakeholders’ engagement
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity-VBA | Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms |  | Outcome 1 | VBA provided communication with national Focal Points, facilitated the negotiation of work agendas and provided technical support in collecting data on flood and drought risks in different countries |  | 1. At least, 400 official letters have been written and sent to the 6 VBA Line Ministries in support the mobilization of actors for the various meetings; 2. Provisional reports have been sent to the various Focal Points for amendment and additional missing information; 3. A country-by-country agenda was negotiated and obtained for the various meetings and activities. 4. VBA worked in collaboration with the national agencies of the six (6) countries to set up six (6) national working groups. Each working group will ensure coordination and synergy of action in the implementation of the activities entrusted to it. | Satisfactory
|  |  |  | Database of VCERs, floods and drought related risk maps are developed |  | 1. Support the concept note finalization for the conduct of the diffrent activities; 2. Identification and creation of IT/ and Database Expert list in support of the completion of the 1122 activity; 3. Support the concept note finalization for a virtual meeting on the implementation of the activity in the 6 countries 4. VBA IT/DB expert visited 6 countries to collect necessary information on understanding current capabilities and needs for establishing National database and accessing the VOLTALARM EWS. | Satisfactory
| Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge |  | Outcome 6 | Impact on environmental indicators is evaluated for current and future scenarios |  | 1.Support the concept finalization of activities 1113, 1114, 1122, 1231-1237 in the 6 countries; 2. Support concept notes finalization for the holding of the various virtual meetings for the implementation of activities 1113, 1114, 1231-1237 in the 6 countries; 3. Organizing and holding a meeting to harmonize the understanding of the terms of reference for carrying out the activity 1231-1237; 4. Support for the development of the final version of the Concept Note for the Conduct of Activities 1231-1237 5. Preparing and sending a message to the National Focal Points to share the finalized conceptual notes of the activities and the virtual meeting with the 6 countries 6. Organzing the mini-workshops at each country to review and validate the two reports (Feasability study of the application of the IUCN Red List of Ecosystem and Integrated basin-wide wetland guidelines to promote ecosystem services sustainability) prepared by IUCN in close coordination with the PMT 7. Organizing and conducting the regional workshop (attanded by more than 50 participants) on 15th and 16th June 2021 mainly to review the ecosystem services status through the two reports and capacity development for Nature-based solutions leading to the development of a bankable project proposal. | Satisfactory
| Outcome 1.3: Risk management strategies in short, medium and longterm to be integrated into development plans (economic, social, environmental aspects) |  | Outcome 7 | Capacity development of relevant stakeholders for integrating risk management strategies into development plans with assigned roles and responsibilities |  | 1. Secondary literature review and discussion with the National stakeholders are carried out to identify existing information (plans, policies or guidelines) for managing risks related to floods and drought events. • Finalization of the Terms of Reference with the WMO and GWP-WA • Recruitment of six (6) national consultants • the signing of six (6) service contracts • Launch and monitoring of data collection and the preparation of interim study reports Pursuant to these steps, the following deliverables were obtained: • One (01) ToR finalized; • Recruitment and contracting with six (6) national consultants; • drawing up and signing six (6) employment contracts; • six (6) national and one (1) regional, reports prepared. • One (1) regional workshop report established • Six (6) mini national workshops to amend and adapt the draft policies, plans, strategies, programs and directives to climate extremes such as flood and drought; • six (6) amendment reports were produced by the country teams. | Will be reported in PPR 4
| Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Outcome 2 | At least 70 % of the population in Volta Basin region has Forecasting and EWS and it is been utilized. |  | 1. Development of the web-EWS is on-going 2.Integration of the existing information from other National and Regional projects | Will be reported in PPR 4
| Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Outcome 2 | Atleast one pilot locations of each Volta Basin countries have been tested with developed tool and models |  | Identification of the pilot sites in each of the project countries in joint consultation with the National agencies are completed and initial consultations are carried out ongoing | Will be reported in PPR 4
| Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Outcome 3 | More than 300 participants are trained on hydro-meteorological risks, prevention, preparedness, and response strategies. These participants disseminate knowledge and tools to other stakeholders. |  | Identification of the National Agencies staffs and local representatives for capacity building trainings and skills development activities or the implementation of this activity, the VBA proceeded as follows: To date, the deliverables resulting from this activity are: six (6) local partners recruited six (6) contracts or partnership agreements signed six (6) flood and drought management committees set up six (6) community flood and drought management action plans developed six (6) activity launch reports five (5) out of six (6) quarterly technical and financial activity reports prepared and available • Ten (10) discussions and monitoring of activities organized with local partners; • Six (6) flood and drought management committees set up; • Six (6) community flood and drought management action plans developed; • six (6) quarterly technical and financial progress reports prepared and available; • six (6) progress reports were produced; • five/six (5/6) hydro-meteorological stations were installed and are operational. | Will be reported in PPR 4
| Outcome 3.1: Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin |  | Outcome 3 | Strengthened plans, policies and guidelines documents with necessary amendments. |  | Plans, policies and guidelines documents are reviewed | Will be reported in PPR 4
| Outcome 3.2: Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Outcome 7 | Locals/national/regional stakeholders integrate risk management policies, plans into national and transboundary development plans. |  | Identification of the National Agencies staffs and local representatives for capacity development and awareness activities | Will be reported in PPR 4
| Outcome 3.3: A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Outcome 7 | Risk management instruments and strategies is adapted and applied at the local level |  | Identification and consultation with the local communities representatives for capacity development and awareness activities | Will be reported in PPR 4
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | NIAMPA Boukari, Project Technical Officer at VBA
|  | Email: | niampaboukary@yahoo.fr; bniampa@abv.int
As a project implementation partner, the Volta Basin Authority (VBA) through the project technical officer, provided support in several areas as follows: - At the technical level, it contributed to technical and coordination meetings both in and outside of Burkina Faso. It took part in the meetings to amend and finalize the working papers (Work Plan, Budget, signing of the agreements and Terms of Reference). VBA regularly participated to the national and regional workshops - in terms of mobilizing the partnership and the stakeholders for the implementation of the project, VBA facilitated the transmission of information, consultations and the mobilization of non-financial co-financing and synergy commitments in favour of the implementation of the VFDM project. It has constantly informed the 6 VBA Line Ministries on the implementation of the project's activities in each country and reported to the Council of Ministers of the Volta Basin. In addition, it has regularly linked the National Focal Points VBA, WMO, and GWP/WA in favour of synergistic support of the project's activities; - administratively, VBA provided institutional communication through over 400 official letters and at least 500 e-mail messages sent to the countries, including in relation to (i) the organization and conduct of EWS missions; (ii) interim study reports, (iii) the selection of national consultants and 60 sites for mapping vulnerability and capacity at the community level, (v) the organization of virtual meetings for the presentation of study reports, concept notes and questionnaires relating to the completion of activities 1113; 1 1.1.4; 1.1.2.2; 1.1.2.3; 1.2.3.1 to 1.2.3.7; 1121; 1124; 2161; 2162, 223; completion of the community-based flood and drought management activities, risk mapping and climate scenarios, IT and DB assessment and identification of the national host agency in each of the Volta Basin countries, support in the design and development of the VOLTALARM EWS. To better achieve efficiency and effectiveness in the implementation of the project, it is recommended to: - have a Work Plan and Budget on time, with clear responsibilities indicated; - provide the National Actors necessary support to facilitate the carrying out of the activities. - hold regular meetings for updating and orientation between the three executing partners; - operationalize the Technical Advisory Committee as well as the operational documents; - make budgetary adjustments to (i) save money; (ii) fill the necessary gaps allowing certain under-budgeted activities to be completely carried out - involve the national working group in a flexible way with less administrative protocol;
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Executive Entity -GWP-WA | Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity: GWP-WA | Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms |  | Outcome 1 | The project team has identified premilinary existing information in relation to floods and drought risk maps in each of the six countries and integration of existing information through different projects on risk maps and national data and information collection is on-going |  | 1. The Project Technical Assistant designed and led the process leading to the selection of 62 technicians, data collection and capacity building of technicians for the development of flood and drought risk maps. 2. The Project Technical Assistant prepared the twelve (12) national capacity building workshops of technicians for the development of flood and drought risk map and participated in the workshops in Burkina Faso, Benin and Togo 3. Comments and improvements to the draft concept note of a joint regional workshop for stakeholders to deliver knowledge on Vulnerability Capacities Exposures and Risks (VCER’s) database and Floods and Drought risk maps of Volta Basin 4. The Project Technical Assistant prepared and facilitated a joint regional workshop for stakeholders to deliver knowledge on Vulnerability Capacities Exposures and Risks (VCER’s) database and Floods and Drought risk maps of Volta Basin 5. The Project Technical Assistant finalized and shared the regional workshop report for stakeholders to deliver knowledge on Vulnerability Capacities Exposures and Risks (VCER’s) database and Floods and Drought risk maps of Volta Basin 6. Comments and improvements to the draft concept note of a national workshops to raise awareness in regional and national stakeholders about the volta risk profile for floods and droughts 7. The Project Technical Assistant prepared and facilitated the six national workshops to raise awareness in regional and national stakeholders about the volta risk profile for floods and droughts | Satisfactory
| Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge |  | Outcome 6 | Building awareness of future risks and impacts on economic, urban, climate, environment etc. due to climate change and variability |  | 1. Participation in the regional workshop and contribution to the finalization of the report of the regional workshop on Nature-Based Solutions and to the various facilitation materials for the workshop. | Satisfactory
| Outcome 1.3: Risk management strategies in short, medium and longterm to be integrated into development plans (economic, social, environmental aspects) |  | Outcome 7 | Capacity development of relevant stakeholders for integrating risk management strategies into development plans with assigned roles and responsibilities |  | Faciliting the discussion with national stakeholders to identify existing information (plans, policies or guidelines) and the ecommendations for managing risks related to floods and drought events | On-going: Will be reported in PPR 4
| Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Outcome 2 | At least 70 % of the population in Volta Basin region has Forecasting and EWS and it is been utilized. |  | 1. Facilitating the planning and attending the six national virtual meeting to present the Web-EWS to the national stakeholders and to obtain their acceptance for its development 2. Comment and improvements provided to the draft concept note of the regional training workshop on the use of the VoltAlarm Platform 3. Participation in the regional workshop and contribution to the finalization of the report of the regional workshop | On-going: Will be reported in PPR 4
| Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Outcome 2 | Atleast one pilot locations of each Volta Basin countries have been tested with developed tool and models |  | 1. Contributing to the elaboration of the guidance note provided to the national agencies to identify pilot sites in each of the six countries of the Volta Basin 2. Comment and improvements provided to the draft concept note of community initiatives for integrated flood and drought management in the Volta Basin 3. Comment and improvements provided to the draft concept note of the terms of reference for the recruitment of local partners who will support the implementation of initiatives at the local level. 4. Participation in the process of recruiting local partners who will support the implementation of initiatives at the local level. 5. Participation in the various discussion sessions organized online with the various structures selected at the end of the recruitment process | On-going Satisfactory
| Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Outcome 3 | More than 300 participants are trained on hydro-meteorological risks, prevention, preparedness, and response strategies. These participants disseminate knowledge and tools to other stakeholders. |  | 1. Development of the concept note for the adaptation of the training manual on the integration of gender in the E2E-EWS-FF and the IFM to the context of the Volta basin; 2. Development of the terms of reference and recruitment of the consultant responsible for supporting the adaptation of the training manual; 3. Adaptation of the manual and development of facilitation materials for national training workshops on gender mainstreaming in the SAP BEB PC and GIRI; 4. Planning and organization of eight national training workshops on gender mainstreaming in E2E-EWS-FF and the IFM 5. Facilitation and reporting of the eight national training workshops on gender mainstreaming in E2E-EWS-FF and the IFM 6. Comment and improvements provided to the draft concept note of national capacity building workshops for Volta Basin actors on "nature-based solutions" with a view to developing bankable projects at the scale of the Volta Basin 7. Participation and animation in the national capacity building workshops (in Benin, Togo and Côte d'Ivoire) and contribution to the finalization of the report of the national workshop 8. The Project Technical Assistant contributed in developing the concept note for the regional program on nature-based solutions in the Volta Basin and then in organizing the regional workshop to present the concept note | Satisfactory
| Outcome 3.1: Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin |  | Outcome 3 | Strengthened plans, policies and guidelines documents with necessary amendments. |  | 1. Faciliting the discussion with national stakeholders to identify existing plans, policies or guidelines for managing risks related to floods and drought events in the volta bassin 2. Participation in the process of recruiting the consultants who will conduct the review of policies, plans, strategies, programs and directives related to adaptation and resilience to climate change in the Volta Basin 3. Comment and improvements provided to the draft report of review of policies, plans, strategies, programs and directives related to adaptation and resilience to climate change in the Volta Basin 4. Support to the prepation and participation to the regional workshop held in Benin that presented the results of the review of policies, plans, strategies, programs and directives related to adaptation and resilience to climate change in the Volta Basin. | Will be reported in PPR 4
| Outcome 3.2: Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Outcome 7 | Locals/national/regional stakeholders integrate risk management policies, plans into national and transboundary development plans. |  | Facilating the identification of the national agencies to identify staffs and local representatives for capacity development and awareness activities | Will be reported in PPR 4
| Outcome 3.3: A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Outcome 7 | Risk management instruments and strategies is adapted and applied at the local level |  | Facilitating the identification and consultation with the local communities representatives for capacity development and awareness activities | Will be reported in PPR 4
[6 empty] | Overall Ratings | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Maxime TEBLEKOU
|  | Email: | maxime.teblekou@gwpao.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Basically, the project implementation is going well with minor delays due to the COVID-19 pandemic situation in 2020, 2021 and early 2022. The concept notes of the activities are finalized by considering the comments and improvements provided by the different partners. The same applies to the methodological approaches and data collection tools proposed by the consultants for the conduct of activities. These different documents (concept notes and methodological guide) are shared with the focal points (WMO, VBA and GWP-WA) of the countries of the Volta Basin to enable them to take ownership of the activities and to make their contributions. During the three years of implementation, GWP-WA has contributed to the collection of data and the preparation of national consultation reports on the assessment of national capacities and needs for forecasting and warning systems. to floods and droughts (which will provide benchmarks for measuring the impacts of the project), the recruitment of local experts, the identification of around sixty sites throughout the Volta basin and the monitoring of data collection at different sites for local community risk mapping. It contributed to the selection of 62 technicians and to the organization of a first series of face-to-face national workshops for the development of flood and drought risk maps in the Volta Basin. GWP-WA also contributed to the development of the project monitoring and evaluation manual, to the communication around the project activities, to the formation of the Project Technical Advisory Committee (PTAC) which annually reviews the progress of the project; risks encountered and mitigation measures, suggestions, and technical assistance on the implementation of activities in subsequent years. He contributed (i) to the adaptation of the training manual on gender mainstreaming in SAP end-to-end for flood forecasting and integrated flood risk management to the context of the Volta Basin; (ii) the organization of eight (08) national training workshops on the mainstreaming gender into end-to-end SAP processes for flood forecasting and integrated flood risk management in the Volta Basin context. GWP-WA has contributed to the process of capacity building, data collection and production of flood and drought risk maps of the Volta Basin, which has now made it possible to develop the risk profile of the Volta Basin. Floods and Drought of the Volta Basin. During the third year of project implementation, GWP-WA facilitated the organization of national awareness workshops for national and regional stakeholders on the flood and drought risk profile of the Volta Basin. GWP-WA also supported the preparation and facilitation of national training workshops on nature-based solutions and the development of bankable projects. GWP-WA took an active part in the preparation and animation of the meetings of the Technical Advisory Committee of the Project. Due to the situation of the covid-19 epidemic, some activities of the first year and second year have been postponed to the third year and now to the fourth year because the project team and external partners were not allowed to meet. travel to the project countries as well as some of the staff of the national agencies working from home. During the third year of project implementation, all the planned activities are almost carried out. Some activities are underway and should be completed by the end of 2022. These are mainly: (i) the development of the action plan to improve the participation of women and vulnerable groups in the integrated management and flood warning at local, national and regional levels in the Volta Basin; (ii) the development of online course modules on dissemination, decision support and response in connection with flood and drought warning; (iii) organization of online courses on dissemination, decision support and response in connection with flood and drought warning; and (iv) the organization of a regional training workshop on the entire Early Warning System (EWS) process for flood forecasting and the three pillars of drought management. and (v) development of flood and drought impact based forecasting and early warning sysem Some of future recommendations for implementation: 1) Implement non-linked activities parallelly in the Six countries 2) Mobilizing National and local stakeholders for their support to the Activities 3) When possible, hire local and/or national experts to implement activities with proper training provided by the Technical partners
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | 1. Indicate trends, both positive and negative, in the achievement of outcomes as per the project indicators. The overall implementation experience has been positive. The project executing entities are working well under overall guidance or oversight of the Implementing Entity (WMO). Also, the project team is continuously involving the National, local and regional stakeholders from the six countries including the ministries responsible for Meteorological, Hydrological, Agriculture, who committed to provide their support and staff engagement in the implementation of the activities and ensuring the deliverables are effective, tailored, open-source and sustainable. This Project continues with high visibility and relevance in the national and regional context ensuring methodologies, tools and products development are maintained and scaled to the entire National portion of the six countries . The institutional arrangements for the Project Management Team (PMT) are in place and operational including the Project Technical Advisory Committee (PTAC). At the National level, each country is requested to provide focal points that will provide necessary support or assistance in fulfilling the tasks or activities of the project ensuring the project activities align with their mandates and tools and products are useful for their day to day services or work. As the national working groups are finalized, the implementation of activities will intensify at both the National and Regional levels, ensuring activities in the country are executing parallelly involving relevant stakeholders. As the National agencies have to carry out their day-to-day services and also working in different on-going initiatives or projects, sometimes the staffs are not able to timely respond or provide feedbacks to the concept note, ToR, technical reports which leads to delay in finalization or completion of the activities. In the third year, the project team spent considerable time and effort to meet and consult the relevant stakeholders identifying current needs, capabilities for developing an early warning system for floods and drought and to discuss synergies with other projects and avoid duplication of efforts. Several Terms of References (TORs) or Concept Note were prepared for the activities planned in the three year of implementation and shared with the National stakeholders for their review, feedback, and support in the implementation. Development of risk maps and climate scenarios under Component 1 has been completed with the support of the National agencies staff to build preparedness measures for climate change events as well as for economic development. Later with the development of the National/Centralized database in each of the project countries, the development of risk maps and climate scenarios could be scaled from the Basin level to the National level. The database (data from different agencies or from different on-going or completed projects) will be connected to the Early Warning System for floods and drought (planned for the fourth of the project) for monitoring, modelling and forecasting. Implementation is expected to be intensified in the coming months and looks promising in delivering on its planned targets. Several other activities are implemented such as identification and review of existing policies, plans and guidelines for the management of climate change extremes. As the project is transboundary, the project team has developed several communication documents (both in English and French) channels and plan for dissemination of the project requirements, deliverables and results to the National and local stakeholders. As the 5 projectcountries are french speaking and one english speaking, the project team has to develop all the reports, concept notes and documents in both the languages which sometimes take time in translation and review. 2. Detail critical risks that have affected progress. A major pandemic (COVID-19) situation has severely affected project progress to date. As informed to the Adaptation Fund during early March 2020 and through PPR-I and PPR-II, National workshops and other planned activities were not conducted due to travel restrictions imposed on the project team and other partners as well as National stakeholders were not available as there were restrictions on having a workshop with more than 15 participants and for more than 2 hours. Several virtual consultations were made with the countries to inform about the delay and even meetings were held to make progress in the implementation of activities (finalization of the reports, filling the data and information availability survey sheet). Informing the National stakeholders at an early stage was well appreciated by the project partners and continued open communication on any challenges or issues were welcomed. Several measures have been in place now (training of local/National experts so as to implement activities as planned, parallel implementation of activities in different countries). However, the measures adopted is taking extra efforts, time and commitment from the Project partners and National/Regional/Local experts who will provide their support in the implementation of activities. 3. Outline response to MTR undertaken this reporting period. The independent MTR was conducted with the national, local and regional stakeholders and the report was submitted to the Adaptation Fund Secretariat for the review. Some of the recommendations on project relevance, project effectiveness, project structure, efficiency and sustainability are considered in the implementation of the pending activities. It is also highlighted that the continous support and participation fromt he national and regional agencies will be important for the success and long term sustainability of the project outcomes 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words N/A for this reporting period. The VFDM project has been progressing satisfactorily positive in terms of technical design and development of the tools and products jointly with the support of National and Regional stakeholders, building capacity, coordination and engagement of the National stakeholders, developing synergies with other projects and initiatives etc. The project management team is continuously implementing innovative methods, measures and process for timely implementation of the upcoming activities with the Regional and National stakeholders. Post covid 19 sitaution, the implementation of activities have been started now at National level and it is expected to continue at the National and local levels through trained national and local consultants. The IP rating is Marginal Satisfactory (MS) based on the overall status of completion of the outputs/activities.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Overall objectives The VFDM project will strengthen community resilience through integrated approach for flood and drought management and support to decision-making. | • Degree of improvement in populations’ resilience to floods and drought events • Percentage of households (including femaleheaded households) with improved livelihoods or economic benefits • Quantitative details of the reduced number of the deaths and damage to assets and environment •Change in quality of climate related advisory to target population by the National services. | • Number of floods and drought disasters without adequate and integrated management • Lack of investment for concrete measures developing resilience to climate change • Increasing growth of populations losing interest in agriculture based economic activities | • Assessment of current capabilities and needs related to the development of risk maps and EWS (minimum 5 agencies in each countries were consulted) • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities- Until the reporting period, synergies with 4 completed and on-going projects (FANFAR, FEW White Volta and Oti-basin, CREWS project in Burkina Faso, Togo, and West Africa, CIMA risk profiles 2018 in 2 countries of the Volta Basin ) were carried out. Other national and regional projects (GEF-REWARD, Adaptation Fund National project in Cote do'Ivoire) and initiatives are screened and synergies/complementarities will be identified. • Development of decision-making tools and risk management strategies • Design and development of the EWS (https://volta.myDewetra.world ) for the Volta Basin is on-going and testing the effectiveness and applicability at the 10 pilot sites will commence from July 2023 For some activities, to be measured at the end of project | • Development of the risks map and end-to-end web-based early warning systems for floods and drought events. • Climate scenarios are mainstreamed into national plans and decision making tools. • 70% of floods and drought events are foreseen and adequate preparedness measures are taken by the beneficiaries
| • Local /national agencies and communities are trained on climate change adaptation measures for floods and drought and mainstreaming of gender •Policies and guidelines at national and transboundary level for flood and drought management are better integrated and action plans are developed. | • Insufficient understanding of risks, shortage of hydro-meteo infrastructures and resources • Lack of participation of Volta Basin countries at the national and transboundary level for flood and drought management • Unavailability of IT equipment’s, trained resources for data and information management and sharing. | • Development of the risk maps for the Volta Basin (risk maps and climate scenarios for the Volta Basin are dveeloped) • National agencies staff are involved in the development of the risk maps (61 technicians working in the national and local agencies and academia were involved in the development of risk maps) and risk prevention and management strategies (more than 8 national agencies are involved in the development of risk prevention and management strategies) • Assessment and consultation with the National agencies on needs and capabilities for the development of the National Centralized database and accessing the EWS (29 agencies Number of Agencies consulted in each country:Benin- 3, Burkina Faso - 6, Cote d'Ivoire - 5, Ghana - 6, Mali - 5,Togo- 4 ) especially meteorology, hydrology, disaster management, water resouces etc.) were consulted for understanding current capacities and needs for establishing centralized database. For some activities, to be measured at the end of project | • More than 1000 individuals from communities, agencies and organizations are trained through various workshops and are expected to disseminate knowledge and tools to other stakeholders • National and transboundary agencies are trained and water and natural resources policies and guidelines are developed
Outcome 1.1 Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms | Development of Flood and Drought risks maps for the Volta Basin region | The existing products, reports and documents don’t have information on Floods and Drought risks mapping for the Volta Basin region and its consequences on human and natural resources. | • Assessment of current capabilities and needs related to the development of risk maps (minimum 5 agencies in each countries were consulted) • Identification and collection of data required for the development of the flood and drought risk maps (National working groups and 61 technicians working in the national and local agencies and academia/universities were involved in the data collection related to vulnerabilities, risks and development of risk maps) • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities for risk maps development. Until the reporting period, synergies with 4 completed and on-going projects (FANFAR, FEW White Volta and Oti-basin, CREWS project in Burkina Faso, Togo, and West Africa, CIMA risk profiles 2018 in 2 countries of the Volta Basin ) were carried out. Other national and regional projects (GEF-REWARD, Adaptation Fund National project in Cote do'Ivoire) | Availability of Flood and Drought risks maps for risk-informed decision making Availability of climate scenarios and impacts due to the projected climate Availability of the risk prevention and management strategies (under finalization)
Output 1.1.1 Inventory of information on vulnerabilities, capacities, exposure and risks (VCERs) for floods and drought in the Volta Basin is conducted | Percentage of baseline information on vulnerabilities, capacities, exposure and risks will be made available for the Volta Basin | There is a lack of updated and integrated information on Floods and Drought related VCERs for the Volta Basin region | • Assessment of current capabilities and needs related to the development of risk maps and climate scenario (6 countries and VBA consultation reports (242 particiants participated) were developed with current capacibilities and needs related to the development of risk maps and climate scenario. check here https://www.floodmanagement.info/volta-basin/deliverables/ ) • Identification of National and local updated data and information available for risk mapping risk maps related data were collected and used for developing risk profiles https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_English.pdf • Identification and selection of National and Regional staff for providing training on VCERS GIS layers (61 technicians working in the national and local agencies and academia/universities were involved in the data collection related to vulnerabilities, risks and development of risk maps) • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities Until the reporting period, synergies with 4 completed and on-going projects (FANFAR, FEW White Volta and Oti-basin, CREWS project in Burkina Faso, Togo, and West Africa, CIMA risk profiles 2018 in 2 countries of the Volta Basin ) were carried out. Other national and regional projects (GEF-REWARD, Adaptation Fund National project in Cote do'Ivoire) | The VCERs database and flood and drought risk maps (risk zones) for the Volta Basin are developed with the available data; Metadata of VCERs will be available
Output 1.1.2 Database of VCERs, floods and drought related risk maps are developed | Progress in terms of developing the database and risk maps (zones) on VCERs of Volta Basin (Percentage of basin surface area). The data from different countries will be made compatible with products and services highlighting the missing data and information of respective countries | No database and risk maps are available for Floods and Drought events at the Volta Basin region. The Volta Basin lacks updated classifications of the regions according to Flood and Drought risks. | • Assessment of current capabilities and needs related to the development of risk maps and centralized database with Hydro, Meteo, Climate, social and structural related data and information Studies and reports on database and IT network for each of the Six countries are available including architecture for the national centralized database https://www.floodmanagement.info/volta-basin/deliverables/ •Virtual trainings and National face-to-face workshops organized for developing exposure and impact layers for the flood and drought events in the Volta Basin . 61 technicains (Number of Male technicians: 49 Number of female technicians: 12 )were involved and 12 national workshops were conducted to develop expsoure and impact layers. • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities until the reporting period, synergies with 4 completed and on-going projects (FANFAR, FEW White Volta and Oti-basin, CREWS project in Burkina Faso, Togo, and West Africa, CIMA risk profiles 2018 in 2 countries of the Volta Basin ) were carried out. Other national and regional projects (GEF-REWARD, Adaptation Fund National project in Cote do'Ivoire) •Availability of flood and drought risk maps for current climate and future climate and visualized under the VOLTALARM EWS Risk maps and climate scenarios are developed with local and national data and information available at the national agencies and archived in the database of VOLTALARM EWS (https://volta.myDewetra.world ) | The VCERs database and flood and drought risk maps (risk zones) for the Volta Basin will be developed with the available data; Metadata of VCERs will be available
Output 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | Number of workshops are organized for the dissemination of knowledge on VCERs and Flood and Drought risk maps No. of staff trained to develop skills for developing risk maps and mitigate the impact of climate –related events (by gender-number of women trained). | The risks related to Floods and Drought are not well identified and are not taken into account by the different actors of Volta Basin Limited knowledge and skills with the National services to develop risk maps for floods and drought events | • Assessment of current capabilities, skills and needs related to the development of risk maps - 6 National level workshops organized to present the study and consultation meetings reports • Identification and selection of National and Regional staff for providing training on VCERs GIS layers - 61 technicians hired to provide support •6 Virtual trainings, and 12 National face-to-face workshops are organized for developing exposure and impact layers for the flood and drought events in the Volta Basin - 1 regional and 6 national workshops are organized with the stakeholders to disseminate the knowledge on VCER, risk maps and climate scenarios | Atleast one workshop per country will be organised to disseminate knowledge on VCERs database and Flood and Drought risk maps 1 transboundary level consultation workshop with National Focal Point (NFP)
Output 1.1.4 Reports and communication documents on VCERs and risk maps | Progress in the development of the VCER and Flood and Drought risk maps report | Report on the VCER and Flood and Drought risk maps are not available for various actors concern by climate change adaptation and disaster risk reduction | •Availability of flood and drought risk maps for current climate and future climate and visualized under the VOLTALARM EWS Reports are available here https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_English.pdf and https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_French.pdf •List of actors and stakeholders to whom the document will be shared - it is shared with more than 30 participants during the national workshop organized in the Six countries. Also posters were prepared and shared on the impact areas in the Volta basin https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/10/Exposure_Impact_Maps_Technicians_6december2021_compressed.pdf | Report, guidelines and infographics materials on VCERs and Flood and Drought risk maps are developed
Outcome 1.2 Bridging the gap in Adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge | Development of future scenario for the climate change variability and Floods and Drought events with VCERs database, Hydro-meteo information, climate projections etc. | There is no prediction about the role of future scenarios on socio-economic, urban, climate and environmental conditions | •Availability of flood and drought risk maps for the future climate scenarios and visualized under the VOLTALARM EWS. Reports available below:https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_English.pdf and https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_French.pdf and information visualized under https://volta.mydewetra.world | Future scenarios are developed for the climate change variability and Floods and Drought events
Output 1.2.1 Scenarios for socio-economic and environment development along with the climate change projections are collected | Progress in acquiring data and information on socio-economic, climate change projections for developing future scenarios | There is no availability of future scenarios for socio-economic and environmental development related to the climate change projections | Data and information related to socio-economic and environmental development are identified and collected at the National and local level and used for the development of risk maps and climate scenario for understanding the flood and drought impacts at local, national and transboundary Climate change projection for next 10, 100 and 1000 years are developed and made available Reports available below:https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_English.pdf and https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/Volta_RiskProfile_Total_French.pdf | Data and information on climate change projection and environment development is made available to the National stakeholders
Output 1.2.2 Projected impacts on water resources, urban development and bio-diversity and agricultural areas are analysed on the basis of future scenarios | Progress in terms of modeling, analysis of qualitative or modeled data output | Lack of methodology to understand the impact of Flood and Drought events on risks; | Methodologies, tools and models for assessing projected impacts on water resources, urban development, and bio-diversity and agricultural areas are developed and visulaized under the VOLTALARM EWS https://volta.mydewetra.world | The future scenarios are developed and impact on various sectors are visualized and presented to the stakeholders
Output 1.2.3 Impact on environmental indicators is evaluated for current and future scenarios | Progress in terms of impact assessment, designing measures and identification of actors | Lack of strategy and action plans for managing environmental risks in the Volta Basin | Assessment study and data collection related to the present environmental status and ecosystem servcies of the Volta Basin region were completed development of guidance document with the National and Regional stakeholders for integrated basin-wide wetland guidelines to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) Reports available here https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2021/08/VFDM-1236-Draft-General-guidance-July-2021-English.pdf and https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2021/08/VFDM-1236-Draft-Orientations-generales-Juillet-2021-French.pdf Developed one regional bankable project concept note/proposal and identification of financial institution or donors is on-going | A tool-kit is designed and developed for assessing environmental risks for current and future scenarios One bankable National project concept note or proposal will be developed and ready for submission to the financial institute
Outcome 1.3 Risk Management strategies in short, medium and long term to be integrated into development plans (economic, social, environmental aspects) | Participation and training of the relevant stakeholders (Number of women involved) on risk management strategies and action plan | A knowledge tool to integrated risk management strategies into development plans are unavailable for the policy-makers of the Volta Basin countries | •Progress in the development of flood and drought risk prevention and management strategies •Capacity development workshops are planned with 40-50% women participants during November - December 2022 and January 2023 To be measured at the 4th PPR report | Capacity development of relevant stakeholders and assigning roles and responsibilities
Output 1.3.1: Guidance documents for stakeholders are developed to raise awareness about the future scenarios | Guidance document on future scenarios for the Volta Basin region is been developed for the National portion of the Volta Basin or transboundary level | There are no reports or guidance documents available for future scenarios of climate change projections on socio-economic and environment in the Volta Basin region. | On-going and planned to be completed by January 2023 Draft strategy available here: https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/12/Draft_ze%CC%81ro_Risk_Management_Strategy_floods_droughts_projetVFDM_EN-2-1.pdf and https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/12/Draft_ze%CC%81ro_Strategie_gestion_inondation_secheresse_projetVFDM-1.pdf To be measured at the end of the project | Availability of Guidance document for risk-informed decision making on future scenarios due to the climate change projections.
Output 1.3.2: Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | Number of workshops are organized for the dissemination of risk management strategies and action plan for their integration into development plans | National stakeholders lack knowledge and tools to mitigate or manage risks due to Floods and Drought events. | Six national workshops will be organized and conducted by January 2023 to finalize the risk management strategy and validate with the national and regional ministers for integration into their development plans | Atleast one workshop per country will be organised 1 transboundary level consultation workshop with National Focal Points(NFP) An action plan is available with roles and responsibilities of the relevant actors
Outcome 2.1 Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities | Progress in the establishment of Forecasting and EWS for Floods and Drought Number of beneficiaries (male and female – data disaggregated by gender) and regions are identified for forecasting and EWS | Presently, there is a lack of integrated forecasting and early warning systems for both Floods and Drought Agencies and populations are unaware of the relevance and utility of the Forecasting and EWS and how to use it | On-going - Progress in the design and development of the VOLTALARM forecasting and EWS for floods and drought (https://volta.myDewetra.world) integrating existing projects and risk maps, observation stations, static data from the Volta Basin To be measured at the end of the project | The Flood and Drought forecasting and EWS is operational At least 70 % of the Volta Basin region covered by Forecasting and EWS and there are used. More than 60% of the women have direct access to the EWS information
Output 2.1.1 Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | Number of meetings and consultation workshops organised and conducted to understand capacities and needs of the NHS and other stakeholders | There is a lack of skills and knowledge on the forecasting and early warning systems among the local and national staffs | One virtual and one face to face training conducted for understanding the current needs and capacities for the EWS. On-going - assessment on existing capabilities and needs on Hydro-meteorological data and information, models and forecasting tools at the National and Regional levels are carried out 3 distance learning courses on flood and drought EWS were conducted with a total participants of 200 from the Volta Basin countries Design and development of models and forecastig system identified. integration with the national database is on-going To be measured at the end of the project | Meeting and consultation workshop are organised at the national and transboundary level with identification of needs and capabilities
Output 2.1.2 The operational centre for the VoltAlarm Early Warning System is established | Progress in the identification of need and procurement of the resources (equipment’s, staffs etc.) List of sofware and hardware required with technical specifications Tentative list of vendors or suppliers | Presently, there is no real-time Early Warning System for Floods and Drought covering the entire Volta basin region | Progress in the identification of need and resources (equipments, Internet, availability of staffs, software, trainings to be conducted etc) at the National and regional levels for development and functioning of the EWS at the national and regional levels are on-going To be measured and presented with the PPR-IV | The operational centre is established in consultation with NMHSs and Volta Basin Authority
Output 2.1.3 The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | Percentage of data collection, storage and management at National and local level | Hydro-meteo data are not available timely and as well not managed | On-going : study on availability of historical and real-time data and information carried out Identification of any data sharing agreement available at the National and regional level To be measured and presented with the PPR-IV | Compatible data or meta-data are available from the respective countries for flood and drought forecasting and EWS
Output 2.1.4 Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | Progress in the development of thresholds levels for Floods and Drought risks linked with the environmental thresholds | Thresholds levels for the Floods and Drought risks linked with the environmental thresholds are not available for the Volta Basin region | On-going Consultation and capacity development with the national and regional stakeholders To be measured and presented with the PPR-IV | Availability of the thresholds for Floods and Drought risks linked with the environmental thresholds in the Volta Basin region
Output 2.1.5 The procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | Percentage of operationalization of Floods and Drought forecasting at the local and regional centers. | Adequate Floods and Drought Modelling and Forecasts are not available at the local and national levels in the Volta Basin region | On-going Consultation and capacity development with the national and regional stakeholders to define procedure for impact based forecasting To be measured and presented with the PPR-IV | Modeling and Impact based forecasting of Floods and Drought are available at the local and national centres of the Volta Basin region.
Output 2.1.6 The web-based Early Warning dissemination interface for VoltAlarm is designed | Progress in the design and development of the early warning dissemination tool Percentage of the population (men, women, elderly, and youths) understanding the added-value of the early warning system | Currently there are no forecasting and early warning techniques available for the communities and agencies of the Volta Basin region, which can be interpreted easily | Development of the web-based platform with existing data and information (from Global level products and other completed and on-going projects) are incorporated and visualized Visualization of local and national data are on-going To be measured and presented with the PPR-IV | The web-based Early Warning dissemination interface is co-designed and developed so that the early warning information will reach more than 70 % of the communities in the Volta Basin prone to floods and drought events
Output 2.1.7 Knowledge and awareness about VoltAlarm within the user groups are increased | Number of workshops/meetings are organised and conducted to develop capacities of the participants (by Gender) Percentage of the population understands the added-value of the early warning system | Lack of knowledge on forecasting and EWS for Floods and Drought | The project team is demonstrating the designed and developed web-based EWS to the National and Regional stakeholders for receiving feedbacks and suggestions. One regional workshop (Number of women participate: 5 Number of Men participate: 40) and presentation during the 12 national workshops are carried out (total participants: 200) Virtual and face-to-face workshop trainings on the VoltaAlarm EWS are carried out with the local, national and regional stakeholders To be measured at the end of the project | Atleast 1 or 2 workshops/meetings per each country are conducted and participants (communities and agencies) have increased knowledge, awareness and skills.
Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons | Pilot-tests are organised to assess the impact of tools and models developed | Lack of medium and long-term adaptation measures with early warning system. | Finalization of the 10 pilot sites for the testing of the EWS are completed together with the initial consultation To be measured at the end of the project | Atleast one pilot locations of each countries have been tested with developed tool and models
Output 2.2.1 Pilot testing for a number of areas over the basin during the monsoon and dry seasons is performed | Progress in the pilot testing (identification and selection of pilot tests, monitoring during the floods and dry season etc.) of forecasting and EWS Participation of various actors and stakeholders working for Floods and Drought management | Agencies and Communities have limited knowledge about the forecasting and EWS for both Floods and Drought events | Finalization of the pilot sites for the testing of the EWS and identification of relevant stakeholders working on floods and drought management are completed To be measured at end of the project | Pilot testing in atleast one location of each riparian countries More than 80% of the participants benefits from the pilot-testing to understand their roles and responsibilities beneficiaries
Output 2.2.2 Feedback from the series of pilot testing is collected | Workshops are organised and conducted to take feedback and develop capacities of the participants for future events Development of the communication material | Lack of coordination and collaboration between the actors and stakeholders. | To be measured at the end of the project once the pilot testing of the VOLTALARM EWS are completed | Atleast 1 workshop per each country is conducted with local and National stakeholders Success stories, best practices, lessons learned are shared through various social media channels so as to reach a broader audience.
Output 2.2.3 Development and implementation of community-based flood and drought management | Progress in the identification and implementation of the local systems Number of people contributing and benefiting from the local systems | Need for local flood and drought systems empowering the communities for enhanced hazard management | community-based flood and drought management activities in the six sites of the volta basin are completed through local partners. Report and manual available here https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/10/Manual-CBFDM-VB_FinalVersion.pdf and https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/11/VersionFinaleManuel-CBFDM-VB.pdf Total population supported with capacity development trainings and tools: Approximately 5000 Number of women involved: 259 elderly involved: 150 and youths involved : 412 Number of local measures identified, developed: at least 3 on each site Total number of local Hydro-Meteo stations installed: 5 | Atleast one local community in each country has measures and is using the products, tools and methodologies for management of floods and drought events
Outcome 2.3 Strengthened awareness of vulnerable people on hydrometeorological risks, prevention, preparedness, and response strategies through education programs using participatory solutions | Workshops are organised and conducted to develop capacities of the participants Number of women, youths are trained | Lack of tools and awareness on mainstreaming gender and natural and nature-based solutions for flood management | 6 national workshops on IUCN nature-based solutions are completed with the national and local stakeholders Number of national training workshops organised:6 Number of participant (female, male and youths); number of countries representative involved:214 Total number of female participants:51 Total number of Male participants:163 Number of participants successfully completed the NbS trainings:200 One Concept note for the implementation of the identified NbS is available and presently donors are screened for potential financing. 8 national gender mainstreaming workshops are organized in the six Volta Basin countries Number of workshops organized with the National and local stakeholders: 8 (workshops reports are available here https://www.floodmanagement.info/volta-basin/deliverables/ - check activities 2.3.2.2) Number of participants including youths in the 8 country workshops: 209 in total Number of women participants involved in each country: 93 in total | Atleast 1 workshop per each country is organised 1 workshop is organised with national focal points of countries
Output 2.3.1 Knowledge and capacity development using the IUCN standards for nature-based solutions | Number of workshops organised and conducted to develop capacities of the participants Number and type of local and national staffs selected for the training Number of women trained | Lack of knowledge on natural and nature-based solutions for Floods | Based on the initial assessment and reports, the project is now using IUCN standards for the nature-based solution instead of original WWF Flood green guide tool, no changes will be made on the original indicators, baseline and targets to be achieved National stakeholders from hydrology, meteorology, disaster management, environmental agencies, munciplaity, water resources were identified for the training workshops on Nature-based solutions, concept note shared and finalized Number of participant (female, male and youths); number of countries epresentative involved:214 Total number of female participants:51 Total number of Male participants:163 Number of participants successfully completed the trainings:200 Workshop reports are available here https://www.floodmanagement.info/volta-basin/deliverables/ check activity 2.3.1.2 One regional concept note for the implementation of the identified NbS is available and presently donors are screened for potential financing. | Atleast 1 workshop per each country is organised and Nature based solutions are identifed for regions in the country affected by floods and drought
Output 2.3.2 Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management | Workshops are organised and conducted to develop capacities of the participants Percentage of women participating in the workshops with dialogue and advocacy Percentage of women with physical, social, political and economic empowerment | Lack of knowledge on mainstreaming gender in forecasting and early warning system for Floods | Gender mainstreaming workshops are organized in each of the Volta Basin countries Number of participants in each country workshops: 209 in total Number of women participants involved in each country: 93 in total Percentage of women with physical, social, political and economic empowerment still be assessed. To measured at the end of the project | Atleast 1 workshop per each country is organised and mainstreaming Gender is practiced in management of floods events
Outcome 3.1 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin | Workshops and meetings are organised with list of participants from different agencies (by Gender) | Unavailability of decision support system and policies for developing resilience to Floods and Drought | Desk study and consultation with the national stakeholders are carried out to understand the available policies and needs for developing flood and drought resilience National and regional reports are available https://www.floodmanagement.info/volta-basin/deliverables/ (check output 3.1.1) To be measured at the end of the project | A decision support system framework and governance policies are established with the stakeholders
Output 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | Desk study and meetings are organised and available baseline data and information is shared as supporting details Number of policies, plans and guidelines to be revised | Lack of strategic framework and information at the transboundary level for the management of water resources , floods and drought event | Desk study and consultative workshop report is available here https://www.floodmanagement.info/floodmanagement/wp-content/uploads/2022/08/RAPPORT-FINAL-REGIONAL-20-MAI-ABV-2022_PDF.pdf To be measured at the end of the project | The transboundary level information for water resources management, floods and drought management is available The strategic framework at the transboundary level is available in consultation with the stakeholders
Output 3.1.2 Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environmental impact is strengthened | Number of workshops organised and conducted to develop capacities of the participants (decision-makers, policy-makers) Number of women participating in the workshops | Lack of knowledge and tools for the key stakeholders to manage flood and drought events at the transboundary level | To be measured at the end of the project | One workshop at the transboundary level is conducted. The present information gap and key long-term strategies are identified and disseminated
Output 3.1.3 Experiences of local communities on key long term strategies for floods and drought management are collected | Progress in the organising meetings or consultation workshops at local level Number of women, elderly, and youths consulted | Lack of involvement of key-stakeholders in the development of key long term strategies for floods and drought management | To be measured at the end of the project | More than 20 meetings or consultation takes place at various locations of the Volta Basin region. The discussion outcomes are drafted to improve the existing policies, plans etc.
Outcome 3.2 Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies | Workshops are organised and conducted to develop capacities of the participants Number of documents reviewed and discussed | Limited knowledge of transboundary policies, plans and guidelines for the key actors to manage risks | To be measured at the end of the project | The available policies, plans and guidelines are used and key long-term strategies are implemented
Output 3.2.1 Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to risk reduction and Early Warning System (EWS) | Number of transboundary consultative workshop organised with the policy-makers and advisors Number of documents reviewed and discussed Number of women participants | Limited knowledge and implementation of action plans, policies and guidelines for the risk management | To be measured at the end of the project | One transboundary consultative workshop is conducted with participants from each country of Volta Basin Climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to flood and drought risk reduction and the Early Warning System are revised or developed and shared with the stakeholders for their approval
Output 3.2.2 Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme (SAP) | Consultative meetings are organised so that new or existing plans, polices and guidelines on climate change adaptation and disaster risks management are integrated into the transboundary SAP. | There is lack of integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | To be measured at end of the project | Improved integration of national policies on risk reduction and climate adaptation into the Transboundary Strategic Action Programme (SAP) resulting in better management of water resources and flood and drought events at the national and transboundary level
Outcome 3.3 A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context | Collaboration meeting is organised with the stakeholders (including community representatives, associations and civil authorities) Number of men, women, elderly, and youths consulted | Lack of consultation and collaboration with the direct and in-direct beneficiaries on the instrument and strategies for climate change risk management | To be measured at the end of the project | Atleast 2-3 meetings in each of the Volta Basin countries are conducted and measures and plans are adapted to the local context
Outcome 3.3.1 Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | Number of meetings organised with the communities and organizations (NGO's, associations etc.) Number of men, women, elderly, and youths consulted | Communities knowledge and experience are not involved in the development of the policies and action plans for managing risks and climate change adaptation | To be measured at the end of the project | Workshops/meetings are conducted and participants are provided with opportunities to share their views and perceptions on the policies and action plans Communities and organizations involvement in the designing and implementation of action plans is drafted
Output 3.3.2 Collaboration with local communities and organizations in finalising the policies, plans and further adopting to manage risks | Number of meetings organised with the communities and organizations Number of men, women, elderly, and youths consulted | Communities are not consulted and involved in the refining of the policies and action plans for managing risks and climate change adaptation | To be measured at the end of the project | Meeting for reviewing and finalizing is conducted and approval or necessary changes suggested by the participants are considered

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - As the VFDM project activities continues to be implemented in the third year, several consultation meetings at the regional and national level with the stakeholders were organized for adequate planning and coordination of the activities. With six targeted countries, there are multiple stakeholders in each countries who need to be involved in most of the activities but some agencies are required for specific activities such as environment agencies, sustainable development, statistics office etc. The communication is often inefficient and information exchange with the executive entities (Volta Basin Autority, Global Water Partnership West Africa and WMO) hampered by national interests. - During the third year, Integration with other ongoing regional projects like the World-Bank funded HYDROMET project in Burkina Faso, the multi-country financed CREWS West Africa initiative or FANFAR was strengthened and visualized in the interest of capitalizing on previous efforts and boosting efficiency of implementation. - The project activities escpecially workshops and training sessions are providing opportunity to bring together various stakeholders at the National, local and regional levels to participate and contribute to the development of deliverables and outcomes of the project. Also, these sessions provides an opportunity for the participants to better understand their roles and repsonsibilities within the project. Also, it provide a way to have dialogue and discussion with other agencies who are involved in the project activities. Through these project related sessions, it was possible that many participants from the National agencies could identify a way to collaborate and build cooperation for the joint project activities (and also beyond the scope of the project) with other Agencies focal points.Some of the critical decisions are unfortunately not being taken jointly by the project technical advisory committee, as each country seeks to take independent decisions based on their particular needs and experience. A considerable gender imbalance still exists at all levels, albeit some progress to improve this situation has been achieved. The imbalance is especially noticeable at the national agencies and at the regional coordination level, less so at the community level. There is an overall lack of conscience at the regional executive entity level and at national hydrometeorological agencies, concerning the fact that ownership of observing equipment sponsored by the project needs to be transferred to national agencies and needs to be maintained and integrated into national networks. - The project is executed by three partners namely WMO, VBA, and GWP-WA. Each of the entities has their respective National focal points and when sharing project information., it was challenging initially to reach out to all the respective focal points. However, coordination at both regional and national levels among project partners and stakeholders are fully established now (a working group of 3-4 individuals are formed at the National level who will provide technical and coordination support) and it will be crucial for project success in the remianing duration. - Due to the covid situation, at National and local levels, staff were not allowed to work from office (instead working from home). This resulted in delays for receiving data and information from them as they were not having remote access to their servers or databases. - The project is mainly Nationally focussed and driven and involves consultation, engagement, and agreement with various national and sub-national stakeholders. These engagements sometimes take time and can result in delays, however, they are necessary to ensure sustainability, ownership, and ultimate success of the project. - One of the six countries is English speaking and others are francophone. So all the concept notes, ToR, and other reporting documents are developed in both English and the French language in order to ensure National stakeholders are provided documents in their respective language and their continuous support and participation are received. This sometimes causes a delay in the implementation of the activities. - The involvement of stakeholders from different National agencies requires proper coordination and support in terms of defining proper roles and responsibilities to each of them.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were minor delays in project implementation largely due to the following factors: 1) Development of detailed work plan for the third year and agreement with the implementing partners took more time than expected, which caused a delay in starting the implementation of the third year project activities including partial pending activities of first and second year. 2) As there are on-going projects in the countries on the similar themes ( CREWS, World Bank Hydromet projects etc.), sometimes getting a time for organizing workshops with right stakeholders is not possible as they are occupied with other work responsibilities. For this, the project team has to wait for having their availabilities for the workshops and results in delay. It is important to ensure we have right stakeholders (techncial and decision makers) so as to have discussion , agreements and joint follow-up actions. 3) Due to the continous COVID-19 outbreak globally, many of the planned has to be postponed or moved to the second and third year of the project as there were travel restrictions to the project countries. or instance, the shipment and installation of equipmentwas (hydro-meteorological observing stations) was considerably delayed. At a different note, the pandemic also caused some workshops and activities to take place only online. While local NGOs still could travel to rural places, support by external (international) technical partners (e.g. K&I) to local communities could only occur online. Nevertheless, besides the pandemic, some delays are caused by slow progress at the institutional level. This concerns the availabiulity of data to set up the VOLTALARM system as well as the decision process on how to manage and operate the system 4) Some of the activities or training sessions were conducted virtually especially for the community-based flood and drought management, risk mapping. However the local NGOs or consultant were trained virtually to practice and test methodology together so that they learn from each other. This took additional time for better understanding of the work to be carried out. Measures are taken to reduce delays: 1) Workplan and agreements were developed by Implementing Partner and shared with the executing and technical implementing partners. The IE requested the partners to provide quick feedbacks and agreement on the implementation of activities including budgeting. 2) The project stakeholders are always informed that the VFDM project is building synergies and complementarities with other on-going initiatives or projects. It is important that VFDM stakeholders inform the other project focal points about the work carried out or planned for future in order to avoid duplication of efforts. 3) The Project Team continued working virtually at both regional levels as well as with National stakeholders so that some works such as finalization of reports, concept note, or ToR could be completed (which does not require travel) . Virtual meetings were organized with the National and local stakeholders for some trainings and later pilot testing of methodology was conducted to better learn the methodology and tools developed.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes have been made to project Outputs at the moment. The development of flood and drought monitoring and forecasting systems initially scheduled for Year 2, has been moved to Year 3 after informing and discussing with EEs and stakeholders, who agreed that the implementation would best be conducted in Year 3 once the capacity assessments, existing information, and methodologies are identified.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | For the activities undertaken to date, the environmental and social safeguards measures have been adequate and as yet no negative impacts have emerged. The stakeholders are made aware of any risks which could arise from the implementation. They need to ensure right processes, laws, involvement of participants are taken into consideration during planning. The major delays were caused by external factors (due to the Covid-19 situation and civil security issues) beyond the control of the project partners.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | There is a considerable gender imbalance at the level of regional and national technical agencies. To the contrary, female involvement in activities on climate adaptation measures (e.g. nature-based solutions) at the level of rural or urban communities, is much more balanced (1/3 to 1/2 of participants are female). There is also a clear difference between socal science and technical professions, with women represented much stronger in the former. The lack of women in technical professions at the level of national and regional agencies is mainly attributable to less women following science or technology study curricula across all Volta basin countries. As a result, there exist less female candidates for recruitment in technical professions. Albeit there is awareness of this issue among the project executive entities, however problem is not rapidly solveable as there is a prior need of preparing more women in technical and scientific disciplines. Another non-negligible reason for female underepresentation in responsibility positions, especially at the community level, are of cultural type. The project partners have undertaken the following measures in relation to gender considerations in the VFDM project until the PPR-3 report: - ToR for hiring gender experts were reviewed by WMO gender experts and had the inclusion of profiles from the Volta Basin region, - The project team aimed for having 50% participation of men and women in all the consultation meetings, training, and project activities at ground level (including as participants and trainers). Howvwe most of the cases its was not possible - The project team ensured equal participation of men and women in institutions and decision-making processes related to the project. However, it is not always possible to ensure equal participation of men and women in some technical activities due to lack of technical background or expertise, social and cultural barriers existing in the countries, however, efforts for such are being made. Some lessons emerging from the project relating to gender include the following: - Based on the implementation experience, women in the Volta Basin are participating in training workshops and decision-making processes and want to be part of the development of resilience in some of the regions.The project has taken commitment from the decision makers to involve women groups in mainstreaming gender into E2E-EWS-FF as well as ensure budgets are allocated for their participation. - At the national levels, project is providing products and services for managing extreme events.Very few countries have female staffs in their Hydrological and Meteorological services. Hopefully this will be improved now after completion of the National workshops on mainstreaming gender in E2E-EWS-Floods and Integrated flood management. To keep track of issues and lessons learned over the course of the project, the MTE for the project included questions disaggregated by gender as well as gender-specific questions on the impacts (positive and negative of project activities. - The number of staff trained to use VOLTALARM EWS and issue impact-based warnings on the impact of, climate-related events (by gender). - Percentage of women, girls, and youths receiving timely early warnings for floods and drought events and the associated impacts - Percentage of local volunteers (male and female) who are integrating disaster risk reduction and adaptation strategies at the community level - Number of women being part of decision-making team at local, national and regional levels. - Number of youths sessions for taking study in STEM related subjects including hydrological, meteorological, disaster management etc.) The responses are available in the MTE report presented at the Adaptation Fund website: https://www.adaptation-fund.org/projects-document-view/?URL=https://spxdocs/en/081140008012217177/6324_MTE%20report_draft-final-UK_VFDM%20.pdf
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Based on the MTE conducted in March 2022, the cooperation among national agencies involved with climate adaptation and impacts within each country requires dissemination of information through planned workshops for agencies within single countries or in the region (this is part of component 2 of the project - pilot testing of the VOLTALARM EWS in the 10 sites). Similarly, it is important to strengthen the collaboration between the national level and the community level (local NGOs and local communities), while ensuring effective involvement of civil society (GWPAO national representations in the 6 countries, the Red Cross, etc.) and civil protection services. National partners (meteorology and hydrology) need to be well prepared in the selection of the technical characteristics of hydro-meteorological measurement equipment and their regular maintenance, to effectively integrate the equipment into the existing national network. Systems must be selected as to make countries autonomous in the management of the early warning system after project wrap-up. Follow-up and maintenance costs should be minimized and made available by each country. Project impact can be increased through intervention of local NGOs, by adressing the difficulties related to agricultural activities and considered a priority by the communities. Difficulties include lack of risk knoweldge, unaware of climate change adaptation measures, losses in agricultural yields, access to seeds, cultivation techniques to counteract the effects of drought, agricultural finance and the fight against diseases that ravage livestock. Note - to be filled also at the project completion.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Baes on the MTE, Climate resilience measures are mostly dependent on local geographic and climatic as well as social conditions. The particular measures proposed in the VFDM are mostly applicable in similar subsaharian contexts. The activity at the regional level, such as data aquisition and exchange as well as the implementation of early warning systems are part of trans-boundary water management practices, in line with UN sustainble development goal SDG 6.5, and therefore upscalable/applicable also outside of the project area.One of the example of the project scaling up is the Burkina faso national hydro-met project is looking for expanding the EWS and risk maps to cover outside the National portion of the Volta Basin region in Burkina Faso (discussion is still on-going). N/A - to be filled also at project completion.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Projects have a greater impact at the rural community level, with interventions made by the local NGOs. These have the capability in particular with respect to climate vulnerability and adaptation in agricultural activities, which they consider prioritarian. Such vulnerabilities include loss of lives, agricultural yields, access to seeds for sowing, particular cultivation techniques to counter the effects of drought, agricultural credits and the fight against diseases that ravage livestock. During the community based activities, communities are trained and made aware of flood level markings in the community. Considering the flood warning marking together with the warning messages from the local authorities, communities can carry out evacutaion to the safer places. Flood marking are also used for raising the level of houses (for future construction). In future meteorological warnings will be useful in understanding the crop changing patterns, timely cutting and drying of crops etc. which will be useful for livelihood and economical activities. Note- to be filled also at the project completion.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The particular climate-adaptating interventions at the community level are strongly dependent on local geographical circumstances and can therefore be replicatd and upscaled mostly in environments similar to the project region. The interventions undertaken at the national or the regional level can be replicated also outside the project area, as they concern transboundary water resources management in accordance with the UN sustainable development goals. Note- to be filled also at the project completion.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | a) The effectve building of capacities and the raising of awareness of climate change impacts to enhance resilience at the level of local communities. b) The attempt to integrate data flows form the basin states at the regional level for improving forecasting capabilities and better coordinate hazard impact mitigation activities c) gender mainstreaming in E2E-EWS-FF and IFM, d) Awareness on nature-based solutions for flood and drought management and most importantly, availability of warning information through the concrete and innovative EWS which includes risk maps for the impact based forecasting. Note- to be filled also at the project completion.
What measures are/have been put in place to ensure sustainability of the project/program results? | Knowledge transfer and education belong to the most sustainable low-cost forms of adaptation measures.Commitment at the regional and national levels to continue providing data and operation of the VOLTALARM EWS. Partnerships (collaboration and coordination at the local, national and regional levels) , transfer of knowledge and sharing of experiences and lesson learned are keys for long term sustainability. Note- to be filled also at the project completion.
What measures are being/could have been put in place to improve project/program results? | All measures that have been put in place have been quite sucessful to improve project results. However, resources availability (high speed internet, national staffs, infrastruture, investement throught the national budget) would create more impacts. However these needs are informed through dialogue, reports and policy documents to the decision makers. Note- to be filled also at the project completion.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | In the interest of long-term sustainability and appropriation of systems by the target countries, it must be ensured that these become as autonomous as possible in the management of the VOLTALARM system after project wrap up. One key is using license-free or low-cost software for data transmission and administration which is presently the system which is made available to the project countries. National hydro-meteorological data and information have been requested to the countries for the development of the EWS which will inturn provide accurate and timely warning (which is quite note possible with only satellite information and products). Risk maps have been developed jointly with the support of National staffs as well as using local and national social, structural and hydro-meteorological information provided by the national agencies. While meterological services are generally well equipped due to their services to commercial aviation, hydological services, which are essential for water resources assesment and flood warning, are under-equipped and poorly functional. Climate adaptation interventions require a clear focus on strenghtening the water resources component of national services. Projects have a greater impact at the rural community level, if these are targeted through interventions of local NGOs. These have the capability in particular with respect to climate vulnerability in agricultural activities, which they consider prioritarian. Such vulnerabilities include loss of agricultural yields, access to seeds for sowing, particular cultivation or honey bee restoration techniques to counter the effects of drought, agricultural credits and the fight against diseases that ravage livestock. Note- to be filled also at the project completion.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Risk maps have been developed jointly with the support of National staffs as well as using the available local and national social, structural and hydro-meteorological information provided by the national agencies. Risk maps together with other hydro-meteorological products have been made available to the NMHSs, civil protection and water resources agencies to timely analyze the floods and drought situation and disseminate the warning to the local population. N/A - to be filled also at the project completion.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | Knowledge products generated by the project are published on the project web portal and are accessible at https://www.floodmanagement.info/volta-basin/deliverables/knowledge-and-learning/, news item: https://www.floodmanagement.info/category/volta-basin/news-events/, press release: https://www.floodmanagement.info/volta-basin/press-room/. The knowledge sharing products includes mainly reports and GIS maps as well as a flood forecasting platform https://www.floodmanagement.info/volta-basin/deliverables/. N/A - to be filled also at the project completion.
If learning objectives have been established, have they been met? Please describe. | Various training and capaicty dveelopment sessions were organized for the development of risk maps. Following the training, national technicians provided in-kind contribution in the development of the vulnerability, exposure maps which were useful for the risk maps development.N/A - to be filled also at the project completion.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | All available geographical information to define areas vulnerable to climatic hazards has been made available by the national agencies. At the time of the MTE however, there was no clear vision on the extent that hydrometerological data would be shared by the states for the operation of the myDEWETRA VOLTALARM platform. The project has been requesting the sharing of the real time data and the discussion between the agencies are on-going. Once the national centralized database is established, countries will be trained for the using of the open and free database. Also MoU will be signed between different national entities to share the real-time data at this centralized database. N/A - to be filled also at the project completion.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project involved national and local stakeholders in the development of the risk maps through collection of hydro-meteorological data, development of GIS layers on exposure and vulnerabilities, etc. Following these capacity development trainings, the risk maps and climate scenarios (one of the major outcomes) were successfully developed and visualized for the entire Volta Basin region.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The development and installation of the VOLTALARM EWS is a clear technological innovation for Volta basin transboundary flood and drought management. This innovative tool can provide support in monitoring and forecasting of the floods and drought events at the same time in the country (it is observed that in several countries at one time of the year, there is a flood situation in one part and drought situation in another part so there is a need for a integrated approach to flood and drought warning services). N/A - to be filled also at the project completion.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A - to be filled at the project completion.
Yes
No
N/A - to be filled at the project completion.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | World Meteorological Organization(WMO)
Type of implementing entity | MIE
Country | Benin, Burkina Faso, Cote d'Ivoire, Ghana, Mali and Togo
Region | Africa
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 100000 | 30000 | 70000 | Total | 20000 | 1000 | 19000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 30% | 30% | 30% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 100000 | Inland flooding | 5: Very effective | Total | 100000 | Inland flooding | 5: Very effective | Total | 20000 | Inland flooding | 4: Effective | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 30% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 10 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated | 10 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated | 12 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 200 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 200 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 200 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 4: Response capability | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 200 |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Disaster risk reduction | 3: Medium capacity | Total | 1000 | Disaster risk reduction | 3: Medium capacity | Total | 200 | Disaster risk reduction | 3: Medium capacity | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 0.4% |  |  | % of female targeted | 30% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 100 | 50% | Public |  | 100 | 40% | Public |  | 300 | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Disaster risk reduction | 3: Medium capacity | Public | National | Disaster risk reduction | 3: Medium capacity | Public | National | Disaster risk reduction | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 30 | National | DRR | 3: Medium capacity | 100 | National | DRR | 3: Medium capacity | 200 | National | DRR | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 40% |  | Disaster risk reduction |  | 40 |  | Disaster risk reduction |  | 20 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 50000 | 50% | 4: Mostly aware |  | 50000 | 50% | 4: Mostly aware |  | 5000 | 30% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 20 | 40% to 60% | 4: Mostly aware |  | 20 | 40% to 60% | 4: Mostly aware |  | 30 | 20% to 39% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 20 | technical guidelines | National |  | 20 | Technical guidelines | National |  | 10 | Training manuals | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | National | 4: Mostly responsive (Most defined elements) |  | Disaster risk reduction | National | 4: Mostly responsive (Most defined elements) |  | Disaster risk reduction | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 20 | National |  | Disaster risk reduction | 20 | National |  | Disaster risk reduction | 10 | National |  | Disaster risk reduction
|  | 10 | Departmental |  | Disaster risk reduction | 10 | Departmental |  | Disaster risk reduction | 10 | Departmental |  | Disaster risk reduction
|  | 10 | Community |  | Disaster risk reduction | 10 | Community |  | Disaster risk reduction | 6 | Community |  | Disaster risk reduction
|  | 10 | Community |  | Agriculture | 10 | Community |  | Agriculture | 6 | Community |  | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Disaster risk reduction | biological assets | 3: Moderately effective |  | Disaster risk reduction | biological assets | 3: Moderately effective |  | Disaster risk reduction | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 5 | km protected | 4: Effective | Mangroves | 10 | km protected | 4: Effective | Mangroves | 1 | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 1 | km protected | 3: Moderately effective | Protected areas/National parks | 10 | km protected | 3: Moderately effective | Protected areas/National parks | 1 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 5 | km protected | 4: Effective | Forests | 10 | km protected | 4: Effective | Forests | 1 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 5 | km protected | 2: Partially effective | Cultivated land/Agricultural land | 10 | km protected | 2: Partially effective | Cultivated land/Agricultural land | 1 | km protected | 2: Partially effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 10000 | 30% | 4: High improvement |  | 10000 | 30% | 4: High improvement |  | 1000 | 10% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 10000 | 30% | From 10% to 20% | Agricultural-related | 10000 | 30% | From 40% to 50% | Agricultural-related | 1000 | 10% | From 10% to 20% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 5000 | 40% | From 10% to 20% | Construction/repairing business | 5000 | 40% | From 40% to 50% | Construction/repairing business | 1000 | 10% | From 1% to 5% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 10000 | 40% | From 10% to 20% | Services | 10000 | 40% | From 40% to 50% | Services | 1000 | 10% | From 0.5 to 1% | Services
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 10000 | 40% | From 10% to 20% | Cultivation | 10000 | 40% | From 40% to 50% | Cultivation | 1000 | 10% | From 0.5 to 1% | Services
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Disaster risk reduction | Supporting livelihoods | 10 | Adaptation strategies | Disaster risk reduction | Supporting livelihoods | 1 | Adaptation strategies | Urban development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50000 | Agribusiness |  | 1000 | 50000 | Agribusiness |  | 1000 | 1000 | Agricultural-related |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD)p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20000 | Services |  | 1000 | 20000 | Services |  | 1000 | 1000 | Agriculture |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD)p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20000 | Fishing |  | 1000 | 20000 | Fishing |  | 1000 | 100 | Fishing |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD)p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20000 | Agriculture |  | 1000 | 20000 | Agriculture |  | 1000 | 100 | Agribusiness |  | 100
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 13 | Disaster risk reduction | National | Communication & Information policy | 13 | Disaster risk reduction | National | Social policy | 1 | Disaster risk reduction | Regional | Social policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 20 | 4: Enforced (Most elements implemented) |  | 4: Effective | 20 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 1: Not enforced (No elements implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Disaster risk reduction | National | Innovation accelerated |  | Disaster risk reduction | National | Innovation accelerated |  | Disaster risk reduction | Regional | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 13 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 13 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 20 | Innovative product |  | 4: Effective | 20 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 2: Partially effective
Note on K21: Ramesh TRIPATHI: Some activiites like risk maps and EWS development can benefit several million population in directly
Note on E55: Ramesh TRIPATHI: No of female working at the National Agencies is not equal to the number of male
Note on E71: Ramesh TRIPATHI: training manual, tools, guidelines, policy and action plan documents will be prepared
Note on F71: Ramesh TRIPATHI:for all levels-regional, national and local