## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | From 01st January to 6th June 2022
| Project Title: | Akamatutu'anga kia Tukatau te Ora'anga I te Pa Enua (PA ENUA ACTION FOR RESILIENT LIVELIHOODS (PEARL)
| Project Summary: | The objective of the programme is to build and implement an integrated approach to further increase the adaptive capacity of remote island communities and ecosystems to disaster risk and climate change impacts through the following: * Strengthening national and local capacity for monitoring and decision making to respond and to reduce risks associated with climate change * Establishing climate resilient water management instruments using integrated and community based approach *Raising awareness and establish a knowledge exchange platform to increase adaptive capacity to revitalise agriculture production systems
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | COK/NIE/Multi/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Finance and Economic Management | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cook Islands | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Cook Islands / Asia-Pacific | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
AFB Approval Date: |  | 2018-03-22
IE-AFB Agreement Signature Date: |  | 2018-05-15 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-12-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
2021-12-06
Original Completion Date:
Revised Completion Date after approval of |  | 2022-06-06
extension request (if applicable)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Other
| Condition or Requirement | Board Decision B.35b/16, six-months no-cost extension of the Project completion date
| Current Status | Condition met and cleared by the AFB Sec
| Planned actions, including a detailed time schedule | Project budget reallocations as part of the new project completion date and annual project performance report
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Request for extension of PEARL Project completion date - February 04, 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.facebook.com/DCDivision #developcookislands, #AdaptationFund | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Emily Pierre-OaAriki | Dominican Republic
| Email: | emily.pierre@cookislands.gov.ck | Ecuador
| Date: | 2022-06-06 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ministry of Foreign Affairs and Immigration | Equatorial Guinea
| Email: | tepaeru.herrmann@cookislands.gov.ck | Eritrea
| Date: | 2022-06-06 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Finance and Economic Management | Fiji
| Email: | emily.pierre@cookislands.co.ck | Finland
| Date: | 2022-06-06 | France
| Executing Agency |  | Gambia
| Name: | Climate Change Cook Islands | Georgia
| Email: | melina.tuiravakai@cookislands.gov.ck | Germany
| Date: | 2022-06-06 | Ghana
| Executing Agency |  | Greece
| Name: | Emergency Management Cook Islands | Grenada
| Email: | lydia.sijp@cookislands.gov.ck | Guatemala
| Date: | 2022-06-06 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Infrastructure Cook Islands | Guyana
| Email: | otheniel.tangianau@cookislands.gov.ck | Haiti
| Date: | 2022-06-06 | Honduras
| Executing Agency |  | Guinea Bissau
| Name: | Ministry of Agriculture | Guyana
| Email: | puna.kamoe@cookislands.gov.ck | Haiti
| Date: | 2022-06-06 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to December 31st 2019 |  |  |  | Financial information PPR 2: cumulative from project start to December 31st 2020 |  |  |  | Financial information PPR 3: cumulative from project start to 31 December 2021 |  |  |  | Financial information PPR 4: cumulative from project start to 6 June 2022
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31st December 2019 | 581595 |  |  | Estimated cumulative total disbursement as of 31 December 2020 | 1286170.3 |  |  | Estimated cumulative total disbursement as of 31 December 2021 | 2795131.11 |  |  | Estimated cumulative total disbursement as of 6 June 2022 | 2908504.73
Add any comments on AF Grant Funds. (word limit=200) | Undisbursed amount as at 31st December 2019: US$759,845.00 Some delays were experienced in project implementation under the following components which has impacted on the projected spends in Year 1: Component 1: Undisbursed amount of US$83,783 due to activities under Output 1 and Output 2 not being able to be carried out due to shipping and travel constraints to the Northern Group islands. These activities are scheduled to be conducted in Year 2. Component 2: Undisbursed amount of US$52,870 is due to travel constraints to the Northern Gorup islands to implement activities under Output 1 on the drafting of the water security policy. Furthermore, funds committed under Output 2 for water making desalination is delayed to be able to procure the most suitable plant. Discussions on specifications are ongoing and desalination equipment expected to be procurred in Year 2 or 3. Component 3:The bulk of undisbursed amount of US$343,586 is related to Output 2; Schools gardens for the Northern Group Islands. Shipping and travel constraints have also played a major part in delays to having this project started in the Northern Group. Procurement of equipment for each of the Northern Islands schools have begun however storage space prior to shipment have meant that major equipment cannot be purchased during Year 1. Discussions with Shipping Company is ongoing with the hope that passage to the Northern islands will be available in Year 2 to start the implmentation of this project. |  |  | Add any comments on AF Grant Funds. (word limit=200) | Undisbursed amount as at 31 December 2020: US$1,178,952 COVID19's unprecedented impacts continue to wreak havoc around the world and the PEARL Project's contingent plans have required a request to extend the Project's completion date (approved in March 2021) and reprogramming of activities and the Annual Work Plan for the year2021. Reopening of the domestic borders and limited international logistic and supply chain services have enabled negotiations with the service providers and the resumption of Project activities in the pa enua. |  |  | Add any comments on AF Grant Funds. (word limit=200) | Undisbursed amount as at 31 December 2021: US$205,521 The nation and the Project continues to feel the constraints and challenges imposed across the board due to the COVID19 pandemic. Adaptive measures by the AF Board of a blanket no cost extension of project completion of up to 12 months due to COVID have helped to buy time for the PEARL Project to try and complete the remaining project activities. |  |  | Add any comments on AF Grant Funds. (word limit=200) | This is the final PPR for the PEARL project and the reported cumulative total disbursement is up to 6 June 2022 - the completion date of the Project.
[9 empty] | . |  |  |  | . |  |  | 1654.8488
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | NIL |  |  | INVESTMENT INCOME | 1527 |  |  | INVESTMENT INCOME | 127.8488
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1 | 101314.8557 |  |  | Component 1 | 135202.11 |  |  | Component 1 | 287398.9495 |  |  | Component 1 | 3723.05
| Component Administration | 37738.13 |  |  | Component Administration | 17728.64 |  |  | Component Administration | 61666.2215 |  |  | Component Administration
| Output 1.1.1 | 33690.6078 |  |  | Output 1.1.1 | 29209.29 |  |  | Output 1.1.1 | 79677.3114 |  |  | Output 1.1.1 | 3723.05
| Output 1.1.2 | 268.9521 |  |  | Output 1.1.2 | 10312.93 |  |  | Output 1.1.2 | 22885.0798 |  |  | Output 1.1.2
| Output 1.2.1 | 0 |  |  | Output 1.2.1 | 0 |  |  | Output 1.2.1 | 0 |  |  | Output 1.2.1
| Output 1.2.2 | 0 |  |  | Output 1.2.2 | 0 |  |  | Output 1.2.2 | 9669.9471 |  |  | Output 1.2.2
| Output 1.2.3 | 0 |  |  | Output 1.2.3 | 45859.2 |  |  | Output 1.2.3 | 16902.505 |  |  | Output 1.2.3
| Output 1.3.1 | 3152.1286 |  |  | Output 1.3.1 | 4620.01 |  |  | Output 1.3.1 | 22047.8607 |  |  | Output 1.3.1
| Output 1.3.2 | 26465.0372 |  |  | Output 1.3.2 | 14657.58 |  |  | Output 1.3.2 | 44670.7836 |  |  | Output 1.3.2
| Output 1.3.3 | 0 |  |  | Output 1.3.3 | 12814.46 |  |  | Output 1.3.3 | 29879.2404 |  |  | Output 1.3.3
| Component 2 | 116853.9722 |  |  | Component 2 | 213834.1 |  |  | Component 2 | 385824.0395 |  |  | Component 2 | 8132.17
| Component Administration | 28611.87 |  |  | Component Administration | 13676.83 |  |  | Component Administration | 30333.8389 |  |  | Component Administration | 1684.89
| Output 2.1.1 | 25458.4982 |  |  | Output 2.1.1 | 21793.27 |  |  | Output 2.1.1 | 28295.3556 |  |  | Output 2.1.1 | 5302.16
| Output 2.1.2 | 0 |  |  | Output 2.1.2 | 0 |  |  | Output 2.1.2 | 874.9532 |  |  | Output 2.1.2
| Output 2.1.3 | 48409.0623 |  |  | Output 2.1.3 | 31536.28 |  |  | Output 2.1.3 | 10691.8595 |  |  | Output 2.1.3
| Output 2.2.1 | 0 |  |  | Output 2.2.1 | 15248.68 |  |  | Output 2.2.1 | 13801.0016 |  |  | Output 2.2.1
| Output 2.2.2 | 11443.1742 |  |  | Output 2.2.2 | 0 |  |  | Output 2.2.2 | 3395.3738 |  |  | Output 2.2.2
| Output 2.2.3 | 2657.0875 |  |  | Output 2.2.3 | 500.56 |  |  | Output 2.2.3 | 86059.4642 |  |  | Output 2.2.3 | 1145.12
| Output 2.3.1 | 0 |  |  | Output 2.3.1 | 0 |  |  | Output 2.3.1 | 0 |  |  | Output 2.3.1
| Output 2.3.2 | 0 |  |  | Output 2.3.2 | 0 |  |  | Output 2.3.2 | 0 |  |  | Output 2.3.2
| Output 2.3.3 | 274.28 |  |  | Output 2.3.3 | 0 |  |  | Output 2.3.3 | 514.275 |  |  | Output 2.3.3
| Output 2.3.4 | 0 |  |  | Output 2.3.4 | 131078.48 |  |  | Output 2.3.4 | 211857.9176 |  |  | Output 2.3.4
| Component 3 | 239658.2274 |  |  | Component 3 | 277252.2304 |  |  | Component 3 | 669296.5337 |  |  | Component 3 | 48469.14
| Component Administration | 28379.26 |  |  | Component Administration | 16863.71 |  |  | Component Administration | 23878.9814 |  |  | Component Administration | 8526.21
| Output 3.1.1 | 8228.4 |  |  | Output 3.1.1 | 9653.77 |  |  | Output 3.1.1 | 6959.087 |  |  | Output 3.1.1 | 894.74
| Output 3.1.2 | 43473.572 |  |  | Output 3.1.2 | 18014.71 |  |  | Output 3.1.2 | 11628.6972 |  |  | Output 3.1.2 | 0
| Output 3.1.3 | 70925.5852 |  |  | Output 3.1.3 | 55268.57 |  |  | Output 3.1.3 | 30541.1603 |  |  | Output 3.1.3 | 1313.64
| Output 3.2.1 | 6100.9335 |  |  | Output 3.2.1 | 3184.42 |  |  | Output 3.2.1 | 19665.3617 |  |  | Output 3.2.1 | 21254.87
| Output 3.2.2 | 54694.2777 |  |  | Output 3.2.2 | 58070.7947 |  |  | Output 3.2.2 | 222421.5444 |  |  | Output 3.2.2 | 0
| Output 3.2.3 | 0 |  |  | Output 3.2.3 | 0 |  |  | Output 3.2.3 | 0 |  |  | Output 3.2.3 | 0
| Output 3.3.1 | 5610.3974 |  |  | Output 3.3.1 | 7452.1876 |  |  | Output 3.3.1 | 0 |  |  | Output 3.3.1 | 0
| Output 3.3.2 | 7916.2899 |  |  | Output 3.3.2 | 2249.1 |  |  | Output 3.3.2 | 1748.535 |  |  | Output 3.3.2 | 0
| Output 3.3.3 | 0 |  |  | Output 3.3.3 | 79921.6881 |  |  | Output 3.3.3 | 81059.1478 |  |  | Output 3.3.3 | 0
| Output 3.3.4 | 0 |  |  | Output 3.3.4 | 0 |  |  | Output 3.3.4 | 111990.3822 |  |  | Output 3.3.4 | 0
| Output 3.4.1 | 13380.4549 |  |  | Output 3.4.1 | 11190.62 |  |  | Output 3.4.1 | 0 |  |  | Output 3.4.1 | 4327.67
| Output 3.4.2 | 674.7768 |  |  | Output 3.4.2 | 0 |  |  | Output 3.4.2 | 1668.3081 |  |  | Output 3.4.2 | 6387.33
| Output 3.5.1 | 0 |  |  | Output 3.5.1 | 0 |  |  | Output 3.5.1 | 0 |  |  | Output 3.5.1 | 0
| Output 3.5.2 | 0 |  |  | Output 3.5.2 | 0 |  |  | Output 3.5.2 | 0 |  |  | Output 3.5.2 | 0
| Output 3.5.3 | 274.28 |  |  | Output 3.5.3 | 0 |  |  | Output 3.5.3 | 600.6732 |  |  | Output 3.5.3 | 0
| Output 3.5.4 | 0 |  |  | Output 3.5.4 | 15382.66 |  |  | Output 3.5.4 | 157134.6554 |  |  | Output 3.5.4 | 5764.68
| Component 4 | 123768.49 |  |  | Component 4 | 78286.3141 |  |  | Component 4 | 166441.2913 |  |  | Component 4 | 53049.26
| Implementing entity oversight cost | 69761.24 |  |  | Implementing entity oversight cost | 48750.1706 |  |  | Implementing entity oversight cost | 88117.7367 |  |  | Implementing entity oversight cost | 17658.85
| Project Execution Cost | 54007.25 |  |  | Project Execution Cost | 29536.1435 |  |  | Project Execution Cost | 78323.5545 |  |  | Project Execution Cost | 35390.41
| TOTAL | 581595.5453 |  |  | TOTAL | 704574.7546 |  |  | TOTAL | 1508960.8141 |  |  | TOTAL | 113373.62
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 | 227353.57 |  |  | Component 1 | 293237.03 |  |  | Component 1 | 5209.96 |  |  | Component 1 | 0
| Component Administration | 30856.5 | 31.12.21 |  | Component Administration | 61771.24 | 31.12.21 |  | Component Administration |  |  |  | Component Administration
| Output 1.1.1 | 62707.27 | 31.12.21 |  | Output 1.1.1 | 96167.1 | 31.12.21 |  | Output 1.1.1 | 5209.96 | 31.01.22 |  | Output 1.1.1
| Output 1.1.2 | 10491.21 | 31.12.20 |  | Output 1.1.2 | 22925.12 | 31.12.21 |  | Output 1.1.2 |  |  |  | Output 1.1.2
| Output 1.2.1 | 0 |  |  | Output 1.2.1 | 0 |  |  | Output 1.2.1 |  |  |  | Output 1.2.1
| Output 1.2.2 | 6857 | 31.12.20 |  | Output 1.2.2 | 7300 | 31.12.21 |  | Output 1.2.2 |  |  |  | Output 1.2.2
| Output 1.2.3 | 26717.74 | 31.12.21 |  | Output 1.2.3 |  |  |  | Output 1.2.3 |  |  |  | Output 1.2.3
| Output 1.3.1 | 22628.1 | 30.06.21 |  | Output 1.3.1 | 20807.86 | 31.12.21 |  | Output 1.3.1 |  |  |  | Output 1.3.1
| Output 1.3.2 | 40730.58 | 30.06.21 |  | Output 1.3.2 | 55543.18 | 31.12.21 |  | Output 1.3.2 |  |  |  | Output 1.3.2
| Output 1.3.3 | 26365.17 | 31.12.20 |  | Output 1.3.3 | 28722.53 | 31.12.21 |  | Output 1.3.3 |  |  |  | Output 1.3.3
| Component 2 | 323600.35 |  |  | Component 2 | 405042.93 |  |  | Component 2 | 15153.67 |  |  | Component 2 | 0
| Component Administration | 25782.32 | 31.12.21 |  | Component Administration | 35529.3 | 31.12.21 |  | Component Administration | 1908.82 | 31.12.21 |  | Component Administration
| Output 2.1.1 | 30856.5 | 31.12.21 |  | Output 2.1.1 | 40498.89 | 31.12.21 |  | Output 2.1.1 | 12099.73 | 31.12.21 |  | Output 2.1.1
| Output 2.1.2 | 274.28 | 31.12.21 |  | Output 2.1.2 | 876 | 31.12.21 |  | Output 2.1.2 | 0 |  |  | Output 2.1.2
| Output 2.1.3 | 16539.77 | 31.12.21 |  | Output 2.1.3 | 10799.38 | 31.12.21 |  | Output 2.1.3 | 0 |  |  | Output 2.1.3
| Output 2.2.1 | 30493.08 | 31.12.20 |  | Output 2.2.1 | 13801.15 | 31.12.21 |  | Output 2.2.1 | 0 |  |  | Output 2.2.1
| Output 2.2.2 | 7542.7 | 31.12.21 |  | Output 2.2.2 | 3413.17 | 31.12.21 |  | Output 2.2.2 | - |  |  | Output 2.2.2
| Output 2.2.3 | 40412.42 | 31.12.21 |  | Output 2.2.3 | 65601.8 | 31.12.21 |  | Output 2.2.3 | 1145.12 | 31.12.21 |  | Output 2.2.3
| Output 2.3.1 | 0 |  |  | Output 2.3.1 | 0 |  |  | Output 2.3.1 | 0 |  |  | Output 2.3.1
| Output 2.3.2 | 0 |  |  | Output 2.3.2 | 0 |  |  | Output 2.3.2 | 0 |  |  | Output 2.3.2
| Output 2.3.3 | 274.28 | 31.12.21 |  | Output 2.3.3 | 601.72 | 31.12.21 |  | Output 2.3.3 | 0 |  |  | Output 2.3.3
| Output 2.3.4 | 171425 | 30.06.21 |  | Output 2.3.4 | 233921.52 | 31.12.21 |  | Output 2.3.4 | 0 |  |  | Output 2.3.4
| Component 3 | 417356.11 |  |  | Component 3 | 719819.54 |  |  | Component 3 | 49051.74 |  |  | Component 3 | 0
| Component Administration | 18513.9 | 31.12.21 |  | Component Administration | 32575.03 | 31.12.21 |  | Component Administration | 8596.21 | 31.12.21 |  | Component Administration
| Output 3.1.1 | 8228.4 | 31.12.20 |  | Output 3.1.1 | 8397.83 | 31.12.21 |  | Output 3.1.1 | 1407.34 | 31.12.21 |  | Output 3.1.1
| Output 3.1.2 | 0 |  |  | Output 3.1.2 | 29543.28 | 31.12.21 |  | Output 3.1.2 | 0 |  |  | Output 3.1.2
| Output 3.1.3 | 62346.59 | 31.12.21 |  | Output 3.1.3 | 14214.29 | 31.12.21 |  | Output 3.1.3 | 1313.64 | 31.12.21 |  | Output 3.1.3
| Output 3.2.1 | 0 |  |  | Output 3.2.1 | 41288.65 | 31.12.21 |  | Output 3.2.1 | 21254.87 | 31.12.21 |  | Output 3.2.1
| Output 3.2.2 | 0 |  |  | Output 3.2.2 | 222508.93 | 31.12.21 |  | Output 3.2.2 | 0 |  |  | Output 3.2.2
| Output 3.2.3 | 0 |  |  | Output 3.2.3 | 0 |  |  | Output 3.2.3 | 0 |  |  | Output 3.2.3
| Output 3.3.1 | 12342.6 | 31.12.21 |  | Output 3.3.1 | 26357.41 | 31.12.21 |  | Output 3.3.1 | 0 |  |  | Output 3.3.1
| Output 3.3.2 | 0 |  |  | Output 3.3.2 | 967.61 | 31.12.21 |  | Output 3.3.2 | - |  |  | Output 3.3.2
| Output 3.3.3 | 137140 | 31.12.21 |  | Output 3.3.3 | 66078.31 | 31.12.21 |  | Output 3.3.3 | 0 |  |  | Output 3.3.3
| Output 3.3.4 | 68570 | 31.12.21 |  | Output 3.3.4 | 73000 | 31.12.21 |  | Output 3.3.4 | 0 |  |  | Output 3.3.4
| Output 3.4.1 | 15313.74 | 30.06.21 |  | Output 3.4.1 | 13388.92 | 31.12.21 |  | Output 3.4.1 | 4327.67 | 31.12.21 |  | Output 3.4.1
| Output 3.4.2 | 5142.75 | 30.06.21 |  | Output 3.4.2 | 15750.22 | 31.12.21 |  | Output 3.4.2 | 6387.33 | 31.12.21 |  | Output 3.4.2
| Output 3.5.1 | 0 |  |  | Output 3.5.1 | 0 |  |  | Output 3.5.1 | 0 |  |  | Output 3.5.1
| Output 3.5.2 | 0 |  |  | Output 3.5.2 | 0 |  |  | Output 3.5.2 | 0 |  |  | Output 3.5.2
| Output 3.5.3 | 274.28 | 31.12.21 |  | Output 3.5.3 | 601.72 | 31.12.21 |  | Output 3.5.3 | 0 |  |  | Output 3.5.3
| Output 3.5.4 | 89483.85 | 31.12.21 |  | Output 3.5.4 | 175147.34 | 31.12.21 |  | Output 3.5.4 | 5764.68 | 31.12.21 |  | Output 3.5.4
| Component 4 | 155356.99 |  |  | Component 4 | 294855.59 |  |  | Component 4 | 134579.32 |  |  | Component 4 | 81599.26
| Implementing entity oversight cost | 73141.56 | 31.01.21 |  | Implementing entity oversight cost | 115818.59 | 31.12.21 |  | Implementing entity oversight cost | 71660.09 | 31.12.21 |  | Implementing entity oversight cost | 36338.88
| Project Execution Cost | 82215.43 | 31.01.21 |  | Project Execution Cost | 179037 | 31.12.21 |  | Project Execution Cost | 62919.23 | 31.12.21 |  | Project Execution Cost | 45260.38
|  | 0 |  |  |  | 0
| TOTAL | 1123667.02 |  |  | TOTAL | 1712955.09 |  |  | TOTAL | 203994.69 |  |  | TOTAL | 81599.26
|  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
|  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
|  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A
[8 empty] | 3000652 |  |  |  | 3000652
Note on N16: Tatiana Paulo: NZD = $0.6857
Note on V16: Tatiana Paulo: NZD = $0.6857
Note on AD16: Tatiana Paulo: NZD = $0.6857

## Risk Assesment
RISK ASSESMENT - June 2022
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Meeting the expectations of the Communities to implement projects but there is insufficient budget | M | Component 1, 2 and 3 consultations were all impacted with communities and stake holders during 2022 from travel bans due to COVID-19 increased cases in several islands, at times communication was conducted through email/social media/phone/photos/zoom with additional cost for equipment to support zoom/phone/tablets/computers communications. ie. Link to travel ban notice - https://www.facebook.com/climatechangecookislands/posts/pfbid02PBMeYsnJYrQEzxvfiMWy65HNi8ysXVAEPegK4VLDXQ1DPeqFRAY7fF1UX75pE7AVl COVID -19 continued to affect/impacted the procurement and delivery of some materials in all Components especially in Component 2 and 3 with increased cost of consultations/workshops & training/materials/equipment /freight/transport. Travel - the availability of regular airline flights/boat charter and Pa Enua Travel Restrictions & Ministerial Travel Bans required delays in travel. With Travel Bans due to COVID-19 restrictions, airline flights/boat charters were disrupted whereas the only means of travel to the Pa Enua, especially the northern group Islands of Penryhn, Manihiki,Pukapuka were charted flights, Rakahanga Nassau and Palmerston were boat charters - with high airline charter/boat charter cost, Southern Group travel to Mitiaro, Mauke, Atiu, Aitutaki and Mangaia have also been impacted by COVID-19 travel bans/restrictions and incurred additional cost . To mitigate this risk, the project team implemented a cost-sharing strategy with other components of the project and also with other government agencies. COVID-19 also impacted on delivery of materials/equipment due to transportation delays from international cargo freight and domestic cargo schedules i.e. delivery of agriculture equipment for northern and southern group (rotary, garden tools, brush chipper for mulching).
Finance personnel is unable to meet financial commitments and targets as defined in the workplan | L | Processing and reconciliation of financial transactions with bank statements by the NIE Finance Manager - DCD, MFEM.
Travel costs exceed the budget to meet Northern Group commitments and activities | M | Cost sharing travelling cost with other PEARL Project Partners and Government Department were preferred for cost recovery, complete project deliveries and implementation. COVID -19 continued to affect/impacted the travel across all Components to the Pa Enua and increased cost of materials/equipment/freight/transport Travel - the availability of regular airline flights/boat charter and Pa Enua Travel Restrictions & Ministerial Travel Bans required delays in travel, additional cost was incurred to Per Diems/Accommodation/Transport i.e. Pa Enua Mayor & EO's Brilliant Resilient Workshop August 2021.
Economic Resilient and Water Security Fund requests exceed available budget | L | Respective Island Governments, Councils and beneficiaries were engaged in 2022 with PMU and partners to strengthen the delivery of the Projects and reporting. During the Pa Enua Mayors & EO's Brilliant Resilient Workshop, islands met with PEARL Project supporting Agencies, suppliers and service providers of equipment/materials for the Water Security Fund and Economic Resilient Fund.
Disputes during contract execution, e.g. the quality of the work is assessed to be inadequate, or regarding issues related to budget and completion time of work | M | Project related grievenances follow the Grievance Redress Mechanism as per the PEARL Project Document (p127-128). If during contract execution the Project Coordinator and Component Coordinators CCCI- EE cannot resolve the conflict at the operating and executing level, the matter must be escalated and addressed by the MFEM-NIE; Tarai V has a mediation process that will be implemented.If the Project Coordinator and Component Coordinators cannot resolve the conflict at the executing level, the matter must be escalated and addressed by the MFEM-NIE; Te Tarai Vaka Activity Management System has a mediation process that will be implemented as per the Grievance Redress Mechanism (refer to the PEARL Prodoc on page 127 & 128).
The project may not receive the funds on time, or there may be a slow disbursement of funds, which can have a significant impact on implementation and co-financing availability. | L | System to manage this is in place plus forward planning by Outputs and progress reporting on a quarterly basis.
Misappropriation of Project Funds | M | Flag to internal audit team of MFEM, Annual audits as well as spot check audits will be enforced during project implementation.
Not able to contract suitable Project Management team for the PMU | L | Project Management team for the PMU established. PEARL Project PMU Admin Clerk was hired to support the PMU.
Poor collaboration between programme partners | M | Ongoing meetings with keystakeholders are conducted weekly, monthly and quarterly (Platform Meetings)
Island Government disputes the role of the PMU in Rarotonga and declines implementation of activities | L | Ongoing communication with Island Governments and Communities is key to managing potential disputes.
Disputes over who should drive the projects on island and the competing interests of various stakeholders | M | The project will be driven through the Local Government Channels to avoid local interests groups but if well consulted and issues adressed properly it shoud not be a problem.
Limited human resources in Government ministries and agencies to contribute to the activities. | M | We will address the HR issues island by island depending on the local capabilities and enter into an agreement for the sub projects. Training Pa Enua staff to maintain and install water utility will continue through ICI and its other projects as this is no longer possible due to the ending of PEARL project. i.e. Manihiki Community Water Tanks.
The government is no longer supportive, politically and financially, of a cross-sectoral and integrated approach to the management of climate risks and opportunities. | L | This is not a risk at this stage and ongoing communication is key to all stakeholders.
Communication, access and community coordination difficulties delay timely implementation of the planned programme activities at the target community level. Communication costs exceed budget allocation. | L | This is not a risk at this stage and ongoing communication is key to all stakeholders. Communication and Awareness has exceeded all targets for 2022 through social media, print media, radio and images. Link to some stories - Career Expo Capacity Building https://www.facebook.com/climatechangecookislands/posts/pfbid027FDnh8rWXNADgfa3tAYehT7bkpCbGNqCVDsjq62xYFSitd2WkqucNduuQi4A7i2Rl Component 1 - https://www.facebook.com/climatechangecookislands/posts/pfbid02Ny8DgBFYaANWC3zfykaZjUTVvCVXBaUy1aS26AGSyZmsjm6VXwYKdaMMqzdVqWKYl Component 2 https://www.cookislandsnews.com/uncategorised/new-water-tanks-for-manihiki/ , Component 3 https://www.facebook.com/climatechangecookislands/posts/pfbid0rTA4ZYGAVEYbP6Nxo81fmKAxroRoYezD7UF8aaavTH1Zu5osd4GRMDPNw2nYxHh8l
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational - Transportation | On going - only one domestic cargo shipping supplier to Northern Group. A new shipping service have however commenced as of December 2020. | The Executing Agency, Component Coordinators and team continue to have regular meetings and contacts with suppliers, buyers, freight services, producers and shipping agents to look at ways to improve delivery and avoid delays to projects.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Lack of compliance with local and national laws in project activities. | Management : Through early intervention at the inception phase, the ESS, Gender Specialists and the technical specialists engaged for the water and food security components will confirm all activities for implementation are compliant with existing laws. Avoidance : The Programme has been designed to be in compliance with relevant national laws, regulations and policies. If activities are not compliant, further appropriate actions will be carried to ensure provisions of applicable existing laws are not breached. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The Programme has been designed to be in compliance with relevant national laws, regulations and policies. Compliance with laws and in particular the following key legislations will be monitored during implementation: Environment Act 2003 and Biosecurity Act 2008. There is the likelihood that some activities will be required to comply with existing laws, e.g. Environment Act 2003. | There may be a rare occasion when the programme or sub-projects will not be in compliance with relevant national laws, regulations and policies and in this case the process to be followed are outlined. | none at the moment | none at the moment
2 - Access and equity |  |  | Lack of equity in access to project resources and activities. | Mitigation: Each Pa Enua has in place a grievance mechanism at the Island Government and at the community level. Avoidance: Measures provided in the ESMP is taken into consideration to ensure ES and Gender safeguarding is followed and risks and impacts remains low. Management: The ESS and Gender specialist will monitor and implement measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities; AGIntel database; Geo Portal | The Programme recognises that the Pa Enua communities are small and in close proximity, and therefore sharing of information and benefits through the network of groups should be easier. However, the programme will make sure compliance by describing the process of allocating and distributing programme benefits. It will ensure that there will be neither discrimination nor favoritism in accessing programme benefits. | Due to competing interests and also insufficient funds to meet 100% demand and meet all the community expectations it will be necessary that the communities fully understand the Programme/projects to be implemented. | none at the moment | none at the moment
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalised and vulnerable groups from project activities. | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Reports of community adaptation action planning processes and consultations with local authorities; AGIntel database; Geo Portal | There are people with disabilities and families living with persons with disability, the elderly, children, women and girls, as well as people with very low income and with limited access to resources to help them in their normal everyday living. The small nature of the communities and their close proximity with each other, marginalised and vulnerable groups are easily recognised and their needs provided at the community and family level. | Specific projects that need to be considered is the siting of water tanks and early warning systems must take into account the need to ensure the marginalised and vulnerable groups are considered in design phase. Agricultural programs will ensure these groups will have more access to produce as well. | none at the moment | none at the moment
4 – Human rights |  |  | lack of respect and compliance with individual human rights | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP and to address any gaps in the current situation in the Pa Enua Mitigation: The law of the country applies to everyone in the country whether they are resident or visitor. | Reports of community adaptation action planning processes and consultations with local authorities. | The Cook Islands Constitution recognises fundamental human rights and freedom that exist and shall continue to exist without discrimination by reason of race, national origin, colour, religion, opinion, belief, or sex. | This is a cross-cutting principle and all activities will be designed to make sure the rights of every person in the Pa Enua are not infringed upon. The Programme recognises that human right issues whether it is to do with rights to resources, land, training, opportunities, and the right to express one’s opinion and the right to be heard, is considered important in the Pa Enua, the risk and impact assessment depicts a very low risk and minor impact for all project sites on this principle. | none at the moment | none at the moment
5 – Gender equality and women’s empowerment |  |  | Lack of gender equity and women’s empowerment in project implementation and outcomes. | Mitigation: ESS and in particular the Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP for gender safeguarding | Reports of community adaptation action planning processes and consultations with local authorities; AGIntel database; Geo Portal | Gender inequality is highest in the small communities of the Pa Enua. There is a strong but defined roles for women based on church teachings and it does not always support gender balance. | Early consultation during Inception phase should ensure that men and women: 1) have equal opportunities to participate in consultation, training and awareness activities; 2) receive comparable social and economic benefits; and 3) do not suffer disproportionate adverse effects during the development process | none at the moment | none at the moment
6 – Core labour rights |  |  | Lack of compliance with local and national labour laws | Mitigation: ESS and Gender Specialist will monitor those mitigating measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities. | The project has been designed to comply with relevant national laws and policies that govern employment rights and appropriate working conditions in the work place. | All persons employed under this programme will go through contractual arrangement following the CIG Procurement Policy. For agricultural projects that are considered under the Economic Resilience Fund in Component 3, it is important, where a project requires assistance to pay workers that proponents ensure the rights of workers are observed and they are paid according to current income laws and their working conditions in accordance to good employer practice. | none at the moment | none at the moment
7 – Indigenous peoples |  |  | Lack of consideration for indigenous people | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities. | The Cook Island Constitution recognizes people of the Cook Islands as ‘people of Cook Islands decent’ and is the closest we have in classifying people as ‘indigenous people’. There are no separate laws for people of Cook Island descent and other ethnic groups. | The law of the country applies to everyone in the country whether they are residents or visitors. | none at the moment | none at the moment
8 – Involuntary resettlement |  |  | Involuntary resettlement of people from their homes and lands for planting as a result of project activities | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Reports of community adaptation action planning processes and consultations with local authorities. | The Programme will focus on lands already used for community water tanks, planting lands that already have access roads and currently used for agriculture purposes and due process will be followed where new lands are identified. | Even though the Programme will be looking at lands already used for public purposes, still, the landowners will be consulted and negotiations as per existing land acquisition processes. The Programme recognises that there will be no requirement for Involuntary resettlement in the Pa Enua | none at the moment | none at the moment
9 – Protection of natural habitats |  |  | Damage and/or degradation to natural habitats as a result of project activities. | Management: Environment Impact Assessment (EIA) Process; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; Plan to minimize introduction of invasive species; Agriculture quarantine protocols to be followed | The Programme will focus on lands already used or cleared, existing access roads so the likelihood that natural habitats may be affected is very low. | The Programme recognises current levels of awareness at the national, island and community level where the awareness for protection of biological diversity has been on-going and in some cases conservation areas have been established. Where a new activity such as the construction of a new community concrete water tank or the construction of a new water catchment building on a new site, or the construction of a water reservoir and laying of irrigation lines for agriculture purpose would go ahead, and if these new activities are identified to have the potential to encroach on special natural habitats, through the National Environment Service ESD form check list and risk identification and EIA process, | none at the moment | none at the moment
10 – Conservation of biological diversity |  |  | Biodiversity loss as a result of project activities. | Mitigation: National Environment Service ESD form check list and risk identification and EIA process | Plan to minimize introduction of invasive species Agriculture quarantine protocols to be followed | The Programme will focus on lands already used or cleared, existing access roads so the likelihood that biodiversity may be affected is very low. | The Programme recognises current levels of awareness at the national, island and community level where the protection of biological diversity has been ongoing. Where a new activity such as the construction of a new community concrete water tank or the construction The Programme recognises current levels of awareness at the national, island and community level where the protection of biological diversity has been ongoing. Where a new activity such as the construction of a new community concrete water tank or the construction | none at the moment | none at the moment
11 – Climate change |  |  | Significant or unjustified increase in greenhouse gas emissions or other drivers of climate change. | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The likelihood of increased greenhouse gas or any other cause of climate change is not high. | Relevant to the Programme, impacts such as potential pollution of coastal waters affecting coral growth and the emission of carbon dioxide into the atmosphere as a result of potential burning of cleared vegetation on lands for agriculture purposes, the use of coastal resources for building weakening the capacity of the coast to protect lands behind it from sea surges. Recognising that existing activities on climate change resilient building has been on-going. | none at the moment | none at the moment
13 – Public health |  |  | Negative impacts on public health as a result of project activities. | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; Public Health Act 2004; | The Programme has been designed to support Public Health in the Pa Enua. The Programme will support the tutaka programme (regular health inspection of homes and villages) of the Ministry of Health through its communication and Media Specialist and will enhance the supply of clean water for cleaning and drinking in homes. | Public and Health workers on each of the islands ensuring all people have access to quality advice and service, good quality drinking water, households have access to water for cleaning, community and formal education and public awareness programs on health issues are in place, alternative medicine in the form of traditional medicine is available, and knowledge on useful plants and herbs are available. | none at the moment | none at the moment
14 – Physical and cultural heritage |  |  | Damage to physical and cultural heritage sites | Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The project has been designed to ensure no physical and cultural heritage sites are modified. | Public and Health workers on each of the islands ensuring all people have access to quality advice and service, good quality drinking water, households have access to water for cleaning, community and formal education and public awareness programs on health issues are in place, alternative medicine in the form of traditional medicine is available, and knowledge on useful plants and herbs are available. | none at the moment | none at the moment
15 – Lands and soil conservation |  |  | Land and soil degradation | Management: Environment Impact Assessment (EIA) Process; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | There is likelihood some manageable impacts will arise from modified lands. Where land is to be modified that may cause soil erosion, standards will be followed to maintain the land in its natural state or as close to its natural state as is possible; and, if land is to be converted, it must promote and protect its current function e.g. sloping lands or forest lands. | The programme targets the use of lands already used and altered. | none at the moment | none at the moment
There will be no changing of soil structure or causing lands and soils to be degraded or values changed.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No additional risks identified. Identification of environmental and social risks related to sub-projects under the Water Security Fund and Economic Resilience Fund was conducted as part of the screening process for each applicant prior to approval of each sub-project.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Regular monitoring and evaluation of implementation of activities are carried out to ensure that all activities for implementation are compliant with the ESMP.
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been effective from the beginning of the project through to the current reporting period.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Component specialists and the technical specialists engaged for each component ensure that activities carried out are checked against the ESMP.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements have been effective from the beginning of the project through to the current reporting period.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/programme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The required capacity to carry out the ESMP are filled and effected in both the IE and also the 3 EE's. Technical and advisory committees composing of various agencies identified in the ESMP advice the component specialists of any likely Environment and Social Risks before they arise and helps identify mitigation measures. The roles of the ESS Specialist and Gender Specialist carried out assessments to ensure that all risks identified for the USPs were effective during the implementation of the USPs.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No new USP's for this reporting period
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Construction of 20Kl Water Tanks - Pukapuka | Yes | Removal of sand for the tank construction from beaches | Yes. | Yes | N/A | Harvest sand from identified areas only | Construct limited concrete tanks per year
USP 2: Construction of 20Kl Water Tanks - Nassau | Yes | Removal of sand for the tank construction from beaches | Yes. | Yes | N/A | Harvest sand from identified areas only | Construct limited concrete tanks per year
USP 3: Construction of 20Kl Water Tanks - Penrhyn | Yes | Removal of sand for the tank construction from beaches | Yes. | Yes | N/A | Harvest sand from identified areas only | Construct limited concrete tanks per year
USP 4: Construction of 20Kl Water Tanks - Manihiki | Yes | Removal of sand for the tank construction from beaches | Yes. | Yes | N/A | Harvest sand from identified areas only | Construct limited concrete tanks per year
USP 5: Component 3 Allocation of Economic Resilient fund. Code - MGS008 small machine procured and dilivered. | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
USP 6: Component 3 Allocation of Economic Resilient fund. Code - MGS007 small machine procured and dilivered. | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
USP 7: Component 3 Allocation of Economic Resilient fund. Code - AUI001 Fencing and Irrigation. | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
USP 8: Component 3 Allocation of Economic Resilient fund. Code - MUK001 Fencing | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
USP 9: Component 3 Allocation of Economic Resilient fund. Code - MUK002 Fencing | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
USP 10: Component 3 Allocation of Economic Resilient fund. Code - MUK003 Fencing | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
USP 11: Component 3 Allocation of Economic Resilient fund. Code - MUK004 Fencing | yes | Nil | Yes | Yes regularly consultations and visits with the Island government farmers and community. Island government contributes with the diliverly, installation and assembling of equipments with the support of the Ministry of Agriculture support team. | Yes gender is considered with the support data from climate change office, AgINTEL on women engaged in farming. | Nil | Monitoring is supported by the Island Governments Agriculture Manager and staff through reports, business plan and AgINTEL.
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances were received for the reporting period. |  | No grievances were received for the reporting period.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Number of Geo Portal Officers trained on each island by Gender | Output | A minimum of one on each island including equal number of women | 0 | 50% | Good
Develop user and administration manual for the Geo Portal | Output | A minimum of 1 training workshop on each island inclding equal number of women | 0 | 50% | Good
School gardens for the northern group islands | Output | Number of students by gender taught science, social science and health & wellbeing units using school garden | 0 | 50% | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
N/A |  | N/A
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Enities, have all made efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the household baseline incorporated sex disaggregated data and gender specific questions. 2 - Encouraging project partners/ executing entities to hold gender sensitive consultations and assessments, for example holding separate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 3 - Ensuring that the Inception Workshop and Implmentation related Workshops had participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during workplanning
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements for Gender Policy compliance have been effective. Discussions on gender issues were held during project inception and work planning, with the following outcomes and agreements: 1) all partners to consider the specific needs and constraints of womens participation in project activities; 2) track gender indicators in all activities; 3) aim for equal participation of women in project activities and activity leadership structures; and 4) capture sex-dissagregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Component 1 - Emergency Management Cook Islands (EMCI) - Geo Portal surveys and mapping has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Continuous sensitisation on participation of both men and women when identifying participants for project activities; persons attending project related workshops and trainings are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities.
Component 2 - Infrastructure Cook Islands (ICI) - Water Security surveys and mapping has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Continuous sensitisation on participation of both men and women when identifying participants for project activities; persons attending project related workshops and trainings are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - Ensuring that access to benefits under the Water Security Fund incorporates both women and men
Component 3 - Ministry of Agriculture (MoA) - Participation in agriculture surveys and mapping has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Continuous sensitisation on participation of both men and women when identifying participants for project activities; persons attending project related workshops and trainings are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - Ensuring that access to benefits under the Economic Resilience Fund incorporates both women and men
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements for Gender Policy compliance have been effective. Womens participation in project activities, as well as their engagement in leadership and training roles has been strong. In some cases womens participation is higher than the targetted 50%. The effectiveness of the EEs efforts to address gender equality has been steady and activity to activity.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | At the moment no major capacity gaps affecting Gender Policy compliance have been identified at the IE or the EEs. The capacity for adherence to the Gender Policy is adequate among the IE and EEs. The EEs will continue to engage with the stakeholders on the importance of gender issues and the participation of both men and women.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: Ministry of Finance & Economic Management | Component 1: Strengthening disaster risk governance to manage disaster risk and enhancing disaster preparedness for effective response to “Build Back Better” in recovery, rehabilitation and reconstruction |  | Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | DRM committees and focal points established at the Pa Enua (grassroot) level and direct engagement in Pa Enua DRM Planning and capacity building for preparedness and mitigation. |  | Achieved. Continuity through the DRM committees and the National EMCI and partners. | S
|  |  | Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level | Expanded GeoPortal Disaster Risk Management Information System; Management response tools linking hazard risk assessments and the DRM Plans |  | Integrated data sets from each of the pa enua is up to date and aggregated at the national level. The new Emergency Cook Islands' website (www.emci.gov.ck) fully operational and updated disaster risk alerts plus promotional and educational materials. Continued support now that the project is complete will be provided by the Office of PM - EMCI Emergency Management Response Centre. | S
|  |  | Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress
|  |  | Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
| Component 2: Integrated water security management planning and implementation for Pa Enua communities |  | Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Allocation of Water Security Fund Strengthened drinking water security including increased institutional capacity and coordination for integrated water management. |  | Under the Government agency - Infrastructure Cook Islands - planned activities that are still outstanding to increase access to safe drinking water for the pa enua through upgraded and installment of water systems has been integrated in to the water management plans of the Agency. | S MS
|  |  | Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Continued community consultation to ensure relevance of each pa enua's Water safety , Drought management and Water development Plans in partnership with the local island government and DRM committee after project completion. | S
|  |  | Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought
| Component 3: Revitalised agricultural production systems strengthening island food sources and livelihoods in the Pa Enua |  | Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Improved variety of staple crops that are resilient in the face of increased climate variability and climate change are grown at the Pa Enua level for local consumption Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Technical training support for nursery/hydroponic, fruit tree management along with pest management. Collate information on traditional knowledge based on stable food crops |  | Component 3 activities will continue as part of Minstry of Agriculture's national business strategies in partnership with each of the island governmen, paenua growers, schools and communities to increase farming and improve food production for subsistence and to supply the local market needs. | S
|  |  | Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas
|  |  | Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Emily Pierre-OaAriki, NIE, MFEM
| Email: | emily.pierre@cookislands.gov.ck
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Overall Rating: Satisfactory The strengthened partnership due to the collaboration of activities by the PEARL Project executing partners - Infrastructure Cook Islands - Water Division, Ministry of Agriculture and OPM - Emergency Cook Islands and Climate Change with the Pa enua stakeholders will see the support of adaptative and climate change strengthening measures that are now in place will continue beyond the Project completion. Capacity building of key pa enua residents in terms of disaster risk planning and preparedness through the PEARL Project's 3 components have increased the institutional capacity to support the adaptation and mitigation steps where it is required, at the point of destination.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator, PMU - Climate Change, Office of the Prime Minister | Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. |  | Outcome 1 |  | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level |  | Project activities 100% achieved and strengthened for the Outcome of Reduced exposure to climate related hazards and threats with information gathered and assessments conducted and updated from stakeholders and Pa Enua community. 11 of the 11 Targets for Component 1 are completed. Activity Line 1.0/ 1.1 An integrated and inclusive data base is established one year from implementation of the programme and All 11 Pa Enua with baseline and updated datasets in the Geo Portal - 100% Completed under SRIC-CC and BSRP Projects. The Geo Portal with climate early warning information has been established and can be viewed online at http://www.emci.gov.ck in the Cook Islands; This assignment is managed by the Emergency Management Cook Islands (EMCI) Division at the Office of the Prime Minister. The Geo-Portal will continue to be loaded with information and this information updated annually by the designated staff at EMCI and supported by the ICT. The information is also to assist EMCI in the assessment of communities in pre and post-disaster situations. This Target is currently being strengthened and updated in the PEARL Project from the DRM Household Surveys/Data from the Pa Enua. CLEWS, DRM Surveys, DRM Plans and MET Drought Reports are assessment dataset in the Geo Portal. Activity Line 1.2.1 Three Management Response tools target is completed with CLEWS, DRM Plans, GEO Portal, MET Services Drought Reports, CSDP, NSDP, JNAP II, Social Media, MET Drought Reports, DRM Household Surveys and Satelitte Phones for each of the islands of the Cook Islands was procured in 2021 to strengthen DRM communications for the remote islands especially Palmerston and Nassau. Activity Line 1.2.2 Monthly usage of management tools target completed with MET Services Drought Reports, AWS CLEWS, Social Media, Geo Portal. At least one App is obtained and used - DRM Survey Tablet Tools Applications to upload information to Geo Portal and AWS Smart App is currently in Beta Testing with MET Services. ArcGIS Survey 1.2.3 has been utilized in DRM Household data collection. Website and Social Media pages were updated and strengthened. Links - Link - website https://emci-site.net/ social media https://www.facebook.com/emciCK Satellite Phone Link - https://www.facebook.com/CookIslandsNews/photos/a.612856485458666/4644989932245281 Activity Line 1.2.3 AWS installation was completed on the Pa Enua Islands of Palmerston, Nassau and Suwarrow. First AWOS in the Pa Enua was installed on Aitutaki. This was implemented by Cook Islands MET Services and installed by young Cook Islanders in partnership with the UNDP RESPAC Fund. Target of 2 (Suwarrow and Nassau) AWS installations were strengthened with an additional AWS installed in Palmerston and the first Pa Enua AWOS at the Airport in Aitutaki. The completion of the AWS installation for the northern group has improved our capability in monitoring meteorological events which influences global climate change. Project activities are achieved. Link to Early Rainfall Watch update for North Workshop with 30 participants was also support for under standing rainfall and being better prepared with Cook Islands Met Services in March. Link - https://www.cookislandsnews.com/national/weather/understanding-rainfall-and-being-better-prepared/ Activity Line 1.3.1 100% Completed and strengthened with training provided for each of the southern group islands and DRM household surveys conducted for all Pa Enua Islands. All 10 Pa Enua DRM plans were updated under the AF PEARL Project and officially endorsed by the Mayors & EO’s at the Brilliant Resilient Workshop August 2021. Activity Line 1.3.2 and 1.3.3 Geo Portal handbook was completed and training was conducted. Collaborating with our traditional community partners (DRM Committees) in the Pa Enua has allowed the DRM survey and DRM Plan endorsements to be better understood and accepted. Follow up tablet training was conducted funded by SPREP that continuded to upskill Focal Points in Mangaia and Aitutaki including Climate Change interns and staff PEARL Project PMU participated in the training. Link to training - https://www.facebook.com/climatechangecookislands/posts/pfbid02EuVFwb7h8dWD7adP2xDJLfCADBfFDbQraheAduhdcWVJSof18BAmWftZ32WzVJeHl | MS
| Strengthened drinking water security including increased institutional capacity and coordination for integrated water management to reduce risks associated with climate induced socioeconomic and environmental losses |  | Outcome 2 |  | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought |  | Targets Achieved - Outcome has been Strengthened with community and island government engagement. Most of the activities conducted in 2021 and 2022 involved procurement of materials and consultation with the people of the Pa Enua in relation to creating awareness around the project and what it intend to achieve in terms of providing the necessary water security frameworks and activities critical to keep community safe from the water shortage risks. The work focused on a number of activities including updating and adjusting the community drought management plans include three water based sub-component including; Water development plan, Water safety plan as well as Drought management plan. The Water development plan component; focused on the future plan for improving water supply for each respective islands which also take in to consideration infrastructure improvement. The water safety plan prescribes the activities around improving water safety. The final component the drought management plan is part of the overall plan to implement infrastructure and systems in place are unable to provide the required water supply to the community when dry spell set in on the islands. This project is tasked to strengthen water security for the communities. Rainwater harvesting and accessing well water is all they have. 10 of the 10 Targets for Component 2 are completed. | MS
|  |  | Outcome 4 |  | Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drought |  | Target Achieved - The recently reviewed Water Security and Drought Management Plans for Water development plan, Water safety program as well as the Drought Management plans will be in 1 document instead of separating these into 3 different working documents. The Water Security and Drought Management Plans were completed for all 10 islands and endorsed/handed out at the Pa Enua Brilliant Resilient Workshop in August 2021. Community consultations on the islands continued with activities and completion of 4 community water tanks were conducted on Nassau and 2 community water tanks on the islands of Manihiki in 2022. Link for Nassau - https://www.facebook.com/climatechangecookislands/posts/pfbid02c7rCcqxe9KQpmuVyFYse1HHFeLJJvWnkHFa2667Z7RsXzx37G3H3SzwoyjGZB93pl Link for Manihiki - https://www.cookislandsnews.com/uncategorised/new-water-tanks-for-manihiki/ Procurement of water bottles and marketing merchandise continues as part of the Climate Change's / PEARL PMU awareness raising programs with the schools and the communities in the pa enua.The team worked with the Island Governnment and Council and delivered the remaining water bottles to all the schools on the island of Aitutaki. All other water bottles were shipped/air freighted to the Pa Enua and all schools have recieved the water bottles. Workshop with CookIslands Met Services 30 participants was also support for under standing rainfall and being better prepared with Cook Islands Met Services in March. Link - https://www.cookislandsnews.com/national/weather/understanding-rainfall-and-being-better-prepared/ International World Water Day media release for 2022 Link - https://www.facebook.com/climatechangecookislands/posts/pfbid037ixb2A214NXkznAJLVXpZNtuc8no4q2wNwp75pJ1e7D4Va3K32n3epx2kGkL2wYtl | MS
| Increased island food security resilience and preparedness for disasters |  | Outcome 6 |  | Number of water efficient irrigation system installed |  | Target Achieved - Total of 25 farmers have been assisted. | S
[5 empty] | Displacement of imported food with island vegetables |  | Agriculture Data has shown an increase of farmers over 48% (AGIntel 2020) from 2018 to 2020 resulting to increased production. Nassau, Palmerston, Rakahanga, Penrhyn, Pukapuka and Manihiki all have hydroponic systems installed with revolving funds established. Southern Group Mitiaro, Atiu and Mauke also have hydroponic systems installed working in partnership with the island governments and school students for capacity development in food security. Maintenance is provided from revenue received from sales of vegetables. The northern group islands are now able to eat leafy green vegetables and eat less canned vegetables. This target has been achieved and strengthened in 2021. There has been 90 types of produce supplied by the Cook Islands local producers during this reporting period.Previously reported in email on December 16th 2020, 31 Types of Produce were supplied locally. The increase in variety of herbs, fruits and added value produce and sourcing of more locally grown produce and less imported produce has increased the access and demand of variety of produce. Current report also includes Rarotonga suppliers. Link to AgIntel reports - https://agriculture.gov.ck/corporate-services/agintel-report/ | S
[5 empty] | Pa Enua fruit products sold in Rarotonga to meet tourist demand |  | This target has been achieved and will continue to be strengthened for sustainability. Farmers on Mauke, Atiu, Mitiaro, Aitutaki and Mangaia are supplying the Rarotonga markets with produce typically imported from overseas and Rarotonga.There has been 90 types of produce supplied by the Cook Islands local producers during this reporting period.Previously reported in email on December 16th 2020, 31 Types of Produce were supplied locally. The increase in variety of herbs, fruits and added value produce and sourcing of more locally grown produce and less imported produce has increased the access and demand of variety of produce. Current report also includes Rarotonga suppliers. Import Substitution – Primefoods now imports 15 types of produce from the Pa Enua rather than from overseas. (Courgettes/Zucchini, Ginger, Avocado, Cherry Tomatoes, Turmeric, Coriander, Eggplant, Spring Onions, Lettuce, Pumpkin, Limes, Lemons, Spinach, Cucumber and Beans 3x varieties), Reference - Pa Enua Domestic Report #2. Farmers from the Pa Enua are supplying Primefoods, CITC, Wigmores Supermarket and markets on Rarotonga with the increase of tourism since the borders have re-opened in 2022 to flights with tourist directly via New Zealand. | S
[5 empty] | Improved variety of staple crops that are resilient in the face of increased climate variability and climate change are grown at the Pa Enua level for local consumption |  | Crop banks established one on each of the southern group islands holding 5 tolerant yam varieties, 3 pineapple varieties, 5 banana varieties etc. Additional crops are now included in the crop bank such as ginger and tumeric. | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Melina Tuiravakai, Project Management Unit, Climate Change Cook Islands - OPM
| Email: | melina.tuiravakai@cookislands.gov.ck
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Rating: Marginally Satisfactory Progress The overall marginally satisfactory rating has continued in 2022 and is accredited to progress made in several areas during this reporting period, namely the successes in Capacity Building with a total of approximately 1272 island stakeholders and key players trained in climate and disaster risk assessment with overall project capacity building/workshop/platform/zoom training/Geo Portal Workshop Southern Group Rarotonga/Pa Enua Brilliant Resilient Workshop Rarotonga/Water Tank installation train the trainer Nassau/DRM Household Surveys Northern Group/AWOS Training & Implementation Aitutaki/Tree Management & Water Strategies Workshop & Field Training Mangaia /Career Expo in Rarotonga and Aitutaki/WASH and Climate Science Event Aitutaki participation (54% women and 46% men) in 11 Pa Enua Islands (Aitutaki, Mauke, Atiu, Pukapuka, Mitiaro, Palmerston, Nassau, Mangaia, Penrhyn, Rakahanga & Manihiki) in 2019, 2020, 2021 and 2022. Participation in Surveys and Workshops has enabled youth and gender participation and innovation with the opportunity for them to utilize technology, smart devices, tablets to conduct island wide surveys. These workshops also include the Quarterly Platform meetings, Raurau Akamatutu (Basket of Resilience) Workshop, Market Access Training, Farmers Workshops, GEO Portal Taskforce Meetings, Pa Enua Water Security Meetings, Program Steering Group (PSG) Meetings, Ear Rainfall Watch, Tablet Training. PEARL Project is tracking well with 100% overall target achievement 2022. Covid 19 impeded on delivery of equipment, materials and transportation. However the Project team focused on target completion and adaptive climate resilient impacts to strengthen the livelihoods of the communities in the Pa Enua and gender inclusion. A total of 100% (37 of the 37) of the targets have been achieved with partnerships with other projects and stakeholders. Component 1 is currently being strengthened and updated with the DRM and Covid 19 Response Household Surveys/Data from the Pa Enua. The positive direction in addressing the area of GEO Portal/Dataset have been significant with a total of 11 of the 11 targets achieved with partnerships from SRIC-CC/BSRP/UNDP ResPAC Fund/Cook Islands Redcross Programs and key stakeholders. These partnerships will assist in mainstreaming Climate Change in local development planning and decision making. Automatic Weather Station Equipment in Aitutaki where the first AWOS fully local installation with the Cook Islands MET Services team and key island stakeholders. Lesson’s learned throughout the PEARL Project have assisted in providing interventions/mediations with shipping agents/suppliers and improvement in streamlining procurement processes. Improved collection of data with localized installation of AWOS on Aitutaki and household surveys on each island of the Pa Enua highlighting vulnerable members of society for the DRM Plans were a highlight. Upskilling unemployed youth in the Pa Enua was one of the most successful aspects and providing opportunities for other employment. Use of smart technology enabled decision makers the ability to make more informed decisions/processes during times of disaster. Component 2 achieved 10 of the 10 targets completed. Increased Water harvesting (and revival of water wells) and storage tanks for the drought prone island of Penryhn including the purchase of the water desalination unit was key. Water monitoring of water tanks equipment LOT in partnership with TAUI pilot project will provide an opportunity to support a locally owned Youth Operated business that is innovative. All schools in the Pa Enua received reusable water bottles to ensure access to safe and affordable drinking water and to increase the reliability and quality of water supplies in targeted areas. Component 3 A total of 16 of the 16 targets have been achieved in this financial year. There has been 90 types of produce supplied by the Cook Islands local producers during this reporting period.Previously reported in email on December 16th 2020, 31 Types of Produce were supplied locally. The increase in variety of herbs, fruits and added value produce and sourcing of more locally grown produce and less imported produce has increased the access and demand of variety of produce. Current report also includes Rarotonga suppliers. Link - https://www.cookislandsnews.com/outer-islands/true-basket-of-resilience/ Communication, engagement, and awareness-raising efforts using social media, partnerships, traditional/cultural forums, surveys, national radio/television and news print have reached global and local communities. Outreach with the PEARL has increased in 2021 and continued in 2022 with stories featured in Cook Islands News, Cook Islands Television and on Climate Change Social Media page. Risks that affected progress COVID-19 impeded on delivery of equipment, materials and transportation. Some equipment (i.e. hydroponics equipment, desalinater, were delayed due to offloading of cargo and or delays from international shipping which then impedes on domestic shipping. Some islands only have shipping every 3 to 4 months. Flights have also had to be chartered in 2020, 2021 and 2022 due to COVID-19 Pa Enua boarder travel restrictions. Some delays for equipment were over 11 months due to international delays. Measures taken to reduce delays was to work with suppliers locally and internationally and communications. One of the key risks that has affected progress has been Operational Delays in procurement due to transportation challenges and COVID-19 cases in Cook Islands. During this reporting period some interventions and mediation with shipping agents and suppliers have contributed to minimizing such delays and travel bans/ shipping delays affected equipment delivery due to COVID-19. The Project team will continue to work towards developing knowledge products that will feature stories of how communities’ climate change vulnerabilities are addressed and resilience are enhanced through the project investments in the communities with partnership with DCD.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Component 1 Coordinator, Emergency Cook Islands, Office of the Prime Minister | Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. |  | Outcome 1 |  | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level |  | Output 1 - An integrated and inclusive data base is established one year from implementation of the programme and All 11 Pa Enua with baseline and updated datasets in the Geo Portal - 100% Completed and strengthened under AF PEARL Project with reports & regular updates on social media. DRM Information and Communications was strengthened with the procurement and training of Satellite Phones for each of the Pa Enua and Rarotonga to communicate during times of disaster, in partnership with each island government, EMCI, Office of the Prime Minister and Cook Islands Red Cross. Link - website https://emci-site.net/ social media https://www.facebook.com/emciCK Satellite Phone Link - https://www.facebook.com/CookIslandsNews/photos/a.612856485458666/4644989932245281 This component is currently being strengthened through the use of appropriate geographical information management systems and appropriate data collection tools. The Geoportal and field data collection tools has greatly improved data analysis. EMCI launches new web map app for the Public Health Areas and Clinics on Rarotonga and Aitutaki with tools funde by PEARL Project ArcGIS in Feb 2022 Link - https://www.facebook.com/emciCK/posts/pfbid02UanmCXsUy8YJ723aYgXRhooR9DRrFY59iM4SN7c56BygsLZX83X8J5T3awvQEBsxl. Monitoring and providing communications of COVID-19 Cases also utilized the ArcGIS software/tools - Link https://www.facebook.com/emciCK/posts/pfbid0VhszpYbKiEYMNaXYrZhkCFRNHBKQ8kqFCpzwjpP3Bm5P5jkegV2RcoNoSh7gAi49l Output 2 - 100% Completed and strengthened under AF PEARL Project with reports & regular updates on social media. Under the PEARL AF Project, AWS installation was completed on the Pa Enua Islands of Palmerston, Nassau and Suwarrow. First AWOS in the Pa Enua was installed on Aitutaki. This was implemented by Cook Islands MET Services and installed by young Cook Islanders in partnership with the UNDP RESPAC Fund. Target of 2 (Suwarrow and Nassau) AWS installations were strengthened with an additional AWS installed in Palmerston and the first Pa Enua AWOS at the Airport in Aitutaki. The completion of the AWS installation for the northern group has improved our capability in monitoring meteorological events which influences global climate change. Workshop with 30 participants was also support for under standing rainfall and being better prepared with Cook Islands Met Services in March. Link - https://www.cookislandsnews.com/national/weather/understanding-rainfall-and-being-better-prepared/ Project activities are achieved. Output 3 - 100% Completed and strengthened with training provided for each of the southern group islands and DRM household surveys conducted for all Pa Enua Islands. All 10 Pa Enua DRM plans were updated under the AF PEARL Project and officially endorsed by the Mayors & EO’s at the Brilliant Resilient Workshop August 2021. Geo Portal handbook was completed and training was conducted. Collaborating with our traditional community partners (DRM Committees) in the Pa Enua has allowed the DRM survey and DRM Plan endorsements to be better understood and accepted. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Lydia Sijp, Emergency Management Cook Islands - OPM
| Email: | lydia.sijp@cookislands.gov.ck
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Component 1 under the PEARL Project tracked well with 100% overall target achieved by the end of 2021. 10 of the 10 Targets for Component 1 were completed and strengthened. Field surveyors (mainly unemployed youth) engagement in the DRM surveys has considerably decreased the number of days needed to conduct the surveys. The utilization of technology, smart devices, to conduct Island wide surveys increased the efficiency of the survey itself and processing that survey data up to the Geoportal for analysis and reporting. The project will continue to use smart devices for island wide surveys. In 2020 and 2021 more emphasis was placed on capacity and resilient building for CC and DRM. In 2022 capacity building with keystakeholders i.e. Puna's and Pa Enua DRM was supported and COVID-19 awareness/case monitoring/supporting Puna's was conducted. i.e. Dashboard COVID-19 Link https://www.facebook.com/emciCK/posts/pfbid0y3Pjp7UTcwHxewgnJo8JnvzBpShk8wVrUpGKFmu2TMSTGpfKfbXqFMoHRsNofzqVl The ArcGIS platform will continue to be the technology to operate the Geoportal and as a repository for geographical data warehousing and dissemination. One of the key risks that has affected progress has been operational delays in procurement due to transportation challenges caused by the COVID-19 pandemic. Communication and Awareness has exceeded all targets for 2021 through social media, print media, radio and images. Link to some stories - Component 1 =Early Rainfall Watch update for North pfbid02tPkYmGVeCmFMUg3hSzWb2bp9P7pDD56fM7HynTwMvXCKKNJnG6MAnYQ7QjnVeWcPl .Workshop with 30 participants was also support for under standing rainfall and being better prepared with Cook Islands Met Services in March. Link - https://www.cookislandsnews.com/national/weather/understanding-rainfall-and-being-better-prepared/ COVID-19 impeded on the travel arrangements to the southern and northern Pa Enua and also impacted on project materials/equipment. This also added to the cost materials and equipment purchased in country.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Component 2 Coordinator, Ministry of Infrastructure Cook Islands | Strengthened drinking water security including increased institutional capacity and coordination for integrated water management to reduce risks associated with climate induced socioeconomic and environmental losses |  | Outcome 2 |  | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought |  | The drought management plan is part of the overall plan to implement the infrastructure and systems in place in case these are unable to provide the required water supply to the community when dry spell set in on the islands. Under this part we saw the construction and repairs to a number of water storage infrastructures being added to the Pa Enua Rainwater harvesting systems; including 8 x 45,000l and 4x 20,000l tanks -Aitutaki.2 x 45,000 l tanks -Mangaia, 8 x 6000l - Palmerston, 4 x 25,000 l, 1 x 80,000l plus 1 x 1 x 65,000 PE Tanks Penrhyn; 4 x 45,000l - Manihiki , 2 x 20,000l concrete tanks in Nassau, 4x20,000l Tanks in Pukapuka a total of 1,040.000 l storage capacity . There also 3 x 45,000l tanks in Rakahanga lined. We also saw the contruction of 1 x Water catchment building in Manihiki - Together with the above, we also have procured a small water desalination unit for the island of Penrhyn. | S
|  |  | Outcome 4 |  | Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drought |  | Within the island communities, villages and agencies also provide their own water purification systems based on community tanks for the community members to acces. This ensures safe drinking water systems are available to the residents. This activity is on top of the Public Health 'boil water befor you drink" messages. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Otheniel.Tangianau, Infrastructure Cook Islands
| Email: | Otheniel.Tangianau@cookislands gov.ck
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Rating - S Overall Component 2 has completed all its set targets as prescribed in the project document. However a number of sub projects on some of the islands could not be fully completed due to time shortages despite the project being extended. Every effort continues to be made to fully complete these through other Water programs. Under the Water Security Funding on the island of Manihki 2 x 20kl tanks in MHX completed (Tauhunu tank; needs minor repairs. We were supposed to do this last month but MIG wanted to use the water for the Admin building foundation works. Once we receive advise from MHX will dismantle guttering from tanks and repair. The materials for repair on the island). The Tukao tank; working, overflowing and yet to be connected by the Admin to the Cyclone center. Awaiting pump. 2 x 45kl tank Ruamanu school also fully repaired and working and safe for use. The rusting galvanized post contaminating the water were removed from the inside the tanks. MHX asking for ne guttering On the island of Penrhyn; Omoka hospital; 100Kl under-ground tank fully repaired, re-instated and working, Omoka Vaine tine 47,000l concrete water tank, Holding capacity and Size increased to 65,000 l. This was done by raising the top closer to the vaine tine building roof system. On the island of Rakahanga Installed 3 liners on 3 tanks, 2 more to complete due to tools breaking down And not enough fittings send from NZ and unable to install tank liners on the Wharf underground tank due to crack in roof structure. On the island of Nassau, 2 x20,000 tanks completed, Repaired 13 Household water catchment buldings. On the island of Pukapuka 4 x20,000 Tanks.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Component 3 Coordinator, Ministry of Agriculture | Increased island food security resilience and preparedness for disasters |  | Outcome 6 |  | Number of water efficient irrigation system installed |  | Ongoing - Island Government partnership to support the farmers with further technical support provided by Ministry of Agriculture (MOA). Installation of Irrigation systems on farms on all southern group islands have been all installed with training provided by MOA. Monitoring of plantations and farms were conducted by Agriculture staff on island and MOA. Agriculture and Fisheries census was conducted in 2021 and 2022 on all islands. Data collected will be published on MOA website when final report is completed. | HS
[5 empty] | Displacement of imported food with island vegetables |  | Agriculture Data continues to show an increase of variety and crop harvest over the past 3 years. Strengthening household and national food security and nutrition and MoA's research and development into crop and tree species and improved agricultural production methods, including livestock. Food cubes were also purchased for the School garderns for each of the Northern Group to support the school gardens in planting vegetables and herbs. Due to COVID shipping delays the remaining equipment/materials are pending on domestic cargo boats schedules to the islands. (3x each for the islands Palmerston, Nassau, Pukapuka, Rakahanga. Manihiki and Penrhyn recieved 6x 3 for each school. Approximately 24 Food cubes) | MS
[5 empty] | Fruit products sold in Rarotonga |  | Increased number of farmers are now supplying to the Rarotonga market from the Pa Enua especially with the opening of the international boarders to tourist. Women farmes have engaged in export to Rarotonga i.e. Aitutaki Hydroponics, Goodway Farms and A taste of Sunshine Link - https://www.facebook.com/Taste-Of-Sunshine-Vege-Farm-285795383214077. | MS
[5 empty] | Improved variety of staple crops |  | Crop banks have been established on each of the southern group islands holding climate tolerant varieties of yam (8 Teve, Aprika, sda yam, Sweet yam, Pacific yam, Etene, Parai and Toka), pineapple (3 Ripley Queen, Smooth Cayenne and MD2), bananas (7 Amoa Cavendish, Kings crown, Rokua, Mario, Ducasse, Utu, Ladyfinger) and taro (20 varieties i.e. Manaura, Manaura cross, veo, titi cross, rakahanga cross, papua) and kumara (4 orange, white, purple, yellow). Additional crops are now included in the crop bank such as ginger and tumeric. | HS
|  |  | Outcome 8 |  | Number of hydroponic systems installed in the northern group islands. |  | Hydroponic systems installed on the Pa Enua islands under the PEARL Project of Nassau x1 , Penrhyn x2 , Palmerston x1, Aitutaki x1, Atiu x1, Mitiaro x1 and Mauke x1. All islands in the northen group have now got hydroponics which includes the school to operate and vegetables sold to the community. Atiu, Mitiaro and Mauke have now got hydroponics which the school uses for learning and also to contribute to the supply of local veggetables. Hydroponic expansion in Aitutaki supported Aitutaki Hydroponics (woman farmer who supplies domestically and rarotonga). | HS
[5 empty] | Displacement of imported food with island vegetables |  | The supply of vegetables from the hydroponics are now available regularly to the island community and is part of the Island Admin business plan to maintain the system ensuring sustainability. an increased number of local growers are now engaged with the agriculture department in the Pa Enua and are utilising the new hydroponics and nurseries. | S
[5 empty] | Number of Coconut press machines installed in the northern group islands |  | All machines are procured and have been delievered to the Pa Enua. Delays on equipment procured under this project have been impeded by COVID-19 international shipping delays. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Puna Kamoe Ministry of Agriculture
| Email: | puna.kamoe@cookislands.gov.ck
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Rating - Satsfactory All Targets achieved. Continuing the PEARL Project partnership with the pa-enua island governments and Ministry of Agriculture will be continued beyond the PEARL Project to provide the technical and advisory support for the farmers and growers. During 2022 MOA has procured Food cubes to support the School garderns for each of the Northern Group to support the school gardens in planting vegetables and herbs. Due to COVID shipping delays the remaining equipment/materials are pending on domestic cargo boats schedules to the islands. (3x each for the islands Palmerston, Nassau, Pukapuka, Rakahanga. Manihiki and Penrhyn recieved 6x 3 for each school. Approximately 24 Food cubes). Monitoring of plantations and farms were conducted by Agriculture staff on island and MOA. Agriculture and Fisheries census was conducted in 2021 and 2022 on all islands by MOA, this is conducted every 10 years. The data collected from the Agriculture and Fisheries census will be published on MOA website when the final report is completed in Q4 2022. Support continues for the Crop banks on each of the southern group islands holding climate tolerant varieties of yam (8 Teve, Aprika, sda yam, Sweet yam, Pacific yam, Etene, Parai and Toka), pineapple (3 Ripley Queen, Smooth Cayenne and MD2), bananas (7 Amoa Cavendish, Kings crown, Rokua, Mario, Ducasse, Utu, Ladyfinger) and taro (20 varieties i.e. Manaura, Manaura cross, veo, titi cross, rakahanga cross, papua) and kumara (4 orange, white, purple, yellow). Additional crops are now included in the crop bank such as ginger and tumeric.
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
AF Outcomes
Outcome 1: Reduced exposure to climate-related hazards and threats
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas
Outcome 7: Improved policies and regulations that promote and enforce resilience measures
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Prevent new and reduce existing disaster risk through the implementation of integrated and inclusive economic, structural, legal, social health, cultural, educational, environmental, technological and institutional data. | Integrated data sets inclusive of economic, structural, legal, social health, cultural, educational, environmental, technological and institutional are created at the Pa Enua level and aggregated at the national level | Separate and non-integrated partial data sets | 100% Completed under BSRP Project between 2014-2017. That baseline data is the target geo database for updates by the PEARL Project. Data enhancement/enrichment expanded to include socioeconomic impacts of the COVID-19 Pandemic. | An integrated and inclusive data base is established one year from implementation of the programme
Output 1: Expanded GeoPortal Disaster Risk Management Information System | Number of Pa Enua islands with baseline and updated datasets in the GeoPortal | Nil Pa Enua with baseline and updated datasets in the GeoPortal | 100% reached All Islands in the North and South have been completed. 2021- Islands of Penrhyn, Manihiki and Rakahanga were completed In 2021, 2019 and 2020 Palmerston, Nassau, Aitutaki, Mauke, Mitiaro, Atiu and Mangaia were updated. 2020 DRM Household Surveys were conducted in Rarotonga. Total of 11 Pa Enua since project inception. | All 11 Pa Enua with baseline and updated datasets in the GeoPortal
|  |  | 100% reached AWS - CLEWS DRM and COVID 19 Household Surveys DRM Plans MET Drought Reports. For sustainability of the Project the Cook Islands ICT Department is conducting the licenses and maintenance of the ArcGIS licenses/server and installation of software on approved GIS users, working with Supplier Eagle Technology in New Zealand and partners EMCI/ICI. DRM Information and Communications was strengthened with the procurement and training of Satellite Phones for each of the Pa Enua and Rarotonga to communicate during times of disaster, in partnership with each island government, EMCI, Office of the Prime Minister and Cook Islands Red Cross. Link - website https://emci-site.net/ social media https://www.facebook.com/emciCK Satellite Phone Link - https://www.facebook.com/CookIslandsNews/photos/a.612856485458666/4644989932245281 | Three critical high level hazard risk assessment dataset in the GeoPortal
| Formalise the GIS Taskforce Meetings | No GIS Taskforce | 100% reached GIS Taskforce was formalised in 2019. Adoption of a Geospatial Policy in 2020 and the use of ArcGIS Software for geospatial data management in 2021. | At least 6 meetings per year
Output 2: Management response tools linking hazard risk assessments and the DRM Plans | Number of management response tools/Early Warning Systems | No management response tools | 100% reached AWS – CLEWS DRM Plans MET Services Drought Reports Social Media CSDP NSDP JNAP II COVID-19 Response and DRM Household Survey Website, GEO Portal and information dissemination strengthened. | Three management response tools
| Usage of management response tool/Early Warning System | No Management response tools | 100% reached These are are aggregated. Communication and Awareness has exceeded all targets for 2021 and 2022 through social media, print media, radio and images. Link to some stories - Component 1 COVID-19 Dashboard Early Rainfall Watch update for North pfbid02tPkYmGVeCmFMUg3hSzWb2bp9P7pDD56fM7HynTwMvXCKKNJnG6MAnYQ7QjnVeWcPl .Workshop with 30 participants was also support for under standing rainfall and being better prepared with Cook Islands Met Services in March. Link - https://www.cookislandsnews.com/national/weather/understanding-rainfall-and-being-better-prepared/ https://www.facebook.com/emciCK/posts/pfbid0y3Pjp7UTcwHxewgnJo8JnvzBpShk8wVrUpGKFmu2TMSTGpfKfbXqFMoHRsNofzqVl Climate Science Expo Aitutaki Dec - https://www.facebook.com/climatechangecookislands/posts/4747438771965629Sat Phones - https://www.facebook.com/climatechangecookislands/posts/4729568547085985 AWOS install in Aitutaki- https://www.facebook.com/climatechangecookislands/videos/263412348990613/ Brilliant Resilient Workshop- https://www.facebook.com/climatechangecookislands/posts/4353713754671468Northern Group DRM Household Survey- https://www.facebook.com/climatechangecookislands/posts/3858500144192834 and https://www.facebook.com/climatechangecookislands/posts/3872439752798873 Geo Portal Southern Group Training follow up - https://www.facebook.com/climatechangecookislands/posts/4747438771965629 Geo Portal Southern Group Training - https://www.facebook.com/climatechangecookislands/posts/3796813897028126 Social Media - Facebook, https://www.facebook.com/emciCK, https://www.facebook.com/climatechangecookislands, https://www.facebook.com/cookislands.meteorological. https://www.facebook.com/DCDivision/ Publications - CSDP NSDP JNAP II GEO Portal - and information dissemination strengthened in Q1 2021. Geoportal hosted at https://ckgov.maps.arcgis.com. | Monthly usage of management tools
| New open source or commercial App obtained for the GeoPortal | No App | 100% reached The Survey Form for DRM Household Surveys developed initially using KoboToolBox in 2019 was reviewed and upgraded to use ArcGIS in particular Survey 123. The DRM Household Survey Forms was therefore upgraded to use ArcGIS, and in particular, Survey123 as the tool for developing survey forms/apps. In addition, COVID-19 socioeconomic data collection was also developed using ArcGIS. ArcGIS Licensed Procured on an annual basis. AWS Smart App in Beta Testing | At least one App is obtained and used
| Climate Early Warning Systems are operating on Nassau and Suwarrow | No Climate Early Warning Systems on Nassau and Suwarrow | 100% reached Under the PEARL AF Project, AWS installation were completed on the Pa Enua Islands of Palmerston, Nassau and Suwarrow. First AWOS in the Pa Enua was installed on Aitutaki. This was implemented by Cook Islands MET Services and installed by young Cook Islanders in partnership with the UNDP RESPAC Fund and AF Fund with localize installation. Target of 2 (Suwarrow and Nassau) AWS installations were strengthened with an additional AWS installed in Palmerston and the first Pa Enua AWOS at the Airport in Aitutaki. The completion of the AWS installation for the northern group has improved our capability in monitoring meteorological events which influences global climate change. Project activities are achieved. | Climate Early Warning Systems are installed and operating on Nassau and Suwarrow
Output 3: Robust Pa Enua DRM Plans and capacity building | Number of Pa Enua DRM Plans updated to 2017 National DRM Plan | One Pa Enua DRM Plan (Atiu) updated to 2017 National DRM Plan | 100% Achieved. This is completed and plans strengthened and updated. DRM Plans endorsed and handed out for all eleven (11) Pa Enua through the Pa Enua Brilliant Resilient Workshop for the Mayors and EO's August 2021. Brilliant Resilient Workshop- https://www.facebook.com/climatechangecookislands/posts/4353713754671468 | All 10 Pa Enua DRM Plans updated to 2017 National DRM Plan
| Number of Geo Portal Officers trained on each island by Gender | No officers | Geoportal Training conducted in Q1-2021. User Manual for Geo Portal Use is developed and used for training in Q1 Y3 2021. There were 10 (8 women and 2 men) participants from Mangaia, Mauke, Mitiaro, Atiu and Aitutaki (Southern Group Islands). About 60% were employees of the respective Island governments and the other 40% were from the private sector, mostly self-employed. 80% of participants were women. DRM and COVID 19 Response Household Surveys were completed in Atiu, Aitutaki, Mauke, Mangaia, Mitiaro, Nassau and Palmerston in 2019 and 2020. It is also to be noted that some of the participants above also went through a similiar training when the DRM surveys were carried out through the PEARL Project. As the DRM Survey was progressing through the Pa Enua, it was standard operational procedure to recruit surveyors as part of the survey team. This way, transfer of knowledge and technology use to the Pa Enua is established. | A minimum of one on each island including equal number of women
| Develop user and administration manual for the GeoPortal | Number already trained – (baseline established at inception) | Workshop Training manual for Geo Portal administrations was developed and implemented at the Geo Portal Southern Group training conducted in January to February 2021. Participants were from the Pa Enua islands of Mangaia, Mauke, Mitiaro, Atiu and Aitutaki. The training manual was also utilized during the DRM Household Survey conducted in 2020 in the Northern Group islands of Manihiki, Rakahanga, Penryhn and Pukapuka. | A minimum of 1 training workshop on each island including equal number of women
Outcome 2: Strengthened drinking water security including increased institutional capacity and coordination for integrated water management. | Number of new or existing drinking sources effectively managed for the basic water requirements during periods of drought | Existing Water Capacity for each Island as identified in the Island Profiles | New Water supply infratsructure have been added to the Pa Enua Rainwater harvesting systems; including 8 x 45,000l and 4x 20,000l -Aitutaki.2 x 45,000 l -Mangaia, 8 x 6000l - Palmerston, 10 x 25,000 l PE Tanks Penrhyn; 2 x 45,000l Manihiki plus 5 x 45,000l Rakahanga to be lined. The total capacity provided and completed in the last year was 920,000 additional storage | 20% increase in safe water over Baseline
| Number of communities that maintain safe drinking water supplies to meet basic needs at all times including during periods of drought |  | All 11 inhabited islands maintain safe drinking water systems and water filtration systems are introduced to the islands especially via the schools and centrally located community tanks systems
Output 1:Robust water Monitoring, reporting and assessment systems established and implemented through increased facilitation and the sharing of knowledge | Number of Water Committees | None | The Project committee in Rarotonga provided project oversight and implementation and worked closely with the Island Councils and stakeholders and achieved project milestones as the island based project partners. | Quarterly meetings
| Number of rain gauges, rainfall harvesting surveys, water resources and storage assessments disaggregated by dataset included on the Geo Portal | % water systems complete to date (baseline established at inception) | Rain gauge has been upgraded on all islands. Surveys and assessment of Water tank monitoring equipment (IOTs) piloted on the island of Aitutaki and rolled out to Atiu, Mangaia, Pukapuka, Manihiki and Penrhyn. | Quarterly increase for each island
| Number of reports available to decision makers on local monitoring and assessment information | Nil (baseline established at inception) | Water Security and Drought Management Plans are available and have been discussed with the respective Communities on Mauke, Atiu, Mitiaro, Manihiki, Palmerston, Pukapuka and with officials only for the Rakahanga Water security and Drought Management plans discussions were also held with the Council in Aitutaki as well. These plans were handed out to all islands at the Pa Enua Brilliant Resilient Workshop in August 2021 to Mayors and EO's of each of the 11 Pa Enua islands. | Quarterly increase for each island
| Number of drought assessment methodologies developed and implemented and used | Nil (baseline established at inception) | Target 100% achieved as all 11 islands received Water Security and Drought Management Plans. These plans were handed out to all islands at the Pa Enua Brilliant Resilient Workshop in August 2021 to Mayors and EO'. Rain gauges installed on all the Pa Enua islands especially around the residential zones. This is to improve rainfall tracking. Water monitoring activities based on Water tank levels with the use of IOTs set up on the islands. Strengthened coordination in this area especially in terms of reporting and tracking consistency and timeliness. Streamlined operations also rolled out to the Northern Island Government and helps with the management of watetr resources on the islands | At least one for the North and One for the South
Output 2. Water Resilient Plans including drinking water safety practices | Number of these drought assessments methodologies being used to support local drought management plans | Nil (baseline established at inception) | Target 100% achieved as all 11 islands recieved Water Security and Drought Management Plans. These plans were handed out to all islands at the Pa Enua Brilliant Resilient Workshop in August 2021 to Mayors and EO's of each of the 11 Pa Enua islands. As the Plans are living documents they Works continue to be updated in coordination with the Pa Enua Island governments and key stakeholders. This will need to be continued to be strenghthened after the Project. | At least one in the North and One in the south
| Number of communities and agencies trained in coping with future water security threats | Nil (baseline established at inception) | Target 100% Achieved - Training on coping with water security threats have also been conducted with government workers and with communites and schools on Mangaia,. Rakahanga, Manihiki, Pukapuka, Palmerston and Nassau. | Year on Year increase in trained communities and agencies for each island
| Number of community level drinking water safety plans (dwsp) reviewed and updated and implemented | Nil (baseline established at inception) | The recently reviewed Water Security and Drought Management Plans mentioned above include in it components for , 1. Water development plan, 2. Water safety program as well as 3 the Drought Management plan in 1 document instead of separating these into 3 different wotking documents. These documents have been prepared for all 11 islands in the Pa Enua. | All plans reviewed and updated by Year 3 of the project
| % coverage of Schools and island communities | % existing coverage of schools and communities (baseline established at inception) | Target 100% achieved. Additional work also included running Rainwater Harvesting Training sessions with the schools. This was conducted for some Primary schools in the North; Manihiki - Tukao Primary, Pukapuka. Penrhyn - Omoka and Tetautua Primary schools and also in Aitutaki schools of Araura Primary and the SDA - Te Akaroa Primary school for example. In some island school student also attended the various community workshops and training sessions on drought rmanagement training and presentations, especially on the island of Atiu, Mauke and Mangaia. All schools in the Pa Enua recieved reusable water bottles to ensure access to safe and affordable drinking water and to increase the reliability and quality of water supplies in targeted areas. Mangaia island was the first pilot of the Pa Enua Schools Water Bottle Project and 80% of students are still using their bottles after 1 year. The Health department on the island and the school have also implemented a healthy living and drinking project in the school and monitor the use of the water bottles and contents. This is conducted throughout the year and the school has seen a decrease in single use plastic bottles and increase of 85% of water in the bottles. The other 15% is coconut water. | 100% coverage of Schools and Island Communities by Year 3 of the Project
Output 3. Allocation of Water Security Fund | Number of proposals approved and implemented | Nil | Target 100% achieved. Fund was fully utilised. The call for Water Security Fund went out to the Pa Enua Island Governments for the submission of priority needs on each island. Priority needs have been assessed and work to address areas of concern in water security was presented for implementation in a Project Design Document that was prepared and guided the fully utilisation of the WS funds. | Full utilisation of fund by Year 3 of the programme
Outcome 3: Increased island food security resilience and preparedness for disasters | Number of irrigation system installed | Unknown. A priority for MoA to establish | Target is 100% Completed. 25 Farms supported on all islands in the Southern Group. | One farm per island in Southern Group
| Displacement of island vegetables imports | Unknown. A priority for MoA to establish | Target is 100% Achieved with Hydroponics in Manihiki, Pukapuka, Rakahanga, Nassau, Palmerston, Penrhyn. Hydroponics is the second income earner for the Island Governments of Pukapuka and Manihki providing fresh vegetables for the communities. | 50% of vegetable imports displaced in Northern Group
| Fruit products sold in Rarotonga | Unknown. A priority for MoA to establish | Target is 100% Completed. Market Access and Supply Chain workshop and meetings were conducted with Buyer from Rarotonga to Mayors and EO's in 2021 at the Brilliant Resilient Workshop in August. Pa Enua Participants had the opportunity to meet one on one with buyers to discuss potential future export opportunities from their islands. | 33% rise in fruit products sold from Southern Group
| Improved variety of staple crops | Unknown. A priority for MoA to establish | Target Achieved and continue to be supported with Crop banks implemented in the Pa Enua and data being provided and uploaded to AgIntel. Crop banks have been established on each of the southern group islands holding climate tolerant varieties of yam (8 Teve, Aprika, sda yam, Sweet yam, Pacific yam, Etene, Parai and Toka), pineapple (3 Ripley Queen, Smooth Cayenne and MD2), bananas (7 Amoa Cavendish, Kings crown, Rokua, Mario, Ducasse, Utu, Ladyfinger) and taro (20 varieties i.e. Manaura, Manaura cross, veo, titi cross, rakahanga cross, papua) and kumara (4 orange, white, purple, yellow). Additional crops are now included in the crop bank such as ginger and tumeric. | 50% of planted crops have improved variety
Output 1: Island plant and seedling nurseries | Number of operating island nurseries | A priority for MoA to establish the number of existing nurseries? | Target 100% Achieved- All Pa Enua Islands either have nurseries or hydroponics. (Atiu, Aitutaki, Mauke, Mitiaro, Mangaia, Manihiki, Rakahanga, Nassau, Palmerston, Penrhyn and Pukapuka) | One per island in the Pa Enua
| Number of nursery business plans | Nil (baseline established at inception) | Target 100% Achieved- 8 nurseries are now operating under the Pa Enua Island governments business plan in partnership with the Component 3 lead agency - Ministry of Agriculture. | All nurseries have business plans
| Production capacity utilisation of island nurseries | Unknown. A priority for MoA to establish existing production capacity | Target is 100% Completed with nurseries operating at 75% production capacity. Ministry of Agriculture signed an MOU with each island government and are continuing to work in parternship to provide technical support and advice and is also included in the Agriculture Act 2021. Link to Hydroponic display at Career Expo 2022 by MOA with over 400 students participation https://www.facebook.com/photo/?fbid=387727260046984&set=pb.100064291405585.-2207520000.. | 75% production capacity utilised per nursery
| Operating costs recovery | Unknown. A priority for MoA to establish existing operating costs | 100% Achieved. All farmers that book their seedlings at the MoA nursery are required to pay a fee and also for fruit trees | 100% of operating costs recovered
Output 2: School gardens for the northern group islands | Number of operating school gardens | Two | Target 100% Achieved- 6 of the Northern Group Islands have School Gardens (Manihiki, Pukapuka, Rakahanga. Nassau, Palmerston and Tongareva) Niua School in Pukapuka has worked with MOA and the island government on Home Gardens and also works in partnership with the Hydroponics. 2021 school garden kits and additional support has been provided for sustainability of the school gardens. School gardens have also been strenghened on the islands of Mauke, Atiu, Aitutaki and Mangaia in 2021 working directly with the Islands Governments, MOA and Pa Enua Schools. Food cubes were also purchased for the School garderns for each of the Northern Group to support the school gardens in planting vegetables and herbs. | One per school in Northern Group
| Number of students by gender taught science, social science and health & wellbeing units using school garden | Nil (baseline established at inception) | Target 100% Achieved- Raurau Akamatutu Workshop has worked with the schools in the Pa Enua in the PEARL Project and will continue to do so in on each of the Pa Enua. The PEARL project will build on all this workshops/capacity building for our schools and work with Island Governments and directly with the schools on the islands to continue to support partners for sustainability and Knowledge Materials. Link to Hydroponic display at Career Expo 2022 by MOA with over 400 students particiaption MOA continues to provide handson training and awareness to students at MOA, School Gardens and with Agriculture Island Officers. https://www.facebook.com/photo/?fbid=387727260046984&set=pb.100064291405585.-2207520000.. Agriculute has also provided all schools in the Northern and Southern Group with training tool kit/posters on seedling sowing, staking plants, pruning and transplant seedlings. | 50% of school population annually
Output 3: Tropical orchards technical support for Southern Group islands | Number of orchard with technical support | Two | Target 100% Achieved- A total of 16 orchard, 1x community plantation in Mitiaro and 35 farmers are being assisted in the southern group since 2019, funded by PEARL, however there are still areas that needs strengthening for each orchard to ensure sustainability and MOA will continue to work in partnership with the Island Government, Island Agriculture Departments and beneficiaries to build capacity. | 12 orchards assisted in Southern Group
| Number of community tree management plans implemented | Nil (baseline established at inception) | Target 100% Achieved- Aitutaki, Mangaia, Mauke, Atiu and Mitiaro have completed the tree management plans in 2019/2020/2021. Tree Management manual was updated and focused on citrus and pawpaw. Arapo Calendars were also available for farmers. | One per island in Southern Group
| Productivity of orchards | Unknown. (baseline established at inception) | Target 100% Achieved- Total of 51 Suppliers provide produce to Primefoods in 2021. Data was collected from the Market Acess Report #2 in partnership with Primefoods. Gender Participation of Suppliers – 39% of the Suppliers are Female and 61% are Male. Market Access and Supply Chain workshop and meetings were conducted with Buyer from Rarotonga to farmers on Aitutaki, Mangaia and Pukapuka in 2021. There has been 90 types of produce supplied by the Cook Islands local producers during this reporting period. Previously reported in email on December 16th 2020, 31 Types of Produce were supplied locally. The increase in variety of herbs, fruits and added value produce and sourcing of more locally grown produce and less imported produce has increased the access and demand of variety of produce. Current report also includes Rarotonga suppliers. | 50% productivity improvement in the Southern Group
Output 4: Pa Enua Agriculture Knowledge Sharing Platform | Number of island integrated in AgIntel | Nil | Target 100% Achieved - All 11 inhabited islands in the pa enua are integrated in to Agintel. Southern Group islands are all providing data to the AgIntel. Quarterly reports are uploaded for 2018, 2019 on the MOA website. Northern Group data was collected and will be uploaded to the MOA website. Communications for data collection, ongoing training and feedback is difficult with the remote islands in the North. To assist with communications zoom equipment have been procured for the northern group islands through the government ICT Division out of the Office of the Prime Minister. Link to site - https://agriculture.gov.ck/corporate-services/agintel-report/ | 11 islands
| Number of Pa Enua farmers using E-Agriculture information | Nil | Target 100% Achieved. MOA has also conducted farmers training workshop on each of the islands. Market Access and Supply Chain meetings/worshops have been conducted on the islands of Aitutaki (over 40 participants), Mangaia (97 participants) and Pukapuka (130 participants) in 2020. MOA has also conducted workshops with farmers on Rarotonga. Communications for data collection, ongoing training and feedback is difficult with the remote islands in the North. To assist with communications zoom equipment have been procured for the northern group islands through the government ICT Division out of the Office of the Prime Minister. | 50% of Pa Enua farmers
Output 5: Allocation of Economic Resilience Fund | Number of proposals approved and implemented | Nil | Target 100% achieved. Fund was fully utilised. - Economic Resilience Fund received 165 applicants from all islands in the Pa Enua. 37 applicants were supported through the procurement of various agricultural farming equipment. | Full utilisation of fund by Year 4 of the programme

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | NIE - Specialist' reports on the incorporation of the Gender & ESS in to Project implementation to date were useful in helping to strengthen the project progress reports with the relevant indicators. The Monitoring and Evalution Specialist's review of the project also highlighted some gaps in the implementation and reporting processes to be addressed, PMU - PEARL Project is tracking well with 100% overall target achievement. Covid 19 impeeded on delivery of equipment, materials and transportation. However the Project team were still focused on target completion. Component 2: Shipping was a main issues for the Water project even towards the end of the project causing delays in getting some of the materials to the islands on time. Components of the projects especially the training related to the construction of 20kl tanks and repairs to some 45kl tanks could not be completed during the designated period as the funds were short. Some materials just took too long to make ship to Raro and re-ship to the islands. Component 3: Shipping was a main issues for delays to materials being shipped/air freighted to Pa Enua due to COVID-19 international shipping delays/equipment and materials shortages.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | COVID-19 impeded on delievery of equipment, materials and transportation. Some equipment (i.e. hydroponics/School Garden materials/School Garden Shed/ Food Cubes equipment were delayed due to off loading of cargo and or delays from international shipping which then impedes on domestic shipping. Some islands only have shipping every 3 to 4 months. Flights have also had to be chartered in 2020 and 2021 due to COVID-19 Pa Enua boarder travel restrictions. Some delays for equipment were over 9 months due to international delays. Measures taken to reduce delays was to work with suppliers locally and internationally and communications. Most community based actitvies were implemented as designed. The activities under Water Security Fund grant were changed especially in the concrete mould supply to Palmerston as well additional water tanks being repaired and constructed in Aitutaki
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Component 3 - Market Access/Supply Chain and Farmer Direct training with Rarotonga Buyer (Primefoods Retail store) has increased the produce of exported vegetables and fruits from the Pa Enua especially from Aitutaki, Mangaia, Mauke, Atiu, Palmerston and Pukapuka . Other Food retailer (CITC) is also purchasing produce from the Pa Enua. There has been a huge interest in purchasing vegetables and fruits from the Pa Enua growers. This has had a huge positve impact in the Pa Enua and encouraged more women farmers to export and youth to participate in agriculture.i.e. In Aitutaki two women farmers and a family were affected by COVID-19 travel ban on the tourism industry and had to diversify their business. They were beneficiaries of the AF Project and expanded their domestic business on Aitutaki to Rarotonga with Primefoods. Link - https://www.facebook.com/climatechangecookislands/posts/4492173680825474 and https://www.facebook.com/climatechangecookislands/posts/4492270427482466 Most community based actitvies were implemented as designed The activities under Water Security Fund grant fund were changed especially in the concrete mould supply to Palmerston as well additional water tanks being repaired and constructed in Aituitaki No changes undertaken at this point to change project design although recommendations to improve the Results Framework and uniformity of definitions used have been noted from the endorsed PEARL Project Monitoring and Evaluations Report 2021 and 2022.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Proposed recommendations of findings by the G&ESS and M&E Specialists were presented to the EE agencies to strengthen the implementation of the final phases of the Project. Limited negative impacts on environment and the pa enua communities. Econonmic Resilient Fund and Water Security Funds applications were vetted and Gender, Environmental and Social Safeguard considereations were taken in to account. All project activies take into account ESS and Gender. The minimum use of local sand for the concrete works for water tank repairs and construction activities were encouraged and most physical works involve people from the island themselves
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The gender consideration in the project was prety consistent. This is from works on the island as well as those that were involved in the community training activities as well. Training works inlove communitiesand local institutions where everyone is asked to participate fully(men or women) The PEARL Project will continue to empower Gender, Youth and the most vulnerable in Y3 2021 of the project. Link to the Media Release from Component 1 and 3 highlights gender leadership, capacity building and youth engagement in the PEARL Project. Link - https://www.cookislandsnews.com/internal/national/environment/recently-installed-automatic-weather-stations-in-northern-group-aim-for-more-accurate-forecasts/ Women farmer participation has increase on each of the Pa Enua with ERF and Orchard support provided directly to beneficiaries. https://www.facebook.com/climatechangecookislands/posts/4492173680825474, https://www.facebook.com/climatechangecookislands/posts/4492270427482466, Report on Pa Enua Domestic Export Report #2 showed 51 suppliers to Primefoods and 39% of the Suppliers are Female and 61% are Male. Import Substitution – Primefoods now imports 15 types of produce from the Pa Enua rather than from overseas. Component 2 - Partnership with TAUI with water monitoring of communicty tanks. Link - https://www.facebook.com/taui.cookislands/posts/274410391415308, https://www.facebook.com/taui.cookislands/posts/273737428149271, https://www.facebook.com/taui.cookislands/posts/273120278210986
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Coordination of intelligence, technical know how between the executing agencies and collaborative planning of adaptative activities to climate change is crucial to a collaborative outcome across the Project. For example: Hydroponic garden in drought prone islands require reprogramming of gardening to their wet seasons, the procurement of the desalinator plant may also aid during the drought prone times. Climate resilience interventions should be adapted to each specific location (e.g. each island in the Pa Enua) and not a one solution fits all. The recent increase in risks associated with shipping schedule and shortage in materials supplies (worldwide) from overseas meant a number of activties were not able to be implemented and completed on time. This is a serious problem which will continue to impact upcoming projects as well.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | This can be done provided the financial resources are given to extend this to the required islands. There is a possibility of climate resilience measures to be replicated and scaled up the small grants, water monitoring, enhanced traditional food security practicies/crops theses measures would provide the most impact and be sustainable as they are at the community level. i.e. Pukapuka Traditional Food Security practices still being observed, pracitices and peserved, as their livelihoods depends on those pracitices due to isolation and limited resources. Report Raurau Akamatutu on Pukapuka hightlights this. Link to Pukapuka visit - https://www.facebook.com/climatechangecookislands/posts/3595422337167284
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A - have not received readiness grants
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A - have not received readiness grants
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Increase adoption and use of 20kl concerete water tanks for both community and residential water storage purposes across all the atoll islands will be replicated under a new project. Also completions of the remaining un-repaired community water catchment buildings will need to be replicated and completed for those islands who still have these yet to repair their water buildings
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The replication of this project is highly likely to be increased under a new up coming - Water Scarcity project
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | A number of community water tanks have been repaired or delivered to the islands including a water catchment building in Manihiki. About 7 more mains to be completed .
What measures are/have been put in place to ensure sustainability of the project/program results? | We have also discussed and included these as part of the Island communities water assets which will be managed by the island government especially interms of managing the distribution of the water harvested and stored in the tanks as well as in maintaning these water infrastructure for the community
What measures are being/could have been put in place to improve project/program results? | Encouraging and working with the Council and Island Government to ensure the overall water harvesting systems require careful and continous monitoring to ensure the guttering are in place to maintain effective rainwater capture and harvesting while advocating for the effective maintenance of the water assest
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Informations and water data were used to justify why the Water Security Fund should focus on the atoll islands. This is because in terms of risks exposure the atoll islands have higher exposure to dry spell risks. This allowed us to adopt and conduct similar water infrastructure repairs and support activities across the 7 atoll islands DRM Information and Communications strengthened with the procurement and training of Satellite Phones for each of the Pa Enua and Rarotonga for communications in the event of disasters in partnership with Red Cross and EMCI. Link - website https://emci-site.net/ social media https://www.facebook.com/emciCK Satellite Phone Link - https://www.facebook.com/CookIslandsNews/photos/a.612856485458666/4644989932245281. Installation of AWS/AWOS on each of the islands provided real time climate data for Emergency management response in natural disasters and Pandemics. Historical climate data of the Cook Islands and in the Pacific inform planning and implementation of the Water Security Fund in determining the most suitable options for water catchment and storage. These historical data were sourced from the national Met Office and regional agencies (Pacific-Australia Climate Change Science and Adaptation Planning Programme Partners).
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Infrastructure Cook Islands delivered a number training sessions around the climate change risks and the relationships and connections to water supply shortages. Rainwater Harvesting Training sessions were held with the pa enua communities as well as in the schools. Information relayed by Climate Change through workshopts (Raurau Akamatutu - Basket of Resilience).
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | Component 1 - * Disaster Risk Management Training Materials * ArcGIS geo-portal Training Materials * Geoportal at https://ckgov.maps.arcgis.com * Media releases on project stories highlighting trainings and implementation timelines are done on a regular basis (see links below): Early Rainfall Watch update for North pfbid02tPkYmGVeCmFMUg3hSzWb2bp9P7pDD56fM7HynTwMvXCKKNJnG6MAnYQ7QjnVeWcPl .Workshop with 30 participants was also support for under standing rainfall and being better prepared with Cook Islands Met Services in March. Career Expo Capacity Building https://www.facebook.com/climatechangecookislands/posts/pfbid027FDnh8rWXNADgfa3tAYehT7bkpCbGNqCVDsjq62xYFSitd2WkqucNduuQi4A7i2Rl Component 1 - https://www.facebook.com/climatechangecookislands/posts/pfbid02Ny8DgBFYaANWC3zfykaZjUTVvCVXBaUy1aS26AGSyZmsjm6VXwYKdaMMqzdVqWKYl Component 2 https://www.cookislandsnews.com/uncategorised/new-water-tanks-for-manihiki/ , Component 3 https://www.facebook.com/climatechangecookislands/posts/pfbid0rTA4ZYGAVEYbP6Nxo81fmKAxroRoYezD7UF8aaavTH1Zu5osd4GRMDPNw2nYxHh8l Link - https://www.cookislandsnews.com/national/weather/understanding-rainfall-and-being-better-prepared/ https://www.cookislandsnews.com/outer-islands/singer-enlists-atiu-teens-to-monitor-climate-crisis/ https://www.cookislandsnews.com/outer-islands/growing-to-survive-and-thrive-in-the-pa-enua/ https://www.cookislandsnews.com/outer-islands/supporting-pa-enua-farmers/ https://www.cookislandsnews.com/outer-islands/500k-for-water-system-developments/ https://www.cookislandsnews.com/outer-islands/encouraging-locally-grown-fresh-produce-on-tongareva/ https://www.cookislandsnews.com/national/outer-islands/smart-farming-technology-for-palmerston-and-nassau/ https://www.cookislandsnews.com/internal/national/environment/recently-installed-automatic-weather-stations-in-northern-group-aim-for-more-accurate-forecasts/ https://www.cookislandsnews.com/weather/keeping-an-eye-out-for-unexpected-turn-of-events/ https://www.cookislandsnews.com/internal/national/local/pa-enua-upskilling-in-disaster-management/ https://www.cookislandsnews.com/internal/national/local/building-confidence-through-training/ https://www.cookislandsnews.com/national/outer-islands/new-technology-for-household-surveys-on-rakahanga/ https://www.cookislandsnews.com/internal/national/technology/upskilling-youth-through-technology-based-surveying/ https://www.cookislandsnews.com/internal/national/outer-islands/pm-unveils-food-security-initiative-on-mitiaro/ Component 2 - Water Security and Drought Plans. Banners, Reports and Water Monitoring tools in partnership with TAUI ltd. Workshop materials i.e. presentation and media release. Link - Component 2 TAUI Partnership for Water Tank Monitoring - https://www.facebook.com/climatechangecookislands/posts/4724206720955501 Tree Management and Water Strategies - https://www.facebook.com/climatechangecookislands/posts/4236830269693151 Component 3 AgIntel data collection from all Pa Enua islands, tree management handbooks, school seedling information training flyers/posters, arapo calenders and technical reports, . Banners, Reports and Workshop materials i.e. presentation and media release. Link - Component 3 Aitutaki Beneficiary Orchard Goodway Farm https://www.facebook.com/climatechangecookislands/posts/4677986332244207 Aitutaki Woman farmer ERF beneficiary Nane Purea Aitutaki Hydroponics https://www.facebook.com/climatechangecookislands/posts/4492173680825474 Aitutaki Beneficiaries site visits - https://www.facebook.com/climatechangecookislands/posts/4287137284662449 Tree Management & Water Strategies https://www.facebook.com/climatechangecookislands/posts/4236830269693151 https://www.facebook.com/climatechangecookislands/posts/4200181156691396 Official Handover of the Mitiaro Hydroponics (400 plant capacity hydroponic) https://www.facebook.com/climatechangecookislands/posts/4051981871511326 https://www.cookislandsnews.com/internal/national/outer-islands/pm-unveils-food-security-initiative-on-mitiaro/ Mangaia ERF Recipients - https://www.facebook.com/climatechangecookislands/posts/4039671639409016 Tongareva Hydroponic First Harvest March - https://www.facebook.com/climatechangecookislands/posts/3938245416218306
If learning objectives have been established, have they been met? Please describe. | Learning objectives have been successfully implemented through workshops and targetted training activities, dissemination of information both around climate change and project objectives and outcomes. Knowledge materials are also distributed to stakeholders at workshops and trainings for future reference. A very important Water tank construction training implemented with construction training activities on two tanks identified for Manihiki and was implemented Feb 2022.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | We never have any issues in this area - the project team and local government agencies have close working relationships with local to regional partners to access information.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | It has brought out the general understanding around climate change impact and the risks associated with its resources and infrastructures. New approaches and intel around interpreting data and climate change impacts needs to be promoted in the communities so they also understand their role and engage in building a resilient and adaptive community.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The use of tablets to collect data and information on Disaster Risk Management household surveys enabling live data uploads to the Geoportal. Previously, this information is collected using paper-based forms, tabulated in spreadsheets and then entered into the Geoportal post survey. The process is time consuming and inefficient. This left room for errors and delays in providing updated information. The use of tablets and live updates have minimised this risk and ensured the consistency of the data uploaded. One other feature is that the app can be used offline for those areas with no internet connectivity.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | Adaptation Fund
Yes
No
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | COK/NIE/Multi/2017/1
Implementing Entity | Ministry of Finance and Economic Management
Type of implementing entity | NIE
Country | Cook Islands
Region | Asia-Pacific | [12 empty] | This section needs to be completed for PPR4
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 5000 | 550 | 4450 | Total | 3000 | 330 | 2670 | Total | 5000 | 550 | 4450
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 15% | 15% | 15% | % of Youth beneficiaries | 20% | 20% | 20%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Hurricane | 2: Partially effective | Total | 5000 | Hurricane | 3: Moderately effective | Total | 3000 | Hurricane | 3: Moderately effective | Total | 5000 | Hurricane | 3: Moderately effective
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Water management | Local | 2: Undertaking or updating of assessments in progress | 3 | Water management | Regional | 2: Undertaking or updating of assessments in progress | 3 | Water management | Regional | 2: Undertaking or updating of assessments in progress | 3 | Water management | Regional | 3: Risk and vulnerability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought
|  | 10 | 2: Monitoring and warning service | Geographical coverage | Regional | 10 | 2: Monitoring and warning service | Geographical coverage | Regional | 10 | 2: Monitoring and warning service | Geographical coverage | Regional | 12 | 2: Monitoring and warning service | Geographical coverage | Regional
|  |  |  | Number of municipalities | 9 |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 12
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 |  |  | Total |  |  |  | Total |  |  |  | Total | 580 | Other | 3: Medium capacity
|  | % of female targeted | 0% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted | 60%
Output 2.1 Strengthened capacity of national and sub-national centers and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 539 | 50% | Public |  | 485 | 50% | Public |  | 580 | 60% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Other | 2: Low capacity | Public | National | Other | 3: Medium capacity | Public | National | Other | 3: Medium capacity | Public | National | Other | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Other | 2: Low capacity | 550 | National | Other | 3: Medium capacity | 220 | National | Other | 3: Medium capacity | 550 | National | Other | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Other |  | 50 |  | Other |  | 30% |  | Other |  | 70% |  | Other
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 550 | 50% | 4: Mostly aware |  | 400 | 50% | 4: Mostly aware |  | 2031 | 50% | 4: Mostly aware
Output 3.2: Strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness
|  | 0 | 20% to 39% | 3: Partially aware |  | 2 | 20% to 39% | 3: Partially aware |  | 2 | 20% to 39% | 4: Mostly aware |  | 2 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | handbooks | National |  | 10 | Handbooks | National |  | 4 | Handbooks | National |  | 11 | Handbooks | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Other | National | 2: Partially responsive (Lacks most elements) |  | Other | National | 2: Partially responsive (Lacks most elements) |  | Other | National | 3: Moderately responsive (Some defined elements) |  | Other | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Water management | 2 | Multi-community |  | Water management | 0 | Multi-community |  | Water management | 2 | Multi-community |  | Water management
|  | 0 | National |  | Disaster risk reduction | 11 | National |  | Disaster risk reduction | 7 | National |  | Disaster risk reduction | 11 | National |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 1000 | 50% | 2: Limited improvement |  | 500 | 50% | 2: Limited improvement |  | 1214 | 50% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  |  | 539 | 50% | From 10% to 20% | Agribusiness | 260 | 50% | From 10% to 20% | Agribusiness | 607 | 50% | From 10% to 20% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Multi-sector | Community-based adaptation | 20 | Physical capital | Multi-sector | Community-based adaptation | 10 | Physical capital | Multi-sector | Community-based adaptation | 28 | Physical capital | Multi-sector | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 5: All (Fully integrated) |  |  |  | 4: Most |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 11 | Other | National | Public policy | 11 | Other | National |  | 11 | Other | National |  | 11 | Other | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 11 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 11 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective | 11 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective | 11 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic scale | Type
|  |  | National | [10 empty] | Disaster risk reduction | National | Innovation rolled out
Output 8: Viable innovations are rolled out, scaled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Disaster risk reduction | Undertaking innovative practices | 2: Partially effective | 3 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective | 3 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 3 | Disaster risk reduction | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I21: Melina Tuiravakai: 50 % of total population (i.e. population of 11 Pa Enuas)
Note on K26: Melina Tuiravakai: Raurau Akamatutu Workshop in Atiu, Mauke have incorporated Hurricane Preparedness. Radio, TV and Print Media promote Hurricane Awareness/Preparedness. All Local telephone books include sections on Hurricane Map Tracking and Awareness. Preparedness