## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 8th of October 2020 to 31st of October 2021
| Project Title: | Improving adaptive capacity of vulnerable and food-insecure populations in Lesotho (IACOV)
| Project Summary: | The project aims at building resilience to impacts of climate change while advancing equitable social welfare and income generating opportunities, as well as safeguarding the environment, in three main ways: i) building and strengthening institutional capacity and systems to support communities and household to access climate service information, adapt to and manage climate change risks; ii) strengthening communities’ awareness and understanding of climate change, its impacts and adaptation, and enhancing communities’ ownership of adaptation plans and interventions, including generating behavioural change for effective climate change management; and iii) facilitating community-based local adaptation planning to deploy resilience building measures and adaptation.These objectives will be achieved through three interlinked components: A) Component 1: Institutional capacity and systems building to support national and community adaptation and management of climate change impacts; B) Component 2: Awareness raising of vulnerable communities on climate change impacts and adaptation; and C) Component 3: Strengthening resilience at community level through community-based concrete adaptation measures and improved food systems.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | LSO/MIE/Food/2018/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Food Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Lesotho | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 and 2 - Country-wide (10 districts of Lesotho) Component 3 - three southern districts of Lesotho (Mafeteng, Mohale’s Hoek and Quthing) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 7th of August 2019
IE-AFB Agreement Signature Date: |  | 19th of December 2019 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 8th of October 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | TBD - planned for Q4 2022
| Original Completion Date: | 31st of October 2024
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report - 20th of November, 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Nkopo Matsepe - Project Coordinator | Dominican Republic
| Email: | nkopo.matsepe@wfp.org | Ecuador
| Date: | 28th of September 2021 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Mokoena France - Director a.i (Lesotho Meterological Services) | Equatoral Guinea
| Email: | mokuena.france@gov.ls | Eritrea
| Date: | 28th of September 2021 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms. Aurore Rusiga - UN WFP Representative & Country Director | Fiji
| Email: | aurore.rusiga@wfp.org | Finland
| Date: | 28th of September 2021 | France
| Executing Agency |  | Gambia
| Name: | Mrs. Malehloa Jockey - Meteorologist- Head of Climate Change Unit (Lesotho Meterological Services) | Georgia
| Email: | malehloa.jockey@gov.ls | Germany
| Date: | 28th of September 2021 | Ghana
| Executing Agency |  | Greece
| Name: | Mr. Elias Sekaleli - Director of Forestry (Ministry of Forestry, Range and Soil Conservation) | Grenada
| Email: | elias_sekaleli@yahoo.com | Guatemala
| Date: | 28th of September 2021 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31st October 2021 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31st October 2021 | 2546565 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | A total of $2,546,565 out of a budget of $3,274,057 has been achieved comprised of Actuals totalling $2,275,606 and Commitments totalling $270,959. This has resulted with the overall Burn Rate of 78% during the first year of implementation. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1: Strengthened sub-seasonal to seasonal (S2S) precipitation and temperature forecasting to feed into National Early Warning System (to trigger early action through government safety net programs) | 294863.24
| Output 1.1.2: Capacities strengthened through development of standard operating procedures in response to climate changerelated drought shocks | 80013.74
| Output 1.2.1: Enhanced understanding of local knowledge and beliefs on climate change and acceptability of climate services | 15227.78
| Output 1.2.2: Strengthened access to tailored seasonal forecasts that meet the needs of vulnerable communities | 69937.49
| Output 2.1.1: Coherent and institutionalized multi-level programme on awareness raising on climate change designed and operationalized | 105868.76
| Output 2.1.2: Enhanced capacity of media houses and reporters to effectively write and publish climate change stories | 45660.45
| Output 2.1.3: Communities understand and use climate information and are aware of climate change threats and impacts on food security | 118886.42
| Output 2.1.4: Raised awareness of children through integration of climate change into school curricula and training of teachers on climate change impacts | 66869.63
| Output 3.1.1: Community-based resilience and adaptation plans developed through community-based participatory approaches | 175180.26
| Output 3.1.2: Community nutrition - sensitive productive assets and other livelihood resources developed to support climate risk reduction and adaptation measures | 1071409.35
| Output 3.1.3: Established market linkages for sustained income generation activities | 136306.58
| Project Execution Costs | 210917.02 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| MIE Management Fees (Including ISC) | 155424.1468
| Total | 2546564.8668
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1: Strengthened sub-seasonal to seasonal (S2S) precipitation and temperature forecasting to feed into National Early Warning System (to trigger early action through government safety net programs) | 956209 | 31st October 2022
| Output 1.1.2: Capacities strengthened through development of standard operating procedures in response to climate changerelated drought shocks | 408309 | 31st October 2022
| Output 1.2.1: Enhanced understanding of local knowledge and beliefs on climate change and acceptability of climate services | 68809 | 31st October 2022
| Output 1.2.2: Strengthened access to tailored seasonal forecasts that meet the needs of vulnerable communities | 292809 | 31st October 2022
| Output 2.1.1: Coherent and institutionalized multi-level programme on awareness raising on climate change designed and operationalized | 27659 | 31st October 2022
| Output 2.1.2: Enhanced capacity of media houses and reporters to effectively write and publish climate change stories | 15159 | 31st October 2022
| Output 2.1.3: Communities understand and use climate information and are aware of climate change threats and impacts on food security | 65659 | 31st October 2022
| Output 2.1.4: Raised awareness of children through integration of climate change into school curricula and training of teachers on climate change impacts | 112159 | 31st October 2022
| Output 3.1.1: Community-based resilience and adaptation plans developed through community-based participatory approaches | 65209 | 31st October 2022
| Output 3.1.2: Community nutrition - sensitive productive assets and other livelihood resources developed to support climate risk reduction and adaptation measures | 1346733 | 31st October 2022
| Output 3.1.3: Established market linkages for sustained income generation activities | 232171 | 31st October 2022
| Project Execution Costs | 235150 | 31st October 2022
| MIE Management Fees (Including ISC) | 325212.975
| TOTAL | 4151247.975 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Political Risk | Medium to Low | The operationalisation of the developed MOUs and SOPs between the MIE and EEs has been a fundamental instrument to mitigate political risk which could adversely affect execution of the project activities. During the reporting period, the government reshuffled both the Minister and the Principal Secretary of the Minsitry of Forestry, Range and Soil Conservation (MFRSC) being one of the Executing Entities. Such change in the management of the MFRSC did not affect the delivery of component 3 of the project as the project coordinator with support from the WFP oriented the new Minister and the Principal Secretary about the obligation of the MFRSC in the project. The project is recieving a commendable support from the government due to strong operational partnerships with technical staff and directors in different line ministries as a result of continous interactions on project planning and execution processes. In addition the Project Steering Committee (PSC) is made up of permanent government staff i.e Directors, Managers, who influence decision making processes by the government and their positions are not affected by changes in government.
Technical Capacity of government partners | Medium | The capacity strenghtening of the EEs and other national partners resulted in satisfactory project implementation in the first year. IE continues to develop partnerships with a broad range of development organizations and provide backstopping to ensure sustainability and to limit risks. A strong project management unit team and a Project Steering Committee (PSC) is in place to ensure that the project delivers its objective as approved by the donor.
Natural disasters such as floods, drought in project sites | Medium | The project was not affected by natural disasters during the reporting period. However the project supported the Ministry of Energy and Meteorology to dessiminate seasonal outlook for the period October to December 2021 and the January- March 2022 rainfall. This enhanced the capacity of climate information users including project beneficiaries on seasonal forecasting and the use of seasonal forecasting in alignment with the objectives of the project. The information would be helpful to Farmers and communities in terms of timely planning and preparednes. Most activities on Forecast based Financing will be implemented in year 2 of the project in collaboration with the International Research Institute which was successfull engaged during the reporting period.
Coordination among government agencies will be ineffective due to the large number of agencies involved, possible captured by sectoral interests, and multiple reporting lines | Medium to Low | The project has established a strong leadership committee (PSC) made up of senior technical government officials from different line ministries. The primary role of PSC is to provide strategic direction on important issues like coordination towards effective delivery and greater impact. In last PSC session one of the actions agreed upon was that the project should use and strenghten the existing coordination/planning structures (instead of at district level) to esnure collaboration between the project and other project with similar objectives and working in the same operational areas. Currently the project has collaborated well with GEF funded project to support revitilization of the government district cordination and technical working structures and establishment of clear TORs which clearly articulate the role of each partner and reporting lines.
Environmental risk | Medium to Low | Field activities implemented under component 3 were defined at project inception through community-based participatory planning approaches based on the menu of options pre-identified in consultation with communities during project preparation. This set of options were pre-screened during design phase and activities are categorized low to moderate risk. Specific community adaptation plans are screened before their approval to assess the actual risk category of each activity, taking into consideration the location and the social and environmental context.
People cut down planted trees for fuel wood (other than community forests) | Low | Improved community ownership and protection of natural resources as well as having alternative sources of income and fuel-efficient has reduced this risk to-date.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Public Health risk (Covid-19 pandemic) | Medium | WHO Covid-19 protocols were observed, meetings and workshops were conducted virtually where possible; limited number of participants for face to face meetings. Public works participants engaged in household level activities and not community public works during total lockdown.
Burning of range lands | Medium | Burning of well managed rangelands in some project sites has been a key concern during the reporting period. The project engaged with local authorities and lead departments in the host Ministry of Forestry, range and Soil Conservation, Ministry of Local government as well as the Ministry of Agriculture and Food Security for a need to conduct continous sensitisation sessions with herd boys, youth groups, boys, girls, men and women. These activities will be undertaken in year 2 of project execution.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project was adversely affected by COVID-19. The delivery of important activities such as procurement processes for goods and services, recruitment of project management staff, planned workshops and meetings across the three components was delayed. To address the effects of COVID-19, during the reporting period, the project employed the following mitigation measures: a) To address delays on procurement processes, WFP used some suppliers with long term agreements (LTA) with WFP and other UN agencies like FAO in efforts to minimise lenghthy procurement protocols, reduce lead time while observing compliance rules. b) The use of internal/international WFP staff (i.e activity managers) and EEs technical staff to lead execution processes when recruitment of project management unit staff was delayed. c) Most meetings and workshops were conducted through virtual plartforms with minimal physical participation by stakeholders to ensure undertaking of activities that need gathering of a large number of people in one place: all the meetings and workshops were undertaken in consideration of COVID-19 restrictions and protection measures.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 - Access and equity |  |  | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | Community sensitization meetings to: i) sensitise on the importance of protecting the community assets. ii) defining clear boundaries. iii) identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported. | 3 | Several awareness raising sessions were undertaken through public gatherings where different socio economic groups including livestock owners were engaged in identifying appropriate solutions (i.e mapping special routes for livestock) for protection of community assets such as stonelines, gully structures created by the project during the reporting period. These sessions were facilitated by the Ministry of Forestry, Range and Social Conservation (EE) with technical support from the WFP (IE) which guided messaging and operationalisation of global WFP tools to mitigate and address environmental managemnt challenges. | N/A | N/A
[5 empty] | % Of targeted communities where sensitisation meetings have been conducted at community level | 100% |  | N/A | N/A
[5 empty] | % Of communities/villages disputes resolution initiatives conducted onsite. | 100%
[5 empty] | % Of communities/villages where special livestock routes have been established | 33% |  | N/A | N/A
3 – Marginalized and vulnerable Groups |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 – Human rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Empowerment of women through provision of cash is likely to distort gender relations with their spouses/partners and perpetuate domestic violence within households. | Hold Gender awareness sessions (including GBV issues) to public works participants and surrounding communities. | # Of domestic violence cases reported. | 0 | Modules on on GBV were included in the foremen and secretaries training, so that they could disseminate the information to community members within project sites. | Social and cultural norms that perpetuate inequalities still exist in the project area. These are specifically related to women's roles and responsibilities for domestic work, child care, and limited decision-making. | The project will continue with intensive education and awareness-raising on gender equality. Furthermore, the project shall continue to ensure mainstream gender in all the activities implemented.
|  |  |  | All Project Staff trained on gender- sesntitive approaches. | # of staff trained on gender sensitive approaches | 16 | Training on GBV during foremen and secretaries training is in progress. Foremen and secretaries are then expected to disseminate the information to community members within project sites. | N/A | N/A
|  |  |  | Advocacy to women to make joint decisions on the use of cash with their partners. | % Of Households making joint decisions on the use of cash within the household. | 70% | All data collected during the first year of implementation was disaggregated by sex. In addition, the agenda for all trainings, workshops across the three components of the project, included gender approaches planned/implemented by the project. | N/A | N/A
6 – Core labour rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 – Conservation of biological diversity |  |  | Possible degradation of biodiversity during brush control due to overharvesting of wild plants used as ethno medicines, sources of fuel wood and sale of plant medicines to neighbouring countries. | Public education and awareness on the value of biodiversity to promote Efficient utilisation and conservation of flora medicines. | # Of awareness raising meetings held on biodiversity conservation at community level. | 21 | The technical staff in the MFRSC performed regular monitoring and sensitization meetings with project beneficiaries and community members. This was to ensure that community takes action in the conservation of natural resources. Media institutions i.e local radio stations, newspapers were engaged to educate and change the mindset of Basotho on natural resource management. | Sensitisation meetings were conducted for beneficiaries at the worksites, and not for the whole community. This might decrease sensitization effectiveness. | The project and its stakeholders will ensure that the sensitisation meetings are held at the community level during public gatherings.
[5 empty] | % Of workers aware of biodiversity and its value. | 45%
11 – Climate change |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | Potential pollution of water due to the use of Chemical fertilizers containing phosphates and nitrates where communal gardens are located near waterways. | Awareness raising for communities on the importance of using environment-friendly fertilizers. | # Of awareness raising sessions conducted on the use of environment friendly fertilisers. | 7 | The Ministry of Agriculture has sensitised the community on using environmentally friendly fertilizers during monitoring visits. There were also radio programs educating the nation on using organic fertilizers. | Currently, the communities are not using any fertilisers. However, there is a possibility that when the need arises, they will buy fertilisers that they can afford, and these are non-organic. | There project through component 3 will intensify efforts to improve household income. The Ministry of Agriculture will build communities capacities on how to make their organic fertilizers and as well as different ways of improving soil fertility.
|  |  |  | Training of communities on controlling sources of irrigation, quantity and volume of water use on irrigation. | % Of sites using environmentally friendly fertilisers. | 0
13 – Public health |  |  | Minor injuries to beneficiaries caused by use of poor-quality tools(hammers) and lack of protective clothing. | Procurement of good and durable quality of tools. | Number of incidents reported | 0 | N/A | N/A | N/A
[5 empty] | % of work sides provided with good quality tools. | 21 | The project procured various tools i.e pix axes, watering cans, mattocks, particulalry under component 3 to enable quality creation of assets at national and community levels. | The improper utilisation of tools i.e pick axes, mattocks may expose the project beneficiaries to injuries. | Regular monitoring visits and awareness creation activities to support project beneficiaries are planned for year 2 of the project.
|  |  |  | Availability of a fully equipped first aid kit at each project site. | # of people trained on first Aid | 0 | N/A | N/A | N/A
[5 empty] | Number of first aid kits distributed | 0 | Procurement of Fist aid kits will be done in year 2.
|  |  |  | Training project participants on Health and safety and proper use of equipment | % Of people trained on Training report on Health, safety, and proper use of equipment during the first meetings. | 0 | The intended trainings on health and safety are planned for year 2 of the project execution.
|  |  | Increased spread of Covid-19 virus due to partial observation of national COVID-19 protocols. | Adoption of national health safety protocols (WHO/WFP co) | % of project sites fully observing COVID-19 protocol | 56% | The project promoted wearing of masks at all times and Social distancing. These measures were observed in most cases. Beneficiaries also constructed tippy taps for handwashing. The project influenced changes in work norms such that project beneficiaries worked mostly in household assets and few hours at community assets where a large number of people would gather. Furthermore, the onsite monitoring team sensitised beneficiaries on the importance of adhering to the protocols for their safety and others. | There might be an increased spread of Covid-19 virus due to partial observation of national COVID-19 protocols in some sites. | Continue Community sensitisations through The National COVID-19 Secretariat (NACOSEC) at the district level.
|  |  | Intense and regular sensitisation on safety measures on COVID-19. | # Of COVID-19 awareness sensitisations done on site. | Percentage of project sites covered with COVID-19 awareness and sensitisation sessions. | 85%
14 – Physical and cultural heritage |  |  | Penalisation of workers for not observing the cultural heritage Related to working the land when there are funerals in the community. | Development of operation protocols to observe cultural heritage on site . | Number of operational protocols developed. | 0 | In the one incident that took place, The local authorities only provided a word of caution to observe cultural practices. They however advised the foreman to ensure osbervation of such cultural practices when there is a need. | Penalization of workers for not observing the cultural heritage related to working the land when there are funerals in the community. | Development of operation protocols to observe cultural heritage on site .
15 – Lands and soil conservation |  |  | Possible degradation of the quality or quantity surface water or groundwater due to land management activities. | Planting of trees to hold the soil particles thereby protecting water sources from exposure to pollutants. | # of trees planted | 18900 | The MFRSC led planting of both fruit and forest trees during the reporting period to metigate land degradation and climate change challenges. The MFRSC has promoted planting of indegenous trees. | N/A | N/A
|  |  | Elevated risk of soil erosion on slopes and flat land surface during brush control and construction of gully structures. | Creation of diversions which will channel excess water down the slope to stop and to stop soil from washing away. | % Of project sites with diversion furrows on the slopy part of the catchment. | 65% | The execution of soil and water conservation structure such as diversion farrows during the reporting period with techncial supervision of the MFRSC was done in consideration of quality assurance and sustainability. | N/A | N/A
|  |  |  | Conduct a soil survey and implement activities in accordance with the characteristics of soils, topography, geology, climate, hydrology, and topology; Integrate level soil bunds and terraces with revegetation measures to ensure proper stability (possibly with drought resistant species); Replant trees/vegetation to improve soil/water retention. | % Of soil survey recommendations implemented in project sites. | 0 | The soil survey has been completed and the report finalisation is in progress. | Due to some challenges in the procurement, the soil survey results will be published after the completion of some asset creation activities. | Enure quick finalisation of the soil survey report and aensure that all assets are built followin the survey recommendations.
[5 empty] | % of the area replanted with trees and vegetation for soil retention across the project sites. | 58% | 18000 trees were procured and distributed across all the project sites.
|  |  | Possible degradation of the quality or quantity of surface water or groundwater. Project activities may include the creation of fishponds. Potential impacts are related to the quantity of water that will be harvested from the rivers to service the fishponds and possible impacts of the discharged water on water quality. | Limit the size of fishponds; analyse the hydrology and flow and ensure that water diversion from the river to the fishpond does not exceed the relevant norms; ensure detailed E&S assessment are done should a fish pond be planned. Avoid the entry of contaminants into the water source; Ensure that ponds and other water reservoirs are away from farm drainage and sewage lines and that wells are at a minimum distance of 30 meters from houses and rivers. | Size and location of the fishponds Maintenance plans Water levels in wells or impoundment structures | N/A, this activity was not implemented during the reporting period | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | While no new risks have been identified, the ESMP has been revised based on the screening carried out before implementation and risks and related mitigation measures have been refined. These are all reported under Section 1 above.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE has supported the safeguard measures by giving capacity to project officers in sensitising communities and assisting them to implement the safeguard measures. Orientation workshops were delivered at the central and local level, incorporating ESS related matters in the CBPPs workshop so that the EE could implement the safeguard measures and screen the activities when conducting the CBPPs at community level. WFP also worked with the University of Lesotho to screen all activities before their implementationa and identify mitigation measures for risks identified.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE liaised with local authorities on those social risks as they involved communities. The EE and local authorities made arrangements to minimise the risks. The EE participated in the screening process of all activities together with the University of Lesotho and in the identification of the mitigation measures. Quality assurance of asset creation was ensured by the Ministry of Forestry (EE), performing constant supervision.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, they have been effective as measures were immediately put into place to address the risks that the communities had identified
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Yes
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes. The capacity to implement ESMP is adequate as all responsiblities and roles were assigned to relevant staff in the MIE, EE and project management unit: The project has a dedicated ESMP focal point who received commendable technical backstopping from the WFP regional office and Headquarters to implement the ESMP. Such support extended to the Field Offices, the Ministry of Forestry, Range and Soil Conservation techncial teams, the Ministry of Environment at national and in the districts. The engagement of the National University of Lesotho was an innovative initiative to work with students specialising in environmental management on data collection for development of the ESMP.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
1. Gully Structures(Mafeteng, Mohaleshoek and Quthing) | Yes | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | No | Yes. In addition, during consultations the grievance mechanism has been brought to the attention of all affected communities. | Yes | Community sensitization meetings to: i) sensitise on the importance of protecting the community assets. ii) defining clear boundaries. iii) identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported.
|  | Minor injuries to beneficiaries caused by use of poor-quality tools(hammers) and lack of protective clothing. |  |  |  | Procurement of good and durable quality of tools. | Number of incidents reported
% Of work sites provided with good quality tools.
[6 empty] | Training project participants on Health and safety and proper use of equipment | % Of people trained on Training report on Health, safety, and proper use of equipment during the first meetings
|  | Increased spread of Covid-19 virus due to partial observation of national COVID-19 protocols. |  |  |  | Adoption of national health safety protocols (WHO/WFP co) | % Of project sites fully observing COVID-19 protocols
2. Stonelines(Mafeteng, Mohaleshoek and Quthing) | Yes | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | No | Yes. In addition, during consultations the grievance mechanism has been brought to the attention of all affected communities. | Yes | Community sensitization meetings to: i) sensitise on the importance of protecting the community assets. ii) defining clear boundaries. iii) identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported.
|  | Increased spread of Covid-19 virus due to partial observation of national COVID-19 protocols. |  |  |  | Adoption of national health safety protocols (WHO/WFP co) | % Of project sites fully observing COVID-19 protocols
3. Tree Planting(Mafeteng, Mohaleshoek and Quthing) | Yes | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | No | Yes. In addition, during consultations the grievance mechanism has been brought to the attention of all affected communities. | Yes | Community sensitization meetings to: i) sensitise on the importance of protecting the community assets. ii) defining clear boundaries. iii) identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported.
4. Brush Layering(Mafeteng, Mohaleshoek and Quthing) | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
5. Diversion Furrows(Mafeteng, Mohaleshoek and Quthing) | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
6. Infiltration ditches(Mafeteng, Mohaleshoek and Quthing) | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
7. Terracing | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
8. Water ways, | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
9. Marginal Land rehabilitation | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
10. Retaining Wall | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
11. Spring Tank | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
12. Ponds | No Risk Identified | N/A | N/A | N/A | N/A | N/A | N/A
13. Brush control. | Yes | Elevated risk of soil erosion on slopes and flat land surface during brush control and construction of gully structures. | No | Yes. In addition, during consultations the grievance mechanism has been brought to the attention of all affected communities. | Yes | Creation of diversions which will channel excess water down the slope to stop and to stop soil from washing away. | % Of project sites with diversion furrows on the slopy part of the catchment.
|  | Possible degradation of biodiversity during brush control due to overharvesting of wild plants used as ethno medicines, sources of fuel wood and sale of plant medicines to neighbouring countries. |  |  |  | Public education and awareness on the value of biodiversity to promote Efficient utilisation and conservation of flora medicines. | # Of awareness raising meetings held on biodiversity conservation at community level.
14. Communal gardens | Yes | Potential pollution of water due to the use of Chemical fertilizers containing phosphates and nitrates where communal gardens are located near waterways. | No | Yes. In addition, during consultations the grievance mechanism has been brought to the attention of all affected communities. | Yes | Awareness raising for communities on the importance of using environment-friendly fertilizers. | # Of awareness raising sessions conducted on the use of environment friendly fertilisers.
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Yes, the feedback mechanism has been established. Beneficiaries call a tool-free number and lay their grievances unanomously to safeguard confidentiality and dignity. The beneficiaries are also reporting their feedback on execution of the project to area chiefs, foremen, councills who escalate the issues to the Field Offices.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Disrespectul supervisors towards other community members |  | Supervisors were reprimanded heavily, those accused of GBV were totaly removed from their roles with intervention from the district coordinators in the Minsitry of Forestry, Range and Soil Conservation (MFRSC) and the Ministry of Police where necessary. The action resulted in project beneficiaries working in the project sites conviniently as attested by post distribution reports after the intervention. The measures were taken in line with the operational guidelines by the MFRSC on dismall of project supervisors and beneficiaries who deviate from the set worknorms.
Unequal workloads between men and women |  | The continous gender awareness sessions that were undertaken resulted in positive attidutes, behaviours and beliefs on allocation of tasks between women and men. In the begining of the project, there were some reported cases that men were complaining that men do more work than women. The awareness creation sessions on gender and protection were provided to the village levels authorities including area chiefs, councillors and a specific training was organised for foremen in the three districts where the project operates. This resulted in improved gender relations among participants, better division or allocation of tasks based on ones health status/condition i.e pregnant women at their early stages be given light works like ensure that tippy taps have water and that all beneficiaries have sufficient water duirng working hours.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes, the design of this project was informed by a comprehensive gender assessment- literature review to generate themes, issues, affecting women and men, engagement of women and men, people with disability, analysis of different activities and roles between genders
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Capacities strengthened through development of standard operating procudures in repsonse to climate change related drought shocks. | output 1.1.1 | Number of staff trained to maintain and integrate new observational data in to database, disaggregated by sex | 0 | 12 | Satisfactory performance, 5 men and 1 women from LMS were trained during the reporting period. This gender inbalance is according to the prevailing staffing arrangement in LMS.
| output 1.1.2 | Number of government staff sensitised and trained at national and district level on drought SOPs,disaggregated by sex. | 0 | 100 | The rating is not applicable at this point as the activity will be done in year 2 following the completion of National SOPs for drought.
Strengthened access to tailored climate services by vulnerable communities to improve decison making for food security and livelihood. | Outcome 1.2 | % of households using seasonal forecast in resilient decision making on agricultural/livelihood strategy. | Baseline 7% Female 7.7% Male 6.4% | END 50% (Male 50% Female 50%) | Poor, During the reporting period the project did not progress well on climate service information activities due external factors such as delayed procurement of systems to strenghthen seasonal to subseasonal forecasts to be accesed by community members. However there were pockects of activities such as forecast group discussions, alert messages to support existing LMS and DMA structures such as dessimination of predicted weather forecasts to different sociao economic groups at national, district and community levels.In year 2, there will be a significant improvement of performance of this indicator given the efforts and progress on diffrent activities on this intervention.
SBCC sessions conducted to increase knowledge on nutrition, gender, HIV, GBV,Food Security and climate change adaption. | output 2.1.1 | Number of people reached through inter-personal SBCC approaches | Female 414 Male 200 | Female 23000 Male 19840 | The performance against this indicator is rated as satisfactory. During the training of project sites foremen and secretaries, the participants were trained on issues relating to GBV, HIV/AIDS and nutrition. This training was done so that they would disseminate the information to community members within project sites. Furthermore, the National Climate Change Communication Strategy has been developed. This strategy serves as a wheel through which tailor-made messages on climate change, nutrition, food security etc will be delivered to all levels of society to inform people's decisions and change in behaviour. This is a nation-wide endeavour. In year 2, it is planned that all vulnerable groups will be reached through different platforms with developed messages to intensify their understanding regarding climate change
|  | % of targeted community members (M/F/MY/FY) receiving key messages on climate change adaptation. | Female 27% Male 21% | At least 90% of community members(40% Male and 50% Female) in target villages are sensitised .
|  | % of targeted community members (M/F/MY/FY) receiving key messages on food security | Female 33% Male 25%
|  | % of targeted community members (M/F/MY/FY) receiving key messages on nutrition. | Female 33% Male 16%
Gender Transformative awareness sessions | output 2.1.1.1 | Proportion of women in decision-making relative to men’s | 43% | 60% | The performance against this indicator is rated as good. 61 women were trained out of 101 participants as leaders in the public works programme. These paricipants were empowered to conduct daily register to facilitate for cash transfer to beneficiaries, while at the same communities are supported to develop local resilience through community and household assets.
Community Based Participatory Process unpacking women practical needs and interest | Output 3.1.1 | % of women who participated in CBPP sessions | 56% | 60% | The performance against thisindicator is rated as good. During the CBPP process, each project site selected a committee of not more than 25 participants. 15 of these committee members were women and youth, these women were empowered through the process to select those activities that would assist communities to adapt to effects of climate change, more especially women, disabled persons and youth as climate change affects these groups of society more than the other.
Adoption of the Public works guidelines that incorporate gender issues | output 3.1.2 | Proportion of beneficiaries/participants that are women | 54% | 60% | The performance against this indicator is rated as satisfactory. The public works guideline advocates for engagement of atleast 50% women in the public works programme. Through public works programme, communities are engaged during the lean season to build communal and household assets to improve their nutrition and food security. Moreover, the public works programme cash-transfer activity transferred cash to not less than 5020 women as against the total of approximately 9200 beneficiaries.
Community assets created that respond to needs of women | Output 3.1.2 | # women supported through HH gardening to increase their income levels | 70 | 105 | 70 out of 105 assests were created by women and those assts included vegtable and fruits production, piggery, chicken to respond to iron and protein needs for women (Performance rated good)
| output 3.1.3 | # of women supported to diversify livelihoods through cottage industries that produce handicrafts, and sewing groups. | 0 | 300 | Poor. The process of engaging the CBOs for the implementation of this activity took longer than expected due to the low number of tenders received. The tender was relaunched and this activity will be implemented starting in year 2.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IE has a dedicated Gender Focal Point who supervises undertaking of gender sensitisation and awareness creation sessions by the EEs in the project sites at Mafeteng, Mohale's hoek and Quthing districts. During the reporting period 3 out of 9 sensitisation sessions were performed by the project management unit Field Officers in the above mentioned districts where the project operates. The sessions were done through direct talks with project beneficiaries gathered in groups of 20 in consideration of COVID-19 protocols. The community based participatory planning (CBPP) system of the IE is undertaken with application of gender lens to ensure effective participation of women and men, youth, people with disabilities in the identification of root causes of climate change challenges and appropriate adaptation measures. Climate change setbacks had largely intensified malnutrition and food insecurity due to limited knowledge and poor adaptive capacities. The established national climate change communication strategy (NCCCS) through support of the IE, is aimed at increasing community’s knowledge about climate change as well as ensuring that opinions of women and men, youth, other vulnerable groups like people with disabilities, herd boys e.t.c are taken into consideration on adaptation interventions that inform social behavioural change. The operationalisation of the NCCCS will be done in year 2 of the project given that such strategy was completed towards the end of year 1 in October 2022.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The community based participatory planning (CBPP) processes engaged all representatives from the different livelihood and age groups (women and men, youth, elders, people with disabilities) so that their context-specific issues are identified and prioritized within the plan. In all the gatherings, women comprised of 60% of the participants and during this analysis the four critical elements of protection mainstreaming which are Safety and Dignity, Meaningful Access; Accountability; and Participation and Empowerment were also investigated to ensure communities are not exposed to any risks.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Through technical backstopping of the IE and the project management unit staff, the EEs systematically collected and reported age and sex data for all project beneficiaries. This applied even to all capacity strengthening activities where trainings were offered to both government and project staff . During focus group discussions conducted by the Lesotho Meteorological Services (LMS) to find out perceptions of different socio economic groups about climate services in the project sites, community members were grouped according to their sex and age groups. This enabled LMS to assess how climate service information is interpretted and used by different socio economic groups.
The Ministry of Forestry, Range and Soil Conservation as the lead implementer of public works mainstreamed gender balance on engagement of foremen for supervision of asset creation activities in the project sites. Also, Public works activities were designed to meet the needs or both Men and Women. These activities were also designed to ensure the same workload for both Men and Women.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Under the Ministry of Forestry, Range and Soil Conservation, 40% Men and 60% Women were trained as Foremen and Secretaries to oversee the execution of asset creation activities in the different project sites.The quarterly post distribution monitoring (PDM) reports of the project have proved that arrangements by the EEs to mainstream gender and protection on execution of project activities have been effective. The PDM results showed among others that provision of cash transfers during lean season, allocation of non food items for asset creation, adequately reached men and women, youth who had good knowledge of the objectives of the project as a result of the CBPP. In addition both men and women created assets -piggery, poultry, vegetable production which resulted in improved consumption score and overall improvement in the consumption of protein, iron and vitamin A rich foods . Part of the created assets included woodlots aimed to reduce distance which women travel to access firewood and reduce their expose to gender- based violence which is rife in the country. Focus group discussions conducted during monthly onsite monitoring affirm that both Men and Women carry out the same roles in the project sites.
Lesotho Meterological Services ensured equal representation of both Males and Females(Men 475 Men, and 811 Women) during focus group to establish whether coomunities receive climate services, access,understand and use the information for improved agricultural practices. This discussions were also effective in engaging with IRI to help them further understand the current situation beneficial in designing a sysstem suitable for the Lesotho context taking into consideration specific information needs and priorities for both Men and Women.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | At the beginning of implementation there was limited gender mainstreaming capacities within EE, but provided trainings filled the identified gaps. There was little trust among communities to elect women in leadership positions(foremen); but streamlined sensitisations and trainings challenged the stereotypes and women representation in leadership position improved. The propotion of women to men in leadership position is 53% to 47%.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Yes, both the call centre and direct reporting to EE offices was promoted during the incpetion of the project and continuos sensitisation activities on weekly, monthly and quarterly basis at project sites. These platforms were also widely known to all stakeholders with emphasis on confidentiality and liberty to access the call and approach EE offices. Two operators; man and woman are engaged as focal points in line with WFP Gender Equality and Women Empowerment fulfilment to operationalise the grivience mechanism
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Uneven workload given to men and women (5 cases reported in different project sites) |  | At the beginning of every cycle of work ( three months rotation of workers in the project sites), gender awareness sessions were done aimed at changing attitutes, behaviours and beliefs that reinforce inequalities between women and men. This resulted in improved gender relations among participants, better division or allocation of tasks based on ones demographic location.
Abusive supervisor-verbal abuse targeting women |  | The concerned foremen were immediately removed from their roles and comprehensive Gender Based violence (GBV) awareness sessions including abuse of authorities pointers were conducted to equip all participants.
Limited adherence to COVID-19 protocols in the project sites i.e social distancing and use of PPE |  | Public work norms were changed such that project beneficiaries were encouraged to work mostly on creation of household assets (particularly during lock downs) as against working on community assets where they would gather in large numbers. In addition where community based participation planning was implemented, the project instrumented engagement of few number of people ensuring social distancing, change in working hours from 4 hours a day in community assets to 2 hours a day, establishment and use of tippy taps and promoted the use of PPE.
Limited mobile money agents (mpesa) forcing participants to travel long distances to redeem their monthly entittlements |  | A comprehensive market assessment was done before implementation of Cash Based Transfers to inform location, capacity and number of available agents that would provide cash to beneficiaries in the vicinity of the project sites to avoid long travelling distances. The shops/agents that were identified were those with sufficient liquidity and registered with VODACOM Lesotho which is contracted by WFP to provide cash for public works beneficiaries.
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1.1: Increased knowledge and technical capacity at national and district levels to forecast, plan and anticipate responses to climate change (CC) impacts |  | Outcome 1 | 1. Contract the International Research Institute (IRI) to strengthen capacity of Lesotho Meteorological Services (LMS) and Disater Management Authority(DMA) on early warning, seasonal forecasting, assessments, historical data analysis and Forecast Based Financing (FBF). 2. Identify necessary equipment and activities for development of computing power. Generate specifications for equipment to facilitate procurement processes. 3. Engage the consultant to conduct the national climate and food security analysis on near and long-term impacts of climate change on food security and nutrition. |  | 1. IRI has been contracted and activities have started such as trainings, workshops to orientate technical staff in LMS and DMA on new forecasting models and how forecast based financing FBF model operates towards functionality of the national early warning system. 2. The technical specifications enabling procurement of appropriate High Performance Computing (HPC) system eguipment have been generated and the procurement process is underway pending finalisation of procurement processes in WFP. The intended HPC system will facilitate timely generation, analysis and dessimination of climate service information to the decission makers and the nation through LMS and DMA structures. 3 The recruitement process for the consultant to conduct national climate and food security analysis is in progress with shortlisting process completed this far. This consultant is expected to start work in the initial months of year 2 of the project. | S
Outcome 2
Outcome 3
| Outcome 1.2: Strengthened access to tailored climate services by vulnerable communities to improve decision making for food security and livelihoods |  | Outcome 1 | 1. Conduct the focus groups discussions at community level. 2. Establish partnerships with relevant service providers for most suited dissemination channels for CS and dissemination of information through several channels (radios, TV) 3. Train partners on seasonal forecast and information tailoring, focus groups discussions at community level (focusing on VDMTs). |  | 1. Conducted focus group discussion in the three districts and 2081 members of the communities participated. youth made a total of 795, Men 475, and women 811. 2. initiated partnerships with Vodacom and Econet Lesotho as the two main network service providers for dissimination of climate messages. 3. Partners (40) 21 women and 19 men were sensitized about seasonal forecasting and infornation tailoring. The dessimination of climate change messages was not done as finalisation of the national climate change communication strategy with structured messages, was delayed. | S
| Outcome 2.1: Strengthened awareness of climate change impact on food security amongst vulnerable communities and youth and knowledge of adaptation actions |  | Outcome 3 | 1. Conduct workshops, consultations and focus groups discussions at all levels (national, district and community) to inform the National Climate Change Communication Strategy (NCCCS). 2. Formulate gender-transformative and age-sensitive NCCCS and Implementation plan. 3. Develop action-oriented research programme for tertiary institutions. 4. Review, updated and disseminated the teachers’ climate change tool kit and manual on climate smart agriculture. 5. Train journalists and editors on CC reporting . |  | 1. The NCCCS has been completed and validated by all stakeholders. Workshops for dessimination of the NCCCS are planned for year 2 which will allow its operationalisation to impact knowledge and social behavioural change on climate change adaptation. 2. The Action Oriented Research Concept has been drafted in collaboration with the National University of Lesotho. 3. CC Toolkit for Teachers and the manuals on climate smart agriculture have been updated. 4. A total of 40 (25 women and 15 men) Journalist and 20 (11 females and 9 males) editors have been trained on CC reporting. | MS
| Outcome 3.1 Increased adaptive capacity of communities and households to respond to droughts and water-related hazards |  | Outcome 6 | 1) Develop detailed overlay of available hazards and vulnerability context for the implementation sites; use Seasonal Livelihood Programming (SLP), 2) Organize community meeting to design CBPP and subsequent updates, development of bylaws and community action plans, focus groups discussions, 3) Develop action plan for implementation of community productive assets, optimising synergies across the districts, and specifying time frames and service provider responsibilities, including MoUs. 4)Implement agreed asset creation activities in the three districts according to the detailed asset creation action plan. 5)Conduct situation analysis on post-harvest losses at district level, 6)Train farmers and implement actions on post-harvest losses (e.g. providing tarpaulins, behavioural change interventions, rehabilitation of small structures). 7)Carry out value chain analysis studies for relevant drought-resistant crops leveraging on the work done by FAO – to include sorghum, high-value tree crops, indigenous vegetables, and indigenous medicinal species. 8)Facilitate linkages with WFP local purchase programme and GoL national school feeding programme. 9)Market linkages support to cottage industries for women, particularly handicrafts, using sustainable harvesting of grasses used for ecosystem regeneration (under Output 3.1.2), as well as sewing. 10)Leverage opportunities to link farmers to existing rural finance / micro credit programme |  | 1) In developing maps that show detailed overlay of hazards and vulnerabilities, data has been collected during the community planning exercise and is yet to be used in developing vulnerability maps once the process to engage a consultant will be finalized. 2) Community-based resilience and adaptation plans were developed using a Community-Based Participatory Planning (CBPP) approach. Each of the 21 project sites had its plans prioritizing the assets that communities felt were of utmost importance in improving food and nutrition security as well as household livelihoods. 22 males and 33 females participated in TOT to learn effective CBPP facilitation, after which they facilitated CBPP roll-out to all selected projects sites. Topics of importance included seasonality, protection, gender and environmental safeguard. 3) Following the planning exercise, district action plans were developed highlighting asset creation activities to be undertaken in all project sites for the duration of the project. Project coordination teams established to oversee and ensure execution of all planned activities. 4) A comprehensive soil survey was initiated to inform the type of assets and vegetation to grow in the different project sites; both the vertical and horizontal properties were mapped from the project areas. Report finalization is pending chemical soil analysis which will be finalized once processes to procure chemical reagents have been finalized. However, asset creation activities continued and included gully rehabilitation, range management and brush control, as well as household and communal gardens. Community-targeting was used to identify participating households (52 percent were female headed households, 48 percent male headed households and a total of at least one percent of all households that hosted people with disabilities) to be engaged in implementing asset creation activities. A total of 101 men (40 percent) and women (60 percent) were trained as Foremen and Secretaries to oversee the execution of asset creation activities in the different project sites. 5) In an effort to understand the situation on post-harvest losses (PHL) in the project districts, Consultants have been engaged to undertake the PHL analysis. The study will be finalized in the second year of project implementation, and 6) A food preservation training of trainers was conducted for 26 female agriculture extension officers. The main aim of this training was to equip agriculture extension officers with recent technologies to use in managing food losses and the trainees are expected to roll-out training of farmers in the different project areas. Once the PHL study has been finalized, its report recommendations will be used to inform more farmers trainings on climate smart technologies to use in sustaining their agricultural production as well as to curb the post-harvest losses. 7) Preparation in progress to engage consultants to perform a value chain analysis for drought resistant crops – and drafting of terms of references is ongoing. 8) In an effort to link farmers to markets, a market linkage forum was held in collaboration with the Department of Marketing, to bring together buyers and producers/sellers together. Buyers highlighted their market needs and requirements including the national school feeding programme. The sellers/producers shared information on their areas of operation and the quantities that they produce for access to markets. A total of 52 percent farmers participated, and 25 percent of all participants were buying institutions. Formation of cooperatives and farmers’ commodity groups is ongoing with technical support from Department of Cooperatives. 9) Market linkages to support cottage industries will be finalized upon engagement of a community-based organization which is currently being procured. 10) Profiling of farmers is in progress and once it has been finalized, linkages to micro finance will continue. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Aurore Rusiga
| Email: | UN WFP, Representative and Country Director
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project rating during this reportingperiod is Satisfatory given some concrete achivements in most of the outputs accross the three components, despite the major challenges brought by COVID-19 in the first year. The project recieved sufficient technical backstopping from the WFP technical team in the country , Regional and Headquarters. Some of the key output indicators are in progress due to restrictions that halted trainings, sensitisation processes, physical meetings and workings and focus group discussions at national and district level. However, the project performed quite well in this first year dispite the above mentioned challenges as metigation measures such as the use of WFP Long Term Agreements to address delays in procurement of goods and services, the use of virtual palrtforms for stakeholders' workshops.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1.1: Increased knowledge and technical capacity at national and district levels to forecast, plan and anticipate responses to climate change (CC) impacts |  | Outcome 1 | 1. Contract the International Research Institute (IRI) to strengthen capacity of Lesotho Meteorological Services (LMS) and Disater Management Authority(DMA) on early warning, seasonal forecasting, assessments, historical data analysis and Forecast Based Financing. 2. Identify necessary equipment and activities for development of computing power. Generate specifications for equipment to facilitate procurement processes. 3. Engage the consultant to conduct the national climate and food security analysis on near and long-term impacts of climate change on food security and nutrition. |  | During this implementation period, the project facilitated the establishment of technical teams that will be supporting the implementation of IRI activities. The project supported the reveiw and adoption of the terms of reference for the Early Warning Technical team, the team will be instrumental in implementation of activities related to Forecast Based Financing. LMS, through the support of the project and technical support of UNEP early warning project, conducted an assessment on the computing infrastructure needs for enhanced climate services and FBF, this lead to the identification of HPC specifications that were submitted to WFP CO for procurement. | S
Outcome 2
Outcome 3
| Outcome 1.2: Strengthened access to tailored climate services by vulnerable communities to improve decision making for food security and livelihoods |  | Outcome 1 | 1. Conduct the focus groups discussions at community level. 2. Establish partnerships with relevant service providers for most suited dissemination channels for CS and dissemination of information through several channels (radios, TV) 3. Train partners on seasonal forecast and information tailoring, focus groups discussions at community level (focusing on VDMTs). |  | The project facilitated several sensitization workshops to introduce the project to the partners and stakeholders. During the workshops, LMS had an opportunity to share basic information about seasonal forecasting and how it can be used for seasonal planning. Through the support of the project, LMS successfully disseminated seasonal Forecting ahead of the farming season nationwide. This activity was implemented in collaboration with the UNEP Early Warning Systems project, targetting the district disaster management teams. The LMS teams also had an opportuninty to share basic forecasting information with communities, through the Focus group discussions that were organised by the project. | s
| Outcome 2.1: Strengthened awareness of climate change impact on food security amongst vulnerable communities and youth and knowledge of adaptation actions |  | Outcome 3 | 1. Conduct workshops, consultations and focus groups discussions at all levels (national, district and community) to inform the National Climate Change Communication Strategy (NCCCS). 2. Formulate gender-transformative and age-sensitive NCCCS and Implementation plan. 3. Develop action-oriented research programme for tertiary institutions. 4. Review, updated and disseminated the teachers’ climate change tool kit and manual on climate smart agriculture. 5. Train journalists and editors on CC reporting . |  | The project performed marginally satisfactorily under this outcome as a result of delayed completion of the NCCCS that would enable execution of most activities on awareness creation and advocacy of climate change and adapatation interventions influencing social behavioural change. Given that the NCCCS has been completed towards end of year 1 period in September 2021. Nevertheless the project succeeded to conduct dedicated, separate trainings of editors and journalists on reporting of CC issues. This training was graced by engagement of BBC media experts and resulted in positive reporting of CC by local news papers and radio stations among the media institutions in Lesotho. Finalisation of climate change tool kit in October 2021, marked another milestones reached by the project in efforts to mainstream CC in school carriculum. Most of the activities under this outcome will be executed in year 2 of the project. | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Mokoena France - Director a.i (Lesotho Meterological Services)
| Email: | mokuena.france@gov.ls
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall project implimentation progress is satisfactory. There are a few things particulalry under component 2 of teh project that are still behind due COVID19 pandemic but I am hopeful they will be completed now that restricitions are being relaxed as we transition in to year 2 of the project execution..
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
| Outcome 3.1 Increased adaptive capacity of communities and households to respond to droughts and water-related hazards |  | Outcome 6 | 1) Develop detailed overlay of available hazards and vulnerability context for the implementation sites; use Seasonal Livelihood Programming (SLP), 2) Organize community meeting to design CBPP and subsequent updates, development of bylaws and community action plans, focus groups discussions, 3) Develop action plan for implementation of community productive assets, optimising synergies across the districts, and specifying time frames and service provider responsibilities, including MoUs. 4)Implement agreed asset creation activities in the three districts according to the detailed asset creation action plan. 5)Conduct situation analysis on post-harvest losses at district level, 6)Train farmers and implement actions on post-harvest losses (e.g. providing tarpaulins, behavioural change interventions, rehabilitation of small structures). 7)Carry out value chain analysis studies for relevant drought-resistant crops leveraging on the work done by FAO – to include sorghum, high-value tree crops, indigenous vegetables, and indigenous medicinal species. 8)Facilitate linkages with WFP local purchase programme and GoL national school feeding programme. 9)Market linkages support to cottage industries for women, particularly handicrafts, using sustainable harvesting of grasses used for ecosystem regeneration (under Output 3.1.2), as well as sewing. 10)Leverage opportunities to link farmers to existing rural finance / micro credit programme |  | Most of the project activities have been successfully completed as per the workplan for the first year of project execution. Activities that were aimed at developing community action plans were finalized with the different communities from the different project areas. And in preparation for the community-based planning exercise, trainers that led the exercise were equipped with skills on how to safeguard the environment, mainstream gender, and protection in planning. Each of the districts then prepared their own action plans that will inform asset creation activities in the different project areas. Although not finalized, a comprehensive soil survey was also undertaken to inform some of the asset creation activities to be undertaken in the different areas. The physical soil profiling was finalized with the chemical analysis still pending. In addition to the soil survey, a study to establish the vegetation index was also conducted to provide a baseline so that later as project execution continues the index can be compared as a proxy to the impact of the project on vegetation cover. Moreover, targeting of household to participate in asset creation was led by the communities themselves where opportunities were also given to households hosting persons living with disability. And due to the losses that communities experience, the project engaged consultants to undertake post-harvest losses analysis. Though this study is yet to be finalized, it is to recommend the technologies that farmers and retailers can use in the management of post-harvest losses. A total of 26 extension officers from the ministry of agriculture and food security were trained as trainers in food preservation in anticipation for a step-down training for farmers in the different areas. While there are efforts to support the establishment of farmers cooperatives/associations for group marketing, the project in collaboration with ministry of agriculture held a market linkage forum whose objective was to bring both buyers and sellers together to share information on the market needs including what the national school feeding programme require for farmers’ decision making and linkage for market access. In the same forum, the ministry of energy and meteorology shared a seasonal forecast to help farmers/ producers plan better their agricultural activities. | S
S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Elias Sekaleli-Director of Forestry (Ministry of Forestry, Range and Soil Conservation)
| Email: | elias_sekaleli@yahoo.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Implementation of the project component is satisfactory as most of the planned activities are on track with exception to a few activities including finalization of the soil survey exercise that will inform the selection of assets to be established and or rehabilitated across the different project sites. In addition and due to the nature of the seasonality of some of the activities to be undertaken in asset creation, delays in procurement has affected timely implementation of other activities. The ministry proposes that in moving forward and in addressing the delays, procurement review meetings be held at the end of every month to check on the procurement process and identify areas requiring support.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on F34: Mookho MONNAPULA:

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Impact | Vegetation index in low-lying southern districts | Sparse to Moderate vegetation cover | To be Meseaured at Midterm Evaluation | 10% Improvement in vegetation Index in low lying project areas, as measured by the LDSF.
| Household dietary diversity score | 40% (Low Dietary diversity) | To be Meseaured at Midterm Evaluation | Increased Household dietary diversity to 6 items
Outcome 1.1 | Capacity to produce sub-seasonal to seasonal forecasts, issue sector specific EW, develop drought preparedness protocols & respond accordingly | Limited national tools/capacities to downscale seasonal forecast SOPs for drought preparedness based on S2S EW do not exist at national or district level | Three workshops have been held virtually by IRI, to introduce tools and methods that will be used to enhance the capacity in seasonal forecasting, 6 technical personel from LMS and Distater Managemetn Authority had participated in the workshops. The practical technical training will start once the installation of systems have been done by IRI | LMS has enhanced tools and capacity to downscale forecast and provide accurate drought Early warning . SOPs based on drought Early warning are developed at national level and in pilot districts.
Output 1.1.1 | # Staff trained to maintain and integrate new observational data into database (gender disaggregated) | 0 | 6 | 12
Output 1.1.1 | # web-based map rooms installed in LMS to share observations, develop EW thresholds and triggers, and process S2S forecasts | 0 | 0 Due to Covid-19-related travel restrictions, the installation of the web- based Map rooms will be postponed to year 2. | 3
Output 1.1.1 | S2S forecasting system to cover national and sub-national levels, with 6 month horizon | there is currently no S2S system in place | The building of S2S forecasting system is in progress folowing the engagement of IRI. However, this will be completed in year 2 due to some groundwork that still needs to be done towards buiding the system. The groundwork includes migration of historical data, capacity buiding , procurement of high computing system etc | Specialised S2S forecasting system operational
Output 1.1.2 | Thresholds validated and triggers and actions developed for national SOPs on drought | Thresholds,triggers and actions for national SOPs on drought outdated/not in place. | 0 This will be done in year 2 upon following completion of activities such as stocktaking of current practices and capacity for seasonal forecasting, scoping study on landscape and existing protocols etc. | Thresholds,triggers and actions for national SOPs on drought in place. TORs for National Early Warning technical team done. IRI to support validation on SOPs.
Output 1.1.2 | # district-level SOPs for drought that define field-level actions developed and applied | 0 | 0 This will be done in year 2 following the completion of National SOPs for drought. | 3
Output 1.1.2 | Number of government staff sensitized and trained at national and district level on drought SOPs, disaggregated by sex | 0 | 0 This will be done in year 2 following the completion of National SOPs for drought. | 100
Outcome 1.2 | % of households using seasonal forecast in resilient decision making on agricultural / livelihood strategy | 7% | To be Meseaured at Midterm Evaluation | 50%
Output 1.2.1 | # of studies on local knowledge and beliefs on climate change and acceptability of climate services | 0 | 0 | 2
Output 1.2.2 | # partners capacitated on using seasonal forecasts to develop culturally appropriate CIS | 0 | 0 | 20
Output 1.2.3 | % of targeted people understand the information | 33% | To be Meseaured at Midterm Evaluation | 80%
Outcome 2.1 | % of targeted community members (M/F/MY/FY) receiving key messages on climate change adaptation. | 25% | 0 | 90%
| % of targeted community members (M/F/MY/FY) receiving key messages on food Security. | 30% | 0 | 90%
| % of targeted community members (M/F/MY/FY) receiving key messages on nutrition. | 28% | 0 | 90%
Outcome 2.1 | % of people having knowledge/awareness, attitude and practice on climate adaptation initiatives | 98% | To be Meseaured at Midterm Evaluation | 70%
Output 2.1.1 | Presence of National Climate Change Awareness Raising and Communication Strategy (NCCAR&CS) | 0 | 1 | 1
Output 2.1.1 | # Gender-transformative awareness raising materials on climate change/ food security/ nutrition links for govt., youth, children, herders, etc developed | 0 | 0 | 10
Output 2.1.2 | # journalists trained on climate change reporting | 0 | 53 | 20
Output 2.1.2 | # climate change impacts and adaptation stories published | 0 | 2 | 2
Output 2.1.3 | # District CC AR Strategies and Action Plans, to interface with existing activities and ongoing projects in each of 3 districts | 0 | 0 | 3
Output 2.1.3 | # district and community level CC AR activities implemented | 0 | 0 | 8
Output 2.1.3 | # people reached through inter-personal SBCC approaches (sex- and age-disaggregated) Female | 0 | 414 | 23000
| # people reached through inter-personal SBCC approaches (sex- and age-disaggregated) Male | 0 | 200 | 19840
Output 2.1.4 | # teachers trained on using updated climate change toolkits in schools | 0 | The toolkit has just been updated, 120 teachers are yet to be trained on using the toolkit in classrooms. | 600
Output 2.1.4 | # of schools implementing CSA activities (via upscaled RVCC CSA manuals) | 0 | 0 | 295
Outcome 3.1 | % targeted communities where there is evidence of improved capacity to manage climate shocks and risks | 0 | To be Meseaured at Midterm Evaluation | 80%
Outcome 3.1 | Coping Strategy Index | 32% | To be Meseaured at Midterm Evaluation | <20%
Output 3.1.1 | # community-based resilience and adaptation plans in targeted areas | 0 | 21 | 21
Output 3.1.1 | # cost-benefit analyses on concrete community adaptation measures | 0 | To be Measured as part of the Planned FFA evaluation which is only starting out during this reporting period. | 21
Output 3.1.2 | # community productive assets created through the project | 0 | 57 | 105
Output 3.1.2 | # of tartget HHs (M/F headed with natural and Physical livelihoods created and improved | 0 | 3322 | 23000
Output 3.1.2 | # of fuel efficient stoves provided, with training on their use | 0 | 0 ( procurement of the stoves is in progress | 200
Output 3.1.2 | # of women supported with HH gardening to increase their income levels | 0 | 70 | 4300
Output 3.1.3 | # smallholder farmers supported/trained on reducing post-harvest losses | 0 | 28( Training of trainers trained while more tailored trainings shall be conducted following the post harvest loses study. | 3000
Output 3.1.3 | # Value chain analysis studies for district-relevant drought-resistant crops | 0 | 0( The Terms of reference for engagment of a consultant have just been completed and the activity will be carried over to year 2. | 4
Output 3.1.3 | # of Women Supported to diversify livelihoods through cottage industries that produce handicrafts and sewing groups. | 0 | 0( the process of engaging the CBOs took longer than expected due to the low tenders recieved, therefore the tender was relaunched and the women will be supported in year 2. | 300
Output 3.1.3 | Quantity of food procured from local farmers | 0 | 0( there was poor harvest in the three districts of the project operation, therefore the farmers did not have the required quantity and quality) | 500MT
Output 3.1.3 | Quantity of fortified food including complementary foods and special nutrition products purchased from local suppliers for school feeding | 0 | 645MT | 2500MT

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During the first year of implementation, the project learned much about the importance of healthy partnerships and the significance of community participation in project planning and design; multiple stakeholders and partners highly echoed this. As a positive lesson, the project introduced a robust community engagement tool to facilitate full ownership of the community's project interventions - community-based participatory planning (CBPP). Community participation has enabled the identification of appropriate climate-resilient adaptation measures that are appreciated and sustained. During the first quarter of project execution, the project focused more on community based participatory planning (CBPP) processes that resulted in the development of community action plans enabling execution of activities in the 21 project sites. Full engagement of district and community level stakeholders enhanced ownership of project/program deliverables and results. It has been noted however that the project should focus more on educating commuity members and village level authorities on climate service information such as forecasts in order to inform their decisions on adaptation capabilities to cope with climate change. In year 2 of project, more focus group discussions and trainings are planned to be undertaken to dessiminate climate service information and educate communicate members on early warning protocols informed by FBF.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Covid-19 pandemic had a significant impact on project implementation. The total and partial lockdown delayed the project progress as some important meetings, focus group discussions, conferences for stakeholders, collection of information in the field and key activities across the three project components were halted. However, the project developed a covid19 reprogramming tool to support implementation amidst the pandemic, using new communication modalities e.g.working from home, virtual meetings and modifying other implementation practices in communities like working in household assets instead of community asset creation. These measures yielded positive results to implementation as communities we able to achieve positive results in household food production. Furthermore, meetings with stakeholders continued virtually, and results were still met even though there were limitations of travelling to the field where necessary.
The project was also negatively affected by delayed procurement. Some key items and activities under the three components are still pending or are within the procurement pipeline e.g. Procurement of High Performance Computing system under component 1. The delay emanated from slow processes in procurement resulting from Covid 19 pandemic (total lockdown), slow response of technical personnel to procurement from both IE and EE regarding specification of items, and generally longer processes in procurement to safeguard policies and ensure compliance. However, the project learned much from this issue, and in the 2nd year of implementation the project is working together with IE and EE to improve on planning and ensure that procurement plans are developed timely and accurate specifications are availed to procurement at the start of the year. The Country Office procurement unit with suport from Regional Office, has also pledged to start project procurement processess timely and where necessary, to do bulk procurement and use storage to keep items that will be used later during implementation to fast track project execution.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | There were no changes made to the project outputs and the project design. The only changes made were related to the project activities where a regprogramming tool was implemented to ensure continuity during COVID-19.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | An Environmental and social risk management plan was put in place with monitoring indicators clearly defined. The indicators were monitored regularly through onsite monitoring as well as through the feedback and accountability mechanisms report. Thus the project was able to to mitigate and avoid adverse environmental and social risks and impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations are well mainstreamed in the project interventions. At the beginning of implementing the project's intervention with communities, it was noticed that community members had little trust to elect women in leadership positions. However, the project sensitised communities and challenged the stereotypes around the roles and responsibilities of men and women, which improved women's representation in leadership positions. The project trained 60 women and 40 men that were elected for the leadership roles in the community activities. In implementing the adaptation activities through public works programme, 53% of targeted beneficiaries engaged in the implementation of adaptation activities are women. Activities such as focus group discussions, stakeholder sensitisation sessions, development of the climate change communications strategy were executed to allow full participation of both men and women nationally and from the target communities. Consequently, both men and women have been actively involved in project activities.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | LSO/MIE/Food/2018/1
Implementing Entity | WFP
Type of implementing entity | MIE
Country | Lesotho
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
| Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 42840 | 42840 | 0 | Total | 1101000 | 301000 | 800000 | Total |  |  |  | Total
|  | % of female beneficiaries | 54% | 53% | 0% | % of female beneficiaries | 54% | 52% | 60% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 24% | 24% | 0% | % of Youth beneficiaries | 24% | 24% | 24% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 4: Effective | Total | 115 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments |  | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 10 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2. Strengthened institutional capacity to reduce risk associated with climate- induced socio – economic and environmental losses. | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 115 | Disaster risk reduction | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  |  |  | 12 | 8%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses |  |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 75250 | 29% | 3: Partially aware |  | 301000 | 60% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Food security | land | 4: Effective |  | Food security | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 21 | ha rehabilitated | 4: Effective | Rangelands | 406 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 3 | ha protected | 3: Moderately effective | Forests | 142 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land | 236 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 3322 | 20% | 3: Moderate improvement |  | 23000 | 60% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 1428 | 60% | From 10% to 20% | Agribusiness | 215000 | 60% | From 20% to 30% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  |  | Physical capital | Food security | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness

## Additional Info.
CLIMATE CHANGE PUBLICATIONS AND FEATURES
https://publiceyenews.com/food-insecurity-count-me-out
https://climatetracker.org/lesotho-outdated-land-degredation-laws-soil-erosion/