## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 01st November 2021 to 31st of October 2022
| Project Title: | Improving adaptive capacity of vulnerable and food-insecure populations in Lesotho (IACOV)
| Project Summary: | The project aims at building resilience to the impacts of climate change while advancing equitable social welfare and income-generating opportunities. It also aims to safeguard the environment through the following interlinked components: 1) building and strengthening institutional capacity and systems to support communities and households to access climate service information, and adapt to and manage climate change risks; 2) strengthening communities’ awareness and understanding of climate change, its impacts, and adaptation, and enhancing communities’ ownership of adaptation plans and interventions, including generating the behavioral change for effective climate change management; and 3) facilitating community-based local adaptation planning to deploy resilience building measures and adaptation. The project objectives are in line with the major goals of the government of Lesotho's 2019 National Strategic Development Plan II as well as the WFP’s Country Strategic Plan (2019-2024) outcomes.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | LSO/MIE/Food/2018/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Food Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Lesotho | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 and 2 - Country-wide (10 districts of Lesotho) Component 3 - three southern districts of Lesotho (Mafeteng, Mohale’s Hoek and Quthing) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 7th of August 2019
IE-AFB Agreement Signature Date: |  | 19th of December 2019 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 8th of October 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | TBD - planned for Q4 2022
| Original Completion Date: | 31st of October 2024
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report - 20th of November, 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Nkopo Matsepe - Project Coordinator | Dominican Republic
| Email: | nkopo.matsepe@wfp.org | Ecuador
| Date: | 21st October 2022 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Mokoena France - Director a.i (Lesotho Meteorological Services) | Equatoral Guinea
| Email: | mokuena.france@gov.ls | Eritrea
| Date: | 21st October 2022 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms. Aurore Rusiga - UN WFP Representative & Country Director | Fiji
| Email: | aurore.rusiga@wfp.org | Finland
| Date: | 21st October 2022 | France
| Executing Agency |  | Gambia
| Name: | Mr. Maqhanolle Tsekoa - Meteorologist- Head of Climate Change Unit (Lesotho Meteorological Services) | Georgia
| Email: | relebohile@gmail.com | Germany
| Date: | 21st of October 2022 | Ghana
| Executing Agency |  | Greece
| Name: | Mr. Elias Sekaleli - Director of Forestry (Ministry of Forestry, Range and Soil Conservation) | Grenada
| Email: | elias_sekaleli@yahoo.com | Guatemala
| Date: | 21st of October 2022 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31st October 2021 |  |  |  | Financial information PPR 2: cumulative from project start to 31st October 2022 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30th October 2021 | 2546565 |  |  | Estimated cumulative total disbursement as of 31st October 2022 | 5203997 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | A total of $2,546,565 out of a budget of $3,274,057 has been achieved comprised of Actuals totalling $2,275,606 and Commitments totalling $270,959. This has resulted with the overall Burn Rate of 78% during the first year of implementation. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The project has achieved 77% cummulative burn rate over the two years of implementation. The program performance spent a total of $5,203,997 out of a budget of $6,763,951 which comprised of Actuals and Commitments totalling $4,426,639 and $777,358 respectfully. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1: Strengthened sub-seasonal to seasonal (S2S) precipitation and temperature forecasting to feed into National Early Warning System (to trigger early action through government safety net programs) | 294863.24 |  |  | Output 1.1.1: Strengthened sub-seasonal to seasonal (S2S) precipitation and temperature forecasting to feed into National Early Warning System (to trigger early action through government safety net programs) | 955502
| Output 1.1.2: Capacities strengthened through development of standard operating procedures in response to climate changerelated drought shocks | 80013.74 |  |  | Output 1.1.2: Capacities strengthened through development of standard operating procedures in response to climate changerelated drought shocks | 170656
| Output 1.2.1: Enhanced understanding of local knowledge and beliefs on climate change and acceptability of climate services | 15227.78 |  |  | Output 1.2.1: Enhanced understanding of local knowledge and beliefs on climate change and acceptability of climate services | 26382
| Output 1.2.2: Strengthened access to tailored seasonal forecasts that meet the needs of vulnerable communities | 69937.49 |  |  | Output 1.2.2: Strengthened access to tailored seasonal forecasts that meet the needs of vulnerable communities | 108502
| Output 2.1.1: Coherent and institutionalized multi-level programme on awareness raising on climate change designed and operationalized | 105868.76 |  |  | Output 2.1.1: Coherent and institutionalized multi-level programme on awareness raising on climate change designed and operationalized | 213693
| Output 2.1.2: Enhanced capacity of media houses and reporters to effectively write and publish climate change stories | 45660.45 |  |  | Output 2.1.2: Enhanced capacity of media houses and reporters to effectively write and publish climate change stories | 59801
| Output 2.1.3: Communities understand and use climate information and are aware of climate change threats and impacts on food security | 118886.42 |  |  | Output 2.1.3: Communities understand and use climate information and are aware of climate change threats and impacts on food security | 140613
| Output 2.1.4: Raised awareness of children through integration of climate change into school curricula and training of teachers on climate change impacts | 66869.63 |  |  | Output 2.1.4: Raised awareness of children through integration of climate change into school curricula and training of teachers on climate change impacts | 127532
| Output 3.1.1: Community-based resilience and adaptation plans developed through community-based participatory approaches | 175180.26 |  |  | Output 3.1.1: Community-based resilience and adaptation plans developed through community-based participatory approaches | 238458
| Output 3.1.2: Community nutrition - sensitive productive assets and other livelihood resources developed to support climate risk reduction and adaptation measures | 1071409.35 |  |  | Output 3.1.2: Community nutrition - sensitive productive assets and other livelihood resources developed to support climate risk reduction and adaptation measures | 2253553
| Output 3.1.3: Established market linkages for sustained income generation activities | 136306.58 |  |  | Output 3.1.3: Established market linkages for sustained income generation activities | 222550
| Project Execution Costs | 210917.02 |  |  | Project Execution Costs | 369140 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| MIE Management Fees (Including ISC) | 155424.1468 |  |  | MIE Management Fees (Including ISC) | 317615
| Total | 2546564.8668 |  |  | Total | 5203997
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1: Strengthened sub-seasonal to seasonal (S2S) precipitation and temperature forecasting to feed into National Early Warning System (to trigger early action through government safety net programs) | 956209 | 31st October 2022 |  | Output 1.1.1: Strengthened sub-seasonal to seasonal (S2S) precipitation and temperature forecasting to feed into National Early Warning System (to trigger early action through government safety net programs) | 41209 | 31st October 2023
| Output 1.1.2: Capacities strengthened through development of standard operating procedures in response to climate changerelated drought shocks | 408309 | 31st October 2022 |  | Output 1.1.2: Capacities strengthened through development of standard operating procedures in response to climate changerelated drought shocks | 34309 | 31st October 2023
| Output 1.2.1: Enhanced understanding of local knowledge and beliefs on climate change and acceptability of climate services | 68809 | 31st October 2022 |  | Output 1.2.1: Enhanced understanding of local knowledge and beliefs on climate change and acceptability of climate services | 22809 | 31st October 2023
| Output 1.2.2: Strengthened access to tailored seasonal forecasts that meet the needs of vulnerable communities | 292809 | 31st October 2022 |  | Output 1.2.2: Strengthened access to tailored seasonal forecasts that meet the needs of vulnerable communities | 221309 | 31st October 2023
| Output 2.1.1: Coherent and institutionalized multi-level programme on awareness raising on climate change designed and operationalized | 27659 | 31st October 2022 |  | Output 2.1.1: Coherent and institutionalized multi-level programme on awareness raising on climate change designed and operationalized | 27659 | 31st October 2023
| Output 2.1.2: Enhanced capacity of media houses and reporters to effectively write and publish climate change stories | 15159 | 31st October 2022 |  | Output 2.1.2: Enhanced capacity of media houses and reporters to effectively write and publish climate change stories | 15159 | 31st October 2023
| Output 2.1.3: Communities understand and use climate information and are aware of climate change threats and impacts on food security | 65659 | 31st October 2022 |  | Output 2.1.3: Communities understand and use climate information and are aware of climate change threats and impacts on food security | 46159 | 31st October 2023
| Output 2.1.4: Raised awareness of children through integration of climate change into school curricula and training of teachers on climate change impacts | 112159 | 31st October 2022 |  | Output 2.1.4: Raised awareness of children through integration of climate change into school curricula and training of teachers on climate change impacts | 62159 | 31st October 2023
| Output 3.1.1: Community-based resilience and adaptation plans developed through community-based participatory approaches | 65209 | 31st October 2022 |  | Output 3.1.1: Community-based resilience and adaptation plans developed through community-based participatory approaches | 44009 | 31st October 2023
| Output 3.1.2: Community nutrition - sensitive productive assets and other livelihood resources developed to support climate risk reduction and adaptation measures | 1346733 | 31st October 2022 |  | Output 3.1.2: Community nutrition - sensitive productive assets and other livelihood resources developed to support climate risk reduction and adaptation measures | 1060990 | 31st October 2023
| Output 3.1.3: Established market linkages for sustained income generation activities | 232171 | 31st October 2022 |  | Output 3.1.3: Established market linkages for sustained income generation activities | 99820 | 31st October 2023
| Project Execution Costs | 235150 | 31st October 2022 |  | Project Execution Costs | 194150 | 31st October 2023
| MIE Management Fees (Including ISC) | 325212.975 |  |  | MIE Management Fees (Including ISC) | 158927.985
| TOTAL | 4151247.975 |  |  | TOTAL | 2028668.985 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Political Risk | Medium | During the current reporting period, there has been reshuffling of both the Minister and the Principal Secretary of the Ministry of Forestry, Range and Soil Conservation (MFRSC) being one of the Executing Entities. However such changes in the management of the MFRSC did not affect the delivery of component 3 of the project as the project coordinator played a pivotal role to orientate the new Minister and the Principal Secretary about the obligation of the MFRSC in the project. The project continues to receive commendable support from the government due to strong operational partnerships with technical staff and directors in different line ministries as a result of continuous interactions on project planning and execution processes. In addition, the Project Steering Committee (PSC) is made up of permanent government staff i.e Directors, Managers, who influence decision-making processes by the government, and their positions are not affected by regular changes in government. Furthermore, in the current year, the Country has recently held national elections with a new Government elected into power. A repeat of a similar orientation process has to be done in order to get the buy-in of the new Government.
Technical Capacity of government partners | Medium to Low | The capacity strengthening activities that include training of government staff and other national partners in the utilization of new forecasting approaches among others, progressed well in year 2. These activities contributed to the satisfactory project implementation to date. IE continued to develop partnerships with a broad range of development organizations and provided backstopping to ensure sustainability and government ownership. A strong project management unit team and a Project Steering Committee (PSC) ensure that the project delivers its objective as approved by the donor. A series of capacity building trainings that were undertaken under the components 1 and 2 of the Project are detailed in the Rating section of the report.
Natural disasters such as floods, drought in project sites | High | The project was greatly affected by natural disasters during the reporting period. The country received normal to above normal rains that impacted negatively on the smallholder farmers' produce. Most of the crops were washed away due to flash floods that the country experienced. However, the project continued supporting the Ministry of Energy and Meteorology to disseminate timely seasonal outlook for the period October to December 2021, January- March 2022 and October 2022 to March 2023. This enhanced the capacity of climate information users including project beneficiaries on seasonal forecasting and the use of seasonal forecasts in alignment with the objectives of the project. The information is helpful to farmers and communities for their timely planning and preparedness.
Coordination among government agencies will be ineffective due to the large number of agencies involved, possible captured by sectoral interests, and multiple reporting lines | Medium | The project has established a strong leadership committee (PSC) made up of senior technical government officials from different line ministries. The primary role of PSC is to provide strategic direction on important issues like coordination towards effective delivery and greater impact. In year 2 of the project implementation period, the project facilitated the resuscitation of the project implementation teams(PIT) that were initiated by the previous GEF, IFAD, and EU-supported projects to improve the coordination of planning and execution processes at the district level. Participation in the development partners' forum where a common approach, synergies, and partnerships are rationalized impacted positively in the delivery of some project activities that included the provision of livelihoods and environmental management equipment and materials that are used at the household and community levels. The project coordinator regularly participates in the management meetings of both the Ministry of Energy and Meteorology and the Ministry of Forestry, Range, and Soil Conservation where overall coordination of project activities is streamlined and strategized.
Environmental risk | Medium to Low | Field activities implemented under component 3 were defined at project inception through community-based participatory planning approaches based on the menu of options pre-identified in consultation with communities during project preparation. This set of options were pre-screened during design phase and activities are categorized low to moderate risk. Specific community adaptation plans are screened before their approval to assess the actual risk category of each activity, taking into consideration the location and the social and environmental context.
People cut down planted trees for fuel wood (other than community forests) ,Vandalism of created community assets (Rangelands) | Medium to Low | The project promoted participatory planning and implementation processes that improved community ownership and protection of natural resources as well as having alternative sources of income. The findings of the onsite monitoring activities provided evidence of the reduced risk of vandalism to date. The project with support from the deaprtment of rangeland management within the MFRSC, accelerated the establishment of Grazing Associations to help with the sensitization of herders and livestock farmers. Continuous sensitizations of safe-guarding assets to achieve sustainability were done. Furthermore, the project team in collaboration with WFP resilience team, procured fuel-efficient stoves for distribution to some households in the communuties. More fuel-efficent stoves will be distributed in year 3.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Price hike for goods and services | Medium | High prices of goods and services were experienced in the country as a result of the COVID-19 recovery and the Russian/Ukraine war that negatively affected the local economy. In addressing this risk, the project changed the modalities of undertaking training workshops by without compromising the quality of the content. In addition, the project in consultation with the Executing Entity, revised the specifications for the High Power Computing System which will be upgraded with additional resources. In some cases, the government facilitated collaborations with other projects funded by other development partners such as IFAD, World Vision and EU on provision of inputs (seeds, beehives, fruit trees, poultry stock) to support community development.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project was adversely affected by the post COVID-19 effects and the Russian/Ukraine war with souring effects on the local economy. The procurement of goods and services that included, planned workshops, procurement of High Power Computing (HPC) system, and meetings across the three components was affected by the increasing prices. To address these effects, the project employed the following mitigation measures: a) Revision of specifications for HPC which can be be upgraded in the future. b) Strenghtened partnership with other development partners to establish synergies, share costs and provide the reguired materials at community level toward greater impact c) Some meetings and workshops were conducted through a hybrid of virtual and physical participation by stakeholders.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes, the design of this project was informed by a comprehensive gender assessment- literature review to generate themes, issues, affecting women and men, engagement of women and men, people with disability, analysis of different activities and roles between genders
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Capacities strengthened through development of standard operating procudures in repsonse to climate change related drought shocks. | output 1.1.1 | Number of staff trained to maintain and integrate new observational data in to database, disaggregated by sex | 0 | 12 | Satisfactory : In year 2, 13 officers were trained from the LMS being 10 Males and 3 females. This is because of staffing arrangements in the Department whereby there are more males than females.
| output 1.1.2 | Number of government staff sensitised and trained at national and district level on drought SOPs,disaggregated by sex. | 0 | 100 | Poor : During the reporting period, 27 staff members have been trained on how to set triggers and thresholds to make decisions on anticipatory action. 15 of them were females while 12 were males. The officers were the Lesotho Vulnerability assessment Committee
Strengthened access to tailored climate services by vulnerable communities to improve decison making for food security and livelihood. | Outcome 1.2 | % of households using seasonal forecast in resilient decision making on agricultural/livelihood strategy. | Baseline 7% Female 7.7% Male 6.4% | END 50% (Male 50% Female 50%) | To be captured during the Mid-term review planned for the beginning of YR3.
SBCC sessions conducted to increase knowledge on nutrition, gender, HIV, GBV,Food Security and climate change adaption. | output 2.1.1 | Number of people reached through inter-personal SBCC approaches | Female 414 Male 200 | Female 23000 Male 19840 | Good: During this reporting period, the number of people reached through interpersonal SBCC approches including text messages, community meetings and schools' sensitization meetings is 38,748 (15,841 male, 22,907 female - inclusive of youth reached being 3,700).
|  | % of targeted community members (M/F/MY/FY) receiving key messages on climate change adaptation. | Female 27% Male 21% | At least 90% of community members(40% Male and 50% Female) in target villages are sensitised . | Good: During the reporting period, out of the total community members (38,748) reached with key messages on climate change adaptation, 59% were female and 41% were male. In Year 3, it is planned to broaden the dissemination reach by introducing additional diseemination channels - theatre, content creation, social media, music, dance, poetry, comedians, etc
|  | % of targeted community members (M/F/MY/FY) receiving key messages on food security | Female 33% Male 25%
|  | % of targeted community members (M/F/MY/FY) receiving key messages on nutrition. | Female 33% Male 16%
Gender Transformative awareness sessions | output 2.1.1.1 | Proportion of women in decision-making relative to men’s | 43% | 60% | The performance against this indicator is rated as good. 61 women were trained out of 101 participants as leaders in the public works programme. These paricipants were empowered to conduct daily register to facilitate for cash transfer to beneficiaries, while at the same communities are supported to develop local resilience through community and household assets.
Community Based Participatory Process unpacking women practical needs and interest | Output 3.1.1 | % of women who participated in CBPP sessions | 56% | 60% | The performance against this indicator is rated as good. During the CBPP process, each project site selected a committee of not more than 25 participants. 15 of these committee members were women and youth, these women were empowered through the process to select those activities that would assist communities to adapt to effects of climate change, more especially women, disabled persons and youth as climate change affects these groups of society more than the other.
Adoption of the Public works guidelines that incorporate gender issues | output 3.1.2 | Proportion of beneficiaries/participants that are women | 54% | 60% | Good: The public works programme cash-transfer activity transferred cash to not less than 5020 women as against the total of approximately 9200 beneficiaries. The cash transfer activity has been done to 1615 women against 2692 total beneficiaries that participated in year 2
Community assets created that respond to needs of women | Output 3.1.2 | # women supported through HH gardening to increase their income levels | 70 | 105 | Good: In year 2, 2692 households took part in the public works programe and 1615 were women who established at least one household garden planted with vegetables. Furthermore, the small stock was purchased and distributed to empower women in the household to improve on nutrition and income generation. 45 women received mascovery ducks, 490 women received chicks, 72 women received rabbits, 14 women received piglets, and 5 women who were already progressive farmers in small stock management received shakcks
| output 3.1.3 | # of women supported to diversify livelihoods through cottage industries that produce handicrafts, and sewing groups. | 0 | 300 | Poor: In year 2, at least 50 people are engaged in cottage industries whereby 46 are women and 4 are men. these people are engaged in sewing and knitting, produce cosmetics and already sell locally and at the nearby market as a way to diversify their livelihoods.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IE has a dedicated Gender Focal Point who supervises undertaking of gender sensitisation and awareness creation sessions by the EEs in the project sites at Mafeteng, Mohale's Hoek and Quthing districts. During the reporting period the IE through the gender focal point has supported the project and visited the project sites to do a gender and protection assessment to identify protection risks, capacities, gaps and opportunities protection likely to compromise programme quality. The exercise was done through diverse focus group discussions of men and women and key informants interviews of community leaders. A three-year accountability to affected populations (AAP) workplan was designed. The EE and other strategic actors will be engaged actively during implementation of this plan. The operationalization of the National Climate Change Communication Strategy (NCCCS) started in year 2 of the project. A total of 5 districts namely Mafeteng, Mohale's Hoek, Quthing two mountainous districts of Mokhotlong and Thaba Tseka were reached. The Districts action plans and the related budget were established to enable the required operationalisation of the NCCCS. This activity is ongoing process. Different stakeholders that include herders, school children, local authorities, government officers, and community members received climate change transformative messages. Public gatherings and sms messages were employed as platforms to deliver the messages.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The IE has advised on the implementation of the public works program by initiating the engagement of caregivers to look after children of nursing mothers where those mothers need to participate in the program. This criteria simply gives the lactating mother a chance to participate in the program while also ensures that the children are safe.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | During capacity strengthening workshops for both LMS and DMA officers, the two Departments ensured the participation of both men and women in all their training. In the focus group discussions held by communities during the dissemination of the seasonal forecast, the officers grouped men and women separately to get opinions from each group and re-grouped them together to gather their response as a group
Beekeeping activity in Lesotho has predominantly led by men. Through advocacy and capacity strengthening on gender tranfarmative activities, executing partners and communities were trained on mainstreaming gender and protection issues in apiculture. The Ministry of Forestry, Range, and Soil Conservation therefore, has trained a total of 29 community members of which 18 were females and 11 were males on the basics of beekeeping to sustain their livelihoods.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Under the Ministry of Forestry, Range and Soil Conservation, through the public works programme, communities were supervised to create assets communally and individually for the improvement of their livelihoods. For instance, from the communal orchards, some communities already reap benefits as they sell fruits and vegetables from the communal gardens. This in turn supports the local economy.The small stock which has procured and distributed to community groups and individuals has been performed through the support and supervision of the Ministry of Forestry and Agriculture, this has resulted in improved consumption score and overall improvement in the consumption of protein, iron and vitamin A rich foods. Part of the created assets included woodlots aimed to reduce distance that women travel to access firewood and reduce their exposure to gender- based violence which is rife in the country. Lastly, focus group discussions conducted during monthly onsite monitoring affirm that both Men and Women carry out the same roles in the project sites.
Lesotho Meteorological Services ensured equal representation of both Males and Females(Men 475 Men, and 811 Women) during focus group to establish whether coomunities receive climate services, access,understand and use the information for improved agricultural practices. This discussions were also effective in engaging with IRI to help them further understand the current situation beneficial in designing a sysstem suitable for the Lesotho context taking into consideration specific information needs and priorities for both Men and Women.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | There is still some stereotype behaviour concerning societal roles assigned to both men and women at the community level. During the protection assessment carried out in some project sites, community members mentioned that if men are engaged in public works and receive cash, they do not improve the household livelihood, while the perception of men is that women do not show them enough respect when they are empowered. Through support of IE, sensitisations were held whereby both men and women in the communities were reminded that they each have equal roles in in the improvement of the household and community livelihoods at large.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Yes, both the call centre and direct reporting to EE offices was promoted during the incpetion of the project and continuos sensitisation activities on weekly, monthly and quarterly basis at project sites. These platforms were also widely known to all stakeholders with emphasis on confidentiality and liberty to access the call and approach EE offices. Two operators; man and woman are engaged as focal points in line with WFP Gender Equality and Women Empowerment fulfilment to operationalise the grivience mechanism. This is still the case in year 2
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Outstanding payments of beneficiaries |  | At the beginning of year 2, the IE advised to register all beneficiaries into the WFP Scope platform which is used for beneficiaries registration and management. This platform had some challenges as the staff needed orientation on how to effect their roles, this is the reason why some beneficiaries payments were outstanding for some time while others received their distribution late. At the end of every cycle, all beneficiaries payments were completed.
Foreman who earned twice from the government |  | A foreman was reported for receiving cash transfed from the public work programme while also receiving a pension from the government. The foreman voluntarily resigned from her duties after being reported.
Ill-treatment of a worker by a foreman |  | The grievance was reported to the call centre, a follow-up was made with involvement of a community-based grieviences committee that is made up of the community leadership (area chief and local government councillor) and community representation. Apparently, the worker sent a false alarm due to the fact that the foreman had enough evidence that the worker was always coming late to work and therefore had to stay behind to complete the daily volume of work. As a result this issue was closed through mutual agreement between the two parties.
A report about a foreman secretary who missed working hours at the project site |  | A proper follow-up was made on the issue by the Project Management Unit (PMU) staff, when checking the records and consulting other workers, it was found that there is no such as all participants' record were clear. This issue was then closed with all parties satisfied about the results.
A storekeeper reporting to be unfairly dismissed from project work |  | Through the PMU staff, a follow-up was made on the grivience. It was found that the storekeeper arrives late at work and community workers are not able to access tools to start work on time. As a result the storekeeper was suspended for a week as a form of disciplinary action. But after that period, he was allowed to report back to work with a promise not to repeat the same offence again.
Limited mobile money agents (mpesa) forcing participants to travel long distances to redeem their monthly entittlements. |  | A comprehensive market assessment was done before implementation of Cash Based Transfers to inform location, capacity and number of available agents that would provide cash to beneficiaries in the vicinity of the project sites to avoid long travelling distances. The shops/agents that were identified were those with sufficient liquidity and registered with VODACOM Lesotho which is contracted by WFP to provide cash for public works beneficiaries.Despite this thorough analysis, beneficiaries still complained about the long distances traveled to the agents. They further mentioned that some agents demanded a certain commission before giving out cash despite the charges paid by WFP already. The matter was reported to VODACOM Lesotho and mitigation into this matter is being addressed by VODACOM Lesotho.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 - Access and equity |  |  | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | In addition to community sensitizations, the project supported formulation of the rangeland management Bill and initial drafting of the soil and water conservation regulations that support: i) the importance of protecting community assets. ii) defining clear boundaries. iii) identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported. | 3 | In year 2 the IE gender focal point developed a gender and protection action plan. Using this plan, the awareness raising sessions were contnuously undertaken through public gatherings where different socio economic groups including livestock owners were engaged in identifying appropriate solutions (i.e mapping special routes for livestock) for protection of community assets such as stonelines, gully structures created by the project during the reporting period. These sessions were facilitated by the Ministry of Forestry, Range and Social Conservation (EE) with technical support from the WFP (IE) which guided messaging and operationalisation of global WFP tools to mitigate and address environmental managemental challenges. | some members of the communities and the village authorities i.e chiefs from the villages in the vicinity of the project sites may not be aware of the structural changes in the rangeland management, special routes for livestock and the established routes for livestock. | The project shall upscale the sensitization sessions beyond the project areas. Awareness raising to the village authorities about the rangeland management bill and the soil and water conservation regulations will be conducted. The project will further support the holding of public gatherings in all the villages closer to the project sites to impact knowledge on the protection of community assets.
[5 empty] | % Of targeted communities where sensitisation meetings have been conducted at community level | 100% |  | N/A | N/A
[5 empty] | % Of communities/villages disputes resolution initiatives conducted onsite. | 100%
[5 empty] | % Of communities/villages where special livestock routes have been established | 33% |  | N/A | N/A
3 – Marginalized and vulnerable Groups |  |  | The project has been screened again at project inception and each activity is screened before its implementation. According to the results of these exercises, no risks are identifiedfor marginalized and vulnerable communities.The use of the corporate WFP community-based participatory planning tools (CBPP) ensure that vulnerable members of the communities i.e herdboys, elderly, women ( who may have missed public gatherings when the project was introduced due to conflicting schedules) are fully engaged in the design and execution of the project activities in the communities. The project is executed such that all socio-economic groups are given a fair chance to be assertive and participate. | N/A | N/A | N/A | N/A | N/A | N/A
4 – Human rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Empowerment of women through provision of cash is likely to distort gender relations with their spouses/partners and perpetuate domestic violence within households. | Hold Gender awareness sessions (including GBV issues) to public works participants and surrounding communities. | # Of domestic violence cases reported. | 0 | Modules on on GBV were included in the foremen and secretaries training, so that they could disseminate the information to community members within project sites. | Social and cultural norms that perpetuate inequalities still exist in the project area. These are specifically related to women's roles and responsibilities for domestic work, child care, and limited decision-making. | The project will continue with intensive education and awareness-raising on gender equality. Furthermore, the project shall continue to ensure mainstream gender in all the activities implemented.
[5 empty] | # Of gender awareness sessions held at the community level | 21 | The gender awareness sessions were provided to a total of 40 foremen (35 women and 15 men) who surprised the day to day implementation of the activities putting gender lenses in the 21 project sites at Mafeteng, Mohale's hoek and Quthing Districts. In addition a total of 26 focus group discussions were undertaken in the project sites to discuss gender and protection issues with a cumulative total of 2856 (1836 female and 1020 male) | The gender assessment in April 2022 revealed that there is still lack of knowledge on gender and protection issues due to cultural stereotypes in some communities especially those in the foothills and in the highlands part of the project sites. | As part of operationalisation of the national climate change communication strategy that influence social behavioural change, the project shall continue to do sensiitisation sessions and mainstream gender in all the activities implemented.
|  |  |  | All Project Staff trained on gender- sesntitive approaches. | # of staff trained on gender sensitive approaches | 16 | Training on GBV during foremen and secretaries training was undertaken. Foremen and secretaries are then expected to disseminate the information to community members within project sites. | N/A | N/A
|  |  |  | Advocacy to women to make joint decisions on the use of cash with their partners. | % Of Households making joint decisions on the use of cash within the household. | 70% | All data collected during the first year of implementation was disaggregated by sex. In addition, the agenda for all trainings, workshops across the three components of the project, included gender approaches planned/implemented by the project. | N/A | N/A
6 – Core labour rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | The project was screened again upon inception and all project activities are screened before implementation. As a result of these exercises, no risks have been identified for the protection of natural habitats. The project activities are mainly low-tech in nature and small scale and do not pose any risk to the natural habitats unlike high-tech activities such as road construction e.t.c with adverse impacts on the environment. The application of soil and water conservation interventions by the project are aimed at protecting the natural habitat and are executed under the close technical supervision of the experts within the Ministry of Forestry, Range, Soil and Water conservation. The natural habitats that are protected include grasslands, indigenous trees, wild animals, and herbal plants. | N/A | N/A | N/A | N/A | N/A | N/A
10 – Conservation of biological diversity |  |  | Possible degradation of biodiversity during brush control due to overharvesting of wild plants used as ethno medicines, sources of fuel wood and sale of plant medicines to neighbouring countries. | Public education and awareness on the value of biodiversity to promote Efficient utilisation and conservation of flora medicines. | # Of awareness raising meetings held on biodiversity conservation at community level. | 21 | Sensitization meetings were undertaken to cover the community at large unlike in the first year where the focus was only on the project work sites. The public gatherings were conducted at council levels for this purpose. This was done to ensure that the community takes action in the conservation of natural resources and protects biodiversity. The use of Media institutions i.e local radio stations, and newspapers was instrumental to educate and change the mindset of Basotho on natural resource management. Furthermore, | While MFRSC staff perform regular monitoring processes, the foremen who supervise the day-to-day execution of the activities need orientation on biodiversity. | The scope of work of the refresher training planned for extension workers and foremen in the first quarter of 2023 will include elements of biodiversity. The project will also continue to support the awareness-raising activities in the project sites on biodiversity.
[5 empty] | % Of workers aware of biodiversity and its value. | 45%
11 – Climate change |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | Potential pollution of water due to the use of Chemical fertilizers containing phosphates and nitrates where communal gardens are located near waterways. | Awareness raising for communities on the importance of using environment-friendly fertilizers. | # Of awareness raising sessions conducted on the use of environment friendly fertilisers. | 7 | The Ministry of Agriculture and FAO in collaboration with the project continued to sensitize the community members on using environmentally friendly fertilizers during monitoring visits. There were also joint radio programs educating the nation on using organic fertilizers. A total of 3 project sites namely Mohlakoana in Quthing district, Siloe, and Lithakaling in Mohale's Hoek district are using organic manure for production in their community gardens and at household levels. | Currently, most community members are not using any fertilizers. However, there is a possibility that when the need arises, they will buy the only fertilisers they can afford, which are often non-organic. | The Ministry of Agriculture will build communities capacities on how to make their organic fertilizers and as well as different ways of improving soil fertility. The CBO to be engaged in year 3 will also work with extension offices to monitor and empower communities to sustain manure production using locally available resources.
|  |  |  | Training of communities on controlling sources of irrigation, quantity and volume of water use on irrigation. | % Of sites using environmentally friendly fertilisers. | 0
13 – Public health |  |  | Minor injuries to beneficiaries caused by use of poor-quality tools(hammers) and lack of protective clothing. | Procurement of good and durable quality of tools. | Number of incidents reported | 0 | N/A | N/A | N/A
[5 empty] | % of work sides provided with good quality tools. | 21 | The project continued to procure various tools i.e pix axes, watering cans, and mattocks (among others) particularly under component 3 to enable quality creation of assets at national and community levels. | The improper utilisation of tools i.e pick axes, mattocks may expose the project beneficiaries to injuries. | Although there was no reported injury in the reporting period, the project will continue to provide sensitization messages for beneficiaries to ensure caution in using the procured tools in the project site.
|  |  |  | Availability of a fully equipped first aid kit at each project site. | # of people trained on first Aid | 0 | A total of 103 (29 males and 80 females) village authorities, extension staff, and the village disaster management teams received training on first aid in some project sites in Mafeteng, Mohale's Hoek, and Quthing districts.15 (8 females and 7 males) PMU staff received training on first aid. | Not all project sites were covered during the year 2. Only 8 out of 21 project sites were covered | The project in collaboration with the Lesotho Red Cross Society and the Disaster Management Authority (DMA) developed an action plan for the undertaking of the training of community members and procurement of necessary equipment for the project sites. Such a plan was finalized in the 3rd quarter of 2022 and will be operationalized in 2023
[5 empty] | Number of first aid kits distributed | 0 | During the reporting period, a total of 103 basic first aid kits were distributed only to the extension staff, village authorities, and village disaster management teams in collaboration with Lesotho Red Cross and DMA. 15 (8 females and 7 males) PMU staff also received the first kits. | Not all project sites were covered during the year 2. Only 8 out of 21 project sites were covered | The project in collaboration with the Lesotho Red Cross Society and the Disaster Management Authority (DMA) developed an action plan for the undertaking of the training of community members and procurement of necessary equipment for the project sites. Such a plan was finalized in the 3rd quarter of 2022 and will be operationalized in 2023
|  |  |  | Training project participants on Health and safety and proper use of equipment | % Of people trained on Training report on Health, safety, and proper use of equipment during the first meetings. | 0 | The project provided sensitization messages through public gatherings and onsite monitoring visits on the proper use of tools. The bulk messages on climate change, health, and nutrition issues. | N/A | N/A
|  |  | Increased spread of Covid-19 virus due to partial observation of national COVID-19 protocols. | Adoption of national health safety protocols (WHO/WFP co) | % of project sites fully observing COVID-19 protocol | 56% | The government canceled COVID-19 restrictions. | N/A | N/A
|  |  | Intense and regular sensitisation on safety measures on COVID-19. | # Of COVID-19 awareness sensitisations done on site. | Percentage of project sites covered with COVID-19 awareness and sensitisation sessions. | 85%
14 – Physical and cultural heritage |  |  | Penalisation of workers for not observing the cultural heritage Related to working the land when there are funerals in the community. | Development of operation protocols to observe cultural heritage on site . | Number of operational protocols developed. | 0 | The work norms were revised and structured such that project activities are not implemented when funerals are administered to respect cultural values | N/A | N/A
15 – Lands and soil conservation |  |  | Possible degradation of the quality or quantity surface water or groundwater due to land management activities. | Planting of trees to hold the soil particles thereby protecting water sources from exposure to pollutants. | # of trees planted | 18900 | The MFRSC continued to lead the planting of both fruit and forest trees during the reporting period to mitigate land degradation and climate change challenges. The MFRSC has promoted the planting of indigenous trees. | Financing the additional quantity of trees reguired to be planted remains a challenge | The project through support of the IE will continue to strengthen partnership with other development partners to join effort to buy more tree to carter for non survival and planting of more trees in the project sites and in the near by villages.
|  |  | Elevated risk of soil erosion on slopes and flat land surface during brush control and construction of gully structures. | Creation of diversions which will channel excess water down the slope to stop and to stop soil from washing away. | % Of project sites with diversion furrows on the slopy part of the catchment. | 65% | The execution of soil and water conservation structure such as diversion farrows during the reporting period with techncial supervision of the MFRSC was done in consideration of quality assurance and sustainability. | During the reporting year, it was observed that foremen will need refresher trainings on supervising application of soil and water conservation techniques. | In year 3, referseher trainings for foremen and secretaries will be prioritised as part of the exit plan for the asset creation activities.
|  |  |  | Conduct a soil survey and implement activities in accordance with the characteristics of soils, topography, geology, climate, hydrology, and topology; Integrate level soil bunds and terraces with revegetation measures to ensure proper stability (possibly with drought resistant species); Replant trees/vegetation to improve soil/water retention. | % Of soil survey recommendations implemented in project sites. | 0 | The soil survey was completed in 2021 | The soil survey report is still incomplete due to the inevitable backlog in agric research, which serves the entire country. | Ensure quick finalisation of the soil survey report and ensure that all assets are built following the survey recommendations.
[5 empty] | % of the area replanted with trees and vegetation for soil retention across the project sites. | 58% | 22450 trees with in-kind support from the MFRSC were distributed across all the project sites.
|  |  | Possible degradation of the quality or quantity of surface water or groundwater. Project activities may include the creation of fishponds. Potential impacts are related to the quantity of water that will be harvested from the rivers to service the fishponds and possible impacts of the discharged water on water quality. | Limit the size of fishponds; analyse the hydrology and flow and ensure that water diversion from the river to the fishpond does not exceed the relevant norms; ensure detailed E&S assessment are done should a fish pond be planned. Avoid the entry of contaminants into the water source; Ensure that ponds and other water reservoirs are away from farm drainage and sewage lines and that wells are at a minimum distance of 30 meters from houses and rivers. | Size and location of the fishponds Maintenance plans Water levels in wells or impoundment structures |  | 1 project beneficiary in the Quthing district was assisted to establish one fishpond (3 by 3 meters). The location and the dimensions were established with technical support from the MFRSC and the Ministry of agriculture on ensuring compliance with E&S and sustenance principles. The pond is at an initial stage of use as it was completed in August 2022/ | Safe utilization of the pond to avoid any unforeseen hazards | The project will support regular monitoring of the pond by the experts in the MFRSC to ensure safety measure and upscale this initiative to other areas
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | There were no new risks identified during the reporting year. The ESMP has however been revised based on the implementation of mitigation measures resulting from the screening exercise at the beginning of the project.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In efforts to strengthen the capacity of the IE to provide technical backstopping to the project on effective implementation of ESP safeguard measures, the WFP Lesotho program team received a full-fledged training from WFP HQ ESS team on AF ESP compliance. The training was concluded with the nomination of an ESS focal point within the IE to ensure the operationalization of the ESS measures working with the ministry of environment to lead the implementation of such measures.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | During the reporting period, the project supported the MFRSC to orientate the directors in relevant line ministries such as the ministry of environment, the ministry of agriculture, and other development partners such as FAO, and GIZ on the AF and WFP ESS framework and established a lead focal point. This facilitated the effective coordination of implementation processes and reporting of ESS activities at national and district levels.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, they have been effective as measures were immediately put into place to address the risks that the communities had identified
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Yes
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes. The capacity to implement ESMP is adequate as all responsibilities and roles were assigned to relevant staff in the MIE, EE, and project management unit. This is facilitated by the continuous support that the project receives from the WFP regional and HQ experts who provide regular oversight missions and refresher training when necessary.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
1. Gully Structures(Mafeteng, Mohaleshoek and Quthing) | Yes | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | No | Yes. | Yes | In addition to the community sensitization meetings that were undertaken during the reporting period, the project supported the formulation of the rangeland management bill and soil and water conservation regulations of the MFRSC to formalize and articulate: i) the importance of protecting community assets and the penalities for trespassers. ii) clear definition of the boundaries of the environmental management activities in the communities. iii) the need for identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported.
[6 empty] | Procurement of good and durable quality of tools. | Number of incidents reported
% Of work sites provided with good quality tools.
[6 empty] | Training project participants on Health and safety and proper use of equipment | % Of people trained on Training report on Health, safety, and proper use of equipment during the first meetings
[6 empty] | Adoption of national health safety protocols (WHO/WFP co) | % Of project sites fully observing COVID-19 protocols
2. Stonelines(Mafeteng, Mohaleshoek and Quthing) | Yes | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | No | Yes. In addition, during consultations the grievance mechanism has been brought to the attention of all affected communities. | Yes | Community sensitization meetings to: i) sensitise on the importance of protecting the community assets. ii) defining clear boundaries. iii) identifying special routes for livestock leading to grazing areas or drinking points. | Number of disputes reported.
|  | Increased spread of Covid-19 virus due to partial observation of national COVID-19 protocols. |  |  |  | Adoption of national health safety protocols (WHO/WFP co) | % Of project sites fully observing COVID-19 protocols
3. Tree Planting(Mafeteng, Mohaleshoek and Quthing) | Yes | Possible disputes between on-site workers and livestock owners due to assets (i.e., stone lines, tree planting, gully reclamation assets) being disrupted by the passage of livestock towards grazing areas. | No | Yes. Consultations were undertaken where necessary and the grievance on damages on tree planting mechanism reported through call centre were brought to the attention of all affected communities and the authorities. | Yes | Community sensitization meetings through public gatherings in the affected public work sites. | Number of disputes reported.
4. Brush Layering(Mafeteng, Mohaleshoek and Quthing) | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
5. Diversion Furrows(Mafeteng, Mohaleshoek and Quthing) | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
6. Infiltration ditches(Mafeteng, Mohaleshoek and Quthing) | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
7. Terracing | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
8. Water ways, | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
9. Marginal Land rehabilitation | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
10. Retaining Wall | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
11. Spring Tank | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
12. Ponds | Yes | No Risk Identified | N/A | N/A | N/A | N/A | N/A
13. Brush control. | Yes | Elevated risk of soil erosion on slopes and flat land surface during brush control and construction of gully structures. | No | Yes. | Yes | Creation of diversions which will channel excess water down the slope to stop and to stop soil from washing away. | % Of project sites with diversion furrows on the slopy part of the catchment.
|  | Possible degradation of biodiversity during brush control due to overharvesting of wild plants used as ethno medicines, sources of fuel wood and sale of plant medicines to neighbouring countries. |  |  |  | Public education and awareness on the value of biodiversity to promote Efficient utilisation and conservation of flora medicines. | # Of awareness raising meetings held on biodiversity conservation at community level.
14. Communal gardens | Yes | Potential pollution of water due to the use of Chemical fertilizers containing phosphates and nitrates where communal gardens are located near waterways. | No | Yes. | Yes | Awareness raising for communities on the importance of using environment-friendly fertilizers. | # Of awareness raising sessions conducted on the use of environment friendly fertilisers.
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Yes, there is a dedicated toll-free number where community members can anonymously report their grievances in adherence to confidentiality and dignity principles. The call center facility is managed by the National University of Lesotho as an independent and neutral partner that is not involved in the execution processes. The beneficiaries can also report their feedback on the execution of the project to area chiefs, foremen, and councills who escalate the issues to the Field Offices.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Delayed payment of cash-based transfers (CBT) to the project beneficiaries. |  | The payments of CBT to the beneficiaries are done on monthly basis during the lean season period. Such payments are done through the Vodacom MPESA facility where beneficiaries are required to register using their national IDs and use sim cards to redeem money in local shops serving as Vodacom Mpesa agents. In year 2, the project received a relatively high grievance related to delayed CBT payments due to lost or misplaced sim cards and the MPESA agenda not having enough flood/cash. With support from the IE, such an issue was reported to VODACOM which facilitated the dynamism of their offices in the project operational areas to allocate new sim cards without charging the beneficiaries and ensuring enough flood in all the agents serving the project beneficiaries.
Abuse of authority/ill-treatment of beneficiaries by foremen |  | Through a toll-free call center, there was one reported case of a foreman abusing their authority by either arriving late at work or treating project beneficiaries differently. When project management unit staff followed up on the case working with the village-level authorities, it was discovered that the beneficiary reported false information: Investigations revealed that the beneficiary deliberately missed some workdays (3 days) without completing a set volume of work which is against work norms. The beneficiary was therefore omitted by the foremen in the CBT payment list for that particular month and hence why he reported the case. The issue was settled with the mutual understanding that the beneficiary will be paid CBT after completing the allocated volume of work for that month
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1.1: Increased knowledge and technical capacity at national and district levels to forecast, plan and anticipate responses to climate change (CC) impacts. |  | Outcome 1 | 1. Engagement of International Research Institutute (IRI) at Columbia University to provide capacity to Lesotho Meterological Services (LMS) technical team on seasonal and sub-seasonal forecasting using PyCPT software. Furthermore, IRI to capacitate LMS on installation of data libraries (DL) on LMS server including training staff on DL maintenance. Furthermore, IRI to provide capacity on the development, maintenance and updating of python based maprooms. 2. IRI to capacitate Disaster Management Authority (DMA) on Forecast Based Finacing/Anticipatory Action model, focusing especially on development of SOPs for drought, including triggers and thresholds settings. 3. Engagement of the local consultant to conduct a study on impact of climate change on Food Security and Nutrition - looking and near and long term impact. ​ 4. - Support LMS to develop 2022 winter season outlook and generate Lesotho cropping season for the period October 2022 to March 2023 using PyCPT​. - Remotely train LMS staff on the latest version of IRI’s Climate Data Tool (CDT) to improve LMS database. 5. Source National Vulnerability data from multiple stakeholders supported by DMA to establish vulnerability data sets for Lesotho (drought aligned) and avail such data to IRI. ​6. Facilitate Procurement of High Power Compputing System (HPC) to support high level data management and multiple datasets analysis - the system is intended to support LMS, DMA and other relevant stakeholders. Additionally, support EWS II project in procurement of Automated Weather Stations to improve forecasting by LMS, this AWS will be installed in 10 districts of the country. 7. Support LMS and DMA (Early Warning Technical Team) to disseminate seasonal forecast and early warning messages for season starting October, November and December (OND) 2022 and January, February and March (JFM) 2023. |  | 1. - IRI facilitated the development of Maptools and Maprooms online platforms for DMA and LMS to improve forecasting and early warning for early action, data management and predictions. In the current year, DMA was fully capacitated on Anticipatory Action/Forecast Based Financing model/initiative, the DMA team further developed timelines for formulation of Lesotho Antipatory Action plan, including SOPs. - Completed the installation of data libraries on the servers of LMS available at 41.203.191.23 supported by IRI. - Supported LMS technical team to develop python based map-rooms through the support of IRI. 2. IRI capacitated DMA, LVAC team, EW & WFP-IACOV technical personnel on development of triggers and threshold setting for drought, and futhermore IRI supported development of Anticipatory Actions for each sector (water, agriculture,natural resource, health, social development) should a trigger be reached in a particular year, the plan is to develop Anticipatory Action Plan (SOPs) for Lesotho in year 3. 3.The project successfully engaged National level Consultant to undertake a study on "Impact of Climate Change on food security and Nutrition" in Lesotho. National and District level data findings validation was done, and the consultant is finalising a study report, which will be shared once ready. 4. - Supported LMS to generate seasonal outlook for the period October 2022 to March 2023 which is Lesotho's cropping season during Southern Africa Regional Outlook Forum (SARCOF-26) using PyCPT and also develop winter 2022 seasonal forecast. - Supported LMS to generate version 2 of ENACTS data assisted by IRI expert using CDT virtually 28 Feb – 11 Mar 22 ​ 5. Lesotho Vulnerability data shared with IRI for development of Map-rooms (process in progress). ​ 6. HPC procurement processes are completed and currently in a contract stage, the exercise is supported by Regional Beareu Johannesberg procurement office. The contracted companies are expected to start installation in the currrent year extending to year 3. Additionally, IACOV collaborated with Early Warning System phase 2 (EWS 2) to procure automatic weather stations (AWS) for institutional capacity and systems building to support national and community adaptation and management of climate change impacts. 7. Disseminated seasonal forecast covering Lesotho's cropping season for the period October 22 to March 2023 through both National Climate Outlook Forum (NACOF) and District Climate Outlook Forum (DICOF) covering 10 districts of Lesotho from 26 Sept - 20 Oct 22. | S
Outcome 2
Outcome 3
| Outcome 1.2: Strengthened access to tailored climate services by vulnerable communities to improve decision making for food security and livelihoods |  | Outcome 1 | 1. Conduct focus groups discussions at community level. 2. Establish partnerships with relevant service providers for most suited dissemination channels for CS and dissemination of information through several channels (radios, TV) 3. Train partners on seasonal forecast and information tailoring, focus groups discussions at community level (focusing on VDMTs). 4. Train Ministry of Agriculture and Food Security Extension Officers on Incorporating Forecast into Agriculture through PISCA model. |  | 1. Focus group discussion conducted in the three districts with participation of 2081 members of the communities. Youth made a total of 795, Men 475, and women 811. 2. Consultations with Econet and Vodacom have progressed in the current year. MOU to be developed with Vodacom to expedite the process, the plan is to start disseminating Climate Change, Climate Service and Early Warning information in year 3. 3. DICOF - dissemination of seasonal forecast at district level - in progress. Successfully held PyCPT training for LMS staff by International Research Institute (IRI) expert virtually 14-25 Feb 22 4. The activity was not implemented in the current year as Extension officers busy supporting farmers with summer cropping, hence the activity is carried over to early YR3. | S
| Outcome 2.1: Strengthened awareness of climate change impact on food security amongst vulnerable communities and youth and knowledge of adaptation actions |  | Outcome 3 | 1. Operationalisation of National Climate Change Communication Strategy (NCCCS) in progress, public gatherings to disseminate Cliamte Change (CC) information done in 4 districts. National music competitions (climate change awareness songs composed) as well as maths and science competition conducted. 2. District action plans under the umbrella of NCCCS to be developed 3. Develop action-oriented research programme for tertiary institutions - an MoU between National University of Lesotho who will be leading the research and WFP signed 4. Develop Gender sensitive awareness raising materials 5. Train teachers on the updated toolkit for teachers 6.Media coverage on climate change stories published, |  | 1. The operationalisation of NCCCS is onging, it has been taking place in 6 districts through radio, print, sensitisations of local government structures, herders and communities through public gatherings. 2. District action plans under the umbrella of the NCCCS were been developed in Mafeteng, Mohake'sHoek, Quthing, Mokhotlong and Thaba-Tseka and collaborations were identified. The remaining districts will develop their action plans in year three of the project. 3. An MoU of Action Oriented Research between the National University of Lesotho and WFP has been initiated. The NUL will be taking lead in the research but working closey with other institutions of higher learning. 4. Gender sensitive awareness raising materials for policy makers, private sector, civil society, national and local government and youth has been developed and will be distributed in year three of the project. 5.CC Toolkit for Teachers and the manuals have been printed and disseminated in the 120 targeted schools in the three districts and climate smart agriculture manuals have been printed and distributed to all schools in the three districts. During the sensitization of herders in Mokhotlong, a gap at the herders school was identified. Teachers need to be capacitated on how to integrate climate change into their curricula so that they easily transfer the knowledge to the herders. 6. 40 climate change stories have been published since year 2 of the project. | S
| Outcome 3.1 Increased adaptive capacity of communities and households to respond to droughts and water-related hazards |  | Outcome 6 | 1) Engage technical support to review and update community actions plans (CAPs). 2) In liaison with the Ministries of Local Government, Forestry, Range and Soil Conservation as well as the Ministry of Agriculture and Food Security develop by-laws to safeguard implementation of CAPs. 3) In collaboration with project components 1 & 2, disseminate results of soil survey, rangeland assessment, ESS and vegetation index that were undertaken in Year 1 to key stakeholders in the across project implementation areas. 4) With support from component 1, develop maps overlaying different vulnerabilities for the different project areas. 5) To build capacity of communities, explore possibilities of implementing a community-led beneficiary feedback mechanism for sustainability. 6) Provide cash-based transfers to vulnerable communities from the different project areas during lean season as support while supporting the resilience building of the same communities through community and household asset creation activities including gully reclamation, orchard establishment/management, fire management structures, fodder production, and agricultural activities. 7) Support capacity strengthening for farmers/households on key areas including how to raise short-cycled animals, IPM and CA, homestead gardening & demonstrations, beekeeping, fodder production techniques, post-harvest management technologies, group marketing, pricing, food quality and handling as well as food preservation and processing. 8) Support the establishment of at least two botanical gardens as well as rehabilitation of wetlands and springs. 9) organize south-south district exchange visits for farmers as well as provide Non-Food Items as per the needs of the households/smallholder farmers including items to help SHFs reduce losses. 10) Finalize the post-harvest losses situational assessment and initiate the value chain analysis for drought resistance crops, indigenous medicinal plants, high value trees and indigenous vegetables. 11) Conduct market assessment and analysis to analyse the prevailing market requirements and demands for both crops and livestock products. 12) Conduct SHFs profiling (inclusive of farmers’ organizations/cooperatives/associations) in all project areas to help identify the different needs of SHFs for their targeted support. 13) Implement market access/linkages activities for SHFs (and cottage industries) with HGSF and other structured markets as targets. 14) In collaboration with component 1 & 2, facilitate access to tailored climate information by SHFs for their adaptive decision making as well as link farmers access to microfinance, and 15) Mainstream gender, protection and nutrition in all component programming. |  | 1) The review and updating of the established community action plans will be undertaken in year 3 of the project. 2) Natural assets created in the communities need to be protected for sustainability. A multi-sectoral task team comprising key stakeholders in the implementation of the Project commenced sensitizations through public gatherings leading to the formulation of By-Laws. The teams were built-up of the following stakeholders: the Ministry of Local Government and Chieftainship (MoLGC), Ministry of Forestry Range Soil and Water Conservation (MFRSC), Ministry of Agriculture Marketing and Food Security (MAMFS) as well as the Ministry of Police and Public Security. In preparation to develop community by-laws to keep safe the community assets developed, the project team with technical support from the key ministries including local government, agriculture, and food security as well as police and forestry, range and soil conservation, sensitized communities on the need to develop or update by-laws for the protection of communal assets. 3) The project disseminated the results of the rangeland management, soil surveys, and ESS plan to the technical staff in relevant line ministries to inform planning and implementation processes of the project activities 4) A consultant was engaged through component 1 to assess the impact of climate change on food security and nutrition. The different vulnerabilities have been mapped for the project districts aimed at informing the proactive implementation of key vulnerability reduction measures. The study report will also be a reference for policymakers and managers across sectors and groupings, who will find the shorter-term projections more relevant to their decision scales. 5) The project has established and maintained the grievances committees in different project sites to receive feedback, address minor conflicts and escalate grievances that have not been resolved while also documenting the proceedings' entire process. 6) On the premise of priorities listed in the community action plans developed at the start of the Project; asset creation activities (both community and household asset creation activities) continued at both community and household levels in the different project sites. Communal assets included rangeland rehabilitation activities, land reclamation, water harvesting activities soil and water conservation as well as agricultural activities aimed at addressing food security inclusive of livestock and crop farming. Household assets created and maintained during this period included homestead gardening (animal and crop farming as well as income generation activities). 7) A total number of 84 (50 F: 34 M) farmers have been trained in food processing and preservation, and 29 (18F: 11M) farmers were trained on basic beekeeping techniques to inform their household beekeeping projects following the provision of beekeeping equipment. Other trainings have been planned for year 3. 8) One botanical garden has been established in the district of Mafeteng. This garden is being used to conserve/preserve endangered indigenous plant species as well as to raise awareness of wild plant species for the communities. 9) SHFs conducted a study tour to Butha-Buthe during National Beekeeping Day to learn from other successful farmers and partners how to improve their beekeeping skills. SHFs conducted exchange learning visits between the Mohlakoana and Katlehong project sites. During these visits, the groups shared their experiences and best practices as a way of cross-fertilization. Procurement of Non-Food Items (NFIs) including weighing scales, pallets, shade nets, and vegetable seeds was finalized during the reporting period. Distribution of the same NFIs is currently underway and will continue into the third year of implementation. The distribution is based on the criteria that was been developed by the project team in collaboration with stakeholders at the district level. 10) Post-harvest losses situational assessment was undertaken in the last reporting period. The study assessed the situation of losses in pulses, cereals, vegetables, and fruits; and analysis confirms that losses are being experienced across the mentioned crops. The study also recommends post-harvest management technologies that SHFs and retailers can implement to reduce the losses experienced. Consultancy terms of reference for value chain analysis (VCA) were finalized and the recruitment processes started for the activity to begin in November 2022. Stakeholder consultations to profile and prioritize crops in each of these categories; drought resistance crops, indigenous medicinal plants, high-value trees, and indigenous vegetables were also finalized to support VCA. Study modality and technical and reference team has also been identified – RBJ VCA to lead the study and capacity building of the technical team. 11) The market assessment analysis was conducted in collaboration with the department of marketing in the Ministry of Agriculture and Food Security in the piloted districts of the Project. The assessment's overall objective was to analyze the prevailing market requirements and demands for both crops and livestock products. The specific objectives of the assessment included: i) evaluating the size of the existing and potential consumer base, ii) identifying the market potential of supply and demand by understanding the market and consumer dynamics as well as iii) indicating the market potential for local produce by evaluating the competitive advantage of farmers. The assessment recommended that regular extension service and training should be provided to smallholder farmers in order to see improved production and quality of their produce. Again, in order to ensure production of quantities required in the market, smallholder farmers are to be encouraged and supported to form aggregation groups. 12) And to identify and understand the needs of farmers that the project is supporting, an exercise to profile the farmers was undertaken and is continuing. 13) In facilitating market access for smallholder farmers’ agricultural produce, the project in collaboration with the ministry of education and training, and the WFP resilience team, held market linkage workshops in the districts of Mohale’s Hoek and Quthing. The aim of the workshops was to link the different farmer groups to the school feeding market. In these trainings, both ministry of education and training officials including school principals, the representatives from the national management agents (NMA) as well as SHFs. A market day was also held to bring together buyers and sellers together. The platform facilitated discussions on the requirements of the markets to inform farmers’ production. Furthermore, in ensuring coordination of all local procurement of farmers agricultural produce, a local purchase task force was resuscitated. Terms of references for this task force was revised and membership reviewed. In collaboration with the IFAD-supported Wool and Mohair Promotion Project, the project held a national cottage industry symposium for women and youth groups and project beneficaries from the districts of operation participated. The aim of the symposium was to provide exposure and a marketing opportunity for the different groups’ products. The event also served as a learning platform for the project team to improve the groups’ capacities as a way to enhance community livelihoods. 14) Climate Change and tailored seasonal weather forecast information with lead from Components 1 and 2; was disseminated to communities including SHFs in the three pilot districts. In liaison with components 1 and 2, access to tailored climate information by communities including SHFs was facilitated through community gatherings to help the communities to make adaptive decisions. Efforts to link SHFs to microfinance will be implemented in year 3 and plans are in place to train SHFs on voluntary savings and credit. 15) In mainstreaming gender, protection and nutrition in all activities, the project team ensures continuous sensitization and implementation on these important cross-cutting issues. | S
S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Aurore Rusiga
| Email: | UN WFP, Representative and Country Director
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall implementation performance of the project is satisfactory. There has been significant improvement in implementation since the 1st year in the three components regarding adherence to compliance protocols to plan procurement activities timely. Most of the activities which were planned for year 2 have been executed. The project continues to receive technical backstopping from WFP technical team in the country, Regional, and Headquarters. There has been improvement in government ownership of the project in the second year as well as in Climate change and climate services information dissemination since the first year of the project.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1.1: Increased knowledge and technical capacity at national and district levels to forecast, plan and anticipate responses to climate change (CC) impacts |  | Outcome 1 | 1. Engagement of International Research Institutute (IRI) to provide capacity to Lesotho Meterological Services (LMS) technical team on seasonal and sub-seasonal forecasting using PyCPT software. Furthermore, IRI to capacitate Disaster Management Authority (DMA) on Forecast Based Finacing/Anticipatory Action model, focusing much on development of SOPs for drought inclusive of triggers and thresholds settings. 2. IRI to capacitate LMS on installation of data libraries (DL) on LMS server including training staff on DL maintenance. Furthermore, IRI to provide capacity on the development, maintenance and updating of python based maprooms.​ 3. Capacity building of DMA committee (Early Warning and Lesotho Vulnerability Assessment Committee teams) on thresholds and trigger setting per sector (Nutrition, Food Security, Water, Forestry Range and Soil Conservation etc.) and use of Map-tools for decisions making on early warning for early action (Anticipatory Action/Forecast Based Finacing). 4. Support LMS to develop 2022 winter season outlook and generate Lesotho cropping season for the period October 2022 to March 2023 using PyCPT​. 5. Engagement of the local consultant to conduct a study on impact of climate change on Food Security and Nutrition. 6. Strengthen Partnership with Lesotho Red Cross Society on Forecast Based Financing model trigger and threshold setting looking at drought episode. 7. Remotely train LMS staff on the latest version of IRI’s Climate Data Tool (CDT) to improve LMS database |  | In the second year of implementation the project successfully engaged International Research Institute (University of Columbia) to capacitate Lesotho Meterological Services and Disaster Management Authority. Disaster Management Authority successfully gathered historical data, developed thresholds and triggers for drought supported by IRI. Disaster Authority together with other stakeholders and line-ministries were capacitated on FBF maptool and managed to develop anticipatory actions at National level, the plan for YR3 is to develop district action plans and validate thresholds and triggers. During this period LMS historical database was improved through engagement of IRI. IRI introduced the Enhancing National Climate Services (ENACTS) approach which focused on the creation of reliable ENACTS climate data using climate data tool (CDT). IRI also introduced the python climate predictability tool (PyCPT) for the generation of seasonal forecasts aimed at decision-making for national and sub-national. The successful completion of capacity building on PyCPT enabled LMS to generate and disseminate rainfall for 2022 winter season and outlook for the period October 2022 to March 2023. This dissemination was done in collaboration with early warning system 2 (EWS 2) project. Sub-seasonal forecast was also introduced to LMS but still needs to be explored further in the third year of the project. For enhancing access to climate information for other stakeholders, map-rooms were developed by IRI. LMS was capacitated to develop python-based map-rooms and the process is still continuing rolling out into the third year of the project. The procurement for HPC and AWS is at the advanced stage where the budget is shared between IACOV and EWS2 project funded through GEF. | S
Outcome 2
Outcome 3
| Outcome 1.2: Strengthened access to tailored climate services by vulnerable communities to improve decision making for food security and livelihoods |  | Outcome 1 | 1. Conduct the focus groups discussions at community level. 2. Establish partnerships with relevant service providers for most suited dissemination channels for CS and dissemination of information through several channels (radios, TV) 3. Train partners on seasonal forecast and information tailoring, focus groups discussions at community level (focusing on VDMTs). 4. Capacitate extension officers on Participatory Integrated Climate Services for Agriculture (PICSA) approach led by LMS. Aiming at enhancing productivity of small-holder farmers. |  | During these period, LMS had an opportunity to share basic weather and climate information through focus group discussions about short range forecasts in Mafeteng (3 IACOV sites), Quthing (Mphaki), Mokhotlong, Thaba Tseka. Also IACOV supoorted long range seasonal forecasts dissemination in collaboration with the UNEP Early Warning Systems project during district climate outlook forums in 9 districts. | s
| Outcome 2.1: Strengthened awareness of climate change impact on food security amongst vulnerable communities and youth and knowledge of adaptation actions |  | Outcome 3 | 1. Operationalisation of National Climate Change Communication Strategy: -public gatherings to disseminate CC information in 10 districts, -National music competitions (climate change awareness songs composed) as well as maths and science competitions. - Radio and television programs to advocate for climate change. 2. District action plans under the umbrella of NCCCS to be developed 3. Develop an action-oriented research programme for tertiary institutions and conduct a symposium. 4. Develop Gender sensitive awareness raising materials 5. Train teachers on the updated climate change toolkit for teachers 6. Media coverage on climate change stories published. |  | The operationalisation of the NCCCS was satisfactory, the team handed over the strategy to government and implementors at national and district level in 6 districts (Maseru, MAfeteng, Mohale'sHoek, Quthing, Mokhotlong and Thaba-Tseka. Dissemination through public gatherings was done in 5 districts where herders, local government structures and communities at large were targeted. Under the umbrella of the NCCCS district action plans were developed in Mafeteng, Mohale'sHoek, Quthing and Thaba-Tseka. Dissemination was also done through National music competitions (children composed climate change songs from the developed messaged in the NCCCS) and maths and science competitions. 120 teachers we trained on how to use the updated climate change toolkit and how to integrate climate change in all subject in the classrooms and printing of the toolkits is in progress. With regard to Action Oriented Research, an MoU between WFP and National University of Lesotho is signed and the program will commence in the 3rd year of the project. Gender transormative awareness raising materials for policy makers, private sector, local governement, youth were developed and will be disseminated in year 3. There is a significant increase in the number of climate change stories that were published since media houses were capacitated on climate change reporting in year 1. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Mokoena France - Director (a.i), Lesotho Meteorological Services
| Email: | mokuena.france@gov.ls
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall implimentation of the activities planned for year 2 of the project, progress is satisfactory. All planned activities were excecuted well and progress towards set outcomes was satifactory. The inclusion of PyCPT into the already exisiting softwares for generation of seasonal forecasts brought more value to LMS products. However progress to the completion of planned activities seemed slow due to remote trainings conducted by IRI. Hence going forward, I would highly recommend in-person trainings for achieving more with respect to time. Futhermore, in the current year there has been notable progress in linking climate services into early warning for early action lead by Disaster Management Authority (DMA). Planned interventions to capacitate on Early Warning model called Anticipatory Action/Forecast Based Finacing were implemeted successfully with the support of International Research Institution (IRI) Columbia university and as a result thresholds and triggers for drought were developed and Anticipatory Actions for multiple sectors developed at National level, there is still need to validate this at district level progressing into YR3. However, there is still need for continued support by IRI to develop the SOPs/Anticipatory Action Plan for drought in Lesotho (piloting 4 districts) in YR3.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
| Outcome 3.1 Increased adaptive capacity of communities and households to respond to droughts and water[1]related hazards |  | Outcome 6 | 1) Engage technical support to review and update community actions plans (CAPs). 2) In liaison with the Ministries of Local Government, Forestry, Range and Soil Conservation as well as the Ministry of Agriculture and Food Security develop by-laws to safeguard implementation of CAPs. 3) In collaboration with project components 1 & 2, disseminate results of soil survey, rangeland assessment, ESS and vegetation index that were undertaken in Year 1 to key stakeholders in the across project implementation areas. 4) With support from component 1, develop maps overlaying different vulnerabilities for the different project areas. 5) To build capacity of communities, explore possibilities of implementing a community-led beneficiary feedback mechanism for sustainability. 6) Provide cash-based transfers to vulnerable communities from the different project areas during lean season as support while supporting the resilience building of the same communities through community and household asset creation activities including gully reclamation, orchard establishment/management, fire management structures, fodder production, and agricultural activities. 7) Support capacity strengthening for farmers/households on key areas including how to raise short-cycled animals, IPM and CA, homestead gardening & demonstrations, beekeeping, fodder production techniques, post-harvest management technologies, group marketing, pricing, food quality and handling as well as food preservation and processing. 8) Support the establishment of at least two botanical gardens as well as rehabilitation of wetlands and springs. 9) organize south-south district exchange visits for farmers as well as provide Non-Food Items as per the needs of the households/smallholder farmers including items to help SHFs reduce losses. 10) Finalize the post-harvest losses situational assessment and initiate the value chain analysis for drought resistance crops, indigenous medicinal plants, high value trees and indigenous vegetables. 11) Conduct market assessment and analysis to analyse the prevailing market requirements and demands for both crops and livestock products. 12) Conduct SHFs profiling (inclusive of farmers’ organizations/cooperatives/associations) in all project areas to help identify the different needs of SHFs for their targeted support. 13) Implement market access/linkages activities for SHFs (and cottage industries) with HGSF and other structured markets as targets. 14) In collaboration with component 1 & 2, facilitate access to tailored climate information by SHFs for their adaptive decision making as well as link farmers access to microfinance, and 15) Mainstream gender, protection and nutrition in all component programming. |  | Implementation of component 3 project activities has been satisfactory during year 2 of the project. While review and updating of the community action plans; developed in year 1, will be done in year 3, the ministry of forestry, range and soil conservation staff continued to work closely with project team in supporting communities to create and maintain both community and household assets within the project areas. Examples od assets included rangeland management, rehabilitation of degraded land as well as agricultural asset creation such as communal gardens, household vegetable gardening and small stock rearing. In Mafeteng district, a botanical garden has been established to conserve some species that the ministry has found to be of importance to the community. Again, during the period under review, farmers were trained on food processing and preservation and more will be trained in year 3, other farmers were provided with beekeeping equipment and trained on basic beekeeping techniques as they started their beekeeping projects. Furthermore, results of studies undertaken in year 1 were disseminated to government technical staff to inform project planning and implementation. These surveys are the rangeland management, soil survey, and the environmental and social safeguard (ESS) survey. As a way of enhancing capacity of farmers, study and exchange visits were undertaken by farmers within the project sites. One of these visits was an exchange to learn and exchange experiences on beekeeping while another was to establish how other communities have fostered commitment and motivation within participating communities. Consultants were also engaged to conduct assessments on post-harvest losses study and on the impact of climate change on food security and nutrition. Both the studies’ recommendations will better inform project implementation in year 3. Communities continued to receive climate change information and climate services for their adaptive planning. This proved to be a necessary step in complementing the asset creation that ministry of forestry, range and soil conservation is leading. In collaboration with the ministry of agriculture and food security, farmers were continually supported to access available markets for their improved livelihoods. To ensure sustainability of project activities, the ministry and its partners have supported the communities to establish a community-based beneficiary feedback platform where community’s grievances will be addressed. Also, the ministry is leading the process of community sensitization to facilitate formulation of by-laws to safe-keep and protect communal assets. This was done in collaboration with other government ministries. The value chain analysis study that will be done for high value tree crops will inform the MFRSC efforts and support to the communities. The ministry looks forward to improved efforts to link farmers with finance service providers for provision of small loans and trainings on voluntary savings and credit.
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Elias Sekaleli-Director of Forestry (Ministry of Forestry, Range and Soil Conservation)
| Email: | elias_sekaleli@yahoo.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Implementation of component 3 activities undertaken in the three districts have been satisfactory during year 2 of the project. Activities on Food processing and preservation were conducted to address the challenges of post-harvest losses. A total of 84 households benefited in this reporting period. Furthermore, Apiculture/ beekeeping trainings were conducted to contribute to the improvement of household income and nutrition status. A total of 29 households benefitted from the basic beekeeping training. And asset creation activities continued under the public works programme in 21 project sites. These activities were aimed at rehabilitating degraded land. Key activities included management of rangelands, gully stabilization, harvesting of water, and forest and fruit trees planting. Again, during the reporting period, a total of 4 000 fruit trees were planted, 3 000 of these were planted in schools while 1 000 were planted at household level.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on F33: Mookho MONNAPULA:

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
| Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Impact | Vegetation index in low-lying southern districts | Sparse to Moderate vegetation cover | In collaboration with the Ministry of Forestry GIS team, the project is working towards satelile monitoring of vegetation Index. In year 2, much effort was placed on verification of the vegetation as on of the key recommendations from the report produced in year 1. | 10% Improvement in vegetation Index in low lying project areas, as measured by the LDSF.
|  | Household dietary diversity score | 40% (Low Dietary diversity) | 62% (Low Dietary diversity) | Increased Household dietary diversity to 6 items
| Outcome 1.1 | Capacity to produce sub-seasonal to seasonal forecasts, issue sector specific EW, develop drought preparedness protocols & respond accordingly | Limited national tools/capacities to downscale seasonal forecast SOPs for drought preparedness based on S2S EW do not exist at national or district level | There was a training for LMS staff on the latest version of IRI’s Climate Data Tool (CDT), particularly on quality control of station data and combining station observations with satellite and reanalysis proxies. IRI provided support to LMS to generate that historical climate data. There was further capacity for LMS on PyCPT which ingested the generated data to develop seasonal outlook of winter 2022 season and Lesotho cropping season for the period October 2022 to March 2023. | LMS has enhanced tools and capacity to downscale forecast and provide accurate drought Early warning . SOPs based on drought Early warning are developed at national level and in pilot districts.
| Output 1.1.1 | # Staff trained to maintain and integrate new observational data into database (gender disaggregated) | 0 | 12 | 12
| Output 1.1.1 | # web-based map rooms installed in LMS to share observations, develop EW thresholds and triggers, and process S2S forecasts | 0 | 2 | 3
| Output 1.1.1 | S2S forecasting system to cover national and sub-national levels, with 6 month horizon | there is currently no S2S system in place | There is ongoing capacity building of S2S forecasting system by IRI and LMS. In the second contract of IRI, S2S will be further investigated. The groundwork includes the enhanced historical data, capacity buiding on forecasting tool being PyCPT and also procurement of high computing system which will be used to run climate models. | Specialised S2S forecasting system operational
| Output 1.1.2 | Thresholds validated and triggers and actions developed for national SOPs on drought | Thresholds,triggers and actions for national SOPs have been developed with support from IRI | 1 | IRI supported validation of thresholds and triggers and in year 3 SOPs will be developed.
| Output 1.1.2 | # district-level SOPs for drought that define field-level actions developed and applied | 0 | In an effort to develop SOPs at National and district level the project together with partners in the current year developed thresholds and triggers and also developed online platform (FBF maptools) for drought in Lesotho and Supported by WFP Regional office and IRI. Therefore in Year 3 focus will be on developing SOPs at national and district level. | 3
| Output 1.1.2 | Number of government staff sensitized and trained at national and district level on drought SOPs, disaggregated by sex | 0 | 27 | 100
| Outcome 1.2 | % of households using seasonal forecast in resilient decision making on agricultural / livelihood strategy | 7% | 59% | 50%
| Output 1.2.1 | # of studies on local knowledge and beliefs on climate change and acceptability of climate services | 0 | One (1) study was carried in PY2, report not yet finalized by consultant. Another study to be carried out in year 3. | 2
| Output 1.2.2 | # partners capacitated on using seasonal forecasts to develop culturally appropriate CIS | 0 | 0 | 20
| Output 1.2.3 | % of targeted people understand the information (climate change) | 33% | 63% | 80%
| Outcome 2.1 | % of targeted community members (M/F/MY/FY) receiving key messages on climate change adaptation. | 25% | 67% | 90%
|  | % of targeted community members (M/F/MY/FY) receiving key messages on food Security. | 30% | 55% | 90%
|  | % of targeted community members (M/F/MY/FY) receiving key messages on nutrition. | 28% | 55% | 90%
| Outcome 2.1 | % of people having knowledge/awareness, attitude and practice on climate adaptation initiatives | 98% | To be measured at MTR | 70%
| Output 2.1.1 | Presence of National Climate Change Awareness Raising and Communication Strategy (NCCAR&CS) | 0 | 1 | 1
1 | Output 2.1.1 | # Gender-transformative awareness raising materials on climate change/ food security/ nutrition links for govt., youth, children, herders, etc developed | 0 | 1 | 10
| Output 2.1.2 | # journalists trained on climate change reporting | 0 | 53 | 20
| Output 2.1.2 | # climate change impacts and adaptation stories published | 0 | 36 | 2
| Output 2.1.3 | # District CC AR Strategies and Action Plans, to interface with existing activities and ongoing projects in each of 3 districts | 0 | 3 | 3
| Output 2.1.3 | # district and community level CC AR activities implemented | 0 | 6 | 8
| Output 2.1.3 | # people reached through inter-personal SBCC approaches (sex- and age-disaggregated) Female | 0 | 414 | 23000
|  | # people reached through inter-personal SBCC approaches (sex- and age-disaggregated) Male | 0 | 200 | 19840
| Output 2.1.4 | # teachers trained on using updated climate change toolkits in schools | 0 | 130 | 600
| Output 2.1.4 | # of schools implementing CSA activities (via upscaled RVCC CSA manuals) | 0 | 86 | 295
| Outcome 3.1 | % targeted communities where there is evidence of improved capacity to manage climate shocks and risks | 0 | To be measured at MTR | 80%
| Outcome 3.1 | Coping Strategy Index | 32% | 27 | <20%
| Output 3.1.1 | # community-based resilience and adaptation plans in targeted areas | 0 | 21 | 21
| Output 3.1.1 | # cost-benefit analyses on concrete community adaptation measures | 0 | 21 | 21
| Output 3.1.2 | # community productive assets created through the project | 0 | 100 | 105
| Output 3.1.2 | # of tartget HHs (M/F headed with natural and Physical livelihoods created and improved | 0 | 3322 | 23000
| Output 3.1.2 | # of fuel efficient stoves provided, with training on their use | 0 | 50 | 200
| Output 3.1.2 | # of women supported with HH gardening to increase their income levels | 0 | 1685 | 4300
| Output 3.1.3 | # smallholder farmers supported/trained on reducing post-harvest losses | 0 | 84 | 3000
| Output 3.1.3 | # Value chain analysis studies for district-relevant drought-resistant crops | 0 | In year 2, the modality to engage the consultant has changed and the project sought support from the WFP regional office. The study will then commence in January 2023. | 4
| Output 3.1.3 | # of Women Supported to diversify livelihoods through cottage industries that produce handicrafts and sewing groups. | 0 | 46 | 300
| Output 3.1.3 | Quantity of food procured from local farmers | 0 | 3.097 MT | 500MT
| Output 3.1.3 | Quantity of fortified food including complementary foods and special nutrition products purchased from local suppliers for school feeding | 0 | 1093MT | 2500MT

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project learned that healthy partnerships with stakeholders and communities are important for achievement of project results. In year 2, the project was able to use existing government coordination structures to identify synergies and complimentarities between line ministries, development partners and private sector for support livelihood interventions that improve adaptive capacity of the affected population. In IACOV project sites, private sector (Standard Lesotho Bank) supported procurement of fruit trees which were planted by community mebers at household and community levels. The ineffective use of climate service information to inform sectoral plans by diffrent line ministries motivated a need for national dialogues that will target all stakeholders including the decision makers and different socio economic groups. Such dialogues serve as platforms for advocacy for use of climate service information by all ministries and partners for decision making that will influence social and behavioral change.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The procurement of the High Power Computing system, Automated Weather Stations, development of Media Press Kits delayed due to limited suppliers in the country. Support was requested from WFP Regional Office (RBJ) to fast track the process. On a longer term, Country Office is enlisting RBJ support to broaden service provider pool to include regional and international suppliers.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | There were no changes made to the project outputs and the project design.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | An Environmental and social risk management plan was put in place with monitoring indicators clearly defined. The project monitoring team monitored indicators regularly through onsite monitoring as well as through the feedback and accountability mechanisms report. Thus the project was able to mitigate and avoid adverse environmental and social risks and impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations are well mainstreamed in the project interventions. At the beginning of implementing the project's intervention with communities, it was noticed that community members had little trust to elect women in leadership positions. However, the project sensitised communities and challenged the stereotypes around the roles and responsibilities of men and women, which improved women's representation in leadership positions. The project trained 60 women and 40 men that were elected for the leadership roles in the community activities.In implementing the adaptation activities through public works programme, 53% of targeted beneficiaries engaged in the implementation of adaptation activities are women. Provision of caregiving facility for breastfeeding mothers engaged in Project activities has been a positive lesson and has boosted commitment of women to the Project as they no longer worry about safety of their young children while they are at work. Gender and Protection assessments during community consultations revealed that on issues of gender and protection; participants are empowered enough to recommend or suggest their preference on the mode of transfer as cash, as well as being able to give feedback and report their grievances confidentially through the established complaints and feedback mechanisms. Activities such as focus group discussions, stakeholder sensitisation sessions, development of the climate change communications strategy were executed to allow full participation of both men and women nationally and from the target communities. Consequently, both men and women have been actively involved in project activities.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Cash-Based Transfers to project beneficiaries (category A beneficiaries) happen during lean season which covers a period of six months in a year. In Year 2, it was observed that when there are no cash tranfers some beneficiaries face food insecurity due to poor harvest that was caused by heavy rains and water logging in fields. This was further exacerbated by hike in prices of food commodities due to the Ukraine - Russian war which has crippled the world economy. To address this challenge, the project collaborated with IOM and IFAD projects to promote cottage industry that enhances diversification of livelihoods such that communities can not only rely on agriculture to improve food security. In year 3, the project will engage a community-based organization (CBO) and will collaborate with financial service providers to provide a continuous guidance and trainings for communities on financial literacy and sustainance of livelihoods. In addition, it is important to mobilize more funding and collaborate with other projects to scale up the implementation of the adaptation activities in other communities.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Project is implemented in one Electoral Division (Ward) within a Community Council. Communities from other EDs have started to realise significant changes brought by environmental activies implemented in the areas of operation and in some they have started to voluntarily replicate similar activities in the neighbouring areas. Scaled up activities are also occuring within areas of operation where community members who are not yet enrolled in the Project assets creation activities have already started creating assets especially at household level.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Livelihoods Adaptation Interventions such as water harvesting interventions and communal gardens yielded almost immediate results that have encouraged and motivated involved communities to do more and help in behavioural positive deviance on climate change adaptation.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The WFP three-pronged approach (3PA) as an inovative programming tool that places the communities at the centre of planning and implementation processes of adaptation activities, has been well adopted by the government. In all the projecct sites, community members are well conversant with the implementation processes and own productive assets created by the project. Such assets include; indeginous chicks, permaculture, agroforestry and conservation agriculture.
What measures are/have been put in place to ensure sustainability of the project/program results? | The Government leading the project will ensure continued support for the project. The consultative process which brings the community, the government, and partners to design multisectoral plans which inform consistent monitoring of the project beyond face out. The approach instilled ownership in government and the community.
What measures are being/could have been put in place to improve project/program results? | The Project is in the process of engaging a CBO to support community initiatives and monitor progress made as well as provide support needed in a timely manner. The CBO will further operationalize the exit strategy of the project and build sustainability beyond project closure working closely with executing entities.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project is strengthening the existing government systems and structures for knowledge management. As a result, strengthening climate service through development of user-friendly tools to avail forecast information (daily, weekly, bi-weekly and seasonally) has made it easier for partners and all users to access this information through online platforms developed and owned by the Lesotho Meteorological Services (LMS) called maprooms.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | This information is availed to stakeholders through sms, emails and social media, radio and television.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | The tool kid manual and permacuture on climate change were developed and shared with schools and extension officers for purpose of capacitation and instealing behavioral change.
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Long protocols that allows for access of data, filling that involve more than one office with no audiquate handover that makes new person not able to assist on time.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | Communities make voluntary saving groups out of their earning from the cash transfers during the lean season. Out of these savings, communities decide which income generating activities to start collectively. As a result, they buy inputs collectively in bulk. These savings groups are linked to the national school feeding program for market access.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | The project was not scaled up from other climate finance initiatives. However, there is collaboration with the GEF funded project-Early Warning Phase2, to procure the Automated Weather Systems and High-Power Computing Systems. In addition, the project built on the previous GEF funded project - Reducing Vulnerability to Climate Change (RVCC) to advance integration of climate change into school curricula.
If you answered yes above, kindly specify the name of the Fund/Organization. | SRAC (Internal WFP funding pool/facility), International Organisation for Migration (IOM), World Vision, Government of Lesotho
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | LSO/MIE/Food/2018/1
Implementing Entity | WFP
Type of implementing entity | MIE
Country | Lesotho
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
| Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 42840 | 42840 | 0 | Total | 1101000 | 301000 | 800000 | Total |  |  |  | Total
|  | % of female beneficiaries | 54% | 53% | 0% | % of female beneficiaries | 54% | 52% | 60% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 24% | 24% | 0% | % of Youth beneficiaries | 24% | 24% | 24% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 4: Effective | Total | 112 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments |  | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 10 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2. Strengthened institutional capacity to reduce risk associated with climate- induced socio – economic and environmental losses. | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 52 | Disaster risk reduction | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  |  |  | 172 | 60% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses |  |  | Sector |  | ;l. |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 75250 | 29% | 3: Partially aware |  | 301000 | 60% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Food security | land | 4: Effective |  | Food security | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 21 | ha rehabilitated | 4: Effective | Rangelands | 406 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 3 | ha protected | 3: Moderately effective | Forests | 142 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land | 236 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 10 | ha protected | 4: Effective
|  | Protected areas/National parks |  | ha rehabilitated | 2: Partially effective | Protected areas/National parks | 3 | ha protected | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 3322 | 20% | 3: Moderate improvement |  | 23000 | 60% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 1428 | 60% | From 10% to 20% | Agribusiness | 215000 | 60% | From 20% to 30% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  |  | Physical capital | Food security | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
[6 empty] | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness

## Additional Info.
CLIMATE CHANGE PUBLICATIONS AND FEATURES
https://publiceyenews.com/dearth-of-laws-threatens-land-rehabilitation/
https://publiceyenews.com/food-insecurity-count-me-out/
https://publiceyenews.com/lesotho-starts-policy-responses-to-land-degradation/
https://publiceyenews.com/a-bill-to-protect-range-resources-introduced/
https://publiceyenews.com/degradation-reduces-land-to-a-hollow-legacy/
https://publiceyenews.com/mismanagement-threatens-land-water-resources/
https://publiceyenews.com/maphutseng-school-reaps-climate-smart-rewards/
https://publiceyenews.com/mohales-hoek-battles-climate-change-effects/
https://publiceyenews.com/lesotho-vulnerable-to-climate-change/
http://informativenews.co.ls/2021/10/20/youth-engage-in-climate-change-dialogue-cop26-preparations/
http://informativenews.co.ls/2021/11/23/linking-climate-change-into-spiritual-practices/
http://informativenews.co.ls/2021/11/02/water-scarcity-is-a-global-crisis-research-finds-out/
http://informativenews.co.ls/2021/09/15/cleaning-campaign-gets-underway/
http://informativenews.co.ls/2021/11/04/world-leaders-meet-to-review-progress-on-paris-agreement/
http://informativenews.co.ls/2021/06/08/lesotho-strengthens-climate-change-management/
https://www.facebook.com/100064009516706/posts/pfbid02TZzDxigKX4tmfQBMA73L4Pc1AgfvzmbBfPNJsEkdVu41ZXDh5PbsppRqqAyHA6NUl/?app=fbl
https://www.facebook.com/100064009516706/posts/pfbid02ruKTgBMVsdgT3bAabG3Mtb5vCcZy2yRXs9aqQvKgFp9xQJTeYQzGrNk8EhL5v2Rhl/?app=fbl
https://www.facebook.com/100064009516706/posts/pfbid02tAv8gNLHHRwkrxpj7yRgbKGwxkvvV5b5BjnsDXe7qkRXvw9goqyMBPJQGQ725VFcl/?app=fbl
https://www.facebook.com/100064009516706/posts/pfbid036oPViRhc28q1HZUHpvTCfoyH3PMDj2q9FERQomBShXW5aXJUMxYrM84CxQ1jc17el/?app=fbl5- Women in energy mark their territory
https://www.facebook.com/100064009516706/posts/pfbid0NmPCtXY6NQvnE64Uvt95TvYYbQk13Jqbfkbyg1VsXv7eGn7z83cBhLTaguPzwX6sl/?app=fbl
https://www.facebook.com/100064009516706/posts/pfbid028hFmimW9EQ4JdB3n6Wh9wU49wdxYG4uuMxaBSRcw4NNNRsD7J4QjAx7Lf55vvscKl/?app=fbl
https://www.newsdayonline.co.ls/lesotho-rolls-sleeves-on-climate-change/
https://www.newsdayonline.co.ls/climate-change-a-threat-to-legacy-preservation/
https://www.newsdayonline.co.ls/eu-fights-climate-change-scare/
https://www.newsdayonline.co.ls/climate-change-is-sexist-activist/
https://www.newsdayonline.co.ls/all-hands-on-deck-in-climate-change-fight/
https://www.newsdayonline.co.ls/eu-celebrates-world-environment-day-in-style/
https://www.newsdayonline.co.ls/lesotho-adopts-global-environmental-law/
https://publiceyenews.com/dearth-of-climate-resilient-seed-inhibits-community/
https://publiceyenews.com/as-lesma-adds-climate-change-theme-to-choral-competition/
https://publiceyenews.com/compulsory-free-education-policy-leaves-out-poor-teenage-herd-boys/
https://publiceyenews.com/farmers-clamour-for-climate-change-cushion/