## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 22 October 2019 - 31 December 2020
| Project Title: | Integrated climate-resilient transboundary flood risk management in the Drin River basin in the Western Balkans (Drin FRM project)
| Project Summary: | The project will assist the riparian countries in the implementation of an integrated climate-resilient river basin flood risk management approach in order to improve their existing capacity to manage flood risk at regional, national and local levels and to enhance resilience of vulnerable communities in the Drin River Basin (DRB) to climate-induced floods. The following results shall be achieved: (i) Improved climate and risk informed decision-making, availability and use of climate risk information; (ii) Improved institutional arrangements, legislative and policy framework for climate-resilient FRM, and development of CCA and FRM strategy and plans at the basin, sub-basin, national and sub-national levels; (iii) Strengthened community resilience through improved flood management, through implementation of structural and non-structural measures and enhanced local capacity for CCA and FRM.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | EE/MIE/DRR/2018/PPC/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Albania, Montenegro and North Macedonia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Drin/Drim River Basin in Albania, Montenegro and North Macedonia | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-10-22 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-10-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2022-05-01
| Original Completion Date: | 2024-12-31
Revised Completion Date after approval of |  | n/a
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report with Annexes, submitted on 23 November 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.adaptation-undp.org/projects/integrated-climate-resilient-transboundary-flood-risk-management-drin-river-basin-western | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
Regional Project Manager |  |  | Dominica
| Name: | Mr Bojan Kovacevic | Dominican Republic
| Email: | bojan.kovacevic@undp.org | Ecuador
| Date: | 2020-07-09 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ms Gerta Lubonja | Equatoral Guinea
| Email: | gerta.lubonja@ambu.gov.al | Eritrea
| Date: | 2020-11-27
| Name: | Mr Momcilo Blagojevic
| Email: | momcilo.blagojevic@mpr.gov.me
| Date: | 2019-05-30
| Name: | Mr Ylber Mirta
| Email: | ymirta@gmail.com
| Date: | 2019-05-30 | Estonia
| Name: | Mr Arduen Karagjozi | Ethiopia
| Email: | arduen.karagjozi@ambu.gov.al | Fiji
| Date: | 2019-05-30 | Finland
| Name: | Ms Ivana Stojanovic | France
| Email: | ivana.stojanovic@mrt.gov.me | Gambia
| Date: | 2019-05-30 | Georgia
| Name: | Ms Ljupka Dimovska Zajkov | Germany
| Email: | dljupka@gmail.com | Ghana
| Date: | 2019-05-30 | Greece
| Executing Agency |  | Guinea Bissau
| Name: | Mr Armen Grigoryan | Guyana
| Email: | armen.grigoryan@undp.org | Haiti
| Date: |  | Honduras
| Implementing Entity: |  | Guinea Bissau
| Name: | Ms Natalia Olofinskaya | Guyana
| Email: | nataly.olofinskaya@undp.org | Haiti
| Date: |  | Honduras
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31 December 2020 | [7 empty] | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS | [7 empty] | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [7 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2020 | 969564 | [6 empty] | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The commencement of the project implementation nearly coincided with the COVID-19 global pandemic outbreak, which lasted throughout and passed beyond the reporting period with the same intensity. This issue impeded the deployment of the Project Management Unit and international key experts, who once on board were prevented from conducting the field visits to the river basin, in order to undertake site inspections and meet stakeholders, especially at the local community level, with whom the distant (online) communication was hardly possible. Thus, timely and quality assessments of the assumptions made in the project documents were delayed, and the relevant management products, such as the terms of reference (ToRs) took more time to develop. Project implementing partners, such as the relevant national institutions (e.g. national hydrometeorological services, water administration entities, etc.) also slowed down the pace of their work due to understaffing caused by massive absence from work caused by the pandemic. | [6 empty] | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | [7 empty] | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant | [7 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA | [7 empty] | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | IRH Regional Component AMOUNT | Albania Component AMOUNT | Montenegro Component AMOUNT | N. Macedonia Component AMOUNT | TOTAL AMOUNT (w/out GMS fee) |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Strengthened hydrometric monitoring networks in the riparian countries | 0 | 0 | 356.2 | 272514.67 | 272870.87
| Output 1.2. Improved knowledge of CC-induced flood risk and risk knowledge sharing through the introduction of river basin modelling tools and technologies for strategic flood risk assessment | 43047.53 | 5005 | 97031.8 | 10688.41 | 155772.74
| Output 1.3. GIS-based vulnerability, loss and damages assessment tools and database | 0 | 0 | 0 | 174.45 | 174.45
| Output 2.1. Drin River Basin FRM Policy Framework and improved long-term cooperation on FRM | 15614.42 | 0 | 613.57 | 0 | 16227.99
| Output 2.2. Regional, national and sub-national institutions are trained in climate-resilient FRM, responsibilities clarified and coordination strengthened | 0 | 0 | 3772.84 | 1974.37 | 5747.21
| Output 2.3. Drin River basin Integrated CCA and FRM Strategy and Plan developed | 0 | 0 | 7356.76 | 399.62 | 7756.38
| Output 3.1. Introduction of appraisal-led design for structural and non-structural measures | 19036.04 |  | 177729.28 | 2612.31 | 199377.63
| Output 3.2. Construction of structural risk reduction measures in prioritized areas | 0 | 0 | 0 | 199012.26 | 199012.26
| Output 3.3. Strengthened community resilience to flooding through the participatory design and implementation of non-structural resilience, adaptation and awareness measures | 10415 | 0 | 1245.37 | 1089.31 | 12749.68
| Output 4: Project Management | 17278.51 | 13674 | 37760.75 | 31161.77 | 99875.03
| TOTAL | 105391.5 | 18679 | 325866.57 | 519627.17 | 969564.24 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE | [7 empty] | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST IRH Regional | PROJECTED COST Albania | PROJECTED COST Montenegro | PROJECTED COST North Macedonia | PROJECTED COST Total Project | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1. Strengthened hydrometric monitoring networks in the riparian countries | 14065 | 95750 | 318962.2 | 37000 | 465777.2 | 2021-12-31
| Output 1.2. Improved knowledge of CC-induced flood risk and risk knowledge sharing through the introduction of river basin modelling tools and technologies for strategic flood risk assessment | 64928 | 46997 | 9938 | 220070 | 341933 | 2023-06-30
| Output 1.3. GIS-based vulnerability, loss and damages assessment tools and database | 6240 | 91900 | 32210 | 28694 | 159044 | 2022-08-31
| Output 2.1. Drin River Basin FRM Policy Framework and improved long-term cooperation on FRM | 163250.75 | 6770 | 9750.75 | 7050.75 | 186822.25 | 2024-07-31
| Output 2.2. Regional, national and sub-national institutions are trained in climate-resilient FRM, responsibilities clarified and coordination strengthened | 105094 | 2953 | 15494 | 10494 | 134035 | 2024-07-31
| Output 2.3. Drin River basin Integrated CCA and FRM Strategy and Plan developed | 0 | 11000 | 8200 | 8200 | 27400 | 2022-06-30
| Output 3.1. Introduction of appraisal-led design for structural and non-structural measures | 61485.32 | 140000 | 335999.71 | 113680 | 651165.03 | 2022-09-30
| Output 3.2. Construction of structural risk reduction measures in prioritized areas | 151566 | 1950 | 222963 | 350930 | 727409 | 2023-10-31
| Output 3.3. Strengthened community resilience to flooding through the participatory design and implementation of non-structural resilience, adaptation and awareness measures | 41566 | 19050 | 55204 | 56870 | 172690 | 2024-10-31
| Output 4: Project Management | 55658 | 42829 | 33526.87 | 34947 | 166960.87 | 2024-10-31
| TOTAL | 663853.07 | 459199 | 1042248.53 | 867935.75 | 3033236.35 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[12 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[12 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[12 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[12 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Government change and/or administrative reforms in the beneficiary countries result in changing priorities that are not fully aligned with the expected results of the project | Low | The project maintained regular consultations with the governments' appointed points of contacts (PoC), as well as high-level governmens' representatives to the Drin Core Group (DCG), which held two sessions during the reporting period, also in the capacity of the Drin FRM Regional Project Board. All relevant materials, e.g. Terms of Reference (ToR) for the key expert positons were shared wth the DCG for their endorsement, while major progress and challenges were presented at the DCG sessions. Meetings and consultations were regularly carried out with the key government stakeholders, representatives of the Directors of National Water Agencies, National Hydrometeorological Services (NHMS) either virtually or in person, COVID-19 pandemic pertmitting. Project continud lobbying and advocating in support of CC adaptation, EWS and DRR at all aforementioned occassons.
Unexpectedly strong extreme climatic events threaten/destroy hydrometeorological and/or flood defense infrastructure | Medium | Disaster risk resilience (DRR) and climate-proofing requirements were embedded in the ToRs for the two detailed design of pre-selected structural flood risk protection measures in Montenegro, initiated durig the reporting period: (i) rehabilitation of emankements along Bojana/Buna River in Montenegro and (ii) regulation of the rivrbed and rehabilitation of Bridges in the downstream Gracanica River. DRR aspects have been included in the ToRs for the Key International Hydrometrics Network expert, so that the specifiactions and isntallation of the hydrometeorological observation equipment will also be defined taking into account the assessment of disaster and climate risks.
Absorption and operational capacities of national project beneficiaries stay inadequate to properly run and maintain modeling, forecasting and EWS | Medium | The ToRs for the Lead International Hydrometrics, Hydraullic Modeller, Hydrologist and Socio-economics Experts , include activities on the needs assessment of the partnering national institutions in financial and resource availablity and management, hydromet network O&M, development of tailor-made trainigs and manuals, etc. aiming at capacity building of all relevant agencies through carrying out training of trainers, on-the-job and field trainings of the staff of relevant agencies, introducing/strengthening internship mechanisms within beneficiaries, developing technical guidelines, methodologies and sustainable operations and maintenance plans for established the modeling, forecasting and EWS.
Changes and turnover in government staff | Medium | The project has relied on the institutional set up of the Drin Core Group and its sub-organizations (Expert Working Groups), systematic institutional memory for all Drin River intitiatives and projects and thus updated the DCG on progress and achievements. in the next period, the proejct will through its Component 2, work on knowledge management and further supporting of DCG systematic institutional memory, so that the new governments' staff can continue building on this information.
Local communities are not interested to be engaged in community-based flood risk reduction measures and EWS | Low | Representatives of the local communities were invited to the national inception workshops in Montenegro and North Macedonia, held in October 2019 and February 2020, respectivelly, at which the project will conducted awareness campaignon the climate-induced natural hazards, vulnerabilities and risks and benefits for reducing these risks. Activities on mobilization of local communities did not commence in the reporting period due to COVID-19 outbreak that nearly conincided with the commmencemtn of the project implementation.
No finances are available for proper operation and maintenance of the upgraded hydrometeorological network, EWS and flood protection structures | Medium | As mentioned above, the Key Internatonal Experts' ToRs include requirements for needs assessment of the partnering institutions in financial and resource availablity and management, and preparation of relevant O&M financing mechanisms.
Failure to engage the private sector in financing mechanisms | Medium | The project supported and coordinated the GEF Drin Flood Insurance Pilot Scheme Project, which among other activities undertook a willingness-to-pay surveys in the three pilot areas in Montenegro, Albania and North Macedonia. If successfull, the pilot scheme approach will be used as a foundation in developing other risk financing mechanisms of which private sector is envisaged to be a part under Drin FRM Component 2 or scaling it up to the basin level, hence failure to engage private sector will shift focus to other mechanisms.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic, the outbreak of which nearly coincided with the commencement of the project, extends with more or less same intensity beyond the Inception Period, thus prolonging negative effects upon the timeliness of the project implementation, so that the timely delivery of certain outcomes could be brought into question. | High | Project team switched to teleworking and telecommuting work modalities, which allowed for maintaining momentum over the activities that had already started and initiating the new ones. Majority of meetings moved onto on-line pratforms thus enabling regular communication with internal and external stakeholders, vendors, etc. Secondly, conditions in the field were assessed and Project Work Plan and Budget were revised in koordination with key national stakeholders, in a way that around 56% of the foreseen delivery in 2020 was moved along 2021 to 2024 period (mostly during 2021). The WP and Budget were sent to the Regional Project Board/ Drin Core Group for endorsement/approval.
COVID-19 pandemic may impact the riparian economies so severely to cause long-lasting economic downturn, which in return may shift the attention from the national authorities from the project to other, more pressing issues. | Med/High | As the project outcomes have been aligned with national priorities, while the project intensified coordination with the DCG and utilizing their influence on the national governments. Project also intensifed meetings with senior officials of relevant government agencies.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As stated above, a number of risk mitigation measures were employed during the current reporting period. The measures proved efficent so far, including those addressing the COVID-19 imposed risks, and as result the project activities were not halted but maintained and gained momentum, especially in the Q3 and Q4 2020. The measures encompassed not just use of virtuall meeting platforms, but also activities such as the e-procurment, monitoring over the work of contractors by using real-time editing/ revewing software tools, e.g. reviewing components of detail of structural flood protection measures, etc. New project management products were fully developed (e.g. Grievance Redress Mechanism), the exisitng ones were updated (e.g. Risk Log, etc.), aiming at increased accountability to the benefiting governments and comunicites, as well as the Adaptation Fund Board.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Poor maintenance of completed flood protection infrastructure by responsible authorities | The project to include activities on developing/enhancing financial sustainability of operations and maintenance of risk reduction and monitoring infrastructure | ESMP yet to be developed for each specific sub-project | n/a | n/a | n/a | n/a
2 - Access and equity
3 – Marginalized and vulnerable Groups |  |  | Low risk significance, no impacts requiring safeguards identified | n/a | ESMP yet to be developed for each specific sub-project | n/a | n/a | n/a | n/a
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | The direct environmental and social risks associated with capacity building or training activities are minimal although there is a risk of gender bias in training due to a lack of access, gender equity and women empowerment in training provided. | 1. The project will use Gender Assessment and Action Plan (GAAP) prepared during the project development phase and updted during the Inception Phase as a tool to monitor/mitigate relevant risks: the project will update the GAAP regularly as relevant, implement it and track implementation 2. Use the Grievance Redress Mechanism (GRM) mechanism to capture any grievances related to gender discrimination 3. The project will tailor all capacity building and training activities to include gender mainstreaming component | Project Objective-level indicators: 1- Women’s representation (%) in consultation meetings on (i) hazard analysis, risk awareness and assessment and vulnerability/capacity analysis; (ii) developing the risk and hazard maps; and (iii) identification of indicators for assessing gender specific aspects of risk and vulnerability Target: At least 30% of women and members of vulnerable groups represented in consultation process and activities defined above 2- Percentage of females and those belonging to vulnerable groups participating in decision-making processes. Target: Women make at least 50% of members of coordination and decision-making bodies, such as the Regional Project Board, National Project Boards, etc. Component 1 - Flood hazard and risk knowledge management tools - level indicators 1- Representation of women and marginalized groups in survey sampling strategies Target: At least 30% of female and members of vulnerable groups targeted in all survey samples 2- Female representation in the Participatory Vulnerability Approach (PVA) tools Target: At least 30% of female persons among those contacted in the PVA 3- Awareness/perception of the climate change among women and vulnerable groups Target: At least 30% of women among those with satisfactory level of CC-related knowledge, based on meeting assessment requirements 4- GIS-based vulnerability assessment tools comply with EUFD standards for addressing GSI dimensions (receptors, exposure, infrastructure, etc.) 5- The recommended adaptation options consider the needs of women. Target: at least 30% of proposed adaption options in the GSI report refer to women in particular Component 2 - Transboundary FRM institutional, legal and policy framework - level indicators 1. Basin-wide and sectoral FRM policies include actions to address gender equality and social inclusion. Target: All FRM policies distinguish women and vulnerable groups as separate beneficiaries 2. GSI indicators, distinguishing women as separate beneficiaries, developed for stakeholders’ assessment Target: gender disaggregated data obtained at a stakeholder institution management level, general personnel level, gaps and capacity development needs identified 3. Institutional capacity development and training project(s) i) increase knowledge of and capacity to use GSI methods and tools, ii) are relevant to the geographic and/or functional mandates of different stakeholders. Target: 5 Institutional lesson learned reports and training material produced on gender responsive flood impact 4. Increased participation of women as well as men in institutional capacity development and training activities, particularly among practitioners and community participants. Target: Women make up at least 30% of trainees Component 3 - Community-based CC adaptation and FRM interventions - level indicators 1. Involvement of women in (i) community-based flood risk management procedures and activities for flood preparedness and response/contingency plans; (ii) the development of action plans for post flood recovery; (iii) the dissemination of information to the communities; (iv) all capacity development activities; and (iv) flood monitoring/warning activities Target: Provision and arrangement are made to ensure that min. 40% women are involved in the above activities 2. Level of awareness at the local community level of GSI dimensions of FRM and EWS including the needs, priorities and contributions of women and other social, particularly vulnerable groups Target: Increased level of knowledge as reported in the meeting satisfaction cards based on separate questions on GSI mainstreaming 3. Female involvement (%) in the identification, prioritization and design of community-level infrastructure (such as small embankments, drainage, flood barriers, etc.); and subsequent regular operations and maintenance. Target: At least 30% of women involved in the above activities 4. Female participation in all training in all training on flood risk assessment and analysis Target: At least 30% of female trainees in all training on flood risk assessment an analysis 5. Training activities contain separate syllabus on GSI dimensions of FRM and EWS Target: At least 20% of the training session is dedicated to GSI dimensions of FRM and EWS 6. Zero tolerance to violation of core labor standards by the selected contractors on implementation of structural measures | n/a | 1. GAAP updated during the Inception period 2. GRM ToR developed and approved by the Drin Core Group (DCG) as the Regional Project Board (RPB) | n/a | n/a
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | 1. Possible ecological consequences (degradation of water quality, exacerbation of riverbed erosion processes, disturbance of fish spawning etc.) affecting critical habitats and offer only temporary solutions to ongoing erosion and siltation processes 2. Project Interventions in proximity of sensitive wetland environment that act as important bird breeding grounds may negatively affect adequate level of water for ecosystems functions | 1/(i) All proposed structural measures with significantly adverse environmental and social impacts were taken out 1/(ii) All structural measures will be positioned in a way to avoid environmentally sensitive areas and all green infrastructures will use a diversity of native species for planting 1/(iii) An integrated landscape management approach will be emphasized for flood control without a narrow emphasis on structural measures that may decrease erosion in own areas while increasing erosion in another 2/(i) Special attention will be given in the transboundary basin-wide hydrological modelling to understand and subsequently prioritize adequate hydrological flows to wetlands to maintain ecosystem functions | ESMP yet to be developed for each specific sub-project | n/a | n/a | n/a | n/a
10 – Conservation of biological diversity |  |  | Project interventions are in proximity to environmentally sensitive areas, critical habitats and protected areas. The project has been designed to improve water management and resilience to climate change. There is the potential for short term small scale impacts to water course during necessary earth works. Importantly, the project intends to improve these ecosystems within the short term, but creating an environmental benefit that will have flow on beneficial impacts to biodiversity
11 – Climate change |  |  | Most of the existing structural measures do not account for future projections of floods, exacerbated by climate change | The project activities represent a paradigm shift in flood control planning by introducing the appraisal-led design for structural and non-structural measures using climate risk information (among other criteria) for detailed design. | ESMP yet to be developed for each specific sub-project
12 – Pollution prevention and resource efficiency |  |  | Potential for the release of chemicals, nutrients, heavy metals and other material from the sediment and for these to enter waterways and groundwater systems during the works | (i) water quality monitoring plan will be developed to ensure chemicals are not released. This will involve testing sediment prior to movement and planning so that the works are not undertaken during rain events (ii) where rainfall is anticipated, appropriate material should be placed under the sediment prior to excavation to ensure there is no seepage into groundwater systems (iii) water quality monitoring for the sources will be designed to identify potential impacts so that management measures can be proactively rather than reactively enacted upon | ESMP yet to be developed for each specific sub-project
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | Likelyhood of sediment movement during the construction activities Accelerated erosion by increasing the speed and volume of channel flow and influence river hydraulics in unpredictable and ways, including the increase of bank erosion. | 1. Prepare an Erosion, Drainage and Sediment Control Plan (EDSCP) and 2. Install silt curtains to restrict sediment movement from the site and covering of sediment where practicable | ESMP yet to be developed for each specific sub-project | n/a | n/a | n/a | n/a
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | (i) As per the ESP Principle 5 (Gender), the GAAP has been updated and approved by the Regional Project Board. (ii) As per the ESP Principles 1, 3, 9, 10, 11, 12 and 15 against which potential negative impacts were identified in relation with the structural flood protection measures, in each ToR for design of a specific structural measure (designs of the two structural measures under development during the reporting period), the project mandated the social and environmental screening (SES), according to both UNDP SES principles and AF ESP, development of an adequate Environment and Social Management Plan and relevant safeguards measures, depending on the ES risks impact assessment. The requireed safeguard measures are yet to be developed.
Have the implementation arrangements been effective during the reporting period? |  | Yes. SE screening procedure was carried out for each of the foreseen structural protection measures against all SE principles, the initially foreseen risks were (re)assessed and safeguards were under development at the end of the reporting period.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures?
Have the implementation arrangements at the EEs been effective during the reporting period?
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, the required capacity for ESMP implementation has proved effective with adequate roles and responsibilities having been assigned to the members of the Project Implementation Unit (PIU): Regional Project Manager (RPM) and Chief Technical Advisor (CTA), both of them are experienced in managing FRM projects, together with National Coordinators and the International Engineer monitoring the design of the identified USP and another pre-selected structural measure in Montenegro, which includes the E&S screening, developing ESMP conductiing ESIA pending the screening outcomes in line with UNDP ESMS and the 15 AF E&S principles, and national legislative requirements. The developed safeguards will be reviewed by an independent third party consultancy before relevant construction permits are granted. Project Quality Assurance (QA) role is performed by the UNDP IRH QA Unit, Regional Programme Manger, Chief Technical Advisor, International Hydrotechnical Engineer and Hydrotechnical Safeguards Specialist, and the Regional Technical Advisor (RTA). As identified under the Project's Environmental and Social Management Framework (ESMF), Annex 6 to the Project Document, upon identification of the USP, the PIU initiated the Environmental and Social Management System (SMS) processes: (i) detailed screening/identification of risks and applicable principles (UNDP SESP screening from Annex 6 will be updated and a screening against AF 15 principles will be conducted in line with the AF Guidance for IE on compliance with the AF ESP); (ii) Impact assessment (scope of ESIA in each USP will depend on the results of risk screening for specific site-based measures, i.e. USP categorization); and (iii) monitoring When broad expertise is required, both screeing and impact assessment within clearly defined ToR may be commissioned during the USP (structural flood protection measure) design to an independent entity, qualified and licensed for ESIA The screening and impact asessment will be reviewed again by a third party during a mandatory review of the USP design.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | With the identification of the below listed USP during the reporting period, update of the overall project ESMF is underway.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Reconstruction of bridges and regulation of riverbed in the downstream Gracanica River in Montenegro | Yes | 1. Segments of the construction activities may pose potential health and safety concerns to local communities; 2. Possible Occupational Health and Safety (OHS) incidents during the construction phase; 3. Possible impact on the Key Biodiversity Area (KBA); 4 Contamination of existing water courses and impacts on water quality; 5. Potential generation of construction waste (both hazardous and non-hazardous); 6. Possible negative impact upon uninterrupted and safe access to public roads by local population during the construction phase, 7. Possible exclusion of local Roma community from participating in decisions that may affect their well-being; 8. Women in local communities may not receive equal access to project information and thus adequate decision-making role | Scope of the impact asessment and a need for full-fledged ESIA to be determined pending the results of the ESP screening and the USP categorization ESMP to be developed following the impact assessment. | Yes, coordination meetings were held with relevant municipal authorities while wider consultation with local communities in the area of intervention were replaced with contacts with local NGOs due to COVID-19 outbreak. The Drin FRM Grievance Redress Mechanism (GRC) has been communicated and thuse widely known to potentially affected parties. | Yes | Under development with the Environmental and Social Management Plan (ESMP) | Under development with the ESMP
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received during the reporting period. |  | N/a
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
To assist the riparian countries in the implementation of an integrated climate-resilient river basin flood risk management approach in order to improve their existing capacity to manage flood risk at regional, national and local levels and to enhance resilience of vulnerable communities in the DRB to climate-induced floods | Objective | Total Number of direct and indirect beneficiaries (disaggregated by sex) with reduced vulnerability to flood risks | 0 | Direct beneficiaries: 190,000 people (50.6% are women) / 12% of the DRB population | N/A, as the activities towards achieving the afore set results have been delayed by the COVID-19 pandemic
Improved climate and risk informed decision-making, availability and use of climate risk information | Outcome | Level of implementation of the systematic gender-responsive socio-economic vulnerability assessment in the DRB | Lack of socio-economic data for risk, damages, losses, exposure and vulnerability assessments. | At least 30% participants of consultations are women | N/A, as the activities towards achieving the afore set results have been delayed by the COVID-19 pandemic
Improved institutional arrangements, legislative and policy framework for climate-resilient FRM, and development of CCA and FRM strategy and plans at the basin, sub-basin, national and sub-national levels | Outcome | Number of staff from targeted institutions trained to respond to impacts of climate-related events | 0 | At least 50 officials and other key national/regional stakeholders trained on improving the enabling environment (minimum 30% women) | N/A, as the activities towards achieving the afore set results have been delayed by the COVID-19 pandemic
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | (i) Gender competencies of each project team member have been assessed and knowledge improved through UNDP's manadatory training courses, e.g: The Gender Journey: Thinking outside the box, UN Course on Prevention of Harassment, Sexual Harassment and Abuse of Authority, Prevention of Sexual Exploitation and Abuse of the Local Population and UN Human Rights and Responsibilities (ii) Gender competencies were amongst criteria in the ToRs for recruitment of the team members (iii) The Project Gender Focal Point and the Regional Project Manager, reviewed and updated the Project's Gender Action Plan (GAP), which was endorsed by the Regional Project Board (RPB) as an annex to the Project Inception Report (iv) Gender responsiveness of the poject budget was assessed during the budger revision process, confirming that project activities were adequately funded to address both men's and women's differentiated adaptation needs. The budget includes sufficent resources for engagement of National Gender Experts who will monitor GAP implementation, conduct gender training of the project team, key stakeholders and local communities, asses capacities of the national partnering institutions to carry out gender-responsive activities and help them build their gender capacities. Revised budget was endorsed by the RPB (v) Project facilitated the increased participation of women as important stakeholders (vi) Finally, the AF Principle 5 - gender equality and women's empowerment has been reviewed against during the social and environmental screening of the sub-projects.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, as the Project has consulted with stakeholders throughout the reporting period in a gender responsive way. Such, gender-informed, participatory methods addressed the key challenge of underrepresentation of either women or men in consultation process, which increased participation of women as important stakeholders and thus guaranteed the inclusion of their often overlooked needs, concerns and abilities in project planning, implementation and monitoring and evaluation. Over 50% of nationally appointed senior stakeholders are women, e.g. two-thirds (66%) of Drin Core Grup members are female. Further, development of the abovementioned gender-sensitive project management tools (GAP), gender sensitive budget, social and environmental screening processes, etc., further demonstrates the Project's complance with the AF Gender Policy. Gender requirements have been embeded in all ToRs for key project internatinal or local experts.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | UNDP performs the role of the EE as well.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | As above.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received during the reporting period. |  | N/a
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Project Manager: | Component 1 – Hazard and risk knowledge management tools / Outcome 1: Improved climate and risk informed decision-making, availability and use of climate risk information
| Output 1.1 – Strengthened hydrometric monitoring networks in the riparian countries based on a unified optimized basin-scale assessment of monitoring needs |  | Outcome 2 | 1.1.1 Review the existing coverage, physical condition and data collection procedure including the quality of data. 1.1.2 Review the monitoring network requirements for effective monitoring for strategic flood risk management, flood forecasting and early warning in the future and optimize the stations coverage 1.1.3 Assessment of the existing telecommunications infrastructure to support the telemetered and automated stations 1.1.4 Half-way through digitizing all relevant historical paper format data for DRB and systematize and store within the hydrometric database. Establish guidelines, procedures, data sharing protocols and user’s manuals for the new hydrometric database 1.1.5 Assessment of the institutional arrangements and capacity for the operation and maintenance (O&M) of the hydrometric network, of the existing roles and responsibilities and the capacity of staff responsible for O&M of the hydrometric network. Assessment of the existing protocols for the collection, transmission, sharing, storage, management and use of the observed data 1.1.6 Establish mechanisms for population and maintenance of centralized basin hydrometric database 1.1.7 Prepare an operational plan for the hydrometric network including transmission of data, data management, data analysis and reporting procedures. 1.1.8 Provide detailed specification and design including costs of all equipment and each component of the hydrometric network specified including the detailed design and bid document for the stations for future rehabilitation / new installation 1.1.9 Procurement and installation of hydrometric monitoring equipment 1.1.10 Review existing financing of hydrometric network O&M; identify resources, training needs and institutional arrangements; develop and implement O&M financing mechanisms for the hydrometric network. |  | Progress was made in the Activity 1.1.8 under which specifications of hydrometric equipment for the part of the basin in North Macedona were developed in coordination with the National Hydromet Services (UHMR). This Activity in Montenegro was delayed to the Q1 2021 while the Activity is not foreseen for Albanian part of the DRB. The ToR for the Lead International Hydrometric Network Expert was developed in coordination with key implementing partners (national authorities, GIZ) and endorsed by the Drin Core Group (DCG)/ Regional Project Board (RPB). A competitive recruitment process was finalized. | MS
| Output 1.2 - Improved knowledge of climate change induced flood risk, and risk knowledge sharing through the introduction of modelling tools and technologies for the strategic flood risk assessment based on EUFD and development of basin flood hazard maps |  | Outcome 8 | 1.2.1 Establish Spatial Data Initiative and data management system for project 1.2.2 Undertake detailed topographic surveys of the river channel through high risk areas including all major infrastructure across the river (e.g. bridges, dams etc.) and along river banks (e.g. flood walls, levees etc.) for the Crn Drim in Macedonia 1.2.3 Acquire/purchase/commission high resolution topographic data for the floodplain areas through high risk areas of the Crn Drim in N. Macedonia. 1.2.4 Using the most appropriate modelling techniques, establish numerical high-level basin-wide numerical hydrological models of the DRB for the production of high-resolution hazard maps in line with EU WFD with detailed modelling for FRB in North Macedonia based on detailed surveys of the physical characteristics of the river basin. GIZ models integrated into hydrological models where available. Maps produced for a number of different return periods and for a range of CC scenarios. 1.2.5 Half-way through integrating detailed hydrological and hydraulic modelling for other Areas for further assessment (AFAs), modelled by GIZ and riparian governments into the high-level river basin model, as and when they become available 1.2.6 Capacity assessment of relevant institutions for flood risk assessment and modelling and developing a long-term capacity development plan and training needs. Training in hydraulic modelling to practitioners |  | Progress was made in the Activity 1.2.3 under which the ToR was developed in coordination with the National Agency for the Real Estate Cadastre for acquiring the LiDAR hi-resolution DEM for the high risk areas of the Crn Drim sub-basin in North Macedonia. The procurement of the DEM is underway, in coordination with the Agency that is in charge of procuremen to fhe LiDAR DEM for the entire country. The ToR for the Lead Hydraullic Modeler developed in coordination with key project stakeholders (national auhorities, GIZ) and endorsed by the DCG/RPB. A competitive recruitment process finalized. ToRs for local experts in hydrology, hydraulic modelling, hydrometrics and GIS developed, recruitment underway for part of the DRB in North Macedonia. | MS
| Output 1.3 - GIS-based vulnerability, loss and damages assessment tool and database established to record, analyze, predict and assess flood events and associated losses |  | Outcome 8 | 1.3.1 Develop and codify methods and tools for undertaking socio-economic surveys to collect necessary information to fully map the socio-economic conditions of within the basin 1.3.2 Undertake socio-economic and vulnerability assessment to fully map existing vulnerability within the DRB, in order to identify the most appropriate adaptation options to reduce vulnerability within the s basin 1.3.3 Develop a GIS-based flood risk model 1.3.4 Implement the DisInventar database in Riparian countries for the systematic recording of damage and loss. Harmonize methods, guidelines and procedures in line with Sendai Framework, for recording flood events, undertaking post-event surveys and assessing vulnerability to flooding 1.3.5 Develop harmonized methods, guidelines and procedures in line with Sendai Framework, for recording flood events, undertaking post-event surveys and assessing vulnerability to flooding as well as assessing the effectiveness of flood mitigation measures in reducing vulnerability and damages 1.3.6 Undertake cost-benefit options analysis using the vulnerability loss and damages model to identify options that maximize benefits as the basis for the development of the Integrated FRM strategy and plan for the basin |  | The ToR for the Lead Socio Economist developed in coordination with key project stakeholders (national auhorities, GIZ) and endorsed by the DCG/RPB. A competitive recruitment process finalized. | MS
Component 2 – Transboundary FRM institutional, legislative and policy framework / Outcome 2: Improved institutional arrangements, legislative and policy framework for FRM, and development of climate change adaptation and flood risk management strategy and plans at the basin, sub-basin, national and sub-national levels
| Output 2.1 – Drin River Basin FRM Policy Framework and improved long-term cooperation on flood risk management |  | Outcome 7 | 2.1.1 Review existing FM policy and enabling environments in each riparian country and develop basin FRM policies for the implementation of FRM legislative and policy framework in line with relevant EU directives 2.1.2 Develop basin risk transfer mechanisms: Development of risk financing and risk transfer mechanisms strategy to include private sector engagement strategy for long-term implementation of risk financing and risk transfer mechanisms for national-level flood risk financing and resilience strategy. Undertake feasibility studies of identified and shortlisted risk financing mechanisms, development of a basin flood insurance model for the assessment of premiums and payouts of flood events of different return periods. Development of basin flood insurance scheme 2.1.3 Sector FRM policies (at least 2 - energy, agriculture): Undertake detailed technical studies on climate change impacts on the identified sectors in the DRB. Develop and codify detailed methodologies for incorporating climate-change responsive flood risk considerations into risk assessments, strategies, policies and plans for the energy and agriculture sectors. Develop and finalize robust sector FRM policies and any necessary enabling guidelines and/or tools for effective implementation of new policies. |  | This Output to be delivered by the Global Water Partnership (GWP) Organization, as the project Responsible Party. No progress was made under this Output. Formalization of the Letter of Agreement between the project and GWP is underway. | MU
| Output 2.2 – Regional, national and sub-national institutions (including meteorological and hydrological sectors) are trained in flood risk management, roles and responsibilities clarified and coordination mechanisms strengthened for effective climate-resilient FRM |  | Outcome 2 | 2.2.1 Institutional mapping to identify the current relevant national and sub-national government departments with functions in flood risk management in each Riparian country 2.2.2 Institutional capacity assessment and gap analysis to include functional, resourcing, technical and financial capacity assessment. Development of long-term Institutional capacity development plan addressing resourcing, technical, and financial needs in each Riparian. Develop training programme for climate risk management and flood risk management and embed in relevant national/regional institutions to improve the technical capacity and knowledge base for climate risk management and a long-term adaptation planning for flood risk management 2.2.3 Revisit the ToRs of the Drin EWG on Floods in terms of mandate, membership, resource requirements, technical capacity and technical enabling environment; data sharing and data access and technical means and tools for coordination. Develop and start implementation of a strategy and work program of the Drin EWG on Floods. |  | This Output to be delivered by the Global Water Partnership (GWP) Organization, as the project Responsible Party. No progress was made under this Output. Formalization of the Letter of Agreement between the project and GWP is underway. | MU
| Output 2.3 – Drin River Basin Integrated CCA and FRM Strategy and Plan Developed |  | Outcome 7 | 2.3.1 Development of an integrated basin flood risk management plan for the DRB with participation of all relevant stakeholders. From the basin plan, and sub-national plans will be developed |  | n/a. Commencement of the activities under this Output is planned in the next reporting period.
Component 3 – Priority community-based climate change adaptation and FRM interventions / Outcome 3: Strengthened resilience of local communities through improved flood forecasting and early warning, implementation of structural and non-structural measures and the strengthened capacity for CCA and FRM at the local level
| Output 3.1 – Introduction of appraisal-led design for structural and non-structural measures using climate risk information and cost-benefit appraisal methods and application of methods to the detailed design of prioritized structural and non-structural measures for three riparian countries |  | Outcome 4 | 3.1.1 Undertake optionnering for long-term FRM measures for DRB in Albania. Feasibility, outlined design and indicative costing 3.1.2.a Undertake detailed design of structural measures to be implemented by project in Albania 3.1.2.b Undertake detailed design of structural measures to be implemented by project in Montenegro 3.1.2.c Undertake detailed design of structural measures to be implemented by project in North Macedonia |  | 3.1.2.a No feasibility, outline design and costing were done at PPG stage for structural measures to be implemented by the project in Albania, thus no structural measures had been pre-selected in this country through project document. Instead, project developed a ToR and advertised procurement for Activity 3.1.1 - underake optioneering for long-term FRM strucural measures in Albania, ahead of the planned time. 3.1.2.b Detailed design of two structural measures in Montenegro: (I) rehabilitation of embakments along the Bojana/Buna river (pre-selected by the Project Document) and (ii) rehabilitation of bridges and regulation of the riverbed in the downstream Gracanica River (USB), is well underway with completion foreseen for Q1 2021. ToRs developed by indepndent international engineer in coordiantion with key implementing partners, and endorsed by the DCG/RPB. | MS
| Output 3.2 – Construction of structural risk reduction measures in prioritized areas |  | Outcome 1 | 3.2.1 Investment in implementation of structural measures in Albania 3.2.2 Investment in implementation of structural measures in Montenegro 3.2.3 Investment in implementation of structural measures in North Macedonia |  | One of the pre-identified sub-projects from the Activity 3.2.3 - Investment in implementation of structural measures in North Macedonia - the improvement of hydraulic capacity of Crni Drim River within the urban zone in the municipality of Struga was completed in the Q4 2020, ahead of the planned time. | S
| Output 3.3 - Strengthened local community resilience to flooding through the participatory design and implementation of non-structural community-based resilience, adaptation and awareness measures |  | Outcome 1 | 3.3.1 Undertake detailed design of non-structural measures implemented by the project 3.3.2 Investment in non-structural measures in Albania 3.3.3 Investment in non-structural measures in Montenegro 3.3.4 Investment in non-structural measure in North Macedonia |  | n/a
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Bojan Kovacevic, Regional Project Manager
| Email: | bojan.kovacevic@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall progress during the reporting period has been rated as "Marginally Satisfactory (MS)", as the project activities have remained on track to achieve most of its major outcomes/outputs, however with significant delay caused by COVID-19 pandemic outbreak issue. The outbreak nearly coincided with the commencement of the project implementation period and lasted throughout the reporting period. The issue impeded the deployment of the Project Management Unit and international key experts, who once on board were prevented from conducting the field visits to the river basin, in order to undertake site inspections and meet stakeholders, especially at the local community level, with whom the distant (online) communication was hardly possible. Thus, timely and quality assessments of the assumptions made in the project documents were delayed, and the relevant management products, such as the terms of reference (ToRs) took more time to develop. The pandemic issue has been addressed by: (i) switching the project team working modality to teleworking and telecommuting and intensive use of online platforms and management tools, and (ii) revising the Multi-annual Project Work Plan and accordingly the Budget, by relocating the funds earmarked for 2020 along the same budget lines mostly over to 2021 and the rest of the project implementation period (2022 - 2024). The proposed changes have been endorsed by the Drin Core Group in its capacity of the Regional Project Board. The activities that could not have been fully or partially implemented through the online working modalities had to be postponed to the subsequent years. The implementation delays in its first year, which could not have been avoided by exercising due diligence, are expected to be caught up with during the rest of the implementation period, and will not impede from achieving most of the project's outcomes/outputs. COVID-19 pandemic effects will continue to be a major challenge to project implementation since it will extend beyond its first year of implementation and will continue to negatively effect local economies in the targeted riparian countries, etc. As a lesson learned during this period, the project will accelerate the uptake of digital solutions while assisting the implementing partners to fast-track the setup of new digital infrastructure, via activities under Component 1, such as, digitalizing all remaining historical paper format data for the DRB, systematizing and storing within hydrometric database, supporting Integrated Management System established through GEF Drin Project, establishing numerical high-level basin wide hydrological and hydraulic models of the DRB, which will integrate the models of flood prone areas already done by other implementing partners.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1. Hazard and risk knowledge management tools / Outcome 1. Improved climate and risk informed decision-making, availability and use of climate risk information | [5 empty] | MS
| Output 1.1 – Strengthened hydrometric monitoring networks in the riparian countries based on a unified optimized basin-scale assessment of monitoring needs |  | Outcome 2 | 1.1.1 Review the existing coverage, physical condition and data collection procedure including the quality of data. 1.1.2 Review the monitoring network requirements for effective monitoring for strategic flood risk management, flood forecasting and early warning in the future and optimize the stations coverage 1.1.3 Assessment of the existing telecommunications infrastructure to support the telemetered and automated stations 1.1.4 Half-way through digitizing all relevant historical paper format data for DRB and systematize and store within the hydrometric database. Establish guidelines, procedures, data sharing protocols and user’s manuals for the new hydrometric database 1.1.5 Assessment of the institutional arrangements and capacity for the operation and maintenance (O&M) of the hydrometric network, of the existing roles and responsibilities and the capacity of staff responsible for O&M of the hydrometric network. Assessment of the existing protocols for the collection, transmission, sharing, storage, management and use of the observed data 1.1.6 Establish mechanisms for population and maintenance of centralized basin hydrometric database 1.1.7 Prepare an operational plan for the hydrometric network including transmission of data, data management, data analysis and reporting procedures. 1.1.8 Provide detailed specification and design including costs of all equipment and each component of the hydrometric network specified including the detailed design and bid document for the stations for future rehabilitation / new installation 1.1.9 Procurement and installation of hydrometric monitoring equipment 1.1.10 Review existing financing of hydrometric network O&M; identify resources, training needs and institutional arrangements; develop and implement O&M financing mechanisms for the hydrometric network. |  | International consultant to support review of the coverage and effectiveness of the existing hydrometeorological observation network and development of the upgraded hydrometric network in the Drin River basin (DRB) recruited. Technical specifications for the procurement of the hydrometeorological observation equipment for North Macedonia developed. Specifications for the hydrometric equipment for Montenegro will be developed in the next reporting period (procurement id not envisaged for Albania). | MS
| Output 1.2 - Improved knowledge of climate change induced flood risk, and risk knowledge sharing through the introduction of modelling tools and technologies for the strategic flood risk assessment based on EUFD and development of basin flood hazard maps |  | Outcome 8 | 1.2.1 Establish Spatial Data Initiative and data management system for project 1.2.2 Undertake detailed topographic surveys of the river channel through high risk areas including all major infrastructure across the river (e.g. bridges, dams etc.) and along river banks (e.g. flood walls, levees etc.) for the Crn Drim in Macedonia 1.2.3 Acquire/purchase/commission high resolution topographic data for the floodplain areas through high risk areas of the Crn Drim in N. Macedonia. 1.2.4 Using the most appropriate modelling techniques, establish numerical high-level basin-wide numerical hydrological models of the DRB for the production of high-resolution hazard maps in line with EU WFD with detailed modelling for FRB in North Macedonia based on detailed surveys of the physical characteristics of the river basin. GIZ models integrated into hydrological models where available. Maps produced for a number of different return periods and for a range of CC scenarios. 1.2.5 Half-way through integrating detailed hydrological and hydraulic modelling for other Areas for further assessment (AFAs), modelled by GIZ and riparian governments into the high-level river basin model, as and when they become available 1.2.6 Capacity assessment of relevant institutions for flood risk assessment and modelling and developing a long-term capacity development plan and training needs. Training in hydraulic modelling to practitioners |  | Recruitment of the lead international consultant to support hydraulic modelling has been finalized. TORs for the national modelling experts in the beneficary countries developed. TORs have been developed for acquiring the LiDAR hi-resolution DEM for the high risk areas of the Crn Drim sub-basin in North Macedonia (in coordination with the National Agency for the Real Estate Cadastre). The procurement of the LiDAR DEM is underway. The project established good cooperation, coordination and information exchange with the partner flood risk modeling project implemented by GIZ. | MS
| Output 1.3 - GIS-based vulnerability, loss and damages assessment tool and database established to record, analyze, predict and assess flood events and associated losses |  | Outcome 8 | 1.3.1 Develop and codify methods and tools for undertaking socio-economic surveys to collect necessary information to fully map the socio-economic conditions of within the basin 1.3.2 Undertake socio-economic and vulnerability assessment to fully map existing vulnerability within the DRB, in order to identify the most appropriate adaptation options to reduce vulnerability within the s basin 1.3.3 Develop a GIS-based flood risk model 1.3.4 Implement the DisInventar database in Riparian countries for the systematic recording of damage and loss. Harmonize methods, guidelines and procedures in line with Sendai Framework, for recording flood events, undertaking post-event surveys and assessing vulnerability to flooding 1.3.5 Develop harmonized methods, guidelines and procedures in line with Sendai Framework, for recording flood events, undertaking post-event surveys and assessing vulnerability to flooding as well as assessing the effectiveness of flood mitigation measures in reducing vulnerability and damages 1.3.6 Undertake cost-benefit options analysis using the vulnerability loss and damages model to identify options that maximize benefits as the basis for the development of the Integrated FRM strategy and plan for the basin |  | International consultant/lead economist to support socio-economic risk and vulnerability assessment and modeling has been recruited. The technical work will commence in the next reporting period. | MS
| Component 2 – Transboundary FRM institutional, legislative and policy framework / Outcome 2: Improved institutional arrangements, legislative and policy framework for FRM, and development of climate change adaptation and flood risk management strategy and plans at the basin, sub-basin, national and sub-national levels | [5 empty] | MU
| Output 2.1 – Drin River Basin FRM Policy Framework and improved long-term cooperation on flood risk management |  | Outcome 7 | 2.1.1 Review existing FM policy and enabling environments in each riparian country and develop basin FRM policies for the implementation of FRM legislative and policy framework in line with relevant EU directives 2.1.2 Develop basin risk transfer mechanisms: Development of risk financing and risk transfer mechanisms strategy to include private sector engagement strategy for long-term implementation of risk financing and risk transfer mechanisms for national-level flood risk financing and resilience strategy. Undertake feasibility studies of identified and shortlisted risk financing mechanisms, development of a basin flood insurance model for the assessment of premiums and payouts of flood events of different return periods. Development of basin flood insurance scheme 2.1.3 Sector FRM policies (at least 2 - energy, agriculture): Undertake detailed technical studies on climate change impacts on the identified sectors in the DRB. Develop and codify detailed methodologies for incorporating climate-change responsive flood risk considerations into risk assessments, strategies, policies and plans for the energy and agriculture sectors. Develop and finalize robust sector FRM policies and any necessary enabling guidelines and/or tools for effective implementation of new policies. |  | This Output is to be delivered by the project Responsible Party - the Global Water Partnership (GWP). Letter of Agreement between the project and GWP is under development. No progress was achieved under this Output. | MU
| Output 2.2 – Regional, national and sub-national institutions (including meteorological and hydrological sectors) are trained in flood risk management, roles and responsibilities clarified and coordination mechanisms strengthened for effective climate-resilient FRM |  | Outcome 2 | 2.2.1 Institutional mapping to identify the current relevant national and sub-national government departments with functions in flood risk management in each Riparian country 2.2.2 Institutional capacity assessment and gap analysis to include functional, resourcing, technical and financial capacity assessment. Development of long-term Institutional capacity development plan addressing resourcing, technical, and financial needs in each Riparian. Develop training programme for climate risk management and flood risk management and embed in relevant national/regional institutions to improve the technical capacity and knowledge base for climate risk management and a long-term adaptation planning for flood risk management 2.2.3 Revisit the ToRs of the Drin EWG on Floods in terms of mandate, membership, resource requirements, technical capacity and technical enabling environment; data sharing and data access and technical means and tools for coordination. Develop and start implementation of a strategy and work program of the Drin EWG on Floods. |  | This Output is to be delivered by the project Responsible Party - the Global Water Partnership (GWP). Letter of Agreement between the project/UNDP and GWP is under development. No progress was achieved under this Output. However, the project is actively engaged with the Drin Core Group (DCG) and the Drin Expert Working Group (EWG) on Floods and with the other regional and national institutional stakeholders. | MU
| Output 2.3 – Drin River Basin Integrated CCA and FRM Strategy and Plan Developed |  | Outcome 7 | 2.3.1 Development of an integrated basin flood risk management plan for the DRB with participation of all relevant stakeholders. From the basin plan, and sub-national plans will be developed |  | Work to be commenced in the next reporting period. | n/a
| Component 3 – Priority community-based climate change adaptation and FRM interventions / Outcome 3: Strengthened resilience of local communities through improved flood forecasting and early warning, implementation of structural and non-structural measures and the strengthened capacity for CCA and FRM at the local level | [5 empty] | S
| Output 3.1 – Introduction of appraisal-led design for structural and non-structural measures using climate risk information and cost-benefit appraisal methods and application of methods to the detailed design of prioritized structural and non-structural measures for three riparian countries |  | Outcome 4 | 3.1.1 Undertake optionnering for long-term FRM measures for DRB in Albania. Feasibility, outlined design and indicative costing 3.1.2.a Undertake detailed design of structural measures to be implemented by project in Albania 3.1.2.b Undertake detailed design of structural measures to be implemented by project in Montenegro 3.1.2.c Undertake detailed design of structural measures to be implemented by project in North Macedonia |  | Detailed technical design of flood risk reduction measures in Montenegro and related environmental and social risk management plan is being finalized with the support of an international engineer. TORs has been developed for the selection of risk reduction sites/measures in Albania. | MS
| Output 3.2 – Construction of structural risk reduction measures in prioritized areas |  | Outcome 1 | 3.2.1 Investment in implementation of structural measures in Albania 3.2.2 Investment in implementation of structural measures in Montenegro 3.2.3 Investment in implementation of structural measures in North Macedonia |  | Although the work was planned to commence in the next reporting period, one pre-selected flood risk reduction sub-project in the Struga Municipality (North Macedonia) has been commissioned and completed in 2020. | S
| Output 3.3 - Strengthened local community resilience to flooding through the participatory design and implementation of non-structural community-based resilience, adaptation and awareness measures |  | Outcome 1 | 3.3.1 Undertake detailed design of non-structural measures implemented by the project 3.3.2 Investment in non-structural measures in Albania 3.3.3 Investment in non-structural measures in Montenegro 3.3.4 Investment in non-structural measure in North Macedonia |  | Work to commence in the next reporting period. | n/a
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Natalia Olofinskaya, Regional Technical Advisor
| Email: | Nataly.olofinskaya@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
This is the first PPR for the project. During the reporting period the project has been formally launched and completed its Inception Phase. The regional and national inception workshops have been conducted, the regional Steering Committee (Drin Core Group) held several meetings with a strong ownership of the national and regional stakeholders. The Project Implementation Unit and the national implementation teams have been established, and the project team has been fully staffed. The Inception report has been submitted and implementation of the project technical activities has started in all beneficiary countries. The project inception phase has been affected by COVID-19 pandemic as reported by the Project Manager above. However, despite delays incurred during the reporting period, the Project Team has demonstrated a very good progress in the second half of 2020. In particular, under the Outcome 1 (Improved climate and risk informed decision-making, availability and use of climate risk information) the project has completed recruitment of international technical consultants on hydrometric monitoring network, hydraulic modelling and socio-economic risk and vulnerability assessment. Specifications for the upgrade of the hydrometeorological observation network and LiDAR DEM in North Macedonia has been developed. Following detailed consultations with GIZ FRM project in the Drin River Basin, a very producting working level cooperation and coordination with GIZ has been established. Under the Outcome 2 (Improved institutional arrangements, legislative and policy framework for FRM, and development of climate change adaptation and flood risk management strategy and plans at the basin, sub-basin, national and sub-national levels), signature of the Letter of Agreement with the Responsible Party - GWP-Med - is still pending, which resulted in the delays in the commencement of the activities. However, the project has been engaged with the Drin Core Group (DCG) with the assistance of GWP-Med (including reporting to the DCG on the inception phase and work plans) and with the Drin Expert Working Group on Floods. The LOA with the GWP-Med will be signed during the next reporting period to allow commencement of the technical activities on policy support and capacity building. Under the Outcome 3 (Strengthened resilience of local communities through improved flood forecasting and early warning, implementation of structural and non-structural measures and the strengthened capacity for CCA and FRM at the local level) some activities have been implemented ahead of schedule due to the completed preparatory work. This includes completion of the flood risk reduction measures in the North Macedonian site in Struga Municipality resulting in a better flood protection for 1000 people. In addition, detailed technical design and safeguards planning are being finalized for the high risk sites in Montenegro with the support of an international engineer. TORs for the selection of the risk reduction sites/measures in Albania have been prepared. In conclusion, despite the delays incurred during the inception phase caused by the COVID-19 pandemic, the project is now fully operational and demonstrated a good progress with the technical activities. It is likely that the project will catch up with the implementation schedule in the next reporting periods. The level of engagement and ownership of the national and regional stakeholders in the Drin River Basin has been very strong. Therefore, the overall progress is assessed as Marginally Satisfactory (taking into acount the delays) with the high likelihood of improvement during the next reporting period.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Agency | Component 1. Hazard and risk knowledge management tools / Outcome 1. Improved climate and risk informed decision-making, availability and use of climate risk information
| Output 1.1 – Strengthened hydrometric monitoring networks in the riparian countries based on a unified optimized basin-scale assessment of monitoring needs |  | Outcome 2 | 1.1.1 Review the existing coverage, physical condition and data collection procedure including the quality of data. 1.1.2 Review the monitoring network requirements for effective monitoring for strategic flood risk management, flood forecasting and early warning in the future and optimize the stations coverage 1.1.3 Assessment of the existing telecommunications infrastructure to support the telemetered and automated stations 1.1.4 Half-way through digitizing all relevant historical paper format data for DRB and systematize and store within the hydrometric database. Establish guidelines, procedures, data sharing protocols and user’s manuals for the new hydrometric database 1.1.5 Assessment of the institutional arrangements and capacity for the operation and maintenance (O&M) of the hydrometric network, of the existing roles and responsibilities and the capacity of staff responsible for O&M of the hydrometric network. Assessment of the existing protocols for the collection, transmission, sharing, storage, management and use of the observed data 1.1.6 Establish mechanisms for population and maintenance of centralized basin hydrometric database 1.1.7 Prepare an operational plan for the hydrometric network including transmission of data, data management, data analysis and reporting procedures. 1.1.8 Provide detailed specification and design including costs of all equipment and each component of the hydrometric network specified including the detailed design and bid document for the stations for future rehabilitation / new installation 1.1.9 Procurement and installation of hydrometric monitoring equipment 1.1.10 Review existing financing of hydrometric network O&M; identify resources, training needs and institutional arrangements; develop and implement O&M financing mechanisms for the hydrometric network. |  | Recruitment of the lead international hydrometric networks consultant, who will review the status and adquacy of the existing hydromet monitoring networks in the riparian countries and identify the optimized networks required for basin-scale flood risk monitoring and management, was finalized, based on the ToR that had been agreed by the implementing partners (GIZ, etc.) Technical specs. of the hydromet equipment for the hydromet monitoring network of the Crn Drin sub-basin in North Macedonia were developed in coordination with the national hydromet service. | MS
| Output 1.2 - Improved knowledge of climate change induced flood risk, and risk knowledge sharing through the introduction of modelling tools and technologies for the strategic flood risk assessment based on EUFD and development of basin flood hazard maps |  | Outcome 8 | 1.2.1 Establish Spatial Data Initiative and data management system for project 1.2.2 Undertake detailed topographic surveys of the river channel through high risk areas including all major infrastructure across the river (e.g. bridges, dams etc.) and along river banks (e.g. flood walls, levees etc.) for the Crn Drim in Macedonia 1.2.3 Acquire/purchase/commission high resolution topographic data for the floodplain areas through high risk areas of the Crn Drim in N. Macedonia. 1.2.4 Using the most appropriate modelling techniques, establish numerical high-level basin-wide numerical hydrological models of the DRB for the production of high-resolution hazard maps in line with EU WFD with detailed modelling for FRB in North Macedonia based on detailed surveys of the physical characteristics of the river basin. GIZ models integrated into hydrological models where available. Maps produced for a number of different return periods and for a range of CC scenarios. 1.2.5 Half-way through integrating detailed hydrological and hydraulic modelling for other Areas for further assessment (AFAs), modelled by GIZ and riparian governments into the high-level river basin model, as and when they become available 1.2.6 Capacity assessment of relevant institutions for flood risk assessment and modelling and developing a long-term capacity development plan and training needs. Training in hydraulic modelling to practitioners |  | Recruitment of the lead international lead hydraulic modeling expert, who is to esablish numerical high-level basin-wide hydrological and hydraulic models and undertake detailed modelling for the Crn Drim sub-basin in North Macedonia, and in line with EUFD produce hi-res flood hazard indudation maps, was finalized. ToR and area boundaries developed for the LiDAR arerial surveillance to produce hi-res Digital Terrain Model (DEM) for hydraulic modelling of the Crn Drim sub-basin in North Macedonia, in coordinatio with the National Real Estate Cadastre Agency. | MS
| Output 1.3 - GIS-based vulnerability, loss and damages assessment tool and database established to record, analyze, predict and assess flood events and associated losses |  | Outcome 8 | 1.3.1 Develop and codify methods and tools for undertaking socio-economic surveys to collect necessary information to fully map the socio-economic conditions of within the basin 1.3.2 Undertake socio-economic and vulnerability assessment to fully map existing vulnerability within the DRB, in order to identify the most appropriate adaptation options to reduce vulnerability within the s basin 1.3.3 Develop a GIS-based flood risk model 1.3.4 Implement the DisInventar database in Riparian countries for the systematic recording of damage and loss. Harmonize methods, guidelines and procedures in line with Sendai Framework, for recording flood events, undertaking post-event surveys and assessing vulnerability to flooding 1.3.5 Develop harmonized methods, guidelines and procedures in line with Sendai Framework, for recording flood events, undertaking post-event surveys and assessing vulnerability to flooding as well as assessing the effectiveness of flood mitigation measures in reducing vulnerability and damages 1.3.6 Undertake cost-benefit options analysis using the vulnerability loss and damages model to identify options that maximize benefits as the basis for the development of the Integrated FRM strategy and plan for the basin |  | Recruitment of the lead international socio-economist, who is to develop methodology and tools for undertaking socio-economic surveys to gather data needed to fully map socio-economic conditions, conducting s/e and vulnerability assessment and oversee development of a GIS-based flood risk model, was finalized. | MS
Component 2 – Transboundary FRM institutional, legislative and policy framework / Outcome 2: Improved institutional arrangements, legislative and policy framework for FRM, and development of climate change adaptation and flood risk management strategy and plans at the basin, sub-basin, national and sub-national levels
| Output 2.1 – Drin River Basin FRM Policy Framework and improved long-term cooperation on flood risk management |  | Outcome 7 | 2.1.1 Review existing FM policy and enabling environments in each riparian country and develop basin FRM policies for the implementation of FRM legislative and policy framework in line with relevant EU directives 2.1.2 Develop basin risk transfer mechanisms: Development of risk financing and risk transfer mechanisms strategy to include private sector engagement strategy for long-term implementation of risk financing and risk transfer mechanisms for national-level flood risk financing and resilience strategy. Undertake feasibility studies of identified and shortlisted risk financing mechanisms, development of a basin flood insurance model for the assessment of premiums and payouts of flood events of different return periods. Development of basin flood insurance scheme 2.1.3 Sector FRM policies (at least 2 - energy, agriculture): Undertake detailed technical studies on climate change impacts on the identified sectors in the DRB. Develop and codify detailed methodologies for incorporating climate-change responsive flood risk considerations into risk assessments, strategies, policies and plans for the energy and agriculture sectors. Develop and finalize robust sector FRM policies and any necessary enabling guidelines and/or tools for effective implementation of new policies. |  | This Output to be delivered by the Global Water Partnership (GWP) Organization, as the project Responsible Party. No progress was made under this Output. Formalization of the Letter of Agreement between the project and GWP is underway. | MU
| Output 2.2 – Regional, national and sub-national institutions (including meteorological and hydrological sectors) are trained in flood risk management, roles and responsibilities clarified and coordination mechanisms strengthened for effective climate-resilient FRM |  | Outcome 2 | 2.2.1 Institutional mapping to identify the current relevant national and sub-national government departments with functions in flood risk management in each Riparian country 2.2.2 Institutional capacity assessment and gap analysis to include functional, resourcing, technical and financial capacity assessment. Development of long-term Institutional capacity development plan addressing resourcing, technical, and financial needs in each Riparian. Develop training programme for climate risk management and flood risk management and embed in relevant national/regional institutions to improve the technical capacity and knowledge base for climate risk management and a long-term adaptation planning for flood risk management 2.2.3 Revisit the ToRs of the Drin EWG on Floods in terms of mandate, membership, resource requirements, technical capacity and technical enabling environment; data sharing and data access and technical means and tools for coordination. Develop and start implementation of a strategy and work program of the Drin EWG on Floods. |  | This Output to be delivered by the Global Water Partnership (GWP) Organization, as the project Responsible Party. No progress was made under this Output. Formalization of the Letter of Agreement between the project and GWP is underway. | MU
| Output 2.3 – Drin River Basin Integrated CCA and FRM Strategy and Plan Developed |  | Outcome 7 | 2.3.1 Development of an integrated basin flood risk management plan for the DRB with participation of all relevant stakeholders. From the basin plan, and sub-national plans will be developed |  | n/a. Commencement of the activities under this Output is planned in the next reporting period.
Component 3 – Priority community-based climate change adaptation and FRM interventions / Outcome 3: Strengthened resilience of local communities through improved flood forecasting and early warning, implementation of structural and non-structural measures and the strengthened capacity for CCA and FRM at the local level
| Output 3.1 – Introduction of appraisal-led design for structural and non-structural measures using climate risk information and cost-benefit appraisal methods and application of methods to the detailed design of prioritized structural and non-structural measures for three riparian countries |  | Outcome 4 | 3.1.1 Undertake optionnering for long-term FRM measures for DRB in Albania. Feasibility, outlined design and indicative costing 3.1.2.a Undertake detailed design of structural measures to be implemented by project in Albania 3.1.2.b Undertake detailed design of structural measures to be implemented by project in Montenegro 3.1.2.c Undertake detailed design of structural measures to be implemented by project in North Macedoni |  | 3.1.2.b Detailed design of two structural measures in Montenegro: rehabilitation of embakments along the Bojana/Buna river (pre-selected by the Project Document) and ehabilitation of bridges and regulation of the riverbed in the downstream Gracanica River (USB), well underway including the Social and Environmental Screening Procedure against the UNDP and AF principles. Based on the identified risks Environmental and Social Impact Assessment (ESIA) will be conducted and adequate safeguards designed. | MS
| Output 3.2 – Construction of structural risk reduction measures in prioritized areas |  | Outcome 1 | 3.2.1 Investment in implementation of structural measures in Albania 3.2.2 Investment in implementation of structural measures in Montenegro 3.2.3 Investment in implementation of structural measures in North Macedonia |  | One of the pre-identified sub-projects for implementation of structural measures in North Macedonia - the improvement of hydraulic capacity of Crni Drim River within the urban zone in the municipality of Struga was completed in the Q4 2020, ahead of the planned time. | S
| Output 3.3 - Strengthened local community resilience to flooding through the participatory design and implementation of non-structural community-based resilience, adaptation and awareness measures |  |  | 3.3.1 Undertake detailed design of non-structural measures implemented by the project 3.3.2 Investment in non-structural measures in Albania 3.3.3 Investment in non-structural measures in Montenegro 3.3.4 Investment in non-structural measure in North Macedonia |  | n/a. Implementation of civil works to commence in the next reporting period
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Armen Grigoryan, Climate and Disaster Team Leader, UNDP Istanbul Regional Hub
| Email: | armen.grigoryan@undp.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | During the Inception Period which overlapped with the most of the reporting period, the Project Management Unit (PMU) with strong relationship with the Drin Core Group (DCG) as the Regional Project Board (RPB), was established. The project developed the Inception Report containing the revised Multi-annual Work Plan, Budget, updated Gender Action Plan and Terms of Reference of the Grievance Redress Mechanism (GRD), which were endorsed by the DCG at the last of its three sessions held during the reporting period. The key international experts to lead the implementation of the Component 1 were recruited, based on the ToRs developed in close coordination with the relevant implementing partners and the DCG. ToR and boundaries for the LiDAR surveillance for production of the high-res DEM of the Crn Drim sub-basin in North Macedonia were developed in coordination with the National Real Estate Cadaster. Close cooperation was maintained with GIZ, among others, at the level of the technical working groups for hydrometry and flood hazard and risk mapping. The schedule of activities and the budget for the Component 2 were under development by the GWP as the designated Responsible Party, narrowly coordinated by with the PMU. Signing of the Letter of Agreement is foreseen for Q1 2021. The implementation of the Component 3 has advanced the most withe the detailed design of the two preidentified structural flood protection measures in Montenegro, encompassing social and environmental safeguards, well underway, and one preidentified structural measure in North Macedonia successfully executed. Despite COVID-19 pandemic overlapping almost completely with the reporting period and significantly impeding the timeliness of the most of the activities, a certain progress was made by the Project by addressing this issue to the extent possible, rated overall as Marginally Satisfactory (MS).
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective To assist the riparian countries in the implementation of an integrated climate-resilient river basin flood risk management approach in order to improve their existing capacity to manage flood risk at regional, national and local levels and to enhance resilience of vulnerable communities in the DRB to climate-induced floods | Total Number of direct and indirect beneficiaries (disaggregated by sex) with reduced vulnerability to flood risks; Number of beneficiaries relative to total population | 0 | No change compared to baseline, project activities have been initiated but results are expected in the future reporting periods | Direct beneficiaries: 190,000 people (50.6% women ) / 12% of the DRB population Indirect beneficiaries: 1.6 million people living in DRB (50.6% women)
| Availability of high-quality flood hazard and risk information generated and disseminated to stakeholders on a timely basis | Gaps in observation and flood risk information hamper effective flood forecasting and EWS, development of basin-level integrated CCA and FRM strategy and plan and climate resilient sectoral planning | No flood hazard and risk maps have been delivered in the reporting period, however, the coordination has started with implementing partners on inclusing of the already developed maps into the basin-level model, which is to be developed by the project, | Enhanced food hazard and risk information for DRB is available and used for: (a) enhanced FFEWS (in cooperation with GIZ) (b) Climate-informed Drin River Basin Integrated CCA and FRM Strategy and Plan and implementation capacities are in place (c) Sectoral planning
| Number and level (where relevant) of effective coordination mechanisms for climate-resilient FRM in DRB (Level 1 = no coordination mechanism; Level 2= coordination mechanism in place; Level 3 = coordination mechanism in place, meeting regularly with appropriate representation (gender and decision-making authorities); Level 4 = coordination mechanism in place, meeting regularly, with appropriate representation, with appropriate information flows and monitoring of action items/issues raised) | 1 coordination mechanism: Drin Core Group/MOU: Level 3 The Drin Coordinated Action was established to promote joint action for the coordinated integrated management of the shared water resources in the basin. The MoU does not currently specifically address joint actions required for cooperation on flood risk management. The existing coordination and bilateral agreements are insufficient for a truly transboundary river basin approach to flood risk management. | State and the efficiency of work among the coordination mechanisms for the climate resilient FRM, is as follows: (a) DCG (Level 3) (b) EWGF (Level 2), c) DRB Framework Agreement on FRM (Level 1) (d) DRB SAP is informe of climate-induced flood risks and integraed resilient FRM measures (Level 2) | 4 coordination mechanisms: (a) DCG/MOU: Level 4 (b) Drin Floods Expert Working Group: Level 4 (c) DRB Framework Agreement on FRM (d) DRB SAP is informed of climate-induced flood risks and integrated resilient FRM measures
Outcome 1 Improved climate and risk informed decision-making, availability and use of climate risk information | Indicator 1.1: a) Coverage and effectiveness of the hydrometric monitoring networks in riparian countries. b) Number of new observation stations installed | Significant gaps in the coverage (especially in Republic of North Macedonia and Montenegro) and inefficiencies in data management, operations and maintenances of the hydrometric monitoring network across DRB prevents adequate forecasting and early warning and efficient decision making on FRM. An integrated basin wide hydrological and hydraulic model for the DRB is absent. Under the new GIZ project, detailed flood modelling and mapping is planned for the Lake Shkoder/Skadar and Bojana-Buna area. Lack of socio-economic data for risk, damages, losses, exposure and vulnerability assessments. | b) 25 of the new hydrometeorological stations, defined in coordination with National Hydromet Service in North Maceonia (UHMR) under procurement: 3 new fully automated meteorological stations, 5 rain gauge stations, 6 fully automated hydrological stations and 11 piezometering stations. | Indicator target 1.1. a) Enhanced coverage and efficiency of the hydrometric monitoring network in DRB and improved O&M provides for improved FFEWS and FRM decisions across DRB. b) Target number of new stations to be defined during Year1 of the project based on the network design.
| Indicator 1.2: Level of introduction of modelling tools and technologies for the strategic flood risk assessment and flood hazard mapping |  | b) ToR for detailed areal surveillance using LiDAR technology of 4,125 sq. kilometers in the Crn Drim River Basin in North Macedonia defined in coordination with the National Geodetic Authority. Procurement of the surveillance is ongoing. | Indicator target 1.2. Enhanced modelling tools and technologies for the strategic flood risk assessment in DRB based on EUFD, including: a) Spatial Data Initiative and data management system; b) Detailed topographic surveys and data for the Crn Drim in Macedonia. c) Detailed hydrological and hydraulic modelling for the Crn Drim in Macedonia and high resolution flood hazard inundation maps d) Numerical high-level basin-wide hydrological and hydraulic models of the DRB integrating detailed area-based modeling developed under AF, GIZ and national projects.
| Indicator 1.3. Level of implementation of the systematic gender-responsive socio-economic vulnerability assessment in the DRB |  | No gender-responsive socio-economic vulnerability assessments in DRB have been completed.Results to be delivered during the next reporting periods. | Indicator target 1.3. (a) Socio-economic data collection tool developed and embedded at local and central institutions to systematically collect damages and losses data. Bespoke GIS-based socio-economic modelling tool developed and introduced. (b) Baseline, progress and final report on social and gender vulnerability. At least 30% participants of consultations are women. (c) Systematic recording of flood damage and losses in DisInventar database
Outcome 2 Improved institutional arrangements, legislative and policy framework for climate-resilient FRM, and development of CCA and FRM strategy and plans at the basin, sub-basin, national and sub-national levels | Indicator 2.1: State of the Drin River Basin FRM Policy Framework and cooperation on flood risk management | Limited basin-level coordination and cooperation on flood risk management. Under an MoU between the national hydromet institutions there is cooperation and data exchange for flood warning, based on regional forecasts, EFAS and SEE FFG. The Drin Coordinated Action was established to promote joint action for the coordinated integrated management of the shared water resources in the basin. The MoU does not currently specifically address joint actions required for cooperation on flood risk management. Institutional capacities at the regional, national and sub-national level across the basin are insufficient to secure climate-resilient FRM. The existing coordination and bilateral agreements are insufficient for a truly transboundary river basin approach to flood risk management. What is missing is a basin-level integrated climate change adaptation and flood risk management strategy and plan and a multi-lateral Framework Agreement for the DRB in the field of flood risk management which establishes the institutional and legal basis for cooperation. | The work on the development of the FRM policies did not start during the reporting period. | Indicator target 2.1 a) FRM policies designed in line with relevant EU directives. b) Basin risk transfer mechanisms designed, including risk financing and risk transfer strategy, private sector engagement strategy, feasibility studies for identified and shortlisted risk financing mechanisms. c) Sector FRM policies (at least 2 – energy, agriculture) based on modelling of climate change impacts on the identified sectors and on the detailed methodologies for incorporating climate-change responsive flood risk considerations into risk assessments, strategies, policies and plans for the energy and agriculture sectors
| Indicator 2.2 a) % increase in institutional capacity to promote integrated climate resilient flood risk management b) Number of staff from targeted institutions trained to respond to impacts of climate-related events |  | The work on the institutional capacity did not start during the reporting period. | Indicator target 2.2 a) 50% increase in institutional capacity (measured through an institutional capacity assessment scorecard) b) At least 50 officials and other key national/regional stakeholders trained on improving the enabling environment (minimum 30% women)
| Indicator 2.3 State of Drin River Basin Integrated CCA and FRM Strategy |  | The work on the development of the DRB CCA and FRM Strategy did not start during the reporting period. | Indicator target 2.3 Drin River Basin Integrated CCA and FRM Strategy and Plan developed and endorsed by regional and national stakeholders; Implementation started
Outcome 3 Strengthened community resilience through improved flood management, implementation of structural and non-structural measures and enhanced local capacity for CCA and FRM | Indicator 3.1: State of climate-responsive design of structural and non-structural measures for long-term FRM investment in DRB | Communities of the DRB remain highly exposed to flooding. In the Riparian countries of the DRB, flood defense and flood risk management are done in a reactive manner and as budgets allow. Relevant institutions have limited annual budgets to address urgent issues like structural defense needs, and currently do not take a climate risk-informed strategic approach (e.g. river basin approach) to flood risk management interventions. Capacities to design climate-responsive and resilient flood protection structures are limited. Many defenses have exceeded their design life and have not been upgraded or maintained and are therefore now largely ineffective. There is limited use of modern eco-system-based flood risk management approaches and approaches which combine both structural and non-structural measures as part of FRM, due to a lack of knowledge and application of non-structural measures and ecosystem-based approaches (EbA) to flood risk management. There is also limited knowledge and capacities among local communities on climate resilient livelihoods for coping with climate-induced hazards | Two identified structural options for DRB in Montenegro are under design One structural measure for DRB in North Macedonia designed | Indicator target 3.1 For each of 3 riparian countries a set of structural and non-structural flood protection options identified and designed using climate risk information and cost-benefit appraisal methods.
| Indicator 3.2: (a) Number of people directly protected from flood risks through structural measures at 3 high risk sites in Albania, Republic of North Macedonia and Montenegro (b) Area of land protected from flood risks through structural measures at Drin FRM project 3 sites |  | (a) 1000 people directly protected by the intervention completed at improving hydraulic capacity of the Crni Drim River in the urban part of the Municipality of Struga in North Macedonia | Indicator target 3.2. (a) 10,000 people directly protected (b) 7000 ha protected, including agricultural and municipal land
| Indicator 3.3: (a) number of communities across DRB supported with non-structural measures and adaptation planning (including training, participatory planning and implementation) (b) scale of agroforestry measures implemented (ha) |  | (a) 0; (b) 0 | Indicator target 3.3. (a) At least 50 communities across DRB are supported with training, participatory CRM and FRM planning and/or implementation of non-structural measures (b) At least 150 ha

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Effective collaboration has been established during the first year of project implementation with key partners, such as relevant ministries, national hydrometeorological services, water management agencies in the three riparian countries, other development actors - GIZ, international NGOs - Global Water Partership, other UN agencies (UNECE), and other projects (GEF Drin Project, GIZ FFEWS Project). Maintaining cooperation, in order to discuss synergies and reduce duplication of activities, became increasingly difficult immediatelly after the COVID-19 outbreak; however the project team with relevant corporate support adapted timely to the use of contemporary communication platforms, as well as online management tools, under the circumstances when almost all multi-lateral and over 70% of bi-lateral meetings had to be done virtually. Keeping up to date with major online communication platforms allowed the project to maintain uninterruped communication with key stakeholders.
COVID-19 pandemic outbreak that nearly coincided with the project start, lasted throughout the first year of its implementation and will continue beyond, thus significantly reducing the pace of project implementation thus causing delays across most activities. Project respoded by changing implementation modalities and switching to telecommuning and teleworking of team members, using of eprocurement tools, etc. Effective use of IT tools has helped maintaining momentum over the most of the activities, while those that were related to physical activity in the field have, in most cases, been postponed for the post covid period. Proficiency in contemporary IT skills, allowed project personnel to keep fulfilling relevant tasks while working remotely.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | COVID-19 pandemic significantly reduced the pace of project implementation thus causing delays in most of the activities. Project respoded by changing implementation modalities and switching to telecommuning and teleworking and using online platforms for meetings and management tools. Delays caused by the novel coronavirus pandemic were addressed by the project team proposing changes in the Multi-annual Work Plan and Budget, in which majority of activities were postponed to 2021 (mostly) and beyond, along the same activity and budget lines. The proposed changes were endorsed by the Project Board and, apart to the affected timeliness, they did not foresee negative impact on project outputs and outcomes.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes have been made to project outputs, outcomes or activities. Project Results Framework remains the same.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Two firms that have been commissioned to provide detailed design of two sub-project structural measures on Bojana/Buna and Gracanica rivers in Montenegro, are tasked with addressing all environmental and social issues (E&S screening, ESMP development and safeguards design) that will be incorporated in the designs for obtaining relevant licences. The designs, together with the safeguards will be reviewed by thirdy party companies before relevant permits are applied for and issued. The entire design development process is overseen by an independent inernational engineer as well as the Project Implementation Unit.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations have been embedded in all project activities. Gender equality as a cross-cutting issue has been made a part of all Terms of Reference, whether concerning the recruitment of the key expers or procurement of gender-responsive design of structural flood protection measures. Thus, all project activities have been gender-sensitive, which will result in the strengtened role of women in decision-making processes concering the climate change adaptation.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 6215
Implementing Entity | UNDP
Type of implementing entity | MIE |  |  | 48.8 | 96153.8462
Country | Albania |  |  |  | 190000 | 190000
Country | Montenegro
Country | Macedonia, former Yugoslav Republic of
Region | Eastern Europe |  |  |  | 0.50607 | 93846.1538
Sector | Disaster risk reduction |  |  |  | 0.49393 | 93846.1538
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 1790000 | 190000 | 1600000 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 50.6% | 50.6% | 50.6% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 24% | 24% | 24% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Inland flooding | 2: Partially effective | Total | 190000 | Inland flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 50.6% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  |  | Disaster risk reduction | National | 1: No plans conducted or updated |  | Disaster risk reduction | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  | 2: Monitoring and warning service | Geographical coverage | National | 3 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 6 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  | 3: Dissemination and communication | Geographical coverage | National | 3 | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 14 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  | Disaster risk reduction | 2: Low capacity | Total | 50 | Disaster risk reduction | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 30% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
[6 empty] | 50 | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Disaster risk reduction | 2: Low capacity | Public | National | Disaster risk reduction | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  |  | National | DRR and Early Warning Systems | 2: Low capacity | 6 | National | DRR and Early Warning Systems | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes N/A | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Regional | 2: Partially responsive (Lacks most elements) |  | Water management | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  |  | Multi-community |  | Water management | 6 | Multi-community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability N/A | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas N/A | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  |  | Disaster risk reduction | National | Environmental policy | 3 | Disaster risk reduction | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  |  | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 3 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  |  |  | Innovation rolled out |  | Disaster risk reduction | Regional | Innovation rolled out
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  |  | Disaster risk reduction | No innovative practices | 2: Partially effective | 3 | Disaster risk reduction | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  |  | Innovative product |  | 1: Ineffective | 6 | Innovative product |  | 4: Effective