## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 31 December 2021 - 31 December 2022
| Project Title: | Building Resilience of the Agriculture Sector to Climate Change in Iraq (BRAC)
| Project Summary: | The project objective is to strengthen the agro-ecological and social resilience to climate change in the four target governorates (Muthanna, Qadisiya, Missan and Thi Qar), by enhancing water availability and use efficiency, and promoting adaptive agriculture production systems and technologies for improved livelihoods and food security of rural households. The project is designed to deal with one of the major constraints in the country that centres around the growing scarcity of irrigation water and to assist the country with strengthening its capacity at the national level for monitoring climate change patterns and providing relevant information to key stakeholders and farmers to enable them to undertake adaptation and risk mitigation measures through an early warning system. The project consists of two components: Component 1: Capacity development to integrate CC adaptation and risk reduction into agriculture planning and production systems Component 2: Climate-resilient agriculture investments
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator:
| Database Number: | IRQ/MIE/Agri/2017/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U
Implementing Entity (IE) [name]: |  | International Fund for Agricultural Development (IFAD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S
| Type of IE: | Multilaterial Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU
| Country(ies): | Iraq | Angola |  |  | International Waters | 5 | 5 | Good
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Four target governorates in Iraq (Muthanna, Qadisiya, Missan and Thi Qar) | Argentina |  |  | Multiple Focal Area
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas
AFB Approval Date: |  | 2018-03-22
IE-AFB Agreement Signature Date: |  | 2018-09-20 | [6 empty] | CC-SP6-LULUCF
Start of Project/Programme: |  | 2019-12-10 | [6 empty] | Cross cutting capacity building
Actual Mid-term Review Date (if applicable): |  | 2023-05-20
| Original Completion Date: | 2025-12-31
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Decision B.31/14
| Condition or Requirement | IFAD will apply its environmental and social management system and that of the executing entity to the full, covering all the activities funded by the Fund, while at the same time developing an overall environmental and social management plan through which IFAD will identify for each activity the requirements for compliance with the Fund’s environmental and social policy (ESP) and document any insurmountable obstacles and constraints
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | IFAD submitted its SECAP Note (Social, Environmental and Climate Assessment Procedure) to the AF Secretariat on 2 September 2021. SECAP conditions are being reviewed as part of IFAD's regular Supervision Missions (the latest mission dated December 2021).
| Category of condition | Decision B.31/14
| Condition or Requirement | Above and beyond the regularly required audits, IFAD will organize an annual external and independent audit of the project’s performance in terms of compliance with the Fund’s environmental and social safeguards by a private auditor familiar with the ESP. In addition to past performance, the audit will include the annual work plan for the coming year and any environmental and social safeguard measures the implementing entity has included. Adoption of the audit recommendations will be a condition for the disbursement of funding following the submission and clearance of the project performance report.
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | The project's approved ESMP (in the original proposal) specifies this condition will be met as of Year 3 (PPR #2). IFAD however proposes to anticipate this requirement and submit an audit around mid-2023, based on the Updated ESMP and Annual Work Plan and Budget for 2023.
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report submitted https://pubdocs.worldbank.org/en/534091581002646997/6535-BRAC-SARP-Inception-Workshop-Report.pdf | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Ms. Sahar Hussein | Dominican Republic
| Email: | saharhusseinjasim@gmail.com | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Adeelah Hammood Ilussen | Equatoral Guinea
| Email: | moen.Iraq@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Tawfiq El-Zabri | Fiji
| Email: | t.elzabri@ifad.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Ministry of Health and Environment | Georgia
| Email: | moen.Iraq@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Agriculture | Grenada
| Email: | utaha123@gmail.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [01 Jan 2020] |  |  |  | Financial information PPR 2: cumulative from project start to [December 2021] |  |  |  | Financial information PPR 3: cumulative from project start to [December 2022] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 Dec 2020] | 0 |  |  | Estimated cumulative total disbursement as of [enter Date] | 0 |  |  | Estimated cumulative total disbursement as of [enter Date] | 23162 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The main reason for the delay was disagreement between ministries on execution modalities, which delayed the areement between the MIE and the EE. It has been agreed that a sub-committee from the Steering Committee will be established and led by the MoEH to guide and oversee the execution of activities in synchronization with SARP. |  |  | Add any comments on AF Grant Funds. (word limit=200) | There has been a major delay as communicated in PPR1 due to the lack of agreement between the MoA and MoEH. Now that the agreement is in place, the project is expected to disburse in 2022. |  |  | Add any comments on AF Grant Funds. (word limit=200) | There has been a major delay as communicated in PPR1 and PPR2 due to the lack of agreement between the MoA and MoEH. Now IFAD is assessing alternative arrangements to ensure the project disburses in 2023. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 1,844 (32,499.2 cumulative) |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
|  | 0 | [6 empty] | Execution cost | 4000
[9 empty] | IE Fees | 19162.99
| TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 23162.99 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1.1 Developing a Climate Change Adaptation Strategy for the Agricultural Sector | 30000 | 2021-12-31 |  | 1.1.1 Developing a Climate Change Adaptation Strategy for the Agricultural Sector (technical assistance and field surveys) | 70000 | 2022-12-31 |  | 1.1.1 Developing a Climate Change Adaptation Strategy for the Agricultural Sector (technical assistance and field surveys) | 83000 | 2023-12-31
| 1.1.2 Develop the skills of government officials concerned with climate change adaptation and risk reduction | 30000 | 2021-12-31 |  | 1.1.2 Develop the skills of government officials concerned with climate change adaptation and risk reduction (training linked to the strategy) | 35000 | 2022-12-31 |  | 1.1.2 Develop the skills of government officials concerned with climate change adaptation and risk reduction (training linked to the strategy) | 31000 | 2023-12-31
| 1.1.3 The Training of Trainers Program (TOT), which targets public administration employees at the national and governorate levels, is implemented and deals with mainstreaming climate change adaptation into issues of environment, agriculture and water. | 30000 | 2021-12-31 |  | 1.1.3 The Training of Trainers Program (TOT), which targets public administration employees at the national and governorate levels, is implemented and deals with mainstreaming climate change adaptation into issues of environment, agriculture and water. | 27540 | 2022-12-31 |  | 1.1.3 The Training of Trainers Program (TOT), which targets public administration employees at the national and governorate levels, is implemented and deals with mainstreaming climate change adaptation into issues of environment, agriculture and water. | 27540 | 2023-12-31
| 1.2.1 Training of project beneficiaries on climate-appropriate methods and technologies | 60000 | 2021-12-31 |  | 2.1.1.Efficient water supply from tertiary canals up to farmland plots is secured, based on climate-proof systems and technologies (identification and feasibility studies) | 120000 | 2022-12-31 |  | 2.1.1.Efficient water supply from tertiary canals up to farmland plots is secured, based on climate-proof systems and technologies (identification and feasibility studies) | 240000 | 2023-12-31
| 1.2.2 Enable water users and organizations to effectively manage irrigation water in the targeted areas | 10000 | 2021-12-31 |  | 2.2.1 Development of the Agricultural Meteorological Network and the Weather Information Management System (Baseline) | 30000 | 2022-12-31 |  | 2.2.1 Development of the Agricultural Meteorological Network and the Weather Information Management System (Baseline) | 30000 | 2023-12-31
| 1.2.3 Exchange of lessons learned and best approaches on climate change adaptation | 15500 | 2021-12-31 |  | Execution cost | 110000 | 2022-12-31 |  | Execution cost | 29503 | 2023-12-31
| 2.1.1.Efficient water supply from tertiary canals up to farmland plots is secured, based on climate-proof systems and technologies (feasibility studies) | 240000 | 2021-12-31 |  | IE Fees | 60000 | 2022-12-31 |  | IE Fees | 40000 | 2023-12-31
| 2.2.1 Development of the Agricultural Meteorological Network and the Weather Information Management System | 50000 | 2021-12-31
| 2.2.2 Develop early warning systems for climate risks | 20000 | 2021-12-31
| TOTAL | 485500 |  |  | TOTAL | 452540 |  |  | TOTAL | 481043 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Project start up and disbursement | High risk. Disagreements between minstries on the modality of execution for certain activities have been the main cause of delay so far. | 1- MoUs to include details of execution modalities for each activity by MoEH, MoA and MoWR. 2- IFAD and the government of Iraq are discussing the possibility of involving UNOPS as a service provider to expedite procurement processes. 3- Second Annual Work Plan and Budget (AWPB) has been developed. Recruitment of additional staff to SARP PMU is ongoing to address staff shortages. 4- a sub-committee from the Steering committee will be led by the MoEH to guide and oversee the execution of activities in synhcronization with SARP.
Threat to security in performing field work | Medium risk. Security risks for visiting the project target areas | IFAD held a workshop in Erbil in June and then visited 2 of the 4 target governorates in December 2022 with support from UNDSS. The project will focus in the governorates in the south of the country where there is no on-going conflict.
The Government capacity is extremely limited and Government budgets for operational purposes are inadequate | Medium risk.The MoHE requested capacity building training to implement the project, including identification of USPs and risks / impacts and mitigation measures identification | IFAD organised capacity strenghtening training(s) for MoA and MoHE (and key partners) to implement the project, including identification of USPs and risks / impacts and mitigation measures identification in 2021 and 2022. Moreover, the project will be implemented through service providers (e.g. UNOPS).
As a result of the security threat in the country, the movement of any staff member within the purview of the UN system is extremely restricted. | Medium risk.The taget governorates in the south of the country are relatively safe - where there is no on-going conflict. | Local contractors and service providers, close contact with local authorities will be used. Besides, the support of established partners (UNOPS, FAO,WFP, etc.) and private sector or civil society will be used as service providers
Increased weather variability related to climate change | High risk. No specific variability identified | The project will have a major focus on capacity development on institutional and technical skills, decision-making tools for adaptation planning and implementation based on climate change modelling and early warning systems, shifting to climate risk-tolerant crops/varieties and breeds, adoption of climate-resilient agronomic systems and technologies.
Low adoption rate of technology by farmers | Low risk. Did not start yet. | Build on the successful approach of establishing FFS demonstration plots, improve incentives and conduct training for farmers, and services providers (ToT) on the various components of technology packages.
Iraq procurement rules and practices are not harmonized across institutions and changing rapidly. | Medium risk. No change | IFAD procurement rules will be applied strictly in the country
Availability of appropriately experienced and qualified non-government service providers. | Low risk. Service providers with appropriate experience and qualified non-government service providers are available | Use of private sector firms which have been used by previously by other UN agencies and other donors to undertake the implementation in the field in partnership with government and NGOs.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Potential impact of construction works | Medium risk | The ESMP will anticipate the completion of environmental and social risks identifification / impacts before work is done on each structure under the terms of legislation and in accordance with the AF Guidelines.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Due to security risks, IFAD held a workship in Erbil for the project management unit were the AWPB was agreed. In addition, IFAD organised with UNDSS a mission to 2 of the 4 target governorates to meet with local staff at the governorates and potential beneficiaries. This helped finalise a list of potential irrigation schemes to be validated through the environmental and social risk screening.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups |  |  | The rehabilitated tertiary canals may not benefit all concerned marginalized and vulnerable groups in the target areas. | Planning and designing of rehabilitation works is done through consultation and agreements with vulnerable groups that may benefit from irrigation water. The inception phase of the project will include the development of a detailed baseline study that will further refine these groups, identify specific activities to target them, including capacity development. Project Component 1 supports the creation and/or institutional development of WUAs with equal access to vulnerable groups and awareness and education on the need to conserve water and promote efficient use. Project Component 1 ensures adequate training and institutional development of beneficiaries and users’ groups to make an effective and efficient use of irrigation water. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | The rehabilitated tertiary canals may not well capture and address the needs of women groups in the target areas. | Planning and designing of rehabilitation works is done through consultation and agreements with vulnerable groups that may benefit from irrigation water. The inception phase of the project will include the development of a detailed baseline study that will further refine these groups, identify specific activities to target them, including capacity development. Project Component 1 supports the creation and/or institutional development of WUAs with equal access to vulnerable groups and awareness and education on the need to conserve water and promote efficient use. Project Component 1 ensures adequate training and institutional development of beneficiaries and users’ groups to make an effective and efficient use of irrigation water. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
6 – Core labour rights |  |  | (i) potential workers accidents; (ii) adverse impacts to the health and daily life of workers and residents due to the increase of noise, deterioration of air quality, aesthetic problems and traffic congestion. | Make sure all machinery and vehicles are operated efficiently and according to the manufacturers specifications, by trained and qualified operators. Make sure all personnel are issued with protection equipment and are advise of its proper use. Installation of adequate signs and delineation equipment in construction sites. Timing of construction activities to avoid traffic load and interference with nearby social activities. Ensure all machinery is in good order and repair and not leaking fuel or volatile emissions. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | (i) dust emissions generated from loading and unloading of materials; (ii) erosion of exposed soils; (iii) generation of debris and pollutants from the breaking of existing degraded structures and backwash water that might affect land and workers health; (iv) use of potentially harmful materials (e.g. materials containing PCB); (v) potential contamination of soil and water due to spills, leakage from fuel storage, wrong dosage of chemicals; (vi) unsustainable use of water with potential effects on marshland and river ecosystems, and fishing activities. | Water extraction monitoring. Provision of uncontaminated water for dust suppression and wash down of vehicles and machinery. Spill control measures to prevent spills from infiltrating into groundwater table. Waste management measures should be implemented to prevent litter and debris and liquid wastes from entering soil excavations and neighbouring farmland areas. Re-use any excess excavation material generated by the construction within the site or on nearby sites. Height and slope of stockpiles should be limited to minimize erosion of unconsolidated materials. Locating stockpiles on flat areas, away from runoff water to ensure sediment or erosion cannot reach waterways. Solid waste that cannot be re- used shall be disposed of in approved landfills. Limit use of harmful materials. If unavoidable impose monitoring and maintenance. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
13 – Public health |  |  | (i) generation of dust, debris and pollutants from the breaking of existing degraded structures and backwash water that might affect land and workers health; (ii) use of potentially harmful materials (e.g. materials containing PCB); (iii) potential public safety concerns associated with the excavation works; (iv) adverse impacts to the health and daily life of workers and residents due to the increase of noise, deterioration of air quality, aesthetic problems and traffic congestion; (v) potential contamination of soil and water due to spills, leakage from fuel storage, wrong dosage of chemicals. | Make sure that activities likely to cause adverse noise impacts are timed to have least impact on surrounding land users and other site activities (e.g. schools, hospitals). Implement air and water quality mitigation measures. Project Component 1 supports the creation and/or institutional development of WUAs with equal access to vulnerable groups and awareness and education on the need to conserve water and promote efficient use for agriculture production, drinking water and other uses. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
14 – Physical and cultural heritage |  |  | (i) unsustainable use of water with potential effects on marshland and river ecosystems, and fishing activities; (ii) the rehabilitated tertiary canals may not benefit the marshland vulnerable people in the target areas. | Minimize marshland habitat degradation due to construction activities. Plant trees and shrubs in vulnerable sites to prevent erosion and pollution. Planning and designing of rehabilitation works is done through consultation and agreements with vulnerable groups that may benefit from irrigation water. Project Component 1 supports the creation and/or institutional development of WUAs with equal access to vulnerable groups. Project Component 1 ensures adequate training and institutional development of beneficiaries and users’ groups to make an effective and efficient use of irrigation water. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
15 – Lands and soil conservation |  |  | (i) erosion of exposed soils; (ii) generation of debris and pollutants from the breaking of existing degraded structures and backwash water that might affect land; (iii) potential contamination of soil and water due to spills, leakage from fuel storage, wrong dosage of chemicals. | Plant trees and shrubs around canals, roads, and drainage areas to prevent erosion and pollution. Waste management measures should be implemented to prevent litter and debris and liquid wastes from entering soil excavations and neighbouring farmland areas. Re-use any excess excavation material generated by the construction within the site or on nearby sites. Height and slope of stockpiles should be limited to minimize erosion of unconsolidated materials. Locating stockpiles on flat areas, away from runoff water to ensure sediment or erosion cannot reach waterways. | To be developed | To be developed | Not started yet | Not started yet | Not started yet
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | N/A. Activities not started yet
Have unanticipated ESP risks been identified during the reporting period? |  | N/A. Activities not started yet
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A. Once activities start, USPs will be identified, as well as related risks / impacts and mitigation measures. The ESMP will be updated with this information during the next reporting period
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | During the incpetion workshop, governmet partners were trained to identify USPs and related risks / impacts and mitigation measures
Have the implementation arrangements been effective during the reporting period? |  | N/A. Activities not started yet. There need to be a follow-up to above training
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A. Activities not started yet.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | N/A. Activities not started yet.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Follow-up capacity strenghtening trainings are required for the MoHE and key actors to identify the USPs and related risks / impacts and mitigation measures. Guidelines to do so have been developed and shared during the inception workshop.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No. Activities not started yet.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | N/A. No USPs identified yet.
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A. Activities not started yet.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes. Gender baseline and approach was established. However, as the project includes USPs, some risks related to gender need to be further assessed.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Gender-responsive indicators at outcome level have been included in the results framework
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Resilience of women improved | Objective | Number of people (disaggregated by gender) whose resilience has been improved (with changed behaviour) as a result of project outputs | none | 16,000 HH (at least 40% women) | N/A. Activities not started yet.
Women using agro- meteorological information to reduce climate risks to their production systems. | Outcome (2.2) | Number of beneficiaries (disaggregated by gender) using agro- meteorological information to reduce climate risks to their production systems. | none | 16,000 HH | N/A. Activities not started yet.
Women with sustained adoption of climate resilient technologies promoted by the project. | Outcome (2.3) | Number of grantees by gender) with sustained adoption of climate resilient technologies promoted by the project. | none | 9,350 HH | N/A. Activities not started yet.
Women wreporting increase in production | Outcome (2.3) | Number of persons (disaggregated by gender) reporting increase in production | none | 6,650 HH | N/A. Activities not started yet.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
N/A. Activities not started yet.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | N/A. Activities not started yet.
Have the implementation arrangements at the IE been effective during the reporting period? |  | N/A. Activities not started yet.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | N/A. Activities not started yet.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | N/A. Activities not started yet.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A. Activities not started yet.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | N/A. Activities not started yet.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1.1.Increased capacity of governmental staff on mainstreaming CC adaptation into the agricultural sector |  | Outcome 2 | No progress expected |  | No progress during the reporting period | N/A
|  |  | Outcome 7 |  |  |  | N/A
| 1.2. Technical and institutional capacity of agriculture practitioners and producers’ organizations in the 4 targeted governorates developed to integrate knowledge on climate-resilient systems and technologies into practice |  | Outcome 3 | No progress expected |  | No progress during the reporting period | N/A
| 2.1. Climate- proof systems and technologies for water supply from tertiary canals up to farmland plots are implemented in the target governorates |  | Outcome 4 | No progress expected |  | No progress during the reporting period | N/A
| 2.2. The national Agro- meteorological Monitoring Network is upgraded informing early warning systems |  | Outcome 1 | No progress expected |  | No progress during the reporting period | N/A
|  |  | Outcome 3 | No progress expected |  | No progress during the reporting period | N/A
| 2.3. Climate resilient agriculture technologies adopted by target farmers and producers’ organizations |  | Outcome 6 | No progress expected |  | No progress during the reporting period | N/A
[6 empty] | Overall Rating | U
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Tarek Abdel Monem
| Email: | t.abdelmonem@ifad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The implementing entity has held a workshop in Erbil in 2022 and fielded a mission in 2 out of the 4 target governorates to foster the project's institutional arrangements and meet governorate teams and potential beneficiaries. The second AWPB has been developed and service providers are being explored (e.g. UNOPS). Disbursement expected in 2023. The overall rating of the project is Unsatisfactory.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1.1.Increased capacity of governmental staff on mainstreaming CC adaptation into the agricultural sector |  | Outcome 2 | Skills for relevant governmental staff on climate change adaptation and risk reduction developed; A Training-of-trainers (ToT) programme is implemented targeting public administration staff, at national and governorate levels, dealing with mainstreaming CC adaptation into environmental, agriculture and water issues. |  | No progress | MU
|  |  | Outcome 7 |  |  |  | MU
| 1.2. Technical and institutional capacity of agriculture practitioners and producers’ organizations in the 4 targeted governorates developed to integrate knowledge on climate-resilient systems and technologies into practice |  | Outcome 3 | Project beneficiaries are trained on climate-resilient approaches and technologies. |  | No progress | MU
| 2.1. Climate- proof systems and technologies for water supply from tertiary canals up to farmland plots are implemented in the target governorates |  | Outcome 4 | Signing an MoU with the Ministry of Water Resources, identifying target canals and developing the feasibility studies |  | No progress | MU
| 2.2. The national Agro- meteorological Monitoring Network is upgraded informing early warning systems |  | Outcome 1 | Assessing the current early warning system and the status of current agro-metorological stations |  | No progress | MU
|  |  | Outcome 3 |  |  | No progress | MU
| 2.3. Climate resilient agriculture technologies adopted by target farmers and producers’ organizations |  | Outcome 6 | No progress expected |  | No progress | N/A
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms. Sahar Hussein
| Email: | saharhusseinjasim@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
ToRs have been developed for the development of the ESMP and the climate strategy for the agriculture sector and execution is expected in Q2 2023. A meeting was held between MoE and the agrometerological department at MoA to discuss outcome 2.2 on the agro-meteorological stations and the ToRs for the stations are being prepared. Meetings with MoA and MoWR have been held to select the irrigation schemes and the environmental and social risk assessment needs for all the irrigation works.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | 1.1.Increased capacity of governmental staff on mainstreaming CC adaptation into the agricultural sector |  | Outcome 2 | Skills for relevant governmental staff on climate change adaptation and risk reduction developed; A Training-of-trainers (ToT) programme is implemented targeting public administration staff, at national and governorate levels, dealing with mainstreaming CC adaptation into environmental, agriculture and water issues. |  | No progress during the reporting period | MU
|  |  | Outcome 7 |  |  | No progress during the reporting period | MU
| 1.2. Technical and institutional capacity of agriculture practitioners and producers’ organizations in the 4 targeted governorates developed to integrate knowledge on climate-resilient systems and technologies into practice |  | Outcome 3 | Project beneficiaries are trained on climate-resilient approaches and technologies. |  | No progress during the reporting period | MU
| 2.1. Climate- proof systems and technologies for water supply from tertiary canals up to farmland plots are implemented in the target governorates |  | Outcome 4 | Signing an MoU with the Ministry of Water Resources, identifying target canals and developing the feasibility studies |  | No progress during the reporting period | MU
| 2.2. The national Agro- meteorological Monitoring Network is upgraded informing early warning systems |  | Outcome 1 | Assessing the current early warning system and the status of current agro-metorological stations |  | No progress during the reporting period | MU
|  |  | Outcome 3 |  |  | No progress during the reporting period | MU
| 2.3. Climate resilient agriculture technologies adopted by target farmers and producers’ organizations |  | Outcome 6 | No progress expected |  | No progress during the reporting period | N/A
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Udai Taha
| Email: | utaha123@gmail.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | 1. Current trend: unsatisfactory 2. Delays in agreement on execution modalities between MoHE and MoA which led to delay in staffing and starting the implementation. 3. N/A 4. Capacity of MoHE and MoA for project management and implementation, including identification of USPs and related risks / impacts and minitiagtion measures has been strenghtened through trainings in 2021 and 2022. Service providers being explored (e.g. UNOPS).
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective | Number of people (disaggregated by gender) whose 29 resilience has been improved (with changed behaviour) as a result of project outputs Increase in income from agriculture. | None The baseline income of 44% of households in the project districts is below the poverty line of 76,896 Iraqi dinars (about $66) a month, or $2.2 a day. | No progress | 16,000 HH (at least 40% women). Increase in income by at least 20% for targeted households.
Outcome 1.1. | IN1.1.1: CC Adaptation Strategy for the Agriculture Sector. | No strategy | No progress | The Strategy is finalized and validated. One Forest Landscape Plan produced and validated.
| IN1.1.2: Number of governmental staff trained on climate change adaptation and risk reduction. | None | No progress | 300 staff
Outcome 1.2. | IN1.2.1: Number of people reporting adoption of climate-resilient systems and technologies. | None | No progress | 16,000 HH
| IN1.2.2: Number of WUAs applying sustainable management of water resources in the target areas. | None | No progress | 20
Outcome 2.1. | IN2.1.1: Number of households reporting improved access to water for production purposes. | None | No progress | 6,650 HH
| IN2.1.2: Number of hectares of farmland irrigated with water from the constructed/ rehabilitated climate-proof infrastructure | None | No progress | 8,322 ha
Outcome 2.2. | IN2.2.1: Number of agro- meteorological stations established/ repaired. | 36 | No progress | 6 (6 new stations are not needed now by the Agro-meteorological department of the MoA. The project will instead install 1 new and rehabilitate 11 existing stations)
| IN2.2.2: Number of beneficiaries (disaggregated by gender) using agro- meteorological information to reduce climate risks to their production systems. | None | No progress | 16,000 HH
Outcome 2.3. | IN2.3.1: Number of grantees (disaggregated by gender) with sustained adoption of climate resilient technologies promoted by the project. | None | No progress | 9,350 HH
| IN2.3.2: Number of persons (disaggregated by gender) reporting increase in production | None | No progress | 6,650 HH
* indicators as per results framework presented in the project proposal.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | No activities took place yet due to delay in the agreement on institutional arrangements and execution modalities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, prolonged delays. The implementing entity has held a workshop in Erbil in 2022 and fielded a mission in 2 out of the 4 target governorates to foster the project's institutional arrangements and meet governorate teams and potential beneficiaries. The second AWPB has been developed and service providers are being explored (e.g. UNOPS). Disbursement expected in 2023.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes in design but a sub-committee from the Steering Committee will be established and led by the MoEH to guide and oversee the execution of activities in synhcronization with SARP. Ministry of Agriculture will still be involved in all activites under BRAC by MoHE as the project seeks to execute its activities in coordination with IFAD's baseline project that is led by the MoA.The project is exploring the possibility of bringing in UNOPS as a service provider to assist with procurement.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | N/A as activities did not start yet.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | N/A as activities did not start yet.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Roles and responsibilities between ministries should have been clear / negotitated before the start of the project
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A as activities did not start yet.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A as activities did not start yet.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A as activities did not start yet.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A as activities did not start yet.
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A as activities did not start yet.
What measures are being/could have been put in place to improve project/program results? | N/A as activities did not start yet.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A as activities did not start yet.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A as activities did not start yet.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A as activities did not start yet.
If learning objectives have been established, have they been met? Please describe. | N/A as activities did not start yet.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A as activities did not start yet.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A as activities did not start yet.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A as activities did not start yet.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | IFAD SARP project (stand alone)
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | IRQ/MIE/Agri/2017/1
Implementing Entity | International Fund for Agricultural Development (IFAD)
Type of implementing entity | MIE
Country
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 110400 | 43028 | 67000 | Total | 0 | 0 | 0 | Total | 0 | 0 | 0
|  | % of female beneficiaries | 0 | 0 | 0 | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 0% | 0%
|  | % of Youth beneficiaries | 0 | 0 | 0 | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 110400 | Drought | 1: Ineffective | Total | 110400 | Drought | 4: Effective | Total | 0 |  |  | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 40% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 36 | 1: Risk knowledge | Geographical coverage | Regional | 6 | 1: Risk knowledge | Geographical coverage | Regional | 0 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 2: Low capacity | Total | 300 | Agriculture | 3: Medium capacity | Total | 0 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 300 | 50% | Public |  | 0 | 0% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 110400 | 40% | 4: Mostly aware |  | 0 | 0% | 2: Partially not aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 |  | 2: Partially not aware |  | 0 | 40% to 60% | 4: Mostly aware |  | 0 |  | 2: Partially not aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change * services to HH and ha of farmland | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Agriculture | 6650 | Multi-community |  | Agriculture | 0 | Multi-community |  | Agriculture
|  | 0 | Multi-community |  | Agriculture | 8322 | Multi-community |  | Agriculture | 0 | Multi-community |  | Agriculture
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 10% | From 0 to 0.5% | Agricultural-related | 9350 | 10% | From 10% to 20% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Financial capital | Agriculture | Supporting livelihoods | 9350 | Financial capital | Agriculture | Supporting livelihoods | 0 | Financial capital | Agriculture | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income. *income per month | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related |  | 66 | 9350 | Agricultural-related |  | 79 | 0 | Agricultural-related |  | 0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 0 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
1.2 = IN2.2.1
2.1.1 = IN1.1.2
3.1.1 = IN2.2.2
3.2.1 = IN1.2.2
4.2 = IN2.1.2
4.1.1 = IN2.1.1 and 2.1.2
6.1.1/2 = IN2.3.1
7.2 = IN1.1.1