## Overview
Project Performance Report (PPR3)*
* Refers to both projects and programs
Period of Report (Dates) |  | From 11/04/2021 to 30/04/2022
| Project Title: | Ecosystem-based Approaches for Reducing the Vulnerability of Food Security to the Impacts of Climate Change in the Chaco Region of Paraguay
vulnerabilidad de la seguridad alimentaria a los efectos del cambio climático en la región del
Chaco en Paraguay
| Project Summary: | The goal of this project is to reduce the vulnerability of the population (selected family agriculture producers and indigenous communities) of the Chaco Region of Paraguay to the impacts of climate change on food security. In order to do so, the project plans to address the main barriers for adaptation in the selected region. Specifically, the project would seek to i) improve information and knowledge for climate resilience; ii) implement concrete cost-effective on-the-ground adaptation measures; and iii) strengthen the institutional capacities to adequately address climate change adaptation issues. The project would be organized accordingly in three components: i) Knowledge management on vulnerability and climate change resiliency improved; ii) adaptive capacity in rural areas of greatest vulnerability strengthened through concrete agro-ecosystem based adaptation measures; and iii) capacity development and awareness to upscale effective implementation of adaptation measures at the national and local levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PRY/MIE/Food/2012/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Environment Programme - UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementation Agency | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Paraguay | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is implemented in the Western Region of Paraguay, known as Paraguayan Chaco. Intervention zones include the communities of General Diaz, Pozo Hondo and the indigenous community of Campo Loa in the district of Mariscal Estigarribia in the Department of Boquerón. Other areas of intervention are the communities of Toro Pampa, San Carlos and Maria Auxiliadora in the Fuerte Olimpo District. In the Department of Alto Paraguay, the intervention zones include the fishing communities of Bahia Negra, the indigenous community of Karcha Bahlut and the Sierra León in the District of Bahia Negra. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-27
IE-AFB Agreement Signature Date: |  | 2017-06-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-04-11 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2021-07-31
2023-12-31
Original Completion Date:
Revised Completion Date after approval |  | 2024-04-11
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each. | Cyprus
Czech Republic
List the Website address (URL) of project |  | Under construction | Democratic People's Republic of Korea
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Marta Moneo - Programme Officer / Climate Change Unit /UNEP | Dominican Republic
| Email: | marta.moneo@un.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ulises Lovera Gaona | Equatoral Guinea
| Email: | ulises.lovera@mades.gov.py | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Jacqueline Alvarez- Regional Director / Latin America and the Caribbean Office / UNEP | Fiji
| Email: | jacqueline.alvarez@un.org | Finland
| Date: |  | France
| Implementing Entity |  | Gambia
| Name: | Gustavo Mañez - Climate Change Coordinator / Latin America and the Caribbean Office/ UNEP | Georgia
| Email: | gustavo.manez@un.org | Germany
| Date: |  | Ghana
| Implementing Entity |  | Greece
| Name: | María Carolina Chiappara - Fund Management Officer / Latin America and the Caribbean Office / UNEP | Grenada
| Email: | carolina.chiappara@un.org | Guatemala
| Date: |  | Guinea
Guinea Bissau
Guyana
Haiti
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 04/30/2020 |  |  |  | Financial information PPR 2: cumulative from project start to 04/30/2021 | [7 empty] | Financial information PPR 3: cumulative from project start to [04/30/2022] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS | [7 empty] | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [7 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 04/30/2020 | 155161 |  |  | Estimated cumulative total disbursement as of [04/30/2021] | 279405 | [6 empty] | Estimated cumulative total disbursement as of 04/30/2022 | UNEP expenditures (reporting period only): $ 281,623.34 Cumulative amount disbursed to Investigacion para el Desarrollo: $ 225,000 Total expenses: $ 130,992 Unspent amount: $94,008 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Total Disbusements as of April 30, 2020: $155,161 Total Committed as of April 30, 2020: $178,210 Total expenditures as of April 30, 2020: $333,371 |  |  | Add any comments on AF Grant Funds. (word limit=200) | Total Disbusements as of April 30, 2020: $279,405 Total Committed as of April 30, 2020: $511,365 Total expenditures as of April 30, 2021: $790,766 | [6 empty] | Add any comments on AF Grant Funds. (word limit=200) | Reporting Period only (April 2021-April 2022) UNEP Total expenditures as of April 30, 2022: $281.623,34 Investigacion para el Desarrollo Uncommitted amount pending of disbursement: $ 225,000 (Investigacion para el Desarrollo total amount: $ 450,000) |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 48097.8 |  |  | INVESTMENT INCOME | 61435.81 | [6 empty] | INVESTMENT INCOME | 51525.83 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant | [7 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA | [7 empty] | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT | [5 empty] | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public | 9514.2 |  |  | Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public | 26890 | [6 empty] | 1.1 Detailed mapping of ecosystems, including agro-ecological zones, water resources, forests and other ecosystems | 72046.33
| Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 0 |  |  | Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 235.77 | [6 empty] | 1.2 Information and monitoring system for agro-climatic risk assessment | 1230.86
| Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 4439.71 |  |  | Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 5528.65 | [6 empty] | 1.3 Assessment of the vulnerability to climate change of specific plants and animals used as food source. | 0,00
| Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 0 |  |  | Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 235.96 | [6 empty] | 1.4 Study of the Ecology, Management and Nutritional components of Algarrobo and Viñal (Prosopis spp.) | 0,00
| Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 0 |  |  | Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 9514.2 | [6 empty] | 1.5 Research on traditional practices that contribute to climate resilience | 0,00
| Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches | 4439.71 |  |  | Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches | 5940.14 | [6 empty] | 1.6 Development of specific protocols for the implementation of good practices in forest management and agriculture on farming and indigenous peoples communities. | 27660.95
| Output 3.1. Training plan for MADES, associated institutions at the national level especially the DNCC (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of climate compatible development and prevention and risk management in all sectors. | 0 |  |  | Output 3.1. Training plan for MADES, associated institutions at the national level especially the DNCC (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of climate compatible development and prevention and risk management in all sectors. | 0 | [6 empty] | 1.7 Elaboration of an analysis of incentives and disincentives for the adoption of climate-resilient agricultural practices in El Chaco region | 38803.39
| Output 3.2. The lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels. | 0 |  |  | Output 3.2. The lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels. | 0 | [6 empty] | 1.8 General vulnerability and impact assessment for the targeted communities | 23892.94
| Project Management Costs | 136767.21 |  |  | Project Management Costs | 231060.37 | [6 empty] | 2.1 Participatory development of integrated adaptation plans with an ecosystem-based approach | 5828.27
[13 empty] | 2.2.1 Training and exchange of knowledge among stakeholders. | 29.27
[13 empty] | 2.2.2 Extension services and acces to inputs for the conservation and restoration of forests. | 0,00
| TOTAL | 155160.83 |  |  | TOTAL | 279405.09 | [6 empty] | 2.2.3 Extension services and acces to inputs for agro-ecological production in farming and livestock, including agroforestry, apiculture, community seed banks and silvopastoral management | 0,00 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[13 empty] | 2.2.4 Implementation of improvements in the efficient use, catchment, harvesting and storage of rainwater | 0,00
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE | [8 empty] | 3.1 National level: Detailed training plan for SEAM and partner agencies at national level on mainstreaming climate compatible development across sectors | 0,00 |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | [5 empty] | 3.2 Local level: Training plan for partner agencies at local level (including but not limited to departmental and municipal governments) | 0,00 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Committed expenditure |  |  |  | Committed expenditure | [7 empty] | 3.3 Identification, systematization and exchange of lessons learned of the project | 2612.26
| Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public. | 18456 | September 2020 |  | Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public. | 249296.58 | July 2021 | [5 empty] | Project Execution Costs: Project Management | 104469.07
| Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 210 | July 2020 |  | Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 82080 | July 2021 | [5 empty] | Total Project Costs | 276573.34
| Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 1019.2 | July 2020 |  | Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 94995 | July 2021 | [5 empty] | Project Cycle Management Fee charged by the Implementing Agency | 5050
| Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 210 | July 2020 |  | Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 0 | [6 empty] | TOTAL | 281623.34
| Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 9420 | October 2020 |  | Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 0
| Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches. | 19263.2 | March 2021 |  | Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches. | 0 | [5 empty] | PLANNED EXPENDITURE SCHEDULE
| Project Management Costs: Committed Contract service - Drivers | 17174 | May 2021 |  | Project Management Costs: Committed Contract service - Drivers | 6074.36 | May 2021 |  |  |  |  | List outputs planned and corresponding projected cost for the upcoming reporting period | Planned expenditure schedule | PROJECTED COST | Est. Completion Date
| Project Management Costs: Travel related services/ vehicle/Personnel Staff | 112458 | December 2021 |  | Project Management Costs: vehicle/Personnel Staff | 78915 | April 2022
[13 empty] | 1.1 Detailed mapping of ecosystems, including agro-ecological zones, water resources, forests and other ecosystems | 179735.19 | 2023-02-01
| Total Committed as of April 30, 2020 | 178210.4 |  |  | Total Committed as of April 30, 2021 | 511360.94 | [6 empty] | 1.2 Information and monitoring system for agro-climatic risk assessment | 62133 | 2023-01-01
[5 empty] | Planned expenditure schedule | PROJECTED COST | Est. Completion Date | Execution Modality |  |  |  |  | 1.3 Assessment of the vulnerability to climate change of specific plants and animals used as food source. | 74921 | 2023-03-01
[8 empty] | UNEP direct exec. | UNDP services | Local partner execution PCA I | Local Partner execution PCA II |  | 1.4 Study of the Ecology, Management and Nutritional components of Algarrobo and Viñal (Prosopis spp.) | 7426.69 | 2023-04-01
[5 empty] | Output 1.1 Studies for the identification of best adaptation practices: Detailed mapping of ecosystems, including agro-ecological zones, water resources, forest and other ecosystems | 78500 | April 21 | - | 9500 | 69000 | - |  | 1.5 Research on traditional practices that contribute to climate resilience | 0
[5 empty] | Output 1.1 Studies for the identification of bet adaptation practices: Study of the ecology, management and nutritional components of algarrobo (Prosopis spp) | 74931 | April 21 | - | - | 74931 | - |  | 1.6 Development of specific protocols for the implementation of good practices in forest management and agriculture on farming and indigenous peoples communities. | 99536.59 | 2023-01-01
[5 empty] | Output 1.1 Studies for the identification of best adaptation practices: Research on traditional practices that contribute to climate resilience. | 93000 | April 21 | - | - | 93000 | - |  | 1.7 Elaboration of an analysis of incentives and disincentives for the adoption of climate-resilient agricultural practices in El Chaco region | 42693.12 | 2023-04-01
[5 empty] | Output 1.1 Studies for the identification of best adaptation practices: Elaboration of an analysis of incentives and disincentives for the adoption of climate-resilient agricultural practices in the Chaco region. | 20000 | April 21 | - | - | 20000 | - |  | 1.8 General vulnerability and impact assessment for the targeted communities | 65587.06 | 2023-01-01
[5 empty] | Output 1.2 Climate change vulnerability assessments to inform decision making and guide adaptation planning developed and disseminated with decision makers, stakeholders and the general public. | 70868 | April 21 | - | - | 70868 | - |  | 2.1 Participatory development of integrated adaptation plans with an ecosystem-based approach | 82722.5 | 2023-03-01
[5 empty] | Output 1.3. The protocol for the implementation of good practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral livestock in rural and indigenous communities, is prepared and made available to subnational governments and members. community to inform decision-making (specialized chapters by topic). | 280001 | April 21 | - | - | 252761 | 27240 |  | 2.2.1 Training and exchange of knowledge among stakeholders. | 38508.49 | 2023-04-01
[5 empty] | Output 1.4 New meteorological stations are installed and the necessary studies are prepared to carry out an agroclimatic risk assessment to inform decision-making by community members and sub-national governments: instalation of 5 meteorological stations | 125000 | April 21 | - | - | 125000 | - |  | 2.2.2 Extension services and acces to inputs for the conservation and restoration of forests. | 14832.4 | 2023-04-01
[5 empty] | Output 1.4 New meteorological stations are installed and the necessary studies are prepared to carry out an agroclimatic risk assessment to inform decision-making by community members and sub-national governments: Evaluation of the vulnerability to climate change of specific plants and animals used as a food source. | 151983 | April 21 | - | - | 151983 | - |  | 2.2.3 Extension services and acces to inputs for agro-ecological production in farming and livestock, including agroforestry, apiculture, community seed banks and silvopastoral management | 319963.4 | 2023-04-01
[5 empty] | Output 2.1 Development of adaptation community plans with ecosystem-based approach | 100000 | April 21 | - | - | 100000 | - |  | 2.2.4 Implementation of improvements in the efficient use, catchment, harvesting and storage of rainwater | 240336.73 | 2023-04-01
[5 empty] | Output 2.2 Implementation of adaptation community plans (technical assistance and inputs to implement concret adaptation measures favoring an ecosystem-based approach) | 463294 | December 20 | - | - | 12000 | 451294 |  | 3.1 National level: Detailed training plan for SEAM and partner agencies at national level on mainstreaming climate compatible development across sectors | 0
[5 empty] | Output 3.1 Training plan for MADES and partner agencies at national level on mainstreaming climate compatible development across sectors. | 71740 | April 21 | 34740 | - | - | 37000 |  | 3.2 Local level: Training plan for partner agencies at local level (including but not limited to departmental and municipal governments) | 0
[5 empty] | Output 3.2 Local level training plan for partner agencies at local level (including but limited to departmental and municipal governments) | 90000 | April 21 | - | - | - | 90000 |  | 3.3 Identification, systematization and exchange of lessons learned of the project | 6862.3 | 2023-04-01
[5 empty] | Output 3.3 Identification, systematization and exchange of lessons learned of the project | 61090 | December 21 | 56590 | - | 4500 | - |  | Project Execution Costs: Project Management | 80837.66 | 2023-04-01
[13 empty] | Total Planned expenditures schedule | 1316096.13
[5 empty] | Project Management Costs | 242199 | December 21 | 162972 |  | 30700 | 48527 |  | Project Cycle Management Fee charged by the Implementing Agency | 79945.37 | 2023-04-01
[13 empty] | TOTAL | 1396041.5
[5 empty] | Total Planned expenditures schedule | 1922606 |  | 254302 | 9500 | 1004743 | 654061 | [5 empty] | TOTAL | #REF! |  |  | TOTAL | #REF!
[16 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[16 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[16 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[16 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
1445348
Disbursement 3 AF: 1.445.345

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1] | Yes
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law | Yes | Yes | Lack of integration of the environmental and social issues in the sub-projects | Realization of ESIA or E&S impact notice of the sub-projects | Number of ESIA or E&S impact notice of the sub-projects designed in compliance with the E&S national regulation and AF’s ESP | 0 | The project has not yet built infrastructure of a size that requires ESIA according to domestic law. The project is in constant communication with the Ministry of Environment and will conduct Environmental Impact Assessments (or Environmental Social Impact Assessments) when adaptation measures such as water pits, which involve soil removal, are identified and approved by the PMU, UNEP, and the Ministry of Environment. | Lack of integration of the environmental and social issues in the sub-projects | Ensure that the planning of sub-projects integrates the active participation of the communities and aspects of social and environmental compliance in accordance with current legislation.
|  |  | Insufficient capacity of stakeholders to manage environmental and social issues in accordance with the national legislation and the AF’s principles. These include the Environmental Impact Assessment (EIA) Law 294/93, Law No. 422/73 (Forest law) and Resolution 2242/06 approving the list of protected species of wildlife threatened of extinction. | Training sessions in environmental and social management, monitoring and evaluation will be conducted as part of the training activities included in components 2 and 3 | Number of training sessions in environmental and social management, monitoring and evaluation | 0 | No training sessions have been conducted during the reported period. Nevertheless, a training plan will be designed and training sessions are expected to be conducted in 2023. | Even if the project complies with environmental law that requires environmental permits for large soil movements, local governments and other key players may continue to fail to do so. | The project will train key stakeholders and municipalities in the area of influence to raise awareness of the importance of compliance with environmental laws and procedures.
2 - Access and equity | Yes | Yes | Given that the beneficiaries are poor people who are not often integrated in the decision-making process, there could be risk of insufficient access of the project resources by these persons. | Clear and transparent criteria for eligibility of the projects beneficiaries will be applied, including for the selection of participants in the training sessions to be organized. | Level of applying the clear and transparent criteria for eligibility of the projects beneficiaries. Level of applying the fair criteria for selection of participants in the training sessions organized. Effectiveness of the project communication system | 0 | The monitoring of the project's environmental and social safeguards has been done to reduce social risks during implementation. All community members regardless of gender, age or disability are considered recipients of project benefits. Participatory community workshops have been held seeking gender inclusion and inviting women to participate. At the same time, the PMU requested the monitoring of environmental and social safeguards to the local ID partner during the fieldwork for data collection in studies of Component 1. It was agreed they are going to conduct separate focus groups with women when possible to include their voices during data collection. Similarly, at the time of reporting, local technicians are being trained in Project Environmental and Social Safeguards to continue minimizing the risks of inequity of the project towards the beneficiaries. | It is possible that people with disabilities are not included in focus groups or interviews. | Invitations to workshops are done specifying women, the elderly, the young, and people with disabilities can and must attend if they want.
Meeting minutes PMU-local partner ID
Local partner ID measures regarding safeguards
Training materials for local technitians regarding social and environmental safeguards
3 – Marginalized and vulnerable Groups | Yes | Yes | Insufficient access to the project activities by vulnerable and marginalized groups, in particular under component 2.2 (implementation of adaptation activities such as reforestation and forest conservation, agro-ecological management measures (good agricultural practices) and water storage and irrigation systems). For extension activities in indigenous communities the problem is that they are very closed communities, which do not readily accept technicians. | The project includes activities to improve life conditions of the marginalized groups, including indigenous people, women and young people. | Percentage of young people and women beneficiaries of the project Rate of income generating activities undertaken by women and young people | 0 | The monitoring of the project's environmental and social safeguards has been done to reduce social risks during implementation. All community members regardless of gender, age or disability are considered recipients of project benefits. Participatory community workshops have been held seeking gender inclusion and inviting women to participate. At the same time, the PMU requested the monitoring of environmental and social safeguards to the local ID partner during the fieldwork for data collection in studies of Component 1. It was agreed they are going to conduct separate focus groups with women when possible to include their voices during data collection. In relation to the communities that show skepticism to the project, it is sought that the hiring of local technicians, residents of the target communities or from the Chaco region, will contribute to generating confidence on the part of the beneficiary communities and the local authorities. In this context, the project hired a Nivaclé technician. He speaks the Nivaclé language spoken by Campo Loa community members and has work experience in agricultural projects. His skills are considered an asset to establish a familiar communication (due to the cultural nexus) and at the same time efficient (since Nivaclé is the native language of the beneficiaries of Campo Loa). At the time of reporting, all local technicians are being trained in Project Environmental and Social Safeguards to continue minimizing the risks of inequity of the project towards the beneficiaries. | It is possible that people with disabilities are not included in focus groups or interviews. | Invitations to workshops are done specifying women, the elderly, the young, and people with disabilities can and must attend if they want.
Meeting minutes PMU-local partner ID
Local partner ID measures regarding safeguards
Local technitians hiring records
4 – Human rights | Yes | Yes | It is slightly probable that the project negatively affect human rights and the rights of children and women. Nevertheless, there is a risk of inequitable access of the segments of the population to the project's resources. | The project includes activities to improve life conditions of the marginalized groups, including indigenous people, women and young people. | Percentage of young people and women beneficiaries of the project Rate of income generating activities undertaken by women and young people | 0 | The monitoring of the project's environmental and social safeguards has been done to reduce social risks during implementation. All community members regardless of gender, age or disability are considered recipients of project benefits. Participatory community workshops have been held seeking gender inclusion and inviting women to participate. At the same time, the PMU requested the monitoring of environmental and social safeguards to the local ID partner during the fieldwork for data collection in studies of Component 1. It was agreed they are going to conduct separate focus groups with women when possible to include their voices during data collection. In relation to the communities that show skepticism to the project, it is sought that the hiring of local technicians, residents of the target communities or from the Chaco region, will contribute to generating confidence on the part of the beneficiary communities and the local authorities. In this context, the project hired a Nivaclé technician. He speaks the Nivaclé language spoken by Campo Loa community members and has work experience in agricultural projects. His skills are considered an asset to establish a familiar communication (due to the cultural nexus) and at the same time efficient (since Nivaclé is the native language of the beneficiaries of Campo Loa). At the time of reporting, all local technicians are being trained in Project Environmental and Social Safeguards to continue minimizing the risks of inequity of the project towards the beneficiaries. | It is possible that people with disabilities are not included in focus groups or interviews. | Invitations to workshops are done specifying women, the elderly, the young, and people with disabilities can and must attend if they want.
Meeting minutes PMU-local partner ID
Local partner ID measures regarding safeguards
Training materials for local technitians regarding social and environmental safeguards
5 – Gender equality and women’s empowerment | Yes | Yes | Risks for gender equality and empowerment of women could be: (i) Insufficient consideration of gender mainstreaming in the implementation of the project; (ii) Not taking into account women’s empowerment in the activities of the project. | Gender will be considered in the selection of beneficiaries. Increase women's availability and access to resources, reduce the workload of women, increase the productivity and generate income through the implementation of ecosystem-based adaptation (EbA) measures under the component 2, A part-time consultant (sociologist or anthropologist) will be hired to analyze and contribute to ensure the integration of gender aspects. Local capacity-building activity 3.2 will integrate coaching actions for trainers to train women in planning, implementing and managing EbA investments. The project results framework includes disaggregated targets by gender for the number of beneficiaries of training activities. | Percentage of young people and women beneficiaries of the project Rate of income generating activities undertaken by women and young people | 0 | To determine the vulnerability of the beneficiary communities, data disaggregated by sex is being considered, which will contribute to the understanding of the reality of women (indigenous and non-indigenous) and valuing their contributions. The PMU has insisted on the incorporation of a gender specialist for the studies carried out in the framework of Component I by the local implementing partner, ID since the PCA signing date. Nevertheless, since the ID team did not include a gender specialist, recently, this was demanded as a urgent matter. The gender specialist is expected to reduce the risks associated with the exclusion of women during participatory rural appraisals and when conducting focus groups with community leaders. At the time of reporting, the gender specialist has been hired and is designing a gender work plan for next fieldworks. Additionally, the PMU has the support of the REDD+ Gender Specialist in Paraguay for sharing knowledge and project strategies. On the other hand, work will be done on the need to strengthen the capacities of women and men according to their interests. For example, in Component II, women in Cacique Sapo requested supplies for beekeeping and honey production, a productive activity traditionally done by men in their communities. Likewise, the exchange of experiences on adaptation to climate change among women leaders of the beneficiary communities will be promoted. | It is possible that the activities of the project and the proposal to promote the participation of women and vulnerable groups may not be enough to change behavior regarding gender inequalities and vulnerable groups. | Include activities and workshops to promote conditions for the participation and empowerment of women and vulnerable populations.
Meeting minutes PMU-local partner ID
Local partner ID measures regarding safeguards
6 – Core labour rights | Yes | Yes | In Component 2, construction and reparation of water storage systems may entail risks of accidents for workers. During the operations, workers will be exposed to the risk of accidents that can range from simple injuries to death. Also in Component 2, the supply of agricultural inputs also presents risks of traffic accident during transportation. | During implementation, the project will ensure compliance with the Code of Labor in Paraguay and will provide adequate protection equipment for workers | Proportion of workers who wear protective equipment. Level of compliance of the project with the Code of Labor. | 0 | The project has not taken measures to reduce this risk, because at the time of reporting, the construction works for Component 2 have been minimal and therefore construction workers were not hired. However, the project prioritizes local companies that have a good business reputation in the community to supply water tanks and plumbing materials. This was to guarantee the installation in a timely manner according to the requirements of the project, to support the local economy, and timely responses when issues with equipment arise. | Informal labour prevails in local communities and vulnerable communities. The project might not be able to address this situation, but contribute to raise awareness on the matter. | Promote training in labor rights, health and safety at work through local technicians who will receive training in the training of trainers format.
7 – Indigenous peoples | Yes | Yes | There is a risk of inequitable access of indigenous peoples to the project's resources. | The project activities that will be implemented within an indigenous community will take into account their rights and culture, and therefore activities may need to be adapted for each linguistic and ethnic context. Furthermore activities will be based on up-to-date information on the status of ecosystems, land uses and other aspects to allow adequate selection of activities to be implemented in the field. The most adequate methodologies and human resources for the project implementation will be identified. In this context, MADES has elaborated guidelines for implementing projects with indigenous communities, and will be taken into account by the AF project when carrying out its activities. With this in mind, the project takes into account systematization, dissemination and use of traditional knowledge and practices as a key strategy to reduce the vulnerability of food production to a changing climate. Traditional practices by both indigenous peoples and farmer communities include the use of local flora and fauna, food harvesting from native tress, collection of fruits and honey, natural medicines, raw materials for shelter building, aesthetic and spiritual values. The development of sound, respectful and effective communication will be encouraged and maintained as an important human factor in the interaction with the different communities and individuals. | Percentage of indigenous people beneficiaries of the project Rate of income generating activities undertaken by indigenous people Effectiveness of the project communication system | 0 | The project maintains an equitable vision of human rights, which also considers cultural diversity, diversity of worldviews, demographics and gender considerations in the implementation of adaptation actions. In this context, from the beginning of the project activities, the free, prior and informed consent (FPIC) of the indigenous communities was implemented. In 2021, the FPIC of the community of Puerto Diana (a community located in Bahia Negra), was officially obtained. At the same time, the community consent workshops were adapted to the local context, and interpreters were hired when necessary. Additionally, all approaches to communities such as community activities are carried out by respecting the leadership and power structures recognized by the communities. In 2022, the PMU insisted on the incorporation of an indigenous peoples' specialist for the studies carried out in the framework of Component 1 by the local implementing partner, ID. This specialist was hired in May 2022 and is expected to improve rural appraisals conduction due to solid experience and knowledge of communitarian work with rural communities. | The level of income generation through the adoption of EbA measures undertaken by indigenous communities could be diminished due to changes in land uses, and biome conversion, which could potentially affect the landscape's capacity to restore its ecosystem services, continuity, and quality. Additionally, constant leadership changes and power shifts within indigenous communities could also compromise income generation in the future. | The project will seek synergies with the local government, organizations, and other projects initiatives in the territory to enhance alignment of the adaptation measures and activities (livelihoods, agriculture, water) to guarantee that the income generation through the AbE´s investments is sustainable for the indigenous communities beyond Project closure.
INDI acknowledgement of FPIC in five communities
FPIC previous records
Local partner ID measures regarding safeguards
8 – Involuntary resettlement | No further assessment required for compliance
9 – Protection of natural habitats | Yes | Yes | The project will be particularly careful in preserving natural habitats and biodiversity, and using sustainably any ecosystem service, conserving land and soil, preventing pollution and promoting resource efficiency. Specifically, the project’s activities seek to incentive practices that allow an increase of production and income per hectare, in order to reduce the need for logging. However, there is a low risk of destruction of vegetation and wildlife habitat, especially in the context of physical infrastructure works, such as meteorological stations and water infrastructure. | Technical feasibility studies will be conducted for physical infrastructure such as meteorological stations and water infrastructure, including environmental protection aspects. As mentioned, all activities will adhere to Environmental Impact Assessment (EIA) regulations as defined by Paraguayan law. | Number of corrective measures applied | 0 | As of the reporting date, no construction works have been carried out, apart from the installation of the pilot or demonstration units. Pre-feasibility studies are expected to be carried out for the location of the meteorological stations, as well as the Environmental Impact Studies required by national legislation, if applicable. | The danger of unsustainable use of ecosystems and degradation due to changes in land use persists. Improving the valuation of ecosystems by neighboring communities and producers, added to the promotion of more sustainable production practices, would facilitate their protection in the future. | Promote the valuation of ecosystems and share information regarding their health resulting from the studies of component 1 of the project. Promote sustainable production practices through field trips, workshops and campaigns to promote knowledge regarding sustainable production practices.
10 – Conservation of biological diversity | Yes | Yes | The Carob (algarrobo) and Prosopis spp. Are nitrogen fixing trees whose activities contribute to the enrichment of the soil, while at the same time providing shade and nourishment (in the form of leaves and seed pods) for livestock. According to SEAM Resolution No. 2242/06, two of the species of Prosopis spp. are categorized as “endangered species". Due to lack of data and reliable information on population and use makes, there is a risk of unsustainable management and use of endangered species. | A study will be conducted to collect data on: (i) the current and taxonomic distribution of algarrobo and Prosopis spp .; (Ii) its population density and (iii) the volumes used by both the industrial sector and the handicraft sector in the Paraguayan Chaco. Among others, these data will allow the Secretariat of the Environment, through the Directorate of Biodiversity Protection and Conservation, to carry out the administrative procedures necessary to issue permits for commercial collection, and export permits. In addition, they will allow regulating the production chain that uses these Species as productive biological resources, while ensuring the protection of endangered species. | Number of measures adopted | 0 | The project will carry out studies to collect information about the use of Prosopis spp. as food source. Based on this and complementary studies, adaptation plans will be developed and adaptation measures will be implemented. These adaptation measures will be in accordance with local and international legislation and consider species listed as having conservation threats category. | Under the principle that we preserve what we know, the use and management of biological and genetic resources of native species are promoted, therefore if the information resulting from the studies is not disseminated and given value, it will be difficult to integrate it into the efforts of forest management plans in the territory risking sustainable and protected by law species conservation in the long-term. | Efforts to integrate key actors such as NGOs, private, public, and academic sectors for the dissemination of knowledge and appropriation of the results of the studies adding value to the forest species and incentives for its conservation.
11 – Climate change | No further assessment required for compliance
12 – Pollution prevention and resource efficiency | No further assessment required for compliance
13 – Public health | Yes | Yes | Access to drinking water: It should also be noted that if the sources of drinking water are contaminated, the consumption of this water can cause disease. Development of water-related diseases: The continuous presence of the water on water storage systems could cause the development of water-related diseases (Malaria, amoebiasis, typhoid fever) | Sensitize communities and include technical support for the effectiveness of the epidemiological monitoring system in the capacity building activities at local level. | Number of sensitization sessions for local institutions in the project area to allow them take in account all new case of water-borne diseases. Evolution of the numbers of waterrelated diseases cases (malaria, bilharzia, diarrhea, schistosomiasis, etc.) | 0 | The vulnerability studies carried out by the local partner ID are contemplating analyzes of the physical and chemical quality of water in different communities. This will allow decision-making in relation to the adaptation measures to be considered appropriate for each community. Training sessions planned to be conducted in 2023 will include sanitation and disinfection with chlorine as well as supply of chlorine. | Efforts related to the diffusion of the use of chlorine and other substances for the purification of water may not be sustainable and/or sufficient. | Links will be established with the governing body for water and sanitation in the country to evaluate potabilization options in the communities.
ID Intermediate products approved
14 – Physical and cultural heritage | No further assessment required for compliance
15 – Lands and soil conservation | No further assessment required for compliance
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | The project includes a Monitoring Plan. This plan shall ensure that the progress of the project and the results of its activities are closely tracked and adjustments are made when necessary for the project to achieve its results efficiently. The M&E plan was not designed to monitor unanticipated ESP risks. Nevertheless, the local technicians recently hired are expected to colect cualitative information about the ESP risks and ESP compliance. At the same time, the Planning, Monitoring and Evaluation specialist will work with the new Indigenous and gender specialist hired by the local partner ID to collect information about the ESP.
Monitoring Manual
Have unanticipated ESP risks been identified during the reporting period? |  | Construction planning for the bi-oceanic road to the community of Pozo Hondo and Jasyrendy is advancing. This new infrastructure could have unintended consequences for the community of Jasyrendy as their way of life with rules and autonomy typical of indigenous communities might be at risk.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | Dialogue will be promoted with the municipality of Mariscal Estigarribia and the Instituto del Indígena to evaluate options for assigning a rural land to the Jasyrendy community.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Safeguard risks were identified during the development phase of the project. Subsequently, a Project Safeguards Manual was drawn up to provide the basis for systematic monitoring and avoidance of environmental and social risks. Questions of opportunity gaps in relation to indigenous applicants have been considered in the hiring process of local technicians. The implementing partner has been requested to implement the Safeguards Manual as well as the Grievance Mechanism during the PCA execution. Local technicians are being trained in the project's environmental and social safeguards.
Have the implementation arrangements been effective during the reporting period? |  | Safeguards implementation arrangements have had little impact in the reported period. However, it is expected that local technicians that have been trained in said safeguards will improve existing measures. At the same time, the hiring of a Planning, Monitoring and Evaluation Specialist who also is in charge of the safeguards monitoring is expected to contribute to the monitoring and the reduction of environmental and social risks.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The executing entity has supported the PMU during requests made to the implementing partner to hire a Gender and Indigenous peoples Specialist. Similarly, the Ministry of Environment has designated one person from de DNCC, who is a gender focal point in the DNCC to support field missions. This designated person is constantly supporting field missions and also contributes to the project during project meetings.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | At the time of reporting, the arrangements made by the Ministry of Environment are considered sufficient considering the financial resources the Ministry has. Nevertheless, the effectiveness of EEs arrangements has not been assessed. It is expected the Mid-term review of the project (to be conducted during second semester of 2022) will contribute to enlightening the effectiveness of project implementation as well as ESP safeguards implementation.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | A grievances Manual was drawn up, the indicators were shared with the beneficiary communities in the EbA workshops, to access it, click on the following link:
Grievances Manual
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | No grievances have been identified or registered through the grivance mechanism. Nevertheless, the PMU has maintained constant communication with community leaders. This made possible to address some concerns that were expressed verbally.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Polítical: Institutions do not prioritize this project | Low | In 2019, the Representatives Chamber declared the AbE Chaco project as a matter of national interest. In June 2021, MADES sent a written communication to the Adaptation fund informing the suspension of project activities until further notice. In July 2021, Congresswoman Marlene Ocampos sent a written official note in the representation of the Permanent Advising Commission of Indigenous peoples of the Representatives Chamber to the MADES Minister expressing concerns about the posibility of project closure. Together, UNEP and MADES sought a solution and improved communication and coordination. Weekly meetings were held in September and October 2021 at the level of the Acting Regional Director of UNEP (Piedad Martín) and the Minister of MADES (Ariel Oviedo) or whoever they appointed. These meetings defined lines of action for strengthening the project and accelerating execution instead of closing the project. The priorities of municipalities, departamental governments and parliamentary commission had been expressed in favour of the project and, as a consequence of the action taken, the risk during the period is considered low. In November 2021 there has been a change of national administration, followed by a change of Municipality authorities. In response to this situation, the project team informed the new authorities by written communication about the project and how its outcomes are aligned to national and local priorities. At the same time, the project team conducted participatory meetings to explain the situation of the project (activities stopped until further notice) and the intention to resume project activities. Constant phone communication has also been maintained with community leaders and Municipality designed representatives from local institutions to plan, implement, and monitor the project activities. Additionally, in September 2021 meetings with community leaders and referents were conducted to restart activities of the project. Meetings were also conducted with municipality authorities and with Mayors. The PMU perceived a favourable attitude of beneficiaries to resuming project activities.
Congresswoman written note
Institutional: The lack of coordination, collaboration and adequate cooperation between executing agencies generates delays in the project´s implementation. | Low | As a result of communication issues between the Project Management Unit (PMU) and the implementing and executing instances (UNEP- Latin America and the Caribbean Office and DNCC- MADES) during 2019 and 2020, delays persisted until 2021. A collaboration agreement has been established with a local implementing partner to speed up the execution and payments. In the previous reported period there were no further inconveniences with this agreement which resulted in a faster procurement process and reduced costs. More recently, since December 2021, new inconveniences related to the technical studies that are being conducted emerged. The process of approval of work plans, field missions and technical products took more time than expected. At the same time, the quality of the intermediate products were not as expected. Currently, the PMU is undergoing a thorough revision of these products in order to advance indicators and project activities.
Institutional: Frequent staff rotation at local implementing agencies may affect the availability of qualified personnel. | Medium | The Project Coordinator finished its two-year contract in March 2021. Additionally, considering the posible closure of the project, MADES advised not to renew the contracts of two drivers, whose contracts were ending in May 2021. Similarly, one team member quit her position as a technical officer of Boqueron in June 2021. In August 2021, the continuity of the AbE Chaco project was already decided and the team designed new terms of references to hire consultants to restructure the project team. There were six new positions identified as required for the team, and these were 1 Technical Officer, 1 Planning Monitoring and Evaluation Specialist, 1 Project Coordinator, 1 Administrative Assistant and 2 Drivers. The calling process started in December 2021 and the completion of this hiring process was until April 2022. At the time of submission of this report, the Coordinator has been already selected and the contract for Project coordinator being prepared. Additionally, since the need for a permanent presence in the field was identified, the PMU started the hiring process of six local technicians to live in the departments of Alto Paraguay and Boquerón . At the time of submitting the report, the technicians have already begun their work in the beneficiary communities.
Hiring records
Local technitians hiring records
Institucional: Lack of interest and participation of key actors and target groups, along with conflicts/differences between actors/groups may weaken and delay the implementation of activities | Low | The conflict of the leadership in one beneficiary community, Karcha Bahlut, resulted in delays in the implementation of the pilot unit in the community. The conflict ended in a change of community leader. The new leader orally agreed to continue with the implementation the pilot unit approved by the former leader. Nevertheless, the acceptance of the community to the pilot unit was given until May 2022. It is expected to have a signed approval for the implementation of the demonstration unit by june 2022. The project team has maintained constant communication and has been monitoring the change of leadership in the community to continue with project activities. In the Pozo Hondo community, a lack of commitment from the neighbor's committee, in which there was supposed to be a change of authorities has been identified. However, up to date, this has not been the case. At the time of reporting, the project team is working with a group of fishermen and small producers. It is expected that the hiring of local technicians is going to contribute to the strengthening of local organizations, including the neighbor's committee. In the Jasyendy indigenous community, there is a disagreement among community members about staying in the community or moving to a new land. Currently, Jasyendy is inserted in the middle of the urban area of ​​Pozo Hondo (Latin community). The Municipality of Mariscal Estigarribia offered them land outside the Pozo Hondo community for those who want to keep their traditional way of life as indigenous. Currently, leaders are debating the proposal and have not yet decided to accept the Municipality's offer. The Project team will accompany and follow up on this issue to ensure the correct implementation of the pilot units. Those who decide to stay in Pozo Hondo will be considered part of the Pozo Hondo community. At the same time, if a group of people decides to move to the new communitarian land, the project will consider them as the Jasyendy community. In any case, both are still part of beneficiary communities identified by the project. The General Díaz Community is settled in the surroundings of the General Díaz Fort since the 1930s. However, until today the community do not have land titles. This situation makes it difficult to carry out pilot interventions in this community. The technical team will follow up and work with the community and local governments in order to clarify the land tenure issue. The inland communities of the Fuerte Olimpo district (San Carlos, Toro Pampa and María Auxiliadora) have new neighbors' committee and up to the time of the report they have shown great interest in the project as well as commitment to support and get involved in project activities. This commitment is expected to give sustainability after project completion. On the other hand, the community of Sierra León is in the process of outmigration due to the lack of access to public services and opportunities. This is shown terms of roads condition and water supply, which has also meant a lack of commitment towards the chage of authorities of their grassroots organization. The later aspect is expected to be addressed closely and as a priority by the local technician responsible for this community. In the community of Cacique Sapo, one group of people has separated from the rest of the community. This was the consequence of alleged leadership conflicts that ended up with the creation of the Santa Rosa community group. The project team continues to work with the original leader of Cacique Sapo, in consideration that the INDI recognized him by law. The team is seeking to find solutions and how to address this conflict in order not to leave anyone behind and reconcile the situation with the law. On the other hand, the technical team perceives a general lack of interest coming from community leaders and beneficiaries in technical studies and, in contrast, high interest in the concrete adaptation measures of the project. To mitigate the risk of participation of key actors at the local level, the project hired local technicians to closely support the communities in adaptation measures. At the same time, it is expected that they will serve as meditators in conflict resolution when power conflicts arise. At the time of submission, the local technicians are starting their activities and were already trained in ESS safeguards and grievance mechanisms, climate change adaptation and project strategy, goals and project monitoring compliance mechanisms.
Field missions reports
Environmental: Climate variability and change, including extremes, are greater than projected by the studies. | Low | Although the access to some isolated communities (due to distance and with intermittent road access) is entirely dependant on weather conditions (frequency and intensity of rains), during the period of this report, there have been no significant or recurring events that have compromised the implementation of field activities. The Chaco region subject to two consecutive years of La Niña phenomenon, which is causing long droughts as well as short but pouring rain events. Considering current weather conditions, schedules have been adjusted in a timely manner based on solid weather forecasts and local road information platforms.
Financial: The use of financial resources involves many levels of authorizations and delays the execution of activities. | Medium | Improvements have been perceived in the implementation of the project linked to the availability and agility of the financial flow. Considering delays in administrative procedures, alternative mechanisms have been sought for making funds available in a more efficient way for the technical execution of the project. This has been achieved through the outsourcing of the administration of the funds through UN agencies in the country and a local partner (Project Cooperation Agreement- PCA). This PCA resulted in faster procurement processes and reduced costs. Despite the PCA's increased efficiency in procurement processes, UNEP and MADES internal processes generate delays in hiring processes and implementing agreements such as the PCA signed with a local implementing partner.
PCA local implementing partner ID
Financial: The use of financial resources is not transparent. | Low | The implementation of the project is carried out following all the principles of transparency and administrative procedures of UNEP, as well as in full compliance with all current national legislation in Paraguay. On the other hand, the project Mid-Term Review (MTR) is expected to be conducted in the second semester of 2022, as it was decided by the Steering Committee in December 2021.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
None |  | Not applicable
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting period, the previously identified risks were at medium and low levels. Different strategies were taken to mitigate the reported risks and in consequence, no risks turned into major issues. In 2021, the most significant risk has been the suspension of project activities and the posible closure of the project. This was exacerbated by the restrictive effects and protection measures during the Covid-19 pandemic. This meant taking all the health protection measures, rethinking and adjusting the planning of community activities, and including the supply of hygiene items. Some activities were carried out virtually within the PMU. These measures have ensured the implementation of the project (more slowly but not stopping). Another risk identified for the proper implementation of the project has been poor communication, lack of planning due to the size of the project and, in consequence, adequate coordination and execution. This issue resulted in restructuring and strengthening the PMU team, particularly concerning the tasks of planning and coordination, technical sphere and presence in the field. More open and informed work sessions have also been held between the PMU, DNCC / MADES, UNEP / Latin American and the Caribean Office so that there is a more positive flow of project information and it translates into a more agile execution of activities. Regarding the newly identified inconveniences related to the technical studies that are being conducted by the local implementing partner, the PMU has called for expressions of interest to NGOs with the technical capacity to help in the implementation of the remaning studies of Component I.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | There were no initial gender assessments attached to the project proposal. However, an initial gender assessment was conducted during the EbA workshop, as well as in the socialization of the indicators of the gender manual (in the process of validation). To access the document, click on the following link:
Gender Manual
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The Component III, wich include all the training workshops includes indicators disagregated by sex. Similarly, in EbA training sessions, the data will be colected by sex to monitor progress.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Capacity development and awareness to implement and upscale effective implementation of adaptation measures at national and local levels | Detailed training plan for MADES and partner agencies at national level (ministries and agencies, including but not limited to MAG and INFONA), on mainstreaming climate compatible development across sectors. | Number of MADES staff trained (by gender) | 0 | 120 | Poor
| Training plan for partner agencies at local level (including but not limited to departmental and municipal governments) | Number of relevant stakeholders trained (by gender) | 0 | 160 | Poor
| Identification, systematization and exchange of lessons learned of the project | Number of lessons learned documents prepared by the project | 0 | 10 | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UNEP has a comprehensive policy that establishes the use of a gender marker. Essentially, the gender marker serves as a monitoring tool that ensures that at the point of project development and implementation, gender perspectives are integrated into all stages, including budgeting. The gender marker has a four-point scale against which the project is evaluated. Each project is required to meet a rating of 2a, which means that gender is fully integrated and the project will make a significant contribution to achieving gender equality. In the event that a project does not meet grade 2a, the project officer is required to review the project and ensure that gender perspectives are fully incorporated and then resubmit the project for review. At the time of reporting, the studies conducted as part of Component I include studies with disaggregated data by sex as well as qualitative data collection which will complement quantitative data to better understand the reality of women (including indigenous women) in the face of two sensitive issues such as water and food vulnerability in the beneficiary communities. At the same time, the PMU is overseeing that fieldwork done by the local implementing partner is instructed by a gender specialist. This incorporation is expected to reduce the risks associated with the exclusion of women during participatory rural appraisals and when conducting focus groups with community leaders. At the time of submission of this report, the gender specialist has been hired and is designing a gender work plan for the next fieldwork. The exchange of experiences on adaptation to climate change among women leaders of the beneficiary communities will also be promoted.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Gender considerations were integrated into the Logical Framework, Work Plans and AOPs, however the effectiveness of the implementation cannot yet be verified.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The executing entity has supported the PMU during requests made to the implementing partner to hire a Gender and Indigenous peoples Specialist. Similarly, the Ministry of Environment has designated one person from de DNCC, who is a gender focal point in the DNCC to support field missions. This designated person is constantly supporting field missions and also contributes to the project during project meetings.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | At the time of reporting, the arrangements made by the Ministry of Environment are considered sufficient considering the financial resources the Ministry has. Nevertheless, the effectiveness of EEs arrangements has not been assessed. It is expected the Mid-term review of the project (to be conducted during second semester of 2022) will contribute to enlightening the effectiveness of project implementation as well as ESP safeguards implementation.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Alleged declarations of beneficiaries in Campo Loa mentioned a case in which the translator in an all-women focus group was a man. In the context of indigenous communities, the presence of a man in an all-women meeting can affect the data collection and the statements women provide. This was addressed with the local implementing partner, and the request for a gender specialist was strongly repeated. At the time of reporting, the local implementing partner has started the hiring process for a gender specialist. It is expected that similar issues will be avoided from now on.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | The proposal of a grievances manual was socialized with the beneficiaries through said mechanism, they will be able to report their concerns and / or complaints (such manual has already been drawn up and is in the process of being updated).
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievances have been reported.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | MU | Rating
Implementing Entity: | Outcome 1: Knowledge management on vulnerability and resilience to climate change improved to implement cost-effective adaptation measures. |  | Outcome 3 | The vulnerability of the local population is determined based on technical criteria and statistical data available in the country; as well as technical studies to justify priorities to implement EbA measures. |  | The local implementing partner is conducting the vulnerability assessments (output 1.8), as well as other technical studies regarding outputs 1.1 on ecosystems,1.4, Algarrobo and viñal nutritional components and 1.5 on local traditional practices that contribute to climate resilience. Intermediate products of the vulnerability assessment as well as the other studies are being validated by the PMU and the Environment Ministry (MADES). The weather station installation has not yet been completed.. At the time of submitting this report, the PMU launched a call for expressions of interest to local NGOs for the elaboration of a 1.3 study on the impacts of climate change on plants and animals used as food sources and 1.6 a study on local traditional practices that contribute to climate resilience, and to develop the community adaptation plans. | Marginally Satisfactory
| Outcome 2. Adaptive capacity in rural areas of greatest vulnerability strengthened through concrete adaptation measures favouring an ecosystem-based approach |  | Outcome 5 | Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  | 18 EbA pilot or demonstration units were implemented in ten communities. These units were agreed upon with the communities and currently serve as “pilots” for the future concrete adaptation measures once the adaptation plans are finished. These units are focused on: a) improving food security through beekeeping (Cacique Sapo and Jasyendy communities), b) improving water availability (Pozo Hondo, General Díaz, Campo Loa, San Carlos, María Auxiliadora, Toro Pampa and Sierra León communities); and, c) Cattle ranching and agroecological practices (Karcha Bahlut and Puerto Diana communities). The second round of pilot units will be implemented during the second semester of 2022. | Marginally Satisfactory
| Outcome 3. Capacity development and awareness to implement and upscale effective implementation of adaptation measures at national and local levels |  | Outcome 3 | No progress was expected in the reporting period |  | No progress was made during this period. | Marginally Unsatisfactory (MU)
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Marta Moneo
| Email: | marta.moneo@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
-Several arrangements were put in place to accelerate the execution rate and funds were made available at the country level mainly through two mechanisms: (a) the UN network agency (UNDP) and (b) through a local partner (Research for Development or ID in Spanish). These arrangements have facilitated the flow of funds and the capacity to respond quickly to project needs. The Implementing Entity considered that this local partner had experience in climate change and solid expertise in vulnerability assessments. Up to date, the vulnerability assessments and additional studies are delayed. This resulted in the PMU strengthening communications with the local implementing partner to oversee and give prompt feedback on delivered intermediate products prepared by the local partner. This is expected to accelerate the delivery of the final products. -To complete the indicators of Component I, the PMU launched a call for expressions of interest to local NGOs for the elaboration of a 1.3 study on the impacts of climate change on plants and animals used as food sources and 1.6 a study on local traditional practices that contribute to climate resilience, and to develop the community adaptation plans. This is expected to answer the indicators that are not being addressed by the current PCA signed with ID. -Despite numerous challenges, initial pilot EbA interventions have been implemented in most of the participating communities as a means to engage them in the project. Communities have shown and communicated both to the PMU and MADES, their interest in the project and their urgent need for support. The communication line with these communities is clear and set for the continuation of the project. -More presence in the communities was also identified as an urgent need to maintain constant and fluent engagement with pilot communities. As a result, the PMU started the hiring process of six local technicians to conduct and support the implementation and monitoring of adaptation measures (the six local technicians are hired and in place at the moment of submitting this report). -The magnitude of the AbE Chaco project made evident that the structure of the PMU team needed to be reinforced in order to incorporate the technical capacity to strategically plan and supervise the different activities and technical assessments being conducted. This proposal was presented to MADES in the Steering Committee in December 2020. During 2021 and until April 2022, the PMU conducted the hiring process of consultants, adding six new people to the team, plus the six local technicians. At the time of the report, the Project Coordinator is also hired and took office. -The COVID 19 pandemic has imposed substantive restrictions in terms of project execution in the intervention areas that have resulted in delays in the implementation rate of the project along with identified coordination weaknesses. This meant the PMU had to adjust to local restrictions and conduct workshops within those restrictions during 2020 and 2021. -The technical and geographical scopes of the project have also made it clear that a stronger institutional coordination mechanism is necessary such as a wider coordination committee that includes representation from all key stakeholders and possibly technical committees that can ensure alignment with key ministries and local governments. This has also been raised with MADES through the Steering Committee. -For the reasons stated above, the progress of this project is rated as marginally satisfactory for this period, being confident that the consideration of the listed recommendations and the arrangements already established or being established will be able to accelerate the implementation and execution rate in the coming period.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Knowledge management on vulnerability and resilience to climate change improved to implement cost-effective adaptation measures. |  | Outcome 3 | The vulnerability of the local population is determined based on technical criteria and statistical data available in the country; as well as technical studies to justify priorities to implement EbA measures. |  | Intermediate products of the vulnerability assessment as well as the other studies conducted by the local implementing partner are being validated by the PMU and the DNCC - Environment Ministry (MADES). The DNCC is closely supporting the revision of the intermediate product. At the same time, the DNCC has a written Agreement with the Meteorological & Hydrological National Directorate (DMH) which will serve as a starting point for the installation of the meteorological stations. | Marginally Satisfactory
Intermediate products aproved
| Outcome 2. Adaptive capacity in rural areas of greatest vulnerability strengthened through concrete adaptation measures favouring an ecosystem-based approach |  | Outcome 5 | Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  | The second round of pilot units will be implemented during the second semester of 2022. DNCC follows the planning of these activities and gives constant feedback on state priorities. | Marginally Satisfactory
Call for expressions of interest
| Outcome 3. Capacity development and awareness to implement and upscale effective implementation of adaptation measures at national and local levels |  | Outcome 3 | No progress was expected in the reporting period |  | No progress was expected in the reporting period | Marginally Satisfactory
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ulises Lovera
| Email: | ulises.lovera@mades.gov.py
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
-The execution of the project has become more dynamic through the PCA with a local partner organization, however an optimal pace of implementation was not reached due to coordination problems in the past. This situation delayed the achievement of established targets, and some delays persist until today. -The vulnerability assessment as well as the other studies (baseline studies to determine the vulnerability of food security) conducted by the local implementing partner had administrative delays during the call for the tender process. Moreover, not many technical bidders applied to conduct these studies in 2020. Currently, intermediate products of these studies are being validated by the PMU and the DNCC. Nevertheless, some technical concerns arose during the revision of intermediate products. In this context, the PMU and DNCC are working closely to improve communication, give prompt feedback on intermediate products to the local implementing partner and therefore advance the indicators of Component 1. - Regarding Component II, the DNCC is following closely the planning of investment for the round two of pilots as well as the planning for future concrete adaptation measures. This support is considered essential to strengthen project recognition in the field and by other institutions in Paraguay.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
Project Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Achieved | Progress since inception | Target for Project End
Outcomes indicators | 1. Increase in generation and use of climate information in sustainable development planning | 0 | 0 | The project is revising intermediate products of the tehnical and vulnerability studies. This are undergoing revision by the PMU and the Environment Ministry (MADES) and are planned to be finished at the end of second semester 2022. The achievement of this indicator is subjected to the delivery of outputs 1.1 to 1.8 and the use of the information generated in the technical studies. | Integration of climate change adaptation, including priority actions and strategic options, into at least two departmental and/or district sustainable development plans
Results indicator | 1.1 Number of detailed ecosystems maps for the areas of influence of the selected communities | 0 | 0 | The local implementing partner will deliver the ecosystems' maps as part of the studies included in the vulnerability assessments. Intermediate products of the vulnerability assessment as well as the remaining studies are undergoing revision by the PMU and the Environment Ministry (MADES). There are no final products on this indicator. To access the supporting documents, click on the following link: | 6
PCA local implementing partner ID
Results indicator | 1.2.1 Number of new functioning meteorological stations in the Paraguayan Chaco | 0 | 0 | Terms of reference for the assembly of the stations and institutional agreements for the operation and maintenance of the weather stations have been drawn up and put for consideration. The georeferencing and validation of the potential locations of the stations in the field along in coordination with DMH have been put in place. Please refer to the following link: | 3
Meteorological stations
Results indicator | 1.2.2 Number of meteorological reports shared with farmers, herders and indigenous communities | 0 | 0 | The completion of these indicators depends on the completion of 1.2.1 new functioning meteorological stations in the Paraguayan Chaco. Once this indicator is achieved the reports will be shared by zones and farmers, herders and indigenous communities will have access to more specific qualitative information regarding temperature and rain in their communities. | 156
Results indicator | 1.3 Existence of a comprehensive and strategic study on the impacts of climate change on plants and animals used as food source. | 0 | 0 | Currently, the PMU is developing a call for expressions of interest to local NGOs for the elaboration of the study on the impacts of climate change on plants and animals used as food sources as part of the vulnerability assessments. | 1
Call for expressions of interest
Results indicator | 1.4 Existence of a study on the local ecology, management and nutritional components of Algarrobo and Viñal (Prosopis spp.) | 0 | 0 | The local implementing partner will deliver the study on Algarrobo and Viñal (Prosopis spp. and Prosopis ruscifolia) as part of the studies included in the vulnerability assessments. Intermediate products of the vulnerability assessment as well as the remaining studies are undergoing revision by the PMU and the Environment Ministry (MADES). There are no final products on this indicator. | 1
Intermediate products aproved
Results indicator | 1.5 Existence of a comprehensive and strategic study on local traditional practices that contribute to climate resilience | 0 | 0 | The local implementing partner will deliver the study on local traditional practices that contribute to climate resilience as part of the studies included in the vulnerability assessments. Intermediate products of the vulnerability assessment as well as the remaining studies are undergoing revision by the PMU and the Environment Ministry (MADES). There are no final products on this indicator. | 1
Intermediate products aproved
Results indicator | 1.6 Existence or specific protocols for the implementation of good practices in forest management and agriculture on farming and indigenous people’s communities | 0 | 0 | Currently, the PMU is developing a call for expressions of interest from local NGOs for the elaboration of the protocols for the implementation of good practices in forest management and agriculture in farming and indigenous people’s communities. The completion of this indicator also depends on Component I, and the results provided by the vulnerability assessments. There are no final products on this indicator.
Call for expressions of interest
Results indicator | 1.7 Existence of a comprehensive and strategic study on incentives for the adoption of climate-resilient agricultural practices in El Chaco region. | 0 | 0 | The PMU is planning to hire a consultant to analyze the legal framework in Paraguay to conclude on incentives for the adoption of climate-resilient agricultural practices in the El Chaco region. | 1
Results indicator | 1.8 Number of general vulnerability and impact assessments | 0 | 0 | In previously reported periods, the vulnerability assessment methodology was developed. This methodology was a starting point for the vulnerability assessments conducted at the moment. Up to date, the local implementing partner is conducting the studies that are intermediate products for the vulnerability assessments. Intermediate products of the vulnerability assessment as well as the remaining studies are undergoing revision by the PMU and the Environment Ministry (MADES). There are no final products on this indicator. | 6
PCA local implementing partner ID
Intermediate products aproved
Outcome indicator | 2. Number of males and females benefiting from the adoption of diversified, climate resilient livelihood options | 0 | 0 | The technical studies are developing a baseline including the number of beneficiaries per community. Nevertheless, at the time of reporting, there is no official number of beneficiaries in the communities that were recipients of pilot adaptation measures such as water tanks and support to their livelihoods. | 80% of local stakeholders identified in the baseline study (local officials, farmers, herders and indigenous people) benefit from the adoption of diversified, climate resilient livelihood options by the end of the project.
Outcome indicator | 2. Average increase in annual cash income among target beneficiaries. | 0 | 0 | The technical studies are developing a baseline for the project. Nevertheless, there is no official data of the annual cash income of the beneficiaries to report. This information will be generated during project implementation. | An average increase in annual cash income of 30%
Outcome indicator | 2. Increase in food availability given the existing and projected climate change with support from the project. (tons/year) | 0 | 0 | The technical studies are developing a baseline for the project. Nevertheless, there is no official data of the food availability of the beneficiaries to report. This information will be generated during project implementation. | Average increase of 60% in food availability (tons/year)
Results indicator | 2.1 Number of integrated adaptation community plans | 0 | 0 | The PMU is developing a call for expressions of interest to local NGOs for the elaboration of the protocols for the implementation of integrated adaptation community plans. The completion of this indicator also depends on Component I, and the results provided by the vulnerability assessments. There are no final products on this indicator. | 6
Call for expressions of interest
Results indicator | 2.2 Existence of adaptation measures being implemented on forest conservation, agriculture, water, regulatory framework and skills in the ten selected communities Number of critical areas with increased resilience | 0 | 0 | 18 EbA demonstration units were implemented in ten communities. These units were agreed upon with the communities and currently serve as “pilots” for the future concrete measures once the adaptation plans are finished. These units are focused on: a) improving food security through beekeeping (Cacique Sapo and Jasyendy communities) b) improving water availability (Pozo Hondo, General Díaz, Campo Loa, San Carlos, María Auxiliadora, Toro Pampa and Sierra León communities). c) Cattle ranching and agroecological practices (Karcha Bahlut and Puerto Diana communities). More recently, the PMU has been planning the second round of pilots as well as the future concrete adaptation measures to be implemented next semester of 2022. | 10
Demonstration / pilot units agreements and records
Field missions reports
Results indicator | 2.2.1 Number of trained local stakeholders | 0 | 177 | Twelve training workshops on EbA concepts were held with the attendance of 177 representatives of communities: Campo Loa, Cacique Sapo, General Díaz, Pozo Hondo, Jasyendy, and Sierra León, Karcha Balhut, San Carlos, María Auxiliadora and Toro Pampa. A total of 63 women and 114 men have attended these training workshops. | 800
EbA training workshops
Results indicator | 2.2.2 Number of ha of forest conservation/restoration areas created with the support of the project | 0 | 0 | No progress was expected in this period | 10
Results indicator | 2.2.3.1 Number of additional hectares applying the agroecological practices promoted by the project | 0 | 0 | No progress was expected in this period | 50%
Results indicator | 2.2.3.2 Percentage of increased honey produced by beneficiaries of the project | 0 | 0 | The local technicians are expected to collect information about the current honey production of beneficiary communities. Nevertheless, the project started to provide beneficiaries with supplies and equipment. This was a request of beneficiaries of Cacique Sapo and Jasyendy communities, both indigenous communities, that already were beneficiaries of an INDI project but lacked some supplies. The PMU agreed to provide lacking equipment and supplies to support the current honey production. The equipment included honey super warmer, solar beeswax extractors as well as bee suits, hives, and queen excluders among others. | 30%
Results indicator | 2.2.4 Number of water harvesting, storage and distribution systems constructed/repared by the project | 4 | 0 | 18 EbA demonstration units were implemented in ten communities. These units were agreed upon with the communities and currently serve as “pilots” for the future concrete measures once the adaptation plans are finished. These units are focused on improving water availability (Pozo Hondo, General Díaz, Campo Loa, San Carlos, María Auxiliadora, Toro Pampa and Sierra León communities). Additionally to this, the PMU has supported the distribution system of drinking water through deep wells in the indigenous community of Puerto Diana. This was besides the pilot measure requested by the community that consisted of the purchase of a small batch of cattle. The community requested plumbing supplies that were provided by the project in March 2022. | 100% of population with at least 1 water harvesting, storage and distribution infrastructure constructed/repared
Pilot unit Cacique Sapo food security
Pilot unit Jasyendy food security
Pilot unit Jasyendi livelihoods
Pilot unit Cacique Sapo livelihoods
Pilot unit Pozo Hondo water availability
Pilot unit General Díaz water availability
Pilot unit Campo Loa water availability
Pilot unit San Carlos water availability
Pilot unit Toro Pampa water availability
Pilot unit Maria Auxiliadora water availability
Pilot unit Puerto Diana livelihoods
Outcome indicator | Number of assessments and strategic recommendations related to climate change adaptation developed to support environmental licensing processes | 0 | 0 | No progress was expected in this period. | Integration of climate change adaptation, including priority actions and strategic options, into at least two departmental and/or district sustainable development plans.
Outcome indicator | Number of local development plans, strategies and processes that integrate adaptation to climate change concerns. | 0 | 0 | No progress was expected in this period. | Integration of climate change adaptation, including strategic recommendations, into at least five assessments developed to support environmental licensing processes.
Results indicator | 3.1 Number of SEAM staff trained (by gender) | 0 | 0 | No progress was expected in this period | 120
Results indicator | 3.2 Number of relevant stakeholders trained (by gender) | 0 | 0 | No progress was expected in this period | 160
EbA training workshops
Results indicator | 3.3 Number of lessons learned documents prepared by the project | 0 | 0 | No progress was expected in this period | 10

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | PRY/MIE/Food/2012/1
Implementing Entity | UNITED NATIONS ENVIRONMENT PROGRAMME
Type of implementing entity | MIE
Country | PARAGUAY
Region | Latin America and Caribbean
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 6000 | 6000 | 0 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 100% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 0 | Drought | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 0% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  |  | Other | Local | 1: No plans conducted or updated | 1 | Other | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Food security |  | Total | 280 | Food security | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 280 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Food security | 2: Low capacity | Public | Local | Food security | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Food security |  | 100% |  | Food security
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 800 | 50% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 1: Aware of neither |  | 0 | 40% to 60% | 5: Fully aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Regional |  | 16 | Technical guidelines | Sub-national
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | National | 1: Non responsive (Lacks all elements ) |  | Food security | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Multi-sector | 9 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | water areas | 5: Very effective |  | Multi-sector | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 10 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 10 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 10 | ha rehabilitated | 1: Ineffective | Forests | 10 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 10 | ha rehabilitated | 1: Ineffective | Forests | 10 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 816 | 10% | 5: Very high improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 816 | 10% | From 0 to 0.5% | Agriculture | 816 | 10% | From 40% to 50% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Water management | Irrigation system | 9 | Physical capital | Multi-sector | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 816 | other |  | 50 | 816 | other |  | 200
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Other | Regional | Other policy | 6 | Other | Regional | other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 6 | 5: Fully enforced (All elements implemented) |  | 5: Very effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Subnational | Innovation replicated |  | Food Security | Community | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices | 1: Ineffective | 10 | Food Security | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 10 | Innovative practice |  | 4: Effective
Note on K21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We do not have a number of indirect beneficiaries. Since communitarian measures are to all community, the direct number includes all community members when communitarian adaptation measures have been taken,
Note on J23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We do not have an exact number of young people. We used the birth rate in the region to estimate that a minimun of 30% of beneficiaries are children or youth.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | -The signing of a collaboration agreement (PCA) with a local partner organization has meant faster procurement processes and reduced costs. This PCA was a response to the significant administrative difficulties at the beginning of the implementation -The perception of the project is generally considered positive by local stakeholders. This was shown in the past by the intervention of the mentioned Congresswoman in response to the possible closure of project activities. The political implication of this intervention gave the project support from MADES to continue as it planned. -On the other hand, the technical team perceives a general lack of interest coming from community leaders and beneficiaries in technical studies and, in contrast, high interest in the concrete adaptation measures of the project. The receptivity of the communities has been also affected by the suspension of activities during the implementation and by the limitations of sanitary restrictions in the face of the Covid-19 pandemic. -The implementation of the EbA demonstration units has been a starting point for the concrete adaptation measures to be implemented after the Component I information is available.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The project has suffered significant delays since the beginning. The administrative arrangements for implementation at the beginning of the project generated significant delays. -The limited presence of the project's technical team on the beneficiary communities was exacerbated by restrictive measures amid the covid-19 pandemic. This situation limited the number of workshops and probably the attendance to these workshops during 2020 and part of 2021. -The lack of adequate planning and communication on the part of the project coordination during previous years created delays and administrative issues that persist until today. -The difficulties involved in accessing the beneficiary communities due to weather conditions represent a difficulty that can be overcome with good planning and communication with the community leaders. In the reporting period, the need to improve the planning and monitorin of the project has been identified. The necessary adjustment measures to improve these aspects are being incorporated into the project.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Although there were adjustments in the original project document, given the time elapsed between its original conception in 2011 and its effective implementation in 2019, no change of objectives in comparison with the current document was found. -An adjustment was made in the intervention area of the community ​​of Bahia Negra, for which it has been agreed with the Municipality of Bahía Negra to include the communities of Sierra León, Karcha Bahlut and the fishermen from the indigenous community of Puerto Diana. -The execution of technical studies required in Component 1 by a local implementing partner differs from the original budget in which the hiring processes were thought to be done by the PMU. -For the implementation of the activities of Component II, a more continuous presence of the technical team in the communities is proposed, which would be achieved by developing community plans for adaptation to climate change and identifying in a participatory way, the adaptation based on ecosystems measures to be implemented in each community.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Although the presence in the communities has not been continuous, the PMU team has taken all possible steps to consider the environmental and social safeguards (ESS) to avoid and minimize negative impacts on beneficiaries. First, the project designed its safeguards based on the risks identified in the project proposal. During implementation, ESS has been considered in the field and for procurement processes. Regarding beneficiary communities, the project targets five indigenous communities (Karcha bahlut, Puerto Diana, Cacique Sapo, Jasyendy and Campo Loa) from three different people (Ishir, Nivaclé and Western Guaraní) with whom the protocol of prior, free and informed consent consultation (FPIC) has been applied satisfactorily. Regarding component 1, the PMU has followed closely the work done by the local implementing partner and requested the hiring of an indigenous peoples specialist as well as a gender specialist to guarantee the ESS are applied during fieldwork. Regarding component 2, the implementation of the EbA pilot units has been based on the participation of the people of each community and consensual agreements between the parties. These agreements seek to ensure the relevance of the interventions and that the priorities of communities are being addressed by the project. An approach of equitable participation between men and women under equal conditions is also sought in project activities.
How have gender been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project's trainings are designed to encourage the participation of men and women on an equal basis. An important lesson that is being identified in the project is the participation of women in the management of water in their families. It has been seen that most of the communities targeted by the project have difficulties in accessing water supplies and depend on few reservoirs to harvest rainwater and on the assistance of local governments (to provide water). Women and children spend a large part of their time carrying water to their homes, which compromises other productive activities. Based on this context, the project has seen the great relevance of interventions to improve the availability and distribution of water in the communities. They will enable a significant change in the use of time for women, with more possibilities to dedicate time to other productive activities. Similarly, access to safe drinking water is expected to improve food security.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No