## Overview
Project Performance Report (PPR2)*
* Refers to both projects and programs
Period of Report (Dates) |  | 11/04/2020 al 11/04/2021
| Project Title: | Ecosystem-based Approaches for Reducing the Vulnerability of Food Security to the Impacts of Climate Change in the Chaco Region of Paraguay
vulnerabilidad de la seguridad alimentaria a los efectos del cambio climático en la región del
Chaco en Paraguay
| Project Summary: | The goal of this project is to reduce the vulnerability of the population (selected family agriculture producers and indigenous communities) of the Chaco Region of Paraguay to the impacts of climate change on food security. In order to do so, the project plans to address the main barriers for adaptation in the selected region. Specifically, the project would seek to i) improve information and knowledge for climate resilience; ii) implement concrete cost-effective on-the-ground adaptation measures; and iii) strengthen the institutional capacities to adequately address climate change adaptation issues. The project would be organized accordingly in three components: i) Knowledge management on vulnerability and climate change resiliency improved; ii) adaptive capacity in rural areas of greatest vulnerability strengthened through concrete agro-ecosystem based adaptation measures; and iii) capacity development and awareness to upscale effective implementation of adaptation measures at the national and local levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PRY/MIE/Food/2012/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Environment Programme- UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementation Agency | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Paraguay | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is implemented in the Western region of Paraguay, known as Chaco. Intervention zones include the communities of General Diaz, Pozo Hondo and the Campo Loa indigenous community in the district of Mariscal Estigarribia in the Department of Boquerón. Other areas of intervention are the communities of Toro Pampa, San Carlos and Maria Auxiliadora in the District of Fuerte Olimpo, and the fishing communities of Bahia Negra, the indigenous community of Karcha Balut and the Sierra León in the District of Bahia Negra, both districts in the Department of Alto Paraguay. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-27
IE-AFB Agreement Signature Date: |  | 2017-06-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-04-11 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2021-07-31
2023-12-31
Original Completion Date:
Revised Completion Date after approval |  | 2024-04-11
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each. | Cyprus
Czech Republic
List the Website address (URL) of project |  | Under construction | Democratic People's Republic of Korea
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Marta Moneo - Programme Officer / Climate Change Unit /UNEP | Dominican Republic
| Email: | marta.moneo@un.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ulises Lovera Gaona | Equatoral Guinea
| Email: | uliseslovera@hotmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Piedad Martin - Acting Regional Director Latin America and the Caribbean Office (UN Environment) | Fiji
| Email: | piedad.martin@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Gustavo Mañez - Climate Change Coordinator, Latin America and the Caribbean Office (UNEP) | Georgia
| Email: | gustavo.manez@un.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | María Carolina Chiappara - Fund Management Officer, Latin America and the Caribbean Office (UN Environment) | Grenada
| Email: | carolina.chiappara@un.org | Guatemala
| Date: |  | Guinea
Guinea Bissau
Guyana
Haiti
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 04/30/2020 |  |  |  | Financial information PPR 2: cumulative from project start to 04/30/2021 | [6 empty] | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS | [6 empty] | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [6 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 04/30/2020 | 155161 |  |  | Estimated cumulative total disbursement as of 04/30/2021 | 279405 | [5 empty] | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Total Disbursements as of April 30, 2020: $155,161 Total Committed as of April 30, 2020: $178,210 Total expenditures as of April 30, 2020: $333,371 |  |  | Add any comments on AF Grant Funds. (word limit=200) | Total Disbursements as of April 30, 2021: $279,405* Total Committed as of April 30, 2021: $511,361* Total expenditures as of April 30, 2021: $790,766 *89,631 USD of the "total committed" budget have been executed at the date of the PPR, making a total of 369,036 USD executed and 421,730 USD committed. This change is not reflected in this report because it is not yet displayed in the financial administrative system of UNEP | [5 empty] | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | [6 empty] | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant | [6 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA | [6 empty] | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public | 9514.2 |  |  | Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public | 26890
| Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 0 |  |  | Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 235.77
| Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 4439.71 |  |  | Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 5528.65
| Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 0 |  |  | Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 235.96
| Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 0 |  |  | Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 9514.2
| Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches | 4439.71 |  |  | Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches | 5940.14
| Output 3.1. Training plan for MADES, associated institutions at the national level especially the DNCC (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of climate compatible development and prevention and risk management in all sectors. | 0 |  |  | Output 3.1. Training plan for MADES, associated institutions at the national level especially the DNCC (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of climate compatible development and prevention and risk management in all sectors. | 0
| Output 3.2. The lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels. | 0 |  |  | Output 3.2. The lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels. | 0
| Project Management Costs | 136767.21 |  |  | Project Management Costs | 231060.37
| TOTAL | 155160.83 |  |  | TOTAL | 279405.09 | [5 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE | [6 empty] | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  |  |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Committed expenditure |  |  |  | Committed expenditure
| Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public. | 18456 | September 2020 |  | Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public. | 249296.58 | December 21
| Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 210 | July 2020 |  | Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 82080 | December 21
| Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 1019.2 | July 2020 |  | Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 0
| Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 210 | July 2020 |  | Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 0
| Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 9420 | October 2020 |  | Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 0
| Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches. | 19263.2 | March 2021 |  | Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches. | 94995 | December 21
| Project Management Costs: Committed Contract service - Drivers | 17174 | May 2021 |  | Project Management Costs: Committed Contract service - Drivers | 6074.36 | May 2021
| Project Management Costs: Travel related services/ vehicle/Personnel Staff | 112458 | December 2021 |  | Project Management Costs: vehicle/Personnel Staff | 78915 | April 2022
| Total Committed as of April 30, 2020 | 178210.4 |  |  | Total Committed as of April 30, 2021 | 511360.94
[5 empty] | Planned expenditure schedule | PROJECTED COST | Est. Completion Date | Execution Modality
[8 empty] | UNEP direct exec. | Local partner execution PCA I | Local Partner execution PCA II
[5 empty] | Output 1.1 Studies for the identification of best adaptation practices: Detailed mapping of ecosystems, including agro-ecological zones, water resources, forest and other ecosystems (1.1) | 78500 | November 21 | 9500 | 69000 | -
[5 empty] | Output 1.1 Studies for the identification of bet adaptation practices: Study of the ecology, management and nutritional components of algarrobo (Prosopis spp) (1.4) | 74931 | November 21 | - | 74931 | -
[5 empty] | Output 1.1 Studies for the identification of best adaptation practices: Research on traditional practices that contribute to climate resilience (1.5) | 93000 | November 21 | - | 93000 | -
[5 empty] | Output 1.1 Studies for the identification of best adaptation practices: Elaboration of an analysis of incentives and disincentives for the adoption of climate-resilient agricultural practices in the Chaco region (1.7). | 20000 | November 21 | - | 20000 | -
[5 empty] | Output 1.2 Climate change vulnerability assessments to inform decision making and guide adaptation planning developed and disseminated with decision makers, stakeholders and the general public. | 70868 | December 21 | - | 70868 | -
[5 empty] | Output 1.3. The protocol for the implementation of good practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral livestock in rural and indigenous communities, is prepared and made available to subnational governments and members. community to inform decision-making (specialized chapters by topic). | 280001 | December 21 | - | 252761 | 27240
[5 empty] | Output 1.4 New meteorological stations are installed and the necessary studies are prepared to carry out an agroclimatic risk assessment to inform decision-making by community members and sub-national governments: instalation of 5 meteorological stations | 125000 | October 21 | - | 125000 | -
[5 empty] | Output 1.4 New meteorological stations are installed and the necessary studies are prepared to carry out an agroclimatic risk assessment to inform decision-making by community members and sub-national governments: Evaluation of the vulnerability to climate change of specific plants and animals used as a food source. | 151983 | November 21 | - | 151983 | -
[5 empty] | Output 2.1 Development of adaptation community plans with ecosystem-based approach | 100000 | April 22 | - | 100000 | -
[5 empty] | Output 2.2 Implementation of adaptation community plans (technical assistance and inputs to implement concret adaptation measures favoring an ecosystem-based approach) | 463294 | April 22 | - | 12000 | 451294
[5 empty] | Output 3.1 Training plan for MADES and partner agencies at national level on mainstreaming climate compatible development across sectors. | 71740 | April 22 | 34740 | - | 37000
[5 empty] | Output 3.2 Local level training plan for partner agencies at local level (including but limited to departmental and municipal governments) | 90000 | April 22 | - | - | 90000
[5 empty] | Output 3.3 Identification, systematization and exchange of lessons learned of the project | 61090 | April 22 | 56590 | 4500 | -
[5 empty] | Project Management Costs | 242199 | April 22 | 162972 | 30700 | 48527
[5 empty] | Total Planned expenditures schedule | 1922606 |  | 263802 | 1004743 | 654061 |  | TOTAL | #REF! |  |  | TOTAL | #REF! |  |  | TOTAL | #REF!
[11 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[11 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[11 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[11 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on G31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vero, favor completar las fechas estimadas.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Polítical: Institutions do not prioritize this project | High | The project responds to national priorities. The project has started a training process for community leaders and referents that contribute to their empowerment on the actions of the project. Constant communication has also been maintained with technicians and authorities from local institutions on the planning, implementation and monitoring of the project activities. The project has been declared of national interest by the National Congress and the great interest of local governments has been verified through their support. Revision Dec21: the poor/lack of communication between the project executing parties (UNEP-MADES) almost led to the cancellation of the project. This situation generated significant delays in the implementation of the project. However, a coordinated action led to the reactivation of the project, after a joint effort done by both parties to identiy and put in place new communication channels and execution tools.
Institutional: The lack of coordination, collaboration and adequate cooperation between executing agencies generates delays in the project´s implementation. | High | The operational agreements between the executing partners and the agencies have been described in detail with the necessary definition of roles and responsibilities. Evaluations have been conducted on the fulfillment of these roles and functions, taking the necessary adjustment measures towards the adequate achievement of the objectives and results of the project. Work has been done to improve communication, planning and coordination of project activities. A collaboration agreement has been established with a local partner to speed up the execution and payments. The Steering Committee and communication between the implementing and executing agency (UNEP) and the government counterparts were strengthened. Work channels were established through UN network agencies in the country (UNDP). Revision Dec21: Considering that the communication between the project management unit (PMU) and the two executing instances (UNEP / ROLAC and DNCC / MADES) was centralized in the coordination of the project, it has been decided to strengthen the PMU team through the incorporation of more people who support the information, planning and coordination work between the parties, due to the size and challenges that the project represent
Institutional: Frequent staff rotation at local implementing agencies may affect the availability of qualified personnel. | Low | In the reporting period, no major effects have been identified in terms of staff turnover and lack of availability.
Institucional: Lack of interest and participation of key actors and target groups, along with conflicts/differences between actors/groups may weaken and delay the implementation of activities | Medium | Although the project has not had a continuous and regular presence in the communities, a participatory approach has been maintained in all the actions of the project. Communication between the project management unit and the different stakeholders involved has been strengthened using all available means. During the second year of implementation there were many difficulties in the participation of local communities due to the Covid-19 pandemic. There have been attempts to maintain frequent contact and visitations to speed up the implementation of activities.
Environmental: Climatic variability and changes, including extreme weather events, are greater than projected by the studies. | Low | Although the access to the communities (isolated from the urban centers of reference and without roads all year round), is entirely subject to the climatic conditions (frequency and intensity of rains); In the period of this report, there have been no very aggressive or recurring events that have significantly compromised the implementation of the activities in the communities. In this regard, schedules have been adjusted in a timely manner based on solid weather forecasts and local road information platforms.
Financial: The use of financial resources involves many levels of authorizations and delays the execution of activities. | Medium | Improvements have been perceived in the technical implementation of the project linked to the availability and agility of the financial flow. Acknowledging this difficulty, alternative mechanisms have been sought for the making funds available in a more efficient way for the technical execution of the project. This has been achieved through the outsourcing of the administration of the funds through UN agencies in the country and a local partner (Project Cooperation Agreement-PCA). To access the PCA_ID Agreement (local partner) click on the following link: Revision Dec21: in addition to these arrangements and directly related to the flaws in communication, planning, and coordination of the project, reinforcing the team of the project PMU has been emphasized, incorporating more high-profile people suited to a project of this size. It is expected that this strengthened team will be able to carry out more comprehensive planning of the entire project with a good forecast of the necessary funds to implement as per time frames. It is also expected to improve the dynamics of project implementation through the execution of a greater volume of activities in the territory, by operating through several implementing tools at the same time (agreements with local partners).
AcuerdoPCA
Financial: The use of financial resources is not transparent. | Low | The implementation of the project is carried out following all the principles of transparency and administrative procedures of UNEP, as well as in full compliance with all current national legislation in Paraguay.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Pandemic Risks (COVID 19) | Medium | All government recommendations and sanitary regulations (laws, decrees and resolutions) were followed. Through the project, the provision of all protective equipment and supplies has been guaranteed, both for the project's technical team and for the beneficiaries of the communities.
Other Environmental Risks: • Weather conditions prevent access to intervention areas in planned time. • Road conditions prevent reaching intervention areas with the necessary equipment for the planned activities. | Medium | The project's technical team constantly monitors the weather forecast and the Chaco road information platforms. Planning has been carried out based on this information and eventually, appropriate adjustments in the itineraries enroute were made.
Other Political Risks • Public institutions of the central government or sub-national governments do not support (or cease to support) the implementation of the project. • Changes in the government cause delays in empowerment to incorporate EbA in its public management. | Medium | The project works in coordination with public institutions at the 3 levels. Regular communication is maintained with all stakeholders and a participatory planning of the project activities. Several training activities are carried out with the different stakeholders involved to improve knowledge on climate change and ecosystem-based adaptation. Revision Dec21: communication has been central during the stages of the project where there was uncertainty about its continuity. Several means, including direct communications (meetings with local authorities and technicians) have been used to effectively communicate with stakeholders. Another aspect to highlight has been the open communication with community leaders and referents about the difficulties in implementing the project. Likewise, it is planned to follow the same strategy with the new municipal authorities elected at the end of 2021.
Other Technical Risks • There are not enough technicians at the local level sufficiently trained in the EbA approach to work with beneficiaries. | Low | No significant risk has been posed on the project during the reporting period.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting period, risks were identified in the implementation of the project, thus, the corresponding mitigation measures detailed in the preceding section have been implemented. The most significant risk has been the restrictive effects and protection measures against the Covid-19 pandemic, which have meant taking all the health protection measures, rethinking and adjusting the planning of community activities mainly. Many activities have been carried out virtually within the technical team of the project and along with stakeholders. These measures have made it possible to continue implementing the project (more slowly but not stopping). Revision Dec21: another main risk identified for the proper implementation of the project has been poor communication, lack of planning due to the size of the project and, in consecuence, adequate coordination and execution, which resulted in restructuring and strengthening the PMU team, particularly concerning the tasks of planning and coordination, and in the technical area and presence in the territories. More open and informed work sessions have also been held between the PMU, DNCC / MADES, and UNEP / ROLAC so that there is a more positive flow of project information and it translates into a more agile execution of activities.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1] | Sí
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law | Yes | Yes | Regarding the activities included in component 2 (which includes the assembly of meteorological stations, reforestation and forest conservation, agroecological management measures [best agricultural practices] and water storage systems), there is a risk of insufficient stakeholder capacity for management of environmental and social issues in accordance with national legislation and AF principles. It includes Law No. 294/93 on Environmental Impact Assessment (EIA), Law No. 2/73 (Forestry Law) and Resolution 2242/06 by which the list of protected species of wildlife in danger of extinction is approved. | The legal framework concerning environmental and social issues in Paraguay, such as sustainable development, climate change, biodiversity, poverty reduction, human rights, was complied with, as well as with all the regulations related to this stage of the project, such as the Decree 1039/18 of Free and Informed Prior Consent Consultationt of the indigenous communities benefiting from the project. On the other hand, regarding the facilities of meteorological stations, the institutional agreements have been drawn up, which are pending the parties' signatures. | The indicators are in the process of being validated by UNEP
2 - Access and equity | Si | Si | Since the beneficiaries of this project are low-income people and are often excluded from the decision-making process, there could be a risk that these people have insufficient access to project resources. | The project is designed to increase the resilience of latinas communities and indigenous people in the Paraguayan Chaco to the impacts of climate change on food safety. Actions to support the continued provision of ecosystem services and the development of water infrastructure shall guarantee access to water and food, and shall reduce the vulnerability to the impacts of climate change. At the moment, specific studies provided for in component 1 are underway, such as; the Methodology for the vulnerability analysis, a Biodiversity study was started, the report is pending by the technical team of the Biodiversity Directorate of MADES. | The indicators are in the process of being validated by UNEP
3 – Marginalized and vulnerable Groups | Yes | Yes | There is a risk that these marginalized and vulnerable groups have insufficient access to the project activities, especially those of component 2.2 (the implementation of adaptation activities such as reforestation and forest conservation, agroecological management measures [best agricultural practices] and water storage and irrigation systems). Regarding the extension activities of the indigenous communities, the problem lies in the fact that these are close-knit ommunities and the technicians (outsiders) are not willingly accepted. | It is important to maintain the credibility of the project with beneficiaries and local authorities as well as to avoid making promises that cannot be kept. The measures to be implemented shall be reinforced according to the priorities elaborated with the central and local authorities, after the vulnerability study is finished. | The indicators are in the process of being validated by UNEP
4 – Human rights | Yes | Yes | There is a possibility that the access to the project´s resources is uneven to the different segments of the population. | The determination of the vulnerability, the base condition for estimating the interventions, will take into consideration all fundamental human rights. | The indicators are in the process of being validated by UNEP
5 – Gender equality and women’s empowerment | Yes | Yes | The risks related to gender equality and the empowerment of women could be: (i) Gender inequality limits the ability of vulnerable people to benefit from the opportunities provided by the project. (ii) Climate change means a disproportionate increase in the workload of women. | In order to determine the vulnerability of the population, gender issues will be especially considered, by incorporating studies with disaggregated data by sex and gender indicators, which will allow knowing the reality of women (indigenous and Latina) and valuing their contributions. On the other hand, work will be done regarding the need to strengthen the capacities of women and men according to their production lines in family farming, to improve their performance and increase the benefits of greater food production. Likewise, the exchange of experiences on adaptation to climate change among women leaders of the beneficiary communities will be promoted. | The indicators are in the process of being validated by UNEP
6 – Core labour rights | Yes | Yes | In both types of communities there are clearly defined divisions of labor between men and women. As indicated in the Gender Technical Note of Paraguay (IDB, 2014), rural women combine tasks that involve carrying water and firewood, buying supplies including food, and transporting their children throughout the entire year. Regarding component 2, the provision of agricultural production also poses a risk such as traffic accidents during transport. | As indicated in the PRODOC, with regard to the contributions of the project to the generation of benefits, in the first activities carried out in the communities, local labor was hired, thus avoiding discrimination of the workers and promoting equal opportunities for the latinos and indigenous communities of the Chaco. | The indicators are in the process of being validated by UNEP
7 – Indigenous peoples | Yes | Yes | Indigenous people have their own language or dialect, which differs from the official languages ​​of the country. | It should be noted that the project respects social diversity. Each cultural group and ethnicity will be carefully considered to help preserve and value knowledge, traditional practices and customs of each community. Special attention will be paid to diverse indigenous communities to ensure that all their rights and customs are respected, in that sense, the project ackgnowledges and encourages full respect for indigenous peoples and their human rights, their dignity, their cultural uniqueness, their autonomy, their identity and their aspirations, therefore, prior to the start of activities to be implemented in their communities, a free, prior and informed consent consultation (CPLI) was conducted with the beneficiary of indigenous communities. The activities were adapted to each linguistic and ethnic context. To access the documents of these consultations, click on the link: | The indicators are in the process of being validated by UNEP
CPLI workshop - Boqueron
CPLI workshop - Alto Paraguay
8 – Involuntary resettlement |  |  | No negative impacts have been identified
9 – Protection of natural habitats | Yes | Yes | Project activities seek to encourage practices that favor increased production and income per hectare in such a way as to reduce the need for tree felling, as well as maintaining and increasing the benefits of ecosystem services. However, there is minimal risk of the flora and fauna space being obstructed, in the context of infrastructure works such as weather stations. | As mentioned in PRODOC, the project activities seek to encourage practices that favor increased production and income per hectare in order to reduce the unsustainable use of natural resources of the ecosystems where communities are inserted. Specific interventions, such as weather stations, will be placed in areas without vegetation. | The indicators are in the process of being validated by UNEP
10 – Conservation of biological diversity | Yes | Yes | Algarrobo and the Prosopis spp are nitrogen-fixing trees that promote soil enrichment while providing shade and food (in the form of leaves and seed pods) for livestock. In accordance with the SEAM Resolution No. 2242/06, two of the Prosopis spp species are classified as "endangered species" due to the lack of data and reliable information about the population and its management, there is a risk of unsustainable management and use of endangered species. | The project will conduct studies to evaluate the characteristics of the different ecosystems and based on these it will develop adaptation plans and implement adaptation actions that ensure the continued provision of some of the critical supporting ecosystem services, provisioning, regulation and culture. Currently, we are working in close coordination with the Directorate for the Protection and Conservation of Biodiversity of MADES, the official counterpart of the project, who supports through a study of Biodiversity in one of the project's intervention locations. | The indicators are in the process of being validated by UNEP
11 – Climate change | Yes | Yes | Climate change poses a threat to the beneficiary communities of the project, specifically in agriculture and the production of food, water, ecosystems and other natural resources. Climate change can lead to negative consequences through gradual environmental alterations such as prolonged drought with respect to the variation in the rainfall regime, which ultimately delays the sowing season of crops, as well as the growth of pastures for breeding animals. | In the PRODOC and in the planning tools for the implementation of the Project, the activities of “Implementation of improvements in the use of efficient, collection, harvesting and storage of rainwater”, as well as “Extension services and access to inputs for agroecological production in agriculture and livestock, including agroforestry, beekeeping, community seed banks and silvopastoral management”, were included in Component 2 of the Project in order to generate greater empowerment by the beneficiaries, such as “demonstration unit to install / improve water harvesting in each community and / or EbA measure” in the project intervention areas. | The indicators are in the process of being validated by UNEP
12 – Pollution prevention and resource efficiency |  |  | No negative impacts have been identified
13 – Public health | Yes | Yes | The constant droughts will also affect the balance of both factors over time, weakening their food security. However, the project is expected to have a positive impact on food security. Access to drinking water: It should also be taken into account that, if the potable water sources become contaminated, the consumption of that water can cause diseases. Development of water-bourne diseases: The continuous presence of water in water storage systems could be the cause of water-bourne diseases such as malaria, amoebiasis, or typhoid fever. | Analysis of food and water provided by the project will be conducted in order to guarantee health conditions for the project beneficiaries. | The indicators are in the process of being validated by UNEP
14 – Physical and cultural heritage |  |  | No negative impacts have been identified
15 – Lands and soil conservation |  |  | No negative impacts have been identified
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | The project includes a technically robust Follow-up and Monitoring Plan, this shall ensure that the progress of the project and the results of its activities are closely tracked and adjustments are made when necessary for the project to achieve its results efficiently. In this sense, a Project Follow-up and Monitoring Manual was drawn up,which includes ESP Risks (in the process of validation) . To access the document, click on the following link:
Monitoring Manual
Have unanticipated ESP risks been identified during the reporting period? |  | So far no unexpected ESP risks have been identified. A continuous evaluation is expected when the Follow-up and Monitoring Manual is implemented, which shall be reported in the next PPR.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | If such risks arise, they shall be reported in the next PPR, as well as the measures implemented to mitigate them.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Safeguard risks were identified during the development phase of the project. During this period, a manual that shall allow systematic monitoring and mitigation of any situation in a timely and effective manner was drawn up. Said manual is in the process of validation by UNEP. To access the document, click on the following link:
Safeguards Manual
Have the implementation arrangements been effective during the reporting period? |  | The safeguards implementation arrangements, provided for in the manual, shall have greater force from the implementation of component 2
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The implementation of the planned Safeguards shall be promoted not only in every agreement, but also in consultancies and with all the local counterparts.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The effectiveness of the arrangements will be determined in the next stage of the project and will be reported in the next PPR.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | A grievances Manual was drawn up, the indicators were shared with the beneficiary communities in the EbA workshops, to access it, click on the following link:
Grievance Manual
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | An important grievance has been reported by the community of Pozo Hondo, where community leaders and referents have received verbal abuse and the threat of being excluded from the project activities by the previous project coordinator due to a confusion and poor communication about the operation of the community's water distribution system, which had been improved by the project (EbA demonstration unit implemented). Following the separation of the project coordinator, consultations were conducted with all the stakeholders involved and an informative and conciliation meeting was held between the parties. In this meeting, it was clarified that the actions of the previous coordinator were not in accordance with the principles of the United Nations and that one community cannot be excluded from being a beneficiary due to a situation of confusion or by the will of one (1) person. A record of the agreement reached and clarification of the facts have been drawn up between the community and those responsible for the project. Click on the following link to access report and minutes.
Field mission supporting documents
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | An initial gender assessment was conducted during the EbA workshop, as well as in the socialization of the indicators of the gender manual (in the process of validation). To access the document, click on the following link:
Gender Manual
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | At the moment they are considered as product indicators.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 3.1 Training plan, for MADES, associated institutions at the national level, especially the National Climate Change Committe (CNCC) (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of development compatible with climate and risk prevention and management in all sectors |  | Number of MADES personnel trained in integrating a compatible development with the climate and EbA in all sectors (by gender) | 0 | 40 | No progress was expected in this period
|  | Number of staff from partner agencies and the general public trained to incorporate climate compatible development and EbA in all sectors (valuing gender roles) | 0 | 200 | No progress was expected in this period
|  | Number of trained people who acknowledge having a new understanding or having acquired skills about EbA (by gender) | 0 | 150 | 177 people (63 women and 114 men) have participated in a training workshop to introduce the concepts of Adaptation based on Ecosystems. To access images of the workshops by community, access the following link:
EbA workshop - women
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UNEP has a comprehensive policy and strategy on gender equality and the environment that establishes the use of a gender marker. Essentially, the gender marker serves as a monitoring tool that ensures that at the point of project development and implementation, gender perspectives are integrated into all stages, including budgeting. The gender marker has a four-point scale against which the project is evaluated. Each project is required to meet a rating of 2a, which means that gender is fully integrated and the project will make a significant contribution to achieving gender equality. In the event that a project does not meet grade 2a, the project officer is required to review the project and ensure that gender perspectives are fully incorporated and then resubmit the project for review.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Although gender considerations are integrated into the Logical Framework, Work Plans and POAs, the effectiveness of the implementation cannot yet be verified, since component 1 only contemplates general studies, prior to intervention in the communities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5]
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5]
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | One of the first activities will be to establish a Baseline in the communities of the intervention areas where it is already contemplated to identify capacity gaps that affect compliance with the GP during the project implementation period and in addition to addressing these gaps, they will be reported in the next PPR.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | The proposal of a grievances manual was socialised with the beneficiaries through said mechanism, they will be able to report their concerns and / or complaints (such manual has already been drawn up and is in the process of being validated)
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievances have been reported.
Note on E39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: añadir link a mecanismo de quejas
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: Sub-national governments integrate information on climate change adaptation (CCA), highlighting vulnerability and resilience, into planning instruments to improve decision-making and implement sectoral and multisectoral measures. |  | Outcome 1 | The vulnerability of the local population is determined based on technical criteria and statistical data available in the country; as well as technical studies to justify recommendations for EbA measures, presented to authorities and the people in the project intervention areas. |  | During this period the methodology of the vulnerability assessment has been developed. This assessment will have the dual objective of identifying these vulnerabilities in a participatory way in the communities and strengthening the capacity in MADES to identify vulnerabilities and adaptation priorities in the Chaco region. Moreover, said assessment has been analyzed and validated in technical meetings with DNCC-MADES. A biodiversity study, which was conducted by the MADES Biodiversity Directorate (DGPCB) has been started but not yet completed. The on-ground work took place in October 2020 and the submission of the results obtained by MADES / DGPCB is awaited. On the other hand, calls for tender for consultancies that shall contribute to the vulnerability assessment were made. In addition, 2 calls for tender were made, firstly, for the study of biodiversity in Boquerón and Alto Paraguay, which has not concluded due to lack of clarity in the only proposals received and secondly, for the baseline study, which has not yet been completed due to lack of bidders. Lastly, ToRs have been drawn up for the thematic studies. | Unsatisfactory
| Outcome 2. Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  | Outcome 2 | Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  | Four EbA demonstration units were implemented in four communities in the department of Boquerón: 2 to improve food security (beekeeping) in Cacique Sapo and Jasyendy; and 2 to improve water availability in Pozo Hondo and Gral. Díaz. Another 13 EbA demonstration units to improve water availability are in the final implementation process: 9 in villages of the Campo Loa community and 4 in Latino communities of Alto Paraguay in Sierra León (in process), San Carlos, María Auxiliadora and Toro Pampa. More details in Project Indicators section. | Marginally Satisfactory
| Outcome 3. Beneficiaries, MADES staff, national partners (CMCC), sub-nationals and the general public trained to incorporate ACC and ABE in the planning processes of sustainable development. |  |  | No progress was expected in the reported period
[6 empty] | Overall Rating | Marginally Unsatisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Marta Moneo
| Email: | marta.moneo@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The COVID 19 pandemic has imposed substantive restrictions in terms of project execution in the intervention areas that have resulted in delays in the implementation rate of the project along with identified coordination weaknesses. Several arrangements were put in place in this reporting period to accelerate the execution rate and funds were made available at the country level mainly through two mechanisms: (a) UN network agency (UNDP) and (b) through a local partner (ID). These arrangements have clearly facilitated the flow of funds and the capacity to respond quickly to project needs. It is the view of the Implementing Entity that this local partner could be further engaged in technical aspects of the project as they have solid expertise on vulnerability assessments, understanding of the Chaco region and ecosystem-based adaptation initiatives. In addition, the size of this project would probably benefit from the engagement of additional local partners to ensure the simultaneous implementation of activities under the different components. The magnitude of this project made it evident, as well, that the structure of the coordination team needs to be reinforced in order to incorporate technical capacity to strategically plan and supervise the different activities and technical assessments. This proposal was presented to MADES in the Steering Committe in december 2020. Additionally, more presence on the field was also identified as an urgent need to maintain a more constant and fluent engagement with pilot communities. Despite these challenges, during this reporting period, initial pilot EbA interventions have been implemented in most of the participating communities as a means to engage them in the project and communities have shown and communicated both to MADES and the coordination team, their interest in the project and their urgent need for support. The communication line with these communities is now clear and set for the continuation of the project. A methodology for vulnerability assessment has already been developed and agreed upon with MADES. The methodology is ready to be applied at the community level, but the assessment has not initiated yet. Again, the succesful development of these vulnerability assessments requires a technically strong coordination unit able to supervise and review this work. The technical and geographical scopes of the project have also made it clear that a stronger instutitional coordination mechanism is necessary such as a wider steering committee that includes representation from all key stakeholders and possibly technical committees that can ensure alignment with key ministries and local governments. This has also been raised with MADES through the Steering Committee. For the reasons stated above, the progress of this project is rated as marginally satisfactory for this period, but the consideration of the listed recommendations and the arrangements already established could easily increase the implementation rate in the coming period.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Sub-national governments integrate information on climate change adaptation (CCA), highlighting vulnerability and resilience, into planning instruments to improve decision-making and implement sectoral and multisectoral measures. |  | Outcome 1 | Vulnerability level of the determined local population, based on technical criteria and statistical data available in the country; as well as technical studies to justify recommendations for ABE measures, presented to authorities and the population in the project intervention areas. |  | The vulnerability studies are included in the local partner agreement (PCA) and the resources for their execution are available. To date, the consultancy for the vulnerability assessment methodology is in its final stages, which will serve as the foundation for the generation of knowledge products. Advanced products are shared and validated by DNCC. There are still no final products on results indicators. To access the products made by the Technical Advisor, enter the following link: | Unsatisfactory
Vulnerability Assessment Supporting Documents
| Outcome 2. Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  | Outcome 2 | Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  | There is a draft proposal for a community approach to implement actions identified in the community adaptation plans. There are EbA demonstration units implemented in 9 beneficiary communities. To access the document, enter the following link: | Marginally Satisfactory
Community of Campo Loa
| Outcome 3. Beneficiaries, MADES staff, national partners (CMCC), sub-nationals and the general public trained to incorporate ACC and ABE in the planning processes of sustainable development. |  |  | No progress was expected in the reported period
[6 empty] | Overall Rating | Marginally Unsatisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ulises Lovera
| Email: | ulises.lovera@mades.gov.py
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
In this reporting period not all the planned goals have been achieved because many activities could not be implemented due tothe restriction and sanitary measures adopted by the Ministry of Public Health and Social Welfare (MSPyBS) in the face of the pandemic of covid-19. On the other hand, there were flaws in planning, communication and coordination by the coordination of the Project Management Unit (PMU). There was no clarity on the actions and tasks to be implemented within the work team or participatory planning of the project activities, nor was there good communication on the administrative procedures to be applied in the execution of the demonstration units. Although the execution of the project has become quite dynamic through the signing of the PCA with a local partner organization that has channeled the project funds, an optimal pace of implementation was not reached due to coordination problems. On the other hand, the baseline studies to determine the vulnerability of food security to the effects of climate change were also unable to move forward as planned, since the call for tender process established by MADES involves many steps and delays the process. Moreover, not many technical bidders applied to conduct these studies. On the bright side, it is noticeable the dynamics that the availability of funds has given at the local level through the local partner (PCA), which has allowed the implementation of at least one demonstration unit in each beneficiary community of the project. Some have not been fully concluded as of the date due to the communication and coordination difficulties already mentioned. On the other hand, it can be said that the channeling of funds through the PCA can be improved through better communication, planning, monitoring and coordination of activities between the technical team and the other stakeholders involved. In this sense, a concrete proposal to incorporate to the team a specialist in planning, monitoring and evaluation, who supports and strengthens the work team in the implementation of the project activities, has been raised for consideration. Additionally, a proposal to expand of the cooperation agreement with the local partner, money-wise was drawn up, which will allow to have a longer execution horizon for the project. Work has also been done on a work proposal to have a greater presence of the project's technical team in the field to improve communication with the beneficiary communities and have a better definition of the actions to be carried out.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Indicador de Resultado | 1. Number of knowledge products developed and disseminated (including meteorological studies, evaluations, protocols and reports) | 0 | The vulnerability studies are included in the local partner agreement (PCA) and the resources for their execution are available. To date, the consultancy for the vulnerability assessment methodology is in its final stages, which will serve as foundation for the generation of knowledge products. Advanced products are shared and validated by DNCC. There are still no final products on results indicators. To access the supporting documents, click on the following link: | Subnational governments integrate information on climate change adaptation (CCA), emphasizing on vulnerability and resilience, into planning instruments to improve decision-making and implement sectoral and multisectoral measures.
1. Participative Methodology Proposal
2. Methodology Propososal based on Indicators
3. Supporting documents- methodology proposal
| 2. Number of sub-national governments and communities who own planning instruments that integrate CCA to shape the design and implementation of sectoral and multisectoral measures | 0 | No progress was expected in this period. There are still no final products on results indicators. However, studies were initiated to serve as inputs and provide scientific evidence for planning, community and local (sub-national governments) Climate Change Adaptation. To access document please click on the following:
Signed PCA
| 3. Increase in the number of meteorological stations provided by the project in the Chaco region | 0 | Terms of Reference have been developed for the assembly of the weather stations (1). The georeferencing and validation of the potential locations of the stations in the field in coordination with DMH have been put in place (2) Institutional agreements have been drawn up (3) There are still no final products on results indicators. To access the proposed institutional agreements, click on the following link:
1. Weather Stations Puchasing Documents
2. Weather Stations Mission Report
3. Agreement´s drafts
Indicador de Producto | 1. Number of studies conducted on (i) the impacts of climate change on plants and animals used as a food source, (ii) the local ecology, management and nutritional components of Algarrobo and Viñal; (iii) local traditional practices that contribute to climate resilience; (iv) incentives for the adoption of climate resistant agricultural practices in the Chaco region; and (v) detailed maps of the ecosystem (1 map for each of the selected communities) | 0 | The methodology for the vulnerability assessment is in its final stages, which has been analyzed and validated in technical meetings with DNCC-MADES (1 and 2). A biodiversity study was initiated by the MADES Biodiversity Directorate (DGPCB). The on-ground work took place in October 2020 and the submission of the results obtained by MADES / DGPCB is awaited (3). On the other hand, calls for tender were made for consultancies on thematic studies. The call for tender to hire a Technical Advisor was concluded (4). Additionally, 2 calls for tender were made, firstly for the study of biodiversity in Boquerón and Alto Paraguay, which has not concluded due to lack of clarity in the only proposals received and secondly, for the baseline study, which has not yet been completed due to lack of bidders (5). Finally, several thematic ToRs were drawn up and put for validation by DNCC and UNEP (6). To access the supporting documents, click on the link: | Studies to identify best adaptation practices developed and disseminated to decision makers, stakeholders and the general public. The studies will cover the following topics (i) the impacts of climate change on plants and animals used as a food source, (ii) the identification of plant genetic resources that contribute to feeding people in the intervention areas, with emphasis on Algarrobo and Viñal, through a detailed registry (iii) traditional local practices that contribute to climate resilience, (iv) incentives for the adoption of best agricultural and livestock practices, resistant to climate, and (v) detailed maps of ecosystems (1 map for each of the selected community).
1. Participative Methodology Proposal
2. Methodology Proposal based on Indicators
3. Study on Biodiversity in Gral. Diaz
4. Open call for technical advisor
5. Call for consultancy Biodiversity in Alto Paraguay and Boqueron and Baseline
6. Thematic studies ToRs
| 2. Number of communities in the Chaco region with detailed ecosystem maps (gis format) to inform decision-making | 0 | The mapping of the communities has resources assigned through the agreement with the local partner (PCA) and resources are available for its implementation. Terms of reference were drawn up. To access these documents click here.
Thematic studies ToRs
Indicador de Producto | 1. Number of communities integrating the results of vulnerability assessments, addressing the differentiated vulnerability status of women and men (respecting local customs), to inform decision-making | 0 | No progress was expected in this period | Climate change vulnerability assessments to inform decision-making and guide adaptation planning prepared and disseminated to decision makers, stakeholders and the general public.
Indicador de Producto | 1. Number of communities who own protocols for the implementation of best practices in forest management, hunting calendar, agro-ecological agriculture and small-scale livestock | 0 | No progress was expected in this period | The protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, is prepared and made available to sub-national governments and community members to inform decision-making (specialized chapters by topic).
Indicador de Producto | 1. Number of new weather stations installed in the Chaco Region of Paraguay to inform decision-making | 0 | Terms of reference for the assembly of the stations and institutional agreements for the operation and maintenance of the weather stations have been drawn up and put for consideration. The georeferencing and validation of the potential locations of the stations in the field along in coordination with DMH have been put in place. Please refer to the following link: | New meteorological stations are installed and the necessary studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.)
Weather Stations Puchasing Documents
| 2. Number of DMH weather bulletins adjusted with project station data, disseminated throughout the duration of the project to community members | 0 | The process of purchasing weather stations began. The resulting data shall contribute to the meteorological information that will be used in preparing the bulletins
Indicador de Resultado | 1. Percentage of assisted families that report increases (quality and/or quantity) in food production as a result of project interventions. | 0 | No progress was expected in this period | Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and food availability , with an emphasis on access to water.
| 2. Percentage of assisted families who report increases in access/ quantity/ quality of water consumed as a result of project interventions | 0 | No progress was expected in this period
| 3. Percentage of families in the community that benefit from adaptation measure with ecosystem-based approaches | 0 | No progress was expected in this period
Indicador de Producto | 1. Number of communities with adaptation plans to guide decision-making | 0 | There is a methodological proposal to address the community for the construction of community adaptation plans that must be agreed on and validated by MADES and UNEP. To access the document, click on the following link: | Community adaptation plans developed with community members and integrated into sub-national planning instruments to guide decision-making.
Adaptation plan proposal
| 2. Number of sub-national governments integrating community adaptation plans into planning instruments | 0 | No progress was expected in this period
| 3. At least 350 families in selected communities that have received the project´s support and participated in the development of community adaptation plans | 0 | There is a proposal for a community approach to implement actions identified in the community adaptation plans, which are currently under review.
Indicador de Producto | 1. Actions with an AbE focus implemented through adaptation measures materials prepared by the project, elaborated to guide the training of members of the selected communities, MADES staff, partners and the general public | 4 | Four AbE demonstration units were implemented in four communities in the department of Boquerón: 2 to improve food security (beekeeping) in Cacique Sapo (1) and Jasyendy (2); and 2 to improve water availability in Pozo Hondo (3) and Gral. Díaz (4). Another 13 AbE demonstration units to improve water availability are in the final implementation process: 9 in villages of the Campo Loa community (5) and 4 in Latino communities of Alto Paraguay in Sierra León (in process), San Carlos (5 ), María Auxiliadora (6) and Toro Pampa (7). | Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that favor ecosystem-based approaches.
1. EbA demonstration unit Cacique Sapo
2.EbA demonstration unit Jasyendy
3. EbA demonstration unit Pozo Hondo
4. EbA demonstration unit General Diaz
5. EbA demonstration unit Campo Loa
6. EbA demonstration unit San Carlos
7. EbA demonstration unit Toro Pampa
8. EbA demonstration unit Ma. Auxiliadora
| 2. Number of local families trained by the project to implement adaptation measures with ecosystem-based approaches, on income and self-consumption. | 177 | Twelve training workshops on ecosystem-based adaptation concepts were held with the participation of members of the 10 villages of the Campo Loa community, Cacique Sapo and Gral. Díaz, Pozo Hondo and Jasyendy (in Boqueron); and Sierra León, Karcha balhut, San Carlos, María Auxiliadora and Toro Pampa (in Alto Paraguay). 177 people (63 women and 114 men) have participated in this training workshop. To access the support documents, go to the following link:
EbA workshops
| 3. Number of local families who have access to inputs, defined as resources in kind, and technical assistance to improve food production through project activities | 11 | TwoAbE demonstration units were implemented in two communities in the department of Boquerón to improve food security (beekeeping) in Cacique Sapo and Jasyendy. They have directly benefited 11 families and 79 families indirectly. Enter the following link:
Food Security Improvement- EbA demonstration units
| 4. Number of people who have access to new collection system, storage and water distribution. | 141 | Two AbE demonstration units were concluded to improve water availability and have benefited 33 families in Gral. Díaz and 108 families in Pozo Hondo. Another 13 AbE demonstration units to improve water availability are in the final stage of implementation, 9 in villages of the Campo Loa community and 4 in Latino communities of Alto Paraguay (Sierra León, San Carlos, María Auxiliadora and Toro Pampa). These measures will be benefiting 755 families in these communities. To access the documents, enter the following link:
Water availability Improvement - EbA demonstration units
Indicador de Resultado | 1. Number of trained people who engage in the integration of AbE measures in development processes from their respective work areas | 0 | No progress was expected in this period | Beneficiaries, MADES staff, national partners (CMCC), sub-nationals and the general public trained to incorporate CCA (and ABE) in sustainable development planning processes.
Indicador de Producto | 1. Number of MADES staff trained in integrating climate compatible development and CCA in all sectors (by gender) | 0 | No progress was expected in this period | Training plan for MADES, associated institutions at the national level, especially the CNCC (ministries and agencies, including, MAG and INFONA, etc.), sub-national and the general public, on the integration of climate compatible development, prevention and risk management in all sectors.
| 2. Number of personnel from partner agencies and the general public trained to incorporate climate compatible development and CCA in all sectors (valuing gender roles) | 0 | No progress was expected in this period
| 3. Number of trained people who acknowledge having a new understanding or having acquired skills (by gender) on CCA and AbE | 0 | No progress was expected in this period
Indicador de Producto | 1. Number of lessons learned prepared by the project | 0 | No progress was expected in this period | Lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels
| 2. Number of families trained on lessons learned (at least one member of the family) | 0 | No progress was expected in this period
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: aqui añadir también la metodología de análisi de vulnarbilidad desarrollada
Note on G33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: aquí ya se han implementado algunas medidas para acceso a aguna. por favor, incluirlas aquí también
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: igual que arriba, no solo de agua, también las de apicultura
Note on G38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: poner aquí las medidas AbE y los talleres que se han hecho. Ya hay familizas beneficiadas directamente por el proyecto y a eso tenemos que referirnos aquí

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | PRY/MIE/Food/2012/1
Implementing Entity | UNITED NATIONS ENVIRONMENT PROGRAMME
Type of implementing entity | MIE
Country | PARAGUAY
Region | Latin America and Caribbean
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 83458 | 2450 | 81008 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 47.45% | 47.45% | 47.45% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 2450 | Drought | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 47.45% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  |  | Other | Local | 1: No plans conducted or updated | 1 | Other | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Food security |  | Total | 2450 | Food security | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 47.45% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 2450 | 47.45% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Food security | 2: Low capacity | Public | Local | Food security | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Food security |  | 75 |  | Food security
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 2450 | 47.45% | 1: Aware of neither |  | 2450 | 47.45% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 9 | 20% to 39% | 1: Aware of neither |  | 9 | 40% to 60% | 5: Fully aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Regional |  | 78 | Technical guidelines | Regional
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | National | 1: Non responsive (Lacks all elements ) |  | Food security | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Multi-sector | 9 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | water areas | 5: Very effective |  | Multi-sector | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 9 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 9 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 9 | ha rehabilitated | 1: Ineffective | Forests | 9 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 9 | ha rehabilitated | 1: Ineffective | Forests | 9 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 816 | 10% | 5: Very high improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 816 | 10% | From 0 to 0.5% | Agriculture | 816 | 10% | From 40% to 50% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Water management | Irrigation system | 9 | Physical capital | Multi-sector | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 816 | other |  | 50 | 816 | other |  | 200
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Other | Regional | Other policy | 9 | Other | Regional | other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 9 | 5: Fully enforced (All elements implemented) |  | 5: Very effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Subnational | Innovation replicated |  | Food Security | Community | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices | 1: Ineffective | 10 | Food Security | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 9 | Innovative practice |  | 4: Effective

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | At the beginning of the implementation there have been significant administrative difficulties; they were corrected through the mechanisms established for that purpose. The signing of a collaboration agreement (PCA) with an organization that manages a package of the project's activities has meant a significant leap in the agility of administrative processes. The receptivity of the communities has been very positive at the beginning of the project. However, since it was not possible to have a more continuous and direct contact with the beneficiary communities, this raised doubts about the execution of the project on the ground. This scarce presence in the communities has been mainly due to administrative difficulties at the beginning of the project and due to restrictive measures in the face of the covid-19 pandemic. Based on this, work has been done on an approach proposal that guarantees the project's technical team to have more permanent contact and communication with the communities. Communication with the authorities has been maintained virtually, however, doubts have also arisen about the implementation of the project in the times initially established. Regarding positive aspects, the implementation of the EbA demonstration units has shown the great difficulties that the communities have to ensure the water supply. The lack of water in the communities conditions all productive activities and women and children spend much of their time transporting water from the few community reservoirs.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The main difficulties have been in the operational execution and in the escarse presence of the project's technical team in the beneficiary communities. This has been due to the delay in administrative arrangements for the implementation and due to the restrictive measures that were established in the fight against covid-19. Another important element has been the lack of adequate planning and communication on the part of the project coordination, since a continuous and systematic execution of the project has not been planned. The difficulties involved in accessing the beneficiary communities due to weather conditions represent a difficulty that can be overcome with good planning and communication with the community leaders. In the reporting period , the need to improve the planning, monitoring and follow-up of the project has been identified. The necessary adjustment measures to improve these aspects are being incorporated into the project.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Although there were adjustments in the original project document, given the time elapsed between its original conception in 2011 until its effective implementation in 2019, no change of objectives in comparison with the current document was found. An adjustment was made in the intervention area of the commmunity ​​of Bahia Negra, for which it has been agreed with the Municipality of Bahía Negra to include the communities of Sierra León, Karcha Bahlut and the fishermen from the urban community of Puerto Diana . For the implementation of the activities of component 2, a more continuous presence of the technical team of the project in the communities is proposed, which would be achieved by developing community plans for adaptation to climate change and identifying in a participatory way, the adaptation based on ecosystems measures to be implemented in each community.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Although the presence in the communities has not been continuous, the necessary safeguards have been taken to avoid negative impacts on the communities. The project has 5 indigenous communities (Karcha bahlut, Puerto Diana, Cacique Sapo, Jasyendy and Campo Loa) from 3 different people (Ishir, Nivaclé and Guaraní Occidental) with whom the protocol of prior, free and informed consent consultation (CCLPI) has been applied satisfactorily. The implementation of the EbA demonstration units has been based on the participation of the people of each community, reaching consensual agreements between the parties (minutes) and that ensure the relevance of the interventions. An approach of equitable participation between men and women under equal conditions is also applied in project activities.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project's technical team and counterparts, as well as the community activities of the project encourages the participation of men and women on equal terms. An important lesson that is being identified in the project is the participation of women in the management of water in their families. It has been seen that most of the communities targeted by the project have difficulties in accessing water supplies and depend on few reservoirs to harvest rainwater and on the assistance of local governments (to provide water). Women and children spend a large part of their time carrying water to their homes, which compromises other productive activities. The project has seen the great relevance of interventions to improve the availability and distribution of water in the communities. They will enable a significant change in the use of time for women, with more possibilities to dedicate time to other productive activities to improve food security.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No