## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
Period of Report (Dates) |  | 11/04/2019 al 11/04/2020
| Project Title: | Ecosystem-based Approaches for Reducing the Vulnerability of Food Security to the Impacts of Climate Change in the Chaco Region of Paraguay
vulnerabilidad de la seguridad alimentaria a los efectos del cambio climático en la región del
Chaco en Paraguay
| Project Summary: | The goal of this project is to reduce the vulnerability of the population (selected family agriculture producers and indigenous communities) of the Chaco Region of Paraguay to the impacts of climate change on food security. In order to do so, the project plans to address the main barriers for adaptation in the selected region. Specifically, the project would seek to i) improve information and knowledge for climate resilience; ii) implement concrete cost-effective on-the-ground adaptation measures; and iii) strengthen the institutional capacities to adequately address climate change adaptation issues. The project would be organized accordingly in three components: i) Knowledge management on vulnerability and climate change resiliency improved; ii) adaptive capacity in rural areas of greatest vulnerability strengthened through concrete agro-ecosystem based adaptation measures; and iii) capacity development and awareness to upscale effective implementation of adaptation measures at the national and local levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PRY/MIE/Food/2012/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Environment Programme- UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementation Agency | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Paraguay | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is implemented in the Western region of Paraguay, known as Chaco. Intervention zones include the communities of General Diaz, Pozo Hondo and the Campo Loa indigenous community in the district of Mariscal Estigarribia in the Department of Boquerón. Other areas of intervention are the communities of Toro Pampa, San Carlos and Maria Auxiliadora in the District of Fuerte Olimpo, and the fishing communities of Bahia Negra, the indigenous community of Karcha Balut and the Sierra León in the District of Bahia Negra, both districts in the Department of Alto Paraguay. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-27
IE-AFB Agreement Signature Date: |  | 2017-06-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-04-11 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2021-10-31
2023-12-31
Original Completion Date:
Revised Completion Date after approval |  | 2023-12-31
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each. | Cyprus
|  | 1. Inception Workshop Report | Czech Republic
2. Updated Logical Framework
3. Validated General Work plan
4. Validated Annual Operating Plan 2019
5. Validated Annual Operating Plan 2020
List the Website address (URL) of project |  | Under construction | Democratic People's Republic of Korea
Denmark
| Project contacts: | Oscar Vargas - Project Coordinator - oscar.vargasacosta@un.org | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Marta Monteo - Programme Officer / Climate Change Unit /UNEP | Dominican Republic
| Email: | marta.moneo@un.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Leo Heileman - Regional Director Latin America and the Caribbean Office (UN Environment) | Fiji
| Email: | heileman@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Gustavo Mañez - Climate Change Coordinator, Latin America and the Caribbean Office (UNEP) | Georgia
| Email: | gustavo.manez@un.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Gricha Zurita - Fund Management Officer, Latin America and the Caribbean Office (UN Environment) | Grenada
| Email: | gricha.zurita@un.org | Guatemala
| Date: |  | Guinea
Guinea Bissau
Guyana
Haiti
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 04/30/2020 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 04/30/2020 | 155161 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Total Disbusements as of April 30, 2020: $155,161 Total Committed as of April 30, 2020: $178,210 Total expenditures as of April 30, 2020: $333,371 |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public | 9514.2
| Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 0
| Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 4439.71
| Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 0
| Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 0
| Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches | 4439.71
| Output 3.1. Training plan for MADES, associated institutions at the national level especially the DNCC (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of climate compatible development and prevention and risk management in all sectors. | 0
| Output 3.2. The lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels. | 0
| Project Management Costs | 136767.21
| TOTAL | 155160.83 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Committed expenditure
| Output 1.1. Studies to identify the best adaptation practices, developed and disseminated to decision makers, stakeholders and the general public. | 18456 | September 2020
| Output 1.2. Climate change vulnerability assessments to inform decision-making and guide adaptation planning, prepared and disseminated to decision makers, stakeholders and the general public. | 210 | July 2020
| Output 1.3. Protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, developed and made available to sub-national governments and members of the community to inform in decision-making (specialized chapters by topic). | 1019.2 | July 2020
| Output 1.4. New meteorological stations are installed and the required studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by the community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.) | 210 | July 2020
| Output 2.1. Community adaptation plans developed alongside community members and integrated into sub-national planning instruments to guide decision-making. | 9420 | October 2020
| Output 2.2.Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that facilitate ecosystem-based approaches. | 19263.2 | March 2021
| Project Management Costs: Committed Contract service - Drivers | 17174 | May 2021
| Project Management Costs: Travel related services/ vehicle/Personnel Staff | 112458 | December 2021
| Total Committed as of April 30, 2020 | 178210.4
| Planned expenditure schedule | PROJECTED COST | Est. Completion Date
| Output 1.1 Studies for the identification of best adaptation practices: Detailed mapping of ecosystems, including agro-ecological zones, water resources, forest and other ecosystems | 78500 | April 21
| Output 1.1 Studies for the identification of bet adaptation practices: Study of the ecology, management and nutritional components of algarrobo (Prosopis spp) | 74931 | April 21
| Output 1.1 Studies for the identification of best adaptation practices: Research on traditional practices that contribute to climate resilience. | 93000 | April 21
| Output 1.1 Studies for the identification of best adaptation practices: Elaboration of an analysis of incentives and disincentives for the adoption of climate-resilient agricultural practices in the Chaco region. | 20000 | April 21
| Output 1.2 Climate change vulnerability assessments to inform decision making and guide adaptation planning developed and disseminated with decision makers, stakeholders and the general public. | 70868 | April 21
| Output 1.3. The protocol for the implementation of good practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral livestock in rural and indigenous communities, is prepared and made available to subnational governments and members. community to inform decision-making (specialized chapters by topic). | 280001 | April 21
| Output 1.4 New meteorological stations are installed and the necessary studies are prepared to carry out an agroclimatic risk assessment to inform decision-making by community members and sub-national governments: instalation of 5 meteorological stations | 125000 | April 21
| Output 1.4 New meteorological stations are installed and the necessary studies are prepared to carry out an agroclimatic risk assessment to inform decision-making by community members and sub-national governments: Evaluation of the vulnerability to climate change of specific plants and animals used as a food source. | 151983 | April 21
| Output 2.1 Development of adaptation community plans with ecosystem-based approach | 100000 | April 21
| Output 2.2 Implementation of adaptation community plans (technical assistance and inputs to implement concret adaptation measures favoring an ecosystem-based approach) | 463294 | December 20
| Output 3.1 Training plan for MADES and partner agencies at national level on mainstreaming climate compatible development across sectors. | 71740 | April 21
| Output 3.2 Local level training plan for partner agencies at local level (including but limited to departmental and municipal governments) | 90000 | April 21
| Output 3.3 Identification, systematization and exchange of lessons learned of the project | 61090 | December 21
| Project Management Costs | 242199 | December 21
| Total Planned expenditures schedule | 1922606 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Polítical: Institutions do not prioritize this project | Low | The project addresses national priorities. In addition, it will provide training to all relevant stakeholders and engage them in the project planning, implementation, monitoring and evaluation, including the development of community adaptation plans. Similarly, the development plans of the Departments and Districts will be revised to incorporate adaptation to climate change. There is a strong commitment from all stakeholders. The focus on best practice will ensure results, which will engage those involved.
Institutional: Lack of coordination, collaboration, and proper cooperation among the executing agencies generates delays in the project´s implementation | Low | The operational agreements between implementing partners and agencies have been described in detail with the necessary definition of roles and responsibilities. A focus of constructive, proactive and consensual development will lead the interactions between stakeholders.
Institutional: Frequent staff rotation at local implementing agencies may affect the availability of qualified personnel. | Medium | On the one hand, decisions, best practices, and lessons learned will be documented throughout the project to support the institutional memory that will support its activities. This memory will also be reinforced through the activity "identification, systematization and exchange of lessons learned from the project". On the other hand, staff members from each institution, as well as non-governmental actors-scientists, engineers, planners and community leaders will be trained by the project, and thus strengthen institutional capacity to plan and implement adaptation activities within and outside government institutions and agencies. If possible, the project will use government structures established to capitalize on good practices and systems that are familiar to government personnel.
Institucional: Lack of interest and participation of key actors and target groups, along with conflicts/differences between actors/groups may weaken and delay the implementation of activities | Low | The design of the project has been highly participative, in order to ensure its focus on real priorities. Furthermore, it's been designed to promote awareness raising and capacity-building activities. Additionally, it will engage all stakeholders during implementation, including monitoring, evaluation and adjustment, if necessary. The project will implement mediation processes to prevent and manage any conflict between actors.
Environmental: Climatic variability and changes, including extreme weather events, are greater than projected by the studies. | Low | The project activities were designed taking into account the newest information and robust available. In addition, the project includes the improvement of the meteorological network and the provision of regular weather information. This will allow to adjust practices to the climatic variability. Long-term activities, such as puddles and tanks, will take into account the uncertainty related to climate change.
Financial: The use of financial resources involves many levels of government and thus, is inefficient. | Low | The coordination team will be established at the Ministry of Environment and Sustainable Development (former Secretariat of Environment-SEAM), ensuring coordination with different sectors and levels of governments that work on climate change. An open call will be made for each activity and the best technical and financial proposal will be selected, ensuring that the provision of services is efficient and that financial resources are used appropriately. Different actors, from private companies to NGOs and community-based organizations (CBOs), will be able to apply the technical proposal being evaluated against the specific terms of reference fot each activity.
Financial: The use of financial resources is not transparent. | Low | The project will follow UNEP and Paraguay´s rules and regulations, which ensures transparency. In addition, the budget includes financial resources to carry out annual audits, so that any potential deviation can be identified to take corrective actions.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Pandemic Risks (COVID 19) | Medium | The project team observes and implements all the sanitary recommendations set by the Paraguayan government (laws, decrees, protocols) to reduce the risk of infections.
Other environmental risks • Weather conditions prevent access to intervention areas in planned time. • Road conditions prevent reaching intervention areas with the necessary equipment for certain activities. | Medium | Although these risks shall not affect the objectives, they can be reasons for delays, so precautions will be taken to permanently monitor the meteorological and road conditions in the intervention areas, shortening the duration of the missions if necessary.
Other Political Risks  Public institutions of the central government or sub-national governments do not support (or stop supporting) the project implementation.  Changes in government cause delays in empowerment to incorporate EBA concepts into its public management. | Medium | The project will work in close coordination with the National Directorate for Climate Change of MADES (Counterpart Institution in the country) in order to promote empowerment by the institution.
Other Technical Risks  There are not enough technicians trained on EBA at the local level to work with beneficiaries | Medium | Training plans on EBA concepts will be developed, first with international trainers, who shall skill-up local trainers.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Overall, the project's risk rating is Medium. Several of the identified risks are under the control of the project team and can be mitigated through a timely and effective project management. Other risks are beyond the project´s control, such as the Covid-19 pandemic, which will require the project team to monitor and plan accordingly, through an adaptive management approach and the implementation of mitigation measures, already put in place by the government, to reduce the possible consequences. The criticallity relationship with the risk posed for each project activity for the current period has been evaluated and informed to the Project Coordinator in the country and the Project Officer.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1] | Yes
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law | Yes | yes | Regarding the activities included in component 2 (which includes the installation of meteorological stations, reforestation and forest conservation, agroecological management measures [best agricultural practices] and water storage systems), there is a risk of a insufficient stakeholder´s capacity in managing environmental and social issues in accordance with national law and the Adaptation Fund´s principles. They include Law No. 294/93 on Environmental Impact Assessment (EIA), Law No. 2/73 (Forest Law) and Resolution 2242/06 which approves the list of protected species within the wildlife endangered species. | Within the reporting period there have been no interventions in the communities beyond the formal project presentations and studies included in component 1. However, regulations related to this stage of the project have been complied with, such as Decree 1039/18 Free and Informed Prior Consent Consultation of the indigenous communities that will be beneficiaries of the project, and the work regulations (Laws) put in place, by the government, for the duration of the Covid-19 pandemic. | Indicators are in the process of drafting
2 - Access and equity | Yes | yes | Since the beneficiaries of this project are poor people and are often excluded from the decision-making process, there could be a risk for these people to have insufficient access to the project´s resources. | Resources will be budgeted in the intervention stage. We are currently working on specific analysis planned in component 1. | Indicators are in the process of drafting
3 – Marginalized and vulnerable Groups | Yes | yes | There is a risk that these marginalized and vulnerable groups have insufficient access to the project activities, especially those of component 2.2 (implementation of adaptation measures such as reforestation and forest conservation, agroecological management measures [best agricultural practices] and water storage and irrigation systems). Regarding the extension activities of indigenous communities, the problem lies in the fact that these are close-knit communities and the project´s technicians could be perceived as outsiders and untrustworthy. | Maintaining the credibility of the project with beneficiaries and local authorities is important, and promises that cannot be kept will be avoided. Measures to be implemented will be reinforced according to the priorities developed with central and local authorities, after the vulnerability assessments that are to be conducted. | Indicators are in the process of drafting
4 – Human rights | Yes | yes | There is a possibility that access to the project´s resources is uneven for different segments of the population. | The determination of vulnerability, a base condition for estimating the interventions,will take into account all fundamental human rights. | Indicators are in the process of drafting
5 – Gender equality and women’s empowerment | Yes | yes | The risks to gender equality and the women´s empowerment could be: (i) Insufficient consideration on gender equality issues in the project implementation; (ii) Disregarding the women´s empowerment in the project activities. | For determining the population's vulnerability, gender issues will be especially considered, incorporating qualitative data in case there is not enough statistical support to incorporate quantitative values ​​in the calculations. | Indicators are in the process of drafting
6 – Core labour rights | Yes | yes | In Component 2, the construction and repair of water storage systems could pose a risks for work-related accidents. During the installations of such systems, workers will be exposed to the risk of accidents that can range from minor injuries to death. Additionally, the transport of agricultural inputs/provisions could pose a risks, such as traffic accidents during transport. On the other hand, Gender aspects (amended in November 2013) regarding the contributions of the project to the generation of equitable benefits based on gender, the project will emphasize on an approach that takes into account gender differences in the roles and responsibilities of men and women in the Chaco´s rural and indigenous communities. In both types of communities there are clearly defined divisions of labor between men and women. As indicated in the Gender Technical Note of Paraguay (IDB, 2014), rural women combine tasks that involve carrying water and firewood, buying supplies including food, and transporting their children, throughout the entire year. | As noted in the interventions set out in the PRODOC, regarding the project´s contributions to the generation of gender equitable benefits, the project will emphasize on an approach that takes into account gender differences in roles and responsibilities of men and women in the Chaco´s rural and indigenous communities. | Indicators are in the process of drafting
7 – Indigenous peoples | Yes | yes | There is a risk that access to project´s resources is unequal for indigenous people. | It is contemplated to work in the same conditions with indigenous and rural populations in the intervention areas, with no discrimination whatsoever; However, some procedures with indigenous people are specific, such as the Free and Informed Prior Consent Consultation , which has been implemented through workshops in indigenous communities. | Indicators are in the process of drafting
8 – Involuntary resettlement |  |  | No negative impacts have been identified |  | Indicators are in the process of drafting
9 – Protection of natural habitats | Yes | yes | The project will be especially focused on preserving natural space and biodiversity, as well as making a sustainable use of ecosystem resources by conserving land and soil, preventing pollution, and promoting resource efficiency. The project activities specifically seek to encourage practices that favor increased production and income per hectare in order to reduce the need for deforestation. However, there is a low risk that the natural space for vegetation and fauna is destroyed, especially in the context of infrastructure works such as weather stations or water storage infrastructure. | As mentioned in the PRODOC, the project's activities seek to encourage practices that favor increased production and income per hectare in order to reduce the unsustainable use of natural resources of the ecosystems where communities are inserted. Specific interventions, such as those of meteorological stations, will be carried out in areas without vegetation. | Indicators are in the process of drafting
10 – Conservation of biological diversity | Yes | yes | Algarrobo and the Prosopis spp are nitrogen-fixing trees that promote soil enrichment while providing shade and food (in the form of leaves and seed pods) for livestock. In accordance with SEAM Resolution No. 2242/06, two of the Prosopis spp species are classified as "endangered species". Due to the lack of data and reliable information about the population and its management, there is a risk of unsustainable management and use of endangered species. | Work shall be carried out in close coordination with the Directorate for the Protection and Conservation of Biodiversity of MADES, the official counterpart of the project, who will support and monitor everything related to the conservation and sustainable use of biodiversity. | Indicators are in the process of drafting
11 – Climate change |  |  | No negative impacts have been identified
12 – Pollution prevention and resource efficiency |  |  | No negative impacts have been identified
13 – Public health | Yes | yes | Food security: The impacts of climate change on water resources and agricultural systems will reduce the availability and access to food. Constant droughts will also affect the balance of both factors over time, which will weaken their food security. However, the project is expected to have a positive impact on food security. Access to drinking water: It should also be borne in mind that if drinking water sources become contaminated, the consumption of that water may be the cause of disease. Development of water-related diseases: The continuous presence of water in water storage systems could be the cause of the development of water-related diseases such as malaria, amebiasis or typhoid fever. | Analysis of food and water provided by the project will be carried out in order to guarantee health conditions for the beneficiaries of the project. | Indicators are in the process of drafting
14 – Physical and cultural heritage |  |  | No negative impacts have been identified
15 – Lands and soil conservation |  |  | No negative impacts have been identified
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | A Project Monitoring Manual is being drafted, such manual will include a ESP Risks monitoring protocol.
Have unanticipated ESP risks been identified during the reporting period? |  | No unexpected ESP risks have been identified so far. It is expected that a constant evaluation is carried out, in line with the Monitoring Manual, which shall be reported in the next PPR.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | If such risks arise, they shall be reported in the next PPR, as well as the measures implemented to mitigate them.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The safeguard risks were identified during the development phase of the project. At the moment a Safeguard Manual that allows a systematic monitoring of them is being drafted. This Manual, once validated with UNEP´s authorities and the national counterpart, shall enable the systematic monitoring and mitigation of any situation that arises in a timely and effective manner.
Have the implementation arrangements been effective during the reporting period? |  | The arrangements for the implementation of the Safeguards, provided for in the Manual, will have greater relevance from the implementation of component 2 onward.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The implementation of the planned Safeguards will be promoted not only in every agreement carried out by the project activities, but also in the planned consultancies, as well as in activities alongside local counterparts.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The effectiveness of the arrangements will be determined in the next stage of the project and will be reported in the next PPR.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | It is planned to implement a grievance mechanism when carrying out direct interventions with the selected communities.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | An initial gender assessment was indeed carried out during the first presentation of the project in the initial workshop, but not as a detailed project work plan.
Does the results framework include gender-responsive indicators broken down at the different levels (objective, outcome, output)? |  | At the moment they are considered as product indicators.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 3.1 Training plan, for MADES, associated institutions at the national level, especially the National Climate Change Committe (CNCC) (ministries and agencies, including, among others, MAG and INFONA), sub-national and the general public, on the integration of development compatible with climate and risk prevention and management in all sectors |  | Number of MADES personnel trained in integrating a compatible development with the climate and EBA in all sectors (by gender) | 0 | 40 | The implementation in the communities has not started yet
|  | Number of staff from partner agencies and the general public trained to incorporate climate compatible development and EBA in all sectors (valuing gender roles) | 0 | 200 | The implementation in the communities has not started yet
|  | Number of trained people who acknowledge having a new understanding or having acquired skills about ABE (by gender) | 0 | 150 | The implementation in the communities has not started yet
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UNEP has a comprehensive policy and strategy on gender equality and the environment, that establishes the use of a gender marker. Essentially, the gender marker serves as a monitoring tool that ensures that at the point of project development and implementation, gender perspectives are integrated at all stages, including the budget. The gender marker has a four-point scale against which the project is evaluated. Each project is required to meet a score of 2a, which means that gender is fully integrated and the project will make a significant contribution to achieving gender equality. In the event that a project does not meet rating 2a, the project officer is required to review the project and ensure that gender perspectives are fully incorporated and then resubmit the project for review.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Although gender considerations are integrated into the Logical Framework, Work Plans and AOPs, the effectiveness of implementation cannot be yet verified, since component 1 only contemplates general studies, prior to intervention in the communities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5]
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5]
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | One of the first activities will be to establish a Base Line in the communities of the intervention areas where it is already contemplated to identify capacity gaps that affect compliance with the GPs during the implementation period of the project and in addition to addressing these gaps, they shall be reported in the next PPR
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Until this period, no grievances were received on the activities, especially because there has still been no interaction with the residents of the communities. |  | A grievance mechanism will be established, thus processes shall be reported from the next PPR onward.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: Sub-national governments integrate information on climate change adaptation (CCA), highlighting vulnerability and resilience, into planning instruments to improve decision-making and implement sectoral and multisectoral measures. |  | Outcome 2 | Vulnerability level of the determined local population, based on technical criteria and statistical data available in the country; as well as technical studies to justify recommendations for ABE measures, presented to authorities and the population in the project intervention areas. |  | The project has been presented to the local authorities, as well as to the general population of the intervention areas; Safeguards have been implemented in indigenous communities in the project intervention areas through the Free and Informed Prior Consent Consultation Workshop conducted with the beneficiary communities. A proposal was agreed with the local counterpart institution, MADES, on procedures to carry out the studies foreseen in this component. | Marginally Satisfactory
| Outcome 2. Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  |  | No progress was expected in the reported period
| Outcome 3. Beneficiaries, MADES staff, national partners (CMCC), sub-nationals and the general public trained to incorporate ACC and ABE in the planning processes of sustainable development. |  |  | No progress was expected in the reported period
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Marta Moneo
| Email: | marta.moneo@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
This project was offically launched in April 2019 after a negotiation period for the execution of the project with the new governemnt after general elections in 2019. the second half of 2019 was mainly focused on the set up of the project cooridnation UNit that is now complete with a National Coordinator, an administrative assistant and two technical experts to support the execution of all activities of the project. Two vehicles were also purchased and alre already being used for the initial consultations that have taken place in the communities where the projectc is to be executed. These initial consultations were mainly focused on the presentation of the project and the compliance with national laws regarding consultation and agreement on participation with local communities. An implementatio plan for the period between may 2019 and may 2020 was also agreed with the counterpart in the government, the MInistry of Environment (MADES). Execution of the projectc in 2020 has suffered important drawbacks mailny due to the COVID pandemic that have prevented for several months the execution of activities on the ground, but has allowed for a more detailed planning of activities in the coming months. A clear plan of execution for the vulnerability assessments reflected under outcome 1 of the project is now ready and modifications to the work plan have been done in order to develop these analysis considering potential risks of the pandemic still in the coming months. Other key elements of the project have also been developed in this fist year of the project including a draft of the Environemtnal and Social Safeguards, the operational manual for project execution and the Gender action plan. All these documents are currently in draft versions and undergoing validation and approval by all stakeholders in the project. Despite the challenges caused by the international COVID emergency, the project has now established a solid basis for execution in the next year and visits to the pilot areas can be organized again following the appropriate security measures established by the government.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Sub-national governments integrate information on climate change adaptation (CCA), highlighting vulnerability and resilience, into planning instruments to improve decision-making and implement sectoral and multisectoral measures. |  | Outcome 2 | Vulnerability level of the determined local population, based on technical criteria and statistical data available in the country; as well as technical studies to justify recommendations for ABE measures, presented to authorities and the population in the project intervention areas. |  | The project has been presented to the local authorities, as well as to the general population of the intervention areas; Safeguards have been implemented in indigenous communities in the project intervention areas through the Free and Informed Prior Consent Consultation Workshop conducted with the beneficiary communities. A proposal was agreed with the local counterpart institution, MADES, on procedures to carry out the studies foreseen in this component. | Marginally Satisfactory
| Outcome 2. Specific adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and availability of food, with an emphasis on access to water. |  |  | No progress was expected in the reported period
| Outcome 3. Beneficiaries, MADES staff, national partners (CMCC), sub-nationals and the general public trained to incorporate ACC and ABE in the planning processes of sustainable development. |  |  | No progress was expected in the reported period
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Oscar Vargas Acosta
| Email: | oscar.vargasacosta@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The rating is due to the fact that the project activities planned for the reported period have a considerable delay in implementation. However, progress is gradual and the expected results will be fully achieved. Furthermore, in the reported period, no deficient products were identified. The project began operating in April 2019 with the inception workshop. Over the first year of implementation, efforts aimed at presenting the project to key stakeholders such as representatives of sub-national governments in the intervention areas, NGOs operating in Chaco and representatives of the academy . At the same time, these presentations served to evaluate the current situation of these institutions regarding their activities in the Chaco; it was found that most of them do not have a significant presence in the western region of the country, which is an important information regarding the arrangements for implementation of Component 2 of the project. As this is one of the first projects of this nature implemented in the country, both for the Implementing Entity and for the local counterpart, this represents an enormous challenge taking into account the difficult terrain conditions (For example: All the communities in the intervention zones are only accesible through dirt roads, which makes it particularly vulnerable to adverse weather conditions, so any rain completely isolates those communities). The Project Management Unit was completed at the end of the reported period, with the incorporation of technical officers, so that the organizational arrangements of the project could advance at a faster rate. Similarly, progress was made in the preparation of the Project Operating Manual, the Monitoring Plan, the Environmental and Social Safeguards Plan and the Gender Plan, which are in the counterpart´s validation processes
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
[8 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Next

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome indicator | 1. Number of knowledge products developed and disseminated (including meteorological studies, evaluations, protocols and reports) | 0 | Institutional arrangement were made to develop the knowledge products. -There is a Work Plan (1) -There are approved AOPs for 2019 (2) and 2020 (3) To access documents please click on the following: | Subnational governments integrate information on climate change adaptation (CCA), emphasizing on vulnerability and resilience, into planning instruments to improve decision-making and implement sectoral and multisectoral measures.
1. Work Plan
2. Annual Operating Plan for 2019
3. Annual Operating Plan for 2020
| 2. Number of sub-national governments and communities who own planning instruments that integrate CCA to shape the design and implementation of sectoral and multisectoral measures | 0 | Studies were initiated to serve as inputs and provide scientific evidence for planning, community and local (sub-national governments) Climate Change Adaptation. To access document please click on the following:
1. PCA
| 3. Increase in the number of meteorological stations provided by the project in the Chaco region | 0 | There is a ToR for the acquisition of Meteorological Stations. - Stations purchasing management is being processed via the UNDP Paraguay office (1) - The location of the stations were identified and it´s currently entering into agreement with the national entity in charge of meteorological information (DMH) (2) - The signing of national inter-institutional agreements for the location of the stations and management of the information is in process (3) Please refer to the following documents:
1. Meteorological Station purchasing documents
2. Meteorological Stations Mission Report
3. Borrador Convenio Marco MADES
Output indicator | 1. Number of studies conducted on (i) the impacts of climate change on plants and animals used as a food source, (ii) the local ecology, management and nutritional components of Algarrobo and Viñal; (iii) local traditional practices that contribute to climate resilience; (iv) incentives for the adoption of climate resistant agricultural practices in the Chaco region; and (v) detailed maps of the ecosystem (1 map for each of the selected communities) | 0 | Alternatives were analyzed to make available financial resources that shall allow the contracting of studies in Paraguay; being the signing of a PCA the implemented mechanism. - There is a ToR to carry out studies for the identification of best adaptation practices prepared and disseminated with decision-makers, stakeholders and the general public. The studies will cover the following topics (i) the impacts of climate change on plants and animals used as a food source, (ii) the identification of plant genetic resources that contribute to feeding people in the intervention areas, emphasizing on Algarrobo and Viñal, through a detailed registry (iii) traditional local practices that contribute to climate resilience, (iv) incentives for the adoption of good agricultural practices and livestock resistant to climate, and (v) detailed maps of ecosystems (1 map for each of the selected communities) asesor técnico de vulnerabilidad (1) To access documents please refer to the following: | Studies to identify best adaptation practices developed and disseminated to decision makers, stakeholders and the general public. The studies will cover the following topics (i) the impacts of climate change on plants and animals used as a food source, (ii) the identification of plant genetic resources that contribute to feeding people in the intervention areas, with emphasis on Algarrobo and Viñal, through a detailed registry (iii) traditional local practices that contribute to climate resilience, (iv) incentives for the adoption of best agricultural and livestock practices, resistant to climate, and (v) detailed maps of ecosystems (1 map for each of the selected community).
1.Draft version TORs Asesor Vulnerabilidad ABE
| 2. Number of communities in the Chaco region with detailed ecosystem maps (gis format) to inform decision-making | 0 | The communities were identified and updated. Bahia Negra was originally indicated in the PRODOC, without indicating if it was the urban or rural area of ​​the district. Then the local government requested through a note, which was sent to the local counterpart and this in turn, to UNEP , to work with the rural community of Sierra León, the native community of 14 de Mayo and the fishing community of Bahia Negra (1) To access documents please refer to the following link:
1. Request Note Bahia Negra
Output indicator | 1. Number of communities integrating the results of vulnerability assessments, addressing the differentiated vulnerability status of women and men (respecting local customs), to inform decision-making. | 0 | The project was presented to the authorities of the sub-national governments of the intervention areas (1) -The project was presented in all the communities and local leaders were identified (2) A PCA was issued to contract an associate to initiate studies. The results will be integrated into the determination of the vulnerability of the local population, differentiating men and women. To access documents please refer to the following link: | Climate change vulnerability assessments to inform decision-making and guide adaptation planning prepared and disseminated to decision makers, stakeholders and the general public.
1. Inception Workshop Report
2. Project Presentation Workshop
3. Nota Conceptual Visita Técnica a Comunidades beneficiarias del Proyecto
Output indicator | 1. Number of communities who own protocols for the implementation of best practices in forest management, hunting calendar, agro-ecological agriculture and small-scale livestock | 0 | Alternatives were analyzed to make available financial resources to allow the contracting of studies in Paraguay; being the signing of a PCA the implemented mechanism (1) - There is an approved AOP, where the preparation of protocols for the implementation of good practices in forest management, hunting calendar, agro-ecological agriculture and small-scale livestock are being considered (2) POA 2020 To access documents please refer to the following link: | The protocol for the implementation of best practices in forest management, the hunting calendar for indigenous communities, agroecological agriculture and small-scale silvopastoral farming in rural and indigenous communities, is prepared and made available to sub-national governments and community members to inform decision-making (specialized chapters by topic).
1. PCA
2. Annual Operating Plan for 2020
Output indicator | 1. Number of new meteorological stations installed in the Chaco Region of Paraguay to inform decision-making | 0 | The process of acquiring meteorological stations began. The resulting data shall contribute to inform the decision-making (1) Please refer to the following link: | New meteorological stations are installed and the necessary studies are prepared to conduct an agroclimatic risks assessment to inform decision-making by community members and sub-national governments. (climatic projections over 30 years, soil study, 4 animal categories, 4 plant categories, etc.)
1. Meteorological Station purchasing documents
| 2. Number of DMH weather bulletins adjusted with project station data, disseminated throughout the duration of the project to community members | 0 | The process of acquiring meteorological stations began. The resulting data shall contribute to the meteorological information that will be used in preparing the bulletins (1) Please refer to the following link:
1. Meteorological Station purchasing documents
Outcome indicator | 1. Percentage of assisted families that report increases (quality and/or quantity) in food production as a result of project interventions. | 0 | No progress was expected in this period | Concrete adaptation measures with ecosystem-based approaches implemented in selected vulnerable communities, favoring greater production and food availability , with an emphasis on access to water.
| 2. Percentage of assisted families who report increases in access/ quantity/ quality of water consumed as a result of project interventions | 0 | No progress was expected in this period
| 3. Percentage of families in the community that benefit from adaptation measure with ecosystem-based approaches | 0 | No progress was expected in this period
Output indicator | 1. Number of communities with adaptation plans to guide decision-making | 0 | No progress was expected in this period | Community adaptation plans developed with community members and integrated into sub-national planning instruments to guide decision-making.
| 2. Number of sub-national governments integrating community adaptation plans into planning instruments | 0 | No progress was expected in this period
| 3. At least 350 families in selected communities that have received the project´s support and participated in the development of community adaptation plans | 0 | No progress was expected in this period
Output indicator | 1. Actions with an ABE focus implemented through adaptation measures materials prepared by the project, elaborated to guide the training of members of the selected communities, MADES staff, partners and the general public | 0 | No progress was expected in this period | Technical assistance provided and inputs distributed to members of selected communities to implement concrete adaptation measures that favor ecosystem-based approaches.
| 2. Number of local families trained by the project to implement adaptation measures with ecosystem-based approaches, on income and self-consumption. | 0 | Initial workshops are planned to train people from the communities in the intervention areas (1) - It is planned to carry out pilot agricultural plots to determine agricultural suitability of selected items To access please refer to the following link:
1. Borrador de Taller de conceptos sobre Adaptación
| 3. Number of local families who have access to inputs, defined as resources in kind, and technical assistance to improve food production through project activities | 0 | No progress was expected in this period
| 4. Number of people who have access to new collection system, storage and water distribution. | 0 | Pilot measures have been identified to improve water collection, storage and distribution systems, all of which will be implemented in the short term (1) Please refer to the following link:
1. Nota Conceptual Medidas Piloto ABE
Outcome indicator | 1. Number of trained people who engage in the integration of ABE measures in development processes from their respective work areas | 0 | No progress was expected in this period | Beneficiaries, MADES staff, national partners (CMCC), sub-nationals and the general public trained to incorporate CCA (and ABE) in sustainable development planning processes.
Output indicator | 1. Number of MADES staff trained in integrating climate compatible development and CCA in all sectors (by gender) | 0 | Local counterpart staff (MADES) were trained on ABE concepts and exchanged experiences with technicians from other countries (1) -International training on EBA topics is planned for national technicians, so that they are able to replicate the knowledge (Training of trainers) by gender. Please refer to the following link: | Training plan for MADES, associated institutions at the national level, especially the CNCC (ministries and agencies, including, MAG and INFONA, etc.), sub-national and the general public, on the integration of climate compatible development, prevention and risk management in all sectors.
1. Adaptation Retreat Mission Report
| 2. Number of personnel from partner agencies and the general public trained to incorporate climate compatible development and CCA in all sectors (valuing gender roles | 0 | Training is planned for partner agencies´staff and the general public to incorporate climate compatible development and EBA concepts in all sectors (valuing gender roles)
| 3. Number of trained people who acknowledge having a new understanding or having acquired skills (by gender) on CCA and ABE | 0 | No progress was expected in this period
Output indicator | 1. Number of lessons learned prepared by the project | 0 | No progress was expected in this period | Lessons learned have been systematized and shared with government specialists at the national, sub-national and general public levels
| 2. Number of families trained on lessons learned (at least one member of the family) | 0 | No progress was expected in this period

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | PRY/MIE/Food/2012/1
Implementing Entity | UNITED NATIONS ENVIRONMENT PROGRAMME
Type of implementing entity | MIE
Country | PARAGUAY
Region | Latin America and Caribbean
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 83458 | 2450 | 81008 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 47.45% | 47.45% | 47.45% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 2450 | Drought | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 47.45% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  |  | Other | Local | 1: No plans conducted or updated | 1 | Other | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Food security |  | Total | 2450 | Food security | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 47.45% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 2450 | 47.45% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Food security | 2: Low capacity | Public | Local | Food security | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Food security |  | 75 |  | Food security
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 2450 | 47.45% | 1: Aware of neither |  | 2450 | 47.45% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 9 | 20% to 39% | 1: Aware of neither |  | 9 | 40% to 60% | 5: Fully aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Regional |  | 78 | Technical guidelines | Regional
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | National | 1: Non responsive (Lacks all elements ) |  | Food security | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Multi-sector | 9 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | water areas | 5: Very effective |  | Multi-sector | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 9 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 9 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 9 | ha rehabilitated | 1: Ineffective | Forests | 9 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 9 | ha rehabilitated | 1: Ineffective | Forests | 9 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 816 | 10% | 5: Very high improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 816 | 10% | From 0 to 0.5% | Agriculture | 816 | 10% | From 40% to 50% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Water management | Irrigation system | 9 | Physical capital | Multi-sector | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 816 | other |  | 50 | 816 | other |  | 200
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Other | Regional | Other policy | 9 | Other | Regional | other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 9 | 5: Fully enforced (All elements implemented) |  | 5: Very effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Subnational | Innovation replicated |  | Food Security | Community | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices | 1: Ineffective | 10 | Food Security | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 9 | Innovative practice |  | 4: Effective

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | In the reported period, efforts were made to establish effective administrative processes. Additionally, the project has been presented to partner institutions or partners whose activities can contribute to the achievements of the project objectives, as indicated in the PRODOC. The first contacts were established with MAG and IPTA, and the second contacts were made with public institutions such as the STP and SEN and with the private sector entities, e.g. the Rural Association of Paraguay and the NGOs working in the Chaco, e.g. Moisés Bertoni, Instituto Desarrollo, Guyra Paraguay, as well as with NGOs based in Chaco e.g. Fundación Desde el Chaco, Sombra de Árbol, ASCIM, etc. Project presentations have been made to beneficiaries of our intervention areas, occasions where an evaluation of the current situation of each community was also conducted and their leaders were identified. Similarly, the project was presented to the local authorities, namely: - Governor of Alto Paraguay, Mr. José Adorno - Governor of Boquerón, Dr. Darío Medina - Mayor of Fuerte Olimpo, Mr. Sergio Cuellar - Mayor of Bahía Negra, Mr. Joao Ferreira - Mayor of Mcal. Estigarribia Mr. Elmer Vogt There is a very important favorable expectation both at the central government level, which declared the project of national interest (With this declaration, all the country's institutions are obliged to support the project's actions to the possible extent) and at the -subnational governments. High expectations are also held by the population in the areas of intervention, therefore it is highly likely that they will promote the empowerment of this project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There is indeed a considerable time delay; however, measures have been identified and implemented to mitigate each bottleneck. The main reasons that contributed in the reported period to the delays are mainly due to: Fist, delays in the transfer of resources to finalize contracts and product purchases. Second, the exceptionally harsh meteorological conditions (journal reports mentioned floods for approximately 5 months in the project intervention areas, which coincided with the beginning of the project and last the COVID-19 pandemic. Regarding administrative delays, an agreement was signed with the local UN Office to process purchases and / or serivice contracts and DSA payments. In addition, procedures have been agreed with the local counterpart, MADES, to operate through local NGOs, which will facilitate procedures for the purchase of goods and service contracts. In relation to the severe weather and road conditions, (they had already been identified as risks), a permanent monitoring of weather and road forecasts is carried out (integrating private Chaco networks), with the aim of reducing risks as much as possible, and sometimes even delaying or advancing missions. Finally, in relation to the COVID-19 Pandemic, although in the reported period Paraguay was not strongly affected, the risk undoubtedly remains; and the regulations issued by the national health authorities are carefully followed in field missions. Also, in the reporting period, which coincides with the COVID-19 pandemic, the activities were carried out only with the dynamics of teleworking and only in phase 3, from June 15, field work will resume.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Although there were adjustments to the original project document, given the time elapsed between its original conception in 2011 until its effective implementation in 2019, the project objectives remain the same. An adjustment was made in the Bahia Negra intervention area, originally indicated in the PRODOC, but given that this District is the largest in the Department of Alto Paraguay, in consultation with the Local Mayor, the following communities were prioritised: Sierra León, the Indigenous community of 14 de Mayo and the fisherman community of the urban area of ​​Bahia Negra. Finally, it should be noted that for component 2, it will be necessary to reevaluate the role of some public institutions that were considered potential partners for project implementation, as is the case of the Ministry of Agriculture (MAG) and the Agriculture Technology Institute (IPTA), given the lack of institutional presence in the intervation area. An alternative is to train the personnel assigned to the agriculture departments of the local governments, which in turn could help to warrant project´s actions sustainability once implementation is completed.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Direct actions on the ground were not contemplated during the reported period, therefore, there has been no opportunity to test the effectiveness of environmental and social safeguards.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Similar to the considerations of the previous item, the interventions with the people of the communities of the intervention have remained at the level of introduction of the project adn there has been significant participation of women. at this stage, component 1 basically requires studies that will serve as input and basis for subsequent interventions, however, gender considerations have indeed been taken into account during the reporting period in terms of women engagement in the introductory meetings and in the initial considerations fro the assessment phase. No significant progress has yet been made in the indicators.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Marta: Creo que la info en esta sección no es relevante en su mayoría. Podríamos decir simplemente que no se ha podido cumplir con el schedule planificado pero se avanzó en el establecimiento de procesos administrativos efectivos así como en la contratación del personal del proyecto.
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No le pondría "considerable delay", le pondría simplemente que no se pudo cumplir con el planned schedule of implementation por los motivos que se detalla
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No me hace sentido esta respuesta. Creo que podríamos poner directamente que se está en proceso de elaboración de las salvaguardas de género que serán incorporadas en el desarrollo de las actividades del proyecto.