## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 5 June 2021 - 4 June 2022
| Project Title: | Building climate and disaster resilience capacities of vulnerable small towns in Lao PDR
| Project Summary: | The project objective is to build climate resilience in small towns along the east-west economic corridor in the central region of Lao PDR. This will be achieved through the provision of climate resilient water infrastructure and the mainstreaming of climate change into urban planning.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Lao PDR | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Sayphouthong and Sethamouk towns, Savannakhet province | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 8 July 2019 (Website says 07/08/2019)
IE-AFB Agreement Signature Date: |  | 24/10/19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 5 June 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | June 2022
| Original Completion Date: | June 2024
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report (will submit in June 2023). | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Buahom Sengkhamyong | Dominican Republic
| Email: | bouahoms@gmail.com | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Syamphone Sengchandala | Equatoral Guinea
| Email: | syamphone.s@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Avi Sarkar | Fiji
| Email: | avi.sarkar@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Xayasene Keovilaysack | Georgia
| Email: | xayasene.k@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 12 August 2021 |  |  |  | Financial information PPR 2: cumulative from project start to [05 June 2021] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [05 June 2021] | 604750 |  |  | Estimated cumulative total disbursement as of 04 June 2022 | 617161 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | (i) IE's total receipt from AF is USD 804,392. (ii) USD 588,910 has been disbursed to EE for project activities under two Agreements of Cooperation of the amount USD 4,587,500 that have been signed with EE (NPSE-Savannakhet). (iii) Out of USD 588,910, EE reported expenditure of project activities = USD 105,000. (iv) In addition, Programme Execution = USD 15,840.92, and Programme Cycle Management Costs = USD 43,402.56. The total of those two = USD 59,243.48. (v) Total expenditure = USD 164,243.48. (iii+iv) (vi) Estimated cumulative total disbursement is USD 588,910 (the disbursment for project activities) + USD 15,840.92 (Programme Execution) = USD 604,750.92. As discussed, Programme Cycle Management Costs (USD 43,402.56) is not included. Kindly note that the cell EF-9 does not allow the decimals so there is a discrepancy of USD 0.92. |  |  | Add any comments on AF Grant Funds. (word limit=200) | (i) There were no further disbursements made to the EE in Y2 so the cumulative disbursement remains the same (=USD 588,910). (ii) Reported Y2 Expenditure of project activities = USD 438,750. (iii) In addition, Programme Execution = USD 12,411, and Programme Cycle Management Costs =USD 574. Total expenditure of those two = USD 12,985. (vi) Estimated cumulative total disbursement is USD 648,153.48 (the toral amount of Y1) + USD 12,411(= Y2 Programme Execution) = USD 617,161.92. As discussed, Programme Cycle Management Costs (USD 43,402.56) is not included. Kindly note that the cell MN-9 does not allow the decimals so there is a discrepancy of USD 0.92. (v) Total cumulative expenditure including Programme Cycle Management Costs is USD 661,138.48 against a total receipt of USD 804,392 which represents a funds utilization rate of 82.2%. (vi) The EE has requested for activities under project components USD 1,720,798 for immediate disbursement and an additional USD 1,819,093 will also be requested soon.to expedite delivery of the project. The two amounts equal to USD 3,539,891. Please note that the above amounts do not include Programme Execution and Programme Cycle Management Costs. Hence, the release of 2nd and 3rd tranches is requested. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | None |  |  | INVESTMENT INCOME | None |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 - Training provided to district, provincial and national government staff on resilient infrastructure design. Female government staff must be represented | 10000 |  |  | Output 1.1.1 - Training provided to district, provincial and national government staff on resilient infrastructure design. Female government staff must be represented | 4800
| Output 1.2.1 - Training provided to district, provincial and national government staff on climate action mainstreamed urban planning. Female government staff must be represented | 10000 |  |  | Output 1.2.1 - Training provided to district, provincial and national government staff on climate action mainstreamed urban planning. Female government staff must be represented | 4950
| Output 1.3.1 - Two master plans developed, using knowledge generated by the project, to both provide sustainable adaptation benefits to the infrastructure designed under this project and to enable the government to better plan for adaptation in other infrastructure, beyond that in the project area. The master plans will include specific provisions for the development and climate change resilience of women. | 80000 |  |  | Output 1.3.1 - Two master plans developed, using knowledge generated by the project, to both provide sustainable adaptation benefits to the infrastructure designed under this project and to enable the government to better plan for adaptation in other infrastructure, beyond that in the project area. The master plans will include specific provisions for the development and climate change resilience of women. | 5000
| Output 2.1 - New resilient infrastructure constructed in response to climate change impacts, including variability. | 0 |  |  | Output 2.1 - New resilient infrastructure constructed in response to climate change impacts, including variability. | 415000 | Procurement process see details in "Procurement" Tab
| Output 3.1 - Project activities and results are captured and disseminated through appropriate information for the beneficiaries, partners and stakeholders and the public in general | 3000 |  |  | Output 3.1 - Project activities and results are captured and disseminated through appropriate information for the beneficiaries, partners and stakeholders and the public in general | 7500
| Output 3.2 - Climate policy - especially the National Adaptation Plan and post-Paris agreement reporting - influenced to reflect the challenges of climate change adaptation in basic service and protective infrastructure, including the provision of infrastructure in a way that benefits women | 2000 |  |  | Output 3.2 - Climate policy - especially the National Adaptation Plan and post-Paris agreement reporting - influenced to reflect the challenges of climate change adaptation in basic service and protective infrastructure, including the provision of infrastructure in a way that benefits women | 1500
| Programme Execution | 15840.92 |  |  | Programme Execution | 12411
| Programme Cycle Management Costs | 43402.56 |  |  | Programme Cycle Management Costs | 574
| TOTAL | 164243.48 |  |  | TOTAL | 451735 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 - Training provided to district, provincial and national government staff on resilient infrastructure design. Female government staff must be represented | 120000 | 2022-02-01 |  | Output 1.1.1 - Training provided to district, provincial and national government staff on resilient infrastructure design. Female government staff must be represented | 0 | n/a (activity completed)
| Output 1.2.1 - Training provided to district, provincial and national government staff on climate action mainstreamed urban planning. Female government staff must be represented | 120300 | 2022-02-01 |  | Output 1.2.1 - Training provided to district, provincial and national government staff on climate action mainstreamed urban planning. Female government staff must be represented | 0 | n/a (activity completed)
| Output 1.3.1 - Two master plans developed, using knowledge generated by the project, to both provide sustainable adaptation benefits to the infrastructure designed under this project and to enable the government to better plan for adaptation in other infrastructure, beyond that in the project area. The master plans will include specific provisions for the development and climate change resilience of women. | 37000 | 2022-06-01 |  | Output 1.3.1 - Two master plans developed, using knowledge generated by the project, to both provide sustainable adaptation benefits to the infrastructure designed under this project and to enable the government to better plan for adaptation in other infrastructure, beyond that in the project area. The master plans will include specific provisions for the development and climate change resilience of women. | 32000 | 2023-03-01
| Output 2.1 - New resilient infrastructure constructed in response to climate change impacts, including variability. | 3245591 | June 2022 (Procurement Process) |  | Output 2.1 - New resilient infrastructure constructed in response to climate change impacts, including variability. | 3539891 | June 2024 (Procurement Process) delays expected/ extension request needed
| Output 3.1 - Project activities and results are captured and disseminated through appropriate information for the beneficiaries, partners and stakeholders and the public in general | 15000 | 2022-06-01 |  | Output 3.1 - Project activities and results are captured and disseminated through appropriate information for the beneficiaries, partners and stakeholders and the public in general | 7500 | 2023-06-01
| Output 3.2 - Climate policy - especially the National Adaptation Plan and post-Paris agreement reporting - influenced to reflect the challenges of climate change adaptation in basic service and protective infrastructure, including the provision of infrastructure in a way that benefits women | 10000 | 2022-06-01 |  | Output 3.2 - Climate policy - especially the National Adaptation Plan and post-Paris agreement reporting - influenced to reflect the challenges of climate change adaptation in basic service and protective infrastructure, including the provision of infrastructure in a way that benefits women | 8500 | 2023-06-01
| Programme Execution | 212443.08 | 2022-06-01 |  | Programme Execution | 368464.08 | 2023-06-01
| Programme Cycle Management Costs | 85397.44 | 2022-06-01 |  | Programme Cycle Management Costs | 338723.44 | 2023-06-01
| TOTAL | 3845731.52 |  |  | TOTAL | 4295078.52 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | None | None | n/a | n/a | Two AoCs are signed with NPSE Savannakhet to ensure compliance with the law and each stakeholder is clear of their role. Dialogue and cooperations with national and regional government is maintained. | n/a | n/a
2 - Access and equity |  |  | Without any safeguarding measures built into the project, the adaptation benefits of the project may not be distributed equally among the target beneficiaries. It may lead to some people being without benefits | Community management with rules ensuring that equal access is guaranteed. These rules will make clear the equitable access for women and indigenous people to water connections. Further discussion of indigenous people is below, in Marginalised and Vulnerable Groups. The project will seek to prioritise connections to female headed households first. | All indigenous groups have the same access rights to water/infrasrtucture. | Indigenous groups have little or no access to infrastructure or improved, climate resilient water. | Two master plans -which are climate, gender and ethnic- aware- were prepared and are under review. Dialogue and cooperations with national and regional government is maintained. Training materals are prepared using a gender lens to strenghten and encourage female participation. | There was no residual impanct. | No residual impacts.
3 – Marginalized and vulnerable Groups |  |  | Without mitigation measures, the presence of indigenous, female, poor and illiterate people could be marginalized. | Community management with rules ensuring that equal access is guaranteed, including for women and indigenous people. This means that all consultations and meetings should be made accessible in indigenous languages, where people cannot, or do not wish to communicate in the Lao Language. This includes providing all information orally to people, as literacy rates are low throughout the project area. The domestic tariff is a rising 3-block structure to ensure affordability by the low-income group (LIG), this special tariff measures will be created to ensure that poor households have continued access to water supply, despite their low incomes. | See "2 - Access and equity" | See "2 - Access and equity" | See "2 - Access and equity" | n/a | n/a
4 – Human rights |  |  | None | None | n/a | n/a | n/a | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | Without measures to ensure and enhance women’s participation in the project and enable them to benefit from the pro-poor tariff, they may see disproportionately less reduction in their vulnerability | The project has set quotas for female participation and benefit in Components 1 and 2. Engagement will take place throughout the project with the Lao Women’s Union and the Women’s representative, which exists in every village. | Women have equal access, and are included on all village-level management committees. | Few provisions for women to manage infrastructure. | See "2 - Access and equity" | There was no residual impanct. | No residual impacts.
6 – Core labour rights |  |  | Failure to safeguard core labour rights could result in exploitation, underpaid or insecure work, hence why mitigation measures are needed | All community contracts must be scrutinised to ensure they comply with both national law and international standards. Where community members provide their labour to the project, they will be paid above minimum wage, the right to organise, and access to all required safety and protective equipment. Women will be provided with access to separate bathrooms and sanitation facilities. | Everyone working for the project is at least 18, and is formally contracted. | No one is employed to work on infrastructure resilience. | n/a - construsiton has not been started. | n/a - construsiton has not been started. | n/a - construsiton has not been started.
7 – Indigenous peoples |  |  | See "3 – Marginalized and vulnerable Groups" | See "3 – Marginalized and vulnerable Groups" | See "3 – Marginalized and vulnerable Groups" | They have minimal access to infrastructure. | n/a - construsiton has not been started. | n/a - construsiton has not been started. | n/a - construsiton has not been started.
8 – Involuntary resettlement |  |  | None | None | n/a | n/a | n/a | n/a | n/a
9 – Protection of natural habitats |  |  | Without mitigation measures, river habitats (and thus fish and aquatic plant life) could suffer | Incorporating protection of habitats and ecosystems into action planning. Designing infrastructure so that it complements nature. Specific design provisions have been made in both cases to minimise the risks. In the case of Sethamouak, the dam is only 1.5m high, meaning that in the rainy and early part of the dry season (up to 9 months in total), the water will flow over the dam, while the strengthened embankment will prevent any flooding and/or erosion in the area around the dam. The dam has been designed with a 1.5m wide weir so that water still flows unimpeded. The IEE finds that this will not affect the availability of water downstream or the ability of fish to swim up and down the river, as the water can pass through the weir for 16-18 hours per day in the dry season. | No negative affects on the natural environment. | The natural environment has been threated by other infrastructure development projects. | n/a - construsiton has not been started. | n/a - construsiton has not been started. | n/a - construsiton has not been started.
10 – Conservation of biological diversity |  |  | None | None | n/a | n/a | n/a | n/a | n/a
11 – Climate change |  |  | Without mitigation measures, the infrastructure may not function properly. This is particularly prevalent in Sethamouak Town, and extensive provisions have been incorporated into the design. | Climate Change policies and guidelines to be explained to understood by project personnel prior to implementation and monitored by implementing partners. The infrastructure at Sethamouak is designed to continue functioning at 30cm river depth. This is less than half the estimated known lowest point of the river during the dry season, meaning the infrastructure can continue functioning, even if the trend of a prolonged dry season continues – unlike ground water systems that are already becoming inviable in the area. | Climate adaptation and mitigation measures are mainstreamed through project implementation. | Existing infrastructures do not consider climate change effects. | See "2 - Access and equity" | There was no residual impanct. | No residual impacts.
12 – Pollution prevention and resource efficiency |  |  | Improper waste disposal and management procedures would lead to pollution of the local area with waste associated with construction. This could cause damage to land and soil, water and the local area generally | Incorporating waste management and disposal into design and operating procedures for the construction | All materials used in construction are properly disposed of. | Waste disposal systems are not always in place. | See "9 - Protection of natural habitats" | There was no residual impanct. | No residual impacts.
13 – Public health |  |  | Failure to incorporate public health into the design could lead to the spread of water and vectorborne disease. | Incorporating public health considerations (Especially relating to water contamination) | All water provided meets Ministry of Health guidelines | Public health issues are common in the target areas. | Dialogue and cooperations with national and regional government is maintained. | There was no residual impanct. | No residual impacts.
14 – Physical and cultural heritage |  |  | None | None | n/a | n/a | n/a | n/a | n/a
15 – Lands and soil conservation |  |  | None | None | n/a | n/a | n/a | n/a | n/a
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, but no unanticipated ESP risks occurred, aside from those planned for. See monitoring measures below, designed to caputre all risks before and during contruction. None occurred beyond this.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE has briefed the PMC and EE on the implementation arrangement of ESP safeguard measures. This is also reflected in the Agreements of Cooperation developed with the EE
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Village chiefs have been made aware of the ESP and the grievance mechanism. All contractors were requested to follow the ESP as per the project document
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | (The approved project document does not contain USPs arrangements, therefore section 5 should not be completed.)
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | (The approved project document does not contain USPs arrangements, therefore section 5 should not be completed.)
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental/social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | Infrastructure construction process (Component 2) has begun: ITB etc., by EE. (Low risk at present) | Construction works are planned to primarily take place in the dry season. In addition, master plans' revision will ensure that climate change adaptation is mainstreamed, and awareness raising activities will contribute to avoid losing communities' confidence in adaptation measures.
Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. | Government has shown sustained support for the project despite Covid-19 -related disruptions. (Low risk at present) | The PMC met at the beginning of the project implementation, approved the workplan and gave guidance on major activities. The project is ensuring robust participation of Government partners at both the national and sub-national levels.
Institutional: Capacity constraints of local institutions may limit the effective implementation of interventions | Capacity constraints have not yet proved a major barrier to project implementation (Medium risk at present as the project moves toward Component 2) | The project has put capacity building at the forefront of its approach to implementation. Training needs assessment was conducted and training materials were developed. Specific training sessions are implemented to improve the capacities of district, provincial and national government staff. In addition, all consultants engaged by the project have been required, thorugh their terms of reference, to develop instructives that help replicate the experience and build specific technical capacities. IE is also continuously involved in augmenting capacity of district, provincial and national partners.
Institutional/social: Lack of commitment/buy-in from local communities may result in delay at intervention sites. | This risk will become more prominent as component 2 progresses. (Low Risk at present) | Focus group discussions have been organised to increase the engagement of communities and village chiefs.
Institutional/social Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | This has not occurred (Low risk) | All stakeholders are kept briefed of the project.
Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Implementation under Component 2 is underway and no such challenges have yet been encountered. (Low Risk at present) | The project involves and will continue to involve communities in the project implementation ensuring total community participation.
Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Financial commitments are being made, with some delays due to Covid-19 - related impacts. Implementation is revving up leading to substantial financial commitments. (Low Risk at present) | The overall financial and administrative management of the project are governed by established UN rules and regulations. UN-Habitat undergoes periodic member state audit as per established regulations. The activities implemented by the implementing agency, NPSE Savannakhet, is governed by Government of Lao PDR’s established admin and financial regulations, which are subjected to interim and financial audits by external auditors.
Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions | Infrastructure interventions-related processes have just begun. There were some delays due to lockdowns and related measures. The project requires a 12-month no-cost extension and pushing back of the MTR accordingly. (Medium risk at present) | Project implementation schedule is constantly revised with implementing partners to re-arrange activities and make sure that the project is on track despite challenges.
Institutional: A lack of coordination between and within national government Ministries and Departments. | Ministries have played an active role in supporting the project implementation (Low risk at present) | Actions taken to mitigate risks 2 and 3 ensure that coordination between and within ministries and other government agencies continues to be effective
Legal: Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues. | No legal issues have happened or are foreseen (Low risk at present). | The PMC and the LCC are tasked to ensure close collaboration with the provincial line departments of Public Works and Transport, Natural Resources and the Environment, NPSE Savannakhet and Planning and Investment.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic challenges programme implementation. | The pandemic outbreak that begun in April lead to strengthened lockdown measures due to community transmission in sevevral provinces. Border closure and lockdown continue to date, as measures are being revised periodically. | Flexible planning and online communication channels were explored to ensure programmme progress. IE staff were vaccined to reduce health risks.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
None in addition to the above

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | A limited assessment was conducted - the training related assessment has been done, while the infrastructure related assessment has not because the construction has not yet started. However, detailed gender policy plan was put forward until the complecation of construction and integrated in the results tracker.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Outcome 1.1 - 40 government staff, at least 15 of whom female, have increased capacity to design climate resilient urban infrastructure in small towns | Outcome | Number of trainees - sex disaggregated; Training materials | 0 | At least 15 female trainees have increased capacity to design climate resilient urban infrastructure in small towns | satisfactory
Output 1.1.1 Training provided to district, provincial and national government staff on resilient infrastructure design. Female government staff must be represented | Output | Number of government staff trained, disaggregated by sex | 0 | 40 government staff trained, 15 of whom are female. | satisfactory
Outcome 1.2 - 60 government staff, at least 20 of whom are female, have capacity to develop climate resilient town master plans and two master plans approved, that support the development of resilient infrastructure, serving 57,144 people, 53.5% of whom are female. | Outcome | Number of trainees - sex disaggregated; Training materials; masterplans that contain specific activities, targets and objectives for women; Focus group Discussion documentation (photographs, attendance, etc) | 0 | 60 government staff, at least 20 of whom are female, have capacity to develop climate resilient town master plans and two master plans approved, that support the development of resilient infrastructure, serving 57,144 people, 53.5% of whom are female. | satisfactory
Outcome 1.2 60 government staff, at least 20 of whom are female, have capacity to develop climate resilient town master plans and two master plans approved, that support the development of resilient infrastructure, serving 57,144 people, 53.5% of whom are female. | Output | No. of staff trained disaggregated by sex | 0 | 60 staff, 20 of whom female, trained | satisfactory
Output 1.3.1 Two master plans developed, using knowledge generated by the project, to both provide sustainable adaptation benefits to the infrastructure designed under this project and to enable the government to better plan for adaptation in other infrastructure, beyond that in the project area | Output | Developed adaptation plans | 0 | 60 staff trained, 20 of whom female. 2 masterplans developed. The master plans will include specific provisions for the development and climate change resilience of women. | satisfactory
Outcome 2 - 57,144 people, 53.5% of whom are female, who currently have inadequate water and/or protective infrastructure, have access to year-round, clean water and protective infrastructure despite current climate hazards and future changes in climate | Outcome | Focus group Discussion documentation (photographs, attendance, etc) | 0 | 57,144 people, 53.5% of whom are female, have access to affordable, clean and climate-resilient water supply | N/A
Outcome 3 - Project implementation is fully transparent. All stakeholders, including women, are informed of products and results and have access to these for replication. | Outcome | Case studies; Other awareness-training materials | 0 | At least 100, including at least 35 women, government staff are aware of the project’s activities and have improved knowledge and capacity to replicate its benefits | N/A
Output 3.2 Climate policy – especially the National Adaptation Plan and post-Paris agreement reporting – influenced to reflect the challenges of climate change adaptation in basic service and protective infrastructure, including the provision of infrastructure in a way that benefits women | Output | NAP and post-Paris climate policies and reporting reflect urban adaptation and basic service provision priorities, and issues relating to women | National Climate change related policies show some consideration of urban infrastructure adaptation | NAP and all post-Paris climate policy thoroughly reflects urban and basic service adaptation priorities | N/A
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Encouraging EE and government partners to promote female representatives and participants at trainings and events. Capacity needs assessment was conducted with an emphasis on gender equality.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, partially, There has been an increase in female voices in the capacity needs assessment, which will add female representation in the following trainings. However, the baseline is very low and very few women work in government departments, especially at sub-national level. Almost all village chiefs are male.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EE has ensured that women have greater involvement in decision making, especially at the village level, and especially with regard to ESP compliance (see previos tab). Community level WATSAN committees will include at least 30% women representatives.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. There has been an increase in female voices, which may lead to increased female attendance in trainings. However, the baseline is very low and very few women work in government departments, especially at sub-national level.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | None per se. However, as above, the project is working with a very low baseline of women presence at the sub-national level
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1.1 40 government staff, at least 15 of whom female, have increased capacity to design climate resilient urban infrastructure in small towns |  | Outcome 2 |  | Conduct training. |  | (i)traning needs assessement conducted in 5 to 7 of April 2022; (ii)24 of May 2022 conducted training on "resilient infrastructure design"totaling of 44 participants of which 13 were women; (iii) 25 of May 2022 conducted training on "climate mainsteamed urban planning"totaling of 48 participants of which 14 were women | S
| Outcome 1.2 60 government staff, at least 20 of whom are female, have capacity to develop climate resilient town master plans and two master plans approved, that support the development of resilient infrastructure, serving 57,144 people, 53.5% of whom are female. |  | Outcome 2 |  | Submit two master-plans for review. |  | Draft of two town-level master plans submitted and reviewed by government institutions and supposed to present to Savannakhet provincial assembly by end of March 2023. | S
| Outcome 2 57,144 people, 53.5% of whom are female, who currently have inadequate water and/or protective infrastructure, have access to year-round, clean water and protective infrastructure despite current climate hazards and future changes in climate |  | Outcome 4 |  | Start construction. |  | In progress | S
| Outcome 3 Project implementation is fully transparent. All stakeholders, including women, are informed of products and results and have access to these for replication. |  | Outcome 1 |  | Develop local language guidance and tools. |  | In progress | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Avi Sarkar | pveovaranh@yahoo.com | pveovaranh@yahoo.com | pveovaranh@yahoo.com | pveovaranh@yahoo.com | pveovaranh@yahoo.com
| Email: | avi.sarkar@un.org | pveovaranh@yahoo.com | pveovaranh@yahoo.com | pveovaranh@yahoo.com | pveovaranh@yahoo.com | pveovaranh@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall progress has been behind the original schedule because the project sites in Savannakhet has been severely affected by Covid-19. During the reporting period (5 June 2021- 4 June 2022), there were several lockdowns in the province including the restriction of gathering more than 10 people. Much of the government's resources and capacity of EE were dedicated to Covid-19 relief efforts. Despite the difficult challenges, the project has made credible progress and this is the reason to rate the progress as satisfactory. Please note that the national and provincial lockdown information is available in the "Lockdown info_Laos" tab.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1.1 40 government staff, at least 15 of whom female, have increased capacity to design climate resilient urban infrastructure in small towns |  | Outcome 2 |  | Conduct training. |  | (i)traning needs assessement conducted in 5 to 7 of April 2022; (ii)24 of May 2022 conducted training on "resilient infrastructure design"totaling of 44 participants of which 13 were women; (iii) 25 of May 2022 conducted training on "climate mainsteamed urban planning"totaling of 48 participants of which 14 were women | HS
| Outcome 1.2 60 government staff, at least 20 of whom are female, have capacity to develop climate resilient town master plans and two master plans approved, that support the development of resilient infrastructure, serving 57,144 people, 53.5% of whom are female. |  | Outcome 2 |  | Review two master-plans. |  | Draft of two town-level master plans submitted and reviewed by government institutions and supposed to present to Savannakhet provincial assembly by end of March 2023. | S
| Outcome 2 57,144 people, 53.5% of whom are female, who currently have inadequate water and/or protective infrastructure, have access to year-round, clean water and protective infrastructure despite current climate hazards and future changes in climate |  | Outcome 4 |  | Start construction. |  | In progress. Survey, design, bidding etc. have been completed. | HS
| Outcome 3 Project implementation is fully transparent. All stakeholders, including women, are informed of products and results and have access to these for replication. |  | Outcome 1 |  | Develop local language guidance and tools. |  | In progress | S
[7 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Xayasene Keovilaysack
| Email: | xayasene.k@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Overall progress is highly satisfactory, considering the impact of COVID-19. Savannakhet had been highly impacted for nearly 24 months as this province is strategically located bordering with Thailand and Viet Nam. This has resulted in high caseload of COVID and engaging the entire provincial government machinery to support this effort. Thus, this project is overall behind the original schedule but considering the achievements in this difficult situation, I am providing the overall rating to be highly satisfactory.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Lockdown info_UNH added
# | Area | From | To | Lock-down type | International boundary | Internal travel | Gathering ppls | Others
1 | Savanakhet | 21 May 2021 | 04 June 2021 | Strict Lockdown | Closed | - Within the city was not allowed from 10 pm to 4 am -Travel between provinces was not allowed unless it was an emergency case | more than 10 people was not allowed | All shops, shools closed except necessary ones like the Pharmacy, and Grocery stores
2 | Savanakhet | 9 August 2021 | 23 August 2021 | Strict Lockdown | Closed | - Do not allow people to enter red zones - travel within the city is not allowed from 9 pm to 5 am - Provincial boundary closed - People living in Kaysone city are only allowed to go out of their homes for necessities such as buying food, going to the hospital, etc. University and Schools closed
3 | Savanakhet | 24 Aug 2021 | 05 Sep 2021 | Strict Lockdown | Closed | - Within the city was not allowed from 10 pm to 4 am -Travel between provinces was not allowed unless it was an emergency case | more than 10 people was not allowed | All shops, shools closed except necessary ones like the Pharmacy, and Grocery stores
4 | Savanakhet | 1 Oct 2021 | ? (1 Nov 2021?) | Lockdown on red zones |  | - within the city was not allowed from 9 pm to 5 am -Do not allow people traveling from/to provinces classified as the red zone |  | - Do not allow people to enter red zones - Schools closed -Activities and events are not allowed
5 | National | 15 Jun 2020 | 31 Jul 2020 | Relaxed | Closed | Most of the companies in Laos were allowed to resume operations. Some entertainment venues are still closed. the regulations for public and private events have been further relaxed. | Meetings of more than 50 people are also still prohibited.
6 | National | 2 Sep 2020 | 20 Sep 2020 | Relaxed | Closed | Domestic journeys within Laos have been possible either by airplane or with bus and rental car. | Meetings of more than 50 people are also still prohibited.
7 | National | 20 Sep 2020 | 13 Apr 2021 | Relaxed | Limited | Domestic journeys within Laos have been possible either by airplane or with bus and rental car. | Meetings of more than 50 people are also still prohibited. | Persons entering Laos must go into quarantine for at least 14 days after entry. On arrival in the country a health check will be carried out.
8 | National | 13 Apr 2021 | 22 Apr 2021 | Increased Enforcement | Closed | All entertainment facilities have been ordered closed. | Large gatherings have been forbidden. | There will be increased enforcement of previously announced COVID-19 restrictions.
9 | National | 22 Apr 2021 | 5 May 2021 | Strict Lockdown | Closed | Travel in or out of Vientiane Capital is prohibited except for cargo trucks. Reidents may only leave their houses for essential tasks. | Gatherings of more than 20 people (except for funerals) are prohibited.
10 | National | 17 May 2021 | 4 Jun 2021 | Lockdown on red zones | Closed | Village offices and essential government offices may open, while emergency service vehicles and personnel must be allowed entrance to red zones. Garbage collection vehicles will also be granted access. | Residents of red zones may not leave their homes unless absolutely necessary, and may not hold family gatherings, parties, social engagements, meetings, or conferences of any kind. | The country has 44 quarantine centers open as thousands of laborers return home to Laos from neighboring Thailand, with those who have symptoms consistent with Covid-19 isolated and tested.
11 | National | 4 Jun 2021 | 19 Jun 2021 | Full Lockdown | Closed | Air and road passenger transport between Vientiane and the provinces is permitted. Passengers who have had two doses of Covid-19 vaccine for one month do not need to quarantine for 14 days. | Meetings may be organised outside red zones but participants must sit one metre apart. | Continue in areas of infection known as red zones, while some virus control measures have been eased.
12 | National | 19 Jul 2021 | 3 Aug 2021 | Extended Lockdown | Closed | Entry into red zones will remain prohibited, except for persons authorized by the Taskforce or local authorities. | Gatherings or parties of any kind may not be held at any location. | All factories and handicraft operations in red zones are to close, except for those wherein employees have received two doses of Covid-19 vaccine, and have dormitories on site, or those producing essential materials.
13 | National | 19 Sep 2021 | 30 Sep 2021 | Full Lockdown | Closed | Residents are prohibited from leaving the capital or infected areas unless authorised by a Covid taskforce. All passenger transport services will be suspended. | Meetings, gatherings, parties and all other activities including cultural events, weddings and religious gatherings are forbidden. | Local and international border crossings will be closed to everyone, except for those authorised to travel by a Covid taskforce.
14 | National | 3 Dec 2021 | 4 Feb 2022 | Relaxed | Closed | Drivers of transport trucks and their assistants may drive to their destination province without having to unload goods and change trucks as before. They are also not required to be tested for Covid-19 or spend 14 days in quarantine. | Funerals are permitted but those attending must comply with all Covid control guidelines. | As of 22 dec, domestic flights (by Lao Airline) may only be travelled on by persons who have full vaccination protection as well as a travel permit from the COVID Task Force Committee.
15 | National | 4 Feb 2022 | 9 May 2022 | Eased | Open | Permitted | Permitted | The quarantine regulations for travellers to Laos have been eased, allowing business travellers to leave quarantine after only 48 hours, and package tourists after only 7 days. Previously, a uniform quarantine of 14 days was a prerequisite for entry into Laos.
16 | National | 9 May 2022 | Now? | Eased | Open | Permitted | Permitted | Travellers can enter the country without quarantine. Unvaccinated persons provide proof of an antigen test upon entry (not older than 48h), while fully vaccinated persons may enter without restrictions.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Lao People's Democratic Republic |  |  |  | Sayphouthong | 48188
Region | Asia-Pacific |  |  |  | Sethamouak | 8956
Sector | Multi-sector |  |  |  |  | 57144
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 |  | Total | 57144 | 57144 |  | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% |  | % of female beneficiaries | 53.5% | 53.5% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 57144 | Inland flooding | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 53.5% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 2 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 100 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 35% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 35% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 2 |  | 2: Partially effective | Catchment area/Watershed/Aquifer | 2 |  | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 5: Very effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 | Level of capacity at the subnational level increased | Capacity to autonomously plan adaptation projects at the sub-national level is limited | Traning needs assessed and training materials prepared accordingly | 5 New adaptation projects prepared by sub-national staff
Output 1.1.1 | Number of government staff trained, disaggregated by sex | There is constrained capacity for government staff to plan for new resilient infrastructure | The training needs assessment (TNA) has been conducted to select the trainee group. | 40 government staff trained, 15 of whom are female
Outcome 1.2 | Comprehensive adaptation action plans in place for Sayphouthong and Sethamouak Towns | 0 | Two town-level master plans prepared and under government review | Sayphouthong and Sethamouak Towns have comprehensive adaptation action plans in place that consider infrastructure, as well as economic, social and environmental adaptation actions beyond the life of this project.
Output 1.2.1 | No. of staff trained disaggregated by sex | There is very limited capacity at all levels to plan for climate change adaptation actions | The training needs assessment (TNA) has been conducted to select the trainee group. | 60 staff, 20 of whom female, trained
Output 1.3.1 | Developed adaptation plans | 0 | Two town-level master plans are prepared and under government review | 60 staff trained, 20 of whom female. 2 masterplans developed. The master plans will include specific provisions for the development and climate change resilience of women.
Outcome 2 | The target population has access to clean, year-round water supply, which is able to withstand current and anticipated future climate extremes | 0 | Relevant activities are in progress | 57,144 people, 53.5% of whom are female, have access to affordable, clean and climate-resilient water supply
Output 2.1 | Physical infrastructures and connections in place | 0 | The activity is in progress | 2 water supply systems constructed that are able to continue functionality in present and anticipated future climate conditions
Outcome 3 | Level of awareness at the local and national level of climate change adaptation actions and potential for replication | Awareness of the need to take adaptation actions and the potential for replication remains very low aside from specialists in climate change adaptation | Ongoing | At least 100, including at least 35 women, government staff are aware of the project’s activities and have improved knowledge and capacity to replicate its benefits
Output 3.1 | No. of knowledge products generated by the project (knowledge products could be newspaper articles, published case studies and tools or guidelines) | 0 | Project brochure produced and disseminated; Keys vulnerabilities assessment guidelines of Sethamouak and Sayphouthong towns produced; Guidelines on resilient infrastructure design produced and Manual on urban planning for small town developed. | At least 20 knowledge products generated by the project by its end (see indicators column)
Output 3.2 | NAP and post-Paris climate policies and reporting reflect urban adaptation and basic service provision priorities, and issues relating to women | National Climate change related policies show some consideration of urban infrastructure adaptation | Relevant activities are in progress | NAP and all post Paris climate policy thoroughly reflects urban and basic service adaptation priorities

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Although communication with the government has been fluid, COVID-19 outbreak in the country has challenged project implementation. Lessons learned: keeping government partners informed and engaged is critical throughout the project life-cycle; adaptation and flexibility are key to overcome the challenges posed by uncertain pandemic situation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There have been some delays in implementation. The causes are 1) the unexpected outbreak in the country that drove part of the workforce of IE to COVID-response; 2) the lockdown and quarantine measures in the country for over 24 months added difficulty to communication and activity implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | -
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, environmental and social safeguards have been effective in avoiding unwanted negative impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations have been applied through encouraging EE and government partners to promote the attendance of female representatives in meetings. However, it remains a challenge to engage women at sub-national government level, for example, due to a lack of female staff.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No