## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 2020-06-15 to 2021-06-30
| Project Title: | Adapting to Climate Change through Integrated Risk Management Strategies and Enhanced Market Opportunities for Resilient Food Security and Livelihoods
| Project Summary: | The overall goal of the project is to enhance climate adaptation and food security of households through access to integrated climate risk management strategies and structured market opportunities. The project will benefit 85,000 households, 382,000 beneficiaries in Balaka, Machinga and Zomba districts for a period of 5 years. The project will achieve the project goal by; 1. Improving access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity; 2. Adopting climate-resilience agriculture practices among targeted farmers thereby contributing to the integrated climate risk management approach; and 3. Strengthening market access strategies and approaches for smallholder farmers.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Food programme (WFP) Malawi Country Office | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Malawi | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Machinga District: Traditional Authorities (TAs) Chiwalo, Kawinga, Sale, Nyambi, Kapoloma, Nkoola, Mchinguza, Nkula and Mposa | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
Balaka District: TAs Toreza, Sawali, Matola, Chanthunya, Amidu, Phalula; Nkaya and Nsamala
Zomba District: TAs Ntholowa, Mbiza, Nkagula, Nkapita and Ngwerero
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-10-11
IE-AFB Agreement Signature Date: |  | 2020-02-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-06-15 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2022-12-01
| Original Completion Date: | 2025-06-30
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | The Project Inception Report was submitted in September 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | Project website not yet developed | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Gilbert Kupunda (National Project Coordinator) | Dominican Republic
| Email: | gkupunda@gmail.com | Ecuador
| Date: | 2020-07-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Peter K. Simbani (Director, Debt & Aid Management Division) | Equatoral Guinea
| Email: | pksimbane@finance.org.mw, secpsdad@finance.gov.mw | Eritrea
| Date: | 2019-01-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Kathy Derore (Resilience Outcome Mananger) | Fiji
| Email: | kathy.derore@wfp.org | Finland
| Date: | 2020-07-01 | France
| Executing Agency |  | Greece
| Name: | Gertrude Kambauwa (Director for Land Resources Conservation Department) | Grenada
| Email: | gkambauwa@gmail.com | Guatemala
| Date: | 2020-07-01 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 30th June 2021
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30th June 2021 | 1575269
Add any comments on AF Grant Funds. (word limit=200) | The above figures incudes: USD 861,850.73 of actuals; USD 711,462.59 of commitments; USD 1,955.34 of precommitments. Indirect Suport Costs (ISC) are included.
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (US Dollars)
| Output 1.1 A weather index microinsurance product designed for drought and dry spells to cover farmers’ needs at scale. | 425123.5161
| Output 1.2 Awareness raised among farmers on weather index insurance and vulnerable farmers enabled access to weather index micro insurance | 20792.1126
| Output 1.3 Strengthen national capacities and systems to provide weather index insurance working with private and public sectors | 12012.2323
| Output 1.4 Support inclusion of insurance as risk transfer mechanism in national agriculture programmes | 0
| Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation | 33846.3074
| Output 2.2 Promote climate resilient agriculture among farmers through extension service support | 15070.6014
| Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops | 8969.6344
| Output 2.4 Provide climate services to inform livelihood decision making amongst farmers | 53685.7439
| Output 2.5 Strengthened access to and use of weather/climate information for targeted communities to inform livelihood decision-making among farmers | 0
| Output 3.1. Strengthened financial capacities and market access opportunities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy) | 0
| Output 3.2 Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced | 32004.6
| Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses | 0
| Output 3.4. Market information provided to inform business planning and activities. | 0
| Output 3.5. Smallholder procurement promoted through government and private sector strategies and programmes | 0
| Total output cost | 601504.7481
| Project Execution Costs | 207744.7619
| MIE fee (including ISC) | 52601.22
| TOTAL | 861850.73
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 A weather index microinsurance product designed for drought and dry spells to cover farmers’ needs at scale. | 519396.24 | July 2021 -June 2022
| Output 1.2 : Awareness raised among farmers on weather index insurance and vulnerable farmers enabled access to weather index micro insurance | 135128.71 | July 2021 -June 2022
| Output 1.3 Strengthen national capacities and systems to provide weather index insurance working with private and public sectors | 55808.9202 | July 2021 -June 2022
| Output 1.4 Support inclusion of insurance as risk transfer mechanism in national agriculture programmes | 7835.4603 | July 2021 -June 2022
| Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation | 421405.3353 | July 2021 -June 2022
| Output 2.2 Promote climate resilient agriculture among farmers through extension service support | 149519.9561 | July 2021 -June 2022
| Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops | 83196.8141 | July 2021 -June 2022
| Output 2.4: Provide climate services to inform livelihood decision making amongst farmers | 169598.3871 | July 2021 -June 2022
| Output 2.5. Strengthened access to and use of weather/climate information for targeted communities to inform livelihood decision-making among farmers | 8134.1901 | July 2021 -June 2022
| Output 3.1. Strengthened financial capacities and market access opportunities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy) | 436976 | July 2021 -June 2022
| Output 3.2. Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced | 391082.4542 | July 2021 -June 2022
| Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses | 591594.1237 | July 2021 -June 2022
| Output 3.4. Market information provided to inform business planning and activities. | 29309.4053 | July 2021 -June 2022
| Output 3.5. Smallholder procurement promoted through government and private sector strategies and programmes | 31107.6594 | July 2021 -June 2022
| Project Execution Costs (PEC) | 385826.4552 | July 2021 -June 2022
| MIE fee | 224833.4196 | July 2021 -June 2022
| GRAND TOTAL | 3640753.5305

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Unavailability of weather and climate data in the targeted district for analysis | Low | The planning process for the Participatory Integrated Climate Services Approach (PICSA) roll-out plan for the 2020/21 planting season in Machinga district was affected, due to a gap in the district context climate products for implementation of the methodology. This is mainly because the government has not yet introduced the methodology to the district at the project onset. Development of the climate products required analysis of historical data amongst others which could not be done as the project inception coincided with the appropriate time for implementation of the PICSA methodology. As such farmers were only sensitised on the general 2020/21 agricultural seasonal outlook during the reporting period and also targeted beneficiaries for the crop insurance project component were enrolled. However, the project in close collaboration with Department of Climate Change and Meteorological Services (DCCMS) resolved this issue in the 1st quarter of 2021.Climate products for the district have thus been developed and rain gauges have also been installed in all the project districts to enhance rainfall data collection.
Partners' failure to integrate the project activities into their regular work (framework) | Low | Despite the COVID-19 pandemic, the project has been successful to include project activities within National, district and local level planning workplans and ensured that the project is included in regular planning and review meetings. It also should be noted that the organizational structure with the 3 district level AF field offices has resulted in good collaboration among all stakeholders. Joint monitoring and evaluation activities are being planned and implemented, including several missions from national level and successful conclusion of 1 technical advisory mission and 1 project steering committee mission.
Humanitarian emergency – A medium/large scale humanitarian emergency occurs in the country, necessitating a diversion of focus for key executing partners and stakeholders. | Low | The ability of the project team to launch the inception workshop, while adhering to government guidelines and making required adjustments at ground level resulted in the project team to ensure roll-out and continuation of project activities even during actual peak periods of the Covid-19 pandemic.
Low stakeholder support/buy in for the project – Key stakeholders do not participate fully in project activities. | Low | Relevant stakeholders have been thoroughly engaged during the project on-set and will continue throughout the project implementation period. The project team with the technical support of WFP has been holding regular review meetings (including one Participatory Integrated Climate Services for Agriculture (PICSA) learning event) and also has developed a more proactive approach to activities including PICSA and insurance design planning for the 2021/22 planting season. Various stakeholders also participated in Catchment Conservation and Management Campaign launch.
Lack of risk diversification and operation in high risk zones may discourage insurance partners | Low | Climate Vulnerability was one key criteria for selecting the targeted districts. Within the targeted districts, additional factors were considered in selection of insurance beneficiaries. Priority was given to households with farming as their main source of livelihood, households with labor, female headed households, households keeping orphans and households with children enrolled in nutrition therapeutic programmes. Even though a selected group of people are targeted under the insurance project component, the project promotes adoption of the crop insurance scheme even to non-project beneficiaries increasing the business case for partners and ensuring that they are able to operate in the context. The approach presents a business opportunity to the insurance sector while increased independent farmer enrollement into the crop insurance policy scheme will lead to reduced climate vulnerability amongst the farmers in the project impact areas due to the risk transfer. During the 2nd quarter and 3rd quarter of 2021, a series of discussions and planning sessions are being held with all insurance partners (members of Insurance Association of Malawi) and Pula to improve the understanding by the insurance partners of the scale of the programme and the potential business case for the insurance sector to engage more proactively in the Area Yield Index Insurance (AYII)-product. Providing clarity on roles and responsibilities of all stakeholders. The project is also promoting climate-resilient agriculture interventions such as Soil and Water conservation.
Political risk considering elections (presidential, parliamentary, and local government elections) | Low | The team reduced the effects by establishing strong operational partnerships with various national organizations and engaging in advocacy. The inception meetings at district and community levels also significantly helped in getting the buy-in from the various stakeholders at district and community levels
Technical Capacity of government partners | Low | Capacity strengthening has been prioritized throughout the project reporting period, both internally for the AF team and with partners/stakeholders. As unexpected constraints relating to the capacities of national partners could result in delays in implementation as well as low quality project outputs, the project will continue to develop partnerships with a broad range of development organizations to ensure sustainability and limit risks. WFP as technical advisor also included the AF team within a series of 13 (1/2 day) trainings sessions on WFP's own integrated resilience programme to further enhance the project team's capacity in implementation of the climate reilient agriculture programme.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Bushfires which would affect Soil and water conservation activities like CA, Afforestation, Natural Tree Regeneration | Medium | The project advocated for establishment of By-laws to curb the practice of unwanted bushfires in the communities at GVH level. Furthermore, the project conducted general sensitisations at community levels prohibiting bushfires.
Covid 19 | Medium | The project conducted a seriese of sensitisations to foster adherance to the Covid-19 preventive and management measures as prescribed by the Governmnet during implementation of project activities. Furthermore, covid 19 personal protective accessories were being provided to project participants/beneficiaries during engagements/implementation of project activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Implementation of risk mitigation measures is continuous throughout the project implementation cycle. Stakeholder capacity strengthening through various trainings has been done during the reporting period to ensure quality delivery of project activities. The use of local coordination structures such as Area Stakeholder Panels (ASPs) and Village Agriculture Committees (VACs), established by the government and use of locally available material resources in support of project activities implementation in particular soil and water conservation has been identified as an essential risk mitigation measure for fostering community ownership of the project processes and results, hence minimizing the risk of activity discontinuity after the project ends. The use of already existing local coordination structures is very much in line with the overall project operational arrangements of using the government machinery for sustainability and capacity building. This is very essential as opposed to creation of project specific local coordination structures (at community level) for long-term sustainability and follow-up. Synergy building with other on-going activities in the same project implementation sites has also been key during the reporting period and will remain as such during the entire project implementation period to minimize risks of double dipping, duplication of efforts and maximize benefits. In addition, there has been 2 project review and planning meetings with the WFP CO team and one oversight spot-check mission on financial reconciliation and procurement processes. This has resulted in a reduced risk on financial accountability. Furthermore, WFP HQ provided 2 training sessions on financial accounting and budget management for AF projects.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | No risk | NA | NA | NA | N/A | N/A | N/A
2 - Access and equity |  |  | Interferance with access to basic services or exacerbate existing inequities by the youth, elders and women in targeted communities | Use of the community based participatory planning methods making sure to incorporate the representation and opinions of all, with a principal focus on the typically marginalized, develop project strategy for ensuring access and equity, promote establishment and use of bylaws, establish Complaints and Feedback Mechanism (CFM) for all project sites | Number of complaints raised in relation to access and equity | 0 | Community based participatory methodologies were employed during annual workplan development as well as during periodic project reviews. A complaints and Feedback mechanism has been established and an operationa manual has been developed, A series of beneficiary sensitisations were conducted promoting access and equity for the assets established under the project. | None | None
3 – Marginalized and vulnerable Groups |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
4 – Human rights |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Limited consideration of various gender needs and exacerbated gender disparities | Target atleast 50% women in project beneficiary identification as well as project activity implementation | Percentage of women in leadership positions in project impact areas | less than 40% | Deliberate efforts were made during project beneficiary targeting to ensure that more than 50% women were targeted. A series of sensitisation sessions were also conducted with the project beneficiaries to enhance consideration of the women in leadership positions during establishement of the project committees. As such atleast 40% representation of women in the project committees was attained. | None | None
6 – Core labour rights |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | Establishment of construction sites for aggregation centres as well as irrigation schemes may involve clearing of the land hence potentially negatively affecting natural habitats | Each beneficiaries of both the irrigation schemes and aggregation centres will be required to plant back a minimum of 20 trees in their homestead and also establish a communal woodlot. Furthermore, the beneficiaries are being encouraged to actively take part in implementation of other soil and water conservation activities like Conservation Agriculture. Implementation of intergrated watershed management activities is also enhancing protection of the natural habitats. | Number of trees replanted by households in the areas where irrigation schemes and aggregation centres will be contructed and number of woodlots established. Number of watersheds delineated and rehabilitated. | 0 | During the reporting period, beneficiaraies have been sensitised on these complementary activities they will be required to implement as beneficiaries of irrigation schemes and aggregation centres. Some of the beneficiaries have already started establishment of tree nurseries in support of this. About 33 catchments have been dilineated during the project reporting period across the three project districts and implementation of various intergrated catchment management activities is underway. | None | None
10 – Conservation of biological diversity |  |  | Deterioration of biological diversity if seed and crop types are not correctly selected (e.g. inadvertent introduction of invasive species) and diversified | Prioritize local species and avoid the use of non-native and invasive species. Additionally, these activities will be designed in close collaboration with the MoAIWD. By working with local leaders and village chiefs to rescue traditional and native plants and crop species, this project will support the conservation of biological diversity and increase ecosystem resilience | Hectarage of land in the impact areas with deteriorated bilogical diversity due to invasive species amongst others | 0 | Implementation of crop diversification project activities has been done with the technical leadership of Crops Officers from the Ministry of Agriculture to ensure that appropriate crops are promoted in the project impact areas. | None | None
11 – Climate change |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | Inappropriate waste disposal i.e. polythen tubes during implementation of afforestation and reforestation project internventions | Advocate for reuse of some of the materials i.e. polythene tubes and advocate for proper collection and storage of used polythene tubes (not in reusable state) for selling to plastic manufaturing companies | Number of farmer groups using reusing polythene tubes and number of farmer groups linked to plastic manufacturing componies for sale of used plastics | 0 | Sensitisations have been conducted to the communities about the practice | None | None
13 – Public health |  |  | Increased cases of injuries during physical asset creation project activities | Provision of First Aid kit and beneficiary sensitisation on safety measures during implementation of asset creation activities | Number of First AID kits provided and number of injury cases recorded during physical asset creation project activities | 0 | Procurement of First Aid Kits is underway; beneficiaries sensitised on safety measures during implementation of asset creation activities | None | None
14 – Physical and cultural heritage |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | Increase in run-off, soil erosion and flooding that can cause harm to live and livelihoods. In addition, increased agricultural production and livelihoods may lead to increased investment in livestock which may have an unintended effect on the environment, mostly on soils and water resources. | Selection of the areas for the interventions will be informed by site-specific feasibility studies and aligned with recommendations from the community based participatory sessions. Environmental screening of the project activities. Conduct project beneficiary and frontline staff sensitisations and trainings | Number of communities with increased run-off, soil erosion and flooding induced by the project | 0 | Community based participatory methodologies were employed during annual workplan development as well as during periodic project reviews. Deatiled soil and water conservation trainings were provided to the frontline staff as well as project beneficiaries prior to commencement of project activity implementation. | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes and this is on going. The tools for periodic monitoring of project interventions and ESMPs implementation provides for capturing any unanticipated ESP risks
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As the Implementing Entity, WFP provided the required technical support to the Ministry of Agriculture which is the Executing Entity (EE) of the project to ensure that the project activities are screened and associated environmnetal and social managemnet plans are developed during the reporting period. In this regard, WFP lead production of a harmonised screening tools which was used by the EE. In the periodic project management meetings, as the implementating entity, WFP also ensured that the EE provided adequate implementation progress on the ESMPs. WFP also provided technical support to the project team to build its capacity of employing community based participatory planning approached which was very key in preparation of project annual workplans. Furthermore, in its capacity as IE, WFP provided various reference materials to support project off-take and ongoing implementation i.e. WFPs access and euity strategy, Complaints and feedback mechnism to be tailored by the project. Additionally, technical backstopping services were made available in implementation of the soil and water conservation activities and all other project components to ensure adherance to standards and minimise the identified risks. Gender mainstreaming sessions were also provided to the project team prior to development of project annual workplans.
Have the implementation arrangements been effective during the reporting period? |  | Yes. The regular programme review meetings between the IE and project team has also ensured that the project team remained on track in implementation of the ESMPs and all project components. Provision of technical support and reference materials during development of project workplans and actual implementation ensured adequate integration of ESPs by the EE.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Implementation of the project activities is adhering to the developed ESMP. The various proposed strategies in the ESMPs are being implemented alongside implementation of the project activities. For instance ToRs for construction of irrigation schemes and aggregation centres, includes some of the mitgation measures for the identified risks. Furthermore, protocols for implementation of the project interventions by the communities includes strategies which will help to minise/mitigate the identified risks across the project activities. Additionally, the EE has set up a monitoring system which also tracks implementation of the ESMPs. At National level, the EE has a full time designated Monitoring and Evaluation Officer who works hand in hand with the District Environmental Committee which oversees ESMP implementation and monitoring at District level. At community level, the EE has empowered the Agriculture Stakeholder Panels to support in monitoring of project activities including implementation of the ESMPs.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. Implementation of the ESMPs alongside project activities implementation has ensured that adequate attention was put in minimising/mitgating the risks which were identified. Engagement of relevant technical experts in implementation of the project activities also proved effectives as appropriate approaches were being adopted. Furthermore,both frontline staff and beneficiary engagement and sensitisations/trainings on the identifed Risks and developed ESMPs was fundamental in fostering adherence to the ESMPs and appropriate standards. Development of the manuals and standard operating procedures also proved to be effective. Use of already established structures at district and community level has proved to be key in fostering project sustainability.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Yes arrangements have been put in place in the developed ESMPs. In particular, the USP include afforestation, construction of aggregation centres, construction of irrigation centres, Nursery establishments and woodlots establishments. Appropriate strategies for minimising the identified risks across the USPs have been included in the ESMPs.
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, the required capacity for ESMP implementation is present and effective with both IE and EE. The IE is responsible for monitoring implementation progress of the ESMPs and also provision of technical support. The IE has designated technical focal persons for all the project components i.e. soil and water conservation, crop insurance, smallholder agriculture produce marketing and Village savings and loans. On the other hand, the EE is responsible for disclosure of the ESMPs to the project beneficiaries and all relevant stakeholders. Furthemore, the EE is responsible for actual implementation of the ESMP and reporting of the progress. The EE has appropriate structures in place at all levels to foste implementation of the ESMPs. at National level the EE has the National Project Coordination Unit (NPCU) which amongst others comprises, theNational project coordinator, project componet leads (Soil and Water Conservation, Crop Insurance, Smallholder Agriculture Produce Marketing and M&E). The NPCU works hand in hand with the District project coordination units (DPCUs) in implementation of the project activities which comprise three technical officers (the District Project Coordinator, Assistant District Project Cooridnator and WFP Programme Associate). The DPCUs work in close collaboration with district subject matter speciallists for technical support. Furthermore, the DPCUs work in close collaboration with frontline workers in all the project impact areas, who spearhead activity implementation at community level. Adequate orientation/sensitisations have ben done at all levels on the ESMPs.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes, the ESMPs, were updated with the USPs which were identified during the reporting period, after conducting the screening exercise. In this regard, appropriate implementation strategies were included in the ESMPs.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
BALAKA DISTRICT
USP 1: [Mitengwe Irrigation Scheme Development]: The irrigation schemes will be developed within the space of 5 years project implementation. A screening exercise for the scheme located in Balaka district in Traditional Authority (TA) Nkaya, in Utale Extension Planning Area (EPA) | Not yet because construction of the irrgation schemes is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | loss of trees and vegetation/ Loss of natural habitats of insects | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees ( boundary planting plus agroforestry species. Fruits tree species to be included too | Number of trees planted
[6 empty] | Conduct sensitization meetings on good farming practices | No of meetings conducted and number of farmers reached
|  | Conflicts within the community, with neighboring communities or with workers from outside community | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the guidelines of the project | No. of sensitization meetings conducted and number of cases recorded and reddressed
|  | Increased cases of injuries | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on occupational safety | No. of meetings and Number of cases registered
[6 empty] | Procure First Aid Kit | No of kits procured
|  | Spread of diseases or introduction of new diseases like Covid-19, HIV/AIDS | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing facilities(Pail, basin and soap) | No. of hand washing facilities distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Soil erosion/Siltation | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Promote good farming practices that enhances water and soil conservation | No of hectares conserved
USP 2: [Njobvu Irrigation Scheme Development]: The irrigation schemes will be developed within the space of 5 years project implementation. A screening exercise for the scheme located in Balaka district in Traditional Authority (TA) Sawali, in Bazale Extension Planning Area (EPA) | Not yet because construction of the irrigation schemes is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongst beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Alter the land cover of forests (loss of trees and vegetation) on a less than 1ha land, Loss of natural habitats of insects | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees (Surrounding the centre) | Number of trees planted
[6 empty] | Conduct sensitization meetings | No of meetings conducted
|  | Increased cases of injuries | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Procure and Distribute First Aid Kits | No of Kits Procured and No of cases registered
|  | Loss of soil/ siltation | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Promote good farming practices | No of hectares under soil and water conservation
|  | Conflicts within the community, with neighboring communities or with workers from outside community | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the guidelines of the project | No. of sensitization meetings conducted and number of cases recorded and reddressed
|  | Spread of diseases or introduction of new diseases like Covid-19, HIV/AIDS | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 3: [M'mangeni Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH : Chiendausiku | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | handwashing/sanitary facility (Basin, Pail, soap) | handwashing facilities distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings & acquisition forms signed
|  | Disruption of marriages | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the dangers of sexual relationships | No of meetings conducted and No of cases
USP 4: [Kapasule Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Mackenzie | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No. of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings, acquisition forms signed and No of cases
USP 5: [Chamba Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Toleza, Bazale EPA, GVH Chimkwita | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 6: [Chisawasawa Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Disi | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs, Covid-19, Waterborne diseases | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre | No of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings & acquisition forms signed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 7: [Matola Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Matola, Bazale EPA, GVH Matola | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs, Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
[6 empty] | Procure and distribute masks | No of masks distributed
USP 8: [Mchilakwenda Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Matola, Bazale EPA, GVH Mchilakwenda | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
USP 9: [Mikaele Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Chilumba | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meeting, acquisition forms signed, No of cases
USP 10: [Mpinga Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Kampeni | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings, acquisition forms signed and No of cases
USP 11: [Kalembera Nursery and Woodlot estanblishment]: The screening was conducted in Balaka district, TA Matola, Bazale EPA, GVH Tembo | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Loss of vegetative cover ( Trees) on a land less tha 1ha during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | - (i) Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | - (ii) Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings, acquisition forms signed and No of cases
USP 12: [Mgumbala Afforestationa : The screening was conducted in Balaka district, TA Nkaya, Utale EPA, GVH Nkaya 1 | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
[6 empty] | Conduct sensitization meetings | No of meetings conducted
|  | Conflicts within the community, with neighboring communities or with workers from outside community | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the guidelines of the project | No. of sensitization meetings conducted
|  | Spread of diseases or introduction of new diseases | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
USP 13: [Kayamba Afforestation]: The screening was conducted in Balaka district, TA Nkaya, Utale EPA, GVH Mgomwa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | No of trees planted
|  | Poor waste disposal i.e. polythene tubes | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitisations on proper waste disposal, resuse of polythene tubes | No of sessitisation sessions, number of farmer groups reached and number of farmer groups reusing polythen tube
|  | Spread of diseases or new introduction of diseases (Covid-19, | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct awareness meetings | No of meetings
[6 empty] | Procure and distribute condoms | No of condoms distributed
[6 empty] | -Procure and distribute masks | No of masks distributed
USP 14: [Meleka Afforestation]: The screening was conducted in Balaka district, TA Chakanza, Utale EPA, GVH Chakanza | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Alter the land cover of forests (loss of trees and vegetation) on a less than 1ha land, Loss of natural habitats of insects | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (Covid-19, HIV/AIDS) | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 15: [Jingasiya Afforestationa The screening was conducted in Balaka district, TA khwalala, Utale EPA, GVH Khwalala | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (Covid-19, HIV/AIDS) | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the diseases | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 16: [Maliwata Afforestationa] The screening was conducted in Balaka district, TA Sawali, Bazale EPA, GVH Maliwata | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (Covid-19, HIV/AIDS) | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Provide handwashing facilities | No of facilities provided
USP 17: [Mmanga Afforestationa] : The screening was conducted in Balaka district, TA Sawali, Bazale EPA, GVH Sawali | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases including HIV/AIDS,TB | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 18: [Misowa Afforestationa The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Misowa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
USP 19: [Mkwekwere Afforestationa The screening was conducted in Balaka district, TAAmidu, Ulongwe EPA, GVH Mkwekwere | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
USP 20: [Zilipaiwo Afforestationa The screening was conducted in Balaka district, TA Sawali, Bazale EPA. GVH Chikalongwe | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases including cholera, HIV/AIDS, TB | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 21: [Pilitu Afforestationa The screening was conducted in Balaka district, TA Sawali, Bazale EPA, GVH Pilitu | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
[6 empty] | Conduct awareness meetings on the importance | No of meetings
|  | Land conflicts | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings | No. of meetings and Number of cases registered
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 22: [MlambeAfforestationa ] The screening was conducted in Balaka district, TA Chanthuya, Rivirivi EPA, GVH Siliya | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (HIV/AIDS, Covid-19) | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 23 [Tithandizane Afforestation ] The screening was conducted in Balaka district, TA Chanthuya, Rivirivi EPA, GVH Chimpakati | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (TB, HIV/AIDS) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 24 [KachingwefAforestationa ] The screening was conducted in Balaka district, TA Chanthuya, Rivirivi EPA, GVH Chimpakati | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Proposed Mitigation/enhancement Measures | No of seedlings out planted
[6 empty] | Planting trees | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No of meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of items distributed
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | Number of meetings conducted
[6 empty] | -Distribution of condoms | Number of condoms distributed
USP 25[Talandira/Sakaiko Afforestation ] The screening was conducted in Balaka district, TA Nsamala, mpilisi EPA, GVH Nsamala | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Proposed Mitigation/enhancement Measures | No of seedlings out planted
[6 empty] | Planting trees | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No of meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | Number of meetings conducted
[6 empty] | -Distribution of condoms | Number of condoms distributed
USP 26[Thamanda Afforestation ] The screening was conducted in Balaka district, TA Chanthunya, Rivirivi EPA, GVH Maitoni | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Proposed Mitigation/enhancement Measures | No of seedlings out planted
[6 empty] | Planting trees | No of trees planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No of meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
[6 empty] | Conduct sensitization meetings on the expected behavior from the beneficiaries as well as guidelines of the project | No of meetings conducted
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | Number of meetings conducted
[6 empty] | -Distribution of condoms | Number of condoms distributed
USP 27 [Manjanja Afforestationa ] The screening was conducted in Balaka district, TA Chanthunya, Rivirivi EPA, GVH Manjanja | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 28 [Mulunguzi Afforestationa ] The screening was conducted in Balaka district, TA Chanthunya, Rivirivi EPA, GVH Chimpakati-Chanza | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute Masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 29[Msechero Afforestationa ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Msechero | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
USP 30 [Mkanongwa Afforestationa ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Chipyali | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Distribution of condoms | No of condoms distributed
[6 empty] | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
USP 31 [NamayaAfforestationa ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Namaya | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting 10 trees where one has been cut | No of seedlings out planted
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of diseases or introduce new diseases (HIV/AIDS, Waterborne diseases) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on diseases transmission and preventive measures | No. of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Increased incidences of open defecation | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of pit latrines | No. of pit latrines constructed
USP 32 [NamondeAfforestationa ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Namonde | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
|  | Spread of Covid-19 | High | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms distributed
ZOMBA DISTRICT
USP 1: Chakalamba Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings to categories of group in the community | Number of targeted groups sensitized
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of project beneficiaries following covid-19 prevention measures
USP 2: [Mgwalangwa Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Increased cases of gender based violence | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization and capacity building meetings on gender based violence | Number of farmers trained and Number of Cases Recorded and resolved
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
USP 3: [Chidule Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 4: [Staubi Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 5: [Chilimani Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. additionally, beneficiaries have been widely sensitised on the project to enhance their understanding of the project concepts as well as their roles in project implementation thereby fostering ownership | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Relevant stakeholders feeling not consulted | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings involving all categories of people | Number of stakeholders sensitized
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 6: [Bonnongwe Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 7: [Mkwezaziyo Afforestation Subproject in Traditional Authority Nkagula] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 8: [Disi Afforestation Subproject in Traditional Authority Nkagula] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Putting hand washing station in place | Number of handwashing station established
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 9: [Mphatsa Afforestation Subproject in Traditional Authority Nkagula] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 10: [Khanda Afforestation Subproject in Traditional Authority Nkagula] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes after outplanting seedlings | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | Number of people following covid-19 prevention measures
USP 11: [khewa Afforestation Subproject in Traditional Authority Ngwelero]: | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 12: [Maliko Afforestation Subproject in Traditional Authority Ngwelero] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 13: [Kadyampakani Afforestation Subproject in Traditional Authority Ngwelero] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 14: [Jumbe 1 Afforestation Subproject in Traditional Authority Ngwelero] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 15: [Bille 1 Afforestation Subproject in Traditional Authority Ngwelero] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 16: [Nanyole Afforestation Subproject in Traditional Authority Ngwelero] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 17: [Ndechere Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 18: [Ndalama Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Project being controlled by a subset of a group- monopolised | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 19 [Jiya Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitisations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 20: [Saiti Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Stakeholders feel that they have not been consulted | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 21 [Taombe Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 22 [Machiringa Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 23: [Solobala Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Stakeholders feel that they have not been consulted | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 24 [Mapemba Afforestation Subproject in Traditional Authority Ntholowa] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 25: [ Sululu Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
|  | Poor disposal of polythene tubes after outplanting seedlings | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of face masks to prevent the spread of COVID-19 | Number of farmers wearing face masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of handwashing facilities in place and being used
USP 26: [Chipulumutso Irrigation Scheme in Traditional Authority Malemia] | Not yet because construction of the irrgation schemes is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Loss of trees to clear land for irrigation | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Panting of trees | Number of trees planted in the catchment
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
|  | Spread of Covid-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Land conflicts | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Adherence to land acquisition procedures | Number of land agreement forms signed
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
USP 27: [Chigumukile Irrigation Scheme in Traditional Authority Malemia] | Not yet because construction of the irrgation schemes is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Loss of trees to clear land for irrigation | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Panting of trees | Number of trees planted in the catchment
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
|  | Spread of Covid-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Land conflicts | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Adherence to land acquisition procedures | Number of land agreement forms signed
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
USP 28: [Tithandizane Irrigation Scheme in Traditional Authority Malemia] | Not yet because construction of the irrgation schemes is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Loss of trees to clear land for irrigation | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Panting of trees | Number of trees planted in the catchment
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
|  | Spread of Covid-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Land conflicts | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Adherence to land acquisition procedures | Number of land agreement forms signed
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
USP 29: [Nsomba Aggregation Centre in Traditional Authority Malemia] | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | high | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 30: [Nthiko Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 31: [Msosa Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 32: [Malupi Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 33: [Kanyesi Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 34: [Masambuka Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 35: [Machinjili Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 36: [Mulomba Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 37: [Chitenjere Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 38: [Nachawe Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 39: [Chitope Afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 40: [Namichimba Afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 41: [Namichimba Re-Afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 42: [Kudwale Afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
USP 43: [Chimwazeni, Sunuzi and Lungazi Re-fforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
USP 44: [Chiloweni and Mulinga Re-afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 45: [Tsekanyenua and Namichimba Afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetings conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process
USP 46: [Utwe Re- Afforestation Subproject in Traditional Authority M'biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 47: [Mulinga and Chilowe Afforestation Subproject in Traditional Authority Nkagula] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 47: [Tsekanyenua Afforestation Subproject in Traditional Authority M,biza] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetings conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 47: [Tsekanyenua Afforestation Subproject in Traditional Authority Malemia] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetings conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 48: [Mambo Trading Aggregation Centre in Traditional Authority Nkapita] | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using picsa bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | high | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 49: [Kwilindi Afforestation Subproject in Traditional Authority Nkapita] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 50: [Matola Afforestation Subproject in Traditional Authority Nkapita] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 51: [Fikila 1 Afforestation Subproject in Traditional Authority Nkapita] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Discrimination of individual groups | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 52: [Jussu 1(Tuntu) Afforestation Subproject in Traditional Authority Nkapita] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Pollution of water courses | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Promote natural regeneration | Area under natural regeneration
|  | Water logging and salinization | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use Pot filling | Number of trees sown intubes
USP 53: [Mikundi Soil and Water Conservation Subproject in Traditional Authority Nkapita] | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles including gender equality. | Solid and liquid waste generation | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | High | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 54: [Aggregation Centre in Traditional Authority Mbiza, GVH lototoni] | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | high | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 55: [Aggregation Centre in Traditional Authority Nkagula GVH, GVH Khanda] | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | high | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 56: [Aggregation Centre in Traditional Authority Nkagula GVH, GVH Kataya] | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | high | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
MACHINGA DISTRICT
USP 1: Nyambi EPA aggregation centre in T/A Nyambi | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | Number of seedligs raised
[6 empty] | Planting trees | Number of trees planted
[6 empty] | Use of cement blocks | No. of blocks moulded
[6 empty] | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for produce storage
[6 empty] | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce storage/fumigation
[6 empty] | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
[6 empty] | Community sensitization meetings | No. of meetings
[6 empty] | Contact and dialogue | No. of meetings
[6 empty] | Training on human rights | No. of trainings and No. of cases registered and redressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured
[6 empty] | Training on accident prevention safety | No. of trainings and No. of cases recorded
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
[6 empty] | Training on prevention of infectious diseases | No. of trainings and No. of cases registered
USP 2: Ngaukanika aggregation centre under T/A Kawinga | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | Number of seedligs raised
[6 empty] | Planting trees | Number of trees planted
[6 empty] | Use of cement blocks | No. of blocks moulded
[6 empty] | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for agricultural produce storage
[6 empty] | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce storage/fumigation
[6 empty] | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
[6 empty] | Community sensitization meetings | No. of meetings
[6 empty] | Contact and dialogue | No. of meetings
[6 empty] | Training on human rights | No. of trainings and No. of cases recorded and addressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured
[6 empty] | Training on accident prevention safety | No. of trainings and No. of cases registered
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
[6 empty] | Training on prevention of infectious diseases | No. of trainings
USP 3: Mchiguza aggregation centre under T/A Mchiguza | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Cutting down of trees and removal of vegetative cover | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
[6 empty] | Use of cement blocks | No. of blocks moulded
[6 empty] | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for produce storage
[6 empty] | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce fumigation
[6 empty] | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
[6 empty] | Community sensitization meetings | No. of meetings
[6 empty] | Contact and dialogue | No. of meetings
[6 empty] | Training on human rights | No. of trainings and No of cases registered and addressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
[6 empty] | Training on accident prevention safety | No. of trainings and no. of injury cases registered
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
[6 empty] | Training on prevention of infectious diseases | No. of trainings and No of cases registered
USP 4: Nkula Headquarters aggregation Centre under T/A Nkula | Not yet because construction of the aggregation centres is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | Number of seedligs raised
[6 empty] | Planting trees | Number of trees planted
[6 empty] | Use of cement blocks | No. of blocks moulded
[6 empty] | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for produce storage
[6 empty] | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce storage/fumigation
[6 empty] | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
[6 empty] | Community sensitization meetings | No. of meetings
[6 empty] | Contact and dialogue | No. of meetings
[6 empty] | Training on human rights | No. of trainings and No of cases registered and addressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured
[6 empty] | Training on accident prevention safety | No. of trainings and No. of cases registered
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
[6 empty] | Training on prevention of infectious diseases | No. of trainings and No of cases
USP 5: Nyenyezi 2 Irrigation scheme under T/A Sale | Not yet because construction of the irrigation scheme is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Increased soil erosion, floods and sediment load | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of marker ridges | Area conserved (ha)
[6 empty] | Ridge realignment | Area conserved (ha)
[6 empty] | Vetiver planting | Area conserved (ha)
[6 empty] | Box ridging | Area ridged (ha)
[6 empty] | Construction of deep trenches | No. of deep trenches
Length (m)
[6 empty] | Construction of stone bunds | Length (m)
|  | Gully formation | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of mansonery checkdams | No. of checkdams
Length (m)
|  | Cutting down of trees and removal of vegetative cover | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
[6 empty] | Tree planting | No. of seedlings planted
Area planted (ha)
[6 empty] | Promote natural tree regeneration (ha) | Area (ha)
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings and No of cases registered
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
[6 empty] | Contact and dialogue | No. of meetings and No of cases registered and reddressed
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Community sensititzation | No. of meetings and No of cases registered.
[6 empty] | Distribution of condoms at the scheme | No. of condoms distributed
USP 6: Chibulubulu Irrigation Scheme under T/A Chamba | Not yet because construction of the irrigation scheme is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Increased soil erosion, floods and sediment load | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of marker ridges | Area conserved (ha)
[6 empty] | Ridge realignment | Area conserved (ha)
[6 empty] | Vetiver planting | Area planted (ha)
|  | Cutting down of trees and removal of vegetative cover | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
[6 empty] | Tree planting | No. of seedlings planted
[6 empty] | Promote natural tree regeneration (ha) | Area (ha)
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings and No of cases registered
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
[6 empty] | Contact and dialogue | No. of meetings and No of cases registered and reddressed
USP 7:Mchuwa Irrigation Scheme under T/A Nyambi | Not yet because construction of the irrigation scheme is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Soil degradation | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Manure making and application | No. of heaps made
Area (ha) applied
|  | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
[6 empty] | Tree planting | No. of seedlings planted
[6 empty] | Promote natural tree regeneration (ha) | Area (ha)
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings
|  | Conflicts amongst community members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
[6 empty] | Contact and dialogue | No. of meetings
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sharing of condoms at construction site | No. of condoms distributed
[6 empty] | Community sensitization meeting | No. of meetings conducted
[6 empty] | Training in infectious diseases | No. of trainings conducted and No of cases registered
USP 8: Mdikira Irrigation Scheme under T/A Nkula | Not yet because construction of the irrigation scheme is yet to commence. However general sensitisations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. | Increased soil erosion, floods and sediment load | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of marker ridges | Area conserved (ha)
[6 empty] | Ridge realignment | Area conserved (ha)
[6 empty] | Vetiver planting | Area conserved (ha)
[6 empty] | Box ridging | Area ridged (ha)
[6 empty] | Construction of deep trenches | No. of deep trenches
Length (m)
|  | Gully formation | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of checkdams | No. of checkdams
Length (m)
|  | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
[6 empty] | Tree planting | No. of seedlings planted
Area planted (ha)
[6 empty] | Promote natural tree regeneration (ha) | Area (ha)
|  | Polluton of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings and No of cases registered
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
[6 empty] | Contact and dialogue | No. of meetings and No of cases registered and reddressed
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Community sensitisations | No of sensitisation compaigns conducted and No of beneficiaries adhering to the preventive measures
[6 empty] | Sharing of condoms at construction site | No. of cases registered
USP 9: Chimwankhwazi afforestation under T/A Nkula | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation .
|  | Removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
[6 empty] | Tree planting | No. of seedlings planted
[6 empty] | Promote natural tree regeneration (ha) | Area (ha)
|  | Conflicts amongst community members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
[6 empty] | Contact and dialogue | No. of meetings
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Encourage contractor to recuit skilled and non skilled labour locally | No. of local workers recruited
[6 empty] | Sharing of condoms at construction site | No. of condoms distributed
[6 empty] | Community sensitization meeting | No. of meetings conducted
[6 empty] | Training in infectious diseases | No. of trainings conducted and No of cases registered
USP 10: Tembenu afforestation under T/A Mposa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
[6 empty] | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
[6 empty] | Tree planting | No. of seedlings planted
USP 11: Mtalikachawu afforestation under T/A Mposa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
[6 empty] | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
[6 empty] | Tree planting | No. of seedlings planted
USP 12: Msombi afforestation under T/A Mposa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
[6 empty] | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
[6 empty] | Tree planting | No. of seedlings planted
USP 13:Mangulu afforestation under T/A Mposa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
[6 empty] | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
[6 empty] | Tree planting | No. of seedlings planted
USP 14: Tiyanjane afforestation under T/A Mposa | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
[6 empty] | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
[6 empty] | Tree planting | No. of seedlings planted
USP 15: Samute afforestation under T/A Kapoloma | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Increased unpaid work for women/girls | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Equal distribution of wprk | Activities done by men and women
|  | poor disposal of the polythen tubes |  |  |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | Inadequate consultation by other stakeholders |  |  |  | Sensitization at all levels | No. of meetings
USP 16:Saidi Ndege Afforestation under T/A Kapoloma | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Spread of endogenous/existing diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of reusable face masks | No. of face masks provied
|  | poor disposal of the polythen tubes |  |  |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | Inadequate consultation by other stakeholders |  |  |  | Sensitization at all levels | No. of meetings
USP 17: Tiyanjane Afforestation under T/A Kapoloma | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . | Spread of endogenous/existing diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provisionn and use of reusable face masks | No. of face masks provied
[6 empty] | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | poor disposal of the polythen tubes |  |  |  | Availability of condoms at the site | No. of condoms
USP 18:Kalambo Afforestation under T/A Nyambi | Yes, Farmer groups involved in afforestation have been sensitised on proper handling of polythene tubes and re-using of the same where possible. Covid preventivie measures sensitisations have continously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period a compaints redress mechanism has been developed and the associated manual. sensitisation of the project beneficiaries on the GRM are continous. | Inadequate consultation by other stakeholders | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the commuties | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization at all levels | No. of meetings
|  | poor disposal of the polythen tubes |  |  |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | Marginalized people having difficulties in filing complaints of feedback |  |  |  | Sensitize the people to chanel the complaints to relevant authorities | No. of complaints lodged
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Some community members were claiming that they were initially identified as project beneficiaries however later on they were replaced by others. |  | The project enhanced backstopping visits and sensitisation to the communties to enhance beneficiary understandng of the project and the insurance component as most of them perceieved that all project beneficiaries will benefit the insurance component of the project. Yet according to the project design, only 30% of the total project target is expected to benefit from the insurance component. With intensified sensitisation, most of the project beneficiaries now have a good understanding of the project and its components.
Inadequate inputs distribution such for agroforestry, afforestation and other soil and water conservation practices |  | The project beneficiaries and extension workers were re-sensitization and encouraged to use locally available resources as much as possible in addressing the soil and water conservation challenges for purposes of project results sustainability. It was therefore made clear to the project beneficiaries that the project will only be providing top up inputs. This concept has now been well understood by the communities and extension workers.
The beneficiaries have been complaining about the delayed provision of the payouts . This is due to the design of the insurance product, as payout amounts can only be calculated at the end of the season. In addition, there is a misconception amongst some beneficiaries that payouts are automatic at the end of the season, irrespective of whether the index has actually been triggered or not. Such beneficiaries think that index insurance is like a government social protection system that provides cash regularly every year. |  | Engagement meetings with beneficiaries were conducted to re-sensitize them on the insurance component and payout processes. WFP and AF project coordination team also closely followed-up with the insurance companies and PULA on the final report and outcome of crop-cuts. For the subsequent year WFP and the AF project team are negotiating with the insurance companies and PULA to develop a roll-out plan with clear timelines to reduce delays in the processes at all stages.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
The AF project in line with the project document implemented a new baseline in the 2nd quarter of 2021, this has resulted in some changes in the values of the baselines from the original project document
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Note that baseline figures have been updated following the baseline survey
Disaggregation of the target by gender | Impact: Enhanced climate adaptation and food security of households through access to integrated climate risk management strategies | % of the population in targeted communities reporting benefits from an enhanced livelihood asset base by gender using the Asset Benefit Indicator (ABI) | 0 | 50% | Good; About 10% F and 10% M. During the reporting period, the project has supported thebeneficiaries to be organised in groups and practice seed multiplication i.e. sweet potatoes, cassava as well as fruits like banana in order to foster crp diversification. Additionally, through the same farmer groups, the benficiaries have been supported under marketing by linking them to better produce markets. Note that the baseline value remained the same even after conducting the baseline survey
| Outcome 1: Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity | % of households in targeted communities with reduced risk related to extreme weather events by gender of household head | 7%F; | F: 65% | Fair. About 17%F & 11%M of the total project beneficiariries have been supported under crop insurance as a risk transfer mechsnism. The insurance report is however not yet released by the insurers which will determine on whether there will be payouts or not in the ended season of 2020/21. During the reporting period, alot of soil and water nservation practices were also promoted leading to reduced climatic risks. Note that the baseline value was updated after the baseline survey. Lower values were established after the baselines on this indicator. This could be mainly due to increased occurance of drought in most impact areas as well as increased fall army worm infestation.
|  |  | 5%M | M: 70%
|  | % of households belonging to vulnerable groups with access to weather index micro insurance by gender of household head | F: 0% | F: 30% | Good. About 28% of the project total beneficiaries have been supported to access micro-insurance services as risk tranfer mechanism. According to the project design, 30% of project beneficiaries were supposed to have been supported from year 1. Thus about 94% of the expected targeted has been attained in year 1. Note that the baseline value remained the same even after conducting the baseline survey
|  |  | M:0% | M:40%
| Output 1.1: Targeted population groups covered by adequate risk reduction systems | Number of people insured (non-cash, partial cash payment and full cash payment by gender | 0 | F: 10,240 | Good. A total of 24,969 project beneficiaries ((14981F, 9988M) were covered under the crop-micro insurance as a risk transfer mechanism during the reporting period against the expected target of 25,600 housheolds. Note that the baseline value remained the same even after conducting the baseline survey
M:15,360
| Output 1.2 Awareness raised among farmers on weather index insurance | Number of people trained on index design by gender | F: 0 | F: 15 | Good. A total of 62 farmers (37F and 25M) have been trained on insurance as a risk transfer mechanism and the Area Yield Index Design which was implemented during the reporting period. Note that the baseline value was updated after the baseline survey
|  |  | M:0 | M: 20
|  | Number of people sensitized on insurance as a risk transfer mechanism by gender | F: 240 | M: 195,075 | Good. Beneficiary sensitisation formed an integral part of the project implementation in year 1 considering that for most of the project beneficiaries, the concept was relatively new. A series of sensitisation compaigns were therefore conducted not only the insurance project beneficiaries which is 94% of the total project beneficiaries, but rather to the entire universal set of beneficiaries, 382500 people, which is 85,000 households. Note that the baseline value was updated upward after the baseline survey. In one of the project sites in Zomba district, crop insurance as a risk transfer mechanism was not a new concept as WFP had previously implemneted the insurance scheme in part of the site
|  |  | M: 160 | F:187,425
| Outcome 2: Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | % of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses by gender | F: 41.1% | F: 90% | Good. About 55%F and 65% males have been made aware of the adverse impacts of climate change and appropriate responses. Besides the crop insurance cover, beneficiaries were engaged to identify the adverse impacts of climate change in their localities, hot spots to be addressed in order to mitgate some of the climate chnage impacts. in this regard, project beneficiaries have implemented any of soil water conservation practices such as vertiva grass plantation, construction of check dams, construction of stone bands and swales, afforestation and reforestation; natural tree regeneration. Furthermore, crop diversification and formation of backyard gardens have been encouraged amongst the beneficiaries. Note that the baseline value was updated upwards after the baseline survey. Balaka and Zomba districts had already been implementing PICSA methodology which amongst others enhances farmers awareness of the adverse impacts of climate change to inform their livelihood decision making.
|  |  | M: 58.9% | M: 95%
|  | % of households using weather and climate information for decision-making on livelihoods and food security by gender and district | F: 60% | F: 75% | Good. About 65%F and 83%M have been using weather and climate information for decision making on livelihoods. As we move into year 2 of project implmentation, trendous improvement is expected because full PICSA methodology training will also be done in Machinga district which has never been trained before. Use of lead farmers as an approach to complement extension workers who have huge workloads will also help significantly to increase coverage and also adequately support the farmers as they make livelihoods decisions based on the climate information provided. Due to the maginute of work the extension workers have, dedication of ample time to farmers to ensure quality livelihood decision making , has been a challenge. Note that the baseline value remained the same even after conducting the baseline survey
|  |  | M: 80% | M: 85%
|  | % of targeted households with borderline to acceptable food consumption score by gender of household head and district | F: 90.9% | F: 75% | Good. *It should however be noted that the baseline of the project happened close to the harvest time and as such it skewed the results since 7 days dietary recal data is used on this indicator. This was a food abundance period as most of the beneficiaries had just harvested. Note that the baseline values were updated upwards after the baseline survey
|  |  | M: 94.2% | M: 80%
| Output: 2.2. Promote climate resilient agriculture among farmers through extension service support | % of HHs involved in CA (minimum tillage, crop diversity, retention of crop residues) by gender of household head | F: 8% | F: 30% | Fair. Due to the late commencement of project implementation on the ground, implementation of some of the CA parctices such as minimum tillage and crop residues retention was challenging. Hence minimal progress registered during the 2020/21 season. More progress is however expected to be registered during year 2 of project implmenetation. Note that the baseline values were updated downwards after the baseline survey. Overall district level statistics were used initially. According to the baseline survey results, limited people are currently practising Minimum tillage/retention of crop residues. Some of the project impact areas have water logging conditions while in some areas (majority of the areas), implementation is minimal due to lack of knoweledge and by-laws prohibiting bushfires and livestock consumption of crop residues in CA plots.
|  |  | M: 7% | M: 35%
| Output 2.3. Support crop diversification with a focus on drought tolerant and nutritious crops | Number of HH accessing improved fruit seedlings, leguminous trees and fodder tree seed by gender of household head | F: 21,590 (Leguminous Trees); F: 9,010 (fodder trees); 2,550 (improved Fruits) | F: 40,000 | Good. Significant progress was registered under this indicator as farmers were supported with direct sowing of agroforestry and fodder seeds as well assorted fruit seedlings for planting at both individual level and group level. Note that the baseline value was updated upwards after the baseline survey. Pigeon peas are predominantly grown in the project mpact areas hence high values of leguminous trees. Additionally, in most of the project impact areas, soil and water conservation projects were previously implemennted by the Governments, besides the normal promotion of the soil and water conservation practices at community level. Furthermore, in some of the project areas, Food For Asset (FFA) was previously implemented by WFP, especially in Zomba and Balaka Districts while in Machinga, FFA is still on -going in one TA in which AF is also being Implemented.
|  |  | M: 23,800 (Leguminous trees); M:11,815 (Fodder trees); 3,400 (Improved fruits) | M: 45,000
| 2.5. Strengthened national capacities and systems to provide integrated climate risk management approaches | Number of intermediaries trained in how to access, interpret and communicate climate information to households, to support household decision-making related to food security, livelihoods, and DRR – disaggregated per gender and district | 10F; 44M | F:80 M: 100 | Good. A good progress was regestered. About 18 Female and 93 Male intermediaries have been trained during the reporting period in PICSA methoologies which is key in informing household decision making related to food security, levilihoods and DRR. Note that the baseline values were updated for this indicator.
| Outcome 3:Strengthened market access strategies and approaches for smallholder farmers | % of households having more secure (increased) access to livelihood assets by gender of household head | F: 9.2% | F:75% | Fair. A fair progress was attained under this indicator as limitted livelihoods assets were created in year 1 mainly due to delayed commencement of project implementation and also the maginute of prepartory works for construction some of the assets live irrigation schemes. Note that the baseline value was updated upwards after the baseline survey. This could be due to the government ongoing efforts on soil and water conservation and livelihoods enhancement.
|  |  | M: 9.9% | M: 80%
|  | % of targeted population with sustained climate-resilient livelihoods by gender of household head | F: 10% | F:75% | Fair. The progress under this indicator is also rated fair because being year 1 of project implementation, much of the benefits have not yet started acruing due to the nature of the internventions. However, as project implementation continues, it is expected that more benefits will continue to be yielded from the assets createds and other internventions implemented. Note that the baseline value was updated upwards after the baseline survey. This could be due to the government ongoing efforts on soil and water conservation and livelihoods enhancement.
|  |  | M: 15% | M: 80%
|  | % change in household income disaggregated by activity type and gender of household head | 0 | F:25% | Poor. Household income is expected to improve mainly as a result of the marketing and finance component of the project as well crop insurance. However, limited progress has been registeered because farmers had not yet sold the produce they had grown collectively. additonally, the insurance payout report had not yet been realesed which will determine whether they will be payouts or not. Furthermore, Limited progress has been made on promotion of VSLs since establishment of the VSLs is stll underway.
M: 30%
|  | % of both male-headed and female HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Both 27% | Both - 40% | Fair. Significant efforts have been during the reporting period to organise farmers into groups for collective produce marketing and linking them to exsting farmer organisation. A market informaton dissemination system is however not yet fully instituted hence the fair progress. This is one of the key priorities in year 2 of project implementation besides construction of aggregation centres and supporting the farmer groups to develop business plans. Note that the baseline value was updated upwards after the baseline survey
|  | % of male-headed HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Men: 37% | Men - 30%
|  | % of female-headed HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Women 36% | women-30%
| cross-cutting Indicators: Improved gender equality and women;s empowerment among assisted populations | % of households where women, men or both women and men make decisions on the use/access of markets | Both 27% | Both - 40% | Fair. Significant efforts have been during the reporting period to organise farmers into groups for collective produce marketing and linking them to exsting farmer organisation. A market informaton dissemination system is however not yet fully instituted hence the fair progress. This is one of the key priorities in year 2 of project implementation besides construction of aggregation centres and supporting the farmer groups to develop business plans. Note that the baseline value was updated upwards after the baseline survey
|  |  | Women 36% | Women - 30%
|  |  | Men: 37% | Men-30%
|  | % of households where women, men or both women and men make decisions on insurance and climate services access | Both- 29% | Both - 40% | Fair. Much of the effort in year 1 of project implementation was concentrated on enhancing understanding of the insurance concept, the AYII design and payout processes amongst beneficiaries, being a relatively new concept to most of the farmers. it is expected that from year 2 onwards, community members will have enhanced opprotunities for accessing the crop insurance services independently with increased presence of the insurer (NICO and IAM) on the ground. Note that the baseline value was updated upwards after the baseline survey
|  |  | Women 34.1% | Women - 30%
|  |  | Men:37% | Men-30%
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Most leadership positions of the local structures were given to men even though most members were female |  | Group dynamics training was provided in which community members were sensitized on the need to have gender balance in leadership positions for project committees. This guided the selection of the members later, which resulted in women being empowered/considered for project committee positions
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | GP manuals and policies have been made available to the project team for reference during project implemenetation. During project inception, an orientation was conducted for the project team to enhance their understanding of the GP, facilitated by the GP focal point of the IE. This was done prior to project's team development of the project annual workplans. The IE focal point on GP has been handy during the reporting period to provide technical backstopping services to the project team.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes they have been effective.The arrangement under IE has been effective through the close collaboration with the Government personnel whereby joint technical expertise has been put to optimum use for effective planning, implementation and review of project activities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Yes, very effective. The Project team were oriented on GP before workplan development to ensure adequate integration of GP in the workplan and also discloure of environmental and social management plans at all levels. Even farmers are able to explain that they mainistream gender and HIV issues in their activity implementation. Deliberate measures were also put in place during beneficiary targeting to prioritise female headed households and other marginalised groups. Additionally, gender considerations were being made in selection of farmers and extension workers to be trained. Where possible, the project has been advocating for atleast 40% women participation
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes it has been effective in a such a way that the District Environmental Sub Committees are now spearheading implementation and monitoring of EE. Gender and HIV mainstreaming is being carried in all activities being implemented. Frontline staff make sure that when working with farmers they emphasize on this and even during farmer trainings , gender issues are always mainstreamed.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A at the moment
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None |  | N/A
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress | Progress to Date | Rating
Implementing Entity: WFP | Outcome 1: Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity | Outcome 1 | Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity; |  | S
Outcome 2
Outcome 3
Outcome 7
| Outcome 2. Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | Outcome 2 | Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach; |  | S
Outcome 3
Outcome 5
Outcome 6
| Outcome 3: Strengthened Market access strategies and approaches for smallholder farmers | Outcome 6 | 3. Strengthened market access strategies and approaches for smallholder farmers. |  | MS
|  |  |  | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Kathy Derore Programme Advisor WFP Malawi
| Email: | kathy.derore@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity | Outcome 1 | Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity; |  | S
Outcome 2
Outcome 3
Outcome 7
| Outcome 2. Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | Outcome 2 | Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach; |  | S
Outcome 3
Outcome 5
Outcome 6
| Outcome 3: Strengthened Market access strategies and approaches for smallholder farmers | Outcome 6 | 3. Strengthened market access strategies and approaches for smallholder farmers. |  | MS
|  |  |  | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Gilbert Kupunda, National Project Coordinator
| Email: | gkupunda@gmail.com
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
AF Outcomes
Outcome 1 | Reduced exposure to climate-related hazards and threats |  | Highly Satisfactory (HS)
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  | Satisfactory (S)
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Marginally Satisfactory (MS)
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | Marginally Unsatisfactory (MU)
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | Unsatisfactory (U)
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  | Highly Unsatisfactory (U)
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
In its capacity as an Implementing Entity, WFP coordinated inception workshops at district and community level. Participation to the inception workshops was however so limited due to the covid 19 preventive measures which were in place at that point in time. Below are the output specific activitivy the IE has done during the reporting period.
Output 1.1 Targeted population groups covered by adequate risk reduction systems
Following WFP's review of its insurance activities, an Area Yield Index Insurance (AYII) product was recommended and designed for the AF project as opposed to the weather index insurance. The AYII has proven to be suitable in the country's context as it covers a wide range of shocks and as such it is more accurate in triggering payouts. WFP supported the Executing Entity in the design of the AYII by engaging PULA and NICO to provide technical support.
Output 1.2 Awareness raised among farmers on weather index insurance
WFP as an implementing Entity provided technical support during:
  - Project beneficiary targeting which was done using the using the National Unified Beneficiary Registration (UBR) database which has proven easier to apply, while in Machinga and Zomba, a simplified harmonized UBR registration format was used. WFP also coordinated discussions between the AF project team and the Ministry of Economic Planning and Development which is implementing/piloting an Enhanced Public Workings Proramme in Balaka District with some TAs overllaping with the AF project targeted TAs. The project is being implemented using catchment management approached with intervention similarities with the AF project especially under the soil and water conservation component. However, the Enhanced Public Works Programme provides direct cash transfers to its beneficiaries as compared to the AF project. Discussions were necessary to identify opportunities for complementarities.
  - Futher support was provided during the design of community messages for raising awareness and education the project beneficiaries as well as frontline workers about the insurance component of the project and the area yield index design which was implemented during the 2020/21 season.
Output 1.3 Develop and test tools and systems for weather insurance ( Strengthen national capacities and systems to provide weather index insurance working with private and public sectors)
WFP as an IE led a series of dicussions with PULA and the Insurance Association of Malawi (IAM) on how to improve sensitization of direct project beneficiaries and the communities as a whole, especially on how the insurance product works and how the payout is triggered. Strategies have thus been developed and a roll-out plan for the 2021/22 season has been developed where PULA and NICO will play a leading role in community engagement, season monitoring and pay-out management.
Output 1.4. Inclusion of insurance as risk transfer mechanisms in national agriculture programs and supported schemes
As an IE, WFP participated in series of national level dialogue sessions were conducted on the AYII producted which has been implemented during the 2020/21 season to enhance stakeholder understanding of the product.
A total of 5 outputs contribute to outcome 2 and actual progress on each output is as outlined below:
Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation
During the reporting period, WFP faciliated harmonisation of soil and water conservation work normes being used by WFP and the government. Updating of the soil and water conservation mannual is currently underway. Posters/Fliers on harmonised work normes have been produced.
In addition, taking into account the importance given to Environmental and Social Standards, all project activities with potential risks such as agroforestry sites, seedling nursery sites, proposed sites for irrigation scheme rehabilitation and construction of aggregation centers were screened using a harmonized ESS screening tool and associated Environmental and Social Management Plans (ESMPs) which was developed with technical guidance from WFP.
Furthermore, WFP has provided 20 solar-powered irrigations pumps to enhance the capacity of irrigation schemes which will be developed under the AF project.
Output 2.4: Provide climate services to inform livelihood decision making amongst farmers
In its capacity as IE, WFP supported both technically and financially (through advance payment to the AF project coordination unit) implementation of the 2020/21 expert and farmer trainings on the Participatory Integrated Climate Services for Agriculture (PICSA) methodologies. This is one of the key approaches for improving farmers accessibility to weather and climate information through extension services to inform their livelihoods decision making such as seasonal planning and climate risk management. PICSA trainings are time sensitive as such the advance payment was made to avoid losing the season since funds had not yet been programmes within WFP by the time the trainings were supposed to be implemented.
Outcome 3 of the project has 4 outputs. However, significant progress was only registered under 2 of the 4 outputs as stated below:
Output 3.2. Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced
WFP, provided technical support towards the assessment of existing farmer organisations (FO) in the project sites as a key step towards linking project beneficiaries to operational FOs. The assessment also informed identification of sites where aggregation centres will be constructed by the project.
Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses
WFP facilitated learning visits to FOs which were previously supported by WFP with construction of aggregation centres to draw lessons as the project intends to consutruct a total of 12 aggregation centres for FOs in the project districts.
Even though implementation of project activities started late, the rating is Marginally Satisfactory (MS), because tangible results from most of the project interventions were achieved, but some especially under Outcome 3 have made limited progress. Plans to accelerate progress have been put in place.
As an IE, the WFP Country office has been handy in provision of technical support across the project components including on procurement and financial management. In this regard, a financial and procurement spot-check was conducted and recommendation for improvement especially record keeping was provided to the project coordination team. In the 4th quarter of 2021, another spot-check will be done to confirm that the recommendations provided have been implemented at full, also considering the roll-out of accounts up to district level in the 2nd quarter of 2021. WFP has also participated in the project technical advisory committee and Project Steering Committee meetings held during the reporting periods including physical project progress monitoring in the project districts
Despite the delays in commencement of project implementation, delays in hiring staff and opening of the EEs bank accounts at national and district levels, limited number of extension workers on the ground and the effects of COVID-19 pandemic, almost all the outcome indicators are on track. Concurrent implementation of project activities and use of already existing lead farmers and community structures in implementation of the project activities played a significant role in the achievement made so far. It is however expected that the ratings will improve with time as benefits/results from the various project interventions continue to get realized and the project enters its second year of implementation.
While wave one and two of the COVID-19 pandemic mainly affected the urban centers, the third COVID-19 wave is significantly impacting both urban and rural areas. In this regard, most stakeholders are working from home and the IE is remotely and virtually providing tehcnical support. The AF team with technical support of the IE is however using this period of time to make progress by proactively and timely planning for year 2 activity implementation including procurement of materials and inputs in support of soil and water conservation activities, further development of Techncial SOPs, development of project communication strategy and improve communications, development of downscaled climate information for the next season, Development of Community sensitisation materials and improvement of its engagement with PULA and the IAM private sector aron implementation of insurance as a risk transfer mechanism and foster their ownership as well as active involvement in insurance scheme implementation at the field level.
The new governments vision 2063, the functioning of the Project Steering committee and renewed interest of government in insurance as a risk mitigation option are potential areas to improve the implementation of Malawi’s rich policies into ground level actions resilience building and diversified livelihoods. This year with Malawi being the chair of the SADC creats additional opportunities.
COVID-19 remains a key challenge for the next year, with this July seeing AF team staff members being affected and even some of our counterparts passing away. Ongoing field operations therefore have been scaled back to the minimum at this point in time and all continuing activities are being implemented under strict adherence to governments COVID-19 restrictions and all health safety measures including social distancing, avoiding gathering of people beyond 10-15 people etc., hence, the reduced level of implementation pace will certainly continue to affect the duration of the project and physical/financial delivery.
In overall, project's progress is Satisfactory to Marginally Satisfactory.
Despite late commencement of project activities' implementation and COVID-19 restrictions, tremendous progress has been registered in overall. Much effort is however expected to be put forward as we move into year two of project implementation to ensure quality project outputs on the ground and project visibility while fostering community ownership. Special efforts will also be put forward especiall on component 3 of the project which registered marginal satisfactory progress in year 1 . Additionally, much of national level engagement will be done for project outputs requiring national level capacity building. The progress registered in year 1 forms a good foundation for national level dialogue on the project including promoting uptake of insurance as a risk transfer mechanism by the government of malawi as well as non-governmental organisations.
Alot of capacity building has been done to the frontline workers as well as farmers. Specifically, the ToT approach played a significant role in ensuring increased coverage of the beneficiaries with the trainings as well as climate services.
Year 1 has also beein challenging due to fall army worm infestation as such most ceraeal produce were severely affected leading to reduced production levels for marketing. Considering that micro-insurance product whiich was implemented this year covers a wide range of shocks including pest infestation, it is hoped that most farmers will be covered, especially those who were targeted under the insurance project component. On another hand, most farmers are very excited to work and sell in groups as this increases the volume of produce for sale and also increases their bargain power. The farmer groups have been trained in market oriented farm planning and management, and their income level and control of assets has improved marginally.
As an executing entity, the AF team held additional roll-out workshops at the district level with the District Executive Committees (DEC), District Agricultural Extension Coordination Committees (DAECC), and district councilors to ensure there was full knowledge of the AF project and its components. According to the project design, 4 outputs contribute to Outcome one and a number of activities have been implemented under the outputs as outlined below:
Output 1.1 Targeted population groups covered by adequate risk reduction systems
A total of 24,241 climate vulnerable people (51% female) or 95% of the target have benefitted from the project interventions in various ways under the insurance as a risk transfer mechanism project component. A total of USD 476,404.06 has thus been paid as insurance premiums for the 24,241 beneficiaries under the component. Following WFP's review of its insurance activities, an Area Yield Index Insurance (AYII) product was recommended and designed for the AF project as opposed to the weather index insurance. The AYII has proven to be suitable in the country's context as it covers a wide range of shocks and as such it is more accurate in triggering payouts. As part of the seasonal monitoring, supplementary information of the seasonal outlook including pest infestation at Traditional Authority Level, Group Village Headman Level and Village Level were collected during the reporting period.
Output 1.2 Awareness raised among farmers on weather index insurance
The project has helped to raise local understanding on climate change and engaged beneficiaries in climate change activities and adaptation strategies with subject matter Specialists, Frontline Workers, Area Stakeholder Panels (ASPs)/Area Development Committees (ADC), village Agricultural Committees ( VACs)/Village Development Committees (VDCs). A total of 57 extension workers (20 in Machinga, 20 in Balaka and 17 in Zomba District) were trainied as ToTs on insurance and a risk transfer mechanism; who further cascaded the training to the insurance beneficiaries across the project districts. A total of 5 capacity building trainings/orientations programs have been accomplished.
During this first year, the critical task was the proper identification of targeted beneficiaries. In Balaka this was done by using the national Unified Beneficiary Registration (UBR) database which has proven easier to apply, while in Machinga and Zomba the office used a simplified harmonized UBR registration format.
While there was an initial delay also due to peak in COVID-19 in July 2020, the AF team has been able to organize and motivate participants to complete incentivised communal assets in soil and water conservation (like gully reclamation, check dams, afforestation, river-bank protection, vetiver nursery establishments and propagation) as a conditionality for insurance premium payment by the project for insurance project beneficiaries. Further materials and inputs support were provided under the insurance component for implementation of incentivised activities such as Seeds for Seed Multiplication, Potato vines, vetiver grass, fruit tree seedlings and Banana suckers. In this regard, nurseries for vetiver grass, fruit seedlings, bananas and afforestation were established in all impact areas. Additionally, seed mulplication sites were established in selected impact sites. Tools and implements to support implementation of the actvities by the insunrance component project beneficiaries such as Hoes, wheelbars, watering canes, phanga knives and shovels were also procured and distributed to isnurance farmer groups.
Output 1.3 Develop and test tools and systems for weather insurance
During the reporting period, collection and analysis of historical rainfall and agrometeorological data for Machinga were completed while the data for Zomba and Balaka were updated. In order to further strengthen Government's capacity in collection of rainfall data, 22 rain gauges were procured and installed in the project impact areas. While overall outcome 1 was a successful, it will be important for the AF team, jointly with PULA and the Insurance Association of Malawi (IAM) and WFP improve on sensitization of direct project beneficiaries and the communities as a whole, especially on how the insurance product works and how the payout is triggered. PULA and IAM will need to work on improving the timeliness of the insurance report and pay-outs. Discussions are currently ongoing to address some of the issues identified.
Output 1.4. Inclusion of insurance as risk transfer mechanisms in national agriculture programs and supported schemes
A series of national level dialogue sessions were conducted on the AYII producted which has been implemented during the 2020/21 season to enhance stakeholder understanding of the product.
A total of 5 outputs contribute to outcome 2 and actual progress on each output is as outlined below:
Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation
Some logistical challenges notwithstanding, during this initial year, under this outcome, the AF project has successfully trained Over 70 extension officers ( 56M and 14F) in catchment management conservation agriculture, agroforestry ( especially tree nursery establishment and fruit tree grafting), physical and biological soil and water conservation structures, irrigation operation and maintenance.
The team is currently also working on preparations of feasibility studies and the actual design of irrigation schemes. While the team has been successful in the identification of sites for irrigation schemes, the roll-out has been delayed as the demand was much higher than planned and the team jointly with WFP is reviewing potential additional resources to address the gap on the ground while avoiding tension among and within communities and addressing some underlaying issues of land-tenure.
In addition, taking into account the importance given to Environmental and Social Standards, all project activities with potential risks such as agroforestry sites, seedling nursery sites, proposed sites for irrigation scheme rehabilitation and construction of aggregation centers were screened using a harmonized ESS screening tool and associated Environmental and Social Management Plans (ESMPs) were jointly developed by the AF with technical guidance from WFPs CO and its regional bureau.
Output 2.2 Promote climate resilient agriculture among farmers through extension service support
In all impact areas, demonstration sites for soil and water conservation including conservation agriculture and complementary practices such as manure making have been implemented. To further enhance the capacity of soil and water conservation project beneficiaries, inputs especially afforestation and agroforestry seeds and seedlings were procured and distributed to soil and water conservation farmer groups. Over 80 vetiver grass nurseries have been established across the project districts and cummulatively, more than 90 hectares of farm land belonging to project beneficiaries has been introduced to agroforestry farming practice. Manure making at household level has also been promoted during the reporting period as a key element to address the lack of organic matter in most of Malawi's soil (as established by AgriLab soil tests) . As part of sensitisations to the project beneficiaries, the AF project hosted the national launch on soil and water conservation practices and manure making in project districts in June 2021 which was presided over by the Minister for Agriculture, Robin C. Lowe. The knowledge and skills adoption under this output including manure making was evident during the joint site visit of the Permenant Secretary (PS) and the Project steering committee members to the 3 districts held in June 2021.
Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops
Over 70 extension officers ( 56M and 14F) were trained in drought tolerant crops for seed multiplication including postharvest crop handling. These trainees further cascaded the trainings to the targeted project beneficiaries. Demonstration sites on drought tolerant crops were also instituted in some project impact areas. Farmer groups of project beneficiaries were also supported with assorted fruit seedlings (Apples, lemons, pawpaws, guavas, mangoes, oranges) within the catchement for growing at individual and group level.
Output 2.4: Provide climate services to inform livelihood decision making amongst farmers
A total of 40 front-line staff in Zomba and Balaka districts were also trained in Participatory Integrated Climate Services for Agriculture (PICSA) methodologies which is one of the key approaches for improving farmers accessibility to weather and climate information through extension services to inform their livelihoods decision making such as seasonal planning and climate risk management. The trained extension workers in turn trained 404 smallholder farmers. The roll-out for Machinga is planned for the 2021/22 season as the Department of Climate Change and Meterological Services (DCCMS) was doing the historical analysis of data as captured under outcome 1.
The team also held several review meeting and successfully co-developed climate products for Machinga District and updated the climate products for Zomba and Balak Districts. This increased ownership of the seasonal forecasts for the project impact areas to improve quality of the information provided to the targeted smallholder farmers on decision making.
Nutrition campaigns including the establishment of back-yard gardens were also promoted and established. A clear integration with nutrition sensitive approaches like consumption of six food groups as per the government recommendations were established and promoted. Additionally diversification of livelihoods and proper hygiene measures at HH level which are key elements of priority during a COVID-19 pandemic were also promoted.
Output 2.5 Strengthen national capacities and systems to provide these integrated climate risk management approaches
A total of 30 DCCMS staff have been trained in NEW R-INSTAT and downsacled seasonal forecasting which is very necessary for production of localised climate products.
Outcome 3 of the project has 4 outputs. However, significant progress was only registered under 2 of the 4 outputs as stated below:
Output 3.2. Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced
An assessment of existing farmer organisations (FO) in the project sites was conducted as a key step towards linking project beneficiaries to operational FOs. The assessment also informed identifiation of sites where aggregation centres will be constructed by the project. Extension workers operating in the project impact areas were also trained on smallholder agriculture produce marketing, who further cascaded the training to the marketing component project beneficiaries.
Furthermore, the project beneficiaries were trained in group dynamics, leadership and introduced to business plan development.
Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses
Learning visits were conducted to FOs which were previously supported by WFP with construction of aggregation centres to draw lessons as the project intends to consutruct a total of 12 aggregation centres for FOs in the project districts.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Timely Project accounts' opening with the Reserve Bank of Malawi (Project Holding Account) and a Commercial Bank (Project Operating Accounts). The delays in creation of these two accounts affected disbursement of the resources. The COVID-19 pandemic also affected the pace at which some of the activities were implemented especially those requiring physical presence since the number of participants at a time could be limited as a COVID-19 preventive measure. On a positive note, good collaboration with other government institutions like the Department of Climate Change and Meteorological Services (DCCMS), Department of agriculture Extension Services (DAES), Environmental Affairs Department, Ministry of Trade, and Ministry of Economic Planning and Development smoothened implementation of most project activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, there have been delays in opening of project holding and operating accounts as well as accessibility of the funds after the accounts were opened due to the internal logistical processes of both the IE and EE. In order to avoid losing the agricultural season, resources for implementation of initial essential activities such as beneficiary targeting, PICSA trainings and community sensitizations were processed from the IE side as an advance, but after the signing of the MOU between the EI and ME side, the situation was normalised. Resources are now being transfered to the EE on quartery basis. This arrangement helped to keep project activities on track.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | In order to remain on track, some activities across the project components were implemented concurrently. For instance, at the onset of project implementation, a number of refresher trainings were supposed to be provided to the extension workers/frontline workers across the project components. These were jointly organised and delivered as a comprehensive package. While training sessions were underway activities on the ground continued to be implemented.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, especially in implementation of soil and water conservation activities. As project activities were being implemented, environmental and social management plans were implemented alongside in order to ensure the identified risks were avoided or mitigated appropriately.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project coordination teams at both National and District levels had capacity strengthening trainings on gender and protection before development of project annual workplans. This was key in enhancing the capacities of the team in developing gender sensitive workplans. Furthermore, during the project inception meetings and community awareness about the project, emphasis was made on gender integration throughout project implementation. As such, prioritization of vulnerable women headed households as well as those caring for orphans was made during beneficiary targeting.
In this regard, more than 40% of the targeted households are female headed. It was easier to target the vulnerable women headed households amongst other, because the community members were already sensitized about the gender considerations of the project and appreciated the need to prioritize and uplift such households.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programmed to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmed?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
The AF project in line with the project document implemented a new baseline in the 2nd quarter of 2021, this has resulted in some changes in the values of the baselines from the original project document as indicated in the remarks column below.
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End | Remarks
Impact: Enhanced climate adaptation and food security of households through access to integrated climate risk management strategies | % of households in target communities who independently access insurance and climate services by gender of household head | 0 | 0 | 80%
| % increase of government owned resilience and climate change adaptation activities | 0 | 0 | 50%
| % of targeted communities where there is evidence of improved capacity to manage climate shocks and risks | 0 | 5% | 100%
| % of the population in targeted communities reporting benefits from an enhanced livelihood asset base by gender | 0 | 10% F and 10% M | 50%
Outcome 1: Improved access to insurance and climate services as risk transfer and reduction mechanisms for targeted farmers affected by climate change and food insecurity | % of households in targeted communities with reduced risk related to extreme weather events by gender of household head | 7%F; 5%M | 17%F and 11%M | F: 65% | The baseline value was updated
M: 70%
| % of households belonging to vulnerable groups with access to weather index micro insurance by gender of household head | 0 | 17% | F: 30%
|  | 0 | 11% | M:40%
| % of households not engaged in coping adverse mechanisms | 14% | 28% | 80%
Output 1.1 Targeted population groups covered by adequate risk reduction systems | Number of people insured (non-cash, partial cash payment and full cash payment by gender | 0 | 24,969 (14,981F, 9988M) | F: 10,240
M:15,360
| Total premiums paid, by access modality (insurance for assets or cash) | 0 | 434344.7 | 460800
| Total sum insured (IFA, partial cash payment and full cash payment) | 0 | 4219476.05 | 2477419
Output 1.2 Awareness raised among farmers on weather index insurance | Number of people trained on index design by gender | F: 0 | F: 37 | F: 15
|  | M: 0 | M: 25 | M: 20
| Number of people sensitized on insurance as a risk transfer mechanism by gender | F: 240 | M: 195,075 | M: 195,075 | The baseline value was updated
|  | M: 160 | F:187,425 | F:187,425
Output 1.3 Develop and test tools and systems for weather insurance insurance tools | Number of national coordination mechanisms supported | 0 | 2 | 3
| Number of staff trained on weather index insurance (disaggregated by public/private, national/local) by gender | F:2; M:8 | Public: 62; 14F and 48M | 50 | The baseline value was updated
Output 1.4. Inclusion of insurance as risk transfer mechanisms in national agriculture programs and supported schemes | Number of national agriculture programs and supported schemes with insurance packages as risk transfer mechanisms | 2 | 2 | 10 | The baseline value was updated
Outcome 2: Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | % of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses by gender | F: 41.1%; | 55% | F: 90% | The baseline value was updated
|  | M: 58.9% | 65% | M: 95%
| % of households using weather and climate information for decision-making on livelihoods and food security by gender and district | F: 60% | F: 65% | F: 75%
|  | M: 80% | M: 83% | M: 85%
| % of targeted households with border line to acceptable food consumption score by gender of household head and district | F: 90.9% | F: 90.9% | F: 75% | The baseline value was updated
|  | M: 94.2% | M: 94.2% | M: 80% | The baseline value was updated
Output2.1: Promote soil and water conservation practices through individual and group asset creation, including irrigation development | No. and type of risk reduction actions or strategies introduced at local level | 5 | 7 types, a)backyard gardening , b) winter cropping in dambos; c) Insurnace as a risk tranfer mechanism; d) various soil and water conservation practices; e) access to climate information; f) Crop Diversification; g) Cultivation of drought torelant crops | 5
| Number of assets built, restored or maintained by targeted households and communities, by type and unit of measure and a percentage of planned | 0 | 12 community woodlots established; 12 irrigation sites identififed for dvelopment; 85 vetiver nurseries established, 98 Ha under agroforestry | 36
| Percentage of households that are involved in irrigation farming, in addition to rain-fed agriculture | 9.6% | 9.6% (No/limited progress registered on this because development of irrigation schemes has not yet been finalised in the impact areas.) | 15% | The baseline value was updated
Output 2.2. Promote climate resilient agriculture among farmers through extension service support | % of HHs involved in CA (minimum tillage, crop diversity, retention of crop residues) by gender of household head | F: 8% | F:14% | F: 30% | The baseline value was updated
|  | M: 7% | M:10% | M: 35%
| Ha of land under CA | 335.72 | 1020 | 3400 | The baseline value was updated
| Ha applied with manure | 8000 | 5100 | 17000 | The baseline value was updated
Output 2.3. Support crop diversification with a focus on drought tolerant and nutritious crops | Number of crops grown by HHs (by type) for crop diversification | 2 | 7 (Maize, Cassava, Groundnuts, sweet potatoes, pigeon peas and cow peas) | 4
| Number of HH accessing improved fruit seedlings, leguminous trees and fodder tree seed by gender of household head | F: 21,590 (Leguminous Trees); F: 9,010 (fodder trees); 2,550 (improved Fruits) | F: 35,200 (Leguminous trees); F9,010 (Fodder trees); 7,550 (improved fruits) | F: 40,000 | The baseline value was updated
|  | M: 23,800 (Leguminous trees); M:11,815 (Fodder trees); 3,400 (Improved fruits) | M: 29,190 (Leguminous trees); M:11,815 (Fodder trees); 6,738 (Improved fruits) | M: 45,000 | The baseline value was updated
Output 2.4. Strengthened access to weather/climate information for targeted communities to inform livelihood decision-making among farmers | Number of main delivery channels used by households to receive information for the climate agricultural services (i.e. in-person intermediaries, radio advisories, and SMS) by gender | 3F; 3M | 3F; 3M | 3F & 3M | The baseline value was updated
2.5. Strengthened national capacities and systems to provide integrated climate risk management approaches | Number of households within the targeted communities that receive climate services, disaggregated by source (i.e. farm intermediaries, radio advisories, and SMS), by gender, vulnerable groups and district | Extension Officer: 19,405F & 8,199M ; Radio: 35,804F & 25,418M; SMS: 1,094F & 1,640M | Extension Officer: 28,600F 16,000M & ; Radio: 35,804F & 25,418M; SMS: 1,094F & 1,640M | Extension Officer: 51,000F &34,000M; Radio: 51,000F & 34,000M; SMS: 51,000F & 34,000M | The baseline value was updated
| Number of intermediaries trained in how to access, interpret and communicate climate information to households, to support household decision-making related to food security, livelihoods, and DRR – disaggregated per gender and district | 10F; 44M | 18F; 93M | F:80 M: 100 | The baseline value was updated
2.6 Strengthened national capacities and systems to provide integrated climate risk management approaches | Number of national coordination mechanisms supported | 0 | 3 | 5
| Number of communities extension workers and national agricultural content development committee members engaged in capacity strengthening initiatives to enhance national food security and nutrition stakeholder capacities | 0 | 8F; 49M | 40F; 64M
| Number of capacity building trainings with national/local entities | 0 | 8 | 20
Outcome 3: Strengthened market access strategies and approaches for smallholder farmers | % of households having more secure (increased) access to livelihood assets by gender of household head | F: 9.2% | F14.2% | F:75% | The baseline value was updated
|  | M: 9.9% | M:14.9% | M: 80%
| % of targeted population with sustained climate-resilient livelihoods by gender of household head | F: 10% | F:15% | F:75% | The baseline value was updated
|  | M: 15% | M:20% | M: 80%
| % change in household income disaggregated by activity type and gender of household head | 0 | 0% (a change in income levels was expected due to the marketing component of the project. However, by June 2021, project beneficiaries had not yet made sales of the farm produce. Much progress will therefore be registered in the subsequent reports) | F:25%
M: 30%
| % of targeted smallholders selling through WFP-supported farmer aggregation systems | 0% | 0% | 10% | The baseline value was updated
| % change in HH savings (by type: individual, group, formal, informal) | 0 | 0% (However no significant change registered because establishment of VSL farmer groups is still underway. Much progress is however expected in year 2 of project implementation) | 30%
| % of HHs accessing markets to sell surplus | 15% | 20% | 50% | The baseline value was updated
| % of HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Both 27% | Both 35% | Both - 40% | The baseline value was updated
|  | Women 36% | Women 30% | Women - 30%
|  | Men: 37% | Men: 25% | Men-30%
| % change in HH participating in FOs | 22.8% | 85% | 95% | The baseline value was updated
Output 3.1. Strengthened financial capacities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy) | No. and type of adaptive financial capacities (Insurance, saving, credit, and financial literacy) created in support of individual or community-livelihood strategies as a percentage of plan | 0 | 30%; Insurance as an adaptive financial capacity | 75%
| Value of HH savings (MK) | F: 5,692.58 | F: 5,692.58 & M: 20,656.97 (no significant progress was registered on this indicator since no significant strides were made in year on establishment of VSL groups, as the process is still underway. | 80000 | The baseline value was updated
|  | M: 20,656.97 |  | 80000 | The baseline value was updated
| Number of HH accessing credit (by type) | 19,550 households | 19,550 households (no much progress was made on improving farmers accessibility to micro-finance institutions for credit since establishsment of VSL groups is still underway) | 23600 | The baseline value was updated
| Value of HH credit accessed (formal) (MK) | K22,079.56 | K22,079.56 ((no much progress was made on improving farmers accessibility to micro-finance institutions for credit since establishsment of VSL groups is still underway) | 80000 | The baseline value was updated
Output 3.2. Strengthen performance and outreach of farmer organizations/cooperatives and enhance their capacity to engage in farming as a business | Quantity of food purchased locally from pro-smallholder aggregation systems (in mt) | 0 | 0 | 2000
Output 3.3. Provider market information to inform business planning and activities | Number of farmers’ organizations trained in market access and post-harvest handling skills | 3 | 22 , training mostly was on market access. | 25
| Number of participants receiving market advice (by type) | 3,918F & 1,448M | 6,248F & 2,982M, government minimum prices and places of commodity and market availability etc | 23,600 (14,160F & 9,440) | The baseline value was updated
3.4. Promoted smallholder procurement through government/private sector strategies and programs | Number of smallholder farmers supported | 0 | 6,248F & 2,982M | 23,600 (14,160F & 9,440)
3.5 Promote public pro-small holder procurement | Number of pro-smallholder policies developed | 0 | 0 | 1
Gender Crosscutting: Improved gender equality and women;s empowerment among assisted populations | % of households where women, men or both women and men make decisions on the use/access of markets | Both 27% | Both 35% | Both - 40% | The baseline value was updated
|  | Women 36% | Women 30% | Women - 30%
|  | Men: 37% | Men: 25% | Men-30%
| % of households where women, men or both women and men make decisions on insurance and climate services access | Both- 29% | Both- 29% | Both - 40% | The baseline value was updated
|  | Women 34.1% | Women 34.1% | Women - 30%
|  | Men:37% | Men:37% | Men-30%

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | World Food programme
Type of implementing entity | MIE
Country | Malawi
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 382500 | 382500 | 0 | Total | 399500 | 382500 | 17000 | Total |  |  |  | Total
|  | % of female beneficiaries | 60% | 60% | 0% | % of female beneficiaries | 80% | 60% | 20% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 20% | 20% | 0% | % of Youth beneficiaries | 40% | 20% | 20% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 7 | Drought | 2: Partially effective | Total | 7 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 5% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 96 | Multi-sector | 3: Medium capacity | Total | 180 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 96 | 20% | Public |  | 180 | 40%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Agriculture | 2: Low capacity | Public | National | Agriculture | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Agriculture | 2: Low capacity | 2 | National | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Agriculture |  | 90 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 4250 | 5% | 3: Partially aware |  | 85000 | 90% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 |  |  |  | 104 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 |  |  |  | 12 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 18000 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 34000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 18000 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 34000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% |  |  | 65000 | 75% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agriculture | 65000 | 75% | From 40% to 50% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Agriculture | Soil water conservation | 10 | Physical capital | Agriculture | Soil water conservation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 85000 | Agricultural-related |  | 365
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | National | Public policy | 2 | Agriculture | National | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Community | Innovation rolled out |  | Food Security | Community | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices |  | 7 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  |  | 5 | Innovative practice |  | 4: Effective
Note on I94: Geoffrey KampupuZiba: Assuming each hh rehabilitates about 0.4 of a ha, giving us 34,000ha