## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 2021-06-15 to 2022-06-30
| Project Title: | Adapting to Climate Change through Integrated Risk Management Strategies and Enhanced Market Opportunities for Resilient Food Security and Livelihoods
| Project Summary: | The overall goal of the project is to enhance climate adaptation and food security of households through access to integrated climate risk management strategies and structured market opportunities. The project will benefit 85,000 households, 382,000 beneficiaries in Balaka, Machinga and Zomba districts for a period of 5 years. The project will achieve the project goal by; 1. Improving access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity; 2. Adopting climate-resilience agriculture practices among targeted farmers thereby contributing to the integrated climate risk management approach; and 3. Strengthening market access strategies and approaches for smallholder farmers.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Food programme (WFP) Malawi Country Office | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Malawi | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Machinga District: Traditional Authorities (TAs) Chiwalo, Kawinga, Sale, Nyambi, Kapoloma, Nkoola, Mchinguza, Nkula and Mposa | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
Balaka District: TAs Toreza, Sawali, Matola, Chanthunya, Amidu, Phalula; Nkaya and Nsamala
Zomba District: TAs Ntholowa, Mbiza, Nkagula, Nkapita and Ngwerero
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-10-11
IE-AFB Agreement Signature Date: |  | 2020-02-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-06-15 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2022-12-01
| Original Completion Date: | 2025-06-30
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | The Project Inception Report was submitted in September 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | Project website not yet developed | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Gilbert Kupunda (National Project Coordinator) | Dominican Republic
| Email: | gkupunda@gmail.com | Ecuador
| Date: | 2020-07-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Peter K. Simbani (Director, Debt & Aid Management Division) | Equatoral Guinea
| Email: | pksimbane@finance.org.mw, secpsdad@finance.gov.mw | Eritrea
| Date: | 2019-01-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Kathy Derore (Resilience Outcome Mananger) | Fiji
| Email: | kathy.derore@wfp.org | Finland
| Date: | 2020-07-01 | France
| Executing Agency |  | Greece
| Name: | Gertrude Kambauwa (Director for Land Resources Conservation Department) | Grenada
| Email: | gkambauwa@gmail.com | Guatemala
| Date: | 2020-07-01 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 2: cumulative from project start to 30th June 2022
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30th June 2022 | USD 4,662,243.00
Add any comments on AF Grant Funds. (word limit=200) | The above figure incudes: USD 2,848,250.84 of Actual direct costs; USD 1,527,606.12 of direct cost commitments and USD 1,836.00 of direct cost precommitments. Indirect Support Costs (ISC) are also included as USD 185,136.30 (Actual), USD99,294.40 (Commitment); and USD119.34 (Precommitments)
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (US Dollars)
| Output 1.1 A weather index microinsurance product designed for drought and dry spells to cover farmers’ needs at scale. | 479164.1039
| Output 1.2 Awareness raised among farmers on weather index insurance and vulnerable farmers enabled access to weather index micro insurance | 109429.7674
| Output 1.3 Strengthen national capacities and systems to provide weather index insurance working with private and public sectors | 18558.3606
| Output 1.4 Support inclusion of insurance as risk transfer mechanism in national agriculture programmes | 3003.2258
| Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation ,8 | 111377.1426
| Output 2.2 Promote climate resilient agriculture among farmers through extension service support | 57710.8686
| Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops | 89509.1231
| Output 2.4 Provide climate services to inform livelihood decision making amongst farmers | 110512.2461
| Output 2.5 Strengthened access to and use of weather/climate information for targeted communities to inform livelihood decision-making among farmers | 11828.6327
| Output 3.1. Strengthened financial capacities and market access opportunities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy) | 433590.6267
| Output 3.2 Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced | 173362.09
| Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses | 25930.08
| Output 3.4. Market information provided to inform business planning and activities. | 13711.68
| Output 3.5. Smallholder procurement promoted through government and private sector strategies and programmes | 20364.08
| Total output cost | 1658052.0274
| Project Execution Costs | 380949.3
| MIE fee (including ISC) | 132535.08
| TOTAL | 2171536.4074
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 A weather index microinsurance product designed for drought and dry spells to cover farmers’ needs at scale. | 491277 | July 2021 -June 2023
| Output 1.2 : Awareness raised among farmers on weather index insurance and vulnerable farmers enabled access to weather index micro insurance | 123693 | July 2021 -June 2023
| Output 1.3 Strengthen national capacities and systems to provide weather index insurance working with private and public sectors | 33429.41 | July 2021 -June 2023
| Output 1.4 Support inclusion of insurance as risk transfer mechanism in national agriculture programmes | 12674.77 | July 2021 -June 2023
| Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation | 615798.55 | July 2021 -June 2023
| Output 2.2 Promote climate resilient agriculture among farmers through extension service support | 65216 | July 2021 -June 2023
| Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops | 42073 | July 2021 -June 2023
| Output 2.4: Provide climate services to inform livelihood decision making amongst farmers | 271331.01 | July 2021 -June 2023
| Output 2.5. Strengthened access to and use of weather/climate information for targeted communities to inform livelihood decision-making among farmers | 26172.37 | July 2021 -June 2023
| Output 3.1. Strengthened financial capacities and market access opportunities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy) | 81534.37 | July 2021 -June 2023
| Output 3.2. Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced | 517870 | July 2021 -June 2023
| Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses | 996600.69 | July 2021 -June 2023
| Output 3.4. Market information provided to inform business planning and activities. | 172567.32 | July 2021 -June 2023
| Output 3.5. Smallholder procurement promoted through government and private sector strategies and programmes | 173004.92 | July 2021 -June 2023
| Project Execution Costs (PEC) | 385826.4552 | July 2021 -June 2023
| MIE fee | 141983 | July 2021 -June 2023
| GRAND TOTAL | 4151051.8652

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Unavailability of weather and climate data in the targeted district for analysis | Low | Following the development of climate change products for the project districts in close collaboration with Department of Climate Change and Meteorological Services (DCCMS) in year one of project implementation, the weather and climate data availability problems have now been significantly minimized. In this regard, the project was able to roll out the Participatory Integrated Climate Services Approach (PICSA) in all the districts including Machinga District, which could previously not implement the approach due to data availability challenges. During the reporting period, the project provided trainings to 109 Rainfall recorders in the project impact areas to enhance rainfall data availability, besides the 31 rain gauges which were procured and mounted in year 1 of project implementation.
Partners' failure to integrate the project activities into their regular work (framework) | Low | Partnership at all levels have been maintained and strengthened during the reporting period. This has resulted into adequate integration of project activities at all levels, National, District and Community. During the reporting period, the project results were presented to the agriculture sector coordination meetings which are held twice a year. Due to the joint and participatory planning approached which the project adopted, increased integration of project activities was noticed at both district and community levels. The use of government implementation structures at both district and community levels further enhanced project activity integration.
Humanitarian emergency – A medium/large scale humanitarian emergency occurs in the country, necessitating a diversion of focus for key executing partners and stakeholders. | Low | During the reporting period, project implementation was affected by cyclone Anna and Gombe which led to some of the households in the impact areas requiring humanitarian assistance. The late onset of rainfall and prolonged dry spells further affected the project implementation. Through partnerships with other stakeholders at district and national levels, humanitarian assistance was provided to some of the affected project beneficiaries. Furthermore, the project promoted winter cropping to enhance food availability in the impact areas and reduce the effects of the dry spells, late rainfall onset as well as the effects of cyclones.
Low stakeholder support/buy in for the project – Key stakeholders do not participate fully in project activities. | Low | Relevant stakeholders have been thoroughly engaged during the project on-set and will continue throughout the project implementation period. Joint monitoring visits have been implemented during the reporting period for both high level officials such the Minister of Agriculture, Principal Secretaries (PSs) and technical officials such as Directors who are members of the National Advisory Technical Committee (NATC). Two project steering committee (PSC) meetings have been held during the reporting period and three NATC meetings. Furthermore, with the support of WFP which is the Implementing Entity (IE) one learning event was organized on the Participatory Integrated Climate Services for Agriculture (PICSA) which drew participation of the Government, Non Government Organizations, the Academia and private sector. Additional learning events were organized on Insurance and integrated resilience programming. Various stakeholders also participated in Catchment Conservation and Management Campaign launch activities.
Lack of risk diversification and operation in high risk zones may discourage insurance partners | Low | During the reporting period, engagements with insurance providers, the Insurance Association of Malawi (IAM) was intensified to foster active participation of the insurance companies in implementation of the crop insurance. The project also provided for annual reviews of the insurance product note with the IAM and Pula (the Technical Advisory Institution) to ensure that emerging risks are taken into consideration in the product design. The annual review is however not yet done as the payout report is not yet released.
Political risk considering elections (presidential, parliamentary, and local government elections) | Low | The team reduced the effects by maintaining strong operational partnerships with various national organizations and engaging in advocacy. The inception meetings at district and community levels also significantly helped in getting the buy-in from the various stakeholders at district and community levels. The project continued to provide project implementation updates to various stakeholders including Full Council Members to further reduce political risks.
Technical Capacity of government partners | Low | In order to enhance the technical capacity of government partners, several technical trainings have been provided to the government officials with key roles in implementation of project activities. For instance, trainings have been provided to the government staff at district and community levels on Insurance, PICSA, gender household vision, soil and water conservation, post harvest handling amongst other. WFP as an Implementing Entity has also facilitated periodic review meetings with the Government Team seconded to the project to review the project implementation progress, provide strategic guidance and identify areas requiring additional technical support from WFP. For instance, WFP officers were determined during the reporting period to provide technical backstopping services on implementation of village savings and loan concepts, smallholder agriculture produce marketing, insurance, and M&E
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
None identified during the 2021/22 implementation year and the risks which were identified during the 2020/21 implementation year are now in the low state (less than 50% of likelihood)
None
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Implementation of risk mitigation measures is continuous throughout the project implementation cycle. The project continued to strengthen stakeholder's capacity through various trainings to ensure quality delivery of project activities. Implementation of soil and water conservation activities has also helped to reduce the risk and impact of natural disasters. Through the soil and water conservation activities, degraded land are restored and also protective measures are implemented. During the reporting period, the project also emphasized on implementation of Environmental and Social Management Plans as mitigation and management measures. Some of the environmental and social management strategies implemented focused on hygiene and sanitation, gender and protection, pre-harvest and post harvest produce handling. Synergy building with other on-going activities in the same project implementation sites remained key during the reporting period and will remain as such during the entire project implementation period to minimize risks of double dipping, duplication of efforts, and maximize benefits. In addition, there has been 3 project review and planning meetings with the WFP CO team. This has resulted in a reduced risk on financial accountability.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | No risk | NA | NA | NA | N/A | N/A | N/A
2 - Access and equity |  |  | Interference with access to basic services or exacerbate existing inequities by the youth, elders and women in targeted communities | Use of the community based participatory planning methods making sure to incorporate the representation and opinions of all, with a principal focus on the typically marginalized, develop project strategy for ensuring access and equity, promote establishment and use of bylaws, establish Complaints and Feedback Mechanism (CFM) for all project sites | Number of complaints raised in relation to access and equity | 0 | Put in place deliberate measures to address the access and equity challenges. For instance, during provision of grants to farmer organizations during the reporting period, proper guidelines were put in place to ensure adequate integration of the youth, women and men. The project also continued to employ community based participatory planning methods during workplan development as well as during the quarterly community project reviews to ensure adequate representation of all gender groups in the project implementation as well as integration of their opinions. Established Complaints and Feedback Mechanism (CFM) for all project sites and monitored utilization of the mechanisms by the various stakeholders including the project beneficiaries. A series of beneficiary sensitizations were conducted promoting access and equity for the assets established under the project. | Above of power through project committees, Youth/old age beneficiries left out. | Increased awareness on appropriate behaviour among the those holding power, accountability mechanism, deliberate actions targeting youth, old age. Emphasis on all representation for group activities through standard operating procedures. On Village Savings and Loans (VSLs), youths have been deliberately incorporated as the project promotes financial independence of all groups (men, women and youths).
3 – Marginalized and vulnerable Groups |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
4 – Human rights |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Limited consideration of various gender needs and exacerbated gender disparities | Target at least 50% women in project beneficiary identification as well as project activity implementation | Percentage of women in leadership positions in project impact areas | less than 40% | The project continued to conduct sensitization sessions in all project sites to enhance enhance gender equality and women empowerment. The project also took part in the 16 days gender activism which takes place annually in December to enhance awareness on gender based violence, promote gender equality and experiment. furthermore, during formation of the Village Savings and Loan Clubs, Radio Listening Clubs and farmers groups for irrigation development and grants award, guidance was made on the groups composition to ensure 40% membership by women and 20% the youth. | Increased gender based violence due to women economic empowerment and more benefiting in the project | Increased sensitization that targets both men and women to encourage men participation even in those activities that seems to be female dominated i.e. VSL. Increase awareness on men supporting gender equality and women empowerment.
6 – Core labor rights |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | Establishment of construction sites for aggregation centers as well as irrigation schemes may involve clearing of the land hence potentially negatively affecting natural habitats | Each beneficiaries of both the irrigation schemes and aggregation centers will be required to plant back a minimum of 20 trees in their homestead and also establish a communal woodlot. Furthermore, the beneficiaries are being encouraged to actively take part in implementation of other soil and water conservation activities like Conservation Agriculture. Implementation of integrated watershed management activities is also enhancing protection of the natural habitats. | Number of trees replanted by households in the areas where irrigation schemes and aggregation centers will be constructed and number of woodlots established. Number of watersheds delineated and rehabilitated. | 0 | Enforcement on implementation of complementary activities by the beneficiaries of irrigation schemes and aggregation centers continued during the reporting period. Though construction of both the irrigation schemes and aggregation centers is not yet completed, most of the beneficiaries have already started establishment of tree nurseries in support of this. | Household agriculture land area reduced due to establishment of woodlot, and implementation of soil and water conservation activities. This also reducing yield and household income | The project will continue to provide the fruit tree seedlings for the beneficiaries to plant at their households to increase household income, also support beneficiaries with crop diversification for increased income.
10 – Conservation of biological diversity |  |  | Deterioration of biological diversity if seed and crop types are not correctly selected (e.g. inadvertent introduction of invasive species) and diversified | Prioritize local species and avoid the use of non-native and invasive species. Additionally, these activities will be designed in close collaboration with the MoAIWD. By working with local leaders and village chiefs to rescue traditional and native plants and crop species, this project will support the conservation of biological diversity and increase ecosystem resilience | Hectarage of land in the impact areas with deteriorated biological diversity due to invasive species amongst others | 0 | Implementation of crop diversification project activities continued during the reporting period with the technical leadership of Crops Officers from the Ministry of Agriculture to ensure that appropriate crops are promoted in the project impact areas. | Promoted crops recommended through crops officers not yielding as required. | The project will enhance messaging on crop diversity so that farmers are diversifying their crops within the season (maize, soy beans, pigeon peas, etc.) so that the farmers may still be able to harvest higher yield in some crops depending on the weather and season and still increase their incomes sales.
11 – Climate change |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | Inappropriate waste disposal i.e. polytene tubes during implementation of afforestation and reforestation project interventions | Advocate for reuse of some of the materials i.e. polythene tubes and advocate for proper collection and storage of used polythene tubes (not in reusable state) for selling to plastic manufacturing companies | Number of farmer groups using reused polythene tubes and number of farmer groups linked to plastic manufacturing companies for sale of used plastics | 0 | Sensitizations continued to be provided to the project beneficiaries promoting reuse of the polythene tubes and proper disposal of the same if they cant be reused anymore. Quarterly monitoring exercises were also done to check implementation of the strategies across the impact areas | Farmer groups poorly disposing polythene tubes, causing animal deaths when tubes are swallowed i.e. goats, cattle | Working with key stakeholders on environmental support sensitizations on proper disposal of polythene tubes, including alerting the communities on the dangers the polythene tubes may bring on them.
13 – Public health |  |  | Increased cases of injuries during physical asset creation project activities | Provision of First Aid kit and beneficiary sensitization on safety measures during implementation of asset creation activities | Number of First AID kits provided and number of injury cases recorded during physical asset creation project activities | 0 | Beneficiary sensitization on safety measures continued during the reporting period. No injuries were reported during the reporting period | Reduced number of beneficiaries as a result of fear and safety | Continued sensitizations on safety measures to avoid injuries, increased awareness to supervisors on handling of injuries and complaints.
14 – Physical and cultural heritage |  |  | No risk | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | Increase in run-off, soil erosion and flooding that can cause harm to live and livelihoods. In addition, increased agricultural production and livelihoods may lead to increased investment in livestock which may have an unintended effect on the environment, mostly on soils and water resources. | Selection of the areas for the interventions will be informed by site-specific feasibility studies and aligned with recommendations from the community based participatory sessions. Environmental screening of the project activities. Conduct project beneficiary and frontline staff sensitizations and trainings | Number of communities with increased run-off, soil erosion and flooding induced by the project | 0 | use of community based participatory methodologies during annual workplan development as well as during periodic project reviews continued to ensure identification of the right interventions, at the right time for the right people and right implementation modalities. Refresher soil and water conservation trainings were provided to the frontline staff as well as project beneficiaries during the project implementation period. | Run offs leaving the soil infertile for crop production, leading to low yields | Promoting interventions that will improve the soil fertility e.g. making and applying different types of manure on crops, practicing crop rotation and other good agricultural practices
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes and this is on going. The tools for periodic monitoring of project interventions and ESMPs implementation provides for capturing any unanticipated ESP risks
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorization according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As the Implementing Entity, WFP continued to provide technical support to the Ministry of Agriculture which is the Executing Entity (EE) of the project to ensure that the developed ESMPs are implemented and monitored. During the reporting period, WFP has participated in three field level project monitoring activities. In the periodic project management meetings, as the implementation entity, WFP has continued to ensure that the EE provided adequate implementation progress on the ESMPs. WFP also provided technical support to the project team to build its capacity of employing community based participatory planning approached which was very key in preparation of project annual workplans. Furthermore, in its capacity as IE, WFP continued to provide various reference materials to support project off-take and ongoing implementation i.e. WFPs access and equity strategy, Complaints and feedback mechanism to be tailored by the project. Additionally, technical backstopping services were made available in implementation of the soil and water conservation activities and all other project components to ensure adherence to standards and minimize the identified risks.
Have the implementation arrangements been effective during the reporting period? |  | Yes. The regular programme review meetings between the IE and project team has also ensured that the project team remained on track in implementation of the ESMPs and all project components. Provision of technical support and reference materials during development of project workplans and actual implementation ensured adequate integration of ESPs by the EE. Field level monitoring provided an opportunity to check and appreciate progress in implementation of both project activities and ESMPs.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | During the reporting period, the project continued to ensure adherence to the developed ESMP in implementation of project activities. The project continued to implement the various proposed strategies in the ESMPs alongside implementation of the project activities. The project continued to use the monitoring system developed in year 1 to track implementation progress of the ESMPs. At National level, the EE has a full time designated Monitoring and Evaluation Officer who works hand in hand with the District Environmental Committee which oversees ESMP implementation and monitoring at District level. At community level, the EE has empowered the District Environmental Committee (DEC) to support in monitoring of project activities including implementation of the ESMPs.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. Implementation of the ESMPs alongside project activities implementation has ensured that adequate attention was put in minimizing/mitigating the risks which were identified. Engagement of relevant technical experts in implementation of the project activities also proved effectives as appropriate approaches were being adopted. Furthermore, both frontline staff and beneficiary engagement and sensitizations/trainings on the identified Risks and developed ESMPs was fundamental in fostering adherence to the ESMPs and appropriate standards. Development of the manuals and standard operating procedures also proved to be effective. during the reporting period, the project continued to foster utilization of the developed standard operating procedures in implementation of project activities. Use of already established structures at district and community level has proved to be key in fostering project sustainability.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Yes arrangements have been put in place in the developed ESMPs. In particular, the USP include afforestation, construction of aggregation centers, construction of irrigation centers, Nursery establishments and woodlots establishments. Appropriate strategies for minimizing the identified risks across the USPs have been included in the ESMPs and are being implemented.
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, the required capacity for ESMP implementation is present and effective with both IE and EE. The IE is responsible for monitoring implementation progress of the ESMPs and also provision of technical support. The IE has designated technical focal persons for all the project components i.e. soil and water conservation, crop insurance, smallholder agriculture produce marketing and Village savings and loans. On the other hand, the EE is responsible for disclosure of the ESMPs to the project beneficiaries and all relevant stakeholders. Furthermore, the EE is responsible for actual implementation of the ESMP and reporting of the progress. The EE has appropriate structures in place at all levels to foster implementation of the ESMPs. At National level the EE has the National Project Coordination Unit (NPCU) which amongst others comprises, the National project coordinator, project component leads (Soil and Water Conservation, Crop Insurance, Smallholder Agriculture Produce Marketing and M&E). The NPCU works hand in hand with the District project coordination units (DPCUs) in implementation of the project activities which comprise three technical officers (the District Project Coordinator, Assistant District Project Coordinator and WFP Programme Associate). The DPCUs work in close collaboration with district subject matter specialists for technical support. Furthermore, the DPCUs work in close collaboration with frontline workers in all the project impact areas, who spearhead activity implementation at community level. Adequate orientation/sensitizations have ben done at all levels on the ESMPs. Additionally, at community level, the project is making use of local coordination structures to support monitoring project implementation. These include the Agriculture Stakeholder Panel at Traditional Authority Level and Village Agriculture Committee and Village Natural Resources Management Committee at GVH level. At district level the following coordination structures are in place to perform monitoring roles: the District Environmental Committee and District Agriculture stakeholder Panel. at National Level its the project established a national technical advisory committee which is responsible for monitoring project implementation progress and proving technical direction and guidance. At National Level, the project has also put in place a Project Steering Committee which mainly performs oversight functions.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes, the ESMPs, were updated with the USPs which were identified during the year 1 of project implementation, after conducting the screening exercise. In this regard, appropriate implementation strategies were included in the ESMPs.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
BALAKA DISTRICT
USP 1: [Mitengwe Irrigation Scheme Development]: The irrigation schemes will be developed within the space of 5 years project implementation. A screening exercise for the scheme located in Balaka district in Traditional Authority (TA) Nkaya, in Utale Extension Planning Area (EPA) | General sensitizations to beneficiaries on covid preventive measures adherence amongst beneficiaries have been done, and also reforestation has been promoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homestead of which 10 are for fruits | loss of trees and vegetation/ Loss of natural habitats of insects | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees ( boundary planting plus agroforestry species. Fruits tree species to be included too | Number of trees planted
[6 empty] | Conduct sensitization meetings on good farming practices | No of meetings conducted and number of farmers reached
|  | Conflicts within the community, with neighboring communities or with workers from outside community | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the guidelines of the project | No. of sensitization meetings conducted and number of cases recorded and redressed
|  | Increased cases of injuries | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on occupational safety | No. of meetings and Number of cases registered
[6 empty] | Procure First Aid Kit | No of kits procured
|  | Spread of diseases or introduction of new diseases like Covid-19, HIV/AIDS | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing facilities(Pail, basin and soap) | No. of hand washing facilities distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Soil erosion/Siltation | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Promote good farming practices that enhances water and soil conservation | No of hectares conserved
USP 2: [Njobvu Irrigation Scheme Development]: The irrigation schemes will be developed within the space of 5 years project implementation. A screening exercise for the scheme located in Balaka district in Traditional Authority (TA) Sawali, in Bazale Extension Planning Area (EPA) | General sensitizations to beneficiaries on covid preventive measures adherence amongst beneficiaries have been done, and also reforestation has been promoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homestead of which 10 are for fruits | Alter the land cover of forests (loss of trees and vegetation) on a less than 1ha land, Loss of natural habitats of insects | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees (Surrounding the center) | Number of trees planted
[6 empty] | Conduct sensitization meetings | No of meetings conducted
|  | Increased cases of injuries | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Procure and Distribute First Aid Kits | No of Kits Procured and No of cases registered
|  | Loss of soil/ siltation | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Promote good farming practices | No of hectares under soil and water conservation
|  | Conflicts within the community, with neighboring communities or with workers from outside community | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the guidelines of the project | No. of sensitization meetings conducted and number of cases recorded and redressed
|  | Spread of diseases or introduction of new diseases like Covid-19, HIV/AIDS | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 3: [M'mangeni Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH : Chiendausiku | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | handwashing/sanitary facility (Basin, Pail, soap) | handwashing facilities distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings & acquisition forms signed
|  | Disruption of marriages | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the dangers of sexual relationships | No of meetings conducted and No of cases
USP 4: [Kapasule Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Mackenzie | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No. of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings, acquisition forms signed and No of cases
USP 5: [Chamba Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Toleza, Bazale EPA, GVH Chimkwita | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 6: [Chisawasawa Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Disi | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) | low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs, Covid-19, Waterborne diseases | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre | No of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings & acquisition forms signed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 7: [Matola Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Matola, Bazale EPA, GVH Matola | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism. | Loss of vegetative cover ( Trees) | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs, Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
[6 empty] | Procure and distribute masks | No of masks distributed
USP 8: [Mchilakwenda Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Matola, Bazale EPA, GVH Mchilakwenda | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
USP 9: [Mikaele Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Chilumba | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meeting, acquisition forms signed, No of cases
USP 10: [Mpinga Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Nsamala, Mpilisi EPA, GVH Kampeni | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings, acquisition forms signed and No of cases
USP 11: [Kalembera Nursery and Woodlot establishment]: The screening was conducted in Balaka district, TA Matola, Bazale EPA, GVH Tembo | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Loss of vegetative cover ( Trees) on a land less the 1ha during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree planting | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | - (i) Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | - (ii) Linking beneficiaries to the nearest Health Centre/Distribution of condoms | No of condoms distributed
|  | Increased conflicts over land | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the need to give land voluntarily and have the Land acquisition forms | No of meetings, acquisition forms signed and No of cases
USP 12: [Mgumbala Afforestation : The screening was conducted in Balaka district, TA Nkaya, Utale EPA, GVH Nkaya 1 | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
[6 empty] | Conduct sensitization meetings | No of meetings conducted
|  | Conflicts within the community, with neighboring communities or with workers from outside community | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the guidelines of the project | No. of sensitization meetings conducted
|  | Spread of diseases or introduction of new diseases | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Procure and distribute condoms | No of condoms distributed
USP 13: [Kayamba Afforestation]: The screening was conducted in Balaka district, TA Nkaya, Utale EPA, GVH Mgomwa | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | No of trees planted
|  | Poor waste disposal i.e. polythene tubes | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitizations on proper waste disposal, reuse of polythene tubes | No of sensitization sessions, number of farmer groups reached and number of farmer groups reusing polythene tube
|  | Spread of diseases or new introduction of diseases (Covid-19, | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct awareness meetings | No of meetings
[6 empty] | Procure and distribute condoms | No of condoms distributed
[6 empty] | -Procure and distribute masks | No of masks distributed
USP 14: [Meleka Afforestation]: The screening was conducted in Balaka district, TA Chakanza, Utale EPA, GVH Chakanza | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Alter the land cover of forests (loss of trees and vegetation) on a less than 1ha land, Loss of natural habitats of insects | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (Covid-19, HIV/AIDS) | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 15: [Jingasiya Afforestation The screening was conducted in Balaka district, TA khwalala, Utale EPA, GVH Khwalala | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (Covid-19, HIV/AIDS) | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings on the diseases | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 16: [Maliwata Afforestation] The screening was conducted in Balaka district, TA Sawali, Bazale EPA, GVH Maliwata | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (Covid-19, HIV/AIDS) | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Provide handwashing facilities | No of facilities provided
USP 17: [Mmanga Afforestation] : The screening was conducted in Balaka district, TA Sawali, Bazale EPA, GVH Sawali | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases including HIV/AIDS,TB | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 18: [Misowa Afforestation The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Misowa | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
USP 19: [Mkwekwere Afforestation The screening was conducted in Balaka district, TAAmidu, Ulongwe EPA, GVH Mkwekwere | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
USP 20: [Zilipaiwo Afforestation The screening was conducted in Balaka district, TA Sawali, Bazale EPA. GVH Chikalongwe | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases including cholera, HIV/AIDS, TB | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 21: [Pilitu Afforestation The screening was conducted in Balaka district, TA Sawali, Bazale EPA, GVH Pilitu | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
[6 empty] | Conduct awareness meetings on the importance | No of meetings
|  | Land conflicts | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings | No. of meetings and Number of cases registered
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 22: [Mlambe Afforestation ] The screening was conducted in Balaka district, TA Chanthuya, Rivirivi EPA, GVH Siliya | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (HIV/AIDS, Covid-19) | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
USP 23 [Tithandizane Afforestation ] The screening was conducted in Balaka district, TA Chanthuya, Rivirivi EPA, GVH Chimpakati | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases (TB, HIV/AIDS) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 24 [Kachingwefafforestationa ] The screening was conducted in Balaka district, TA Chanthuya, Rivirivi EPA, GVH Chimpakati | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Proposed Mitigation/enhancement Measures | No of seedlings out planted
[6 empty] | Planting trees | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No of meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of items distributed
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | Number of meetings conducted
[6 empty] | -Distribution of condoms | Number of condoms distributed
USP 25[Talandira/Sakaiko Afforestation ] The screening was conducted in Balaka district, TA Nsamala, mpilisi EPA, GVH Nsamala | Yes, Farmer groups involved in afforestation have been sensitized on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period a complaints redress mechanism has been developed and the associated manual. sensitization of the project beneficiaries on the GRM are continuous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Proposed Mitigation/enhancement Measures | No of seedlings out planted
[6 empty] | Planting trees | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No of meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | Number of meetings conducted
[6 empty] | -Distribution of condoms | Number of condoms distributed
USP 26[Thamanda Afforestation ] The screening was conducted in Balaka district, TA Chanthunya, Rivirivi EPA, GVH Maitoni | Yes, Farmer groups involved in afforestation have been sensitized on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period a complaints redress mechanism has been developed and the associated manual. sensitization of the project beneficiaries on the GRM are continuous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Proposed Mitigation/enhancement Measures | No of seedlings out planted
[6 empty] | Planting trees | No of trees planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No of meetings conducted
[6 empty] | Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
[6 empty] | Conduct sensitization meetings on the expected behavior from the beneficiaries as well as guidelines of the project | No of meetings conducted
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | Number of meetings conducted
[6 empty] | -Distribution of condoms | Number of condoms distributed
USP 27 [Manjanja Afforestation ] The screening was conducted in Balaka district, TA Chanthunya, Rivirivi EPA, GVH Manjanja | Yes, Farmer groups involved in afforestation have been sensitized on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period a complaints redress mechanism has been developed and the associated manual. sensitization of the project beneficiaries on the GRM are continuous. | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | -Distribution of condoms | No of condoms distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 28 [Mulunguzi Afforestation ] The screening was conducted in Balaka district, TA Chanthunya, Rivirivi EPA, GVH Chimpakati-Chanza | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  | Spread of diseases or introduction of new diseases | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct awareness meetings | -No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | Procure and distribute Masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
USP 29[Msechero Afforestation ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Msechero | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
USP 30 [Mkanongwa Afforestation ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Chipyali | Yes, sensitization of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Distribution of condoms | No of condoms distributed
[6 empty] | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
USP 31 [NamayaAfforestationa ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Namaya | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting 10 trees where one has been cut | No of seedlings out planted
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of diseases or introduce new diseases (HIV/AIDS, Waterborne diseases) | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on diseases transmission and preventive measures | No. of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms distributed
|  | Increased incidences of open defecation | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of pit latrines | No. of pit latrines constructed
USP 32 [NamondeAfforestationa ] The screening was conducted in Balaka district, TA Amidu, Ulongwe EPA, GVH Namonde | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | loss of trees and vegetation on a less than 1ha land, Loss of natural habitats of insects during nursery establishment | Medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees where some have been cut | No of seedlings out planted
[6 empty] | Use of tree branches or thinned sprouts when constructing fences or marking planting stations | Sensitization meetings
|  | Spread of Covid-19 | medium | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings. | No. of sensitization meetings conducted
[6 empty] | -Procure and distribute masks | No of masks distributed
[6 empty] | Distribute handwashing/sanitary facility (Basin, Pail, soap) | Number of handwashing facilities distributed
|  | Spread of HIV/AIDS and STIs | Low | Yes. The Balaka District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | -Conduct sensitization meetings on the dangers of unprotected sex | No of meetings conducted
[6 empty] | -Distribution of condoms | No of condoms distributed
ZOMBA DISTRICT
USP 1: Chakalamba Afforestation Subproject in Traditional Authority Nkagula]: | Yes, Farmer groups involved in afforestation have been sensitized on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. sensitizations on gender based violence and gender balance in leadersip positions have also been done. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings to categories of group in the community | Number of targeted groups sensitized
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of project beneficiaries following covid-19 prevention measures
USP 2: [Mgwalangwa Afforestation Subproject in Traditional Authority Nkagula]: | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Increased cases of gender based violence | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization and capacity building meetings on gender based violence | Number of farmers trained and Number of Cases Recorded and resolved
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
USP 3: [Chidule Afforestation Subproject in Traditional Authority Nkagula]: | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 4: [Staubi Afforestation Subproject in Traditional Authority Nkagula]: | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism . | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 5: [Chilimani Afforestation Subproject in Traditional Authority Nkagula]: | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Relevant stakeholders feeling not consulted | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct sensitization meetings involving all categories of people | Number of stakeholders sensitized
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 6: [Bonnongwe Afforestation Subproject in Traditional Authority Nkagula]: | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 7: [Mkwezaziyo Afforestation Subproject in Traditional Authority Nkagula] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 8: [Disi Afforestation Subproject in Traditional Authority Nkagula] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Putting hand washing station in place | Number of handwashing station established
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 9: [Mphatsa Afforestation Subproject in Traditional Authority Nkagula] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 10: [Khanda Afforestation Subproject in Traditional Authority Nkagula] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes after outplanting seedlings | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | Number of people following covid-19 prevention measures
USP 11: [khewa Afforestation Subproject in Traditional Authority Ngwelero]: | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 12: [Maliko Afforestation Subproject in Traditional Authority Ngwelero] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 13: [Kadyampakani Afforestation Subproject in Traditional Authority Ngwelero] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 14: [Jumbe 1 Afforestation Subproject in Traditional Authority Ngwelero] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | following covid-19 prevention measures as set by Ministry of Health | No of people following covid-19 prevention measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 15: [Bille 1 Afforestation Subproject in Traditional Authority Ngwelero] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 16: [Nanyole Afforestation Subproject in Traditional Authority Ngwelero] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | No of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | provision of face masks to prevent the spread of COVID-19 | No of people putting on face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 17: [Ndechere Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 18: [Ndalama Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Project being controlled by a subset of a group- monopolised | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 19 [Jiya Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 20: [Saiti Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Stakeholders feel that they have not been consulted | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 21 [Taombe Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 22 [Machiringa Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism . | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 23: [Solobala Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Stakeholders feel that they have not been consulted | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 24 [Mapemba Afforestation Subproject in Traditional Authority Ntholowa] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 25: [ Sululu Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
|  | Poor disposal of polythene tubes after outplanting seedlings | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of face masks to prevent the spread of COVID-19 | Number of farmers wearing face masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of handwashing facilities in place and being used
USP 26: [Chipulumutso Irrigation Scheme in Traditional Authority Malemia] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested of which about 10 are fruit trees | Loss of trees to clear land for irrigation | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Panting of trees | Number of trees planted in the catchment
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Land conflicts | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Adherence to land acquisition procedures | Number of land agreement forms signed
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
USP 27: [Chigumukile Irrigation Scheme in Traditional Authority Malemia] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homestead of which 10 are fruit trees | Loss of trees to clear land for irrigation | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Panting of trees | Number of trees planted in the catchment
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Land conflicts | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Adherence to land acquisition procedures | Number of land agreement forms signed
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
USP 28: [Tithandizane Irrigation Scheme in Traditional Authority Malemia] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested of which 10 are fruit trees | Loss of trees to clear land for irrigation | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Panting of trees | Number of trees planted in the catchment
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Land conflicts | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Adherence to land acquisition procedures | Number of land agreement forms signed
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
USP 29: [Nsomba Aggregation Centre in Traditional Authority Malemia] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homestead of which 10 are fruit trees | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 30: [Nthiko Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 31: [Msosa Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 32: [Malupi Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 33: [Kanyesi Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 34: [Masambuka Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 35: [Machinjili Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 36: [Mulomba Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 37: [Chitenjere Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 38: [Nachawe Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 39: [Chitope Afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 40: [Namichimba Afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 41: [Namichimba Re-Afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 42: [Kudwale Afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
USP 43: [Chimwazeni, Sunuzi and Lungazi Re-fforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of farmers sensitized
USP 44: [Chiloweni and Mulinga Re-afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 45: [Tsekanyenua and Namichimba Afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetings conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process
USP 46: [Utwe Re- Afforestation Subproject in Traditional Authority M'biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 47: [Mulinga and Chilowe Afforestation Subproject in Traditional Authority Nkagula] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 47: [Tsekanyenua Afforestation Subproject in Traditional Authority M,biza] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetings conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 47: [Tsekanyenua Afforestation Subproject in Traditional Authority Malemia] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetings conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 48: [Mambo Trading Aggregation Centre in Traditional Authority Nkapita] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested of which 10 are fruit trees | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using picsa bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 49: [Kwilindi Afforestation Subproject in Traditional Authority Nkapita] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism y. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 50: [Matola Afforestation Subproject in Traditional Authority Nkapita] | Yes, Farmer groups involved in afforestation have been sensitized on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles including gender equality. | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 51: [Fikila 1 Afforestation Subproject in Traditional Authority Nkapita] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Discrimination of individual groups | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Spread of HIV and STIs | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitize community on HIV & AIDS | Number of people sensitized
USP 52: [Jussu 1(Tuntu) Afforestation Subproject in Traditional Authority Nkapita] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitized on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Poor disposal of polythene tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | re-using the polythene tubes after planting the seedlings | Number of polythene tubes collected and re-used
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
|  | Pollution of water courses | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Promote natural regeneration | Area under natural regeneration
|  | Water logging and salinization | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use Pot filling | Number of trees sown in tubes
USP 53: [Mikundi Soil and Water Conservation Subproject in Traditional Authority Nkapita] | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Solid and liquid waste generation | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  | Inadequate community participation on the project | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Conduct Sensitization meetings with all groups of people | Number of meetinga conducted
|  | Spread of COVID-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of hand washing items | Number of Hand washing station in place
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Using masks to prevent the spread of COVID-19 | Number of people using face masks
USP 54: [Aggregation Centre in Traditional Authority Mbiza, GVH lototoni] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 55: [Aggregation Centre in Traditional Authority Nkagula GVH, GVH Khanda] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested of which 10 are fruit trees | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
USP 56: [Aggregation Centre in Traditional Authority Nkagula GVH, GVH Kataya] | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees athomested | Spread of HIV and STIs | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization community on HIV & AIDS | Number of people of people sensitized
|  | Use of agro-chemicals to pollute environment | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | conduct farmer training on the safe use of agrochemicals and in integrated pest management | Number. of farmers trained
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Store produce in PICS bags | No of farmers using pics bags
|  | Conflict over land use | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Signing of land agreement form/ transfer form | Number of Land agreement forms signed
|  | Spread of Covid-19 | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of masks by workers and supervisors | Number of workers and farmers wearing masks
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meeting on covid-19 preventions | Number of farmers and workers sensitized on covid 19 preventive measures
|  | Increased incidences of injuries to workers | low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of First Aid kit | Number of fully stocked. first Aid Kit provided
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of PPE | Number of PPE provided and being used by all workers
|  | Generation of Solid and liquid waste | medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of a rubbish pit and pit latrine for biodegradable waste | No of pits constructed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision of waste bins for collection and disposal of non-biodegradable waste e.g. construction waste | No of bins provided
MACHINGA DISTRICT |  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities
USP 1: Nyambi EPA aggregation centre in T/A Nyambi | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | Number of seedligs raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Planting trees | Number of trees planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of cement blocks | No. of blocks moulded
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for produce storage
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce storage/fumigation
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Community sensitization meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on human rights | No. of trainings and No. of cases registered and redressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on accident prevention safety | No. of trainings and No. of cases recorded
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on prevention of infectious diseases | No. of trainings and No. of cases registered
USP 2: Ngaukanika aggregation centre under T/A Kawinga | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary of the irrigation scheme is also planting a minimum of 20 trees at homested | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | Number of seedligs raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Planting trees | Number of trees planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of cement blocks | No. of blocks moulded
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for agricultural produce storage
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce storage/fumigation
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Community sensitization meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on human rights | No. of trainings and No. of cases recorded and addressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on accident prevention safety | No. of trainings and No. of cases registered
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on prevention of infectious diseases | No. of trainings
USP 3: Mchiguza aggregation centre under T/A Mchiguza | General sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary is planting a minum of 20 trees at homested | Cutting down of trees and removal of vegetative cover | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Planting trees | Number of trees planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of cement blocks | No. of blocks moulded
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for produce storage
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce fumigation
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Community sensitization meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on human rights | No. of trainings and No of cases registered and addressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on accident prevention safety | No. of trainings and no. of injury cases registered
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on prevention of infectious diseases | No. of trainings and No of cases registered
USP 4: Nkula Headquarters aggregation Centre under T/A Nkula | construction of the aggregation centres is yet to commence. However general sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary i also planting a minumum of 20 trees at homested | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | Number of seedligs raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Planting trees | Number of trees planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of cement blocks | No. of blocks moulded
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Angle iron for roofing | No. o f iron bars procured
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of PICs bags | No. of farmers using PICS bags for produce storage
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of tapauline for drying and covering produce after fumigation | No. of farmers using tapaulines during produce storage/fumigation
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Use of protective wear | No. of protective gears procured/No. of farmers using protective gear
|  | Soil erosion | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Vertivar planting | Area planted
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws developed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Community sensitization meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on human rights | No. of trainings and No of cases registered and addressed
|  | Injury from heavy machinery | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Use of protective wear | No. of protective gears procured
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on accident prevention safety | No. of trainings and No. of cases registered
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Awareness meetings | No. of meetings
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training on prevention of infectious diseases | No. of trainings and No of cases
USP 5: Nyenyezi 2 Irrigation scheme under T/A Sale | construction of the irrigation scheme is yet to commence. However general sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary is planting a minimum of 20 trees at homestead | Increased soil erosion, floods and sediment load | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of marker ridges | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Ridge realignment | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Vetiver planting | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Box ridging | Area ridged (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Construction of deep trenches | No. of deep trenches
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Length (m)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Construction of stone bunds | Length (m)
|  | Gully formation | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of mansonery checkdams | No. of checkdams
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Length (m)
|  | Cutting down of trees and removal of vegetative cover | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Area planted (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Promote natural tree regeneration (ha) | Area (ha)
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings and No of cases registered
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings and No of cases registered and reddressed
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Community sensititzation | No. of meetings and No of cases registered.
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Distribution of condoms at the scheme | No. of condoms distributed
USP 6: Chibulubulu Irrigation Scheme under T/A Chamba | Construction of the irrigation scheme is yet to commence. However general sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary is constructing a minimum of 20 trees at homestead | Increased soil erosion, floods and sediment load | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of marker ridges | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Ridge realignment | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Vetiver planting | Area planted (ha)
|  | Cutting down of trees and removal of vegetative cover | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Promote natural tree regeneration (ha) | Area (ha)
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings and No of cases registered
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings and No of cases registered and reddressed
USP 7:Mchuwa Irrigation Scheme under T/A Nyambi | Construction of the irrigation scheme is yet to commence. However general sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary is constructing a minimum of 20 trees at homested | Soil degradation | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Manure making and application | No. of heaps made
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Area (ha) applied
|  | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Promote natural tree regeneration (ha) | Area (ha)
|  | Pollution of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings
|  | Conflicts amongst community members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sharing of condoms at construction site | No. of condoms distributed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Community sensitization meeting | No. of meetings conducted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training in infectious diseases | No. of trainings conducted and No of cases registered
USP 8: Mdikira Irrigation Scheme under T/A Nkula | construction of the irrigation scheme is yet to commence. However general sensitizations to beneficiaries on covid preventive measures adherance amongs beneficiaries have been done, and also reforestation has been prompoted a lot during the reporting period. Each beneficiary is constructing a minimum of 20 trees at homestead of which 10 are for fruit trees | Increased soil erosion, floods and sediment load | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of marker ridges | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Ridge realignment | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Vetiver planting | Area conserved (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Box ridging | Area ridged (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Construction of deep trenches | No. of deep trenches
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Length (m)
|  | Gully formation | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Construction of checkdams | No. of checkdams
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Length (m)
|  | Cutting down of trees and removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  |  | Area planted (ha)
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Promote natural tree regeneration (ha) | Area (ha)
|  | Polluton of air and water due to use of agrochemicals | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Training in Integrated Pest Management | No. of trainings and No of cases registered
|  | Conflicts amongst members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings and No of cases registered and reddressed
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Community sensitizations | No of sensitisation compaigns conducted and No of beneficiaries adhering to the preventive measures
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Sharing of condoms at construction site | No. of cases registered
USP 9: Chimwankhwazi afforestation under T/A Nkula | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities
|  | Removal of vegetative cover | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree Nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Promote natural tree regeneration (ha) | Area (ha)
|  | Conflicts amongst community members | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Development of by-laws | No. of by-laws
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Contact and dialogue | No. of meetings
|  | Spread of infectious diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Encourage contractor to recuit skilled and non skilled labour locally | No. of local workers recruited
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Sharing of condoms at construction site | No. of condoms distributed
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Community sensitization meeting | No. of meetings conducted
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Training in infectious diseases | No. of trainings conducted and No of cases registered
USP 10: Tembenu afforestation under T/A Mposa | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
USP 11: Mtalikachawu afforestation under T/A Mposa | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
USP 12: Msombi afforestation under T/A Mposa | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
USP 13:Mangulu afforestation under T/A Mposa | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
USP 14: Tiyanjane afforestation under T/A Mposa | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Removal of vegetative cover during nursery establishment and poor disposal of the polythen tubes | Medium | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Tree nursery establishment | No. of seedlings raised
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Tree planting | No. of seedlings planted
USP 15: Samute afforestation under T/A Kapoloma | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Increased unpaid work for women/girls | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Equal distribution of wprk | Activities done by men and women
|  | poor disposal of the polythen tubes |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | Inadequate consultation by other stakeholders |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Sensitization at all levels | No. of meetings
USP 16:Saidi Ndege Afforestation under T/A Kapoloma | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Spread of endogenous/existing diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provision and use of reusable face masks | No. of face masks provied
|  | poor disposal of the polythen tubes |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | Inadequate consultation by other stakeholders |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Sensitization at all levels | No. of meetings
USP 17: Tiyanjane Afforestation under T/A Kapoloma | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Spread of endogenous/existing diseases | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Provisionn and use of reusable face masks | No. of face masks provied
|  |  |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | poor disposal of the polythen tubes |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Availability of condoms at the site | No. of condoms
USP 18:Kalambo Afforestation under T/A Nyambi | Yes, sensitisation of farmer groups involved in afforestation continued during the reporting period, focusing on proper handling of polythene tubes and re-using of the same where possible. Covid preventive measures sensitizations have continuously been done in the project impact areas and during each farmer engagement, the measures have been adhered to. Additionally, smallholder farmers have been adequately sensitised on the project components including their roles and gender equality in project participation . During the reporting period, adequate awareness was also made to the project beneficiaries on use of the complaints redress mechanism | Inadequate consultation by other stakeholders | Low | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities | Yes, the data was gender disaggregated. A total of 25F and 25M beneficiaries were consulted during the screening process | Sensitization at all levels | No. of meetings
|  | poor disposal of the polythen tubes |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | re-using the polythene tubes after planting the seedlings | No. of polythene tubes reused per season
|  | Marginalized people having difficulties in filing complaints of feedback |  | Yes. The Zomba District Environmental Sub-committee was consulted as well as the communities |  | Sensitize the people to chanel the complaints to relevant authorities | No. of complaints lodged
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Some community members were claiming that they were initially identified as project beneficiaries however later on they were replaced by others. |  | The project enhanced backstopping visits and sensitisation to the communties to enhance beneficiary understandng of the project and the insurance component as most of them perceieved that all project beneficiaries will benefit the insurance component of the project. Yet according to the project design, only 30% of the total project target is expected to benefit from the insurance component. With intensified sensitisation, most of the project beneficiaries now have a good understanding of the project and its components.
Inadequate inputs distribution such for agroforestry, afforestation and other soil and water conservation practices |  | The project beneficiaries and extension workers were re-sensitization and encouraged to use locally available resources as much as possible in addressing the soil and water conservation challenges for purposes of project results sustainability. It was therefore made clear to the project beneficiaries that the project will only be providing top up inputs. This concept has now been well understood by the communities and extension workers.
The beneficiaries have been complaining about the delayed provision of the insurance payouts. This is due to the design of the insurance product, as payout amounts can only be calculated at the end of the season. In addition, there is a misconception amongst some beneficiaries that insurance payouts are automatic at the end of the season, irrespective of whether the index has actually been triggered or not. Such beneficiaries think that index insurance is like a government social protection system that provides cash regularly every year. |  | Engagement meetings with beneficiaries were conducted to re-sensitize them on the insurance component and payout processes. WFP and AF project coordination team also closely followed-up with the insurance companies and PULA on the final report and outcome of crop-cuts. For the subsequent year WFP and the AF project team are negotiating with the insurance companies and PULA to develop a roll-out plan with clear timelines to reduce delays in the processes at all stages.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
The AF project in line with the project document implemented a new baseline in the 2nd quarter of 2021, this has resulted in some changes in the values of the baselines from the original project document
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Note that baseline figures have been updated following the baseline survey
Disaggregation of the target by gender | Impact: Enhanced climate adaptation and food security of households through access to integrated climate risk management strategies | % of the population in targeted communities reporting benefits from an enhanced livelihood asset base by gender using the Asset Benefit Indicator (ABI) | 0 | 50% | Good; During the reporting period, the project has supported the beneficiaries to be organized in groups and practice seed multiplication i.e. sweet potatoes, cassava as well as fruits like banana in order to foster crop diversification. Additionally, through the same farmer groups, the beneficiaries have been supported under marketing by linking them to better produce markets and also provision of grants. Farmers accessibility to climate information has improved as well as utilization of the climate information. Farmer accessibility to crop insurance as a risk transfer mechanism has been also promoted to both direct and indirect project beneficiaries. Implementation of various soil and water conservation activities has also enhanced smallholder farmers adaptive capacity to climate change. The project progress is therefore on track. Note that the baseline value remained the same even after conducting the baseline survey.
| Outcome 1: Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity | % of households in targeted communities with reduced risk related to extreme weather events by gender of household head | 7%F; | F: 65% | Good. About 18%F & 11%M of the total project beneficiaries have been supported under crop insurance as a risk transfer mechanism. During the reporting period, a lot of soil and water conservation practices were also promoted leading to reduced climatic risks. Collectively, 27F and 18M reported reduced risks related to extreme weather events. Note that the baseline value was updated after the baseline survey. .
|  |  | 5%M | M: 70%
|  | % of households belonging to vulnerable groups with access to weather index micro insurance by gender of household head | F: 0% | F: 30% | Good. About 18% Females and 11% Males had access to the crop insurance however, discussions are still underway with IAM and PULA on how best to improve farmers accessibility. About 34% of the total project beneficiaries expressed interest to access the insurance cover Note that the baseline value remained the same even after conducting the baseline survey
|  |  | M:0% | M:40%
| Output 1.1: Targeted population groups covered by adequate risk reduction systems | Number of people insured (non-cash, partial cash payment and full cash payment by gender | 0 | F: 10,240 | Good. A total of 25395 project beneficiaries ((16,103F, 9,292M) were covered under the crop-micro insurance as a risk transfer mechanism during the reporting period against the expected target of 25,600 households. Note that the baseline value remained the same even after conducting the baseline survey
M:15,360
| Output 1.2 Awareness raised among farmers on weather index insurance | Number of people trained on index design by gender | F: 0 | F: 160 | Good. A total of 160 farmers (43F and 117M) have been trained on insurance as a risk transfer mechanism and the Area Yield Index Design as ToT. The lead farmers further sensitized the general farmers. Note that the baseline value was updated after the baseline survey
|  |  | M:0 | M: 20
|  | Number of people sensitized on insurance as a risk transfer mechanism by gender | F: 240 | M: 195,075 | Good. Beneficiary sensitization was conducted several times during the reporting period to sensitize the beneficiaries about payouts, about the insurance report and on the registration for insurance service. this formed an integral part of the project implementation in year 2 considering that for most of the project beneficiaries, the concept is still relatively new. The sensitization campaigns were conducted not only the insurance project beneficiaries which is 30% of the total project beneficiaries, but rather to the entire universal set of beneficiaries, 382500 people, which is 85,000 households. Note that the baseline value was updated upward after the baseline survey. In one of the project sites in Zomba district, crop insurance as a risk transfer mechanism was not a new concept as WFP had previously implemented the insurance scheme in part of the site
|  |  | M: 160 | F:187,425
| Outcome 2: Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | % of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses by gender | F: 41.1% | F: 90% | Good. About 79% females and 93% males have been made aware of the adverse impacts of climate change and appropriate responses. The beneficiaries were sensitized with information regarding the prospects of the season using the downscaled seasonal forecast, and using the lead farmer approach most farmers have been trained in PICSA methodology to enhance their usage of climate information in planning, and have received climate information for their areas. The project beneficiaries have implemented soil and water conservation practices such as vetiver grass plantation, construction of check dams, construction of stone bands and swales, afforestation and reforestation; natural tree regeneration. Furthermore, crop diversification and formation of backyard gardens have been encouraged amongst the beneficiaries. Note that the baseline value was updated upwards after the baseline survey. Balaka and Zomba districts had already been implementing PICSA methodology which amongst others enhances farmers awareness of the adverse impacts of climate change to inform their livelihood decision making while for Machinga District, it was the first time to roll out full PICSA methodology during the reporting period.
|  |  | M: 58.9% | M: 95%
|  | % of households using weather and climate information for decision-making on livelihoods and food security by gender and district | F: 60% | F: 75% | Good. About 75%F and 90%M have been using weather and climate information for decision making on livelihoods. As we move into year 3 of project implementation, tremendous improvement is expected more lead farmers have been trained in the PICSA methodology who will be helping in cascading the trainings to all our project beneficiaries. Note that the baseline value remained the same even after conducting the baseline survey
|  |  | M: 80% | M: 85%
|  | % of targeted households with borderline to acceptable food consumption score by gender of household head and district | F: 90.9% | F: 75% | Good. *About 95% F and 97.9%M had the food consumption score in the range of borderline to acceptable line. It should however be noted that the baseline of the project happened close to the harvest time and as such it skewed the results since 7 days dietary recall data is used on this indicator. The same period was used for the annual outcome monitoring survey to allow for results comparability. This was a food abundance period as most of the beneficiaries had just harvested. Note that the baseline values were updated upwards after the baseline survey
|  |  | M: 94.2% | M: 80%
| Output: 2.2. Promote climate resilient agriculture among farmers through extension service support | % of HHs involved in CA (minimum tillage, crop diversity, retention of crop residues) by gender of household head | F: 8% | F: 30% | Good. The project promoted conservation agriculture, integrating crops with trees (agroforestry) manure making and application among farmer fields and it also mounted various demonstrations on three themes i.e drought mitigation, integrated soil fertility improvement and crop diversification
|  |  | M: 7% | M: 35%
| Output 2.3. Support crop diversification with a focus on drought tolerant and nutritious crops | Number of HH accessing improved fruit seedlings, leguminous trees and fodder tree seed by gender of household head | F: 21,590 (Leguminous Trees); F: 9,010 (fodder trees); 2,550 (improved Fruits) | F: 40,000 | Good. Significant progress was registered under this indicator as farmers were supported with legume pass on such soya. further direct sowing of agroforestry and fodder seeds as well assorted fruit seedlings for planting at both individual level and group level. The project also distributed sweet potato vines to farmers. Pigeon peas are predominantly grown in the project impact areas hence high values of leguminous trees. Additionally, in most of the project impact areas, soil and water conservation projects were previously implemented by the Governments, besides the normal promotion of the soil and water conservation practices at community level. Furthermore, in some of the project areas, Food For Asset (FFA) was previously implemented by WFP, especially in Zomba and Balaka Districts while in Machinga, FFA is still on -going in one TA in which AF is also being Implemented.
|  |  | M: 23,800 (Leguminous trees); M:11,815 (Fodder trees); 3,400 (Improved fruits) | M: 45,000
| 2.5. Strengthened national capacities and systems to provide integrated climate risk management approaches | Number of intermediaries trained in how to access, interpret and communicate climate information to households, to support household decision-making related to food security, livelihoods, and DRR – disaggregated per gender and district | 10F; 44M | Extension Officers F:31 M:84 Lead Farmers F: 650 M:1109 | Good. A good progress was registered. About 1,193 Male and 6818 Female intermediaries have been trained during the reporting period in PICSA methodologies which is key in informing household decision making related to food security, livelihoods and DRR. The approach to use lead farmers have helped to increase number of intermediaries Note that the baseline values were updated for this indicator.
| Outcome 3:Strengthened market access strategies and approaches for smallholder farmers | % of households having more secure (increased) access to livelihood assets by gender of household head | F: 9.2% | F:75% | Good. about 40.1% Female beneficiaries and 45.2% Male beneficiaries reported having more secure (increased) access to livelihood assets. Note that the baseline value was updated upwards after the baseline survey.
|  |  | M: 9.9% | M: 80%
|  | % of targeted population with sustained climate-resilient livelihoods by gender of household head | F: 10% | F:75% | Good. about 40.1% Female beneficiaries and 45.2% Male beneficiaries reported to have sustained climate-resilient livelihoods. Note that the baseline value was updated upwards after the baseline survey.
|  |  | M: 15% | M: 80%
|  | % change in household income disaggregated by activity type and gender of household head | 0 | F:25% | Fair. About 5% in household income levels by both gender groups was reported during the annual outcome monitoring. Significant progress is expected to be registered in the third year of project implementation following provision of farmer group grants, increased VSLs as well as enhance linkages to markets.
M: 30%
|  | % of both male-headed and female HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Both 27% | Both - 40% | Good progress has been registered on use of market advice. The PICSA, Gender household visioning, and SHEP approaches have enhanced the progress especially through use of lead farmers. Significant improvements are expected to be made in the third year of project implementation when the partnership with farm radio trust gets fully operationalized.
|  | % of male-headed HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Men: 37% | Men - 30%
|  | % of female-headed HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Women 36% | women-30%
| cross-cutting Indicators: Improved gender equality and women's empowerment among assisted populations | % of households where women, men or both women and men make decisions on the use/access of markets | Both 27% | Both - 40% | Good progress has been registered on accessibility and use of market advice. The PICSA, Gender household visioning, and SHEP approaches have enhanced the progress especially through use of lead farmers. Significant improvements are expected to be made in the third year of project implementation when the partnership with farm radio trust gets fully operationalized. Note that the baseline value was updated upwards after the baseline survey
|  |  | Women 36% | Women - 30%
|  |  | Men: 37% | Men-30%
|  | % of households where women, men or both women and men make decisions on insurance and climate services access | Both- 29% | Both - 40% | Good progress has been registered on accessibility and use of insurance and climate services. The PICSA and Gender household visioning approaches have enhanced the progress especially through use of lead farmers. Significant improvements are expected to be made in the third year of project implementation when the partnership with farm radio trust gets fully operationalized. Note that the baseline value was updated upwards after the baseline survey
|  |  | Women 34.1% | Women - 30%
|  |  | Men:37% | Men-30%
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
None
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The implementing entity continued to provide technical support to the project coordination team during the reporting period. Adequate support by the IEs Gender Protection focal person was provided during the annual workplan development and development of M&E tools. IE focal point on GP has also been handy during the reporting period to provide technical backstopping services on Gender and Age Marker Reporting. Additionally, the IE provided speak up sessions to the project coordination unit to promote reporting of any unethical issues at workplace including GBVs, sexual harassments etc.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes they have been effective. The arrangement under IE has been effective through the close collaboration with the Government personnel whereby joint technical expertise has been put to optimum use for effective planning, implementation and review of project activities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EE has ensured that the monitoring tools and project reporting templates are gender responsive. Furthermore, the EE integrates gender in implementation of the project activities. Use of grievance redress mechanisms by the project beneficiaries have also been encouraged during the reporting period. Furthermore, during the reporting period, the EE took part in the 16 days of gender activities which is done annually in December to promote issues of gender protection.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes it has been effective. There has been adequate gender integration in implementation of project activities as well as reporting. Adequate awareness through sensitizations has been made during the reporting period. Youth integration has been emphasized throughout. For instance, in provision of grants to farmer groups under the marketing component of the project, 20% youth integration was made mandatory in the farmer group composition
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A at the moment
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None |  | N/A
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress | Progress to Date | Rating
Implementing Entity: WFP | Outcome 1: Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity | Outcome 1 | Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity; |  | S
Outcome 2
Outcome 3
Outcome 7
| Outcome 2. Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | Outcome 2 | Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach; |  | S
Outcome 3
Outcome 5
Outcome 6
| Outcome 3: Strengthened Market access strategies and approaches for smallholder farmers | Outcome 6 | 3. Strengthened market access strategies and approaches for smallholder farmers. |  | S
|  |  |  | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Kathy Derore Programme Advisor WFP Malawi
| Email: | kathy.derore@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity | Outcome 1 | Improved access to insurance as a risk transfer mechanism for targeted farmers affected by climate change and food insecurity; |  | S
Outcome 2
Outcome 3
|  | Outcome 7 | Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach; |  | S
| Outcome 2. Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | Outcome 2
| Outcome 3: Strengthened Market access strategies and approaches for smallholder farmers | Outcome 6 | 3. Strengthened market access strategies and approaches for smallholder farmers. |  | S
|  |  |  | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Gilbert Kupunda, National Project Coordinator
| Email: | gkupunda@gmail.com
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
AF Outcomes
Outcome 1 | Reduced exposure to climate-related hazards and threats |  | Highly Satisfactory (HS)
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  | Satisfactory (S)
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Marginally Satisfactory (MS)
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | Marginally Unsatisfactory (MU)
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | Unsatisfactory (U)
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  | Highly Unsatisfactory (U)
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
In its capacity as an Implementing Entity, WFP continued to provide technical support towards implementation of the project in the reporting period. Below are the output specific activities that the IE has done during the reporting period.
Output 1.1 Targeted population groups covered by adequate risk reduction systems
WFP continued to lead discussions with the private sector to ensure active participation of the sector in implementation of crop insurance as a risk transfer mechanism. Several dialogue sessions were conducted with PULA the crop insurance product note designers to ensure continued improvements in the design of the insurance cover product and enhance its relevance to the targeted beneficiaries to foster its adoption. Some of the discussions with PULA cantered on improving on the time the pay-outs are provided to the beneficiaries after a cropping season ends due to the heavy delays which have been experienced previously. WFP also led the recruitment of PULA, the insurance product designers to provide insurance beneficiary registration processes covering both Tier 1 and Tier 2, where Tier 1 are the intended project beneficiaries. During the reporting period, more than 15% of Tier 2 beneficiaries were registered, which demonstrated enhanced understanding on the relevance crop insurance cover amongst the communities and hence increased demand.
A series of dialogue sessions have also been conducted with the Insurance Association of Malawi (IAM) to ensure that they play an active role, enhance their engagement with insurance beneficiaries and that they put in place adequate mechanisms on the ground for insurance premiums collections and pay-outs administration.
WFP also played very important roles in organization and administration of the 2020/21 insurance pay-outs.
Output 1.2 Awareness raised among farmers on weather index insurance
To enhance farmers awareness on the crop insurance cover, WFP as an implementing Entity:
- Facilitated the engagement of PULA to provide training of trainer’s sessions to district staff who further trained the extension workers and farmers to enhance their understanding of the crop insurance product note for the 2021/22 season and associated processes.
- Also facilitated the engagement of PULA to sensitize national stakeholders which included Government Ministries and Departments, Civil Society Organizations, and the Academia on the 2021/22 crop insurance product note design.
- Additionally, facilitated the engagement of PULA and IAM to develop sensitization materials covering both beneficiaries and non-beneficiaries to further enhance their understanding of the crop insurance concept and facilitate increased adoption of product note.
Output 1.3 Develop and test tools and systems for weather insurance (Strengthen national capacities and systems to provide weather index insurance working with private and public sectors)
WFP as an IE led a series of discussions with PULA and the Insurance Association of Malawi (IAM) on how to improve some of the processes in insurance implementation i.e., the crop cut experiments which inform pay-outs calculations to ensure that they are done in a consultative and transparent manner.
Output 1.4. Inclusion of insurance as risk transfer mechanisms in national agriculture programs and supported schemes
Besides initiating a national level stakeholder meeting on the insurance product note implemented by the project during the 2021/22 season, WFP also facilitated dialogue sessions with other national level stakeholders such as Ministry of Economic Planning and Development, World Bank, Disaster Risk Management to share experiences as they were also in the process of designing a crop insurance cover.
A total of 5 outputs contribute to outcome 2 and actual progress on each output is as outlined below:
Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation
During the reporting period, WFP provided technical support on how to ensure that value for money is maintained as the project implements irrigation development. About 20 solar powered irrigation pumps have been provided to the project to support irrigation development. Adequate technical backstopping services were also provided on implementation of soil and water conservation practices to ensure standards adherence.
Output 2.2 Promote climate resilient agriculture among farmers through extension service support
Technical backstopping services have been provided during training of trainer’s sessions for the extension workers. WFP has also participated in 3 field visits during the reporting period to check implementation progress on the ground, during which adequate feedback was provided to the project staff on areas on improvements.
Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops
WFP provided technical support on sensitisation materials and protocols which were developed to support crop diversification in the project impact areas. The project adopted seed multiplication in a pass-on arrangement to enhance crop diversification amongst the beneficiaries.
Output 2.4: Provide climate services to inform livelihood decision making amongst farmers
In its capacity as IE, WFP provided technical support in organisation of the 2021/22 Participatory Integrated Climate Services for Agriculture (PICSA) methodologies. This is one of the key approaches for improving farmers accessibility to weather and climate information through extension services to inform their livelihoods decision making such as seasonal planning and climate risk management.
WFP also organised a learning event on PICSA implementation in the country to foster government uptake and integration which is key for sustainability.
Output 2.5 Strengthened access to and use of weather/climate information for targeted communities to inform livelihood decision-making among farmers
WFP provided additional complementary rain gauges in the project impact areas to improve collection and presence of climate information in the project areas. Furthermore, WFP has allowed the project coordination unit to utilise the FLA which it has with Farm Radio Trust to climate information to the project beneficiaries at no additional costs.
Outcome 3 of the project has 5 outputs. Below are the output specific achievements:
Output 3.1. Strengthened financial capacities and market access opportunities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy)
Technical support was provided in the development of training materials for financial literacy farmer trainings and in the design of VSLs. Technical support has also been provided in the design and operationalisation of the farmer grants.
Output 3.2. Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced
WFP provided technical support towards the assessment of existing farmer organisations (FO) in the project sites as a key step towards linking project beneficiaries to operational FOs. The assessment also informed identification of sites where aggregation centres will be constructed by the project.
WFP also provided technical support in the design and implementation of the household visioning trainings to the farmers.
Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses
During the reporting period, WFP provided technical input in the design of the produce aggregation centres which will be constructed in selected project impact areas. Furthermore, WFP provided technical guidance on the warehouse/aggregation centres equipment to be procured.
Output 3.4. Market information provided to inform business planning and activities.
WFP provided technical support on smallholder farmers accessibility to both climate and market information. Through the farmer group approach, establishment of radio listening clubs and partnership with Farm Radio Trust, it is expected that farmers accessibility to both climate and market information will improve.
Output 3.5. Smallholder procurement promoted through government and private sector strategies and programmes
WFP participated in project national level dialogues which amongst others focused on enhancing smallholder farmers integration in procurements.
Overall, the rating is satisfactory because significant progress has been made across the project components. As an IE, the WFP Country office has been regularly providing technical support across the project components, including procurement, financial management, roll-out and scale-up of insurance and gender integration. This has ensured that the project remains on track. As part of project coordination, WFP has participated in Three National Technical Advisory Committee Meetings and two Project steering committee meetings. In addition, the WFP staff within the AF project benefited from an integrated resilience bootcamp at the end of July additional government district and AF staff will also benefit from an integrated resilience bootcamp targeting cooperating partners and government district staff.
Slow progress, however, has been noted on construction of aggregation centres and development of irrigation schemes which is currently at bidding stage. This has been the case due to the lengthy consultations which were required with the relevant government departments at both national and district levels, due to the continued impacts of COVID-19 with staff absences and office closures. In addition, to the impact of floodings induced by the tropical storms hitting in early 2022. It is expected that constructors will be on ground by September 2022.
Economic challenges, including fuel and forex being experienced in the country have also affected project execution as the cost of project activities implementation has gone up. During the reporting period, the country has experienced three times fuel prices upward adjustments of cumulatively more than 90% and a 25% currency devaluation. WFP and the AF team is currently reviewing what can be done to mitigate these financial challenges within the project budget.
In addition, WFP is continuing to follow-up with the AF to ensure that there is a clear plan to catch-up the backlog encountered with the aggregation centres and development of irrigation schemes.
Despite the changes in the economic situation of the country which rendered implementation of the activities expensive, the project remained on track and registered significant progress on the ground across the project components. Hence the overall rating is satisfactory. The project managed to register significant progress through utilisation of devolved structures at district and community levels in implementation of most of the project activities. Joint implementation of the project activities also helped to save on time and financial resources. More effort are however required to ensure fully operationalisation of the VSL concept and complete construction of aggregation centres and irrigation schemes in the subsequent year. Another notable factor which affected project results are cyclones which the country experienced during the 2021/22 rainy season as well as the late onset of rainfall. More than 30% of the project physical structures were affected by the cyclone and the late onset of rainfall affected crop yield. In most cases farmers had to plant more than once.
According to the project design, 4 outputs contribute to Outcome one and a number of activities have been implemented under the outputs as outlined below:
Output 1.1 Targeted population groups covered by adequate risk reduction systems
A total of 25,395 climate vulnerable community members (16,103F and 9,292M), representing 99.2% of the target total project target have benefitted from the project interventions in various ways under the insurance as a risk transfer mechanism project component. During the 2021/22 growing season, the project continued with the implementation of the Area Yield Index Insurance (AYII) product. Various stakeholders at both National, District and Community levels were engaged on the product note which was implemented in order to enhance understanding and foster adoption. about 15% of not project beneficiaries were registered during the reporting year as Tier 2 beneficiaries who are expected to cover on their own 100% of the insurance premium. As part of the seasonal monitoring, supplementary information of the seasonal outlook including pest infestation at Traditional Authority Level, Group Village Headman Level and Village Level were collected during the reporting period. Rain gauge recorders were also training in both new and old rainfall stations to enhance data available.
During the 2020/21 growing season, a total of 22,379 farmers out of the 24,998 insured (representing 90%) qualified for a total pay-out of MK 485,235,909.68 (MK323,725,914.00 for Batch 1; and K161,509,995.6 for Batch 2). The payouts helped the farmers to buy food stuff, assets like livestock and also procure farm inputs for the 2021/22 growing season. The payout amounts per farmer ranged from MK4,150 to MK79,850.00.
The 2021/22 payout report is however not yet released.
Output 1.2 Awareness raised among farmers on weather index insurance
The project continued to raise local understanding on climate change and engaged beneficiaries in climate change activities and adaptation strategies with subject matter Specialists, Frontline Workers, Area Stakeholder Panels (ASPs)/Area Development Committees (ADC), village Agricultural Committees ( VACs)/Village Development Committees (VDCs). About 43Females and 117Males Extension officers have cumulatively been trained on crop insurance as a risk transfer mechanism and more than 195,075 Males and 187,425 Females community members have been sensitised. During the reporting period, the insurance beneficiaries were still on 100% premium cover by the project and they completed a number of incentivised communal assets in soil and water conservation (like gully reclamation, check dams, afforestation, river-bank protection, vetiver nursery establishments and propagation) as a conditionality for insurance premium payment by the project. Further materials and inputs support were provided under the insurance component for implementation of incentivised activities such as Seeds for Seed Multiplication, Potato vines, vetiver grass, fruit tree seedlings and Banana suckers. The project continued with maintenance of the nurseries for vetiver grass, fruit seedlings, bananas and afforestation which were established in all impact areas in year 1 of project implementation. Additional nurseries have also been established in the year 2 project implementation. Additional seed multiplication sites were established during the reporting period.
Output 1.3 Develop and test tools and systems for weather insurance
During the reporting period, the project continued to update and analyse historical rainfall and agrometeorological data for the project impact areas. The project teams tried to work hand in hand with PULA during beneficiary registration for the 2021/22 insurance cover as well as during the crop cut experiments which inform pay-outs calculations. More collaboration with both PULA and Insurance Association of Malawi (IAM) will be expected during the 2022/23 season in order to address the challenges which were previously experienced and also ensure that sustainability mechanisms are adequately put in place for intervention continuity even after project finalization.
Output 1.4. Inclusion of insurance as risk transfer mechanisms in national agriculture programs and supported schemes
Two national level dialogue sessions were conducted on the AYII products which was implemented during the 2020/21 season and the 2021/22 season to enhance stakeholder understanding of the product. A national Launch of the 2020/21 season pay-outs was also held and presided over by the Minister for Agriculture, in Balaka District, which is the project impact area. Four high level project supervisory visits were conducted during the reporting period during which an interface with the insurance project beneficiaries was provided for the delegation to appreciate how the interventions is positively changing lives of the project beneficiaries.
A total of 5 outputs contribute to outcome 2 and actual progress on each output is as outlined below:
Output 2.1 Promote irrigation along with soil and water conservation practices through individual and group asset creation
During the reporting period the following key achievements have been made:
- Finalised identification of sites for irrigation development, sensitised communities about the development, acquired land lease for irrigation development and initiated procurement of the constructor to facilitate the irrigation development. Now, the bidding process is underway.
- Facilitated implementation of soil and water conservation activities such as gully reclamation, construction of deep trenches, swales, stone bands, maintenance of woodlots, orchards and nurseries established in year one of project implementation, and establishment of seed multiplication sites and additional nurseries for afforestation, vetiver grass and fruit seedlings; amongst others.
Output 2.2 Promote climate resilient agriculture among farmers through extension service support
In all impact areas, demonstration sites for soil and water conservation including conservation agriculture and complementary practices such as manure making continued to be implemented. To further enhance the capacity of soil and water conservation project beneficiaries, inputs especially afforestation and agroforestry seeds and seedlings were procured and distributed to soil and water conservation farmer groups. Manure making at household level has also been promoted during the reporting period as a key element to address the lack of organic matter in most of Malawi's soil (as established by AgriLab soil tests) . Refresher trainings were also provided to extension workers on implementation of climate resilient agricultural practices.
Output 2.3 Support crop diversification with a focus on drought tolerant and nutritious crops
Mounting of demonstration sires for crop diversification and establishment of seed multiplication sites was done during the reporting period on a pass-on arrangement. Farmer groups of project beneficiaries were also supported with assorted fruit seedlings (Apples, lemons, pawpaw’s, guavas, mangoes, oranges) within the catchment for growing at individual and group level.
Output 2.4: Provide climate services to inform livelihood decision making amongst farmers
A total of 31 Female Extension workers and 84 Male extension workers have been trained in Participatory Integrated Climate Services for Agriculture (PICSA) methodologies across the project impact areas, which is one of the key approaches for improving farmers accessibility to weather and climate information through extension services to inform their livelihoods decision making such as seasonal planning and climate risk management. The trained extension workers in turn trained 450 Female Lead Farmers and 1, 109 Male Lead Farmers who in turn reach out to not less than 17,000 smallholder farmers. The project team continued monitoring adoption of the PICSA approaches by the farmers to enhance their livelihood decision making and hence resilience capacity to climate change.
Nutrition campaigns including the establishment of back-yard gardens were also promoted and established. A clear integration with nutrition sensitive approaches like consumption of six food groups as per the government recommendations were established and promoted. Additionally, diversification of livelihoods and proper hygiene measures at HH level which are key elements of priority during a COVID-19 pandemic were also promoted.
Output 2.5 Strengthen national capacities and systems to provide these integrated climate risk management approaches
The project organised two national level PICSA engagements to enhance adoption of the approach by the various stakeholders for its sustainability. The Department of Climate Change and Meteorological services was also constantly engaged on production and dissemination of downscaled climate forecasts
Outcome 3 of the project has 4 outputs. Below is an outline of the key achievements made:
Output 3.1. Strengthened financial capacities and market access opportunities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy)
More than 23,000 project beneficiaries have been oriented on market orientation, financial literacy, and gender household visioning. Furthermore, more than about 95 farmer groups have been supported grants, reaching out to less than 2,000 farmer groups which will enhance the farmer capacity to do crop production for business as well as enterprise diversification into livestock production and apiculture production to widen their income base.
Output 3.2. Performance and outreach of farmer organizations/cooperatives strengthened, and capacity to engage in farming as a business enhanced
More than 95 farmer groups have been assisted to develop business plans, provided with trainings on Smallholder Horticulture Empowerment and Promotion (SHEP), an approach which realizes Market oriented Agriculture and converts farmers mind from "grow and sell" to "grow to sell".
Output 3.3. Targeted farmers supported to access storage and aggregating infrastructure for greater market access, including establishment of rural warehouses
The project finalised identification of sites for construction of aggregation centres and procurement processes of a contractor is under way. it is expected that the contractor will be on the site by September 2022. The project has also initiated procurement of equipment’s for the aggregation centres as provided for in the project document.
Output 3.4. Market information provided to inform business planning and activities.
Through the PICSA and SHEP approach, the project has enhanced smallholder farmer groups accessibility to both climate and market information.
Output 3.5. Smallholder procurement promoted through government and private sector strategies and programmes
The project coordination unit has been integrated in key coordination structures in the agriculture sector such as the National Agriculture Investment Plan (NAIP) working group which amongst others looks at how to promote smallholder farmers integration in procurements.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | : - Use of devolved government structures at all levels helped to foster timely implementation of project activities and ascertain sustainability of project interventions. : - Enhanced stakeholder collaboration including the private sector has also proved to be key in fostering intervention complementarities, improving intervention scale up and ascertaining intervention sustainability. : - Joint planning and supervision missions have also proved to be key in fostering stakeholders’ commitments towards implementation of project activities. Use of community participatory processes has also helped ensuring implementation of relevant activities to the community members, hence fostering ownership, commitment, and sustainability. : - Capacity building to the community members has been key for knowledge transfer, hence fostering project sustainability. Additionally, use of locally available resources in implementation of project interventions has also proved to be fundamental for project sustainability. : - The cyclones Anna and Gombe affected the project progress on the ground as some of the physical structures were affected. Community preparedness for such extreme climatic events as well as construction of quality standards structures is very key.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, some delays have been encountered especially on construction of aggregation centers and development of irrigation schemes due to the thorough stakeholder consultations which were required with the government stakeholders. However, procurement of the contractors for both the aggregation centers and irrigation schemes were now initiated and we are at bid evaluation stage
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | In order to improve the impact of grants to farmer groups, the grant which were meant to be provided to only 12 farmer groups were changed in terms of value per farmer group from USD 35,000 to USD3,000 per farmer group and the number of benefiting farmer groups was increased from 12 to 95. This was an alignment to similar support being offered by the government to the similarly farmer group category (small-medium scale farmers). The small-scale grants will enhance smallholder farmers capacity to do crop production for business and diversify their enterprises into other income generating activities like livestock production and apiculture, hence fostering rapid resilience capacity building.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, especially in implementation of soil and water conservation activities. As project activities were being implemented, environmental and social management plans were implemented alongside in order to ensure the identified risks were avoided or mitigated appropriately. Furthermore, for beneficiaries of irrigation schemes, aggregation centers and grants, it was a mandatory requirement for them plant a minimum of 20 trees around their homestead of which 10 should be fruit trees
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project coordination teams at both National and District levels with the gender focal points from both the government and WFP in order to ensure adequate integration of gender issues throughout the project implementation cycle. This has enabled equity considerations of all gender groups in implementation of project activities. The gender household visioning trainings which were provided to the project beneficiaries, has also enhanced the participation of both the men, women and their children in their household decision making processes. The vision setting has helped the project beneficiaries to be focused on their household plans to ensure attainment of their desired status.
Gender inclusion has been promoted also through deliberate setting of targeting criteria which promote gender inclusion. i.e., during provision of grants to farmer groups, each farmer group was requested to include 20% the youth and at least 40% women.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programmed to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmed?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
The AF project in line with the project document implemented a new baseline in the 2nd quarter of 2021, this has resulted in some changes in the values of the baselines from the original project document as indicated in the remarks column below.
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End | Remarks
Impact: Enhanced climate adaptation and food security of households through access to integrated climate risk management strategies | % of households in target communities who independently access insurance and climate services by gender of household head | 0 | 0% | 80% | 34% smallholder farmers across to the project impact areas however expressed interest to participate in crop insurance independently however they were not covered due to lack of insurance collection mechanism in the ipact areas
| % increase of government owned resilience and climate change adaptation activities | 0 | 30% | 50% | During the reporting year about 5 government owned resilience and climate change adaptation project have been introduced such as MWASIP, MRDP, Financial Access for Rural Markets Smallholder Enterprises (FARMSE), Social Support for Resilient Livelihood Project (SSRLP), TRADE. All these are livelihood enhancement projects.
| % of targeted communities where there is evidence of improved capacity to manage climate shocks and risks | 0 | 26% of the GVHs | 100%
| % of the population in targeted communities reporting benefits from an enhanced livelihood asset base by gender | 0 | 90.6% | 50% | 89.5% of the targeted female beneficiaries and 96.7% of the targeted male beneficiaries are reporting benefits from enhanced asset base
Outcome 1: Improved access to insurance and climate services as risk transfer and reduction mechanisms for targeted farmers affected by climate change and food insecurity | % of households in targeted communities with reduced risk related to extreme weather events by gender of household head | 7%F; 5%M | 27%F and 18%M | F: 65% | The baseline value was updated
M: 70%
| % of households belonging to vulnerable groups with access to weather index micro insurance by gender of household head | 0 | F: 18% | F: 30% | Accessibility by independent households (Tier 2 beneficiaries) is currently still being controlled because discussions on mechanisms for premium payment by independent households are still underway with the IAM and PULA.
|  | 0 | M: 11% | M:40%
| % of households not engaged in coping adverse mechanisms | 14% | 32% | 80% | Limited progress made due to effects of cyclones and late rainfall onset
Output 1.1 Targeted population groups covered by adequate risk reduction systems | Number of people insured (non-cash, partial cash payment and full cash payment by gender | 0 | 25,395(16,103F, 9,292M) | F: 10,240
M:15,360
| Total premiums paid, by access modality (insurance for assets or cash) | 0 | 457481 | 460800
| Total sum insured (IFA, partial cash payment and full cash payment) | 0 | 3580120 | 2477419
Output 1.2 Awareness raised among farmers on weather index insurance | Number of people trained on index design by gender | F: 0 | F: 43 | F: 15
|  | M: 0 | M: 117 | M: 20
| Number of people sensitized on insurance as a risk transfer mechanism by gender | F: 240 | M: 195,075 | M: 195,075 | The baseline value was updated
|  | M: 160 | F:187,425 | F:187,425
Output 1.3 Develop and test tools and systems for weather insurance insurance tools | Number of national coordination mechanisms supported | 0 | 3 | 3
| Number of staff trained on weather index insurance (disaggregated by public/private, national/local) by gender | F:2; M:8 | Public: 160; 43F and 117M | 50 | The baseline value was updated
Output 1.4. Inclusion of insurance as risk transfer mechanisms in national agriculture programs and supported schemes | Number of national agriculture programs and supported schemes with insurance packages as risk transfer mechanisms | 2 | 3 | 10 | The baseline value was updated
Outcome 2: Adopted climate-resilient agriculture practices among targeted farmers contributing to the integrated climate risk management approach | % of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses by gender | F: 41.1%; | 79.3% | F: 90% | The baseline value was updated
|  | M: 58.9% | 92.6% | M: 95%
| % of households using weather and climate information for decision-making on livelihoods and food security by gender and district | F: 60% | F: 75% | F: 75%
|  | M: 80% | M: 90% | M: 85%
| % of targeted households with border line to acceptable food consumption score by gender of household head and district | F: 90.9% | F: 95% | F: 75% | The baseline value was updated
|  | M: 94.2% | M: 97.9 | M: 80% | The baseline value was updated
Output2.1: Promote soil and water conservation practices through individual and group asset creation, including irrigation development | No. and type of risk reduction actions or strategies introduced at local level | 5 | 7 types, a)backyard gardening , b) Winter cropping in dambos; c) Insurance as a risk tranfer mechanism; d) Various soil and water conservation practices; e) Access to climate information; f) Crop Diversification; g) Cultivation of drought torelant crops (h) Distribution of grants | 5
| Number of assets built, restored or maintained by targeted households and communities, by type and unit of measure and a percentage of planned | 0 | 114 community woodlots established; 3 irrigation sites identififed and priotised for dvelopment; 497 vetiver nurseries established, 954.5 Ha under agroforestry | 36
| Percentage of households that are involved in irrigation farming, in addition to rain-fed agriculture | 9.6% | 34% | 15% | This indicator was updated based on self declaration annual monitoring data. A significant increase on the percentage of households involved in irrigation was has been reported (9.6% to 34%) due to increased sensitisation on the need for farmers to practice irrigation farmers as well as winter croping. The statistsic also include farmer who established small scale vegetable gardens in the dambo lands. The baseline value was updated
Output 2.2. Promote climate resilient agriculture among farmers through extension service support | % of HHs involved in CA (minimum tillage, crop diversity, retention of crop residues) by gender of household head | F: 8% | F:50.7% | F: 30% | The baseline value was updated
|  | M: 7% | M:49.0% | M: 35%
| Ha of land under CA | 335.72 | 2390 | 3400 | The baseline value was updated
| Ha applied with manure | 8000 | 8184 | 17000 | The baseline value was updated
Output 2.3. Support crop diversification with a focus on drought tolerant and nutritious crops | Number of crops grown by HHs (by type) for crop diversification | 2 | 7 (Maize, Cassava, Groundnuts, sweet potatoes, pigeon peas, banana and cow peas) | 4
| Number of HH accessing improved fruit seedlings, leguminous trees and fodder tree seed by gender of household head | F: 21,590 (Leguminous Trees); F: 9,010 (fodder trees); 2,550 (improved Fruits) | F: 55,021 (Leguminous trees); F9,378 (Fodder trees); 11, 600 (improved fruits) | F: 40,000 | The baseline value was updated
|  | M: 23,800 (Leguminous trees); M:11,815 (Fodder trees); 3,400 (Improved fruits) | M: 29,980 (Leguminous trees); M:12,615 (Fodder trees); 14,600 (Improved fruits) | M: 45,000 | The baseline value was updated
Output 2.4. Strengthened access to weather/climate information for targeted communities to inform livelihood decision-making among farmers | Number of main delivery channels used by households to receive information for the climate agricultural services (i.e. in-person intermediaries, radio advisories, and SMS) by gender | 3F; 3M | 3F; 3M | 3F & 3M | The baseline value was updated
2.5. Strengthened national capacities and systems to provide integrated climate risk management approaches | Number of households within the targeted communities that receive climate services, disaggregated by source (i.e. farm intermediaries, radio advisories, and SMS), by gender, vulnerable groups and district | Extension Officer: 19,405F & 8,199M ; Radio: 35,804F & 25,418M; SMS: 1,094F & 1,640M | Extension Officer: 45,280F, 31,280M & ; Radio: 36,800F & 26,989M; SMS: 1,094F & 1,640M | Extension Officer: 51,000F &34,000M; Radio: 51,000F & 34,000M; SMS: 51,000F & 34,000M | The baseline value was updated. Note that radio listening clubs have just been established hence no significant imporvement registered on use of radios to access climate information.
| Number of intermediaries trained in how to access, interpret and communicate climate information to households, to support household decision-making related to food security, livelihoods, and DRR – disaggregated per gender and district | 10F; 44M | Extension Officers F:31 M:84 Lead Farmers F: 650 M:1109 | F:80 M: 100 | The baseline value was updated
2.6 Strengthened national capacities and systems to provide integrated climate risk management approaches | Number of national coordination mechanisms supported | 0 | 3 | 5
| Number of communities extension workers and national agricultural content development committee members engaged in capacity strengthening initiatives to enhance national food security and nutrition stakeholder capacities | 0 | F:38 M:95 | 40F; 64M
| Number of capacity building trainings with national/local entities | 0 | 10 | 20
Outcome 3: Strengthened market access strategies and approaches for smallholder farmers | % of households having more secure (increased) access to livelihood assets by gender of household head | F: 9.2% | F:40.1% | F:75% | The baseline value was updated
|  | M: 9.9% | M: 45.2% | M: 80%
| % of targeted population with sustained climate-resilient livelihoods by gender of household head | F: 10% | F:40.1% | F:75% | The baseline value was updated
|  | M: 15% | M:45.2% | M: 80%
| % change in household income disaggregated by activity type and gender of household head | 0 | 5% (both F & M) | F:25% | Significant progress is expected to be registered in the third year of project implmenetation following provision of farmer group grants, increased VSLs as well as enhance linkages to markets.
M: 30%
| % of targeted smallholders selling through WFP-supported farmer aggregation systems | 0% | 0% (construction of aggregation centres is yet to be finailised) | 10% | The baseline value was updated
| % change in HH savings (by type: individual, group, formal, informal) | 0 | 18.76% | 30% | Due to the VSL concept, gender household visioning trainings and financial literacy trainings
| % of HHs accessing markets to sell surplus | 15% | 25% | 50% | The baseline value was updated. Limited progress made due to the effects of cyclones and late rainfall onset which affected yield
| % of HHs within the targeted communities using market advice to make livelihood related decisions (by type) | Both 27% | Both 37.6% | Both - 40% | The baseline value was updated
|  | Women 36% | Women 31% | Women - 30%
|  | Men: 37% | Men: 26.5% | Men-30%
| % change in HH participating in FOs | 22.8% | 87% | 95% | The baseline value was updated
Output 3.1. Strengthened financial capacities to enhance investment in climate-resilience agriculture (including saving, credit, and financial literacy) | No. and type of adaptive financial capacities (Insurance, saving, credit, and financial literacy) created in support of individual or community-livelihood strategies as a percentage of plan | 0 | 70% (Insurance, VSL, Financial Literacy, Grants, Gender household visioning, SHEP) | 75%
| Value of HH savings (MK) | F: 5,692.58 | F: 15,701 & M: 90,126 | 80000 | The baseline value was updated
|  | M: 20,656.97 |  | 80000 | The baseline value was updated
| Number of HH accessing credit (by type) | 19,550 households | 44,550 households | 23600 | The baseline value was updated
| Value of HH credit accessed (formal) (MK) | K22,079.56 | K35,477.56 | 80000 | The baseline value was updated. Grants to farmer groups have not been captured in this average credit value because the farmers will not be given direct cash, but rather materials.
Output 3.2. Strengthen performance and outreach of farmer organizations/cooperatives and enhance their capacity to engage in farming as a business | Quantity of food purchased locally from pro-smallholder aggregation systems (in mt) | 0 | 0 | 2000
Output 3.3. Provider market information to inform business planning and activities | Number of farmers’ organizations trained in market access and post-harvest handling skills | 3 | 245 farmer committees trained in market access and post-harvest losses at Group Village Headman level | 25
| Number of participants receiving market advice (by type) | 3,918F & 1,448M | 8,637.6F & 5,758.4M, government minimum prices and places of commodity and market availability etc | 23,600 (14,160F & 9,440) | The baseline value was updated
3.4. Promoted smallholder procurement through government/private sector strategies and programs | Number of smallholder farmers supported | 0 | 6,248F & 2,982M | 23,600 (14,160F & 9,440)
3.5 Promote public pro-small holder procurement | Number of pro-smallholder policies developed | 0 | 0 | 1
Gender Crosscutting: Improved gender equality and women;s empowerment among assisted populations | % of households where women, men or both women and men make decisions on the use/access of markets | Both 27% | Both 37.6% | Both - 40% | The baseline value was updated
|  | Women 36% | Women 31% | Women - 30%
|  | Men: 37% | Men: 26.5% | Men-30%
| % of households where women, men or both women and men make decisions on insurance and climate services access | Both- 29% | Both- 47.6% | Both - 40% | The baseline value was updated
|  | Women 34.1% | Women 34.1% | Women - 30%
|  | Men:37% | Men:21.2% | Men-30%

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | World Food programme
Type of implementing entity | MIE
Country | Malawi
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 382500 | 382500 | 0 | Total | 399500 | 382500 | 17000 | Total |  |  |  | Total
|  | % of female beneficiaries | 60% | 60% | 0% | % of female beneficiaries | 80% | 60% | 20% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 20% | 20% | 0% | % of Youth beneficiaries | 40% | 20% | 20% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 7 | Drought | 2: Partially effective | Total | 7 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 5% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 96 | Multi-sector | 3: Medium capacity | Total | 180 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 96 | 20% | Public |  | 180 | 40%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Agriculture | 2: Low capacity | Public | National | Agriculture | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Agriculture | 2: Low capacity | 2 | National | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Agriculture |  | 90 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 4250 | 5% | 3: Partially aware |  | 85000 | 90% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 |  |  |  | 104 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 |  |  |  | 12 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 18000 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 34000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 18000 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 34000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% |  |  | 65000 | 75% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agriculture | 65000 | 75% | From 40% to 50% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Agriculture | Soil water conservation | 10 | Physical capital | Agriculture | Soil water conservation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 85000 | Agricultural-related |  | 365
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | National | Public policy | 2 | Agriculture | National | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Community | Innovation rolled out |  | Food Security | Community | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices |  | 7 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  |  | 5 | Innovative practice |  | 4: Effective
Note on I94: Geoffrey KampupuZiba: Assuming each hh rehabilitates about 0.4 of a ha, giving us 34,000ha