## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 20 October 2021 - 19 October 2022
| Project Title: | Increasing the resilience of both displaced persons and host communities to climate change-related water challenges in Jordan and Lebanon
host communities to climate change-related water challenges
| Project Summary: | This regional project will support the development of a comprehensive response framework to climate change combined with the Syrian crisis especially in an urban context. The project’s main aim is achieved through identifying effective approaches and best practices to build urban resilience, focused on actions that address water challenges and that benefit both DPs and host communities especially women and youth. The framework is not only developed for the project’s target areas, but also for areas with similar contexts. The project will focus on supporting a sustainable water management approach, by reducing water use of unsustainable sources by means of reducing water losses and increasing water use efficiency and by increasing water supply of sustainable sources via supporting water harvesting and promoting the use of non-conventional sustainable water resources. The approach also includes promoting innovative, low cost and sustainable techniques (more information on these techniques is available in the full/final project’s proposal) and establishing urban-rural linkages as water challenges also impact agriculture and livelihood security. The project identifies DPs as the most vulnerable group due to socio-economic challenges that could affect affordability to access water in the target areas. However, the project also recognizes increased tension between DPs and host communities and the needs of poor Lebanese and Jordanians. To that end, the overall aim of the said regional project is to better respond to climate change impacts and vulnerabilities in the context of the Syrian crisis in Lebanon and Jordan. This will be done by UN-Habitat implementing the following components of the regional project: 1. Component 1: increasing the resilience of municipal governments through managing urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from Displaces Persons (DPs) migration; 2. Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems 3. Component 3: Demonstrating what concrete adaptation measures respond to the needs of both DPs and host communities through increasing the adaptive capacity of the water sector via expanding unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context; and 4. Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project knowledge management (KM) and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration)
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AF00000166 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jordan, Lebanon | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mafraq and Irbid sub-districts in Jordan, Zahle district in Lebanon | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2021-07-14
IE-AFB Agreement Signature Date: |  | 2021-07-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-10-20 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2025-10-19
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report submitted in October 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
Regional Project Coordinator |  |  | Dominica
| Name: | Hussien Muhsen | Dominican Republic
| Email: | hussien.muhsen@un.org | Ecuador
| Date: | 2022-08-01 | Egypt
National Project Coordinator/Jordan
| Name: | Jawad Dukhgan
| Email: | jawad.dukhgan@un.org
| Date: | 2022-06-19
National Project Coordinator/Lebanon
| Name: | Layal Abi Esber
| Email: | layal.abiesber@un.org
| Date: | 2022-03-15
Government(s) DA [if regional project/program add rows as necessary]
|  | Ministry of Environment /Jordan | El Salvador
| Name: | HE. Dr. Muawieh Radaideh
| Email: | ministeroffice@moenv.gov.jo
Date:
Ministry of Environment /Lebanon
| Name: | H.E Dr. Nasser Yassine | Equatoral Guinea
| Email: | ny05@aub.edu.lb | Eritrea
| Date: |  | Estonia
| Implementing Entity | UN Habitat | Ethiopia
| Name: | Yasmine Mostafa | Fiji
| Email: | yasmine.mostafa@un.org | Finland
| Date: |  | France
| Executing Entity | UN ESCWA
| Name: | Sara Hess
| Email: | sara.hess@cepal.org
Date:
| Executing Agency | JOHUD | Gambia
| Name: | Aseel Almukhaimer | Georgia
| Email: | aseel.m@johud.org.jo | Germany
| Date: |  | Ghana
| Executing Agency | HFDJB | Greece
| Name: | Abdallah Alsardi | Grenada
| Email: | Abdallah.alsardi@badiafund.gov.jo | Guatemala
| Date: |  | Guinea
| Executing Agency | PRI | Guinea Bissau
| Name: | Geoff Lawton | Guyana
| Email: | Geoff@permaculture.org.au | Haiti
| Date: |  | Honduras
Hungary
| Executing Agency | Yarmouk Water Company | Iceland
| Name: | Mahmoud Obiedat | India
| Email: | obiedat2008@yahoo.com | Indonesia
| Date: |  | Iran (Islamic Republic of)
| Executing Agency | UNICEF/Jordan | Iraq
| Name: | Tanya Chapuisat | Ireland
| Email: | tchapuisat@unicef.org | Israel
| Date: |  | Italy
| Executing Agency | UNICEF/Lebanon | Jamaica
| Name: | Paul Edwards | Japan
| Email: | pedwards@unicef.org | Jordan
| Date: |  | Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 10/20/2021 | [5 empty] | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 19/10/2022 | 414881 |  |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The first agreement was signed with UN ESCWA on 25/10/2022 and the first disbursement amount 164,957.20 USD Regional Technical Office (RTO) mobilization was initiated and the cost 60,449.4 USD and it is part of the executing cost of the project total 149,864 USD Due to COVID-19 and the disturbance of the global supply chain, overall expenditure was below the anticipated amount, which led for two project amendments submissions on February 21st and August 10th of 2022. The first amendment was due to the financial crisis in Lebanon, which made it unfeasible for the two public entities to perform any activities as EEs. The project team had to change the EE to UNICEF, and for the same reason, UN-Habitat had to hire the technical field team –referred to as the Regional Technical Office in the project proposal –who was supposed to be recruited by LARI. The second amendment was due to COVID-19 and its direct impact on the prices of activities implementation. Some items and their related costs under outputs 2.8 and 3.8 have been revised to reflect these changes. The changes did not affect the budget allocated for both outputs and the project's overall budget, which remains the same as in the original project document. The project team is ensuring that spending for the next reporting year will makeover delays due to amendments. Where all the contractual agreements with EEs have budgets that entail this delay and accommodate for it with more spending in PPR year two period. |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | NA |  |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Territorial planning and development strategy / guidelines at district level with climate change and gender mainstreamed (Lebanon) | 48000
| Output 1.2 Urban master plans at municipal level with climate change and gender mainstreamed (Lebanon) | 10542.4
| Output 1.3 Urban master plans at municipal level with climate change and gender mainstreamed (Jordan) | 0
| Output 2.1 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rain Water Harvesting (RWH) in Lebanon | 0
| Output 2.2 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rain Water Harvesting (RWH) in Jordan | 0
| Output 2.3 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.3: Grey Water Treatment and Reuse (GWTR) in Jordan | 0
| Output 2.4 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4: Efficient treatment and reuse of wastewater,from Zahle WWTP, in Lebanon | 0
| Output 2.5 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.5: Efficient treatment and reuse of wastewater in Jordan | 0
| Output 2.6 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for water-use-efficient irrigation of treated wastewater for fruit trees in Lebanon from Zahle WWTP, Lebanon | 0
| Output 2.7.1 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7:Water-use Efficient irrigation of treated wastewater from Maerad and Al Kaider WWTPs in Jordan | 0
| Output 2.7.2 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7:Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan | 0
| Output 2.8 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.8; permaculture demonstration | 0
| Output 2.9 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.9; permaculture demonstration | 1907
| Output 3.1 Rooftop Rain Water Harvesting RWH) in Lebanon + show room | 0
| Output 3.2 Rooftop Rain Water Harvesting (RWH) in Jordan + show room | 0
| Output 3.3 Grey Water Treatment and Reuse (GWTR) in Jordan | 0
| Output 3.4 Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon | 0
| Output 3.5 Efficient treatment and reuse of wastewater in Jordan | 0
| Output 3.7.1 Water-use Efficient irrigation of treated wastewater from Maerad and Alkaider WWTPs in Jordan | 0
| Output 3.7.2 Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan | 0
| Output 3.8 Permaculture demonstration - closed loop water system in Jordan | 0
| Output 3.9 Permaculture demonstration - closed loop water system in Lebanon | 0
| Output 4.1 Regional / international KM with focus on project lessons sharing and replication (incl. international seminars and regional platforms & policy dialogue) 4.1 - Travel to participate in international seminars with steering committee members (WUF Participation) | 45000 |  |  | 13036
| Output 4.2 Jordan and Lebanon KM with focus on project progress, best practices and lessons learned shared + capacity building - Contractual Services for Steering Committee Meetings - General Operating and Other Direct Costs - associated with steering committee meetings | 110000
| Output 4.3.Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | 0
| Output 4.4.Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | 0
| PROJECT EXECUTION COSTS Regional Project coordination | 18850.64
| National Project execution | 106776.93
| Travel Related to Execution | 12429.24
| Operations | 11807.57
| Terminal evaluation | 0 | 149864.38
| Project Cycle Management Costs :UN-H ROAS Project Support Costs: AF and UN-H policies compliance Progress / evaluation Travel | 3929.72 | 3929.72 ROAS
| Project Cycle Management Costs : UN-H ROAS overall project supervision, incl. AF and UN-H policies (esp ESP and GP) and regulations compliance and regional admin, coordination and travel | 22955.89
| Project Cycle Management Costs: UN-H HQ Overall project supervision, incl .compliance to UN-H policies (gender, human rights, climate change, etc.) | 22681.76
| TOTAL | 414881.15 |  |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE | [5 empty] | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Territorial planning and development strategy / guidelines at district level with climate change and gender mainstreamed (Lebanon) | 262113 | October 30th 2023
| Output 1.2 Urban master plans at municipal level with climate change and gender mainstreamed in Lebanon |  |  | 7896534.22
| Output 1.3 Urban master plans at municipal level with climate change and gender mainstreamed in Jordan | 92400 | October 1st 2023
| Output 2.1 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1 | 88450 | October 19th 2023
| Output 2.2 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.2 | 74700 | August 30th 2023
| Output 2.3 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.3 | 136831.6 | September 30th 2023
| Output 2.4 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4 | 101200 | October 19th 2023
| Output 2.5 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.5 | 16000 | September 30th 2023
| Output 2.6 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6 | 57300 | October 19th 2023
| Output 2.7.1 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7 | 102800 | August 30th 2023
| Output 2.7.2 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7 | 71400 | August 30th 2023
| Output 2.8 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.8 | 179200 | September 30th 2023
| Output 2.9 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.9 | 246707 | September 30th 2023
| Output 3.1 Rooftop Rain Water Harvesting RWH) in Lebanon + show room | 208888 | October 19th 2023
| Output 3.2 Rooftop Rain Water Harvesting (RWH) in Jordan + show room | 426410 | August 30th 2023
| Output 3.3 Grey Water Treatment and Reuse (GWTR) in Jordan | 521378 | September 30th 2023
| Output 3.4 Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon | 2246556 | October 19th 2023
| Output 3.5 Efficient treatment and reuse of wastewater in Jordan | 839466 | September 30th 2023
| Output 3.7.1 Water-use Efficient irrigation of treated wastewater from Maerad and Alkaider WWTPs in Jordan | 399200 | August 30th 2023
| Output 3.7.2 Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan | 338360 | August 30th 2023
| Output 3.8 Permaculture demonstration - closed loop water system in Jordan | 261599 | September 30th 2023
| Output 3.9 Permaculture demonstration - closed loop water system in Lebanon | 544055 | October 19th 2023
| Output 4.1. Regional / international KM with focus on project lessons sharing and replication | 35000 | October 31st 2023
| Output 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned shared + capacity building | 105280 | October 31st 2023 | 300618
| Output 4.3.Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | 65000 | October 31st 2023
| Output 4.4.Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | 0
| PROJECT EXECUTION COSTS Regional Project coordination | 113149.36 | October 31st 2023 | 343030
| National Project execution | 338423.07 | October 31st 2023
| Travel Related to Execution | 6475.76 | October 31st 2024
| Operations | 18192.43 | October 31st 2025
| Terminal evaluation | 0 | October 31st 2026
| Project Cycle Management Costs :UN-H ROAS Project Support Costs: AF and UN-H policies compliance Progress / evaluation Travel | 24121 | October 31st 2023 | 24120.65
| Project Cycle Management Costs : UN-H ROAS overall project supervision, incl. AF and UN-H policies (esp ESP and GP) and regulations compliance and regional admin, coordination and travel | 281958 | October 19th 2023 | 78039.56
| Project Cycle Management Costs: UN-H HQ Overall project supervision, incl .compliance to UN-H policies (gender, human rights, climate change, etc.) | 543432.68 | October 19th 2023
| TOTAL | 8746045.9 |  |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[10 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[10 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[10 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[10 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Delay of project start-up because critical staff is not in place and / or lengthy contracting process, incl. negotiations with execution entities | Low | 1.1 UN-Habitat appointed critical staff at UN-H ROAS to start the process required to start the project, incl. putting project staff in place and preparing the inception workshop immediately after signed project agreement between UN-Habitat and the AF; 1.2 All execution entities have been identified and proposed project activities and budgets have already been agreed upon. 1.3. UN-habitat commits to organise the inception workshop within three months of the signed project agreement between UN-Habitat the AF
2. Loss of government support (at ministerial and municipal level) for the project and activities because of elections and related functions of the project steering committee, which may result in lack of prioritization of AF project activities or different pace of execution of activities in Jordan and Lebanon | Low | 2.1 National Project Steering Committees (PSCs) have already been formed during the project preparation phase and these have approved proposed project activities and budgets, etc. This shows a participatory and inclusive project design process took place with ownership of the project as a result.
3. A lack of coordination between and within national government Ministries and Departments and municipalities | Low | 3.1 Regional and National PSCs are to ensure coordination. Representatives from the target municipalities are members of both regional and national PSC. 3.2 Roles and responsibilities related to project implementation of PSC members, also for operation, maintenance and sustainability of activities, have already been identified and focal points within the ministries and municipalities were appointed through an official letters. 3.3 An MoU signed between UN-H, MoLA , Irbid Municipality, and Mafraq Municipality to ensure high coordnation.
4. Capacity constraints of executing entities, local institutions, communities and the private sector may limit the effective implementation of interventions | Low | 4.1 The project has a strong capacity building and training component (component 2), designed to operate, maintain, sustain and replicate project activities, esp. at the community level 4.2 UN-Habitat have dedicated project staff with expertise in spatial / urban planning, climate change, community organization and technical design, M&E and safeguards to ensure quality control from UN-Habitat side 4.3 Regular meetings conducted by team members and Ministries officials to coordinate and ensure work synergies
5. Communities may not adopt activities during or after the AF project, including infrastructure maintenance | low | 5.1 A strong participatory approach at the community level is used (component 2) during project implementation and included in theAoCs and UN to UN agreements with EEs to ensure ownership and support of communities to the realised interventions in the targeted project areas. UN-Habitat works with UNICEF and NGOs partners already well established in the target area, to build on relations already established. 5.2 Capacity building and training of communities was includided in the AoCs and UN to UN agreements with EEs in the project to be undertake awareness raising and understanding of the benefits of the activities, including infrastructure operation and maintenance (component 2).
6. Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity or needed capacity | Low | 6.1 Financial management arrangements have been defined during project preparation, including identification of all executing entities, which already agreed on the activities and budgets 6.2 UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, ensure documentation of clearly defined roles and responsibilities for management, internal auditors, the governing body, other personnel and demonstrates proof of payment / disbursement; In line with AF and UN-Habitat policies, audits should take place annually and / or for each contract of USD 500k. 6.3 Activity specific procurement managed by the executing entities as agreed through standard Agreements of Cooperation (with relevant conditions, incl. evidence of recognised procurement policies and procedures and specific terms and conditions for timely disbursement of funds for project activities while at the same time ensure provisions on good financial management, hence minimizing the risk of fund mismanagement or corruption). The RPMU has a certifying role (for key procurements / expenditures).
7. Inflation and instability of the national currency leading to budget issues and increased prices for infrastructure delivery | Medium | 7.1 Amendment of project initiated and approved to take into account inflation 7.2 All budgets are in US$ 7.3 Clauses included in all contract, incl. with private sector, that they can’t increase the costs during the project duration.
8. (9) Political instability and COVID-19 in the target localities inhibits movement and access to target areas | Low | 9.1 The selected project sites are labelled as being safe. However, UN-habitat with the UN security unit and in line with COVID-19 procedures kept monitoring the safty of the sites and let field work proceed accordingly 9.2 Execution entities were asked to have permanent field staff at project sites, recuing the need to travel
9. (10) Poor weather conditions (especially in winter) affect implementation of activities | Low | 10.1 UN-habitat and the proposed execution entities have developed their work plan according to expected weather conditions and the majority of activities should be able to be carried out despite severe weather conditions as they are inside closed areas. No adaptation of plans were required within the reporting period
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
10.(8) The discrepancy between the official and black-market exchange rates of the US dollar might jeopardize the engagement of public entities as executing partners | Medium | 8.1. All executing entities Identified can receive dollars without being impacted by negative exchange rates
11. Possible delays in permitting process for the project activities in Lebanon due to the financial crisis affecting functioning of all Government services | Medium | 11.1 Regular follow ups and meetings were conducted with involved authorities to ensure swift permit application and review process | Application for EIA permit initiated Permitting / approvals needed during construction of treated wastewater storage and conveying system not yet started awaiting the finalization of the detailed design
12. Financial crisis in Lebanon making it impossible to make transfers to government agencies in Fresh USD | Medium | 12.1 Amendment of project initiated and approved to change executing entities; originally involved entities would continue to be involved as beneficiaries. | The inflation did not impact the project due to mitigation steps taken
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Pollution. On-plant accidental spills, overflows, seepages and discharges of wastewater treatment may contaminate soil, groundwater or surface water. Spills, overflows and seepages are at plant level and can be contained there. | Carry out regular inspections and routine tests to avoid spills, overflows, seepages and discharge of low-quality water; include detailed risks mitigation measures identified in country-specific ESIA-ESMP reports in construction, operation and maintenance plans | Monitoring of wastewater handling and possible spills, overflows and seepages. Construction and O & M report addressing above. | Check standards for water quality, treatment and construction. | Jordan: the Agreements of Cooperation prepared with Yarmouk water company, JOHUD, HFDJB have the EIA as a conditional requirment before implementation and have a monitoring of water quality as an O&M procedure Lebanon: an EIA consultant has been contracted to implement an EIA study for the wastewater reuse project at Zahle; the mitigation plan will include automatic bypass procedures for various scenarios including possible overflows beyond the design capacity of the storage reservoir; excess treated wastewater would be discharged back to the river | Possible on-plant accidental spills, overflows, seepages due to failure of automatic bypass sytem | Include in the design a manual emergency bypass possiblity and a communication channel to notify relevant staff at the plant regarding the emergency. Fix the malfunctioning equipment. Undertake soil and water quality tests (BOD, COD, TDS, heavy metals) in spill areas and decide on remedial actions accordingly.
13 – Public health |  |  | Yes. Safe water: water quality from RWH and GWTR systems may not comply to standards Jordan: 64 RWH and 40 GWRT systems with following direct beneficiaries: 42,284 Lebanon: 10 RWH systems with following direct beneficiaries: 16,360 | Rainwater collected will be treated using sand and carbon filter, a micro filter, and chlorine. This will ensure water quality compliance. Note that tap water is not used for drinking or cooking. Water and roofs will be regularly monitored, especially at the start of the rainy season; Filter will be changed annually, as per supplier recommendation. The chlorine tank should not be empty so there will be no pumping of air that impacts water quality; Students and building staff will be made aware (through curriculum) of requirements of using water + involved in operation and maintenance; Remote monitoring systems will be installed | Water quality monitoring complying to standards; Awareness raising campaign; O & M (training) reports with attendance lists and photos; checking of filters and chlorine tank | Water quality check (compliance to tap water quality standards) Check filters and chlorine tank | Jordan: the Agreements of Cooperation prepared with JOHUD, and the UN to UN agreement with UNICEF include Operation and maintainance plans with periodic water quality check within the timeframe of the project Lebanon: the UN to UN agreement with UNICEF include Operation and maintainance plans with periodic water quality check within the timeframe of the project; an ESAP was developed for the rainwater harvesting projects | Possible system malfunction could cause odors and water contamination | Discharge of collected water in a safe way through tankers
|  |  | Yes. Safe water: treated wastewater used for irrigation may not comply to quality standards / unmonitored irrigation water may compromise safety of crops; also covid-19 may be detected in water entering the treatment facility Jordan: Extra from Maerad WWTP: storage tank with a capacity of 2,000m3 Exra from Al Kaider: Storage tank with a 500m3 Extra from Mafraq: 9,000 m3 Lebanon: From Zahle WWTP: 20,000 m3 | Although the project intervention aims to increase the quality of water for irrigation, regular testing of water quality is required based on monitoring requirements included in EIA / ESMP studies and irrigation will only begin after testing; Farmers will be made aware of requirements for use + involved in operation and maintenance; | Monitoring parameters for treated effluent would be based on monitoring requirements specified in EIA / ESMP studies. | National standards if any and WHO / FAO guidelines when needed | Jordan: the Agreements of Cooperation prepared with Yarmounk water company has water quality monitoring of the effluent from the WWTPs (Me'rad, Ikeider,and Mafraq) as a requirment during the implementation of the project Lebanon: the UN to UN agreement with UNICEF includes water quality monitoring of the effluent from the Zahle WWTP; monitoring would be based on EIA recommendations; EIA recommendations will also include the need for an automatic bypass following electricity failure events | Possible fluctuations in treated wastewater quality due to shock loads; possible malfunction in automatic bypass system | Include in the design a manual emergency bypass possiblity and a communication channel to notify relevant staff at the plant regarding the emergency. Fix the malfunctioning equipment. Undertake soil and water quality tests (BOD, COD, TDS, heavy metals) in spill areas and decide on remedial actions accordingly.
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, a social risk is anticipated: the economic crises and deteriorating economic conditions in Lebanon are expected to exacerbate sentiments of hostility towards Syrian refugees in Lebanon
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | In order to mitigate this social possible risk, UN Habitat together with UN ESCWA will develop a communication plan with key messages that are sensitive to the situation in Lebanon and do not cause any harm to Syrian refugees or host communities
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | ESP safeguards were included in the Agreements of Cooperation and UN to UN agreements with Executing Entities
Have the implementation arrangements been effective during the reporting period? |  | Activities have not yet started
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Implementation has not yet started. Nevertheless, the project document including the ESMP, which is a binding and integral part of all agreements with Executing Entities includes a clear indication of the need to implement the ESP of the Adaptation Fund. UN-Habitat, as the IE, monitors the compliance of the EE with the policies to make sure that (for example) women are actively participating in meetings and events and that gender disaggregated data is collected UNICEF in Lebanon: an Environmental Impact Assessment study is currently being developed for output 3.4 in Lebanon. The latter study will mainstream all the requirements of the Adaptation Fund ESP in the proposed enviornmental and social safeguards' measures. The associated Environmental and Social Management plan will be part of the tendering documents and will be implemented by any contractor involved on output 3.4. UN ESCWA: all ESP safeguards were assessed and monitored during implementation according to the UN to UN agreement signed by assigning a focal point for ESP in UN ESCWA that report to the UNH. UNICEF in Jordan: Implementation has not yet started. However, all ESP safegaurds will be assessed during implementation according to the UN to UN agreement drafted to be signed JOHUD: Implementation has not yet started. However, all ESP safegaurds will be assessed during implementation according to the agreement of cooperation drafted to be signed HFDJB: Implementation has not yet started. However, all ESP safegaurds will be assessed during implementation according to the agreement of cooperation drafted to be signed PRI: Implementation has not yet started. However, all ESP safegaurds will be assessed during implementation according to the agreement of cooperation drafted to be signed YWC: Implementation has not yet started. However, all ESP safegaurds will be assessed during implementation according to the agreement of cooperation drafted to be signed
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Activities have not yet started
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  |  |  | The concept of the Grievances mechanism was prepared already by the project team and will be implemented through each EE and considers the community accessiblilty, transparency, fairness and effective means of communication.The Grievence mechanism also considers the special needs of different groups as well as gender considerations and potential environmental and social risks, especially human rights (as shown on posters). A combination of mailboxes (at community / building level) and telephoning options offer an immediate way for employees and people affected by the project to safely express their concerns.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Limited participation women and youth and roles are not specified in plans | Output 1.1, 1.2, 1.3 | % women and youth participation in assessment and planning Women and youth considerations in plans | 0 | Women: 40 % Youth: 15 % Specific mentioning | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Women and youth should get a chance to be involved with RWH and GWTR activities | Output 2.1, 2.2, 2.3 | Focal point identified % youth participating in awareness campaigns | 0 | 1 per building Youth: 30 % | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Farmers and workers, incl. Syrians and youth are targeted | Output 2.6, 2.7 | % Syrians and youth participation | 0 | Syrian: 15 % Youth: 30 % | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Students are targeted of which most female | Output 2.8 | % female students | 0 | Female: 60 % | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Students are targeted of which most female | Output 2.9 | % female students | 0 | Female: 51 % | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Women and youth need to be involved with RWH and GWTR | Output 3.1, 3.2, 3.3 | Focal point identified | 0 | 1 per building | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Farmers and workers, incl. Syrians and youth are targeted | Output 3.7 | % Syrians and youth participation | 0 | Syrian: 15 % Youth: 30 % | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Employees could be female | Output 3.8 | % female employees | 0 | 50% | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Employees 50% of which are to be females | Output 3.9 | % female employees | 0 | 50% | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Limited involvement of women in meetings | Output 4.1, 4.2 | Women and youth considerations in KM | 0 | Specific mentioning | Poor: activities have not started yet, this will be measured at the mid -term and end of project
Women roles and youth are not specified in plans and knowledge management | Output 4.3 | Women and youth considerations in plans / KM | 0 | Specific mentioning | Poor: activities have not started yet, this will be measured at the mid -term and end of project
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UN-Habitat presented the Gender Policy to all Executing Entities and partners highlighting the importance of its compliance at any stage of the project and stressed on the importance of an adequate women representation in trainings and events. Special attention has been paid to achieving gender balance in every activity, from recruitment processes to the invitations to the project inception workshop and steering committee meetings. UN-Habitat also ensured adding complicance with the GP in all the agreements of cooperation and UN-to-UN agreements with the Executing Entities in addition to assigning a gender focal point within all the EEs.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | All Executing Entities (UN ESCWA,UNICEF, JOHUD, HFDJB, PRI, and YWC (in addition to consulting firms in component 1 and 4) have to comply with the Gender Policy as per their agreement with the Implementing Entity, this includes ensuring the collection of gender disaggreated data, and ensuring women's representation in trainings, workshops and events, and that the gender dimension of climate change is integrated in their work packages. Implementation has not yet started. Nevertheless, the project document which is a binding and integral part of all agreements with Executing Entities includes a clear indication of the need to implement the GP of the Adaptation Fund. UN ESCWA: all Gender safeguards were assessed and monitored during implementation according to the UN to UN agreement signed by assigning a focal point for gender in UN ESCWA that report to the UNH. UN ESCWA ensured women's involvement in the knowledge managment and communication work. UNICEF: UNICEF is commeted to its global Gender Policy 2021-2030 and accompanying Action Plan 2022-2025. Gender safeguards should be assessed and monitored during implementation according to the UN to UN agreement signed, by assigning a focal point for gender in UNICEF that report to the UNH.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Implmentation arrangements are in progress.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] | [5 empty] | The concept of the Grievances mechanism will be prepared to deal with all cases on the level of EEs activities and the IE activities. The detailed Grievances mechanism will be shared with EEs to be implemented on two levels (the EE and the IE)
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity UN Habitat: | Component 1: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration |  | Outcome 2 |  | Agreements with 3 municipalities in both countries to prepare Urban master plans that mainstream climate change and gender |  | MoU between UN Habitat , Ministry of Local Administration, and two Municipalities (Irbid and Mafraq) was signed in Jordan and tendering process to select a executing consulting firm was announced in October. Agreement with the Municipality of Zahle and the Ministy of Environment in Lebanon was made; tendering process was launched in May and offers were received from interested consulting firms. The evaluation was completed but an agreement has not yet been signed with the selected consulting firm. Mobilization of RTO in Lebanon for planning purposes. | S
| Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  | Outcome 3 | Outcome 8 | Capacity needs assesssment to Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  | AoC with partners prepared to include the capacity needs assesssment in the work plan for Jordan. Site assessments launched, public consultations implemented and feasibility study developed for rainwater harvesting and wastewater reuse projects in Lebanon. Start up of capacity building to operate and maintain project activities. | MS
| Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  | Outcome 4 | Outcome 6 | Conduct the first technical assessments for the water harvesting, graywater, irrigatin systems and permaculture in order to expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  | AoC with partners prepared to include the detailed work plan that have technical assessments for the water harvesting, graywater, irrigatin systems and permaculture | MS
| Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) |  | Outcome 3 | Outcome 8 | Start the process of development of regional urban risks and vulnerabilities management model in the context of climate change and urban Conduct regional and national steering committees meetings |  | Tendering process completed to select a consulting firm who will work on output 4.3 (and component 1) in Lebanon, agreement signature not yet done; tender documents for the same activities were prepared in Jordan Three steering commitees meetings were conducted including two national steering committee meetings and one regional committee meeting (inception workshop) | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Hussien Muhsen
| Email: | hussien.muhsen@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project overall implementation progress rating is Marginally Satisfactory (MS) due to delays in project activities due to project activities review in both countries under the COVID 19 and Ukraine war resulting inflation and prices changes. Nevertheless, the project team start the background work to prepare implementation arrangements with partners, including UN-ESCWA UN to UN agreement, MoU between UN Habitat, MoLA, Mafraq and Irbid Municipalities , MoU between UN Habitat, Jaresh University, and PRI, in addition to AoCs with EEs and UN to UN agreement with UNICEF prepared and ready to be reviewed by UN Habitat HQ and signed. The first regional Inception workshop, first national steering committee in Jordan, and the first national steering committee in Lebanon were conducted.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: JOHUD / Aseel Almukhaimer | Output 2.2 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rain Water Harvesting (RWH) in Jordan |  | Outcome 3 | Outcome 8 | Signature of Agreement of Cooperation [AOC] with the EE. This includes developing the work-plan, agreeing on payments schedules and gathering all the documents needed to finalize the agreement. In addition, the EEs were expected to revise their budget allocation and conduct another preliminary assessment to make sure they can still deliver the outputs after the change in prices due to global inflation |  | All the documents related to the AOC were finalized and sent to HQ legal department for their revision. After HQ clears the AOC, we will go ahead and sign the agreement | S
| Output 2.7.1 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7:Water-use Efficient irrigation of treated wastewater from Maerad and Al Kaider WWTPs in Jordan |  | Outcome 3 | Outcome 8 |  |  |  | S
| Output 3.2 Rooftop Rain Water Harvesting (RWH) in Jordan + show room |  | Outcome 4 | Outcome 6 |  |  |  | S
| Output 3.7.1 Water-use Efficient irrigation of treated wastewater from Maerad and Alkaider WWTPs in Jordan |  | Outcome 4 | Outcome 6 |  |  |  | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jawad Dukhgan
| Email: | jawad.dukhgan@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Based on the results of reviewing the project’s outputs and activities in Jordan and on-ground assessments of targeted execution sites and beneficiary communities, the executing entities highlighted that because of COVID-19, there have been unprecedented changes in the global supply chain, which resulted in a significant increase in prices of freight charges and material and equipment needed to realize their outputs. Hence, the executing entities had to review their allocated budgets and conduct another assessment to provide more accurate estimations, which was later sent as an amendment request for the AF board. After the approval of the AF board, the documents were edited and submitted as an AOC package for UN-Habitat HQ for legal approval. On a positive note, all the required documents were prepared and now we are following up with HQ to get them cleared to sign the agreement.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: HFDJB / Abdallah Alsardi | Output 2.7.2 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7:Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan |  | Outcome 3 | Outcome 8 | Signature of Agreement of Cooperation with the EE. This includes developing the work-plan, agreeing on payments schedules and gathering all the documents needed to finalize the agreement. In addition, the EEs were expected to revise their budget allocation and conduct another preliminary assessment to make sure they can still deliver the outputs after the change in prices due to global inflation |  | All the documents related to the AOC were finalized and sent to HQ legal department for their revision. After HQ clears the AOC, we will go ahead and sign the agreement | S
| Output 3.7.2 Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan |  | Outcome 4 | Outcome 6 |  |  |  | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jawad Dukhgan
| Email: | jawad.dukhan@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Based on the results of reviewing the project’s outputs and activities in Jordan and on-ground assessments of targeted execution sites and beneficiary communities, the executing entities highlighted that because of COVID-19, there have been unprecedented changes in the global supply chain, which resulted in a significant increase in prices of freight charges and material and equipment needed to realize their outputs. Hence, the executing entities had to review their allocated budgets and conduct another assessment to provide more accurate estimations, which was later sent as an amendment request for the AF board. After the approval of the AF board, the documents were edited and submitted as an AOC package for UN-Habitat HQ for legal approval. On a positive note, all the required documents were prepared and now we are following up with HQ to get them cleared to sign the agreement.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: PRI / Nadia Lawton | Output 2.8 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.8; permaculture demonstration |  | Outcome 3 | Outcome 8 | Signature of Agreement of Cooperation with the EE. This includes developing the work-plan, agreeing on payments schedules and gathering all the documents needed to finalize the agreement. In addition, the EEs were expected to revise their budget allocation and conduct another preliminary assessment to make sure they can still deliver the outputs after the change in prices due to global inflation |  | All the documents related to the AOC are still being finalized and to be sent to HQ legal department for their revision. After HQ clears the AOC, we will go ahead and sign the agreement | MS
| Output 3.8 Permaculture demonstration - closed loop water system in Jordan |  | Outcome 4 | Outcome 6 |  |  |  | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jawad Dukhgan
| Email: | jawad.dukhan@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Based on the results of reviewing the project’s outputs and activities in Jordan and on-ground assessments of targeted execution sites and beneficiary communities, the executing entities highlighted that because of COVID-19, there have been unprecedented changes in the global supply chain, which resulted in a significant increase in prices of freight charges and material and equipment needed to realize their outputs. Hence, the executing entities had to review their allocated budgets and conduct another assessment to provide more accurate estimations, which was later sent as an amendment request for the AF board. After the approval of the AF board, the documents were edited and submitted as an AOC package for UN-Habitat HQ for legal approval. On a positive note, most of the required documents were prepared and soon will be sent to our HQ for their revision and clearance.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: UNICEF - JORDAN / Ahmad Afaneh | Output 2.3 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.3: Grey Water Treatment and Reuse (GWTR) in Jordan |  | Outcome 3 | Outcome 8 | Signature of the Un to Un Agreement . This includes developing the work-plan, agreeing on payments schedules and gathering all the documents needed to finalize the agreement. In addition, the EEs were expected to revise their budget allocation and conduct another preliminary assessment to make sure they can still deliver the outputs after the change in prices due to global inflation |  | All the documents related to the Un to Un agreement are still being finalized and to be sent to HQ legal department for their revision. After HQ clears the agreement, we will go ahead and sign it. | MS
| Output 3.3 Grey Water Treatment and Reuse (GWTR) in Jordan |  | Outcome 4 | Outcome 6 |  |  |  | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jawad Dukhgan
| Email: | jawad.dukhan@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Based on the results of reviewing the project’s outputs and activities in Jordan and on-ground assessments of targeted execution sites and beneficiary communities, the executing entities highlighted that because of COVID-19, there have been unprecedented changes in the global supply chain, which resulted in a significant increase in prices of freight charges and material and equipment needed to realize their outputs. Hence, the executing entities had to review their allocated budgets and conduct another assessment to provide more accurate estimations, which was later sent as an amendment request for the AF board. After the approval of the AF board, the documents were edited and submitted as an AOC package for UN-Habitat HQ for legal approval. On a positive note, most of the required documents were prepared and soon will be sent to our HQ for their revision and clearance.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: Yarmouk Water Company YWC / Mahmoud Obeidat | Output 2.5 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.5: Efficient treatment and reuse of wastewater in Jordan |  | Outcome 3 | Outcome 8 | Signature of Agreement of Cooperation with the EE. This includes developing the work-plan, agreeing on payments schedules and gathering all the documents needed to finalize the agreement. In addition, the EEs were expected to revise their budget allocation and conduct another preliminary assessment to make sure they can still deliver the outputs after the change in prices due to global inflation |  | All the documents related to the AOC are still being finalized and to be sent to HQ legal department for their revision. After HQ clears the AOC, we will go ahead and sign the agreement | MS
| Output 3.5 Efficient treatment and reuse of wastewater in Jordan |  | Outcome 4 | Outcome 6 |  |  |  | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jawad Dukhgan
| Email: | jawad.dukhan@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Based on the results of reviewing the project’s outputs and activities in Jordan and on-ground assessments of targeted execution sites and beneficiary communities, the executing entities highlighted that because of COVID-19, there have been unprecedented changes in the global supply chain, which resulted in a significant increase in prices of freight charges and material and equipment needed to realize their outputs. Hence, the executing entities had to review their allocated budgets and conduct another assessment to provide more accurate estimations, which was later sent as an amendment request for the AF board. After the approval of the AF board, the documents were edited and submitted as an AOC package for UN-Habitat HQ for legal approval. On a positive note, most of the required documents were prepared and soon will be sent to our HQ for their revision and clearance.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: Consultant Company / NA | Output 1.3 Urban master plans at municipal level with climate change and gender mainstreamed (Jordan) |  | Outcome 2 |  | Agreement not signed yet |  | Not applicable | Not applicable
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jawad Dukhgan
| Email: | jawad.dukhan@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The satisfactory rating is based on fulfilling most of the expected outputs for this phase. Primarily signing an MOU with the Ministry of Local Administration and two municipalities. However, there were some delays in issuing the RFP as it was a long process of coordination and data gathering from the municipalities and the Ministry of Local Administration to make sure they were involved and agree with the proposed tasks and outputs that the consultant will undertake
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: Unicef Lebanon Office / Paul Edwards | Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  | Outcome 3 | Outcome 8 | Capacity needs assesssment to Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  | Public consultations with farmers and other local stakeholders Startup of technical assessment of targeted buildings / areas Feasibility assessment for rainwater harvesting and wastewater reuse outputs | S
| Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  | Outcome 4 | Outcome 6 | Expand climate change resilient (unconventional) water harvesting and supply options, using innovative, low-cost and replicable techniques |  | Implementation not started yet | Not applicable
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Layale Abi Esber
| Email: | layal.abiesber@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The satisfactory rating is based on the efficient engagement of Unicef in the implementation of public consultations, site / technical assessments and a feasibility analysis to confirm the validity of the earlier proposed activities and associated budgets given the worldwide inflation which has taken place since project inception. The latter assessments and studies were instrumental in informing the amendment process which took place between August and October 2022. However, implementation has not yet started making it impossible to rate their performance on component 3.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: Consulting Firm in Lebanon (TBD) | Component 1: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration |  | Outcome 2 |  | Agreement not signed yet |  | Not applicable | Not applicable
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Layale Abi Esber
| Email: | layal.abiesber@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | A consulting firm has been selected on the basis of being the lowest technically compliant bid, but an agreement hasn't been signed yet. Therefore it is not yet possible to specify the name of the firm or to rate their performance.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
UN-ESCWA | Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) |  | Outcome 3 | Outcome 8 | development of regional urban risks and vulnerabilities management model in the context of climate change and urban |  | Two national steering committee meetings were held - one each in Lebanon and Jordan in October 2022. The project launch in October 2021 brought together the regional steering committee. Project stakeholders participated in the World Urban Forum in June 2022, sharing the project and its objectives. Participation in these events was also shared on social media (Facebook and Twitter) by ESCWA and UN-Habitat. ESCWA is currently in the process of contracting a full-communications officer, developing a web page that will host the virtual Community of Practice, and beginning work on the "before" video. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sara Hess
| Email: | sara.hess@cepal.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The rating of satisfactory is based on the fulfillment of project objectives like participating in international seminars and organizing the regional and national steering committee meetings. There have been several overarching delays in the project associated with the project design which has delayed the development of knowledge products to share. Despite delays, as much of the knowledge management work that could be done for 4.1 and 4.2 was completed through the cooperation of a strong inter-agency team of UN-Habitat and ESCWA. Additionally, the development of a separate project website to host the virtual COP is underway.
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Number and type of targeted institutions with increased capacity to minimize exposure to climate change through climate change and gender mainstreamed strategies / guidelines and urban master plans at district level | 0 | Activity not initiated yet | 1
| Number and type of targeted institutions with increased capacity to minimize exposure to climate change through climate change and gender mainstreamed strategies / guidelines and urban master plans at municipal level | 0 | Activity not initiated yet | 10 (8 Lebanon, 2 Jordan)
| Relevant threat and hazard information generated and disseminated through to stakeholders on a timely basis | 0 | Activity not initiated yet | 10 (8 Lebanon, 2 Jordan)
| Evidence-based climate-changed mainstreamed municipal plans developed, disseminated during project and operational | 0 | Activity not initiated yet | 3
Output 1.1 | Number of staff/people with increased capacity trained to respond to, and mitigate impacts of, climate-related events (in line with AF results indicator 2.1.1) through assessment and planning processes (workshops/trainings) | 0 | Regional technical office mobilized to start planning for implementation | 480
| % women participating | 0 |  | >40 %
| % youth participating | 0 |  | >15 %
Output 1.2 | Number of staff trained to respond to, and mitigate impacts of, climate-related events (in line with AF results indicator 2.1.1) through assessment and planning processes (workshops/trainings) | 0 | Regional technical office mobilized to start planning for implementation | 240
| % women participating | 0 |  | >40 %
| % youth participating | 0 |  | >15 %
| % awareness/knowledge on the need to take gender informed decisions on climate change | 0 |  | 50%
| No of climate change mainstreamed municipal plans based on vulnerability data developed or adapted (in line with AF results indicator 1.1) | 0 | Activity not initiated yet | 8
| Percentage of municipal inhabitant in target areas covered by the municipal plans | 0 |  | 50%
| Percentage of women, youth and Syrians in target areas covered by the municipal plans | 0 |  | 50%
Output 1.3 | Number of staff / people trained to respond to, and mitigate impacts of, climate-related events (in line with AF results indicator 2.1.1) through assessment and planning processes (workshops/trainings) | 0 |  | 450
| % Women participating | 0 |  | >45 %
| % youth participating | 0 |  | >15 %
| No of climate change mainstreamed municipal plans based on vulnerability data developed or adapted (in line with AF results indicator 1.1) | 0 |  | 2
| Percentage of municipal inhabitant in target areas covered by the municipal plans | 0 |  | 0.5
| Percentage of women, youth and Syrians in target areas covered by the municipal plans | 0 |  | 0.5
Outcome 2 | Percentage of targeted direct population aware climate change and appropriate responses to climate change (in line with AF results indicator 3.1) | 0 | Activity not initiated yet | 0.3
| % Women aware | 0 |  | >40 %
| % Youth aware | 0 |  | >15 %
| % of targeted direct population with skills enhanced using acquired climate information and knowledge to undertake, operate, maintain and replicate proposed adaptation measures | 0 | Activity not initiated yet | 30%
| Innovative adaptation practices / technologies encouraged to be replicated and upscaled through replication plans (in line with AF results indicator 8) | 0 | Activity not initiated yet | 8
Output 2.1 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 10
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
Output 2.2 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 64
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
Output 2.3 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 40
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
Output 2.4 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 1 (for Zahle, to irrigate 800 ha of land)
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared |  |  | 1
Output 2.5 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 3 (for WWTPs)
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
Output 2.6 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 |  | 1 (800 ha farmland)
| Number O & M plans produced and shared |  |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
Output 2.7 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 1 (for 195 dunum farmland)
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
Output 2.8 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 1
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
| No. of students completed permaculture curriculum with certificate | 0 |  | 200
| % Women from students | 0 |  | >50%
Output 2.9 | No. of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2) | 0 | Activity not initiated yet | 1
| Number O & M plans produced and shared | 0 |  | 1
| Number of replication guidelines produced and shared | 0 |  | 1
| No. of students completed permaculture curriculum with certificate | 0 | 1 (government staff trained by PRI and obtained a certificate) | 270
| % Women from students | 0 |  | >50%
Outcome 3 | Ha of farmland with more sustained climate-resilient livelihoods | 0 |  | Lebanon: 800 ha / Jordan: 195 Dunums
| Innovative techniques / interventions | 0 |  | 4
Output 3.1 | Number of RWH systems installed | 0 | Activity not initiated yet | 10
| Volume of rainwater collected and stored to supply safe and clean freshwater during dry periods | 0 |  | 245 m3
Output 3.2 | Number of RWH systems installed | 0 | Activity not initiated yet | 64
| Volume of rainwater collected and stored to supply safe and clean freshwater during dry periods | 0 |  | Rainwater harvesting systems with an annual estimated rain water collection of 3,780 m3
Output 3.3 | Number of GWTR systems installed | 0 | Activity not initiated yet | 40
Output 3.4 | One reservoir | 0 | Activity not initiated yet | 1 (10,000 m3)
| Two pumping lines | 0 |  | 9300 meters (3,300 m to Zone A and 5,500 m to Zone B)
| Water quantity | 0 |  | 20,000 m3
| Water quality | Baseline quality |  | Compliant to standard
Output 3.5 | Water storage constructed / installed | 1 | Activity not initiated yet | 1x 2000 m3 (Maerad WWTP) 1x500 m3 (AlAkaider WWTP)
| Water quality | Baseline quality |  | Compliant to standard
Output 3.6
Output 3.7 | Conveyor irrigation pipeline 6’ size installed (in meters) | 0 | Activity not initiated yet | 4000m
| Treated and stored channeled water from Maered WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods Treated and stored channeled water from Al Kaider WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods | 0 |  | 60 dunum
| Treated and channeled water from Mafraq WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods | 0 |  | 60 dunum
| Treated and channeled water from small ponds and thus sustaining climate-resilience of agriculture livelihoods | 0 |  | 75 dunum
| Treated and channeled water from small ponds and thus sustaining climate-resilience of agriculture livelihoods | 0 |  | 8 ponds
Ouput 3.8 | Permaculture demonstration site established, including: -Biofertilizer site -Organic crop garden -Olive trees (Orchard monoculture conversion to Food Forest) -Compost Chicken system with egg production | 0 0 0 0 | Activity not initiated yet | 1,000 m2 of organic soil fertilizer production 1,000 m2 of diverse organic crop garden in full production 1,000 m2 of organic mix food forest majoring in olives 30 chickens producing compost
Output 3.9 | Permaculture demonstration site established, including: - Agricultural Waste Management for Sustainable Crop Production - Urban, Peri-Urban and Rural Agriculture and Water Harvesting as Adaptation Measures - Apiculture and the reduction of chemical substance use at farm level - Introducing adapted crop varieties and diversifying farm production | 0 0 0 0 | Activity not initiated yet | 30 20 80 10
Outcome 4 | Strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning (in line with AF results indicator 3.2) | 0 |  | 50%
| % increased of gender-sensitive good practices /lessons learnt per country at national and city level that are shared | 0 |  | 30%
Output 4.1 | Number of technical committees formed to ensure transfer of knowledge (in line with AF results indicator 3.2.1.) - Regional steering committee formed - National steering committees formed | 0 0 0 | 1 - Regional Steering Committee and 2 - National Steering Committees | 1 5 4
| Number of tools and guidelines developed and shared with relevant stakeholders through the CoP (in line with AF results indicator 3.2.2). - Project video developed and shared with relevant stakeholders - No of good practices per city shared - Number of regional workshops held | 0 0 0 | 1 Regional workshop held | 2 1 5
Output 4.2 | No. of municipal plans on gender sensitive climate adaptation that have been developed/revised (for incorporating the good practices) | 0 |  | 8 (6 in Lebanon and 2 in Jordan)
| No. of bilateral city-to-city meetings held among Jordan and Lebanon on gender sensitive climate adaptation practices | 0 | 1 in Lebanon (Zahle) | At least 6 exchange in both countries
| No. of field visits conducted and lessons learned shared | 0 | 1 in Lebanon (Zahle) | 4
| No. of field visits exchanged with a focus on gender and climate change | 0 |  | 20
| No. of participants to the visits (gender disaggregated | 0 |  | (50 % Women)
Output 4.3 | Number of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2). | 0 | Activity not initiated yet | 1 (with gender consideration)
| Regional’ urban risks and vulnerabilities assessment, planning and management approach model developed and shared | 0 |  | 1
| No of views of the online modules | 0 |  | 500
| Presentations of the model given / shared at events and webinars | 0 |  | 5
| % increased interest in applying the model in other cities/countries | 0 |  | 30%
| % increased awareness of the content of the module | 0 |  | 30%
Output 4.4 | Number of tools and guidelines developed and shared with relevant stakeholders (in line with AF results indicator 3.2.2).Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities developed/published and shared | 0 | Activity not initiated yet | 1
| % increased interest in replicating upscale rainwater harvesting in other cities in Jordan | 0 |  | 30%

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The Agreements with Excuting Entities preparation time should be considered in the project design and preparations.The team have amended the implementation plan of EEs to speed up the process and make a progress during next year. The existing RICCAR database of climate projections has been shared between ESCWA and Habitat to help inform the municipal planning processes. This includes climate projections for the Mashreq Region through 2070.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, the project had to make two amendments in the first year, the first was becasue the need to change EEs in Lebanon, and the second was after conducting intial assessment of project operational costs that required a revision of project indicators due to COVID 19 and war in Ukrain implications . Another reason was changing permaculture project site from JUST to Jerash which affected the progress of the project.The team have amended the implementation plan of EEs to speed up the process and make a progress during next year.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Two amendment requests were filed: the first amendment included primarily a change in executing entities in Lebanon due to the financial crisis affecting the ability of governmental entities to receive money in dollars; the second amendment included primarily a change in the targets as a result of the worldwide inflation of prices, as well as a change in outputs in Lebanon to adapt the project to findings from initiated field assessments and additional public consultations.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No implementation yet, so it is not possible to measure the environmental and social safeguards impact
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | No implementation yet, so it is not possible to measure the gender considerations' impact. However, one of the lessons learned is that gender considerations must be embedded in all agreements and Memorandam of Understandings from the start of the work, in order to ensure mobilizing resources to achieve gender mainstreaming
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UN-Habitat
Type of implementing entity | MIE
Country | Jordan | Lebanon
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  | 260667 |  | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries |  | 40% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  | 15% |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 11 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Urban development | Local | 3: Risk and vulnterability assessments completed or updated | 11 | Urban development | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Urban development | 3: Medium capacity | Total | 10 | Urban development | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 1170 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Urban development | 2: Low capacity | Public | Local | Urban development | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | Local | Urban development | 2: Low capacity | 930 | Local | Urban development | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Water management |  | 30% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 40500 | 40% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 2: Partially not aware |  | 3 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Regional |  | 9 | Technical guidelines | Regional
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 1: Non responsive (Lacks all elements ) |  | Water management | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  |  |  | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Urban development | Local | Urban policy | 3 | Urban development | Local | Urban policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 2: Partially effective | 3 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Urban adapt | Subnational | Innovation rolled out |  | Urban adapt | Sub-national | Innovation rolled out
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Water management | No innovative practices | 1: Ineffective | 8 | Water management | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness