## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 29 June 2021 to 28 June 2022
| Project Title: | Adaptation Initiative for Climate Vulnerable Offshore Small Islands and Riverine Charland in Bangladesh
| Project Summary: | Bangladesh has a low-lying topography extremely exposed to sea-level rise, cyclones, tidal surges, salinity intrusion, erratic rainfall, drought, and floods, causing it to be one of the world’s most vulnerable countries to climate change. The vulnerable communities who live on chars - small alluvial islands in rivers and the Bay of Bengal are particularly at risk from climate change. These communities have already experienced several climate change impacts including frequent tidal surges, increasingly intense cyclones, and saltwater intrusion into freshwater and soil. Furthermore, climate change is projected to have an adverse impact on agriculture and other local livelihoods; fragile houses, access to drinking water, and rural infrastructure, which includes existing cyclone protection embankments. The impacts of climate change also disproportionately affect the poor and are especially severe for women and children, who are forced to spend a greater portion of their time on livelihood and domestic activities. In this context, a project name “Adaptation Initiative for Climate Vulnerable Offshore Small Islands and Riverine Char land in Bangladesh” is implementing by the Ministry of Environment, Forest and Climate Change (MoEFCC), Government of the People's Republic of Bangladesh following UNDP’s National Implementation Modality. It’s a five-year project that started in 29 June 2021 and is financed by Adaptation Fund (AF). The main objective of the project is to enhance the climate resilience of vulnerable communities who live on coastal islands and riverine chars in Bangladesh. This objective will be achieved through the following four project outcomes: 1) Community infrastructure improved, and adaptive capacity increased for the vulnerable small island and riverine char communities to manage and plan for climate change impacts; 2) Resilience of vulnerable small coastal island communities enhanced against climate-induced disasters through improved infrastructure, management practices, and community-based emergency responses; 3) Adaptive capacity of vulnerable communities improved through the dissemination of climate-resilient agricultural practices and the development of diversified livelihoods; and 4) Increased awareness and availability of information on climate change impacts and adaptation options for vulnerable communities, local-level government, and policymakers. To achieve these outcomes, the project activities are grouped into four components which are as follows: Component 1. Enhanced climate resilience of households through climate-resilient housing, electrification and climate-proof water provisioning Component 2. Increased climate resilience of communities through infrastructure that is resilient to cyclones and floods, climate risk mapping, and inclusive cyclone preparedness. Component 3: Improved income and food security of communities by innovating and providing assistance to selected households for climate-resilient livelihood practices. Component 4. Enhanced knowledge and capacity of communities, government and policymakers to promote climate resilient development on chars. Spanning over five years, the project interventions will benefit an estimated ~341,000 people (~31,000 direct beneficiaries and 310,000 indirect beneficiaries) living on chars in the districts of Rangpur and Bhola. The project will contribute toward the achievement of the Government of Bangladesh’s national priorities as outlined in the Bangladesh Climate Change Strategy and Action Plan (BCCSAP) and Nationally Determined Contribution (NDC). This initiative is part of UNDP’s continuous effort to achieve Sustainable Development Goals and eradicate poverty and inequality and tackle the dual threats of climate change and natural disasters.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Environment, Forest and Climate Change (MoEFCC) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Bangladesh | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 1. Lakshmitari Union of Gangachara Upazila under Rangpur District; 2. Mujibnagar Union of Char Fasson Upazila under Bhola District; and 3. Six additional coastal islands in Bhola District for CPP interventions | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-05-07 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-06-29 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | N/A (expected 24-Dec-23)
| Original Completion Date: | 2026-06-28
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Prior to the first disbursement, UNDP shall submit to the Adaptation Fund Board, through the secretariat, the revised environmental and social risk identification and analysis in the format complying with the environmental and social policy and gender policy of the Fund.
| Current Status | Condition met and cleared by the AFB Sec
| Planned actions, including a detailed time schedule | N/A
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception Report submitted to AFB on 9 Nov 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Bablu Kumer Barua | Dominican Republic
| Email: | bablu.kumer.barua@undp.org | Ecuador
| Date: | 2022-09-25 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Arif Mohammad Faisal | Fiji
| Email: | arif.faisal@undp.org | Finland
| Date: | 2022-09-25 | France
| Executing Agency |  | Gambia
| Name: | Mohammed Solaiman Haider | Georgia
| Email: | haider.doe@gmail.com | Germany
| Date: | 2022-09-25 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 28 June 2022 |  |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 28 June 2022 |  | 11666 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | The Project Document was signed between three parties: Government, Implementing Partner- Ministry of Environment, Forest and Climate Change (MoEFCC), and UNDP dated 24 June 2021. The Project Inception workshop was held on 29 June 2021. Project Implementation is yet to be initiated by the Implementing Partner due to delay in approval of Technical Assistance Project Proposal (TAPP). UNDP CO has followed up with the Planning Commission to approve the TAPP, so IP can start Project Implementation soon. in the mean time, UNDP has supported IP to complete recruitment of key Project Staff of the PMU. Note: The estimated cumlative total disbursement does not inlcude IE fee |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  | N/A |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (in USD) |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
|  | Project Management: Salary of PMU Staffs | 11408
|  | Project Management:Travel cost (Local) | 258
|  | Total Executing Cost | 11666
|  | Implementing entity fee per Legal Agreement | 423607
|  | Total Cost | 435273 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (in USD) | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | Output 1.1. Cyclone and flood resilient houses for the most vulnerable households. | 11000 | 2023-06-28
|  | Output 1.2. Community-level nano-grids installed for electrification to enhance adaptive capacity | 11000 | 2023-06-28
|  | Output 1.3. Locally appropriate rainwater harvesting systems for safe drinking water and home-garden irrigation. | 11000 | 2023-06-28
|  | Output 2.1. Climate resilient infrastructure built to protect life and prevent asset loss | 8250 | 2023-06-28
|  | Output 2.2. Embankments repaired and innovative model for community embankment management introduced. | 20000 | 2023-06-28
|  | Output 2.3. Climate-resilient investment on chars promoted through climate hazard maps and expanded cyclone early warning systems. | 10000 | 2023-06-28
|  | Output 2.4. Cyclone Preparedness Programme (CPP) modernised and expanded to provide timely cyclone early warning and response at scale. | 485000 | 2023-06-28
| 35 | Output 3.1. Climate-resilient agriculture implemented and supported at a community level | 11000 | 2023-06-28
|  | Output 3.2. Diversified livelihoods developed and supported for the most vulnerable households | 25000 | 2023-06-28
|  | Output 4.2. Knowledge and awareness generated to promote climate resilient approaches and strategies | 10000 | 2023-06-28
|  | Project Management Cost | 80000 | 2023-06-28
|  | TOTAL | 682250
|  | Implementing Entity Fee per Legal Agreement | 0
|  | GRAND TOTAL | 682250
[6 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on F38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: since tranche will not be required to be disbursed, IE fee to be received is 0

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Identifying climate-resilient livelihood options that are suitable to the condition of the vulnerable people. | Medium | A ToR is developed to hire a National Consultant to identify innovative livelihood options that will be suitable considering local, social, economic, ecological, and climatic conditions and will be accepted by the local communities. The Procurement process will start once the Technical Assistance Project Proposal (TAPP) is approved. However, the capacity of the vulnerable people is carefully assessed and lessons from other projects are reviewed by the Project Manager.
Uncertainty regarding the intensity of climatic events that may affect the project interventions, including housing and infrastructure. | Medium | The project is collecting all climate scenarios from the vulnerable areas and accordingly preparing the work plan. The risk information is shared with the Department of Environment (DoE) and Bangladesh Water Development Board (BWDB) and used to design the Terms of References (ToR) to procure firms, especially for infrastructure and houses. Hazard and vulnerability maps will be developed as soon as the TAPP is approved.
Current and predicted climate variability and/or extreme climate events negatively impact timeline of the project. | Medium | The project integrated the two outputs focusing on hazard risk scenarios and early warning communication to enable strong preparedness planning. Activities under relevant outputs will be implemented early in the project’s lifespan. Memorandum of Understanding (MOU) with the Cyclone Preparedness Programm (CPP) and BWDB has been developed accordingly, so that potential impacts of extreme climate events are minimized. A multi-year business continuity plan is developed.
Influence of government and local political leaders in selection of beneficiaries. | Medium | Several meetings and joint field trips were organized with the officials from DoE, BWDB, and Local Government representatives to confirm their commitment to successful implementation of the project. In addition, stakeholder consultations are continuing to ensure that government agencies maintain their commitment during project implementation. Grievance Redressal Mechanism will be established once the National Project Director is onboard after the approval of TAPP.
Capacity constraints of local communities and other stakeholders may limit the ability to undertake the implementation of proposed interventions. | Low | Local adaptation measures are identified considering the capacity of the communities and implementing agency
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The Project TAPP approval process experienced delays due to Covid-19 and associated post-Covid activities that the government has had to attend to. So the project couldn't start implementation of field activities after the Inception workshop which resulted in a significant delay in Project implementation and a low delivery rate. Note that the Technical Assistance Project Proposal (TAPP) process is a mandatory government requirement for all development projects in Bangladesh. | Medium | UNDP Bangladesh is closely following up with the implementing ministries, Economic Relations Division (ERD), and the Planning Commission to expedite the approval of the TAPP. Several coordination meetings are organized with DoE, CPP, BWDB and ERD. MOU and meeting minutes for CPP and BWDB are finalized. As per government procedures, the implementation of a NIM project is not allowed until the approval of TAPP. While waiting for TAPP approval, the project has already initiated preparatory work including the development of the terms of references (ToRs) and procurement documents to engage individual consultants and firms to implement the project's proposed activities, e.g. climate-resilient housing, solar nano grid, rainwater harvesting system, solar cold storage, cluster houses, and alternative livelihoods support. So once the TAPP is approved, the project will implement all activities in full swing.
The beneficiaries of the proposed project are poor people in vulnerable communities who are often not integrated into decision-making processes. There is, therefore, a risk that certain community members may benefit more than others. This may result in both intra- and inter-community conflicts. | Low | Beneficiary selection criteria and the process is developed in consultation with the community and local government for all interventions.
There is a risk that vulnerable and marginalised groups will be excluded during the implementation of project activities and have insufficient access to the associated benefits. | Low | The project is ensuring the inclusion of marginalized and vulnerable groups – especially women and people living with disabilities. The beneficiary households selection guideline is developed following this strategy. Community consultations have been incorporated for all activities that do not achieve complete coverage of the target population. This will allow for the identification of marginalised and vulnerable households.
No activities are, or will be, included in the design of the proposed project that are not in line with established international human rights. Moreover, the proposed project will promote the fundamental human rights of access to food, water and information. | Low | Meetings with stakeholders are continuing throughout project implementation to ensure that the benefits of the project are shared broadly in a non-discriminatory, equitable manner through participatory processes and transparent selection criteria.
The proposed project is targeting communities where men occupy the majority of the leadership positions. There is, therefore, a risk that women will not benefit equitably from the proposed project’s climate change adaptation and capacity-building interventions. | Low | The project Manager completed a mandatory course of UNDP on gender and human rights to ensure gender equity and women’s empowerment in the project. Measure to ensure equity in benefit sharing from project interventions will be part of project implementation.
Local communities will be involved in the implementation and maintenance of climate change adaptation interventions. Therefore, local community members may be exposed to the risk of accidents while implementing the proposed project’s climate change adaptation interventions. | Low | The project has developed Terms of References (ToRs) and Request for Proposal (RFP) for hiring firms for construction works. As part of the ToRs, the vendors are required to follow the International Labour Organisation Convention core labour standards, avoid any negative discrimination, and eliminate any child labour or forced or compulsory labour.
There is a low risk that houses have been constructed in areas that conflict with the infrastructure interventions under Component 2 (Specifically Output 2.1). This may result in temporary resettlement while infrastructure is being put in place | Low | In-depth consultations with any households that may be at risk of requiring resettlement are included in the beneficiaries' selection process. The possibility of involuntary resettlement for the repair of embankments is checked at the field level during the joint field trip with DoE and BWDB.
On-the-ground adaptation interventions (specifically EbA) will include the planting of species for enrichment and/or restoration of ecosystems. This could lead to long-term alteration of natural habitats in terms of species assemblages and structure, which may result in various disturbances and negative environmental impacts. Adaptation interventions involving hard infrastructure will also be constructed – for example, the rehabilitation of damaged embankments. Such interventions may result in the disturbance of small areas of natural habitat. | Medium | EbA approach for strengthening embankment is discussed with BWDB and included in the MoU.
There is a low risk that adaptation interventions involving the construction of hard infrastructure – for example, the rehabilitation of damaged embankments (Activity 2.1.2.) could negatively impact biodiversity. | Low | A ToR is developed to hire a firm to develop an environmental management plan and conduct environmental monitoring. It will help the Project to ensure that Project activities do not cause significant loss of biological diversity. The firm will be recruited once the TAPP is approved.
Risks have been identified that are associated with the grey infrastructure interventions (Output 2.2.). These interventions include raising houses on plinths, repairing flood protection embankments and the construction of dual-purpose cluster house/storm shelters. | Medium | In the ToR and RFP for hiring construction firms, the Project added mandatory conditions that all relevant environmental codes and standards should be followed by the firms during the design and construction of the grey infrastructure interventions.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In this reporting period, the Project TAPP approval was delayed due to Covid-19 and associated post-Covid activities. So, the project couldn't start the actual implementation of field activities which resulted in a significant delay in Project implementation and a low delivery rate. Note that the Technical Assistance Project Proposal (TAPP) is a mandatory government requirement for all development projects in Bangladesh. UNDP closely follows up with the DoE, Economic Relations Division (ERD), and the Planning Commission to expedite the approval of the TAPP. Several coordination meetings are organized with DoE, CPP, BWDB and ERD. UNDP coordinated with DoE, CPP, and BWDB to sign MoUs to ensure collaboration in the future to implement the project’s interventions. Due to the proactiveness of UNDP, the TAPP is approved later on by the government. Secondly, there was a risk that vulnerable and marginalized groups could be excluded during the beneficiaries selection process, especially for housing interventions. To mitigate the risk the project organized community-level consultation meetings where local community people identified the vulnerable and women-headed households in their villages. Project staff physically verified the vulnerability of each and every households and talked with women members of the families.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | No appreciable risk | The involvement of government entities in the selection of adaptation interventions and technical design will ensure that all relevant laws will be considered during project implementation. Once implemented, the monitoring of adaptation interventions will provide a means of tracking their alignment with national laws for the duration of the project. | ** Environmental monitoring indicators and plan for the project will be finalized by an outsourced consultancy firm that will be hired after the approval of TAPP. |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
2 - Access and equity |  |  | The beneficiaries of the proposed project are poor people in vulnerable communities who are often not integrated into decision-making processes. There is, therefore, a risk that certain community members may benefit more than others. This may result in both intra- and inter-community conflicts. | This risk will be mitigated through the beneficiary selection approach (Annex 14_A), and the incorporation of community consultation for all interventions that do not achieve complete coverage of the target populations. Furthermore, both beneficiary and non-beneficiary communities will be sensitised towards the approach of prioritising the support from the proposed project to the most vulnerable communities. A grievance mechanism (see Annex 14_G) has also been developed to support any community members who feel they are experiencing discrimination. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
3 – Marginalized and vulnerable Groups |  |  | There is a risk that vulnerable and marginalised groups will be excluded during the implementation of project activities and have insufficient access to the associated benefits. | The proposed project has been designed to ensure that marginalised and vulnerable groups – especially women and people living with disabilities – will not be adversely affected by, but will instead benefit from, relevant climate change adaptation activities. Community consultations have been incorporated for all activities that do not achieve complete coverage of the target population. This will allow for the identification of marginalised and vulnerable households. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
4 – Human rights |  |  | No activities are, or will be, included in the design of the proposed project that are not in line with established international human rights. Moreover, the proposed project will promote the fundamental human rights of access to food, water and information | The project seeks to ensure that benefits of the project are shared broadly in a non-discriminatory, equitable manner through participatory processes and transparent selection criteria. Extensive stakeholder consultations were held during project preparation (Appendix A) and will be continued throughout project implementation. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
5 – Gender equality and women’s empowerment |  |  | The proposed project is targeting communities where men occupy the majority of the leadership positions. There is, therefore, a risk that women will not benefit equitably from the proposed project’s climate change adaptation and capacity-building interventions. | Gender equity and women’s empowerment were considered across all relevant design aspects of the proposed project and gender equity will be adhered to throughout the implementation period. To this end, a gender assessment was conducted during the development of the proposal to ensure that gender considerations were fully considered during project design (see Annex 12). In particular, equal rights, responsibilities, opportunities and access of women to the benefits of climate change adaptation have been considered. For example, project activities that target the most vulnerable community members (Activities 2.1.1. and 3.2.1.) are prioritised towards women-led households. For technical assessments, as well as capacity-building activities, women will be strongly encouraged to participate. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
6 – Core labour rights |  |  | Local communities will be involved in the implementation and maintenance of climate change adaptation interventions. Therefore, local community members may be exposed to the risk of accidents while implementing the proposed project’s climate change adaptation interventions | During implementation, the National Project Steering Committee and Management Units will ensure respect for international and national labour laws and codes, for any work that may be carried out in relation to the project. This includes the eight International Labour Organisation Convention (ILO) core labour standards related to fundamental principles and rights of workers, as well as ILO Convention No. 169, which concerns rights of indigenous and tribal peoples. Prioritisation of women participation may be used to provide fair and equal opportunity for women to seek employment as labourers. All forms of negative discrimination in respect of employment and occupation will be eliminated. The proposed project will not engage in child labour in any of its activities. All forms of forced or compulsory labour will be eliminated. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
7 – Indigenous peoples |  |  | No appreciable risk | No mitigation necessary.
8 – Involuntary resettlement |  |  | There is a low risk that houses have been constructed in areas that conflict with the infrastructure interventions under Component 2 (Specifically Output 2.1). This may result in temporary resettlement while infrastructure interventions are completed. | The project will ensure that in-depth consultations are conducted with any households that may be at risk of requiring resettlement. The possibility of involuntary resettlement has been considered for the repair of embankments and a resettlement policy has been prepared for this possibility (see Annex 11). Any involuntary relocation or resettlement will only be conducted after extensive community consultation and negotiation with any affected households. Benefits including reimbursement for the cost of the house, further livelihood support and provisioning of new land will all be included in any negotiated package. A grievance mechanism has also been developed (see Annex 14_G) and will be in place to address any concerns of affected community members. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
9 – Protection of natural habitats |  |  | On-the-ground adaptation interventions (specifically EbA) will include the planting of species for enrichment and/or restoration of ecosystems. This could lead to long-term alteration of natural habitats in terms of species assemblages and structure, which may result in various disturbances and negative environmental impacts. Adaptation interventions involving hard infrastructure will also be constructed – for example, the rehabilitation of damaged embankments (Activity 2.1.2.). Such interventions may result in the disturbance of small areas of natural habitat. | The promotion of EbA interventions through the proposed project is more likely to result in the restoration, improved management and protection of natural habitats, as well as the strengthened supply of ecosystem goods and services. To ensure that this principle is adhered to, the consultation with and inclusion of relevant stakeholders (community and authority level) during project design and implementation is prioritised. All necessary impact assessments will be conducted before the implementation of interventions. Furthermore, all national environmental laws will be respected during the selection and implementation of adaptation interventions. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
10 – Conservation of biological diversity |  |  | There is a low risk that adaptation interventions involving the construction of hard infrastructure – for example, the rehabilitation of damaged embankments (Activity 2.1.2.) could negatively impact biodiversity. | The project will ensure the conservation and sustainable use of biological diversity factors are considered in the process of finalising adaptation interventions. Adaptation intervention sites (specifically under Activity 2.1.1.) will be selected using a participatory approach and input from an environmental expert to ensure that activities do not cause significant loss of biological diversity. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
11 – Climate change |  |  | No appreciable risk | No mitigation measures necessary
12 – Pollution prevention and resource efficiency |  |  | No appreciable risk | No mitigation measures necessary
13 – Public health |  |  | No appreciable risk | No mitigation measures necessary
14 – Physical and cultural heritage |  |  | No appreciable risk | No mitigation measures necessary
15 – Lands and soil conservation |  |  | Risks have been identified that are associated with the grey infrastructure interventions (Output 2.2.). These interventions include raising houses on plinths, repairing flood protection embankments and the construction of dual-purpose cluster house/storm shelters. | The project will ensure that all relevant environmental codes and standards will be followed during the design and construction of the grey infrastructure interventions. To comply with both national legislation and the Environmental and Social Principles of the Adaptation Fund, it is recommended that a comprehensive ESIA is undertaken at selected sites and an EMP commensurate with the identified impacts is developed prior to the construction of any greyinfrastructure. |  |  | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started | Not applicable as the implementation of the project has not started
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As the TAPP has not yet been approved, implementation has not been initiated. So no action has been taken
Have the implementation arrangements been effective during the reporting period? |  | As the TAPP has not yet been approved, implementation has not been initiated. So no action has been taken
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | As the TAPP has not yet been approved, implementation has not been initiated. So no action has been taken
Have the implementation arrangements at the EEs been effective during the reporting period? |  | As the TAPP has not yet been approved, implementation has not been initiated. So no action has been taken
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Since project implementation hasn’t started, USPs have not been identified. Once identified, the process ESP compliance will be put in place.
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, some capacity for ESMP implementation exists with the IE and EEs. Additional capacity for ESP compliance will be recruited once project implementation starts, with roles and responsibilities clearly identified and assigned.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Since project implementation hasn’t started, USPs have not been identified. Once identified, the process ESP compliance will be put in place.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 2.1. Climate-resilient mini-disaster shelter/cluster houses built to protect life and prevent asset loss. | Output Level | Number of dual-purpose cluster house/ disaster shelters constructed and in use by women-led beneficiaries households | 0 | 50% | Not applicable as the implementation of the Project has not started.
Output 2.4. Cyclone Preparedness Programme (CPP) modernised and expanded to provide timely cyclone early warning and response at scale. | Output Level | Number of CPP female volunteers trained | 0 | Increase female representation in CPP by at least 25% (out of ~2,500 CPP volunteers trained in Mujibnagar ) | Not applicable as the implementation of the Project has not started.
Output 3.1 Climate-resilient agriculture implemented | Output Level | Number of female trained in climate-resilient agricultural practices | 0 | Include at least 25% female representation, but aim is for a minimum of 50% in 64 field school trainings held in Mujibnagar and Lakshmitari. | Not applicable as the implementation of the Project has not started.
Output 3.2 Diversified livelihoods supported at the village level. | Output Level | Number of female beneficiaries provided with technology, skills and materials to make their livelihoods climate resilient | 0 | Minimum 50% female beneficiaries out of ~6,500 people provided with technology, skills and materials to make their livelihood climate resilient. | Not applicable as the implementation of the Project has not started.
Output 4.2. Knowledge and awareness generated to promote climate resilient approaches and strategies | Output Level | Number of women reached by awareness-raising campaigns | 0 | Minimum 50% women population out of 75% of the population in the target areas reached by awareness campaigns | Not applicable as the implementation of the Project has not started.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | As the TAPP has not yet been approved, implementation has not been initiated. So no action has been taken
Have the implementation arrangements at the IE been effective during the reporting period? |  | No
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | As the TAPP has not yet been approved, implementation has not been initiated. So no action has been taken
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | No
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1) Community infrastructure improved, and adaptive capacity increased for the vulnerable small island and riverine char communities to manage and plan for climate change impacts; |  | Outcome 4 | At the end of the Project, 900 climate-resilient houses will be strengthened for cyclone & storm surges, 500 HHs provisioned with rainwater harvesting system and 30 solar nano-grids installed for 300 – 450 houses. |  | As the TAPP has not yet been approved, implementation has not been initiated. However, ToR is developed to hire Architect, Civil Engineer, and other National Consultants for assessment. RFPs are developed for hiring firms for retrofitting houses, establishing nano-grids, and RWHS. | Unsatisfactory (U)
| 2) Resilience of vulnerable small coastal island communities enhanced against climate-induced disasters through improved infrastructure, management practices, and community-based emergency responses; |  | Outcome 1 | At the end of the Project, 20 dual-purpose cluster houses will be constructed, 12.5 km of embankments repaired and strengthened; 8 climate hazard and vulnerability maps produced; 12,500 CPP volunteers trained and 7 islands equipped with CPP equipment; 8 mobile floating medical units provisioned. |  | As the TAPP has not yet been approved, implementation has not been initiated. However, several meetings were organized with Cyclone Preparedness Programme (CPP) and Bangladesh Water Develop Board (BWDB) and drafted MOUs. Identify the weak and damaged portions of the embankments, developed detailed costing for re-sectioning embankments and irrigation pipe outlets, and finalize all designs in collaboration with BWDB and DoE. Identified CPP volunteers for capacity development, and prepared a detailed implementation plan and budget for CPP equipment and volunteer capacity development. | Unsatisfactory (U)
| 3) Adaptive capacity of vulnerable communities improved through the dissemination of climate-resilient agricultural practices and the development of diversified livelihoods; |  | Outcome 6 | At the end of the Project, 6500 people provided with climate resilient livelihoods; 64 field school trainings conducted; 4 solar cold storage units installed; and 80 hectares of land irrigated through 6 solar irrigation pump. |  | As the TAPP has not yet been approved, implementation has not been initiated. However, a desk review was conducted to identify alternative livelihood options. ToR is developed to hire Livelihood Consultants to identify climate-smart innovative livelihood options that will be suitable considering local, social, economic, ecological, and climatic conditions and will be accepted by the local communities. Organized discussion with the Department of Agriculture (DAE) to learn lessons from other livelihood projects in the different agro-ecological zone of Bangladesh | Unsatisfactory (U)
| 4) Increased awareness and availability of information on climate change impacts and adaptation options for vulnerable communities, local-level government, and policymakers. |  | Outcome 3 | At the end of the Project, 250 government staff will be trained to incorporate climate risk into their operational activities; 4 adaptation innovation & learning centres established; 75% of the population in the target areas reached by awareness campaigns; 10 manuals and brochures developed on CCA, resilient livelihood, climate-smart agriculture etc. |  | As the TAPP has not yet been approved, implementation has not been initiated. However, some knowledge products, reports, case studies etc. of other climate-adaptation projects of UNDP and GoB are reviewed. | Unsatisfactory (U)
[6 empty] | Overall Rating | Unsatisfactory (U)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Arif Mohannad Faisal
| Email: | arif.faisal@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Although the inception workshop was held on 29 June 2021, project implementation has been delayed due to the protracted government approval process of the Technical Assistance Project Proposal (TAPP) which is a mandatory government requirement for all development projects in Bangladesh. The TAPP approval process for the project has been delayed due to pending results of (i) the assessment of possible duplication of activities with the low-cost housing project (Asrayon/housing project) led by the Prime Minister's Office, (ii) the assessment of possible duplication of repair and maintenance work of embankments at Mujib Nagar by the Bangladesh Water Development Board (BWDB) (iii) the redesign of TAPP documents and revision of project budget in line with feedback provided at the SPEC meeting on 3 March 2022. All these tasks have unfortunately experienced delays due to Covid-19 and associated post-Covid activities that the government has had to attend to. In the meantime, UNDP has revised the TAPP and project budget according to the recommendations of the SPEC meeting and shared it with the Department of Environment (DoE). At DoE's request, UNDP arranged a field mission in Bhola and Rangpur (project site) to assess interventions on embankments and to secure no-objection from the Bangladesh Water Development Board (BWDB). According to the recommendations of the Planning Commission, DoE has taken initiative to sign a Memorandum of Understanding (MoU) with the Cyclone Preparedness Programme (CPP) and BWDB. The project has developed the MoUs and DoE has already shared both MoUs with the Secretary, MoEFCC for concurrence and endorsement. Once signed, both these MOU’s will be included in the TAPP and thereafter DoE is expected to submit the revised TAPP to the Planning Commission by September 2022. Since the project budget is US$ 9.2 million, the TAPP has to be approved by the Executive Committee of the National Economic Council (ECNEC), chaired by the H.E. Prime Minister. While waiting for TAPP approval, the project has already initiated preparatory work including the development of the terms of references (ToRs) and procurement documents to engage individual consultants and firms to implement the project's proposed activities, e.g., climate-resilient housing, solar nano grid, rainwater harvesting system, solar cold storage, cluster houses, and alternative livelihoods support. In addition, the project is also readying itself for other activities, e.g., verification of socio-economic baseline information in project sites, selection and identification of project beneficiaries, climate risk and vulnerability assessment of project sites, needs assessment of beneficiaries for housing, water supply, and energy for lighting and cooking, selection of potential alternative livelihoods support and analysis of market systems, etc. Based on the above reasons, an implementation rating of 'Unsatisfactory' is assigned. Once the TAPP is approved, the project hopes to fast-track implementation and catch up on the time lost in the first year.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator:
Note: Bangladesh Government can't recruit National Program Director (NPD) for any development project until the approval of the TAPP. So the NPD for this project is not yet recruited by the Ministry of Environment, Forest and Climate Change (MoEFCC). Therefore the Rating and Justification by the Executing Entity is not written here and is not applicable.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective Level | Enhanced climate resilience of vulnerable communities in the Mujibnagar and Lakshmitari Unions. | TBD; preferably vulnerability index method; |  | Lower vulnerability
Outcome 1: Enhanced climate resilience of households through climate resilient housing, electrification and climate-proof water provisioning | Number of households with increased resilience through strengthened houses, electrification and water provisioning. |  |  | Strengthened houses 900 nos; HHs with electricity 300-450; 500 HHs provisioned with rainwater
Output 1.1 Cyclone and flood resilient houses for the most vulnerable households. | 1.1.1: Number of houses made resilient against climate disasters (cyclones and floods) | 0 | A ToR is developed to hire a Civil Engineer to prepare the Bill of Quantities (BoQ), detailed design, and other estimations of the civil works. | 900 houses retrofitted in Mujibnagar and Lakshmitari
Output 1.2 Community-level nano-grids installed for electrification to enhance adaptive capacity | 1.2.1: Number of nano-grids installed and operational. | 0 | A ToR is developed to hire national consultant to provide technical support for establishing solar nano-grid, solar irrigation pumps, and solar cold storage | 30 nano-grids; 300 to 450 HHs covered under each grid
Output 1.3 Locally appropriate rainwater harvesting systems for safe drinking water. | 1.3.1: Number of household rainwater harvesting systems installed and operational. | 0 | A ToR is developed to hire a national consultant to determine the households' drinking water demand and design a locally appropriate Rainwater Harvesting System. | 500 units
| 1.3.2: Number of water user groups established and trained. | 0 | 0 | 10 water user groups
Outcome 2: Increased climate resilience of communities through infrastructure that is resilient to cyclones and floods, climate risk mapping and inclusive cyclone preparedness | Number of people with increased resilience through strengthened disaster infrastructure. |  |  | TBD (# of people covered by the cluster houses and embankments)
Output 2.1 Climate-resilient mini-disaster shelter/cluster houses built to protect life and prevent asset loss. | 2.1.1 Number of dual-purpose cluster house/ disaster shelters constructed and in use. | 0 | A ToR is developed to hire an Architect to design cluster houses and adaptation learning centers | 16 nos cluster house; 50% women beneficiary
Output 2.2 Embankments repaired and innovative model for community embankment management | 2.2.1 Km of damaged embankments repaired/ strengthened. | 0 | Meeting and field mission organized with DoE and BWDB to select the location of damaged embankment | 12.5 km of embankments repaired in Mujibnagar
| 2.2.2 Km of riverbank strengthened. | 0 | A ToR is developed to hire a consulting firm to develop an environmental management plan and conduct environmental monitoring. | 14.5 km of riverbank strengthened in Lakshmitari
| 2.2.3 Number of community embankment management groups established | 0 | 0 | 3 community embankment management group will be established at each project site.
Output 2.3 Climate-resilient investment on chars promoted through climate hazard maps and expanded cyclone early warning systems. | 2.3.1 Km2 of char areas mapped | 0 | A ToR is developed to hire a consultancy firm to develop hazard and vulnerability maps | 8 climate hazard and vulnerability maps
| 2.3.2 Number of households in Mujibnagar receiving periodic updates during cyclone risk periods | 0 | 0 | All HHs of Mujibnagar
Output 2.4 Cyclone Preparedness Programme (CPP) modernised and expanded to provide timely cyclone early warning and response at scale. | 2.4.1 Number of CPP volunteers trained | 0 | A meeting was organized with CPP to assess the current training needs of the volunteers. | ~2,500 CPP volunteers trained in Mujibnagar (increase female representation in CPP by at least 25%) 10,000 CPP volunteers trained on six additional islands (5000 CPP trained by mid term)
| 2.4.2 Existing cyclone shelters in Mujibnagar provisioned with CPP equipment | 0 | 0 | 7 existing cyclone shelters (3 cyclone shelters completed by mid-term) and 16 cluster houses (7 houses completed by mid-term) provisioned with CPP equipment in Mujibnagar. ~2,500 CPP volunteers provided with personal cyclone preparedness equipment (50% by mid-term) 8 mobile floating medical unit procured and provisioned (4 nos by mid of project) 6 additional islands equipped with CPP Equipment (3 islands by mid-term)
Outcome 3: Improved income and food security of communities by innovating and providing assistance to selected households for climate resilient livelihoods practices | Number of people with provided with improved climate resilient livelihoods; |  |  | ~6,500
Output 3.1 Climate-resilient agriculture implemented and supported at a community level | 3.1.1 Number of field school sessions held; | 0 | 0 | 64 field school sessions
| 3.1.2 Number of people trained in climate-resilient agricultural practices; | 0 | 0 | 7500 farmers trained; % of female minimum 25; target 50
| 3.1.3 Number of cold storage units installed and operational; | 0 | 0 | 4 (2 unit in Mujibnagar and 2 unit in Lakshmitari)
| 3.1.4 Hectares of agricultural land irrigated; | 0 | 0 | 80 ha
Output 3.2 Diversified livelihoods supported at the village level. | 3.2.1 Number of people provided with technology, skills and materials to make their livelihoods climate resilient. | 0 | A ToR is developed for Livelihood Specialists to conduct a needs assessment and develop alternative livelihoods | 6500 people (minimum 50% female beneficiary)
Outcome 4: Enhanced knowledge and capacity of communities, government and policymakers to promote climate resilient development on chars. | Number of people reached by knowledge products and awareness raising | 0 |  | TBD
Output 4.1. Local government institutions are capable of climate risk-informed planning and implementation. | 4.1.1 Number of staff from local government institutions, Bangladesh Water Board and Department of Agriculture trained. | 0 | 0 | 250 persons (% female) by LGIs
Output 4.2. Knowledge and awareness generated to promote climate resilient approaches and strategies | 4.2.1 Number of adaptation innovation centres established | 0 | 0 | 4 centers (2 in each project locations)
| 4.2.2 Number of people reached by awareness-raising campaigns | 0 | 0 | 75% of the population in the target areas (minimum 50% women).
| 4.2.3 Number of knowledge products developed | 0 | Two flyers or Project briefs are developed for different stakeholders | 10 products by types

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Delay in the Government's approval of the Technical Assistance Project Proposal (TAPP) - which is a mandatory government requirement for all development projects in Bangladesh. The Project TAPP experienced delays due to Covid-19 and associated post-Covid activities that the government has had to attend to. So the project couldn't start implementation of field activities after the Inception workshop which result in a significant delay in Project implementation and a low financial burn rate.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | UNDP Bangladesh is closely following up with the implementing ministries, Economic Relations Division (ERD), and the Planning Commission to expedite the approval of the TAPP. Several coordination meetings are organized with DoE, CPP, BWDB and ERD. MOU and meeting minutes for CPP and BWDB are finalized. As per government procedures, the implementation of a NIM project is not allowed until the approval of TAPP. While waiting for TAPP approval, the project has already initiated preparatory work including the development of the terms of references (ToRs) and procurement documents to engage individual consultants and firms to implement the project's proposed activities, e.g. climate-resilient housing, solar nano grid, rainwater harvesting system, solar cold storage, cluster houses, and alternative livelihoods support. So once the TAPP is approved, the project will implement all activities in full swing.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The length of damaged embankments for repair and strengthening is finalized based on the current situation of the embankment and the demand of BWDB. Also, the selection of CPP volunteers for capacity building, training topics, and equipment lists is finalized based on the current demand for CPP. The installation sites of solar nano-grid and RWHS in two Unions will be decided based on the real demand of the community and beneficiaries households.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | A firm is yet to be engaged to develop an environmental/social management and environmental monitoring plan (safeguards support) for the project.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Women prefer to take decisions jointly with their husbands for resettlement of the households during retrofitting of their climate-vulnerable houses
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | No lesson learned as the implementation of the project is not started
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A, as the project has not started implementation
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A, as the project has not started implementation
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A, as the project has not started implementation
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A, as the project has not started implementation
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A, as the project has not started implementation
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A, as the project has not started implementation
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A, as the project has not started implementation
What measures are being/could have been put in place to improve project/program results? | N/A, as the project has not started implementation
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Knowledge management and dissemination systems of the Project are not established yet as the Project team is not fully recruited.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Yes, during design, project validation workshop and inception workshop. As project starts implementation, result will be disseminated through various channels, including websites, social meda channels, facebook, twitter, etc
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A, as the project has not started implementation
If learning objectives have been established, have they been met? Please describe. | N/A, as the project has not started implementation
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A, as the project has not started implementation
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A, as the project has not started implementation
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The innovative practices are yet to be pilot or tested in the project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
UN | United Nations Development Programme (UNDP)
Type of implementing entity | NIE
Country | Bangladesh
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 372000 | 31000 | 341000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 52% | 56% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 40% | 39% | 40% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 1: Risk knowledge | Geographical coverage | Local | 3 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 3 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 20 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Local | 4 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Salinization | No. of adopted Early Warning Systems | Category targeted | Hazard | Salinization | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 4: Response capability | Geographical coverage | Local | 4 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Health | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Health | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha protected | 2: Partially effective | Cultivated land/Agricultural land | 100 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Livestock production |  | 0 | 200 | Livestock production |  | 7500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 0 | 200 | Agriculture |  | 4500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Handicrafts |  | 0 | 25 | Handicrafts |  | 28125
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Trading |  | 0 | 200 | Trading |  | 12500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related |  | 0 | 200 | Agricultural-related |  | 37500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | other |  | 0 | 25 | other |  | 62500
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note: As the TAPP of the Project is not approved yet by the Government, so all PMU staff was not recruited and implementation was not started. So M&E data was not collected.