MONITORING REPORT SUBMITTED SIX MONTHS AFTER PROJECT START AND EVERY SIX MONTHS AFTER THE LAST MONITORING REPORT

Date of Submission: 04 February 2022

Monitoring Report Number e.g., First Report, Second Report etc.:

Implementing Entity: NABARD

Country: Afghanistan/India

Adaptation Fund Grant I.D:

Grant Type: S-S Cooperation Grant

Project Description/Project Title: Accreditation of NIE in Afghanistan through the South-South Cooperation Grant of the AF

Project Sector: peer-peer support, knowledge and learning

| Activity | Expected Output | Progress (include completion Date “month & year”) | Comments/Explanation (also explain any deviation from initial plan) |
| --- | --- | --- | --- |
| Submission of Detailed Action Plan to NEPA (DA in Afghanistan) | Action plan including process & timelines for accreditation | Completed Aug, 2019 | Post the commencement of project and kick-off meeting with NEPA (DA in Afghanistan), detailed action plan highlighting the process and timelines submitted |
| Constituting a Consultative Group for the NIE accreditation process in Afghanistan | The consultative group is responsible for establishing national mandate for accreditation process, required approvals | Completed Oct, 2019 | Consultative Group comprises of representatives from the Designated Authorities to AF (NEPA), Ministry of Environment, Planning Commission, Finance Ministry and Key ministries of the Afghanistan Govt. |
| Identifying potential NIEs in Afghanistan & forwarding the list of the potential NIEs to NABARD | List of Potential NIEs received from Afghanistan | Completed Oct, 2019 | Delay from NEPA in submitting the names of potential NIEs in Afghanistan for accreditation |
| Preparation of EOI template based on AFB Accreditation Standards | EOI template for submission of information by potential NIEs | Completed Oct, 2019 | EOI template based on the AFB standards and requirements submitted to NEPA to be filled from potential NIEs |
| Submission of EOI along with required documentation by potential NIEs in Afghanistan to NABARD | Filled EOI along with documents received from potential NIEs | Completed March, 2020 | Delay from NEPA in submitting the EOI documentation to NABARD |
| Scrutiny and Review of the EOI submitted by the potential NIEs | Identifying suitable potential NIEs based on EOI | Completed March, 2020 | Based on EOI & documents submitted, four potential NIEs shortlisted for further process |
| Submission of documents by four potential NIEs based on AFB standards | For shortlisting suitable NIE in Afghanistan | Completed November, 2020 | Delay from NEPA in submitting the documentation from four potential NIEs |
| Scrutiny and Review of the documents submitted by the potential NIEs. | Shortlisting of NIE based on the documents submitted | Completed January, 2021 | Based on the documentation, one NIE to be shortlisted from four potential NIEs |
| Organising a Workshop in Afghanistan with the Shortlisted NIE for accreditation | Overview of Accreditation Process & Presentations from Potential NIEs for suitability | Completed June & July, 2021 Further steps delayed due to Civil Unrest in Afghanistan | The workshop was supposed to be organized in Afghanistan. However, due to Covid-19, it was delayed and finally through mutual agreement has been conducted virtually NIE Selection Report submitted to NEPA. |
| DA of Afghanistan to provide Nomination letter in favour of the identified NIE to enable it to submit on-line application for accreditation. | Endorsing NIE for accreditation process by DA in Afghanistan | Ongoing | Endorsement letter for shortlisted NIE to be received from DA in Afghanistan. Further steps have been delayed due to unrest in Afghanistan |
| Training & Capacity building of the identified NIE for the accreditation process | Requirements for application for accreditation to AFB | To be initiated |  |
| Visit of selected NIE representatives to ongoing AF projects in India & meeting with concerned officials in India | Training & Capacity building of NIE for accreditation process | To be initiated |  |
| Compilation of documentation required for accreditation | Required documentation for application to AFB | To be initiated |  |
| Submission of application to the Adaptation Fund Board | As per the AFB application system | To be initiated |  |
| Completion of Accreditation Process | Based on the feedback on application form submitted & completion of the process | To be initiated |  |
| Overall comment on progress | Some of the activities have been delayed due to the delay in submission of documentation from potential NIEs. Delays has also happened due to the current pandemic situation of Covid-19 and Civil Unrest in Afghanistan. Workshop in Afghanistan was scheduled in March 2020, but could not be conducted due to the pandemic situation. The workshop has been conducted virtually in June 2021 and NIE Selection report submitted to NEPA in July 2021. However, endorsement letter is yet to be received from NEPA, Afghanistan to move ahead in the application process. |  |  |
| New completion date or Expected completion date | The process of shortlisting has been completed and report submitted to NEPA, however due to Civil unrest, the process has been delayed. Expected Completion date can be June 30, 2022 post submission of endorsement letter by DAE in Afghanistan. |  |  |

Contact Person: Dr. Surendra Babu, General Manager			Email: climate.change@nabard.org; surendra.babu@nabard.org