- COMPLETION REPORT SUBMITTED NOT MORE THAN SIX MONTHS AFTER PROJECT COMPLETION

Date submitted to AFB secretariat:

Implementing Entity: Environmental Projects Implementation Unit SA- EPIU

Country:  Armenia

Adaptation Fund Grant I.D:

Grant Type: TA-ESGP

Project Description/Project Title: [Project to support National Implementing Entity sourcing of Technical Assistance for Assessment and management of Environment, Social and Gender Risks within Projects and Programmes in Armenia]

Project Sector: Institutional capacity building

| Activity | Expected Outcome | Outcome Achieved/Not Achieved | Comment/Explanation (also explain any deviation from initial plan) |
| --- | --- | --- | --- |
| Development of procedures/manuals/guidelines for screening projects that cover environmental and social and gender related risks, for undertaking project environmental and social and gender risk assessment, and for formulating risk management plans that are gender responsive. | Development of environmental, social and gender risk screening and assessment guidelines and integrating them to the existing operational manual (publication of guidelines with 100 examples.) | Outcome achieved | Formulated and elaborated manual, which covers the environmental and social and gender responsive risks and assessment guidelines. Includes thorough and detailed analysis regarding the gender-related situation in Armenia |
| Development of policy/avenues for public disclosure and gender responsive consultation | Elaboration of gender responsive, environmental and social Policies for public disclosure | Outcome achieved | Developed dashboard for undertaking project environmental and social and gender risk assessment, and for formulating risk management plans that are gender responsive. The dashboard supports the detection and management of environmental and social risks, and the categorization of projects/programmes according to their potential environmental and social impacts, as well as it guides and supports the systematic screening of proposals and/or funded projects/programmes to ensure that environmental and social risks are adequately identified and assessed by EPIU and its partners in an open and transparent manner |
| Development of transparent, accessible, fair and effective mechanisms for receiving and addressing complaints about environmental or social harms and complaints related to gender inequalities and other adverse gender impacts caused by projects/programs during implementation. | Creation of a relevant grievance mechanism, that addresses environmental and social harms and complains related to gender inequalities as well as other adverse gender impacts caused by projects/ programs during and after implementation | Outcome achieved | Developed project-level grievance mechanism, including grievances relating to gender. Developed transparent, accessible, fair and effective grievance mechanism for receiving and addressing complaints about environmental or social harms and gender inequalities and other adverse impacts caused by projects/programmes during implementation. |
| Training of selected entity staff to carry out the relevant tasks related to the implementation of the Fund's Environmental and Social Policv and the Gender Policy | Organizing corresponding trainings with the staff members | Outcome achieved | Conducted trainings for selected entity staff to carry out the relevant tasks related to the implementation of proposed Environmental and Social Policy and the Gender Policy, Monitoring and Evaluation Framework. |
| Budget | State whether overall expenditure was over or under the planned budget and give brief explanation for deviations of more than 30%. The overall expenditure was right at the planned budget. The overall budget of 19,500 USD was disbursed. |  |  |
| Summary of overall outcome including any challenges faced and how they were resolved, and an explanation of how achieved outcomes will be disseminated or taken forward*. | Overall outcomes: Manual covering the environmental and social and gender responsive risks and assessment guidelines. Developed dashboard for undertaking project environmental and social and gender risk assessment, and for formulating risk management plans that are gender responsive. Developed Gender Policy and Gender Action Plan. Developed Monitoring and Evaluation system, which includes specific methods and tools to monitor project indicators, data collection and M&E system, strategic planning, and the monitoring and evaluation of project activities. Developed project-level grievance mechanism. Conducted trainings for EPIU staff. |  |  |
| Any feedback/general comment to the AFB secretariat |  |  |  |

*If there have been any delays in project implementation that affected project completion dates, state the reasons for the delays.

Contact Person: Koryun Bznuni 							Email: koryun-bznuni@epiu.am