- COMPLETION REPORT SUBMITTED NOT MORE THAN SIX MONTHS AFTER PROJECT COMPLETION

Date submitted to AFB secretariat: February 22, 2023

Implementing Entity: Centre de Suivi Ecologique

Country: Mauritius Island

Adaptation Fund Grant I.D:

Grant Type: S-S Cooperation Grant

Project Description/Project Title: This South-South cooperation grant was requested by CSE to support the Designated Authority of Mauritius to identify a potential NIE candidate and to provide technical assistance to this latter for the preparation and submission of its accreditation’s application.

Project Sector: peer-peer support

Project Completion Date: July 14, 2022

| Activity | Expected Outcome | Outcome Achieved/Not Achieved | Comment/Explanation (also explain any deviation from initial plan) |
| --- | --- | --- | --- |
| 1. Screening exercise, including an information workshop on the AF and the main features of an operational NIE | - Call of interest - Institutions completed the expression of interest form - Screening report - Check-list of key questions addressed during assessment - Presentation and set of slides - Evaluation sheet - NIE nominated | Achieved (February 2020) | CSE prepared and shared a work plan with the Designated Authority (DA). Then, a call for interest was prepared by CSE and launched by the Designated Authority. Four institutions expressed their interest to undertake the accreditation process. The applications have been reviewed by CSE in collaboration with the DA. CSE organized a mission in Mauritius from 1st to 13th of February in order to provide guidance to the DA for the final selection of the best NIE candidate. The Ministry of Environment, Solid Waste and Climate Change (MoESWCC) was selected as NIE candidate. During this mission, a task-force was set up within the selected institution and a road map developed for collecting the supporting documents. |
| 2. Train the NIE on accreditation process, set up a Task Force and elaborate a road map to collect supporting document | - Presentation and set of slides - Road map to collect supporting document | Achieved (February 2020) | Key profiles have been identified to be part of the MoESWCC accreditation task-force for the collection of the supporting documents. The roles and responsibilities of the task-force have been defined and the documents collection began. For the gap noted (the missing documents), a road map was developed. |
| 3. Collecting supporting documents - Collecting and analyzing relevant supporting documents for each performance criteria required in the application form - Review of questions raised by the Accreditation Panel during previous applications submitted with CSE support (to better understand the expectation) - Preparing and sharing a note on accreditation standards (to better understand what is expected), using the AF’s guidance document on its accreditation standards | - List of supporting documents / information collected - Summary of previous questions raised by the AF panel and the Board to applicants during accreditation process - Note on accreditation standards | Achieved (June 2021) except the “Summary of previous questions raised by the AF panel and the Board to applicants during accreditation process” | Many documents have been collected. The roadmap has been completed and share it to the Mauritians colleagues .However, due to the coronavirus pandemic, delays have been noted and CSE could not undertake any mission in Mauritius. At one point, there was no more interaction due to the situation mentioned above. However, the process was revived through meetings via Zoom involving CSE experts and the Task Force set up within the MoESWCC. |
| 4. Review of the adequacy of all required back-up documentation to ensure it meets the requirements of the AF accreditation panel and filling gaps - Checking the documents collected against AF requirements - Identifying potential gaps or weaknesses - Providing guidance on how to overcome issues identified - Supporting the task-force in organizing supporting documents | -Supporting documents check-list including a brief description of AF requirements - Documentation of the main findings | Achieved (June 2021) | The review of the adequacy of the required documentation have been done by CSE ’experts on all documents sent by the MoESWCC. |
| 5. Translation of supporting documents | Supporting documents in English | Not applicable | Mauritius is an English-speaking country; documents are available in English. |
| 6. Submission of the application folder | - An application for accreditation as a NIE - A one-page summary report | Achieved (July 2022) | Initially, CSE did not have access to the system to support the MESWCC during the submission phase. In order to continue the support as indicated in the contractual clauses with the AF, a request was made by CSE to the MESWCC focal point to have access to the connection parameters and thus to the accreditation portal. This allowed CSE to verify compliance and subsequently advice was given to the Task Force in charge of submitting the documents in the system. Finally, the application was submitted on July 14, 2022 by the MoESWCC. |
| 7. Responding to AP comments |  | Not started yet | The accreditation file has been submitted but interactions with the Accreditation Panel have not yet started. |
| Budget | State whether overall expenditure was over or under the planned budget and give brief explanation for deviations of more than 30%. Expenditures were in line with the budget. There was no overrun between the planned budget and actual expenditures. However, the project took longer than expected due to the covid 19 pandemic, so the second planned mission was not held. In fact, part of the remaining amount was used for the purchase of the Zoom license to hold the meetings with MoESWCC colleagues and the other part was used as additional staff time of CSE experts involved in the project. |  |  |
| Summary of overall outcome including any challenges faced and how they were resolved, and an explanation of how achieved outcomes will be disseminated or taken forward*. In the case of the South-South Cooperation Grant and Readiness Package Grant, please state whether the entity was accredited? If not, then what challenges remain and how can they be resolved? | Overall, this Readiness support allowed MoESWCC to follow all stages of the accreditation process through to submission. From upgrading the task force team in charge of piloting within the institution, collecting existing documentation, developing new documents on the governance framework and business procedures. The process was very informative for both institutions despite the coronavirus pandemic that slowed the momentum of the project. In this context, alternatives had to be found to continue the support. Thus, Zoom sessions were regularly organized to maintain the pace and boost the Mo ESWCC team because the response time was too long. Given the commitment of the CSE in its South-South cooperation strategy, a call via Zoom was organized with the focal points of the MESWCC in order to make them aware of the functioning of the platform and the process of uploading documents. Then, the MESWCC focal points uploaded the documents into the system. A review was conducted by the CSE to provide guidance and recommendations to the MESWCC focal points on certain issues. Once these recommendations were implemented, a final review was conducted by CSE to validate and provide a no objection to the submission of the accreditation application. After consultation and approval by MoESWCC management, the accreditation application was submitted to the Adaptation Fund on July 14, 2022. The accreditation application has been submitted, but interactions with the accreditation panel have not yet started. However, CSE has committed to providing its services in terms of support and advice to MoESWCC during interactions with the Accreditation Panel to address comments. The final takeaway from this process is that the motivation, commitment, and responsiveness of the applicant will determine the quality of the applicant submission. |  |  |
| Any feedback/general comment to the AFB secretariat | The project completion date was set on June 2022 as recorded in the last progress report sent to the AFB secretariat, however it was only in July that the MoESWCC submitted its accreditation application, therefore CSE remains committed to following the process. |  |  |

*If there have been any delays in project implementation that affected project completion dates, state the reasons for the delays.

Contact Person : Aïssatou Boubou Sall Sylla                                                                    Email : aissata.sall@cse.sn

Head of Climate Finance Unit, Centre de Suivi Ecologique

N°105 Rue Léon Gontran Damas, FN22 Fann – Dakar

BP: 15 532 Dakar – Fann

Tel: +221 33 825 80 66 / +221 33 825 80 67 - Mob: +221 77 685 15 90