## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 04/03/2022 - 18/03/2023
| Project Title: | Bunda Climate Resilience and Adaptation Project
| Project Summary: | The project seeks to develop and implement concrete adaptation actions at grassroot levels to increase community livelihood reseilence to climate change effects in Bunda District through concrete and practical cost effective and mult-stakeholders climate adaptation interventions. In particular, the project aims to improve livelihoods of the poor and vulnerable communities by achieving the following objectives: i) Enhance climate resilience for improved access to rural water supply system in selected drought prone agro-pastoral communities. ii) Improve agricultural productivity, livelihood and agro-ecosystem resilience through Climate Smart EVA practices. iii) Promote paradigm change of small-scale fishers for sustainable income and climate resilient rural livelihood through aquaculture innovations in selected villages. iv) Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods in selected rural communities. v) Strengthening institutional capacity and knowledge management on climate change adaptation.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Environment Management Council | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2021-10-07
IE-AFB Agreement Signature Date: |  | 2021-10-13 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2022-03-04 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2025-03-04
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Johanes Agumba Bucha | Dominican Republic
| Email: | jbucha2003@yahoo.co.uk | Ecuador
| Date: | 2023-03-18 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Switbert Mukama | Equatoral Guinea
| Email: | switbert.mukama@vpo.go.tz | Eritrea
| Date: | 2023-05-02 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Fredrick Mulinda | Fiji
| Email: | nieaf@nemc.or.tz | Finland
| Date: | 2023-04-25 | France
| Executing Agency |  | Gambia
| Name: | Changawa Mkwazu | Georgia
| Email: | ded@bunda.go.tz | Germany
| Date: | 2023-03-18 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 4 March 2023 |  |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 4/03/2023 | 786269 |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | NIL |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Climate resilient rural water supply system established in selected drought prone agro-pastoral communities | 386011.58
| Output 1.2 Community Based Water Supply Organizations established and trained on their functions | 7255.42
| Output 2.1 Climate smart EVA practices to improve food security through small scale and micro-irrigation schemes enhanced in selected villages | 116602.13
| Output 3.1 Traditional fishing practices transformed for improved climate resilient livelihood and sustainable income generating activities in selected villages. | 99701
| Output 4.1 Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods in selected rural communities. | 51345
| Output 5.1 Capacity of the district and communities in Bunda is strengthened to respond to extreme weather events. | 15105
| EXECUTION FEE | 60248.87
| IMPLEMENTING ENTITY FEE | 50000
| TOTAL | 786269
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | ESTIMATED COMPLETION DATE | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Climate resilient rural water supply system established in selected drought prone agro-pastoral communities | 78890.37 |  | 2024-10-30
| Output 1.2 Community Based Water Supply Organizations established and trained on their functions | 4518.84 |  | 2024-11-30
| Output 2.1 Climate smart EVA practices to improve food security through small scale and micro-irrigation schemes enhanced in selected villages | 128243.37 |  | 2024-11-30
| Output 3.1 Traditional fishing practices transformed for improved climate resilient livelihood and sustainable income generating activities in selected villages. | 27413 |  | 2024-09-30
| Output 4.1 Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods in selected rural communities. | 58424 |  | 2024-09-30
| Output 5.1 Capacity of the district and communities in Bunda is strengthened to respond to extreme weather events. | 14111 |  | 2024-08-31
| EXECUTION FEES | 30000 | 2023-11-24 | 2024-11-30
| IMPLEMENTING ENITY FEE | 30000 | 2023-11-25 | 2024-11-30
| TOTAL | 371600.58 |  | 2024-11-30 | [5 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Competing interests between different stakeholders regarding accessing and use of project benefits and related resources | Low | Educating the stakeholders about the project objectives and expected outputs
Local communities with limited participation and willingness to promote project initiatives | Low | Not experienced so far. The communities participate in project activities
High expectations for quick investments on the ground and resources beyond the available project resources | Low | Awareness raising about the project objectives and expected outputs
Project financial management | Low | Risk not experienced so far
Delay in project implementation due to government bureaucracy, long and inefficient procurement processes | Low | Seeeking early approval of the procurement plan and early announcement of the tenders
Limited Stakeholders Involvement | Low | Risk not experienced so far
Low adoption rate of proposed innovations and adaptation technologies by communities | Low | Risk not experienced so far
Financial risk | Low | Risk not experienced so far
Conflict Management | Low | Risk not experienced so far
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The main risk mitigation measure employed by the project during the current reporting period , was awarness raising on the project notably its objectives and expected outputs. This has been effective in managing high expectations of some of project beneficiairies who expected the project to solve every problem in the community

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | According to the National Environmental Management Act (2004) and the Environmental Impact Assessment (EIA)and Environmental Audit (EA)Regulation (2005) and Sectorial Regulations and Guidelines of the United Republic of Tanzania, most of the components/activities of the proposed project do not fall within the First Category of projects that require full EIA. There is no activity under any component which require full EIA as their size are small and location of the interventions to do not require further assessments. However, where some activities are not fully itemized there might be a risk that such activities will not comply with certain laws. | The project activities strongly comply with all relevant national laws including international standard).They do not conflict with any domestic laws and policies, but they strongly support implementations of those laws and policies as indicated at Part II E of the approved project document | Number of national laws with which the project must comply | Since inception, the project was compliant with Environmental Management Act, 2004 by ensuring that the project activities do not cause any detrimenatl impact to the environment. | Close monitoring and implementation of the Environmental Management Plan | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
2 - Access and equity |  |  | The constitution of the United republic of Tanzania specifies equitable distributions of benefits within communities, and prohibits any actions that promote economic imbalances among citizens and communities. However, some activities of the project, under component 1,2 and 3 for livelihood improvement are not intended to provide a benefit for all, but target those livelihoods in need as well as the livelihoods which are involved in restoration activities, transforming exploitive agriculture, chicken and beekeeping. Also given that the beneficiaries are rural people and marginalized poor families who are not often integrated in the villages politics and decision-making processes, there could be also a risk of insufficient access of the project resources by these people. | The project activities being implemented do not reduce or prevent communities at the sites in all villages from accessing basic health services, clean water and sanitation, energy, education, housing, safe and decent working conditions and land right. Communities and beneficiaries will be highly sensitized to enhance priorities of the most vulnerable communities while ensuring benefits to reach further communities for scaling ups and replications. In addition, measures have been put in place to able this project to closely monitor all targeted beneficiaries to assure equal access of men, women, youth and the most vulnerable. | Number of people with reduced access to basic social services as a result of the project | None has reduced access to basic social services | Monitoring of project activities to ensure equitable access to basic social services by all project beneficiaries | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
3 – Marginalized and vulnerable Groups |  |  | In this project, there is no single activity or initiatives identified with execution that could generate a negative impact on marginalized and/or vulnerable groups. But without extensive consultation with marginalized/vulnerable groups at the project sites and in training exercises, it is probable that project activities will exclude these marginalized/vulnerable groups, thus preventing them from accessing benefits – both in terms of resources and training | Marginalized and poor vulnerable village groups especially women have been widely involved during implemenation of this project. This project ensures that all components enhance the adaptive capacity of marginalized and vulnerable groups including transforming their social life to better levels especially for women and girls. | Number of marginilized and vulnerable groups negatively impacted by the project | None of the marginalized and vulnerable groups being negatively affected by the project | Monitoring of the project activities to ensure that no marginalized and vulberable group is negatively affected by the project | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
4 – Human rights |  |  | None anticipated. No activities are identified whose execution is not in line with the established international human rights. Project objectives promote basic human rights for equitable access to service and clean and safe drinking water, access to food, information, and quality and health environment. | The project respect and adhere to all relevant conventions on human rights, national and local laws in relation to human rights. | Number of cases from the project that demonsrtate violation of human rights | No reported case from the project that demonstrate violation of human rights | Monitoring of the project activities to ensure that basic human rights for equitable access to service and clean and safe drinking water, access to food, information, and quality and health environment are observed | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
5 – Gender equality and women’s empowerment |  |  | Without extensive, transparent and fair involvement of women and other gender sensitive groups, it is likely that women will be inadequately represented during implementation of this project. This inadequate inclusion of women would be compounded as the negative effects of climate shocks are expected to be experienced disproportionately by women compared to men. | From the begging the project has ensured inclusion of gender equality and women empowerment issues with activities sensitive to gender equality particularly equal rights, responsibilities, opportunities and access of women and youth to resources allocated to improve their resilience to the current and future climate change effects. | Number of women in the projecct villages benefiting from the project | About 40% of women in the project villages participate and benefit from project activities | Monitoring of the project activities to ensure that gender equality and women empowerment are integrated in all project operations | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
6 – Core labour rights |  |  | Activities under component 1,2 3 and 4 will involve labor works for implementations of concrete adaptation actions through the popular implementation modality known as Force Account where community members and beneficiaries provide the labor force. However, in doing so local communities might be exposed to the risk of minor accidents while executing some constructions and tree planting and ecological restoration activities. | Core labor rights are respected and considered in the project implementation. The employment and Labor Relation Act, 2004 prohibits employment of children less than 18 years of age, stipulated types of contracts that can be entered with employees. | The number of cases from the project that demonstate violation of core labour rights | No violation of core labour rights | Monitoring of the project activities to ensure that there is no violation of core labour rights | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
7 – Indigenous peoples |  |  | None anticipated | All project interventions ensure equitable access to project benefits and resources by local peoples and to most extent communities at grass-root and relevant marginalized community groups are included in community consultation and during participatory planning of activities. | Number of cases from the project that demonsrtate exclusion of the local people in project execution | Indigenous people (local people) are fully engaged in the project | Monitoring of the project activities to ensure that local people benefit from project interventions | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
8 – Involuntary resettlement |  |  | None anticipated | The project implementation does not include voluntary or any involuntary resettlement. | Number of cases from the project that demonstrate voluntary or involuntary resettlement | Involunatry resettlement does not exist in the project | Monitoring of the project activities to ensure that no involunatry resettlement | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
9 – Protection of natural habitats |  |  | Project interventions include planting of tree species, bee-keeping, improved ecosystem and environmental quality and services and functions provide water access and improved food security through drip irrigation interventions. Despite this focus, there is a low risk that the interventions of concrete adaptation actions could result in destruction of small areas of natural habitat. | By implementing conservation measures linked to economic benefits to the people to tackle climate change in Bunda district, the project contributes to improved management of natural ecosystems, particularly in the context of future climate change. | Number of project activities that demonstrate protection of natural habitats | The natural habitats are highly degraded due to unsustainable human activities in the past. | Monitoring of the project activities to ensure that the project contributes towards protection and restoration of natural habitats | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
10 – Conservation of biological diversity |  |  | Without careful planning and mapping of project site, on-the-ground adaptation interventions might adversely impact on local biodiversity. For example, planting exotic, invasive species might outcompete indigenous species and impact negatively on both indigenous species richness and on the ecosystem services. | The project implementation has been keen not cause any risk to biological divesity. Tree planting has involved local species , no excotic trees has been planted. None of the activities involved clearing of naturla vegetation | Number of project activities that contribute to conservation of biological activities | There is no project activity that may cause any significant risk to biological diversity | Monitoring of the project activities to ensure that the project interventions do not cause any rsik to biological diversity | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
11 – Climate change |  |  | None anticipated. The project will contribute to climate change adaptation and mitigation, thus will complement the national and global efforts to combat detrimental effects of climate change | Through the Four (4) components, this project improve climate resilience of agro-pastoral rural communities in Kongwa district, facilitate transfer of climate adaptation technologies to local communities in rural villages, and promote innovations development for climate solutions in rural villages and communities | Number of project activities that contribute to climate change adaptation | During inception of the project it was found that there was no concerete measures to address climate change impacts in the project area. For example, women in some villages had to walk about 5 Km to fetch water due to prolonged dry spells in the area. | Monitoring of the project activities to ensure that the project interventions contribute to enhancement of capacities of project beneficiaries in adaptation of climate change impacts | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
12 – Pollution prevention and resource efficiency |  |  | None anticipated | The proposed project is visualized to cause no any harm or pollution. | Number of reported cases of pollution emanating from project activities | No pollution cases exist | Monitoring of the project activities to ensure no siginicant environmental pollution emante from project activities | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
13 – Public health |  |  |  | The proposed project enhances the quality of public health. Indeed, through components 1, 2 and 3, contribution of this project to the general public health is clear. | Number of project activities that contibute to public health | In project villages, sanitation and hygiene is poor due to limited access to water | Monitoring of the project activities to ensure that the project interventions contributes to public health. In particular, project activities in components 1 and 2 contribute to public health | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
14 – Physical and cultural heritage |  |  | None anticipated | No physical and cultural heritage sites which exists in the project sites | Number of cases from the project related to destruction of physical and cultural heritage | No physical and cultural heritage sites in the project villages | No physical and cultural heritage sites in the project villages. Thus nothing is done about this indicator | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
15 – Lands and soil conservation |  |  | None anticipated. | This project is design to enhance and promote conservation of soil and land resources. . The project activities under components 2 and 4 contribute into increased soil stability, rehabilitate the degraded contour bands/windrows and reduced runoff of nutrients from top soil, promote improved soil fertility and productivity, improve the hard pan soils and waste land to productive lands. | Number of project activities contributing to lands and soil conservation | The status of land and soil health in some project villages is poor. Soil erosion has destroyed roads and some farming land. | Monitoring of the project activities to ensure that the project interventions contribute to land and soil protection. Close monitoring is being done for project activities under components 2 and 3 to ensure that they really into increased soil stability, rehabilitate the degraded contour bands/windrows and reduced runoff of nutrients from top soil, promote improved soil fertility and productivity, improve the hard pan soils and waste land to productive lands. | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No unanticipated ESP risks were identified during the reporting period
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks during the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE had regular visits to the project sites and had instructed the EE to submit the quarterly reports that integrate ESP safeguard measures
Have the implementation arrangements been effective during the reporting period? |  | Yes. The IE has conducted several monitoring visits to ensure that the project is on track
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE has a monitoring and evaluation plan that integrates ESP safeguard measures
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. The EE has been able to carry out most of the activities planned for Year 1. The EE has been submitting the quarterly to the IE
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance recived during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Support to gender based accsess to clean water | Output | 'Number of women accessed clean water. | More than 50% of women accessed to clean water | Extension of water network from Mwiruruma to Muranda village covering of 18km established. | Satisfactory. Extension of water network covering 18 km to supply clean water to 8,000 women established
Support to gender based livelihoods | Output | Number of women involved in improved local chicken keeping practices | More than 95% of women engage in improved local chicken keeping preparation and training | Establish 8 chicken keeping structures for facilitating improved local chicken keeping at Neruma, Mumagunga, Namhula, and Chingurubhila villages | Satisfactory. A total 120 women attend improved local chicken keeping training
Training of government stakeholders: technical staff, community groups and civil society in climate risk management and project measures for further scaling up | Output | Number of communities and district staff trained on climate risk management | None of staff trained on climate risk management | Over 2000 knowledge products (IEC) developed and distributed | Satisfactory. Out of 50 participants who attended the training , 15 were women
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The monitolring team of the IE comprised of at least 2 female members
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. The IE has been keen in ensuring project monitoring data are disaggregated by sex
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The project management unit of the EE comprises of 1 female
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. The project interventions take into account men, women and youth . Furthemore, the project monitoring data are disaggregated by sex
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Enhancing Climate resilience for improved access to rural water supply system in selected drought prone agro-pastoral communities of Bunda distric | Enhancing Climate resilience for improved access to rural water supply system in selected drought prone agro-pastoral communities of Bunda distric | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through rural water supply interventions | S
| Improve agricultural productivity, livelihood and agro-ecosystem resilience through climate smart EVA practices | 2.Improve agricultural productivity, livelihood and agro-ecosystem resilience through climate smart EVA practices | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through establishment of drip irrigation structures | S
| Promote paradigm shift of small scale fishers for sustainable income and climate resilience livelihood through aquaculture innovations | 3. Promote paradigm shift of small scale fishers for sustainable income and climate resilience livelihood through aquaculture innovations | Outcome 5 | Increased ecosystem resilience in response to climate change and variability |  | Fish ponds constructed and fish fingerlings hatchery constructed for improved | MS
| Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods Bunda District | .Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods Bunda Distric | Outcome 5 | Increased ecosystem resilience in response to climate change and variability |  | The tree planting and natural regeneration interventions in degraded areas will contributed to ecosystem resilience | S
| trengthening institutional capacity and knowledge management on climate change adaptation | trengthening institutional capacity and knowledge management on climate change adaptation | Outcome 2 | Strengthened Institutional capacity to reduce risks associated with climate induced |  | Trainingof district officers was conducted. This is envisaged to build their capacity in integrating climate change in district development plans | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Fredrick Mulinda
| Email: | fredrick.mulinda@nemc.or.tz
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Despite some internal delays, the EE has implemented most of activities planned for this reporting period satisfactorily. However, more improvements should be done in the second year of the project
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Enhancing Climate resilience for improved access to rural water supply system in selected drought prone agro-pastoral communities of Bunda distric | Enhancing Climate resilience for improved access to rural water supply system in selected drought prone agro-pastoral communities of Bunda distric | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through rural water supply interventions | S
| Improve agricultural productivity, livelihood and agro-ecosystem resilience through climate smart EVA practices | 2.Improve agricultural productivity, livelihood and agro-ecosystem resilience through climate smart EVA practices | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through establishment of drip irrigation structures | S
| Promote paradigm shift of small scale fishers for sustainable income and climate resilience livelihood through aquaculture innovations | 3. Promote paradigm shift of small scale fishers for sustainable income and climate resilience livelihood through aquaculture innovations | Outcome 5 | Increased ecosystem resilience in response to climate change and variability |  | Fish ponds constructed and fish fingerlings hatchery constructed for improved | MS
| Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods Bunda District | .Improve ecological and environmental services and functions to sustain climate sensitive rural livelihoods Bunda Distric | Outcome 5 | Increased ecosystem resilience in response to climate change and variability |  | The tree planting and natural regeneration interventions in degraded areas will contributed to ecosystem resilience | S
| Strengthening institutional capacity and knowledge management on climate change adaptation | trengthening institutional capacity and knowledge management on climate change adaptation | Outcome 2 | Strengthened Institutional capacity to reduce risks associated with climate induced |  | Trainingof district officers was conducted. This is envisaged to build their capacity in integrating climate change in district development plans | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dickson B. Balige
| Email: | dickson.balige@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Most of the activities planned for 1st Year of the project were implemented. However, delays in procurement of goods and services seem to slow the progress of the project. This will be mitigated in second year of the project through timely submission of purchase request and make close up to speed up the procurement process
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Output | Number of pump houses rehabilitated |  | 100 % of pump houses are below the required standards | 3 pump houses have been rehabiliated | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
Output | Number of water pumping machines purchased |  | 90 % of water pumping machines are out of use | 2 water pumping machines have been procured | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
Output | Number of water storage structures rehabiliated |  | 90 % of water stoage structures in the project villages are faculty | 1 water storage tank has been rehabiliated | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
|  | Number of Community Owned Water Supply Organization(COWSOs) established | 0 % of Community Owned Water Supply Organization(COWSOs) exist in the project area | 3 COWSOs have been established | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
|  | Number of people ( COWSO members) trained on operation and maintanance of water supply structures | None COWSO members trained | 60 COWSO members trained (36 men and 24 women)
|  | Number of water kiosks constructed | 0 water kiosk in the project area | 2 water kiosks have been constructed | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
|  | % Cover of water network structures ( kilometers of pumped water network from lake Lake Victoria) | Water access > 5Km from the community | Piped water accessible within 500 m from the water outlet point.
|  | % Cover of boreholes (Kilometers of drilled boreholes network) | Water access > 5Km from the community | 2 boreholes drillled
|  | Number of water storage tanks | 0 water storage tanks in the area | 2 water storage tanks installed
Output | Number of water network constructed and rehabilitated in the project site | Number of water network constructed and rehabilitated in the project site | 0% of water networts exist in the project area | 2 water networks established | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
Output | Number of borehole drilled |  | 0 borehole drilled in the project area | 1 borehole has been drilled | Atleast 37,468 people (of which 18,108 are female and 18,359 are male )from drought prone agro-pastoral communities in the project sites of Bunda District have access to rural water at the end of the project
Output | Number of improved climate sensitive irrigation schemes established | Number of improved climate sensitive irrigation schemes establishe | 0% of drip irrigation schemes | 2 drip irrigation schemes established | Increase food security in Bunda district by 30% benefitting about 60% females and 40% males
|  | % increase of women farmers in Irrigation schemes at Mchigando | 0 % of women in irrigation schemes | On progress
Output |  | Number of post harvesting structures constructed | 100 % of post harvesting structures in the project area below the required standards | 1 warehouse for crop storage constructed | Increase food security in Bunda district by 30% benefitting about 60% females and 40% males | 200 small scale fishers of which at least 40% are females trained on climate resilient aquaculture innovations
|  | % of farmers adopting drought resistant and early maturing seeds | Less than 10 % of farmers adopting drought resistant and earky maturing seeds | 100 farmers supplied with drough resistant seeds
|  | Number of farmers trained in farmers field schools (disaggrivated by gender , 50% being women) | 0 farmers trained | 50 farmers trained ( 25 men and 25 women)
Output | Number of modern paddy hulling machine, sunflower seed pressing & oil refinery machine, cassava graters and horticultural drying devices purchased | Number of modern paddy hulling machine, sunflower seed pressing & oil refinery machine, cassava graters and horticultural drying devices | 0 modern crop processing machine exist | 1 modern paddy hulling machine has been procured | Increase food security in Bunda district by 30% benefitting about 60% females and 40% males
Output | Number of modern chicken hatchery facility constructed |  | 0 hatchery exist | 1 modern hartchery facility constrcuted | Increase food security in Bunda district by 30% benefitting about 60% females and 40% males
Output |  | Number of ponds for aquaculture activates established | 0 fish ponds | 5 fish ponds have been constructed | 200 small scale fishers of which at least 40% are females trained on climate resilient aquaculture innovations
Output | Number of tilapia cages established | Number of tilapia cages established | 0 tilapia cages exist in the project area | 100 cages have been established | 200 small scale fishers of which at least 40% are females trained on climate resilient aquaculture innovations
|  | Number of primary and grownout brooder and hatchery feeds production facilities | 0 faciliate exists | 1 1 faciliate constrcuted
|  | Number of people trainied on aquaculture | None trained | 40 people were trained
|  | Number of feed prepration houses established | None exististed | 1 feed processing facility constructed
|  | Number of fingerlings produced | O fingerlings producued | At least 1000 finderlings produced per week
Output |  | Number of Wooden Outboard Engine Boats procured | 0 boat exist | 1 boat procured | 200 small scale fishers of which at least 40% are females trained on climate resilient aquaculture innovations
|  | Number of pelletizer and feed mixer machines procured | 0 machine exists | 1 pelletizer and 2 feed mixer machine procured
|  | Number of people trainied on modern feed formulation methods | 0 people trained | 2 pelletizer and 2 feed mixer machine procured
Output | Number of Hatchery for mass production of Fingerlings established | Number of Hatchery for mass production of Fingerlings established | 0 fingerlish hatchery exist | 1 fingerling hatchery facility constructed | 200 small scale fishers of which at least 40% are females trained on climate resilient aquaculture innovations
|  | Number of degraded ecosystems to be restored | About 90% of the area is degraded | At least 10 sites have been identified for restoration | Restore and Rehabilitate at least 100 acres of the degraded ecosystems in the project sites.
Output | Number of restored and rehabilitation ecosystems | Number of restored and rehabilitation ecosystems | Nearly 90 % of the landscape is highly degraded | A total 100 acres in the project village have identified for ecological restoration
Output |  | Number of tree nurseries established | 0 reliable and well equiped tree nurseries in the project villages | 2 tree nurseries have been established | Plant 1 million trees in 5 wards
Output | Number of tree planted |  | less than 10% of degraded land has been planted with trees | 100,000 trees planted
|  | Number of ecological schools established | 0 eleocogical school exists | 1 secondary school and 1 primary school are being developed to become eco-schools
Number of school and village tree nurseries established
Output | Number of beehives purchased and distributed to farmers |  | 0% of modern bee hives in the selected project sites | 250 beehives have been procured and distributed to beekeeping groups
Output |  | Number of communities and district staff trained on climate risk management | 0 staff trained on climate risk management | 50 district officers trained | Over 2000 knowledge products (IEC) developed and distributed
Output |  | Number of district development plans reviewed to integarted climate change issues | 0 reviewed district development plans, | 1 plan reviewed | Over 2000 knowledge products (IEC) developed and distributed
Output |  | Number of village development plans reviewed to integrate climate change issues | 0 reviewed village development plans, | Not done in this reporting period, will be done in the second year of the project | Over 2000 knowledge products (IEC) developed and distributed
Output | Number and type of knowledge products developed and disseminated | Number and type of knowledge products developed and disseminated | Zero information about the project in media | 500 brocures of the project prinited and disseminated | Over 2000 knowledge products (IEC) developed and distributed
| Number of capacity building workshops for district officersconducted |  | zero workshop on climate change | 1 workshop for district officers and 1 workshop for community leaders and officers held

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | High expections of the communities whereby they wanted the project support issues which were not in the project document . This was addressed by raising awarness of community members on project objectives and expected outputs
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Fund disbursement delays from IE to EE due to internal processses of the bank. This was addressed by changing the bank
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes was made
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | All project interventions took gender into consideration whereby in each project activity dealing directly with the community men, women, youth and the eladerly were considered. The priority was given to women, youth and the elderly. For example, the members of community based water supply organzations include the significant number of women. This has led to positive attitude towards the project by the community.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | National Environment Management Council
Type of implementing entity | NIE
Country | Tanzania
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 41968 | 4500 | 37468 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 2: Partially effective | Total | 41968 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 5 | Multi-sector | 2: Low capacity | Total | 30 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 2% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 10 | 5% | Public |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 1: No capacity | Public | Local | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 3 | Local | Multi-sector | 2: Low capacity | 3 | Local | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 90 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 4500 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 2 | 20% to 39% | 3: Partially aware |  | 2 | 20% to 39% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 1 | Training manuals | Local |  | 4 | Training manuals | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Agriculture | 3 | Community |  | Agriculture
|  | 1 | Community |  | Water management | 3 | Community |  | Water management
|  | 0 | Community |  | Food security | 2 | Community |  | Food security
|  | Baseline information |  |  |  | Target Performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated | 1: Ineffective | Rangelands | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated |  | Rangelands | 1000 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated | 1: Ineffective | Rangelands | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated | 1: Ineffective | Rangelands | 1000 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 500 | 5% | 2: Limited improvement |  | 500 | 10% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 500 | 10% | From 1% to 5% | Agribusiness | 500 | 10% | From 10% to 20% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 500 | 10% | From 1% to 5% | Agriculture | 500 | 10% | From 10% to 20% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 500 | 10% | From 1% to 5% | Livestock production | 500 | 10% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households |  | Alternate Source
|  | 500 | 10% | From 1% to 5% | Agribusiness | 500 | 10% | From 10% to 20% | Agribusiness
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Adaptation strategies | Food security | Supporting livelihoods | 7 | Adaptation strategies | Multi-sector | Soil water conservation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 500 | Agriculture |  | 1 | 500 | Agriculture |  | 2
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 500 | Agriculture |  | 0.5 | 500 | Agriculture |  | 1.5
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 500 | other |  | 0.5 | 500 | other |  | 2
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 500 | Agriculture |  | 0.5 | 500 | Agriculture |  | 1.5
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 4 | Multi-sector | National | Environmental policy | 6 | Multi-sector | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 5 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Community | Innovation rolled out |  | Food Security | Community | Innovation rolled out
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices | 1: Ineffective | 3 | Food Security | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 4 | Innovative practice |  | 4: Effective