## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 12/10/2021 - 31/10/2022
| Project Title: | Enhancing Climate Change Adaptation for Agro-Pastoral Communities in Kongwa District
| Project Summary: | The project seeks to address the climate change challenges facing the agropastoral communities in Kongwa district . This is done through practical and concrete climate adaptation interventions . In particular, the project aims to achieve the following objectives: (1) to enhance climate resilient rural water supply system in vulnerable agro-pastoral communities at Mtanana and Ugogoni wards; (2)to support transformation of exploitive agro-pastoral practices to diversified climate smart and sustainable livelihoods; (3)to improve ecological functions to sustain climate sensitive livelihoods in Kongwa District; and (4)to strengthen capacities of institutions, extension services and trainers to reduce risks associated with climate- induced livelihood failures in Kongwa district.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Environment Management Council | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-01-06
IE-AFB Agreement Signature Date: |  | 2020-08-27 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-10-12 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2024-10-31
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Boniface Chija | Dominican Republic
| Email: | bbchija@gmail.com | Ecuador
| Date: | 2022-10-31 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Switbert Mukama | Equatoral Guinea
| Email: | switbert.mukama@vpo.go.tz | Eritrea
| Date: | 2022-12-19 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Fredrick Mulinda | Fiji
| Email: | nieaf@nemc.or.tz / kasigazi.koku@gmail.com | Finland
| Date: | 2022-12-15 | France
| Executing Agency |  | Gambia
| Name: | Dr. Dominico B Kilemo | Georgia
| Email: | dbkilemo@gmail.com | Germany
| Date: | 2022-10-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31 October 2022 |  |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] | [5 empty] | Financial information PPR 3: cumulative from project start to [insert date] | [5 empty] | Financial information PPR 4: cumulative from project start to [insert date] | [5 empty] | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31/10/2022 | 330102 |  |  |  | Estimated cumulative total disbursement as of [enter Date] | [5 empty] | Estimated cumulative total disbursement as of [enter Date] | [5 empty] | Estimated cumulative total disbursement as of [enter Date] | [5 empty] | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | [5 empty] | Add any comments on AF Grant Funds. (word limit=200) | [5 empty] | Add any comments on AF Grant Funds. (word limit=200) | [5 empty] | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | NIL |  |  |  | INVESTMENT INCOME |  | 360102 |  |  |  | INVESTMENT INCOME | [5 empty] | INVESTMENT INCOME | [5 empty] | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Climate resilient rural water supply system established | 87246
| Output 1.2 Community Based Water Supply Organizations established | 12412.4
| Output 2.1 Best agricultu ral – climate smart practices enhance d to improve food security | 49731.5
| Output 2.2 Natural pasture, local breeds and livestock management system improved | 22873.5
| Output 2.3 Market and value chain of agro-pastroral products improved | 55877.9
| Output 3.1 Integrated ecological and management systems implemented | 46757.2
| Output 4.1 Institutional and technical capacity strengthened | 13203.5
| EXECUTION FEE | 42000
| IMPLEMENTING ENTITY FEE | 30000
| TOTAL | 360102 | [10 empty] | TOTAL | 0 |  |  |  |  | TOTAL | 0 |  |  |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE | [5 empty] | PLANNED EXPENDITURE SCHEDULE | [5 empty] | PLANNED EXPENDITURE SCHEDULE | [5 empty] | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Climate resilient rural water supply system established | 113090 |  | 2023-07-31
| Output 1.2 Community Based Water Supply Organizations established | 20715 |  | 2023-07-31
| Output 2.1 Best agricultu ral – climate smart practices enhance d to improve food security | 72444 |  | 2023-06-30
| Output 2.2 Natural pasture, local breeds and livestock management system improved | 25200 |  | 2023-06-30
| Output 2.3 Market and value chain of agro-pastroral products improved | 74783 |  | 2023-09-30
| Output 3.1 Integrated ecological and management systems implemented | 83036 |  | 2024-02-28
| Output 4.1 Institutional and technical capacity strengthened | 33500 |  | 2024-03-31
| EXECUTION FEES | 35160 | 2023-11-24 | 2024-03-31
| IMPLEMENTING ENITY FEE | 30000 | 2023-11-25 | 2024-03-31
| TOTAL | 487928 | [10 empty] | TOTAL | 0 |  |  |  |  | TOTAL | 0 |  |  |  |  | TOTAL | 0
[11 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | [5 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | [5 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[11 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | [5 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | [5 empty] | How much of the total co-financing as committed in the Project Document has actually been realized?
[11 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | [5 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | [5 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[11 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | [5 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | [5 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Competing interests between different stakeholders regarding accessing and use of project benefits and related resources | Low | Educating the stakeholders about the project objectives and expected outputs
Local communities with limited participation and willingness to promote project initiatives | Low | Not experienced so far. The communities participate in project activities
High expectations for quick investments on the ground and resources beyond the available project resources | Low | Awareness raising about the project objectives and expected outputs
Project financial management | Low | Risk not experienced so far
Delay in project implementation due to government bureaucracy, long and inefficient procurement processes | Low | Seeeking early approval of the procurement plan and early announcement of the tenders
Limited Stakeholders Involvement | Low | Risk not experienced so far
Low adoption rate of proposed innovations and adaptation technologies by communities | Low | Risk not experienced so far
Financial risk | Low | Risk not experienced so far
Conflict Management | Low | Risk not experienced so far
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | According to the National Environmental Management Act (2004) and the Environmental Impact Assessment (EIA)and Environmental Audit (EA)Regulation (2005) and Sectorial Regulations and Guidelines of the United Republic of Tanzania, most of the components/activities of the proposed project do not fall within the First Category of projects that require full EIA. There is no activity under any component which require full EIA as their size are small and location of the interventions to do not require further assessments. However, where some activities are not fully itemized there might be a risk that such activities will not comply with certain laws. | The project activities strongly comply with all relevant national laws including international standard).They do not conflict with any domestic laws and policies, but they strongly support implementations of those laws and policies as indicated at Part II E of the approved project document | Number of national laws with which the project must comply | The project is compliant with existing laws | The project has contuned to adhere to existing laws | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
2 - Access and equity |  |  | The constitution of the United republic of Tanzania specifies equitable distributions of benefits within communities, and prohibits any actions that promote economic imbalances among citizens and communities. However, some activities of the project, under component 1,2and 3 for livelihood improvement are not intended to provide a benefit for all, but target those livelihoods in need as well as the livelihoods which are involved in restoration activities, transforming exploitive agriculture, livestock and beekeeping. Also given that the beneficiaries are rural people and marginalized poor families who are not often integrated in the villages politics and decision-making processes, there could be also a risk of insufficient access of the project resources by these people. | The project activities being implemented do not reduce or prevent communities at the sites in all villages from accessing basic health services, clean water and sanitation, energy, education, housing, safe and decent working conditions and land right. Communities and beneficiaries will be highly sensitized to enhance priorities of the most vulnerable communities while ensuring benefits to reach further communities for scaling ups and replications. In addition, measures have been put in place to able this project to closely monitor all targeted beneficiaries to assure equal access of men, women, youth and the most vulnerable. | Number of people with reduced access to basic social services as a result of the project | No reported case of reduced access to basic social services as a result of the project | The project interventions promote equitable access to basic social services | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
3 – Marginalized and vulnerable Groups |  |  | In this project, there is no single activity or initiatives identified with execution that could generate a negative impact on marginalized and/or vulnerable groups. But without extensive consultation with marginalized/vulnerable groups at the project sites and in training exercises, it is probable that project activities will exclude these marginalized/vulnerable groups, thus preventing them from accessing benefits – both in terms of resources and training | Marginalized and poor vulnerable village groups especially women have been widely involved during implemenation of this project . s. This project ensures that all components enhance the adaptive capacity of marginalized and vulnerable groups including transforming their social life to better levels especially for women and girls. | Number of marginilized and vulnerable groups negatively impacted by the project | No reported case of marginalized and vulnerable groups being negatively affected by the project | The project continues to observe that no marginalized and vulberable group is negatively affected by the project | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
4 – Human rights |  |  | None anticipated. No activities are identified whose execution is not in line with the established international human rights. Project objectives promote basic human rights for equitable access to service and clean and safe drinking water, access to food, information, and quality and health environment. | The project respect and adhere to all relevant conventions on human rights, national and local laws in relation to human rights. | Number of cases from the project that demonsrtate violation of human rights | No reported case from the project that demonstrate violation of human rights | The project has contunied to ensure that its interventions promotes basic human rights for equitable access to service and clean and safe drinking water, access to food, information, and quality and health environment. | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
5 – Gender equality and women’s empowerment |  |  | Without extensive, transparent and fair involvement of women and other gender sensitive groups, it is likely that women will be inadequately represented during implementation of this project. This inadequate inclusion of women would be compounded as the negative effects of climate shocks are expected to be experienced disproportionately by women compared to men. | From the begging the project has ensured inclusion of gender equality and women empowerment issues with activities sensitive to gender equality particularly equal rights, responsibilities, opportunities and access of women and youth to resources allocated to improve their resilience to the current and future climate change effects. | Number of women in the projecct villages benefiting from the project | About 30% of women in the project villages participate and benefit from project activities | Since inception of the project, inclusion of gender equality and women empowerment issues has been signdicantly considered | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
6 – Core labour rights |  |  | Activities under component 1,2 and 3 will involve labor works for implementations of concrete adaptation actions through the popular implementation modality known as Force Account where community members and beneficiaries provide the labor force. However, in doing so local communities might be exposed to the risk of minor accidents while executing some constructions and tree planting and ecological restoration activities. | Core labor rights are respected and considered in the project implementation. The employment and Labor Relation Act, 2004 prohibits employment of children less than 18 years of age, stipulated types of contracts that can be entered with employees. | The number of cases from the project that demonstate violation of core labour rights | No violation of core labour rights | The project has continued to ensure that there is no violation of core labour rights | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
7 – Indigenous peoples |  |  | None anticipated | All project interventions ensure equitable access to project benefits and resources by local peoples and to most extent communities at grass-root and relevant marginalized community groups are included in community consultation and during participatory planning of activities. | Number of cases from the project that demonsrtate exclusion of the local people in project execution | Indigenous people (local people) are fully engaged in the project | The project has continued to ensure that local people benefit from project interventions | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
8 – Involuntary resettlement |  |  | None anticipated | The project implementation does not include voluntary or any involuntary resettlement. | Number of cases from the project that demonsrtate voluntary or involuntary resettlement | Involunatry resettlement does not exist in the project | No involunatry settlement | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
9 – Protection of natural habitats |  |  | Project interventions include planting of tree species, bee-keeping, improved ecosystem and environmental quality and services and functions provide water access and improved food security through drip irrigation interventions. Despite this focus, there is a low risk that the interventions of concrete adaptation actions could result in destruction of small areas of natural habitat. | By implementing conservation measures linked to economic benefits to the people to tackle climate change in Kongwa district, the project contributes to improved management of natural ecosystems, particularly in the context of future climate change. | Number of project activities that demonstrate protection of natural habitats | The natural habitats are highly degraded due to unsustainable human activities in the past. The project has started interventions towards restoration of natural habitats | The project continues to promote interventions that contribute towards protection and restoration of natural habitats | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
10 – Conservation of biological diversity |  |  | Without careful planning and mapping of project site, on-the-ground adaptation interventions might adversely impact on local biodiversity. For example, planting exotic, invasive species might outcompete indigenous species and impact negatively on both indigenous species richness and on the ecosystem services. | The project implementation has been keen not cause any risk to biological divesity. Tree planting has involved local species , no excotic trees has been planted. None of the activities involved clearing of naturla vegetation | Number of project activities that contribute to conservation of biological activities | No project activity that may cause any significant risk to biological diversity. Component 3 of the project enhances biological diversity. | The project continues to promote interventions that contribute towards conservation of biological diversity | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
11 – Climate change |  |  | None anticipated. The project will contribute to climate change adaptation and mitigation, thus will complement the national and global efforts to combat detrimental effects of climate change | Through the Four (4) components, this project improve climate resilience of agro-pastoral rural communities in Kongwa district, facilitate transfer of climate adaptation technologies to local communities in rural villages, and promote innovations development for climate solutions in rural villages and communities | Number of project activities that contribute to climate change adaptation | During inception of the project it was found that there was no concerete measures to address climate change impacts in the project area. For example, women in some villages had to walk about 7 Km to fetch water due to prolonged dry spells in the area. | The project has continued to progress activities that contribute to enhancement of climate change resilience by agropastoral communities in the project villages | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
12 – Pollution prevention and resource efficiency |  |  | None anticipated | The proposed project is visualized to cause no any harm or pollution. | Number of reported cases of pollution emanating from project activities | No pollution cases exist | The project continues to observe that no siginicant environmental pollution emante from project activities | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
13 – Public health |  |  |  | The proposed project enhances the quality of public health. Indeed, through components 1, 2 and 3, contribution of this project to the general public health is clear. | Number of project activities that contibute to public health | In project villages, sanitation and hygiene is poor due to limited access to water | The project has contunued to progress activities that contributes to public health. In particular, project activities in components 1 and 2 contribute to public health | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
14 – Physical and cultural heritage |  |  | None anticipated | No physical and cultural heritage sites which exists in the project sites | Number of cases from the project related to destruction of physical and cultural heritage | No physical and cultural heritage sites in the project villages | The project contunues to observe that no physical and cultural heritage sites exist in the project villages | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
15 – Lands and soil conservation |  |  | None anticipated. | This project is design to enhance and promote conservation of soil and land resources. . The project activities under components 2 and 3 contribute into increased soil stability, rehabilitate the degraded contour bands/windrows and reduced runoff of nutrients from top soil, promote improved soil fertility and productivity, improve the hard pan soils and waste land to productive lands. | Number of project activities contributing to lands and soil conservation | The status of land and soil health in some project villages is poor. Soil erosion has destroyed roads and some farming land. | The project has continued to progress activities that contribute to land and soil protection. he project activities under components 2 and 3 contribute into increased soil stability, rehabilitate the degraded contour bands/windrows and reduced runoff of nutrients from top soil, promote improved soil fertility and productivity, improve the hard pan soils and waste land to productive lands. | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No unanticipated ESP risks were identified during the reporting period
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks during the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE had regular visits to the project sites and had instructed the EE to submit the quarterly reports that integrate ESP safeguard measures
Have the implementation arrangements been effective during the reporting period? |  | Yes. The IE has conducted several monitoring visits to ensure that the project is on track
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE has a monitoring and evaluation plan that integrates ESP safeguard measures
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. The EE has been able to carry out most of the activities planned for Year 1. The EE has been submitting the quarterly to the IE
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance recived during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Support to gender based livelihoods | Output | 'Number of gardens established by women | More than 98% of women engage in traditional agriculture | Establish three drip irrigation schemes and improve food security by 90% at Mtanana and Ugogoni wards | Satisfactory. 2 gardens (each with area of 1 acre ) have been estbalished by women.
Support to gender based livelihoods | Output | Number of women attended FFFS and training | More than 98% of women engage in traditional agriculture | Establish three drip irrigation schemes and improve food security by 90% at Mtanana and Ugogoni wards | Satisfactory. A total 40 women attend the FFFS training
Promoting bee keeping and fruit plants as income diversification activities to increase female and old people adaptive capacity in the district | Output | Number of modern beehives purchased and used by farmers, women and old people | 0% of modern bee hives in the selected project sites | Restore and Rehabilitate at least 90% of the degraded ecosystems in Mtanana and Ugogoni wards to sustain climate sensitive rural likelihoods | Satisfactory. Out of 200 beehives supplied, 80 were given to groups with women and old people
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The monitolring team of the IE comprised of at least 2 female members
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. The IE has been keen in ensuring project monitoring data are disaggregated by sex
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The project management unit of the EE comprises of 2 females
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. The project interventions take into account men, women and youth . Furthemore, the project monitoring data are disaggregated by sex
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | .Enhance climate resilient rural water supply system in vulnerable agro-pastoral communities at Mtanana and Ugogoni wards |  | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through rural water supply interventions | S
| Support transformation of exploitive agro-pastoral practices to diversified climate smart and sustainable livelihoods |  | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through establishment of drip irrigation structures, construction of cattle dip and introduction improved breeds for diary production | S
| .Improve ecological functions to sustain climate sensitive rural livelihoods at Mtanana and Ugogoni wards and in selected rural communities of Kongwa district |  | Outcome 5 | Increased ecosystem resilience in response to climate change and variability |  | The tree planting and natural regeneration interventions in degraded areas will contributed to ecosystem resilience | MS
| Strengthen capacities of institutions, extension services and trainers in to reduce risks associated with climate- induced livelihood failures in Kongwa district |  | Outcome 2 | Strengthened Institutional capacity to reduce risks associated with climate induced |  | Training materials for district oficers was developed. Furthermore, a training for trainers for commmunity memberes was connducted. This is envisaged to strenghten the institutional capavity to reduce climate risks at village level | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Fredrick Mulinda
| Email: | fredrick.mulinda@nemc.or.tz
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
With exception of ecosystem resoration interventions which require more supersviion by the EE, most of the project activities planned for Year 1 have been implemented succesfsuly to a large extent . However, in the coming year the EE need to improve in the following areas : (i) The annual monitoring plan should be aligned well with the results framework of the approved project document to easy reporting in the PPR (ii) While, the project has achieved signficant result in community awareness about the project and community participation in project activities, more efforts are needed in some villages (iii) Close monitoring and supervision is needed for activities under component 3 as they require commitment and support from village governments
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Enhance climate resilient rural water supply system in vulnerable agro-pastoral communities at Mtanana and Ugogoni wards |  | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through rural water supply interventions | S
| Support transformation of exploitive agro-pastoral practices to diversified climate smart and sustainable livelihoods |  | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adpative capacity of communities have been enhanced through establishment of drip irrigation structures, construction of cattle dip and introduction improved breeds for diary production | S
| Improve ecological functions to sustain climate sensitive rural livelihoods at Mtanana and Ugogoni wards and in selected rural communities of Kongwa district |  | Outcome 5 | Increased ecosystem resilience in response to climate change and variability |  | The tree planting and natural regeneration interventions in degraded areas will contributed to ecosystem resilience | S
| Strengthen capacities of institutions, extension services and trainers in to reduce risks associated with climate- induced livelihood failures in Kongwa district |  | Outcome 2 | Strengthened Institutional capacity to reduce risks associated with climate induced |  | Training materials for district oficers was developed. Furthermore, a training for trainers for commmunity memberes was connducted. This is envisaged to strenghten the institutional capavity to reduce climate risks at village level | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Dominico B Kilemo
| Email: | dbkilemo@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project performance during Year 1 was satisfactory because most of the planned activities were implemented. Looking at the 4 components of the project, it can be seen that there is at least one concrete climate change adaptation measure put in place in each component. Water supply system under compoment 1 has been developed. Climate reslient agriuculture through drip irrigation technology and livestock disease conrol measure ( animal dip constructiom) have been supported under compoent 2. Interventions for ecosystem restoration and conservation under component 3 have been implemenetd to some extent mainly tree planting, identification of degraded areas and preparaiton of restoration plans. Therefore, it is evident that the project performance during the first year is satisfactory . For next steps the following are recommended:(i)The establihsed livelihood groups should be monitored closely (ii)Communities should be closely supervised to ensure that the supplied trees are planted and tended (iii) Monitoring of Environmental and Gender Compliance should be enhanced thus ensuring that the project is compliant to ESP and GP of AF
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Output | Number of borehole and number of solar pumps installed |  | 0% of required boreholes 0%– water pump driven by solar energy | 2 boreholes have been drilled and 1 has solar powered water pump | 100% of vulnerable agro-pastoral communities of Mtanana and Ugogoni wards in Kongwa district have access to climate resilient rural water supply system
Output | Number of water kiosks constructed |  | 0 % community water points/ community water Kiosks exist | 2 community water points have been constructed
Output | Number of constructed cattle troughs |  | 0% cattle troughs constructed in Mtanana and Ugogoni wards | 2 cattle water troughs( 1 in Ugogoni ward and 1 in Mtanana ward) have been constructed , each with a capacity of serving 200 cattle at a time.
Output | Number of Community Based Water Supply Organization(COBWSOs)established/supported |  | 0% of COBWSOs exist and has effective management structure at Mtanana and Ugogoni wards | 6 COBWSOs have been estbalished and trained
Output | Number climate sensitive drip irrigation schemes |  | 0% of drip irrigation schemes | 2 drip irrigation schemes established | Establish three drip irrigation schemes
Output | Number of farmers using water management techniques in farms |  | Damaged contour band/ windrows. 0 farmers making contour bands | 60 farmers attended training on how to make contour bands thus contributing to soil and water conservation | Improve food security by 90% at Mtanana and Ugogoni wards
Output | Number of farmers using improved seeds and use intercropping with drought resistant varieties |  | Less than 10% farmers use improved drought tolerant and early maturing seeds | 100 farmerhouseholds were supplied with improved sorghum seeds and sunflower seeds
Output | Number of farmers trained and using FFS |  | 90% of farmers use traditional methods of agricultural systems | 60 farmers trained through FFS
Output |  | Number of gardens estbalished by women | 90% of farmers use traditional methods of agricultural systems | 2 gardens (each with area of 1 acre ) have been estbalished by women.
Output | Number of women attended FFFS and training |  | 90% of farmers use traditional methods of agricultural systems | A total 40 women attend the FFFS training
Output | Number of pasture farms |  | 0 Pasture farms exist | 2 farms (with a size of 2 acres each) have been identified and prepared ready for seed sowing
Output |  | Number of local breeds improved through cross breeding techniques | Over 90% of agro-pastoralists have local breeds of cattle | 6 bulls of improved cattle breed have been supplied to the farmers. Each bull has capacity of serving at least 10 cows a year
Output | Number of local farmers trained on market and financial issues |  | 0 farmers trained on market and financial issues | 50 farmers were trained
Output |  | Number of machines and equipment for improving quality and packaging of agricultural products | 0 machine and equipment | Honey press machine , ground nuts peeling machine and honey filters have been procured and given to farmers
Output | Number of restored and rehabilitated ecosystems |  | less than 10% of degraded land has been restored | A total 100 acres in the project village have identified for ecological restoration | Restore and Rehabilitate at least 90% of the degraded ecosystems in Mtanana and Ugogoni wards to sustain climate sensitive rural likelihoods
Output | Number of ecological restoration and rehabilitation plans developed |  | No project vallage has ecological; restoration plan | 10 village ecological restoration plans developed
Output |  | Number of modern beehives purchased and used by farmers, women and old people | 0% of modern bee hives in the selected project sites | 200 beehives have been procured and distributed to beekeeping groups whose members include women and old people
Output | Number of tree planted |  | less than 10% of degraded land has been planted with trees | 30,000 cashnew nut trees and 20,000 fruit trees were planted
Output | Number of improved charcoal and firewood stoves |  | 0 improved charcoal and firewood stoves in the project villages | Not done in the reporting period. It will be conducted in Year 2 of the prject
Output | Number of news outlets in the local press and media that have covered the project activities |  | Zero information about the project in media | The news about the project were disseminated through TV and instagram page of Kongwa District Council. There has 2 occasions whereby the project news were disseminated. The first event was during the Steering Committee Meeting held in September 2022 and Training of farmers on making contour bands held in October 2022 | Increased adaptive capacity within relevant development sector services and infrastructure assets
Output |  | Number of training materials for district officers developed | 0 relevant training modules available at the district, | 1 training material developed
Output |  | Number of district development plans reviewed to integarted climate change issues | 0 reviewed district development plans, | Not done in the reporting period. It will be conducted in Year 2 of the prject
Output |  | Number of village development plans reviewed to integrate climate change issues | 0 reviewed village development plans, | Not done in the reporting period. It will be conducted in Year 2 of the prject
Output | Number of awareness meetings conducted |  | 5 awareness meetings were held during project formulation phase | 20 awareness meetings were held during the reporting period
Output | Number of tools and equipment purchased |  | 0 tools and equipment purchased to support project monitoring | 4 office chairs, 3 office tables, 1 file cabinet, 1 projectors, 7 Laptops and three printers were procured

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | High expections of the communities whereby they wanted the project support issues which were not in the project document . This was addressed by raising awarness of community members on project objectives and expected outputs
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Fund disbursement delays from IE to EE due to internal processses of the bank. This was addressed by changing the bank
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes was made
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Poject reports include beneficiaries in terms of gender i,e rural water supply , tree planting, training etc. It was learned that gender consideration in project perfomancce help to determine the effectiveness of the community practices and actual imformation based on community livelihoods with no group based bias.Specifically through gender issues it was learned that, by considering gender issues, it enabled the project to identify some good gender practices as well as adressing some gaps and challenges in terms of gender consideration in daily community practices.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Drip irrigation is a concrete adaption intervention with a potential for replication within and outside Kongwa district
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | TZA/NIE/Agric/2019/2
Implementing Entity | National Environment Management Council
Type of implementing entity | NIE
Country | Tanzania
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 84500 | 4500 | 80000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 84500 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 1: No capacity | Total | 30 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 1: No capacity | Public | Local | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | Local | Multi-sector | 1: No capacity | 3 | Local | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 90 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 4500 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 3: Partially aware |  | 2 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | Local |  | 4 | Training manuals | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Agriculture | 3 | Community |  | Agriculture
|  | 1 | Community |  | Water management | 3 | Community |  | Water management
|  | 0 | Community |  | Food security | 2 | Community |  | Food security
|  | Baseline information |  |  |  | Target Performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated | 1: Ineffective | Rangelands | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated |  | Rangelands | 1000 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated | 1: Ineffective | Rangelands | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 5 | ha rehabilitated | 1: Ineffective | Rangelands | 1000 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 500 | 10% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 1% to 5% | Agribusiness | 500 | 10% | From 10% to 20% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 1% to 5% | Agriculture | 500 | 10% | From 10% to 20% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 1% to 5% | Livestock production | 500 | 10% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households |  | Alternate Source
|  | 0 | 0% | From 1% to 5% | Agribusiness | 500 | 10% | From 10% to 20% | Agribusiness
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Food security | Supporting livelihoods | 7 | Adaptation strategies | Multi-sector | Soil water conservation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 1 | 500 | Agriculture |  | 2
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 0.5 | 500 | Agriculture |  | 1.5
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | other |  | 0.5 | 500 | other |  | 2
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 0.5 | 500 | Agriculture |  | 1.5
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 4 | Multi-sector | National | Environmental policy | 6 | Multi-sector | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 5 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Community | Innovation rolled out |  | Food Security | Community | Innovation rolled out
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices | 1: Ineffective | 3 | Food Security | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 4 | Innovative practice |  | 4: Effective