## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 13 2021 to October 13 2022
| Project Title: | Strategic Water Harvesting Technologies for Enhancing Resilience to Climate Change in Rural Communities in Semi-Arid Areas of Tanzania (SWAHAT)
Enhancing Resilience to Climate Change in
Rural Communities in Semi-Arid Areas of
Tanzania (SWAHAT)
| Project Summary: | The objective of SWAHAT project is enhancing resilience and adaptation of semi arid rural communities to climate change-induced impacts of drought, floods and water scarcity. This will be achieved through strategic water harvesting technologies that will contribute to improved crops, aquaculture and livestock productivity, reforestation as well as combating emerging crops and livestock pests and diseases. The conceptual design of the water harvesting dam has been designed to ensure afforestation of the catchment before the dam thus prevention excessive siltation. The constructed or rehabilitated dams will supply water for all the proposed resilience and adaptation enhancing integrated innovations to be implemented on the semi-arid landscapes. In addition, synergism between aquaculture and agricultural activities will be done to enhance nutrient recycling and improve resource use efficiency. Nursery for fruits and forest trees as well as vegetable gardens will be established and supply seedlings for afforestation and horticulture. Pastureland and animal husbandry infrastructure will be established downstream of the dam for improved productivity and supply of manure for soil fertility improvement. The afforested landscape will integrate apiary units, provide fuel wood and restore habitats for biodiversity conservation. All these integrated approaches will contribute to livelihoods diversification to improve adaptation and resilience capacity to climate change of the semi-arid communities and the surrounding ecosystem. The project will be accomplished through four integrated components for concrete adaptation strategies namely: 1. Installation and rehabilitation of community water harvesting facilities that will integrate agriculture, livestock, tree planting and aquaculture; (Cost 436,571 USD). 2. Develop and implement participatory afforestation program for locally adapted fruit and forest trees (Cost 164,540 USD). 3. Develop integrated climate resilient livelihoods diversification through improved technologies in agriculture (Cost 172,815 USD). 4. Formulate and implement interventions for integrated management of emerging climate change related pests and diseases that affect crops and livestock productivity. (Cost 68,900 USD) 5. Knowledge Management (KM): (Cost 241,920 USD)
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Environmental Management Council | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Unitied Republic of Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam, Tanzania, Indian Ocean | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 23rd September 2020
IE-AFB Agreement Signature Date: |  | 09/11/2020 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | Otober -13th - 2021 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | NA
| Original Completion Date: | October 2025
Revised Completion Date after approval of |  | October 2025,
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Gender
| Condition or Requirement | Gender responsive communications approaches, activities, and tools has been worked on and the full details s attached as ANNEX 8 as a separate word document.
| Current Status | Condition met but clearance pending by AFB Sec
| Planned actions, including a detailed time schedule | Implementations of planned activities will be carried out as outlined in the Table 1 of Annex 8 of Gender responsive communication approaches, activities and tools for adaptation to climate change impacts.
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report (30/10/2021) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Fredrick Mulinda | Dominican Republic
| Email: | nieaf@nemc.or.tz / kasigazi.koku@gmail.com Phone +255753240517 | Ecuador
| Date: | 20/1/2023 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Switbert Mukama | Equatoral Guinea
| Email: | switbert.mukama@vpo.go.tz | Eritrea
| Date: | 2022-12-10 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Fredrick Mulinda | Fiji
| Email: | nieaf@nemc.or.tz / kasigazi.koku@gmail.com | Finland
| Date: | 2022-12-08 | France
| Executing Agency |  | Gambia
| Name: | Sokoine University of Agriculture (SUA) | Georgia
| Email: | kusolwap@gmail.com / kusolwa@sua.ac.tz | Germany
| Date: | 2022-11-26 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to October 13th, 2022 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [13 th October 2022] | 408132 |  |  | Estimated cumulative total disbursement as of [13/03/2022] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The above figure include cumulative amount received from NIE (NEMC) as amont for proposal Development: 27,007.00 USD, Quarter 1 activity: USD 157,000.00, Additional USD 55,900.00, Quarter 2: USD 40,000, Quarter 3 USD 40,045.00; and Quarter 4: USD 88,180.00 to add to the total received this year from NEMC. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT SPENT | Amount budgeted | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Proroject preparation and planning | 24700
| Output 1.1 - Activity 1.1.1 Land Survey, dam site mapping and land clearing of dam sites: | 8000
| Output 1.1- Activity 1.1.2 Excavation of dams to water storage depth/capacity, re-installation of dykes and construction of spillway | 197153
| Output 1.1 Activity 1.1.3 Installation of bore holes and water supply channels for strategic intervantions | 0
| Output 1.2 - Activity 1.2.1 Planting of forest trees in the catchment areas to protect water harvesting dams | 8750
| Output 2.1 - Activity 2.1.1 Establishment and management of community Nurseries | 12620
| Output 2.1 - Activity 2.1.2 Selection and collection of of the best adapted tree species for semi arid areas | 6000
| Output 2.1 - Activity 2.1.3 Optimization of propagation methods for each of the selected species | 3855
| Output 2.2 - Activity 2.2.1 Planting of forest trees and fruits in the farm land and degraded land for conservation | 2800
| Output 2.2 - Activity 2.2.2 Management,monitoring and evaluation of performance of planted trees on nurseries | 12600
| Output 3.1 - Activity 3.1.1 Excavations and establishment of model fish ponds | 0
| Output 3.1- Activity 3.1.2 Stocking of fingerlings and management of fish ponds | 0
| Output 3.1- Activity 3.1.3 Construction of water and nutrient recycling systems from fish to vegetable | 4900
| Output 3.2 - Activity 3.2.1 Establishment and management of horticultural crops | 0
| Output 3.2 - Activity 3.2.2 Design and establish irrigation systems for horticulture crops | 2120
| Output 3.2. - Activity 3.2.5 Develop vegetable nurseries, vegetable gardens and apiary units | 2305
| Output 3.3 - Activity 3.3.2 Construction of livestock water drinking points and water delivery trenches | 5855
| Output 3.3 - Activity 3.3.3 Establish model pasture paddocks for rotational grazing | 0
| Output 4.1 - Activity 4.1.1 Site selection, excavation of pits and building dip tanks | 0
| Output 4.1 - Activity 4.1.2 Formation of village committee for dip tank management | 0
| Output 4.2 - Activity 4.2.1 Establishing plant health clinics and surveillance systems in field crop production | 0
| Output 4.2 - Activity 4.2.2 To establish insect traps based on abundant species in the location for early warning | 0
| Output 5.1 - Activity 5.1.1 Conduct training workshops on safety and sustainable use of harvested water | 0
| Output 5.2 - Activity 5.2.1 Farmers Groups training on nursery techniques, establishment and management | 3900
| Output 5.2 - Activity 5.2.2 Capacity building to communities on tree planting and management skills and income generation | 5210
| Output 5.2 - Activity 5.2.3 Dissemination for wider capacity building and knowledge dissemination | 0
| Output 5.2 - Activity 5.2.4 Mainstreaming training into various platforms and establishment of farmer schools | 0
| Output 5.3 - Activity 5.3.1 Training of farmers in the target communities on fish farming practices | 0
| Output 5.3 - Activity 5.3.2 Development of manuals and fliers on aquaculture and value addition and marketing | 0
| Output 5.3 - Activity 5.3.3 Training of farmers on value chain of different adapted commercially high value vegetable crops | 0
| Output 5.3 - Activity 5.3.4 Training on apiary and postharvest handling of vegetable crops | 0
| Output 5.3 - Activity 5.3.5 Training on modern livestock management for climate change adapatation | 0
| Output 5.4 - Activity 5.4.1 Participatory surveillance and scouting for identification of major insect pests and vectors | 0
| Output 5.4 - Activity 5.4.2 Formation and training of diptank users and diptank attendants | 0
| Output 5.4 - Activity 5.4.3 Participatory design diagnostic tools for pest and disease and implementation of management options /IPM technologies | 0
| Transport related to project execution - Vehicle purchase and insurance from Components 1 to 5 | 32400
| NEE Execution costs: Transport related to project execution - Vehicle purchase and insurance | 9400
| NEE Execution costs: Inception meeting held centrally with all stakeholders prior to implementation for planning purpose | 8791.5
| NEE Execution fee 9.5% (SUA) | 38772.54
| NIE Execution cost 8.5% (NEMC) 34,691.22 was to be held at NEMC, not disbursed to SUA | 0
| Unused but committed funds by NEE | 18000
| TOTAL | 408132.04 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1- Activity 1.1.2: Excavation of dams to water storage depth/capacity, re-installation of dykes and construction of spillway | 136520 | November 2023
| Output 1.1 - Activity 1.1.3: Installation of bore holes and water supply canals for strategic intervantions | 41000 | Nevember 2023
| Output 1.2 - Activity 1.2.1: Planting of forest trees in the catchment areas to protect water harvesting dams | 11580 | Ongoing Activity
| Output 1.2 - Activity 1.2.2: Establish water user groups for governance mechanism for equitable water resource sharing | 12700 | Ongoing Activity
| Output 2.1 - Activity 2.1.1: Establishment and management of community Nurseries | 12600 | Ongoing Activity
| Output 2.1 - Activity 2.1.2:Selection and collection of of the best adapted tree species for semi arid areas | 5000 | Ongoing Activity
| Output 2.1 - Activity 2.1.3:Optimization of propagation methods for each of the selected species | 4600 | December 2023
| Output 2.2 - Activity 2.2.1:Planting of forest trees and fruits in the farm land and degraded land for conservation | 8420 | Ongoing Activity
| Output 2.2 - Activity 2.2.2:Management,monitoring and evaluation of performance of planted trees | 12200 | Ongoing Activity
| Output 2.2 - Activity 2.2.3:Supply and and demonstration of sustainable use of fuel wood through energy saving cook stoves, | 6000 | Ongoing Activity
| Output 3.1 - Activity 3.1.1:Establishment of model fish ponds | 12000 | December 2023
| Output 3.1 - Activity 3.1.2:Stocking of fingerlings and management of fish ponds | 10560 | December 2023
| Output 3.1 - Activity 3.1.3:Establishment of water distribution and nutrient recycling systems from fish to vegetable | 4600 | December 2023
| Output 3.2 - Activity 3.2.1: Eestablishment and management of horticultural crops | 6860 | Ongoing Activity
| Output 3.2 - Activity 3.2.2:Design and establish irrigation systems for horticulture crops | 6800 | Ongoing Activity
| Output 3.2 - Activity 3.2.5:Develop vegetable nurseries, improved community vegetable gardens | 9600 | Ongoing Activity
| Output 3.3 - Activity 3.3.2:Construction of livestock water drinking points and water delivery trenches | 9000 | September 2023
| Output 3.3 - Activity 3.3.3: Establish model woodlot for rotational firewood harvesting (to replace model pasture ) | 9000 | Ongoing Activity
| Output 4.1 - Activity 4.1.1:Rehabilitation of old dip tanks, | 15600 | Ongoing Activity
| Output 4.1 - Activity 4.1.2: Formation of village committee for dip tank management | 5700 | Ongoing Activity
| Output 5.1 - Activity 5.1.1:Conduct training workshops on safety and sustainable use of harvested water | 6700 | Ongoing Activity
| Output 5.2 - Activity 5.2.1:Farmers Groups training on nursery techniques, establishment and management | 6900 | Ongoing Activity
| Output 5.2 - Activity 5.2.2: Capacity building to communities on tree planting and management skills and income generation | 9800 | Ongoing Activity
| Output 5.3 - Activity 5.3.1:Training of farmers in the target communities on fish farming practices | 8400 | Ongoing Activity
| Output 5.3 - Activity 5.3.3: Training of farmers on value chain of different adapted commercially high value vegetable crops | 6800 | Ongoing Activity
| Output 5.3 - Activity 5.3.4: Training on apiary and postharvest handling of vegetable crops | 4200 | Ongoing Activity
| Output 5.3 - Activity 5.3.5: Training on modern livestock management for climate change adapatation | 6600 | Ongoing Activity
| Output 5.4 - Activity 5.4.2: Formation and training of diptank users and diptank attendants | 5600 | Ongoing Activity
| NIE Project Management Fees 8.5% NEMC | 33604
| NEE Project Execution Costs (9.5%) SUA | 37557
| TOTAL | 466501 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Conflict among users of water and forest resources | Low | Knowledge management regarding sensitization on water user rights in the community and climate change. Construction of livestock drinking troughes adjacent to the dam. Establishing efficient water delivery tanks and pipes for irrigation of vegetable gardens and nursery trees.
Political will at regional and district and village local government to accept and support project objectives | Low | Participatory engagement of stakeholder from the beginning of the project
Limited capacity and willingness to understand and implement project interventions | Low | Capacity building through knowledge management worksops to the community to engage themselves in the project activities.
Change price of materials for project implementatio | Low | Need for regular budget review and flexibility, plannig for reducing or meging or prioritizing of some activities
Delays in disbursement of funds | Medium | • Timely reporting and application of funds • Encourage site/field visits and engagement of executing entity for visibility of project implementation. Change from quarterly to biannual disbursement of funds in order to reduce this risk.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Failure of establishment of planted tree on degraded land due to poor rainfall | Rainfall in these semi arid areas are still erratic | (i) We agreed to start the new planting early on the on-set of rains to ensure quick establishment of seedling root systems and avoid death of seedlings (ii) We will conduct tailored trainings to communities on management and maintenance of newly planted trees in degeraded land, (iii) We will introduce prizes to farmers who will have at least 50% of the planted treessurvived after one year since planting. (iv) Set a replanting program each year to the end of the project to ensure succession of new tree establishment.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
With regards to the risk mitigation, the project team embarked on undertaking knowledge management which focused on capacity building and empowerement of community members. Above that putting people's participation at the centre has been pivotal towards risk mitigations, of which SWAHAT project is employing participatory approaches through its identification, planning for solutions/interventions, implementation, monitoring and evaluation of interventions. Therefore, all these project approaches have significantly contributed towards risk mitigations.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Invations and conflicts may lead to possible property, crop livestock losses and reduce livelihoods resilience | Component 1: Activity 1.1.1, and Activity 1.1.2 where safeguard measures included: (i) Capacity building on governance of Land ownership, water user rights and forest resources, Participatory governance and management of water user rights, forest resources and Implement water resources management at target village. | (i) Number of Capacity building done on awareness creation on land laws (ii) Number of conflicts and resolutions conducted | No conflicts were experienced this year | (i) Capacity building on governance of Land ownership, water rights and forest resources, Community meetings with district representatives, local leaders and villgers to discuss the land ownership system at local community level, diffrent laws and bylaws were revised, identified the legal boundaries of the land allocated for the dams (ii) Conducted workshop on Participatory governance and management of water user rights, forest resources and (iii) Capacity building was conducted with villagers on dam's water resources management at target villages. | Very few, slow learners are still relactant to accept total tree planting of the protected farmlands | Continue capacity building and discussion with their local leaders on land ownership and protection of natural resourcs on farmlands Continued surveillance and awareness creation on laws and by laws related to project implementation and adaptation to climate change - report on number of conflicts and resolutions conducted
2 - Access and equity |  |  | Unequal access to the use of water from the dam for livestock and farming. | • Ensuring high levels of transparency during project design and implementation • Capacity building of representatives of the disabled, the elderly, women, youth, community leaders and planners in consultative process • Participatory resource management • Assist communities set up mechanisms to ensure equal participation of and benefits for group | Additional focus groups discussions and household surveys will be organized during project implementation to assess effective equal participation and benefits of members | There was no water reservoirs/dams before project intervention. | Conducted a workshop on participatory water resource management • Assist communities to set up mechanisms to ensure equal participation of and benefits for group members, vulnerable households, men and women, youth and elders in the project | Additional focus groups discussions and household surveys will be organized during project implementation to assess effective equal participation and benefits of members | Further assessment of households for the effective equal participation and benefits of members
3 – Marginalized and vulnerable Groups |  |  | Lack of representation and participation and decision making of some community members in the project benefits | • Sensitization of the community on the project components and their rights to participate • Institutionalization of the project activities for continued execution | Additional focus groups discussions and household surveys will be organized during project implementation to assess effective equal participation and benefits of members | There was no marginalized social groups | Village local community meeting to describe the project benefits is for every member of the village and to empower project ownership by the village members. | Additional focus groups discussions has not observed any change to this risk for participation and equal benefits of members | Further focus froup discussions will be conducted to ensure equal participation and sharing of benefits.
4 – Human rights |  |  | Lack of representation and participation and decision making of some community members in the project benefits | • Sensitization of the community on the project components and their rights to participate • Institutionalization of the project activities for continued execution • The project will adhere to national and international human rights standards, policies, rules and regulation | Participatory group discussion and monitoring of the progress of project implementation - number of member composition, involvement and contribution to project interventions Regular surveillance and abiding to grievance management mechanism - Assessment on number of reported cases of human right violations - Child labour cases discrepancies in salaries salaries | No violation of human rights | During initiation of the project we raised awareness on human right issues that should be maintained | Based on the monitoring and evaluation of activities conducted, did not identify any risks on human rights, however we will keep on monitoring the potentail risk on human rights. | continue monitoring the risk during the coming year.
5 – Gender equality and women’s empowerment |  |  | Unequal participation of women and men in the project could lead to an exacerbation of existing gender inequalities in the community, in particular unequal access to income-generating activities | The project is committed to ensure 50% participation of women in most project components. In this respect, Project activities in all components have to be gender sensitive and to empower women. In addition, the project will implement the following mitigation measures: - All project staff will be trained on gender-sensitive approaches. - Incorporate gender sensitive approaches into trainings, workshops and awareness raising activities. - Mechanisms for selection of beneficiaries will be gender-sensitive in order to ensure equal participation of men and women taking into consideration different needs. - A socioeconomic and gender specialist will accompany communities in the development, implementation and monitoring of the plans developed through the participatory process. - Develop capacity building for women empowerment and continued monitoring and support of their involvement in the community | Conduct focus group discussions and household surveys during project implementation to assess effective equal participation of members Gender disaggregated and gender specific targets will be monitored indicators: - % of targeted community members - # house holds - # women and men participating in nursery, vegetable, aquaculture, cooking stoves and other project interventions | No risk at the beginning of the project | Awareness raising was conducted with respect to gender equity | The risks can still occur during subsequent project implementation | There is a need to continue monitoring the potential risk an a continue awareness raising among community members .
6 – Core labour rights |  |  | Missunderstanding between employee and employer Dismissal and termination of contracts -Workplace hazards | Human resource expert Project team | Implementation of grievance management mechanism in the cause of any difficulty event at work place | There ws no problems with labour rights at workplace | No labour grievance so far therefore no measures was needed | The risks can still occur during subsequent project implementation | Continue monitoring the risk during the coming year.
7 – Indigenous peoples |  |  | NA | NA | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | NA | NA | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  |  | Carry out risk assessment during implementation of the project Carry out selective clearance or removal of trees in the area designated for agricultural sites. Offsets through planting of trees in the degraded land sites is bigger than the cleared sites in each project community | Counting the number of surviving trees and other vegetation cover measuring size of the areas planted with trees | Some indigenous trees adapted to the area were present and these were selectively retained during the cleaning | Retentionof important species and planting of tree in the catchment ares | no impacts were identified | Continue counting the number of tree species in the area
10 – Conservation of biological diversity |  |  | As the project will introduce fruit trees and forest trees planting tendency of farmers to start neglecting indigenous species may lead to loss of biodiversity. Currently the demand for planting introduced fruits and forest tre species has been shown by some community members and groups such as schools and churches. | • Capacity building on importance of biodiversity to livelihoods and associated risks. • Interventions will emphasize on utilization of locally adapted species • Participatory development and implementation of conservation practices | • Project team and M&E specialist to monitor and oversee adaptation of introduced intervention and integration of native species. The indicators to include: • Vegetation index to determine enhanced ecosystem resilience to climate change | Theree were no intorduced species | We have intorduced non invasive fruit tree species in some sites such as lemon, passion and avocado | The anticipated risks persists during the project cycle | Continue awareness creation and monitoring of introduced tree species
11 – Climate change |  |  | NA | NA | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | Possible over use of water for irrigation of nurseries and vegetables, creating competiton for available water for fish and livestock, and possible spillage of fertilizers and spraying pesticides in crops may lead to pollution | • Compliance to environmental laws • Integrated soil fertility and pest management • Resource use efficiency by recycling waste water from aquaculture into model vegetable gardens • Water User Association will be set up at community level so as to be able to control sources of irrigation, quantity and volume of water use on irrigation. • Specialized irrigation officer to train farmers on efficient irrigation of gardens | • Project team to monitor and provide follow-up advise on water use for irrigation, animals and fish farming • Routine check on water sources during project implementation should be enforced by water use authorities | There was no pollution during the start of te project | Although there is no impact yet, formation of water user committee, Capacity building on efficient water utilization , Capacity building of sustainable fertility and pest management as stratgies among nursery and vegtable farming groups was done in order to minimize the risk for the impact to happen. | The potential of the risk to happen still exist. | Continue with awareness creation and monitoring
13 – Public health |  |  | Reduce human ability to work due to illness thus reducing labour force at household level, Cost in human treatment against illness | • Capacity building in public health related to water use in component 1 • Fish farming in the dams will feed on the larvae of possible parasites (eg. malaria, schitosomiasis) • Establishment of bore holes for increasing access of clean and safe drinking and domestic water • Establishment of bore holes for increasing access of clean and safe drinking and domestic water | • Continued monitoring of disease occurrence and other public health indicators related to water-borne diseases and infections • Focus group discussions with locals on public health issues • Household surveys and key informant interviews on the impact of trainings on public health Sampling of successful colonization of fish in the dams and ponds established Maintenance and repair of bore holes for clean water availability | No Public health concern during the project | Awareness creation on publich health was done to the target community | So far no publich health impact has been observed. | Continued monitoring of any project acticites and any risk leading to public health concerns.
14 – Physical and cultural heritage |  |  | No identified impacts | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | Fertilizer and pesticide use may have impact on soil polution Localised deforestation during establishment of vegetable gardens may lead to land degradation | • Capacity building to promote integrated soil conservation practices • Minimize soil disturbances by machines during dam construction • Forests and fruit tree planting • Reduction of use of fertilizers and pesticides will minimize pollution and associated components of semi arid landscapes such as rivers, and ponds | • Regular farmers and experts meetings for continued monitoring of implementation of land conservation measures to minimize land degradation and soil erosion in vegetable gardens and management of fish ponds gardens and management of fish ponds, Level of land degradation and soil erosion | Land was occupied by local shrubs grazed by livestock and used for local fuel wood harvesting | • Capacity building to promote integrated soil conservation practices • Minimize soil disturbances by machines during dam construction • Forests and fruit tree planting in some sites | Anticipated risks are expected to continue happening | There is a need to continue monitoring the potential risk an a continue awareness raising among community members on land and soil conservation.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Noy yet for the moment
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA untill it happens in the future.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | During the Implemtantation of the activites, ESP measures have been checked for compliance in all project interventions. The Implementing Entity with meetings with EE have agreed on social inclusion on enviromentantal safeguarding in implementation of the project activites
Have the implementation arrangements been effective during the reporting period? |  | YES
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The matter of ESP is discussed with the executing entity during planning of each project activity and compliance is observed accordingly.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | YES
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Grievance on ownership of the dam and sorrounding land was experienced in some communities of the project sites |  | The local government intervened by implementing exixting laws and by laws to resolve this grievenace
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | YES
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Improved households access to water supply | Objective (Component 1) | Number of households with improved access to water supply | Existing high level of water scarcity | 80% of women relieved from drudgery and time wasting in fetching water from long distances Atleast 30,000 females and 20,000 males having access to water supply | Good
Increased access to cooking energy sources | Objective (Component 2) | Number of females accessing fire wood from wood lot stock | Scarcity of energy affecting domestic supply of firewood | atleast 80% of women relieved from drudgery and time wasting in fetching firewoods | N/A
Improved households food and nutrition security | Objective (Component 3) | Number of households disaggregated by gender with improved food and nutrition security | Communities affected by food and nutrition insecurity |  | Satisfactory
Increased diversified sources of income generation activities in the community | Objective (Component 3) | Number of people adopted diversified sources of income generation activities by gender | Communities affected by low levels of income and limited diversified sources of income. | Atleast 720 of community members trained on, nursery techniques, tree planting, management and sustainable utilization of fruit and forest tree species. at least 80% being women with knowledge on establishment, propagation and management of fruits and forest tree species. | Good
Increased capacity of community to establish and manage fruit and forest tree nurseries | Objective (Component 2) | Number of people (disaggregated by gender) with increased capacity to establish and manage fruit and forest tree nurseries | Low capacity of communities to establish nurseries and plant and manage trees | at least 80% being women with knowledge on establishment, propagation and management of fruits and forest tree species. | Good
Model fish farming ponds establisment at each water harvesting dams | Objective (Component 3) | Number of women participating in each fish farming per village community | Local fish ponds aare available including farmers but neither organized nor improved in term of management | Six groups of model aquaculture farms established with gender disaggregated membership. At least 30% of households (of which at least 20% are of women) within target community are integrated in aquaculture. | N/A
Model vegetable farms establisment at each water harvesting dams | Objective (Component 3) | Number of women participating in vegetable gardening per village community | Local vegetable gardens are available including farmers but neither organized nor improved in term of management | Six groups of model vegetable farms with diversified vegetable crops established with gender disaggregated membership. At least 30% of households (of which at least 20% are of women) within target community are integrated in vegetable gardening. | Satisfactory
Increased number of community population including women farmers involved in IPM technologies for resilience to climate change | Objectives (Component 4 ad 5) | • Number of people trained on sustainable water management and water rights • Number of people trained and practicing livelihoods interventions (tree planting, vegetable, fish, livestock production and bee keeping • Number and types of Knowledge management documents produced and diffused to target project communities and beyond | None | At least 70% community population of which 50% are women farmers involved in the project adopted and implementing the IPM technologies for resilience to climate change | N/A
Raised level of target community involvement in integrated aquaculture, horticulture, livestock and apiculture management | Objective (component 3) | • Number of farmers in the target communities with built capacity and practicing profitable apiculture, fish farming, crop and livestock production (disaggregated by sex). | None | At least 30% of households (of which at least 20% are of women) within target community are integrated in aquaculture, horticulture, livestock and apiculture | Good
Increased number of women with knowledge on establishment, propagation and management of fruits and forest tree species | Objective (component 2 and 5) | Number of community members trained on, nursery techniques, tree planting, management and sustainable utilization of fruit and forest tree species | None | Increased number of people (i.e. least 30% being women) with knowledge on establishment, propagation and management of fruits and forest tree species | Good
Increased level of women practicing profitable apiculture, fish farming, crop and livestock production | Objective (component 3) | • Number of farmers in the target communities with built capacity and practicing profitable apiculture, fish farming, crop and livestock production (disaggregated by sex). | None | At least 30% of whom are women practicing profitable apiculture, fish farming, crop and livestock production | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IE has provided technical backstopping and guidance to EE to ensure the ability of women has been strengthened through involvement in Nursery establishment and management, gardening, and livestock keeping to act as agents of change.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | 1. the project should target to achieve at least 50% women beneficiaries in each intervention 2. the project has ensured solid participation and benefit on the part of youth, particularly girls. 3. gender-transformative approach has been mainstreamed in implementation of the SWAHAT project, 4. Mechanisms to manage potential risks to the promotion of gender equality and the empowerment of women as well are also identified
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievance related to gender was encounted
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1: Installation, rehabilitation and establishment of community water harvesting dams |  | Outcome 4 | 2 dams established for water harvesting in the project sites |  | 4 Water harvesting dams established | Highly Satisfactory (HS)
| Component 2: Develop and implement participatory afforestation program for locally adapted fruit and forest trees utilization |  | Outcome 5 | At least 20,000 locally adapted fruits and forest trees in 2 project sites established And at least 2 nurseries with multi purpose fruits and forest trees per village established |  | Planted 6000 planted tree seedlings despite poor survival rate due to drought. 2 Nurseries for fruits and forest trees established with a total of 27,000 assorted fruits and forest tree seedlings established | Satisfactory (S)
| Component 3: Develop integrated climate resilient livelihoods diversification for climate change |  | Outcome 6 | Two model vegetable gardens with diversified vegetable crops established |  | One model vegetable gardens with diversified vegetable crops established | Satisfactory (S)
| Component 4: Formulate and implement interventions for integrated management of emerging pests and diseases |  | Outcome 3 | None |  | none | N/A
| Component 5: Knowledge Management |  | Outcome 3 | (i) Six model vegetable gardens with diversified vegetable crops established (ii) Four livestock water drinking centers established with 5 drinking troughs per project site |  | 2 Vegetable gardems and 10 livestock drining troughs established in two project sites | Satisfactory (S)
|  |  | Outcome 3 | We targeted to deliver the following packages on knowledge management: (i) Awareness of climate change and adaptation strategies, (ii) Nursery establishment and management of forest and fruit trees seelings (iii) Selection of Adaptation of forest and fruit trees in semiarid regions, (iv) Vegetavle gardening and production |  | All five packages of knowledge management were imparted to farmers groups but printouts of manuals are not completed | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Fredrick Mulinda
| Email: | nieaf@nemc.or.tz / kasigazi.koku@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has delivered satisfactorily on its year one objectives with few excepts in some activities such as tree planting and timely commencement of activities in areas where acceptance was partly an issue. We recommend use of weather projection in chosing the time for implementation of weather sensitive activities such as excavation of dams and planting of trees, coupled with sufficient awareness to clear doubts among beneficiaries.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1: Installation, rehabilitation and establishment of community water harvesting dams |  | Outcome 4 | 2 dams established for water harvesting in the project sites |  | 4 Water harvesting dams established | Highly Satisfactory (HS)
| Component 2: Develop and implement participatory afforestation program for locally adapted fruit and forest trees utilization |  | Outcome 5 | At least 20,000 locally adapted fruits and forest trees in 2 project sites established And at least 2 nurseries with multi purpose fruits and forest trees per village established |  | Planted 6000 planted tree seedlings despite poor survival rate due to drought. 2 Nurseries for fruits and forest trees established with a total of 27,000 assorted fruits and forest tree seedlings established | Satisfactory (S)
| Component 3: Develop integrated climate resilient livelihoods diversification for climate change |  | Outcome 6 | Two model vegetable gardens with diversified vegetable crops established |  | One model vegetable gardens with diversified vegetable crops established | Satisfactory (S)
| Component 4: Formulate and implement interventions for integrated management of emerging pests and diseases |  | Outcome 3 | None |  | none | N/A
| Component 5: Knowledge Management |  | Outcome 3 | (i) Six model vegetable gardens with diversified vegetable crops established (ii) Four livestock water drinking centers established with 5 drinking troughs per project site |  | 2 Vegetable gardems and 10 livestock drining troughs established in two project sites | Satisfactory (S)
|  |  | Outcome 3 | We targeted to deliver the following packages on knowledge management: (i) Awareness of climate change and adaptation strategies, (ii) Nursery establishment and management of forest and fruit trees seelings (iii) Selection of Adaptation of forest and fruit trees in semiarid regions, (iv) Vegetavle gardening and production |  | All five packages of knowledge management were imparted to farmers groups but printouts of manuals are not completed | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Paul Mbogo Kusolwa
| Email: | kusolwap@gmail.com and kusolwa@sua.ac.tz
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Positive progress: 1. Dams have been established in 4 project sites, 2. Nurseries for fruits and forest trees have been established in two project sites, 3. Vegetable gardens established and maintained through irrigation from harvested water from the dam, 4. ten livestock drinking troughs established and 5. Knowlege management for awareness of climate change, nursery and vegetable procuction imparted among community members. Negative Progress: 1.Adverse climate change challenges (extremly Low annual rainfalls) leading to shortage of harvsted water such that failed to serve the whole year round/season in one project site. 2. Grievances of some community members towards receiving the concept of tree planitng in some selected agricultural lands for adapatation to climate change.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator |  | Baseline | Progress since inception | Target for Project End
Overall Objective: Enhancing resilience of rural community to climate change-induced challenges of drought, floods and high temperatures in semi-arid regions in Tanzania | Percentage of people with improved livelihoods and resilient to climate change | 0 | 5% | At least 30% increase in crop and livestock productivity at the end of the project At least 240 ha of land planted with adapted fruits/forest tree by the end of the project At least 50% of people adopt diversified sources of income generation activities i.e. at least 30,000 females and 20,000 males having access to water supply
| Number of households disaggregated by gender with improved food and nutrition security | 20% | 25%
| Number of people adopted diversified sources of income generation activities | 5000 | 10000
| Number of households having access to water supply | 5000 | 10000
Component 1: Installation, rehabilitation and establishment of community water harvesting dams | Number of sites where physical water dams has been constructed to deal with climate risk | 0 | 4 | Six (6) water harvesting dams constructed Improved governance on water use rights, management and distribution At least 6 bore holes for domestic water use established in needy villages 80% of women relieved from drudgery and time wasting in fetching water from long distances
| Number of constructed water supply channels | 0 | 6
Component 2: Develop and implement participatory afforestation program for locally adapted fruit and forest trees entailing nursery establishment, tree planting, management and sustainable harvesting and utilization | Number of community members trained on, nursery techniques, tree planting, management and sustainable utilization of fruit and forest tree species | 0 | 80 | At least 6 nurseries with multi purpose fruits and forest trees per village established At least 100,000 locally adapted fruits and forest trees planted in the projct areas. Increased number of people (i.e. least 30% being women) with knowledge on establishment, propagation and management of fruits and forest tree species. Sustainable use of fruits and forest tree products developed
| Number of nurseries established | 0 | 2
| Number of fruit and forest trees produced and planted on farmlands | 0 | 0
| Area size of catchment planted with forest trees. | 0 | 12ha
Component 3: Develop integrated climate resilient livelihoods diversification through improved technologies in apicultures, aquaculture, crop and livestock production | Number of farmers in the target communities with built capacity and practicing profitable apiculture, fish farming, crop and livestock production (disaggregated by sex). | 20 | 20 | At least 30% of whom are women practicing profitable apiculture, fish farming, crop and livestock production. Twelve model aquaculture farms each with at least 4 ponds established in the project districts Twelve model horticulture farms with diversified vegetable crops established 4 livestock water drinking centers established per project district 12 model apiary units established in the entire project area At least 30% of households (of which at least 20% are of women) within target community are integrated in aquaculture, horticulture, livestock and apiculture.
| Number of established model fish ponds and horticulture fields downstream of the water harvesting dams | 0 | 2
| Number and size of apiary units and livestock water points | 0 | 10
| Amount of honey and fish; and crop and livestock harvests yielded per household | 0 | 0
Project Component 4: Formulate and implement interventions for integrated management of emerging climate change related pests and diseases that affect fruit trees, fish, crops and livestock productivity | Number of major insect pests and vectors affecting crop and livestock production in target areas | 0 | 0 | At least one guideline for each insect pest/vector and disease produced and distributed to target farmers At least 70% community population of which 50% are women farmers involved in the project adopted and implementing the IPM technologies for resilience to climate change
| Number of crops diseases in the target areas | 0 | 0
| Developed IPM technologies for management of pests and diseases | 0% | 0%
Project Component 5: Knowledge Management | Number of people trained on sustainable water management and water rights | 0 | 100 | At least 70% community population of which 50% are women farmers involved in the project adopted and implementing the IPM technologies for resilience to climate change At least One compresnsive training manual/guideline/fliers generated and distributed to target community for each strategic interventions (fruits and trees, vegetables, fish, bee keeping, water use and safety, and climate change adaptation )
| Number of people trained and practicing livelihoods interventions (tree planting, vegetable, fish, livestock production and bee keeping | 0 | 0
| Number and types of Knowledge management documents produced and diffused to target project communities and beyond. | 0 | 0

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Low adoption by a few people who did not participate in the consultative and local inception meetings, Change of local govermment structure from village community lead to changes in management in some village communities, Climate variability low rainfall affected the establishment of newly planted tree seedling on catchment site. .
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delay of start of the project implementation with respect to onset of wet season affected the excavation of the dams (dams were dug in a rush to atleast complete before the on set of rains to avoid the stuck of equipment on the sites. The project was schedueld to start early June 2020, however it was launched in October 2021 due to negotiation of modalities of fund disburseennt between AF and the Government of URT.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Shifting of some activities between quarters e.g. excavating 2 instead of 1 dam and implementation of some knowledge management activities in quarter 1 which were planned in next years/quarters.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Women have proved to be very effective in engaging and delivering results in interventions. They only needed to be recognized, included, trained and given roles. More than 80% of the established tree nurseries workers are women.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | Water harvesting dams: Diversified income generation activities for adaptation to climate change such as tree nurseries, vegetable garnening, acquaculture, inacting drinking water troughs for livestock
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | National Enviroment Management Council
Type of implementing entity | NIE
Country | Tanzania
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 48730 | 35301 | 13429 | Total | 68137 | 35301 | 32836 | Total |  |  |  | Total
|  | % of female beneficiaries | 54.62% | 54.62% | 45.38% | % of female beneficiaries | 60% | 60% | 60% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 48.2% | 47.47% | 48% | % of Youth beneficiaries | 55% | 55% | 55% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 48730 | Drought | 2: Partially effective | Total | 68137 | Drought | 3: Moderately effective | Total |  |  |  | Total
|  | % of female targeted | 54.62% |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Water management | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 2 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 4 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 4 |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Water management | 2: Low capacity | Total | 40 | Water management | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 20 | 50% | Public |  | 40 | 50% | Public |  |  |  | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Water management | 2: Low capacity | Public | Regional | Water management | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 4 | Local | Water management | 2: Low capacity | 5 | Local | Water management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Water management |  | 20% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 48730 | 55% | 2: Partially not aware |  | 68137 | 60% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Local |  | 9 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 9 | Community |  | Water management | 48 | Community |  | Water management
|  | 7 | Community |  | Agriculture | 22 | Community |  | Agriculture
|  | 7 | Community |  | Food security | 16 | Community |  | Food security
|  | 15 | Community |  | Disaster risk reduction | 52 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Water management | land | 4: Effective |  | Water management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 2 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 4 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2 | ha rehabilitated | 2: Partially effective | Cultivated land/Agricultural land | 2 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 2400 | 12% | 2: Limited improvement |  | 5850 | 12% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 2400 | 12% | From 5% to 10% | Agriculture | 5850 | 12% | From 10% to 20% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 2400 | 12% | From 5% to 10% | Livestock production | 5850 | 12% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 2400 | 12% | From 1% to 5% | Aquaculture | 5850 | 12% | From 5% to 10% | Aquaculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 2400 | 12% | From 0.5 to 1% | Agribusiness | 5850 | 12% | From 5% to 10% | Agribusiness
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 4 | Adaptation strategies | Water management | Community-based adaptation | 52 | Adaptation strategies | Water management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 2400 | Agriculture |  | 100 | 11700 | Agriculture |  | 200
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 2400 | Livestock production |  | 200 | 11700 | Livestock production |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 2400 | Aquaculture |  | 10 | 11700 | Aquaculture |  | 50
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Water management | Community | Innovation replicated |  | Water management | Community | Innovation replicated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Water management | No innovative practices | 1: Ineffective | 9 | Water management | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 9 | Innovative practice |  | 3: Moderately effective